Department for International Development, Nigeria

State Partnership for Accountability, Responsiveness and Capability (SPARC)

Annual Review, 2014

February 2015
Abbreviations

AG	Accountant General
AIA	Agreed Intervention Approach
BC&CoA	Budget Classification and Chart of Accounts
BCC	Budget Call Circular
BoIR	Board of Internal Revenue
BPS	Budget Policy Statement
CDF	Comprehensive Development Framework
CGS	Conditional Grant Scheme
CoP	Community of Practice
CSOs	Civil Society Organisations
DCF	Donor Cooperation Framework
DFID	Department for International Development
EFU	Economic and Fiscal Update
EXCO	Executive Council
FAAC	Federal Account Allocation Committee
FSP	Fiscal Strategy Paper
G&SI	Gender and Social Inclusion
HoS	Head of Service
HRM	Human Resource Management
HRMIS	Human Resource Management Information System
IFMIS	Integrated Financial Management Information System
IGR	Internally Generated Revenue
IPSAS	International Public Sector Accounting Standards
KM	Knowledge Management
KPIs	Key Performance Indicators
M&E	Monitoring and Evaluation
MDAs	Ministries, Departments and Agencies
MDGs	Millennium Development Goals
MTSS	Medium Term Sector Strategy
NGF	Nigeria Governors’ Forum
OHoS	Office of the Head of Service
OSSAP	Office of the Senior Special Assistant to the President
PFM	Public Financial Management
PSM	Public Service Management
SAVI	State Accountability and Voice Initiative
SDP	State Development Plan
SPARC	State Partnership for Accountability, Responsiveness and Capability
SPRM	State Peer Review Mechanism
VFM	Value for Money

Annual Review - Summary Sheet

Title: State Partnership for Accountability, Responsiveness and Capability (SPARC)
Programme Value: £65,127,109		Review Date: November 2014
Programme Code: / PO 4052/CNTR 200708082	Start Date: / August 2008	End Date: / April 2016

Summary of Programme Performance
Year	2009	2010	2011	2012	2013	2014
Programme Score	A	A+	A+	A+	A+	A+
Risk Rating	High	High	High	High	High	High

Summary of progress and lessons learnt since last review

The programme continues to perform above expectation with its fifth year of scoring ‘A+ - moderately exceeded expectation’ with each of the four Outputs scoring ‘A - met expectation’ or above. The period through to the scheduled end of programme in April 2016 will contain significant challenges to maintaining this standard of performance, not least from the upcoming national elections in 2015, the increasing terrorist activity of Boko Haram and the major fall in the oil price with the consequent reduction in Federal funding to the states. Nonetheless, the programme has put in place robust measures to mitigate these risks and it is likely that the current performance standard will be sustained to the end of programme.

Key results during the year include:

- Lagos, Kaduna and Kano approved their first ever State Development Plans. Some 33 Medium Term Sector Strategies have been developed or rolled over in the year, and in Enugu, Jigawa and Kano these represent over 75% of government business.
- Improved budget preparation processes have been solidified in all states. Lagos and Kano actually announced 2014 budgets which were less than those of 2013. Yobe produced their 2013 accounts for audit within four weeks of the end of the year, and they (and preceding years) are publicly available.
- Working in collaboration with SAVI, SPARC has supported the development of civil society engagement in the budget process. As a result, the 2014 budget in Kano included spending priorities demanded by civil society; in Yobe civil society and the media engaged all MDAs on the budget discussions for 2014
- Zamfara produced its first ever Procurement Bill; Anambra is using a new Procurement Manual which has resulted in cost savings of nearly £20 million from 18 construction projects.
- Increasingly, corporate planning is being rolled out to a wider range of MDAs in an increasing number of states
- Gender and social inclusion issues are now being reflected in sector strategies and budgets in Enugu, Jigawa, Niger, Yobe and Zamfara

Output 1 - Policy and strategy development, monitoring and evaluation processes improved
State governments’ planning processes are getting better and the quality of the resulting Medium Term Sector Strategies (MTSS’s) is improving. Many of the plans are fully costed and 90% of states now have results frameworks against which annual performance is being reviewed. Further work needs to be done to try to embed the direct linkage between ceilings, allocations, spending and service improvements.

Output 2 - State public financial management processes improved
Budget processes and documentation continues to improve with most states adopting credible and realistic (that is, affordable) budget frameworks. As a result, at the aggregate level, the variation between actual spending and original budget is reducing. However, at the sector level, there continues to be a wide variance between the approved budgets and the actual budget releases due to the limited capacity for cash flow forecasting. Useful work is being carried to strengthen tax administrations, as part of the strategy to increase internally generated revenues from state level domestic taxes. As the fiscal situation deteriorates, with less funds flowing from the Federal Government, further efforts to upgrade tax administration and revenue collection performance will be beneficial.

Output 3 - State public service management processes improved
States are demonstrating considerable enthusiasm and effort in the area of HRM reform. Mandate mapping is being adopted by the ‘new’ states and corporate planning is being implemented, in various forms, across most of the 10 states. Performance management, mainly through the introduction of service charters, is gaining a hold. As expected, progress with establishment and workforce planning has proved more challenging in a number of states. Post the election period, these gains are likely to be most at risk as new administrations may be reluctant to address these sensitive issues so early in their administrations.

Output 4 - Federal support to state governance improved
Despite the disruption to the Nigeria Governors’ Forum in the lead up to the 2015 elections, its Secretariat continues to provide technical support in fostering good governance in all 36 states. The programme’s knowledge management processes and products are complementing the dissemination of lessons learned as well as distributing guidelines. Progress with implementing the State Peer Review Mechanism has slowed, in part due to the complexity of adopting the methodology. Planning for the alignment and coordination of SPARC’s and FEPAR’s activities around common areas of interest, during the next year or so, has just started.

Progress with implementing 2013 Annual Review recommendations
All of the recommendations have been addressed and are either fully adopted or continue to be work in progress for resolution during early 2015.

Summary of recommendations for the next year Programme wide
The programme team should complete the following tasks during 2015: (a) prepare a compendium of the main lessons learned for dissemination through its Resource Centre. This synthesis could be publicised through a regional ‘event’ post the 2015 elections to raise the awareness/stimulate continued interest in governance reform by the new administrations and (b) where major gaps remain in the evidence base for the ToC, commission additional analytical work in advance of the Programme Completion Review scheduled for early 2016.

A case study on SPARC’s impact on service delivery should be completed.

SPARC should complete an internal and informal assessment of the new state administrations’ commitment to two of the DFID Partnership Principles, namely the commitment to both PFM reform and strengthening domestic accountability. This ‘light touch’ analysis, prepared jointly with SAVI, could then feed into SPARC’s decisions on the priority areas for intervention during 2015 and early 2016. Updating the political economy analyses post elections would feed into this planning process. However, it needs to be recognised that new administrations might still be in the very early stages of settling in and much may remain unknown.

In responding to the major uncertainties around the results and consequences of the national elections, it is essential that DFID implements its leadership role as part of the re-engagement process. Also, SPARC may benefit from adopting a more flexible and responsive planning approach. For the 2015/16 work plan, budget and logframe revisions, consideration should be given to adopting a two phase approach given the considerable uncertainties that exist, especially around the priorities and commitments of the new administrations. Phase 1 would be an outline plan to guide the programme’s activities in the first 6 months. Phase 2 would comprise a review of the first 6 months’ results and a revised work plan, budget and logframe targets through to the end of the programme. These planning exercises would need to avoid becoming too onerous and avoid deflecting the programme’s attention away from ‘front line’ technical support to its state partners

For the remaining period of the programme, the current quarterly progress reporting by SPARC should be amended along the following lines:
- State level reporting of progress against activities in work plans should be six monthly
- The level of detail in, and therefore the length of, the six monthly reports should be reduced (by half if possible)
- A short (no more than say 30 pages) quarterly issues-based report should be prepared by SPARC. The report should set out an broad overview of progress towards the logframe, including in key components and in states. It should focus on issues arising from, such as, the election transition, the effectiveness of the risk management strategy (informed by the updated political economy analysis), the design and implementation of the agreed intervention approaches with each new administration and highlighting any areas where DFID’s greater engagement would be beneficial.

In relation to VfM:
  1. SPARC will need to maintain tight controls over fee costs over the remainder of the programme to avoid excessive reliance on short-term international consultants. A priority for the remainder of the programme will be to demonstrate a lower cost and more financially robust model of TA provision by continuing the positive trend in the increased use of national consultants and permanent staff
  2. SPARC should further experiment with alternative methods of knowledge transfer that make less intensive use of project staff and consultants, including greater use of peer learning and exchanges between MDAs and between state governments and more active dissemination of KM products.
  3. It is recommended that a more thorough statistical analysis should be conducted to verify the robustness of the current VfM indicators using econometric techniques including comparisons between states and over time (and including SPARC and non-SPARC states).

Output 1 Policy and strategy development, monitoring and evaluation processes improved
1. In terms of further developing the implementation of MTSS’s, the Review supports the adoption of the suggested approach to work with willing state governments to give special attention to establishing a working sequence starting with making an accurate ceiling (given policy guidelines and fiscal projections), and then proceeding with devising the MTSS, approving a budget, projecting cash flow and releasing cash.
2. Guidelines to provide a roadmap for establishing State Statistics Bureaus on a sustainable basis should be considered.

Output 2 State public financial management processes improved
1. SPARC should continue to contribute to tax administration reform, drawing on GEMS3 expertise and more generally DFID’s international experience in this area.
2. With the prospect of new administrations facing a financial crisis, SPARC should remain available to assist state governments, when and where a request is made, to examine options for budget reprioritisation, to update cash flow forecasts, to propose immediate revenue performance improvements and to update debt management and sustainability plans.
3. The existing good working relationship between SPARC and SAVI should be built on through closer collaborative planning, more joint working and sharing of costs, where possible.

Output 3: State civil service performance processes improved
Faced with the incoming new administrations, it will be important for SPARC to maintain its strong relations with change leaders, such as the Heads of Service (HoS), and continue to be responsive to assisting with specific HRM issues and not necessarily expect for comprehensive reform across a broad front. It will important to try and embed the gains made to date and to continue support to reform mandated organisations, such as the Bureau of Public Service Reform in Kaduna

Output 4: Federal support to state governance improved
There should be closer collaboration with FEPAR and SAVI to work jointly on areas of common interest with a view to delivering results in specific areas. DFID will need to take a proactive role in facilitating this closer working between the three programmes and provide ongoing progress monitoring.
A. Introduction and Context

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

Nigeria is a large and diverse Federation. New estimates reveal that approximately 60 million out of 170 million Nigerians live below the national poverty line, with a further 60 million people living not far above it. Poverty is worse in the North than the South. Nigeria’s poverty and underdevelopment are widely attributed to poor governance. Although limited public resources is an issue in Nigeria particularly in northern states, the ineffective use of resources is the biggest impediment to sustained improvement in public services, and ultimately in making progress towards achieving the country’s Millennium Development Goals. Unfortunately, however, state government is often ineffective. The situation in many states in Nigeria is characterised by low institutional capacities, including weak planning systems, poor budgeting and cash management, very poor human resource management, extensive corruption in procurement and very weak audit capacity. The states are also subject to limited oversight or accountability – by the Federal Government, State Houses of Assembly, civil society or the media.

Set up in 2008, the SPARC programme was designed to work with selected Nigerian state governments (initially Enugu, Jigawa, Kaduna, Kano and Lagos and then in 2012 extended to include Anambra, Katsina, Niger, Yobe and Zamfara) to tackle problems identified earlier by delivering improved (a) policies and strategies; (b) public financial management; (c) state civil service performance, and (d) Federal support to state governance. The programme is supporting the delivery of the results outlined in the DFID Nigeria Operational Plan 2011-2015, particularly scale-up plans for the North. There are strong links with other DFID programmes[1] and it is complementary to the activities undertaken by them.
[1] These programmes include: Partnership to Transform Health Systems (PATHS 2),Education Support Programme in Nigeria (ESSPIN), Growth and Employment in States (GEMS), Partnership for Reviving Routine Immunisation in Northern Nigeria – Maternal, New-born and Child Health for Reviving Routine Immunisation in Northern Nigeria (PRRINN/MNCH, Federal Public Administration Reform (FEPAR), States Voice and Accountability Initiative (SAVI)

The UK is providing total funding of up to £65.1m to SPARC. The programme was originally approved by Ministers in 2007 as a £45.9m programme to run until 2014; in late 2012, the Secretary of State for International Development approved the scaling up of SPARC to an additional 5 states and the extension to 2015 with an additional £14.5 million allocation. In 2014, the programme was extended to April 2016 to provide continuity beyond the Nigerian national elections in 2015, at an additional cost of £4.7 million.

The impact of the intervention is expected to be Nigeria’s own resources used efficiently and effectively to achieve the MDGs. The programme’s outcome is the efficiency and effectiveness of the 10 selected state governments’ use of public resources is enhanced. The programme has four outputs:

Output 1: Policy and strategy development, monitoring and evaluation processes improved.
Output 2: State public financial management processes improved.
Output 3: State civil service performance processes improved.
Output 4: Federal support to state governance improved.

The programme’s approach is based on the theory of change which assumes that technical advice (activities) leads to stronger government institutions (outputs) which can better use resources (outcome). With other DFID interventions (such as the sector programmes in education and health), this will improve public service delivery and livelihoods of the poor (impact). Better use of resources requires states to reduce leakage, increase budget predictability and implementation, while improving policy and planning, and civil service performance.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The programme’s Outcome is the efficiency and effectiveness of the 10 selected state governments’ use of public resources is enhanced. The assessment of progress towards Outcome is ‘A – meets expectation’. Table 1 below summarises Outcome milestone performance to November 2014 by Outcome indicator across the whole programme.

Table 1: Summary of Outcome Performance
Indicators	Score	Description

Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	B	Moderately did not meet expectation
Realism and predictability of multi-year capital and recurrent budgets.	A++	Substantially exceeded expectation
Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	A+	Moderately exceeded expectation
Responsiveness and success of State Governments to National initiatives to improve state performance.	B	Moderately did not meet expectation

It is likely that this assessment will hold through to the end of the programme in April 2016.

Overall output score and description

The overall Output score is A+.

Table 2: Summary of Scoring by Output together
Output	Score	Description	Weighting
1. Policy and strategy development, monitoring and evaluation processes improved	A++	Substantially exceeded expectation	25%
2. State public financial management processes improved	A+	Moderately exceeded expectation	40%
3. State public service management processes improved	A++	Substantially exceeded expectation	25%
4. Federal support to state governance improved	A	Met expectation	10%

Key lessons
Lessons learned
Programme wide
1. Enabling real institutional change is difficult, takes time and is more successful when underpinned by an organisational home for reform and appropriate legislation. Likewise, sustainable governance reform is promoted by locally owned, strong, agreed, routine processes embedded in organisational structures which have appropriate staffing and resources, backed by legislation and political commitment;
2. There may be a greater opportunity to secure political will for institutional change through supporting governance reforms in sectors where there is political interest or where there is an active and resilient government/private sector/civil society intersect – dependence on health and education (DFID priorities) can be confining, and support for sectors should be specific to the local context
3. Platforms for partnership strengthening and programme collaboration are required, and could be usefully promoted by DFID, to draw relationships and programmes together – examples to build on include the Kaduna Development Cooperation Framework; Lagos State Development Plan (SDP); Jigawa Comprehensive Development Framework; Enugu Medium Term Implementation Plan; Anambra SDP.

Output 1: Policy and strategy development, monitoring and evaluation processes improved
1. The quality of MTSS’s is improving in terms of meeting content standards, being costed and, more importantly, containing policies that are increasingly evidence-based. Also baseline data is now available in several states for their priority sectors, thus enabling the articulation of sufficiently comprehensive results frameworks against which states are able to monitor and report on implementation performance.
2. Despite these improvements in the MTSS’s further effort is needed. While there is some evidence that inter-relationship and read-over between the policy framework (SDP), medium term strategy (MTSS) and resource allocation (budgets) is strengthening, there remain reservations on the effectiveness of MTSSs in guiding the allocation of essential resources.
Output 2: State public financial management processes improved
The community of practice model is proving a successful mechanism for facilitating reform.
Output 3: State civil service performance processes improved
1. The investment and development of the Human Resources Management Resource Suite and the effort to raise the awareness of Heads of Service and other senior officers about modern HRM practice has yielded significant benefits in influencing Heads of Service to prioritise modernisation of HRM policies and processes.
2. With hindsight, the original intention to undertake state-wide workforce audits, as a platform for assessing potential cost savings which states could derive from rationalising the workforce, were overambitious.
Output 4: Federal support to state governance improved
Experience so far in the roll out of the SPRM has shown that there is a need to make the process more attractive to states. A review of the process is planned in this work plan year to specifically look at how to shorten the process without compromising the quality as well as pruning down the framework of indicators to make them manageable and more implementable in States.

Please note that the output scores below measure progress against the milestones that are presented in a generic way as each type of milestone indicator vary indicator vary significantly between states and for brevity are not shown.

Changed assumptions and considerations for any future redesign
Original assumptions hold true; however the evidence base for the ToC, for those assumptions from Output to Outcome and from Outcome to Impact, remain largely untested. Further work by SPARC during 2015 will seek to document evidence more comprehensively and, where possible, test assumptions. Two features to consider in the design of the new governance programme post April 2016: (1) introduce some form of ‘incentive’ to attract, and then retain, the engagement of state governments and (2) enable the new programme to engage directly on governance issues in any of the social and economic sectors which are priorities for the state governments.

Sharing lessons learned
The programme team will complete the following tasks during 2015: (a) prepare a compendium of the main lessons learned for dissemination through its Resource Centre. This synthesis could be publicised through a regional ‘event’ post the 2015 elections to raise the awareness/stimulate continued interest in governance reform by the new administrations and (b) commission additional analytical work to build the evidence base for the key assumptions in the ToC.

Key actions
Action/recommendation	Resp’ibility	Timing
Prepare a compendium of the main lessons learned including those lessons learnt in the 2015 Resource Centre	SPARC	Jan-Feb 2015
Commission additional analytical work to substantiate ToC; / to include a case study on service delivery impact	SPARC / DFID with SPARC/IMEP	Apr-Nov 2015 / No later end Dec 2015
Complete an internal and informal assessment of the new state administrations’ commitment to DFID’s third and fourth Partnership Principles	SPARC with SAVI	Apr-Jun 2015
Strengthen the MTSS process by trialling a process with selected state governments to strengthen the linkages between making an accurate ceiling (given policy guidelines and fiscal projections) devising the MTSS, approving a budget and projecting and releasing cash	SPARC	Feb-Apr 2015
Provide a roadmap for establishing State Statistics Bureaus	SPARC	No later end Aug 2015
Continue to support tax administration reform	SPARC	No later end Aug 2015
Assist state governments in responding to the likely fiscal crisis	SPARC	Apr ongoing to end of programme
Build on collaborative, joint working with SAVI	SPARC/SAVI	Jan-Feb and ongoing
Help embed HRM reforms through continued support to HoS and reform mandated organisations	SPARC	Apr ongoing to end of programme
SPARC, SAVI and FEPAR to identify opportunities to work jointly on common areas of interest	DFID with SPARC, SAVI, and FEPAR	Areas of interest agreed by no later than Apr 2015 with ongoing implementation to end of programme
VfM measures: / Maintain tight control over fee costs; demonstrate lower cost model of TA provision, including methods of knowledge transfer (such as peer review and exchange) / Conduct statistical analysis of the current VfM indicators to verify their robustness using econometric techniques including comparisons between states (over time and between SPARC and non SPARC states)	SPARC / DFID through SPARC/IMEP	Ongoing / No later end Dec 2015
Current quarterly progress reporting by SPARC should be extended to six months and made shorter. A quarterly issues based report should be introduced	SPARC to propose an outline format for the quarterly and six monthly reports and DFID to agree	Agreed by end Feb 2015
Consideration should be given to adopting a two phase planning approach for the programme’s activities in 2015/16	SPARC to decide on it planning approach in consultation with DFID	Agreed by end Feb 2015
DFID’s leadership role in driving through the post election re-engagement strategy with the new administrations has to be effective	DFID	Ongoing

Has the logframe been updated since the last review?
Yes, the key changes made are summarised as follows:
1. In response to recommendations within the 2013 Annual Review Report and 2013 ARIES Report, the following adjustments have been made to the logframe: a) reducing the weighting of Output 4 from 20% to 10% and increasing the weightings of Outputs 1 and 3 from 20% to 25%, b) adjusting Output 1-3 statements to better reflect the emphasis on systems and processes, and c) changing the delivery date of targets from end 2015 to end 2014 given that SPARC was, at the time, scheduled to end in mid-2015.
2. Adjustments to 2014 state level milestones in order to: a) better align milestones with data availability
(e.g. changing references from 2014 budget variance to 2013), b) improve the clarity of milestones, and c) reflect changing state government priorities (e.g. in terms of sectors or MDAs being supported).

## C: DETAILED OUTPUT SCORING

Output title	Policy and strategy development, monitoring and evaluation processes improved
Output number per LF		1	Output score	A++
Risk		High	Impact weighting (%)	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones[2]	Progress[3]			Score[4]
		% of states where ‘fully/largely achieved’	% of states where ‘partially achieved’	% of states where ‘not achieved’[5]
1.1 Extent to which policy and strategy making processes meet good practice standards.	State Development prepared in line with good practice standards	80	20	0	A++
1.2 Quality and comprehensiveness of policies and strategies.	The 2015-2017 MTSS’s are consistent with Strategy content standards	56	33	11	A
1.3 Extent to which results frameworks are comprehensive and measured.	The 2015-2017 MTSS’s contain a comprehensive Results Framework with KPIs (including G&SI disaggregation)	60	0	40	A+
1.4 Extent to which performance management processes are being used	Annual reviews of sector performance completed in line with good practice standards	75	25	0	A++
1.5 Extent to which political commitment to governance reform is evident.	State governments continue to make scheduled progress with their reform agendas	70	10	20	A++
[2] These milestones are generic and are presented as illustrations of the type of milestones being used since the 2014 milestones for each indicator vary significantly between states and for brevity are not shown. The actual progress listed is a summary synthesis of progress reported against state logframes. For a detailed description of progress against state level logframes, including state specific milestones, see the Progress Against 2014 Logframe Milestones report held by SPARC
[3] Progress is reported against actual achievement against the milestones specified in each state logframe
[4] Scoring of each milestone is based on the % of states where progress is assessed as ‘fully/largely achieved’ using the following scale where 0% ≤ C < 40% ≤ B < 50% ≤ A < 60% ≤ A+ < 70% ≤ A++ ≤ 100%
[5] ‘Not achieved’ includes (a) no evident progress or (b) too early to measure

Key Points
1. There is evidence that recent state development plans and policy definition have better met expected process and content standards and contain policies that are increasingly evidence-based with requisite good practice being implemented in Anambra, Enugu, Jigawa, Kano, Lagos, Yobe and Zamfara.
2. An increasing number of MTSSs are being prepared throughout the SPARC states that adequately conform to content standards and are comprehensively costed.
3. There is also increasing capacity of the central planning agencies to provide guidance and supervision to MDAs both on policy formulation and strategic planning.

Summary of responses to issues raised in previous annual reviews

Issue 1: Improved monitoring and evaluation of MTSS implementation.
Response: completed, Monitoring & Evaluation Guidance Note issued

Issue 2: Re-assess the impact weighting for this Output
Response: completed, weighting increased from 20% to 25%

Recommendations

1.	MTSS’s are gradually becoming part of the routine of the planning and budgeting processes across all 10 states. Whilst SPARC’s early emphasis, rightly, has been on process and content, there are now some states where SPARC’s role should be to help strengthen the ‘read across’ between MTSS expenditure ceilings, budget allocations and actual spending. The Case Study on the 2014 MTSS Review sets out (at page 79) a sensible ‘package’ of support and this approach should be adopted where there are willing and cooperative state governments, as best as possible within an uncertain planning and fiscal environment during 2015. Specifically, the Review supports the adoption of the suggested approach to “ring fence a specific sector, so that special attention is focused on establishing a working sequence between making an accurate ceiling (given policy guidelines and fiscal projections) devising the MTSS, approving a budget and projecting and releasing cash.” It is important that, at least on a sample basis for illustrative purposes, the adoption of MTSS’s are capable of making visible differences to service delivery with a clear ‘line of sight’ from policies, through operational plans and budgets to the management of services ‘on the ground’.
2.	SPARC has supported several states with the initial setting up of their State Statistical Bureaus. Some guidelines to provide a roadmap for establishing these offices on a sustainable basis should be considered and, if provided, would be a cost effective intervention.

Output title	State public financial management processes improved
Output number per LF		2	Output score	A+
Risk		High	Impact weighting (%)	40
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress			Score
		% of states where ‘fully / largely achieved’	% of states where ‘partially achieved’	% of states where ‘not achieved’
2.1 Extent to which the budget is credible and policy based.	Budget process informed by (a) Economic Policy Update (b) Fiscal Strategy Paper and (c) Budget Policy Statement with budget ceilings better aligned to MTSS’s	60	30	10	A+
2.2 Extent to which the budget is comprehensive and transparent.	Annual budget documentation better meets PEFA standards such as Budget Calendar and Budget Call Circular	22	33	45	C
2.3 Level of predictability and / control in budget execution.	More realistic forecasts of internally generated revenues using revenue/cash forecasting model	78	0	22	A++
2.4 Quality of accounting, / recording and reporting.	Improved accounting and budget performance reports produced in compliance with IPSAS and FAAC standards	25	63	12	C
2.5 Extent and quality of external scrutiny and audit.	State Auditor General Offices completing more effective annual audits	83	17	0	A++

Key Points
1. Progress continues to be made in all states through the provision of support to strengthen budget processes and in particular the development of budget process documentation and the introduction of more realistic budget frameworks (Indicator 2.1). Improved budget documentation is now produced in all states and includes Economic and Fiscal Updates, Fiscal Strategy Papers, and Budget Policy Statements.
2. Overall, states appear to be recognising the importance of adopting and presenting more realistic aggregate and sector budget allocations based on the fiscal forecasting model,. Support to update economic and fiscal performance analysis and establish macro fiscal frameworks have guided the development of more credible budgets, whilst the preparation of budget policy statements including sector allocations has supported improved annual and sector budgeting. However, the translation of sector allocations into the annual budget process has been not been fully embraced across all states.
3. At the sector level, there continues to be a wide variance between the approved budgets and the actual budget releases. Cash flow forecasting is insufficiently developed, despite the programme’s intervention, to enable state governments to prepare and update cash flow forecasts regularly. This undermines their ability to provide timely and reliable information on the availability and release of funds to spending units.
4. On the demand side, work has continued in conjunction with SAVI to sensitise CSOs, State Houses of Assembly and the media in areas such as budget tracking and monitoring states including Katsina, Yobe and Kano.
5. Strategies to support improvements in internally generated revenue (indicator 2.3) have been prepared and agreed in several states, and states are now being supported to implement these strategies. In particular Niger and Anambra have made progress in progressing IGR strategies.
6. There are early signs of an imminent financial crisis facing state governments. In addition to the high spending (largely unbudgeted) in the run up to the elections, the major drop in oil prices is reducing the size of the Federal allocations.

Summary of responses to issues raised in previous annual reviews

Issue 1: Sustainability of the PFM database
Response: For now, the World Bank is providing a temporary ‘home’ for the extended PFM database. However, despite the World Bank’s efforts to attract the interest of the Nigeria Central Bank to take on the permanent responsibility, the future ongoing management of the database remains uncertain. DFID and SPARC will aim to facilitate finding a solution.

Issue 2: Absence of best practice standards for implementing new compter based systems for financial and human resources management.
Response: The development of generic guidelines relating to Integrated Financial Management Information Systems (IFMIS), Human Resource Mangement Information System (HRMIS) and Tax Administration systems is expected to be completed in early 2015.
Issue 3: Rewording of the Output statement.
Response: Completed, revised wording included in updated logframe.

Issue 4: Re-assess the impact weighting for this Output.
Response: Completed, with decision to retain the 40% weighting.

Recommendations

1.	With the rapidly increasing importance of internally generated revenues, and the demands for more effective functioning of the State Boards of Internal Revenue, SPARC should continue to support tax administration reform, drawing on GEMS3 expertise and DFID’s international experience in this area.
2.	The prospect of a fiscal crisis, resulting from the costs of the elections and the reduction in oil prices, may necessitate urgent and drastic actions by the newly appointed Governors to ‘balance the books’. SPARC should remain available to assist state governments, when and where a request is made, to examine budget reprioritisation, to update cash flow forecasts, to propose immediate revenue performance improvements and to update debt management and sustainability plans.
3.	The existing good working relationship between SPARC and SAVI should be built on through closer collaborative planning, more joint working and sharing of costs, where possible.

Output title	State public service management processes improved
Output number per LF		3	Output score	A++
Risk		High	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress			Score
		% of states where ‘fully / largely achieved’	% of states where ‘partially achieved’	% of states where ‘not achieved’
3.1 Clarity and appropriateness of public service organisation and operational management	Mandates reviewed and organisational restructuring commenced, informed by corporate plans	100	0	0	A++
3.2 Extent to which HRM policies and organisation are in place.	HRM policies revised and HRM improvement plans being implemented	80	10	10	A++
3.3 Extent to which establishment planning and workforce planning, management and development is in place.	Establishment and workforce plans being developed	33	22	45	C
3.4 Extent to which MDA performance management / policies and procedures are in place.	Service Charters being introduced with annual reviews	71	0	29	A++

Key Points

1. Performance in the difficult area of PSM output milestones has been better than expected, especially in the light of the already documented substantial political and institutional constraints to reform in these areas. States are demonstrating considerable enthusiasm and effort in the area of HRM reform. Despite the expectation that extensive vested interests and civil servants’ resistance would only permit limited human resources management reform, considerable progress has been achieved ‘across the board’. In most cases, Heads of Service are now keen to modernise HRM policies, and develop plans to improve HRM processes. It appears that this was facilitated by engaging Heads of Service directly in the launch of the Human Resources Management Resource Suite in 2013. Nevertheless, as elections approach the expectation is that even committed Heads of Service will find it increasingly difficult to get sensitive HRM reform policies and plans approved at ExCo level.
2. The enthusiasm with which the original SPARC states engaged with the process of mandate mapping and rationalisation in earlier years is matched by the new states. Anambra and Katsina have made excellent progress, having already submitted mandate mapping results for approval at Head of Service level. Yobe is also well on the way, and is in the process of developing and agreeing a process for rationalisation of mandates. Among the original states, Lagos is preparing to revise and update its mandate compendium.
3. All states have focused on various approaches to corporate planning. In line with the revised guidelines introduced in 2012/13, more diversity is now apparent in the approaches, including reorganisation plans (Kano and Yobe), corporate improvement plans (Katsina and Zamfara) as well as the more highly structured corporate plan approach in other states.
4. As expected, progress with establishment and workforce planning (Indicator 3.3) has proved more challenging in a number of states.
5. Seven states are working directly on performance management. The majority have approached performance management through the adoption of service charters.

Summary of responses to issues raised in previous annual reviews (where relevant)

Issue 1: Commitment to HRM reform.
Response: A responsive approach has been adopted to work with State Governments’ interests and priorities, supporting those areas where progress is possible.

Issue 2: Rewording of the Output statement.
Response: Completed, revised wording included in updated logframe.

Recommendations

Post-elections, of the three Outputs, it is likely that progressing PSM reforms will be most at risk, especially where new administrations might be struggling to respond to severe financial constraints. It will be important for SPARC to maintain its strong relations with change leaders, such as the Heads of Service, and continue to be responsive to assisting with specific HRM issues and not necessarily expect for comprehensive reform across a broad front. It will important to try and embed the gains made to date through, in part, concentrating support on those reform mandated organisations, such as Kaduna’s Bureau of Public Service Reform which are likely to survive electoral transition.

Output title	Federal support to state governance improved
Output number per LF		4	Output score	A
Risk		Medium	Impact weighting (%)	10
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress	Score
4.1 Effectiveness of National mechanisms for improving state / governance.	(a) At least 3 out of 6 states have been supported to begin implementation of their SPoAs, (b) strategic options for transition of the MDG-CGS scheme post 2015 has been prepared, and (c) the NGFS has been supported to implement at least 50% of 1st year objectives in its Strategic Plan	Anamabra, Ekiti and Niger states are in the process of implementing their SPoAs. / A concept note for a Strategic Options Paper has been produced and approved by the CGS and a desk review of relevant materials has commenced. / 55% of 1st year NGF Strategic Plan objectives have been implemented	B
4.2 State governments have a mechanism for accessing and sharing lessons through appropriate Federal organisations	10 state governments are sharing SPARC lessons with other states	All 10 SPARC supported state governments are sharing lessons with other states (Abia, Imo, Ekiti, Osun, Ondo, Ogun, Oyo, Taraba and Delta) through Northern, South East and South West share fairs and the SPARC ASK help desk	A+

Key Points

1.Although the NGF by its very nature remains political, the NGF Secretariat has continued to embark on technical activities amidst all the politics. So far, the Secretariat has implemented more than 50% of the first year objectives of its Strategic Plan despite challenges faced at the NGF demonstrating the resilience of the organisation in its commitment to fostering good governance in all 36 states.

2.Lesson learning continues to play a huge part in the way SPARC works. Based on lessons earlier collated and disseminated, other non-SPARC states are beginning to show interest in SPARC results by demanding for SPARC support in achieving similar results in their own states. Opportunities for joint working with FEPAR on areas of common interest are starting to be identified.

Summary of responses to issues raised in previous annual reviews

Issue 1: Continued cautious and ‘wait and see’ approach to supporting the NGF.
Response: Agreed and reflected in 2014/15 work plans and budget allocation.

Issue 2: Defer support to Federal regulatory bodies.
Response: Agreed.
Issue 3: Reduce Output weighting and amend risk assessment.
Response: Actioned, as part of the revised logframe.

Recommendations

Further explore opportunities for closer collaboration with FEPAR on areas of common interest.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

As a technical assistance programme, SPARC’s main cost drivers are fees payable for long-term and short-term international and national consultants, as well as salaries for permanent staff. The proportion of SPARC’s total expenditure spent on fees and salaries amounted to 63% in the financial year 2013/14 (short term TA 32%, long term TA 23%, salaries 8%). SPARC has taken steps to achieve greater value for money associated with costs of providing consultants. Average fee rates fell by 18% over the period FY2009/10 to FY2012/13. However, they have since increased to a level 6% below the 2009-2010 baseline. SPARC estimates that these cost controls have resulted in a cumulative saving of £1,840,994 over the course of the programme.[6]
[6] The GEMS3 annual review in 2013 provided comparative data on average daily fee costs for all State Level Programmes indicating that SPARC’s costs were higher than the other programmes. The comparison has not been updated for 2014. However, indications from the early part of FY 2014-2015 suggest an increase in average fees paid by SPARC.

SPARC has achieved major cost savings on fees by increasing the use of national consultants in relation to the use of international consultants. Across the programme the proportion of consultancy days provided by national consultants rose from 44% in 2009/10 to 61% in 2013/14. SPARC has also been able to reduce its use of short-term consultants by hiring long-term Nigerian staff to undertake much of the technical work at state level. SPARC estimates that this shift has resulted in cumulative efficiency savings of £3,276,116 over the course of the programme.

Over the first four months of financial year 2014/2015 (July 2014 - October 2014) there appears to have been a departure from the trends noted above. The ratio of international consultant days to national consultant days has fallen to 1.0. Over the same period the fee element of the activity budget has increased from 57% to 67%. The average daily fee paid to consultants (all categories) has risen from £450 to £504. SPARC considers that these figures are mainly the result of the increased use of short-term international consultants at central level for the purpose of conducting lesson learning and evaluative case studies, knowledge management and quality assurance work. This has been an exceptional activity justified by the need for evidence gathering and lesson learning as the programme nears completion. Over the course of the year SPARC considers that the above ratios will move towards previous levels, but will remain somewhat off-trend.

In view of this development SPARC will need to maintain tight controls over fee costs over the remainder of the programme to avoid excessive reliance on short-term international consultants. A priority for the remainder of the programme will be to demonstrate a lower cost and more financially sustainable model of TA provision by continuing the positive trend in the increased use of national consultants and permanent staff. SPARC should also further experiment with alternative methods of knowledge transfer that make less intensive use of project staff and consultants, including greater use of peer learning and exchanges between MDAs and between state governments and more active dissemination of KM products.

Increased security threats have also been an important cost driver. SPARC reports that additional expenditure on security over the past three years has amounted to £460,000. This has mainly been for enhancing the security of SPARC offices, arranging for mobile police escorts, and recruiting full time security personnel.

SPARC also reports increasing expenditure on programme initiatives, in particular workshops. This reflects the intensive consultation process associated with the expansion into new states and the 2011/12 State Evaluation and Assessment Tool (SEAT)/Public Expenditure and Financial Accountability (PEFA) exercises. The security situation in the north of Nigeria has resulted in more workshops being held out of state in safer locations, which has resulted in additional costs.

VFM performance compared to the original VFM proposition in the business case

In response to the DFID Nigeria policy on VFM assessment, and in recognition of the importance of better integrating VFM assessment into programme decision-making, SPARC has prepared a 2014 VFM Working Paper, building on those prepared in 2011, 2012 and 2013. The following analysis is derived from the 2014 VFM Working Paper:

Economy

SPARC’s VFM report documents cumulative cost savings (at economy level) over the course of the programme amounting to £2,698,489 in total, of which £831,044 was made over the period 2013/14. These savings have been generated from fee rate reductions reported above (£1,840,994) and a variety of economies in the use of conference facilities, hotels and transport, as well as cost sharing with other projects (£857,495)

Efficiency

SPARC’s VFM report states that the programme has delivered efficiency savings from the following sources:
- Encouraging state governments to finance activities that would otherwise have been funded by SPARC. Examples include state governments funding the development or upgrading of IFMIS in Enugu and Jigawa, state government officials acting as lead trainers and facilitators in Niger, and Kaduna state government contributions to the review and refresh of the Development Cooperation Framework in Kaduna. These examples represent a cost saving for SPARC (estimated at £2,117,926 over the course of the programme) and an indication of government commitment, which should enable better results and sustainability.
- Minimising increases in administrative expenditure. Despite expanding into five additional states, SPARC has reduced the share of its total budget spent on programme administration from 15% in 2010-11 to 13% for 2011/12 and onwards. This represents a cumulative saving of £463,462.
- As a result of its drive to improve efficiency, SPARC has been able make savings since the start of the programme amounting to £5,857,504 in total, of which £1,896,321 was made over 2013/14.
- Increasing use of permanent national staff as an alternative to short term consultants. As discussed above this has resulted in cumulative savings of £3,276,116 over the course of the programme.

Taken together, these efficiency savings amount to £5,857,504 over the course of the programme and £1,896,321 during 2013/14.

Another important source of VFM efficiency has been SPARC’s practice of actively reallocating resources between states and between outputs according to assessment of where results are most likely. SPARC has adapted its methodology over the years to guide this allocation. In 2012/13 SPARC introduced the three level categorisation of states as part of its Consolidation and Expansion Strategy (CES) and adjusted state level financial ceiling accordingly. In 2014/15 The method for allocating funds was adjusted to include the CES weightings, a measure of reform traction and a VFM measure of state level results against spending presented in the 2013 Annual Review. These measures have tended to result in greater differentiation over time in spending levels between states and outputs. For example there has been a significant reduction in state allocation for Kano (from a 7.8% to 5.4% share) between 2013/2014 and 2014/2015 following concerns raised in the 2013 Annual Review about the reform commitment of the state and the state government’s ability to make productive use of SPARC’s assistance.

Effectiveness

SPARC measures its outcomes in terms observed changes in key PFM variables and public management processes. VFM effectiveness measures by comparing changes in these indicators to SPARC expenditure. Headline results include:
- Budget realism. SPARC reports that the states where it works have made progress towards more realistic budgets. Around £928 million has been cut from state budgets cumulatively over the course of the programme. These are resources that would not have been available and would never have been spent. The benefit of removing them from the budget has been to enable better budget execution and a higher level of releases. Comparing budget reductions to SPARC expenditure (PFM activity budget only) yields a VFM effectiveness ratio of 85. In other words £1 of SPARC expenditure is associated with £85 in cuts to unaffordable budgets.
- Improved budget execution. As a result of greater budget realism and other PFM improvements states supported by SPARC have been able to increase their budget execution rates from 68% at baseline to 83% in 2012/13. This has enabled additional expenditure of around £1.2 billion over the course of the programme. Comparing this additional expenditure to resources provided by SPARC (PFM activity budget only) yields a VFM effectiveness ratio of 111. In other words £1 of SPARC expenditure is associated with increased state level expenditure of £111.
- Increase expenditure on social sectors. SPARC reports corresponding increases in the budget execution rate for the health and education sectors resulting in increased expenditure of around £324 million over the course of the programme. This translates to a VFM efficiency ratio of 8 (considering total SPARC expenditure). In other words £1 of SPARC expenditure is associated with increased state level expenditure on health and education of £8.
- SPARC’s VFM report also includes other VFM effectiveness ratios including the average cost of a standard MTSS improvement, and the average cost of a corporate planning stage.
- All of the VFM effectiveness measures presented in the SPARC VFM report show improvements over time, but substantial variations between states.
Assessment of whether the programme continues to represent value for money

The evidence presented on VFM economy and efficiency suggests that SPARC has been able to deliver increasing value for money at these levels. However, it must be recognised that SPARC’s consultant intensive model of TA delivery is relatively high cost. SPARC has been correct to adapt its working methods to make greater use of national staff working permanently at state level, and should be encouraged to move further in this direction. In addition, greater use should be made of lower cost methods of knowledge transfer (such as peer review and exchange, if it is shown to be a cheaper modality). It would be very useful for the purposes of the successor programme for SPARC to use its remaining time to experiment further with alternative TA models and collect data and case study evidence on relative costs and benefits.

The VFM effectiveness measures suggest that SPARC may be delivering very good value for money fully in line with DFID’s strategic vision of using limited UK resources to lever more effective use of Nigeria’s own resources. However, the VFM measures will need further development and testing to provide more solid evidence. There are three main sources of doubt about the robustness of the presented indicators.
- The headline VFM figures are based on averages that obscure very large variations in VFM effectiveness between states and between years. There will therefore be a large margin of error around the presented ratios.
- There has been no attempt to compare changes in outcomes between states and between years and to relate these to different levels of SPARC spending using econometric techniques.
- There is no comparison of changes in states supported by SPARC and changes in states not receiving SPARC support. Such counterfactual evidence would be essential to begin to make claims about causality.
The initial assessment of VFM effectiveness suggests very encouraging results and excellent value for money. If confirmed, this will have important implications for other public sector reform programmes and the SPARC successor programme. However, in their present form the indicators are not sufficiently robust. It is therefore recommended that SPARC should conduct a more thorough statistical analysis using robust econometric techniques including comparisons between states and over time (and including SPARC and non-SPARC states).

Quality of financial management

SPARC continues to demonstrate a high quality of financial management. In particular: a) it is estimated that future costs will be in line with the current approved budget and forecasting profile, b) narrative and financial reporting requirements have been adhered to, and c) auditing requirements have been met based on last audit report to March 2012.

Date of last narrative financial report[7]	October 2014 for quarter ended 30 Sept 2014
Date of last audited annual statement	March 2013, external audit every 2 years
[7] Financial reporting by the programme consists of (a) quarterly budget completion rates by activity within each output and by state (plus the cross cutting activities and components of the programme) and (b) monthly statements of expenditure in support of invoices submitted by the service provider

E: RISK

Overall risk rating: Medium

Overview of programme risk

The programme is medium risk due to a complex operational environment characterised by low willingness for governance reform, general insecurity, and rapidly approaching elections – but this is mitigated by strong, politically aware programme management, and good results evidenced so far.

Specific risks include:

1. Lack of political will: politics is a key driver of state planning and budgeting, and civil service management, rather than commitment to governance reform and service delivery.
2. Politicisation and preoccupation with elections. The imminent 2015 elections are a key driver, and interest in governance reform even at a technical level is dropping and likely to drop further.
3. Insecurity and conflict. There are security challenges in all states – with terrorist attacks in the north and criminal activities in the south, and these risks are likely to escalate approaching and post 2015 elections.
4. Lack of continuity with state government administrations. In states where continuity of leadership is low, reform continuity can be undermined. New administrations can jettison reforms associated with previous regimes. This will be particularly challenging post 2015 elections which will see a change of Governor in eight of the 10 states. Continuity is also challenging internally when dealing with changes in programme staffing, and this could increase if there is discontinuity between the staffing of SPARC and its successor.
5. Lack of continuity with the transition to the new governance programme scheduled to commence in April 2016.

In terms of risk mitigation in relation to the reform leadership in the new administrations, SPARC has produced election transition strategies for each of the 9 states affected by the elections. These strategies have helped other DFID programmes to plan for their transition as well as providing a template for DFID itself to prepare for its role over this period of re-engagement. Two considerations emerge from these proposed approaches:

The fundamental importance of DFID implementing its proposed leadership role in re-engaging its state programmes with the new administrations with support from SPARC. Change in administrations is also an upside risk.

The likely need for SPARC, with DFID agreement, to, adopt a flexible and responsive planning approach. These risks present a difficult context for SPARC in its preparation of the coming year’s work plans and budgets and in setting targets for achievement by the end of programme. Prioritisation needs to be influenced by a number of considerations including:

- Underlying objective to try and preserve the gains already made
- New administrations’ own articulation of reform priorities, the details of which may emerge only slowly
- Findings of the political economy analyses and their implications for commitment and the identification of ‘open doors’ for reform activity
- SPARC’s assessment of likely sustainability for each reform area using its own the 7 criteria of sustainability
- Potential synergies arising from closer working with SAVI and FEPAR
- Some judgement around which states are most likely to be partners in the new governance programme

It is highly unlikely that there will be clear or even comprehensive data to inform appropriate responses to the above factors. SPARC will have to start its planning exercise before the ‘dust has settled’ following the elections. It may be worth considering a two phase approach to the 2015/16 planning cycle: (1) an initial work plan, say perhaps for the first 6 months, followed by (2) a mid year review after 6 months resulting in a revised plan for the remainder of the year. It would be too onerous to complete two detailed planning exercises in the one year. However if some form of outline, abbreviated work plan could be produced for phase 1, then the phase 2 revised plan may not prove to be too burdensome.

Outstanding actions from risk assessment

The outstanding action is the conclusion by DFID of arrangements for a successor programme to begin in February 2016 to provide for an orderly handover to the new service provider.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Yes, delivery of the programme is on schedule. The programme accelerated progress towards outcomes and outputs in 2013/14, with 93% of milestones achieved compared to 86% in 2012/13. At the end of the first quarter of 2014/15 (July to September 2014), 50 % of activity milestones have been completed, and of the remainder, nearly all are well in progress. Programme performance in delivering all milestones shows that progress is on track. However, the upcoming national elections, combined with possible, related security issues (and the deteriorating situation arising from Boko Haram’s activities) may result in unexpected serious delays with programme implementation during 2015.

Performance of partnership(s)

The last Contract Performance Review was undertaken in March 2014, with the programme (contract service provider – HTSPE, now DAI) scoring 88%. All criteria were scored either 3 (most responsibilities are delivered efficiently and effectively) or 4 (proactive supplier delivering efficiently and effectively). Capturing and sharing lessons scored 4, as did proactive promotion of innovation. The partnership with DFID is strong – communication with DFID and delivery of agreed action points scored 4, whilst demonstration of willingness to improve partnerships with DFID and project stakeholders also scored 4. The 2013 Annual Review determined SPARC represents Value for Money.

Asset monitoring and control

The level of confidence in the management of programme assets is high. Detailed asset registers are maintained and these are subject to formal internal checks every 12 months, supplemented by occasional spot checks by management. The March 2013 audit report raised no issues of concern with regard to asset monitoring and control.

G: CONDITIONALITY

Update on partnership principles

No specific conditions apply to the programme; DFID’s partnership principles have not been adopted explicitly in the management and monitoring of the programme. During the last year, at the programme level, there have been no publicly-expressed concerns over the State Governments’ compliance with the four principles: (1) commitment to reducing poverty and achieving the MDGs, (2) commitment to respecting human rights and other international obligations, (3) commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption and (4) commitment to strengthening domestic accountability. However, the commitment to reform does vary between states and even within states over time.

The results of the upcoming elections, combined with the need for SPARC to plan in detail a ‘re-engagement’ programme of activities with each of the new administrations, provides a review point to assess, internally and informally within SPARC and jointly with SAVI, the likely commitment of the new Governors to PFM reform and to strengthening domestic accountability. This light touch analysis could then feed into SPARC’s decisions on the priority areas for intervention during 2015 and early 2016. Updating the political economy analyses post elections would feed into this planning process.

H: MONITORING & EVALUATION

Evidence and evaluation

During the year under review, the programme has completed a substantial body of analytical work with the objective of contributing to the better understanding of ‘what works and why’ (lesson learning) and to validating the key assumptions in the programme’s Theory of Change (ToC). The main reports include: (a) State Level Governance Trend Data (aka ‘Triangulation Study’) (b) Value Chain and Sustainability Case Study (c) 2014 MTSS Review Case Study (d) M&E Case Study on MTSS Improvement (e) Impact of Budget Case Study (f) Corporate Planning Processes Case Study (g) Knowledge Management Case Studies (h) Case Study of SPARC’s Political Engagement Approach (i) Understanding Political Commitment and (j) PFM Case Study ‘Assessment of the impact of PFM support to strengthen budget processes and documentation on improved fiscal realism, budgetary allocations and resource allocation’. Two additional relevant reports are in draft stage, namely the ODI study and SPARC’s internal evaluation study.

In terms of lesson learning around approaches, processes and broad change management issues, there is an extensive body of persuasive evidence that is emerging. It needs now to be compiled into a single document for ease of reference and for dissemination as a knowledge management product. However, in relation to validating the assumptions in the ToC, progress is less evident. The Triangulation Study highlighted the challenges in establishing causal links between inputs, outputs and outcomes, especially when data availability is limited. The Study concluded that “it is not possible to conclusively say that there is better functioning governance broadly.... nor that where there are changes to aspects of governance that these have influenced service delivery.” The findings of the Value Chain and Sustainability Case Study, whilst helpfully moving forward the assessment and understanding of ‘sustainable’ reforms, have not yet been fully analysed against the main assumptions in the ToC. More work needs to be done by the programme to (a) assess the extent to which this substantial body of analytical work does validate the ToC and (b) where major gaps remain, then decide what further analytical work is practical, feasible and cost effective to undertake in advance of the Programme Completion Review scheduled for early 2016.

Monitoring progress throughout the review period

SPARC continues to implement and refine its internal monitoring and reporting system which includes:
M&E MIS: performance management reports, quarterly progress reports, annual report, annual change programme performance reviews in each state, and report on progress against the logframe. In addition, ongoing implementation monitoring takes place at all levels of SPARC; State and Federal teams are in touch with their government counterparts on a daily basis, following up on agreed actions, helping to review documents prepared by government and participating in various Committees and Technical Working Group meetings in order to monitor reforms.

Progress reporting is extensive with detailed quarterly analyses, by state, across all activities. However, monitoring during the coming year needs to focus more closely on the effectiveness of SPARC’s electoral transition strategy and the content of the resulting agreed intervention areas. The risk mitigation strategy will need to be monitored closely.

This 2014 Annual Review was designed as a ‘light touch’ review following the in-depth review completed in 2013. In addition to meeting with DFID and the National Programme Team based in Abuja, State Team Leaders came to Abuja to update the Review Team on progress and issues within the following states: Enugu, Kaduna, Kano, and Katsina. Meetings were held with the Secretariat of the Nigeria Governors’ Forum as well as with representatives from the Office of the Senior Special Adviser to the President, including from the unit administering the Conditional Grant Scheme. PFM reform discussions were held with the Senior Economist at the World Bank. Prior to completing the fieldwork in Abuja, the Review Team provided initial feedback on its findings to SPARC and to DFID.