PROJECT Annual Review - Summary Sheet
This Summary Sheet captures the headlines on project performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Scaling up Family Planning in Zambia
Programme Value: £14.8million		Review Date: February 2015
Programme Code: 202342	Start Date: March 1 2012	End Date: 28 February 2016

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score		A	A+	A+
Risk Rating	High	High	Medium	Low

Summary of progress and lessons learnt since last review
The Scaling up family planning (SUFP) project is now fully operational in all 26 planned districts, an addition of 6 districts from the last annual review. Increased collaboration and planning with project partners and government stakeholders have resulted in improved project delivery and overachievement against most project indicators. Of key note are the following:

SUFP collaborated with key partners UNFPA, Ministries of Health and Community Development, Mother and Child Health (MCDMCH), Medical Stores Limited to ensure availability of Reproductive health commodities in project districts through training and supply chain monitoring exercise in SUFP supported districts. Intensive focus on the management and distribution of the reproductive health commodities resulted in near zero stock outs of a comprehensive package of reproductive health commodities in project supported facilities.

The adolescent family planning strategy was finalised and disseminated to MCDMCH, partners at national and district level and to the Adolescent Health Technical Working Group. SUFP supports its implementation in project districts conducting outreaches for both in and out of school adolescents and youth in hard to reach areas. Adolescents who have been oriented in the strategy have been used as agents of change by the districts in implementation.

The mentorship program attached to the family planning centres of excellence and the use of Community Based Distributors are interventions that are cost-effective and will contribute to increased uptake of FP services if sustained. MCDMCH and MOH have indicated to SUFP that these strategic approaches will be replicated by the government after project close-out.

Concerted steps to address sustainability in project delivery commenced with increased incorporation of FP messages and services in national events such as World AIDS Day, Child Health week and Youth day.

Summary of recommendations for the next year
- Abt Associates to develop and implement a sustainability framework and exit strategy by July 2015.
- SUFP project partners to sustain the focus on strengthening the RH commodities supply chain at all levels.
- DFID to conduct a VfM session with Abt Associates by April 2015 to address VfM issues associated with the administration and management costs and metrics used for monitoring cost effectiveness; and report to the Head of Office on progress.
- DFID to approve by March 2015 a no cost extension to the MOU with UNFPA to December 2015 for oversight of DFID funded RH commodities and procurement of additional commodities identified by the national needs assessment with balance funds.
- DFID to revise logical framework output risk ratings as specified under key actions in line with the revised classification of the project as ‘Low’ risk.
A. Introduction and Context

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme
The UK government is providing up to £14.8 million over four years (2012 – 2016) to scale up family planning (FP) for under-served areas and populations in 26 districts and build the capacity of the public sector to deliver quality comprehensive family planning services beyond the project timeframe.

The Scaling Up Family Planning (SUFP) project has several components as follows:-
- Delivery of FP services is implemented by Abt Associates in partnership with Planned Parenthood Association of Zambia (PPAZ), Imperial Health Sciences (IHS) and American College of Nurse Midwives (ACNM). £11,541,762
- Procurement of reproductive health commodities is carried out by UNFPA based on gaps identified by the government’s Reproductive Health Commodity Security Committee. Supplies are warehoused and distributed by Medical Stores Let (MSL) through the public sector drug supply system. £2.9million
- Procurement of office equipment, furniture and vehicles by Crown Agents. £372,030

The SUFP districts of operation were chosen together with the government based on low contraceptive prevalence rates, high unmet need and underserved rural areas. The project is working with community health workers, traditional and religious leaders to sensitise communities on the uptake of family planning services and to provide accurate information to address myths and misconceptions. Outreach services are being delivered in partnership with the Ministry of Community Development Mother and Child health (MCDMCH) working with health facilities. A focus of the project is on adolescents, a particularly vulnerable but hard to reach group. The project works with adolescent peer educators and schools to broaden its reach with this group. Abt Associates works with health facilities and the district health team to strengthen their supply chain and supports increased availability of family planning products at health facilities in project districts.

The SUFP project’s overall impact will be improved maternal health in Zambia. By 2016 the project is expect to contribute to:

- Reducing maternal mortality from 591/100,000 to 443/100,000.
- Averting 92,450 unintended pregnancies (13,868 in adolescents)
- Averting 13,059 unsafe abortions (1,958 in adolescents)
- Averting 298 maternal deaths (45 in adolescents)

The project outcome will be increased use of family planning in Zambia. This will be measured by:

- An increase in contraceptive prevalence rate nationwide for rural married women from 27.6% to 36% and from 48.5% to 69% in women of reproductive age in project intervention areas
- A decrease in the percentage of women and girls with unmet need for family planning in project areas from 27% to 5%.

80% of these results will be attributable to DFID.

The Scaling Up Family Planning (SUFP) Project is fully aligned with the Government of the Republic of Zambia’s eight year integrated family planning scale up plan 2013 to 2020. This has as its objective increasing the contraceptive prevalence rate for modern methods (women married or in union) from 33% in 2007 to 58% by 2020. The plan and the national commitments have been triggered by strong leadership from the MCDMCH and political support from the former First Lady, the high level family planning event in the UK in July 2012 and coordinated work on FP in country by all partners.
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The project is on track to deliver on expected national outcome result as measured by the preliminary Zambian Demographic Health Survey (ZDHS) 2014. In addition to meeting the 2015 milestone, the life of project target for use of contraceptives by rural married women nationwide has been exceeded with the ZDHS 2014 recording 39% contraceptive prevalence rate for this target group against a life of project target of 36% by February 2016.
Outcome Indicator	Baseline	Milestone 2015	2015 Progress
Contraceptive prevalence rate	National: 27.6% for all rural married women (DHS 2007) / SUFP Project Areas: 48.5% (SUFP survey 2012)	National: 34% for all rural married women / SUFP Project Areas: 64.2% / Breakdown: / 15-19 yrs: 40% / 20+: 60% / Rural: 65%, Urban 35%	National: 39% for all rural married women / SUFP Project Areas: Not measurable
Percentage of women and girls with unmet need for family planning in project areas	27%	10% / Breakdown: / 15-19yrs: 16% / 20+: 4% / Rural: 15%,Urban: 5%, / .	Not measurable in 2015

No data was available to measure outcome progress in project areas for the period under review. Indications from progress against outputs however suggest that the project is on track to meet outcome targets.
.
Overall output score and description: A+
The project moderately exceeded expectation. Overall, the uptake of modern contraceptive methods by women and girls exceeded expectation with 138,981 additional women using a modern method of contraception against a target of 120,000, the majority favouring short term methods. The project procured FP products in response to nationally identified gaps and this coupled with intensive support to the supply chain at all levels resulted in increased availability of comprehensive family planning products at health facilities with stock out rates below 1%.

The milestone for increasing access to family planning services for under-served areas was exceeded with 72% of target communities covered by outreach services against a target of 50%, 78% of these in rural areas. Efforts to move to government led health facilities supported outreach activities in communities continued with good results. Community support for family planning remains high and for the period under review, the project focused exclusively on training of community leaders and community based distributors in rural areas. The project developed adolescent FP strategy was adopted by GRZ and implementation commenced in project areas. Progress in increasing government capacity continued with the project exceeding targets in number of health facilities offering family planning services and are sensitive to the needs of adolescents. The 14 centres of excellence in operation offering comprehensive family planning services and mentoring in family planning for health facilities in project districts should help increase the overall percentage of staff in districts trained.

Key lessons
Intensive support to the supply chain at all levels continues to be necessary to ensure that RH commodities procured reach health facilities. Specifically, support at the district and health facility level is required to ensure adequate inventory management and timely requisitioning of RH commodities. RH commodities forecasting should be based on a comprehensive needs assessments and fully incorporated into national supply chain planning.

Government led outreach services were effective in increasing uptake of family planning services in communities. Their performance was further increased with the participation of community leaders in the social mobilization component of FP outreach.

The lower than expected uptake of long term reversible contraceptives methods is mostly confined to Inter-uterine Contraceptive devices (IUCDs). Health service provider reluctance to promote this method coupled with cultural issues contribute to the low uptake. Communities with past experience of IUCDs recall the lack of capacity of health providers to remove the devices when projects close. Sufficient capacity must be established to prevent a recurrence of this state of affairs at project end.

The project risks are being consistently and appropriately addressed with project milestones met. As such a review of the risk rating for outputs and the project overall was made during the AR process.

Key actions

- DFID to approve by March 2015 a no cost extension to the MOU with UNFPA to December 2015 to enable sustained oversight of DFID funded RH commodity procurement and distribution and increase availability of equipment and RH commodities at health facilities. Ensure that the balance funds are applied to procurement of RH commodities according to gaps identified in national RH commodity assessment.
- DFID to conduct a VfM session with Abt Associates by April 2015. The project SRO to send an Information note at that point to the Head of Office reporting on progress and confirming that the key VfM issues have been addressed.
- DFID to revise output 1 risk rating from High to Medium and Output 2, 3 and 4 risk ratings from ‘Medium’ to ‘Low’.
- SUFP with DFID’s concurrence to review logical framework targets for long term reversible methods and reduce to take into account expressed client preference and challenges associated with increasing uptake particularly in rural areas. Revised targets should however continue to be modestly ambitious.
- The SUFP project to continue engagement on national supply chain issues at national and district level. DFID through the Malaria and Child Health project implemented by UNICEF and through the Donor working group on supply chain to monitor and promote coordinated donor support to the National Supply Chain strategy and MSL. The SUFP project through UNFPA at the national level and Abt Associates at the district and health facility level to continue to strengthen forecasting, distribution and inventory management of RH commodities.
SUFP in collaboration with Zambia Emory HIV Research Project to continue to address the issues surrounding uptake of LARCs particularly IUCDs. Actions should include expanding LARC in Couples Voluntary Counselling and Testing and addressing the issue concretely in the project exit strategy.
- SUFP to evaluate the effectiveness of RH radio spots in SUFP districts, monitoring the prevalence of myths associated with use of LARCs.
- SUFP to continue to advocate to the MCDMCH to support the mentorship program as a sustainable way to build capacity in FP. SUFP district health officers to encourage District Health teams in ring fencing budgets and staff for FP centres of excellence and mentorship activities as part of 2016 planning exercise.

Has the logframe been updated since the last review?

The logframe was updated as per the recommendation of the 2014 annual review as follows:-
- Impact Indicator 1: Maternal mortality ratio. The milestone for 2014 was changed to 512/100,000 to bring this in line with the departmental results framework
- Outcome indicator 1: Percentage Contraceptive prevalence rate (CPR). The project logframe now includes the monitoring of both the national contraception rate for rural currently married women – source ZDHS in addition to the CPR rates in 8 project districts. As such, baseline figures were revised and targets and milestones set for both estimates.

C: DETAILED OUTPUT SCORING

Output 1	Expanded Availability of Choice of Family Planning methods
Output number per LF		Output 1	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output Indicator 1.1: / Number of additional women and girls using: / i) Short Term Methods and ii) Long Term Reversible Methods / (Disaggregated by: method type; urban/rural; age 15-19, 20+; source of method)	Total New Clients: 120,000 / Breakdown as follows: / Short term: 70,000 / Rural: 50,000: / age 15-19: 8,200, / age 20+: 41,800 / Urban: 30,000: / age 15-19: 2500, / age 20+: 27,500 / Long term: 50,000 / Rural: 30,000: / age 15-19=2,500, / age 20+=27,500; / Urban: 20,000: / age 15-19: 3,000, / age 20+: 15,000	Total New Clients: 138,981 / Breakdown as follows: / Short term: 106,925 / Rural: 80,523: / age 15-19: 22,698, / age 20+: 57,825; / Urban: 26,402: / age 15-19: 5,873 / age 20+: 20,529 / Long term: 32,056 / Rural: 24,028: / age 15-19: 3,729, / age 20+: 20,299; / Urban: 8,028: / age 15-19: 1,321, / age 20+: 6,707
Output Indicator 1.2: Percentage of public sector facilities covered by the program that experienced a stock-out of the full comprehensive package of FP methods during the last 12 months	1%	0.8%
Output Indicator 1.3: Couple Years of Protection generated attributable to the project / (Disaggregated by: urban/rural; age 15-19 and 20+)	Total : 210,000 / Urban: 80,000 / age 15-19: 20,000 / age 20+: 60,000 / Rural: 130,000 / age 15-19: 30,000 / age 20+: 10,000	Total: 274,847 / Urban: 69,123 / age 15-19: 9,420 / age 20+: 59,703 / Rural=205,724 / age 15-19: 30,843 / age 20+: 174,881
Output Indicator 1.4: Percentage of national forecasted need in FP commodities met by project	4%	34%

Key Points
SUFP has exceed the year 3 (Feb 2015) milestones for all output 1 indicators with the exception of targets set for the uptake of long term reversible conceptive (LARC) methods. It should be noted that although the targets for LARC methods were not met, significant progress has been made when compared with the 2014 AR with 64% of LARC target attained in 2015, compared to 47%. The SUFP project districts as selected in conjunction with the districts heath teams are predominantly rural including the 6 final districts added in the period under review. This may have a bearing on progress against indicators as the skew to rural populations is greater than anticipated at project inception. In addition progress on uptake of family planning methods indicates that project is encountering a higher unmet need for family planning in rural areas than anticipated.

Notable actions during the period under review include the following:-
- Trained 271 health care workers on Logistics and Commodity Management for Essential Medicines in 16 SUFP supported districts.
- Together with UNFPA, and in collaboration with MoH and MCDMCH, SUFP carried out a Rapid Supply Chain and Logistics Management M&E assessment in the 13 SUFP year 2 districts. The assessment showed that there were no stock outs of LARC methods (Jadelle, Depo-Provera or IUCDs) recorded during the assessment exercise.
- SUFP also conducted a rapid assessment of a supply chain and logistics management of RH commodities in the 6 new year 3 project districts. The assessment revealed that most health care workers were not trained in supply chain and logistics management of medicines and medical supplies and none of the health centres had a full mix of reproductive health commodities. The results of the assessment informed the training and support given to health facilities with regards management and availability of RH commodities.
- SUFP facilitated the expansion of quality sterilization processes in SUFP and other districts. In collaboration with an international consultant hired through IHS, SUFP coordinated an assessment of autoclaves that were procured by the government using DFID funds from previous projects and distributed to all the districts in the country including those being supported by SUFP. The assessment found that a number of equipment had not been properly installed in the facilities, that health care workers did not know how to use them and that facilities with inconsistent or no electricity had been provided with autoclaves. SUFP worked to ensure appropriate redistribution of equipment, general maintenance where possible and for the Centres of Excellence, full operationalization of the sterilization equipment.
- High numbers of new acceptors of long term methods, with strong preference for injectables and implants and low demand for IUCDs. Operations research revealed misconceptions about IUDs are most common. There are concerns about lack of removal services after project end that influence method choice and cultural barriers remain including reluctance to undress before younger health providers when not ill. Health providers have also been reported as being reluctant to promote IUCDs.
- Delays in commencement of procurement of RH commodities in years 1 and 2 have cumulated in the project’s higher contribution to the national RH commodities pool than originally projected.

Summary of responses to issues raised in previous annual reviews (where relevant)
Further integrate the HIV Prevention project to optimize value for money and increase the numbers of long acting family planning users.
SUFP have worked with the Zambia Emory HIV Research Project (ZEHRP) to integrate LARC training and HIV prevention into facility based FP service provision and community level demand creation activities respectively. Training of health facility staff in provision of LARC methods as part of Couples Voluntary Counselling and Testing (CVTCT) and Couples Family Planning Counselling has been carried out for 20 SUFP districts and HIV prevention training in 7 SUFP districts.

Carry out close monitoring of UNFPA to ensure commodity procurements are on track
SUFP has improved communications and follow up with the UNFPA country office with the SUFP Logistics and Supply Chain Team Leader liaising with the UNFPA country office by telephone or in-person on a regular basis. There have been delays in the period under review in receiving the last batch of DFID funded RH commodities in-country and this is now expected in April 2015. DFID contributes to a national pool of RH commodities and national stocks of RH commodities are not in short supply. MSL however continues to experience challenges in ensuring timely and adequate distribution of commodities to district and health facility level. UNFPA have commenced procurement of additional equipment and medical products based on a national assessment and agreed by DFID.

Recommendations
- Sustain the focus on strengthening the RH commodities supply chain at all levels.
- Approve a no cost extension to the MOU with UNFPA to December 2015 to enable sustained oversight of DFID funded RH commodity procurement and distribution and increase availability of equipment and RH commodities at health facilities.
- Continue to address the issues surrounding uptake of LARCs particularly IUCDs. Actions should include continued incorporation of LARC training in Couples Voluntary Counselling and Testing under HIV Prevention project; project exit strategy to address concretely the issue of removal services for LARCs and training/ refresher trainings through Centres of Excellence to improve health provider counselling and insertion/removal skills for IUCDs.
- Review logical framework targets for long term reversible methods and reduce to take into account expressed client preference and challenges associated with increasing uptake. Due to the additional couple years protection obtained from long term reversible contraceptives compared to short term methods however, revised targets should continue to be modestly ambitious.
- Output 1 risk rating has been revised from High to Medium during this annual review. The operational challenges experienced in delivering this output have to a large extent being addressed. The supply chain from national level to districts however remains precarious and continues to present a risk to output delivery.

Output 2	Increased access to family planning services for under-served areas and populations
Output number per LF		Output 2	Output Score	A+
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones(Feb 2015)	Progress (Jan to Dec 2014)
Indicator 2.1: Percentage of target communities covered by outreach services (both community mobilisation service provision) by the project in target district (by: urban/rural )	Total: 50% / Breakdown: / Rural - 80% / Urban -20%	Total: 72% / Breakdown: / Rural - 78% / Urban - 22%

Key Points
The SUFP project continues to demonstrate strong performance against the Output 2 indicator by expanding outreach services from 20 to all 26 project districts. The integration of FP services into other outreach events undertaken by health facilities staff including the safe motherhood week and National Voluntary Counselling and Testing day has also contributed to the increase in outreach services. A comprehensive outreach comprises community mobilization, BCC messaging and FP service provision. The inclusion of community gate keepers is increasingly deployed to great effect.

- In the period under review, SUFP conducted over 1,435 outreaches over across all 26 project districts.
- SUFP implemented its innovative ‘camping’ approach in the final 6 districts of Mwense, Sesheke, Chavuma, Itezhi Tezhi, Kaoma and Petauke. HPs, CBDs, drama groups and community leaders are trained during the two week camping events to provide family planning services, provide family planning commodities, and to spread family planning BCC messages, respectively. The ‘camping’ method ensures that clients understand the benefits of family planning at the same time that they have access to the services and that their community leaders understand the importance of family planning (which addresses an important cultural barrier) all at the same time.
- SUFP supported the district health Maternal and Childhealth coordinators to plan, budget and execute outreach activities. It is expected that this close collaboration will increase the capacity of the District Maternal and Child health (MCH) coordinators to independently implement outreach activities in the future. Currently however the SUFP project provides logistical support for all FP outreach services in districts of operation due to lack of GRZ funds.

Summary of responses to issues raised in previous annual reviews (where relevant)
Urgently complete the adolescent strategy and begin implementation. Liaise with other relevant organizations including Population Council funded by DFID for the Adolescent Girl empowerment project to ensure a coherent approach
The adolescent family planning strategy was finalised and disseminated to MCDMCH, partners at national and district level and to the Adolescent Health Technical Working Group (ADH-TWG). SUFP supports its implementation in project districts. Adolescents who have been oriented to the strategy have been used as agents of change by the districts. Population Council as part of the Adolescent health technical working group contributed to the development of the strategy. SUFP and Population council have jointly reviewed their areas of implementation and adjusted interventions to avoid duplication.

Recommendations
- SUFP to continue to facilitate the increase in outreaches that are district led and integrated into appropriate activities, supporting districts as necessary to include the expanded FP approach into district health planning. Reporting on outreaches should be disaggregated to identify whether they are district or project led to enable improved analysis of the extent and impact of integration of services
- SUFP to increase adolescent focused social mobilization activities as part of outreach services. This will include increasing the repertoire of drama groups to include more adolescent focussed sketches.
- Annual review process has revised output 2 risk rating from ‘Medium’ to ‘Low’ to account for the sustained track record for successful output delivery.

Output 3	Increased community support for family planning
Output number per LF		Output 3	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (Feb 2015)	Progress ( Jan to Dec 2014)
Output Indicator 3.1: Number of SMAGs trained as CBDs in project districts / (Disaggregated by: urban/rural)	Total 300: / Breakdown / Urban=90; Rural=210 / Cumulative project total to date : 550	Total 255 / Breakdown: Urban=0; Rural=255 / Cumulative total achieved to date: 615
Output Indicator 3.2: Number of community leaders trained as CBDs in project districts / (Disaggregated by: urban/rural)	Total 180 / Breakdown - / Urban=50; Rural=130 / Cumulative project total:365	Total 150 / Breakdown - Urban=0; Rural=150 / Cumulative total achieved to date: 886
Output Indicator 3.3: Percentage of community leaders in project districts sampled who report favourable attitudes towards family planning / (Disaggregated by: urban/rural)	Not projected to be measured	Not projected to be measured

Key Points
The milestones for the period under review performed moderately below expectation although cumulatively the project has greatly exceeded the targets to date for CBD training. As such, an A score was awarded for the output in this AR period. In addition, the life of project target for community leaders trained as CBDs has been exceeded with 886 trained against a life of project target of 390. The strong performance against the output indicators is due to demand by district health authorities for trained community health workers to support health service promotion and provision in rural communities. As all 6 districts added in Year 3 were all rural, no training was conducted in urban areas in the period under review.

- In year 3 SUFP continued to engage key stakeholders such as traditional and religious leaders, councillors, school authorities and community to mobilize communities to embrace and advocate for FP services.
- SUFP partner Planned Parenthood Association of Zambia (PPAZ) implemented adolescent activities in Itezhi tezhi and Petauke. PPAZ conducted outreaches for both in and out of school adolescents and youth in hard to reach areas in order to increase understanding and uptake of FP among adolescents and youth. They have been closely working with the SUFP district officers and PPAZ district based structures to facilitate these activities.
- FP focused radio spots with messages in local languages were developed and distributed to all SUFP districts targeting community members, especially sexually active adults and adolescents. They have been aired by community radio stations and used by traditional leaders, peer educators, drama groups and other community structures to increase acceptance of FP. The radio spots were developed in local languages with the participation of community members in message formulation and in the implementation.

Summary of responses to issues raised in previous annual reviews (where relevant)
Promote even tighter links between CBDs and existing district structures
At the national level SUFP is part of the team facilitating the development of the National CBD strategy in collaboration with MCDMCH and other stakeholders. This strategy aims at harmonizing and standardizing CBD activities in the country. This should legitimize the role of the CBD and enable greater integration of CBD FP activities in district planning.

Carry out formative research to remove barriers to reaching adolescents
SUFP designed and carried out a gatekeepers assessment in Siavonga and Kaoma to provide insights to the attitudes and opinions on FP held by adults who have influence over access of adolescents and youths to family planning. The findings will be used to recommend future project interventions aimed at increasing access to FP for young people and increasing acceptance for FP among gatekeepers.

Recommendations
- Encourage health facilities to continue holding integrated outreaches within their respective catchment areas. This promotes ownership and accountability by health facility staff as well as reducing the cost of holding outreaches.
- Messages given to clients e.g. on IUDs and Jadelle should be carefully reviewed and structured to continue to dispel myths.
- Use the findings from the gatekeepers’ assessment to strengthen the involvement of adult members of the community in facilitating the uptake of family planning services as appropriate among adolescents. The findings of the assessment should also be shared with the government, technical working groups and health partners to inform on adolescent health programming nationally.
- Evaluate the effectiveness of RH radio spots in SUFP districts, monitoring the prevalence of myths associated with use of LARCs.
- Monitor and report on the implementation of the adolescent strategy in SUFP districts.
- Output risk was downscaled from ‘High’ to ‘Medium at last annual review. Output risk rating has been revised further to ‘Low’ due to strong performance against output indicators.
- DFID to ensure that Government allocation and disbursement of funds to district health teams and its potential impact on sustained provision of quality FP services is examined as part of SUFP project evaluation.

Output 4	Increased public sector capacity to provide comprehensive family planning services
Output number per LF		Output 4	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (Feb 2015)	Progress ( Jan to Dec 2014)
Output Indicator 4.1: Number of public sector health facilities in project districts with the capacity to provide Long Term Reversible Methods / (Disaggregated by: urban/rural; facility level)	Total: 180 / Urban: 70 / Rural: 110	Total: 369 / Urban: 83 / Rural:286
Output Indicator 4.2: Number of public sector health facilities in project districts providing Adolescent Friendly Health Services / (Disaggregated by: urban/rural; facility level)	Total: 180 / Urban=70; / Rural=110	Total: 369 / Urban=83; / Rural=286
Output Indicator 4.3: Percentage of health workers in facilities covered by the project trained in i) Long Term Reversible Methods and ii) Adolescent Friendly Health Services / (Disaggregated by: urban/rural; cadre of health worker)	Total: 90% / Urban (36%); / Rural (100%)	Total: 63 % / Urban (32%); / Rural (68%)

Key Points
SUFP far exceeded the 2015 milestones for output indicators 4.1 and 4.2 by conducting trainings during ‘camping’ sessions, mentorship in Centres of Excellence and through collaboration with ZEHRP (training in LARCs) and other partners. Under indicator 4.3, SUFP has not achieved the targets as trainings were carried out for just one provider per facility. SUFP plans to meet the overall LOP target through mentorship and training initiatives from the Centres of Excellence.

SUFP has to date established 14 Centres of Excellence that act as training centres for LARC training and refresher trainings. Many of the centres also have a trained mentor actively mentoring local CBDs and health providers.

A mentorship training of trainers’ workshop for 24 health care workers took place in July 2014 expanding the number of districts with active mentors to all 26 SUFP districts. The mentors were also trained on integration of nutrition into FP services as part of DFID’s drive to mainstream nutrition activities into health projects as appropriate. The focus has been on improving post-partum nutrition and infant and young child feeding.

In collaboration with ACNM, joint monitoring visits to assess the impact of the mentorship project were conducted in selected districts. The assessment indicated that the mentorship program is in operation and mentors are successfully imparting knowledge to health providers on family planning service delivery. The number of mentors however is insufficient to fully address the capacity needs of the districts with regards FP services, in particular delivery of LARC methods.

SUFP as part of the FP technical working group has actively participated in policy level discussions, to advocate for provision of injectable conceptive by trained CBDs to expand access of communities to FP services. The government has responded positively and developed a policy enabling trained CBDS to provide injectable contraceptives under the supervision of health care providers.

Government actual support to FP services continues to be patchy despite tremendous progress at the district level in terms of incorporating FP into district planning and supporting outreach services. In particular government allocation and timely disbursement of financial resources for outreach services and the rate of staff transfers from health facilities continue to be risk factors that threaten the continued availability of quality FP services at project end.

Summary of responses to issues raised in previous annual reviews (where relevant)

Work is needed to maximize the use of ACNM and ensure value for money
ACNM have participated in the SUFP work planning meeting and monitoring of the trained Health care providers and CBDs in selected districts. They have reviewed and are in the process of revising the mentorship training materials. Their experience in training and supporting the mentorship project are being fully utilized to obtain buy-in for the adoption of the training materials from the FP working group and from MCDMCH. ACNM will conduct their final mentorship training in Q1 of year 4 after which they will make recommendations for the continued implementation and sustainability of the mentorship project.

Recommendations

SUFP to advocate to the MCDMCH to support the mentorship program as a sustainable way to build capacity in FP. SUFP district health officers to encourage District Health teams in ring fencing budgets and staff for FP centres of excellence and mentorship activities.

Output risk rating revised from ‘Medium’ to ‘Low’ as project has mitigation strategies through the Centres of Excellence with capacity to training health providers to manage risks associated with GRZ staff transfers.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The key cost drivers for SUFP are:
- Staff costs (including long term and short term TA) : 55%
- Training: 25%
- Travel: 10%

Unit costs for Training and Staff costs are shown in VfM indicators below. Travel costs have increased as a percentage of total expenditure (from 6% to 10%) largely driven by increased ground transportation and travel related accommodation costs.

VfM performance compared to the original VfM proposition in the business case

SUFP monitors VfM routinely against a set of indicators and has prepared an annual VfM assessment which combines quantitative and qualitative analysis. Highlights from the assessment are shown here:

VFM stage	Indicator	Benchmark/Trend and analysis
Economy	Average STTA rates = £673 / Average LTTA rates = £331 / Ratio of national to international TA: / Nat 93% - Int 7% (days)	Average International and National TA rates have reduced since Year 1. / National TA ratio has already exceeded internal target which was to rise to 75% at a mid point and 80% by end of project.
Efficiency	Administration and Management % of total expenditure: / 36%(since inception) / 29% (in Year 3) / Unit cost per training participant: / Health worker = £75 / Community based distributor = £79 / Commodities = £37 / Unit cost of community meeting = £120 (£1,126 in Year 2) / Unit cost of providing services to each additional user of family planning = £13	Administration and management costs are high compared to external benchmarks. Set up costs during inception phase was high however there has been no further decline in Year 3 costs as expected. / Unit costs are in line with external benchmarks for comparable training courses. (range = £30 - £106). / Unit cost of community meetings has reduced since Year 2 and now includes integrated outreaches conducted by health facilities / Unit cost of service provision to new users is lower than internal trend projections, with Year 3 target of £15. This is due to higher than planned number of additional users reached in Year 3.
Effectiveness	Cost per Couple Year Protection / Year 3 = £14.50 / Value of government contributions to SUFP activities: / £1.3m or 73% of SUFP expenditure on Output activities in Year 3	Unit cost is in line with expected internal trend projections. Target projected for Year 3 was £14. Based on Abt projects, the project is off track to reach the overall target of £18 per CYP by the end of the project. / The value of government contributions to SUFP activities in Year 3 has doubled compared to Year 2 (£0.63m), up to 73%. This is partly due to the additional districts SUFP is working in. This compares very favourably with other DFID health projects (range 10%-44%).

Assessment of whether the programme continues to represent value for money
There is good evidence that VfM is embedded within day to day operations of the project. The SUFP project records good results with respect to VfM in several areas including fee rates for International and National technical assistants, costs for radio spots (with negotiated reductions of up to 40%) and printing of IEC materials by using nationally validated existing materials from partners such as USAID Communication support for health and PPAZ. There are however VfM issues associated with administration and management costs, the cost of CYPs and metrics used for monitoring cost effectiveness with no clear indication as to how these might be addressed.
Recommendation: DFID to conduct a VfM session with Abt Associates by April 2015. The project SRO to send an Information note at that point to the Head of Office reporting on progress and confirming that the VfM key issues are being addressed.
Quality of financial management
For the component of the project implemented through Abt Associates:
- Expenditures January to December 31st	= £3,497,414
- Disbursement by DFID January to December 31st 2014	= £3,948,918
- Expenditures April to December 31st (FY 2014-2015)	= £2,726,328 detailed as follows:
Output 1 - Expanded availability of choice of family planning methods	£ 315,862
Output 2 - Increased access to family planning services for underserved areas and populations	£ 867,946
Output 3 - Increased community support for family planning	£ 957,189
Output 4 - Increased public sector capacity to provide quality comprehensive family planning services	£ 454,711
Milestone Awards	£ 130,620
TOTAL	£ 2,726,328
Forecast budget	£ 3,466,337

Key cost drivers (Also refer to Figure 1 below).
- Labour – in the period under review, labour remained the largest cost driver particularly with the expansion to the remaining 6 districts. As in previous reviews and based on the project design, SUFP requires a large number of staff in the field and technical assistance from head office.
- Field costs, the majority of which majority are training and workshop related reduced to 24% in the year compared to 30.8% the previous year. The reduction is partly due to the mentorship project that has reduced the need for external training input and associated costs increasing VFM.
- Travel – the project works in extremely rural areas so high travel costs for monitoring are expected.
- International labour costs have significantly reduced from 9.8% in 2013/14 to 2.7% in the current year. This can be viewed as an indication of skills transfer to local staff by international contractors that modelled the SUFP project approach during the first years of the project. Assuming that assumptions on quality of service provisions continue to hold, this has resulted in greater VFM and supports long term sustainability of the intervention in districts.

Figure 1. In-year project cost drivers

SUFP Cost Drivers
Based on expenditure Jan 2014 - Dec 2014

Figure 2. Overall project budget performance to-date

As it enters the final year, the project is relatively on-track against the total project budget at 78% expenditure by December 2014 (refer to Fig. 2. above). The in-year budget expenditure for the FY2014-2015 is also on track with 79% budget spent by December 2014.

Reproductive Health Commodities procurement financial report

Total expenditure on commodities	1,681,694
Committed for commodities (purchase order stage)	222,508
Total Expenditure to-date	1,904,204
Total disbursed by DFID to UNFPA (last disbursement January 2014)	2,457,350
Balance to be spent	553,146

The project planned to procure Depo-Provera, Noristerat, Jadalle Implant, Microgynone, and Copper-T. However the actual procurement has been based on national quantification and national needs. Therefore the actual procurement has so far been limited to three contraceptive commodities namely Depo-Provera, Jadalle and Noristerat.

Additionally, from the buffer funds, UNFPA has ordered 45,000 vials of Lignocaine to arrive in March 2015 and in process of ordering IUCD and Implant insertion kits worth USD62,400, again in response to nationally identified gaps. In addition to procurement of commodities, UNFPA also provided support to SUFP in the following;
1. Project Monitoring visits
2. Capacity building in Supply chain for the project districts
Date of last narrative financial report	13/02/2015
Date of last audited annual statement	18/07/2014

E: RISK

Overall risk rating: The project risk rating has been revised during the annual review process from ‘Medium’ to ‘Low’. The consistent meeting of targets over the three annual review periods (including the current period under review) suggests that the project is able to manage identified risks.

Overview of programme risk and Ongoing Actions

2013 Risk Rating	Risk	Action	Update
High	2012 fraud investigation raised IAD concerns over effectiveness and quality of Abt’s contracting processes	CFWU were content with the report of Abt senior management review of the fraud investigation. No further action required	No longer a risk however DFID will continue to implement appropriate programme management checks and processes.
Medium	Weaknesses in supply chain for RH commodities to district and facility level	Intensive support to supply chain in collaboration with UNFPA, MSL and MCDMCH showing goods.	Targets have been met but project focus on procurement and supply chain management still required. Risk remains at medium
Low	Project fails to reach adolescent girls	Adolescent FP strategy by adopted GRZ and implementation commenced. / Current GRZ interest in adolescent and sexual reproductive health issues. Zambia hosted international conference in December 2014	Targets have been met for the period under review.
Medium	Community opposition from traditional/religious leaders and men to family planning	Training and mobilization activities promoting FP continue focusing on community leaders, CBDs and SMAGs. Operations research on gatekeepers attitude to family planning undertaken and will inform on engagement with this group.	Project exceeded targets indicating successful engagement of these groups. Risk is downscaled to Low.
Medium	Shortage of health workers at rural health facilities	GRZ recruiting and training more nurses and midwives. / GRZ policy for CBDs to now deliver injectable contraceptives. New cadre of Community Health Assistants can deliver some contraceptives methods. Insertion of IUCDs however is limited to higher cadre health staff.	Ongoing problem. SUFP continues to work to influence staff transfers at district level. Risk remains at Medium
Medium	Fragile sustainability of project impact	District health teams embraced government led outreach services. / Centres of excellence established to increase district level capacity to deliver comprehensive services	Support for family planning high on GRZ’s health agenda with both Permanent Secretaries reiterating commitment. Development of good exit strategy and consideration of future support as part of new DFID health project. Issue of incorporating FP fully into district health plans and release of funds for activities continues. Risk remains at Medium.
Medium	Abt to formalize Operating agreement with MOH and MCDMCH	Agreement with GRZ finalized	No longer a risk

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Project overall continues to deliver against the planned timeframe. For RH commodities, the project was moderately behind schedule with delivery of procured commodities. However this has not had a direct impact on RH commodity availability at health facilities during the period under review. Issues with stock-out of RH commodities are primarily as a result of the weaknesses of the national supply chain.

Performance of partnerships
Abt has demonstrated improved engagement and effective partnerships with UNFPA for RH commodities; ACNM in improving quality of training and mentorship project and PPAZ in the implementation of the adolescent FP strategy. The quality of engagement will need to be sustained to ensure that project objectives are met and opportunities exploited to ensure sustainability of project interventions.

Asset monitoring and control
SUFP has an updated vendors list as per the SUFP Operations Manual as well as recommendations from the 2014 spot check conducted by DFID. The vendors supply various consumable and non-consumable goods to SUFP according to commercial and procurement standards.
Inventory controls - The fixed assets register is up to date. All newly procured items have been added to the inventory list with numbers, responsible owners, location, value and institutional labels. SUFP has been working with the MCDMCH to deliver assets such as bicycles to project districts. This has supported improved collaboration between the government and the project in terms of assets management and provided value for money by reducing transportation costs for project goods.

Based on the 2014 spot check of the SUFP project, store rooms are secured with keys kept by the Accountant. The Administration & Programme Manager is responsible for routine quarterly checks of the store rooms and the safe. The last check was done on 12th January 2015. The Deputy Director also conducts random checks on a needs basis.

G: CONDITIONALITY

Update on partnership principles (if relevant) Not applicable

H: MONITORING & EVALUATION

Evidence and evaluation
The ZDHS 2014 found that maternal mortality ratio has been reduced to 398 per 100,000 live births from a baseline of 591 in 2007. As such, the SUFP project impact target of contributing to the reduction of maternal mortality to 443 per 100,000 live births by 2016 has been exceeded. The decline in the maternal mortality ratio is indicative of an overall reduction in poverty levels nationally and a massive investment and improved coordination of maternal health interventions over the last 10 years. However, the ZDHS 2014 also records the unmet need for family planning as 26.5% and despite being highly cost-effective, only 1% of women use a long-acting reversible contraception (LARC) method such as the non-hormonal copper IUD or hormonal implant, suggesting more work is needed in this area. To note that the SUFP baseline CPR rate at 48% was higher than initially projected suggesting improvements prior to project commencement. The SUFP project is currently the major contributor to addressing the unmet need for family planning in project districts.

A Project evaluation is scheduled for 2016 however this will not include measurement of maternal mortality ratio.

Monitoring progress throughout the review period
The strengthening of RH reporting at district level through SUFP has supported the availability of family planning data from the district health management Information systems. Data is available for improved decision making on reproductive health activities by district health teams and evidence of this was apparent in some project districts and improved MCDMCH reporting on family planning activities at the national level. Concerted efforts however are required to ensure that the data influences decision making in all project districts.

Progress overall on reproductive health services are reviewed at the interagency coordinating committee meetings chaired by MCDMCH, with the most recent conducted in January 2015. In addition, MCDMCH conducted a nationwide review of progress on reproductive, maternal, adolescent, newborn and child health in December 20014 in support of the development of a joint Embassy of Sweden and DFID national programme to strengthen the continuum of care for reproductive, maternal, newborn and adolescent health.

A joint annual review process was undertaken for the SUFP and ZEHRP projects and was conducted by the Health Adviser and Programme officer. The process included a field trip to two project sites – Katete and Chama in Eastern Province with teams comprising of DFID staff, MCDMCH reproductive health specialist and staff from SUFP and ZEHRP. The process has also drawn on the orientation visits undertaken by the new health adviser in November and jointly with the Head of Office in December 2014 to three project districts of Choma, Kabwe and Ndola and discussions with communities, MCDMCH, district community medical officers and team and health facility staff.