The lograme for the DFID support to the Fund Management Team of FONERWA draws heavily on the logframe for the Fund itself. Indicators marked with [*] are also currently included in the FONERWA logframe

PROJECT TITLE	Creation of the National Fund for Climate & Environment (FONERWA)
IMPACT	Impact Indicator 1					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (Jun 2015)			Target – cost extension / (Oct 2015)		Version 1.3
Contribute to wealth creation and poverty reduction in Rwanda through low carbon and climate resilient economic growth	Percentage change in national climate change vulnerability index*				Methodology development through ENR sector before June 2015
					Source
					Indicator under development by DFID Climate & Environment Dept. Not currently measured by GoR but included in FONERWA M&E framework.
	Impact Indicator 2					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (Jun 2015)			Target – cost extension / (Oct 2015)
						390,940				502,160		613,380					724,600			724,600
	Rwanda National Green-house Gas Emissions reductions in relation to the baseline scenario[1]				Planned
					Achieved					n/a		n/a
					Source
					Biannual GHG inventory / National communications with UNFCCC / GoR Economic Data

OUTCOME	Outcome Indicator 1					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (Jun 2015)			Target – cost extension / (Oct 2015)		Assumptions
Rwanda able to finance and further develop national programmes and private sector initiatives which contribute to low carbon and climate resilient development	Cumulative volume of finance [US$ millions] mobilized for climate and environment purposes as / A). contributions to Fund; / B). leveraging (including co-financing for Fund supported projects)dis- aggregated by: / a).private sector / b).GoR / c).MDBs / other development partners (including DFID)/other sources*	Planned				A (a) 0. 0 / (b). 0.0 / (c). 0. 0 / B (a). 0 / (b). 0.0 / (c). 0.0				A (a). 0.0 / (b). 0.0 / (c). 0.0 / B (a). 0.0 / (b). 0.0 / (c). 0.5		A (a). 0.0 / (b).3.0 / (c).30 / B (a).4.6 / (b).0.0 / (c).1.1					A (a) 0.0 / (b) 4.2 / (c) 59.5 / B (a) 7.2 / (b) 6.2. / (c) 11			A (a) 0.0 / (b) 5.1 / (c) 60.3 / B (a) 7.4 / (b) 6.8 / (c) 15.0		- Climate and environment is mainstreamed into EDPRS II - Climate & environment programmes complement wider pro-poor activities - Strong macro performance continues
		Achieved					A (a). 0.0 / (b) 3.6 / (c) 53.2 / B (a) 2.6 / (b) 7.0 / (c) 0.5		A (a) 0.0 / (b) 4.2 / (c) 59.5[2] / B (a) 3.2 / (b) 6.2 / (c) 11.0					A (a) / (b) / (c) / B (a) / (b) / (c)
		Source
		Fund manager progress reports, agreed with REMA
	Outcome Indicator 2					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (Jun 2015)			Target – cost extension / (Oct 2015)
	Number of Project Profile Documents: / a) received by the FMT / b) meeting the standard required to proceed to Project Document stage / c) approved by the FMC[1]*	Planned				(a). 0 / (b). 0 / (c). 0				a.0 / b.0 / c.0		(a). 45 / (b). 23 / (c). 13					(a). 1088 / (b). 53 / (c). 21			(a). 1148[3] / (b). 63 / (c). 26
		Achieved					fund only capitalised in July 2013		(a) 1028 / (b) 64 / (c) 20					(a) 1089 / (b) 74 / (c) 22
		Source
		Fund manager progress reports, agreed with REMA
	Outcome Indicator 3					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (Jun 2015)			Target – cost extension / (Oct 2015)
	% of projects successfully implemented.[4]*				Planned	0				0		80					80			80
					Achieved					fund only capitalised in July 2013		28					16
					Source
					Fund manager progress reports, agreed with REMA
INPUTS (£)	DFID (£)					Govt (£)					Other (£)			Total (£)					DFID share (%)
	2.2					-					-			2.2					100%
INPUTS (HR)	DFID (FTEs)
	0.5 C&E Adviser; 0.1 Programme manager; 0.1 Results & Evaluation adviser

OUTPUT 1	Output Indicator 1.1					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (June 2015)			Target – cost extension / (Oct 2015)		Assumptions
Process of screening projects and disbursing finance is managed effectively	% of a )Project Profile Documents / b) Project Documents approved, reviewed within 20 and 30[2] working days respectively, and in accordance with agreed screening procedures*				Planned	(a) 0 (b) 0				(a) 50 (b) 40		(a) 80 (b) 60					(a) 90 (b) 80			(a) 90 (b) 80		Other donors are willing/able to contribute to a well-designed and effective Fund - Donors willing to follow GoR priorities - Private sector is interested in investing in low carbon and/or climate resilient activities - Wider enabling environment supports private sector investment
					Achieved					fund only capitalised in July 2013		(a) 100 / (b) 0
					Source
					Fund manager progress reports, agreed with REMA; Joint Sector Reviews
	Output Indicator 1.2					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (June 2015)			Target – cost extension / (Oct 2015)

	Cumulative % of total funds a) committed b) disbursed to approved projects (disaggregated by recipient: / government agency, / private sector, / CSOs)*				Planned	0 / 0				0 / 0		n/a / n/a					65 / b) 25			72 / 30
					Achieved					fund only capitalised in July 2013		57.3 / 8.2					a) 66.5 / b) 4
IMPACT WEIGHTING					Source					RISK RATING
35%					Fund manager progress reports, agreed with REMA, Joint Sector Reviews					Medium
INPUTS (£)	DFID (£)					Govt (£)					Other (£)			Total (£)					DFID share (%)
	0.65m					-					-			0.65m					100%
INPUTS (HR)	DFID (FTEs)
	0.2 C&E Adviser

OUTPUT 2	Output Indicator 2.1					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (June 2015)			Target – cost extension / (Oct 2015)		Assumptions
Capacity for managing the Fund built and transferred to Government of Rwanda	Number of initial local technical staff recruited who are retained at the end of the project period			Planned		0				0		0					n/a			3		- Trained staff remain in the Fund Secretariat - Sufficient numbers of staff to cope with workload
				Achieved					n/a		n/a					n/a
				Source
				Fund manager quarterly progress reports, agreed with REMA
	Output Indicator 2.2					Baseline (June 2012)		Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (June 2015)			Target – cost extension / (Oct 2015)
	Fund Secretariat Management systems embedded			Planned				n/a		n/a		n/a					Organogram IOPs JDs operational			MIS / Performance Management
				Achieved				n/a		n/a		IOPs and JDs					n/a
				Source
				Fund manager quarterly progress reports agreed with MINIRENA
	Output Indicator 2.3					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (June 2015)			Target – cost extension / (Oct 2015)
	% of the Fund Secretariat made up of local technical staff			Planned		0				10		50					80			100
				Achieved					100%		100%					100%
				Source
				Fund manager quarterly progress reports, agreed with REMA
	Output Indicator 2.4					Baseline (June 2012)			Milestone 1 (June 2013)			Milestone 2 (June 2014)					Milestone 3 / (June 2015)			Target – cost extension / (Oct 2015)
	Number of government of Rwanda staff recruited for the fund management secretariat			Planned		0			0			0					7			9
IMPACT WEIGHTING				Achieved					0			4					6					RISK RATING
25%				Source					Medium
				Fund manager quarterly progress reports, agreed with REMA, discussions with REMA and MINIRENA staff
INPUTS (£)	DFID (£)					Govt (£)				Other (£)					Total (£)			DFID share (%)
	0.65m					-				-					0.65m			100%
INPUTS (HR)	DFID (FTEs)
	0.2 C&E Adviser

OUTPUT 3	Output Indicator 3.1					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (June 2015)			Target – cost extension / (Oct 2015)		Assumptions
Awareness raising and technical assistance support submission of good quality proposals	Number of people trained in developing proposals (disaggregated by private sector/district level government/central government/CSO)				Planned	0				100		175					759			800		Sufficient numbers of high quality proposals are received - Steering Committee and Technical Committee meet regularly and function effectively
					Achieved					291		786					857
					Source
					Fund manager progress reports, agreed with REMA
	Output Indicator 3.2					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (June 2015)			Target – cost extension / (Oct 2015)
	a)Number of people visiting the FONERWA website; / b)Number of requests to the FMT for Technical Assistance in proposal development			Planned		(a) 0 (b) 0				(a) 0 (b) 50		(a) 0 (b) 150					(a) 1545[5] (b) 200			(a) 2060 (b) 250
				Achieved					(a) 0 (b) ~200		(a) 1545 / (b) >302
				Source
				Fund management team quarterly progress report; based on information from the FONERWA website and email records

IMPACT WEIGHTING	Output indicator 3.3					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)			Milestone 3 / (June 2015)					Target – cost extension / (Oct 2015)
25%	Number of financial instruments targeting the private sector developed and piloted by the FMT				Planned	0				1		1			2					2
					Achieved					1		1
					Source					RISK RATING
					Fund Management Team quarterly progress reports, agreed with REMA					Medium
INPUTS (£)	DFID (£)					Govt (£)				Other (£)					Total (£)				DFID share (%)
	0m					tbd				CDKN contribution to training figures – show here					0m				No DFID resources
INPUTS (HR)	DFID (FTEs)
	0.1 C&E Adviser

OUTPUT 4	Output Indicator 4.1					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)					Milestone 3 / (June 2015)			Target – cost extension / (Oct 2015)		Assumptions
Results from FONERWA are effectively and transparently monitored and lessons disseminated	% of active projects reporting data of sufficient quality to satisfy FONERWA monitoring and evaluation system		Planned			0				80		80				80				80		- Sufficient M&E capacity and expertise is available - Results are shared widely and lessons acted upon
			Achieved					fund only capitalised in July 2013		28
			Source
			Fund Management Team quarterly progress reports
	Output indicator 4.2					Baseline (June 2012)		Milestone 1 (June 2013)				Milestone 2 (June 2014)					Milestone 3 / June 2015			Target – cost extension / (Oct 2015)
	“% of implementing projects that demonstrate (a) transparent community participation; / b) a significant gender focus”		Planned				(a) n/a (b) n/a		(a) n/a / (b) n/a				(a) n/a / (b) n/a					(a) 60 (b) 60			(a) 60 (b) 60
			Achieved					fund only capitalised in July 2013				a.100 / b.63
			Source
			Fund Management Team quarterly progress reports (aggregated project level data)
IMPACT WEIGHTING	Output indicator 4.3					Baseline (June 2012)				Milestone 1 (June 2013)		Milestone 2 (June 2014)				Milestone 3 / (Jun 2015)				Target – cost extension / (Oct 2015)

15%	Evidence that lessons learnt are being used to adapt programme implementation		Planned			n/a				n/a		n/a				evidence of lessons learnt being incorporated, as assessed through Annual Review				evidence of lessons learnt being incorporated, as assessed through Annual Review
			Achieved					n/a		n/a
			Source					RISK RATING
			Fund Management Team quarterly progress reports					Medium
INPUTS (£)	DFID (£)					Govt (£)					Other (£)			Total (£)					DFID share (%)
	0.2m					0.2m					100%
INPUTS (HR)	DFID (FTEs)
	0.1 Results & Evaluation Adviser

1 Captures projects and programmes with climate and environment as their focus and also proposals for the Fund to cover the incremental climate and environment costs associated with new/existing programmes in other sectors
[1] As used in the SNC (difference between business as usual and mitigation scenario in tCO2e) , annual projections is the basis of the calculations and the next figures will come from 3rd National Communication
[2] Only direct financing to FONERWA is considered (DFID, UNDP, KFW, DCF/AfDB )
[1] Emphasis on large scale, cross-sector and integrated project planning and execution using project management approaches that have a track record of successful implementation IDP and VUP will serve as institutional vehicles for effective planning and implementation of projects/programs.
[3] On average 60 submitted per call
[4] Where success is defined as the project being on track to delivering at least 80% of the results set out in its Project Document
[2] Provided project documents received by FMT within 15 working days of next scheduled meeting of the management committee
[5] This is based on the number of people that visited the site in October. The cumulative figure for the next extension Year is as a result of the 1545/3 last months before October which has been added to 1545