Business Case

Summary Sheet

Overseas Territories Department Business Plan Summary: / The UK Government’s (UKG) responsibilities for its Overseas Territories (OTs) derive from the UN Charter, Chapter XI Article 73[1] which places on the UK the obligation to promote their development and the well-being of their inhabitants. These obligations are reflected in UK legislation. While legal liability rests primarily with each OT Government, UKG will frequently be considered responsible, in political and public terms, for the decisions or failures to act on the part of OT Governments. / The FCO leads on the constitutional relationship between the UK and its 14 OTs. But under the International Development Act (IDA) 2002, which specifically exempts development assistance to the UK OTs from the poverty reduction criteria which apply to the rest of the aid budget, successive UK Governments have placed a responsibility on DFID to meet the ‘reasonable assistance needs’ of ODA-eligible Territories: currently Montserrat, St Helena (including Tristan Da Cunha) and Pitcairn. Overseas Territories Department (OTD) has taken the ‘reasonable assistance needs’ in the aided-OTs to include physical access to the islands and the human capacity and budget necessary for delivery of essential public services and related public infrastructure (eg. roads; health, education, and social care facilities
[1] http://www.un.org/en/sections/un-charter/chapter-xi/index.html

Title: / Pitcairn Financial Aid 2019 -20
Programme summary / To support the provision of public services to meet the reasonable assistance needs of the people of Pitcairn (including health, education and securing sea access), given self-sufficiency is not a viable option for this UK Overseas Territory. This is in line with the 2012 Overseas Territories White Paper and consistent with relevant elements of UK’s Aid Strategy and DFID’s 2015-2020 Single Departmental Plan
What is the rationale for UK Aid spending? / The UK’s vision for its Overseas Territories (OTs) as vibrant and flourishing territories, proudly retaining aspects of their British identity and generating wider opportunities for their people, was set out in the 2012 White Paper[2]. The White Paper has three main strands: / to strengthen the engagement and interaction between the UK and the OTs; / to work with OTs to strengthen good governance arrangements, public financial management and economic planning; and / to improve the quality and range of support available / HMG recognises that the prospect of financial self-sufficiency for Pitcairn is not possible, given its small population and extremely remote location. The level of support provided reflects this as well as the lack of social and economic opportunities for islanders. Without UK financial aid, the government would be unable to provide any essential public services and the islanders would have to return to basic subsistence or leave the island. UK is the only source of significant external financing available to Pitcairn. / The International Development Act (IDA) 2002 specifically exempts development assistance to the UK OTs from the poverty reduction criteria which apply to the rest of the aid budget. / The context in which Pitcairn remains reliant on financial assistance and UK’s commitment to meeting islanders’ reasonable assistance needs will not change; this will be a continuation of previous annual financial commitments given HMG’s responsibility for meeting Pitcairn’s reasonable assistance needs.
Programme Value: £3,600,000 / Further details required in Annex A		Country/ Region or Sector: Pitcairn
Department/Country Office confirmation / Contact name		Lesley Reid, SRO
Threshold for Approval of Business Case:		HoD
Date of Approval of Concept Note:	21/02/2019	Name of Approver: John Gordon
Date of Approval of Business Case	06/06/2019	Name of Approver: John Gordon
Programme Code: 300235	Start Date: / 01/04/2019	End Date: / 31/03/2020
Overall programme risk rating: / Further details in “Risk” section	Moderate
Vault Number:			45983685
[2] https://www.gov.uk/government/publications/the-overseas-territories

Strategic Case

A1. The UK’s relationship with the OTs is different from that which it has with more traditional development partners. Our obligation to financially support the OTs derives from the UN Charter: “to promote to the utmost, within the system of international peace and security established by the present Charter, the well-being of the inhabitants of these territories [whose peoples have not yet attained a full measure of self-government]”. The International Development Act 2002 specifically exempts aid to the OTs from the poverty reduction criteria that apply to the rest of the DFID aid budget.
A2. Pitcairn’s limited economic activity includes a tourism market (mostly based on homestays, visiting yachts and passing cruise ships), craft sales, production and sale of honey, basic agriculture and fishing. Off-island economic activities consist of international sale of postage stamps and commemorative coins, although income from these is steadily reducing, and internet domain registration. GDP measures are largely irrelevant in this small, isolated community that currently has no tax base, though New Zealand inflation plays a part in the context of imported consumer goods and professional services.
A3. Two key challenges to socio-economic development require continual consideration in all aid and/or development planning are:
A3 (i) The legacy of the child sexual abuse history and the continuing need to maintain stringent child protection procedures: HMG has put in place interventions to create a substantial child safeguarding framework and a series of bi-annual independent reviews have taken place since 2009. The most recent review took place on island in late 2017, with the report being finalised in mid-2018. The review noted a distinct feeling of acknowledging the wrongdoings of the past and a focus on working collaboratively with HMG to establish a culture of child protection. The review also highlighted the important role that the community of professionals, including the police officer, social worker, teacher and doctor, play in providing input, guidance, knowledge and oversight regarding child safeguarding on the Island.  As with all previous reviews, HMG continues to work with the Government of Pitcairn to consider the recommendations and conclusions made.
A3 (ii) The ageing population and its economic activity declining with little/no immigration: The able-bodied population has declined, and the natural growth rate of the population is already far below a sustainable replacement rate. Altogether, there are 7 children between two families, four of whom attend secondary school in New Zealand and there have been no births among current residents since 2010. With a resident population of 43 (of whom 9 are off island long term), there are 27 in paid employment with only 9 of this group under 50. Of the 26 islanders over 50, 11 are of pensionable age[3]. Based on these demographics and current projections, by 2025 the age dependency ratio (those under 18 and over 65 compared to the productive population) will be over 100 percent and, assuming there are no children on island, the population could reduce to 33, with those over 65 accounting for more than 50% of the population.
[3] Pensionable age on Pitcairn is 65.
Even considering Pitkerners currently living off island, there has been a steady decline in the population in recent years, with this trend expected to continue without repopulation. There are only three options of increasing the population – children being born to islanders, the return of some of the Diaspora and/or immigration to the island. It is worth noting that a non-resident islander recently returned to live on Pitcairn with her spouse and 2 young children. Additionally, 2 families (each with 2 children) have made substantive enquiries about emigrating to Pitcairn, with one submitting a full application which is under consideration by the Governor’s office. However even with an increase in population by 40/50% this will not reduce the liabilities for HMG and dependency on aid. There would be an increase in health and education costs for the island in addition to the need for increased public services, all of which are funded from financial aid.
In the short term, maintaining and preventing non-communicable diseases (diabetes, hypertension, coronary heart disease) in the ageing population will be important for islanders to keep an active workforce as well as to minimise the need for care in later life. In the longer term however, this calls into question the sustainability of the island: who will do the work; who will look after the increasingly ageing population and how; who will operate the long-boats, critical to the island’s economic and social opportunities?
The island continues to promote immigration[4] and investing in tourism promotion, with the tourism department funded from Financial Aid (all associated infrastructure has been funded through EDF) to reverse population decline. But the island faces a very uncertain future with continuing HMG financial aid required. HMG remains engaged with the islanders in a concerted, meaningful, and frank discussion to understand their ideas and concerns about the future, which will inform any medium-long term vision for the island of the viability of the Island. The Pitcairn Island Council (the Council) will lead work, with external facilitation and supported by HMG, to determine what the future holds for the community. In parallel, there is ongoing consideration (led by the FCO) of HMGs longer term options for Pitcairn should the status quo prevail
[4] http://www.immigration.gov.pn/ .
Gender Equality
A4. As in previous years we have considered the likely impact on gender inequality and whether it will make sustained improvements in gender equality. The small resident adult population of 37 is split between men (20) and women (17). Of these 4 men and 7 women are over 65. The remaining adults are employed in government posts or the island store. Two of the 6 key posts responsible for managing the affairs of the Island are held by women. Given the small size of the population it is hard to draw meaningful inferences from these numbers; however, in recent years women have been elected to 5 of the 7 positions in the Island Council, including deputy mayor. It is also worth noting that although women have the option to work on projects and have worked on projects in the past, currently no women on island are employed on projects so their public sector income is limited to that received from government posts.
A5. In general, limited public services are provided to meet basic needs in health, social care, education and community policing, according to existing island policies and the core international conventions which apply to Pitcairn[5]. The Convention on the Elimination of all forms of Discrimination Against Women (CEDAW) is still to be extended to Pitcairn (although this is expected in 2019), a recognition of the progress Pitcairn has made on gender issues.
[5] European Convention on Human Rights (ECHR), the International Covenant on Civil and Political Rights (ICCPR), the International Covenant on Economic, Social and Cultural Rights (ICESCR), the International Convention on Elimination of all forms of Racial Discrimination (ICERD), the Convention Against Torture and Other Cruel, Inhuman and Degrading Treatment or Punishment (UNCAT), and the Convention on the Rights of the Child (CRC).
A6. Services are provided equally for all islanders, with specific attention for the needs of children and the elderly. Service delivery professionals address vulnerabilities on an individualised and family basis; including safeguarding and development of the island’s children, support and care of the elderly (the majority of whom are women); and support for those with mental health issues.
Child Safeguarding
A7. Whilst the Partnership Principles do not apply for development assistance to the Overseas Territories, the key gender issue on Pitcairn which is the legacy of child abuse, outlined in A4-6 above is actively managed. Child safeguarding remains a primary focus of HMGs efforts on Pitcairn Island. This includes the provision of an FCO Administrator who is the designated child safeguarding officer and the provision of four expatriate professionals funded from financial aid: a Social Worker (Family and Community Adviser - FCA), Teacher, Doctor and a Police Officer seconded from the New Zealand Police Force, each of whom have specific roles to ensure continued child safeguarding. This provides a multi-agency approach to child safeguarding on island. As noted above, there is now increased engagement by the Council and most members of the community on child safeguarding. Most Islanders acknowledge that what happened was wrong, why it took place and what needs to happen to keep children safe in the future. The current measures are regarded as effective, having been reaffirmed in all CSRs, including the last review in 2017, being carried out to ensure all reasonable measures to safeguard the three children living on Pitcairn are in place.

Terrorism and financing
A8. The risk of funding being used to finance terrorism activities is nil, given the remoteness and close monitoring of the destination of funds, through a delivery chain map.
PITCAIRN BUDGET
HMG’s contribution to the budget
A9. Pitcairn has required development assistance (90-95% of its budget requirements from 2004 onwards) and HMG’s financial support has been critical to the island in terms of: (i) the maintenance of basic public services at reasonable levels for a small and isolated population; (ii) appropriate child protection and security; and (iii) the provision of adequate shipping services. This is unlikely to change in the near future.

A10. HMG will therefore provide up to £3.6m (net) in Financial Aid to cover the shortfall between revenue and recurrent expenditure for the financial year 2018/19. This compares to a net provision in 2018/19 of £3.10m and is a 21% increase from 18/19, broken down as follows (a more detailed breakdown is shown in the Financial Case:

18/19 19/20 / £0.0m £0.0m / To meet Pitcairn's Reasonable Assistance needs including the operating/support costs of PIO 1.213 1.17 / Shipping Subsidy 1.550 2.623 / Long and short term Technical Assistance 0.637 0.572 / Expected revenue/income -0.314 -0.884 / contingency for unexpected expenditure in year 0.014 0.022 / Financial aid settlement 3.100 3.503 / Capital Expenditure 0 0.097 / Total Financial Aid Settlement (net) 3.100 3.600

A11. Included in the FA settlement is £0.097m for capital expenditure. This is required for the replacement of critical infrastructure (e.g. 24-hour generators for clinic and satellite, as well as a rigid inflatable boat, to be used as additional passenger craft). There has also been some allowance made for exchange rate fluctuations and unexpected expenditure.

Shipping costs
A12.  The increase in financial aid is mainly attributed to the new shipping service to the island, which began in March 2019.  HMG made a commitment in 2015 to improve the level and frequency of the shipping service to and from Pitcairn.  The previous shipping contract was issued in 2009 and provided 12 passenger and 4 freight journeys (rotations) every 3 months at an annual cost of £1.5m. Rotations originated from New Zealand, calling at Pitcairn before making 2 return journeys to Mangareva in French Polynesia (the nearest airport for onward connections), finally returning to New Zealand from Pitcairn. The previous vessel was a flat-bottomed riverboat, built in 1968, which broke down on several occasions, including on its last voyage to Pitcairn.  We understand that it subsequently proved impossible for the owner to sell. Following an unsuccessful tender exercise during 2016, a revised tender issued in 2017/18, drawing on advice from an international maritime expert, who undertook a feasibility study to determine the options available.  The feasibility study showed that it would be possible to fully charter a vessel with appropriate freight and safety specifications if we had a minimum of 26 runs and a decent return on passenger sales (80%, early results seem to indicate this is achievable).

A13.  The information from the feasibility study allowed the design of a robust procurement process. Inputs from DFID commercial specialists enabled the government of Pitcairn to settle on an Expression of Interest/Invitation to Tender process (published worldwide - the eventual winner is based in Norway) that contained key procurement features. These were separate technical and commercial panels; inclusion of the scoring methodology in the documents; a Q&A session for bidders with all information published for other bidders; independent marking by the six panel members; and panel discussions about the results. This process delivered two workable options (freight plus passengers) and a final choice. The Government of Pitcairn (GPI) received EOIs from 21 vessels, rather than 5. This produced a genuine competition and ensured best value for money.  The contract with the successful supplier was drawn up by maritime lawyers.

A14.  The successful bidder offered an increase in the number of passenger voyages, but was unable to increase the number on berths, due to maritime regulations regarding the number of available passenger berths on a freighter.  The new service allows for a considerable increase in journeys to/from Pitcairn with the number of passenger voyages almost doubling from 12 to 26, which includes 3 special tours per year to the outlying islands and almost equating to monthly journeys between Pitcairn and Mangareva.  It will continue to provide 4 freight runs between New Zealand and Pitcairn per year; no increase in freight journeys was required as the new ship is able to carry significantly more than its predecessor). However, the successful bid proposes a 45% increase in shipping costs net of potential revenues. This is largely down to an increase in fixed costs of running a full charter service versus a partial one under the previous contract.

A15.  The benefits with this new service are primarily from using a higher quality, newer and better maintained vessel, and more frequent service.  The cost breakdown of the shipping costs is a fixed amount of NZ4.1m for maintaining the ship at anchor and NZ980k for maintaining the cost at sea for the 26 journeys. The ship costs US$7,200 per day or NZ10,940 plus baseline daily fuel costs of NZ384 per day, whether it sits at anchor or is sailing. The only difference in cost if it is sailing is the additional cost of fuel. We break even on the additional fuel costs at sea for the Mangareva to Pitcairn service if three passenger seats are sold on each run. Assuming fixed costs of the shipping service are covered through Financial Aid over the period of the contract, maximising revenues to cover the variable sea costs by running services where more than the minimum passenger seats have been sold, makes sense with this new service.

A16. The tourism department are working extremely hard to sell berths. The more that are sold, the more total fuel costs of running the ship (at sea and at anchor) are offset. Total revenues expected if 80% are sold would be NZ1.375m. At present, these revenues revert to the Pitcairn administration and therefore help defray the cost of the shipping. At present, the logic behind the 26 journeys is largely provided by the marine expert following a decision to increase the service in 2015.  Of course, these figures do not take into account the added economic benefits that a regular shipping service brings to the Island economy. Increased homestays, tours and sales of curios all contribute to the Island economy and reduce dependence on GPI jobs – a core objective of any aid intervention. The value for money and cost considerations still need to be carefully monitored.

A17.  The increase in voyages mean that the cost of medical trips to French Polynesia (Pitcairn is able to access the health services on Tahiti) will reduce in next year’s Financial Aid, given that, depending on diagnosis and treatment, patients should be able to be treated and return to Pitcairn more quickly.  The current Health Policy[[1]] provides Pitcairn islanders with subsidised travel for medical purposes and, where necessary, accommodation costs.  Those requiring medical treatment in French Polynesia or New Zealand in the past have often needed to stay off Island for 3 and sometimes 6 months for treatments that lasted a few weeks, resulting in extra accommodation and living costs. With the regular service, it is now possible to return after three or four weeks.  Shorter convalescence/quicker return time for patients in Tahiti will, we estimate, save around $50,000 per annum, possibly more.  The same applies for GPI Council officials attending meetings such as the Joint Ministerial Council or meetings at the South Pacific Community in New Caledonia.  And children at boarding school in New Zealand will now have the opportunity to return home for longer holidays, something not previously possible meaning it could be years before they were able to see their parents again.
[[1]] Pitcairn Government Health Policy
A18.  Pitcairn is a popular and growing tourist destination for the ardent traveller.  To increase revenue from fare sales, there are two tours planned this year.  The first is a fully sold out one-week tour to Oeno to see the full solar eclipse on 2 July 2019, with passengers paying NZ$8,250 instead of NZ$5,000 for a regular fare.  In October, there is a 2-week tour to all four islands. This is being sold at NZ$12,995.  GPI shall use the information and data from these two tours to inform their decision making on what tours to run and how to price them in 2020 and beyond. Early indications are promising. The ship is also being used for the Henderson Plastics expedition (the Deputy Governor is leading a group of conservationists and islanders to clean up plastic pollution from Henderson Island, a designated World Heritage Site) in June, with 11 expedition members paying $7,500 for the three-week expedition, which exceeds the 80% target for that time period.
A19.  GPI are also exploring sub-leasing the vessel to reputable NGOs that wish to hire the vessel for scientific expeditions and are aiming to make a small mark up on the base cost of full sales of NZ$5,000 for a week. Further research and marketing are required, but they estimate charging around NZ$125,000 - 150,000 for such a charter. Work on this is scheduled for later in the year – the focus has rightly been on the three non-standard trips (Oeno, Henderson and 4 – Islands)
A20.  The revenue stream for 19/20 should increase to around £740,000 (as opposed to projected revenue of £126,000 in 2018/19).  Over time, the revenue streams from passenger fares and associated charges on island will increase, thus ensuring recovery of some of the increased costs of this enhanced service.  That said, the fixed costs (when the ship is at anchor) accounts for 80% of the overall shipping costs.  While berth capacity is forecast at 80% for the 26 planned journeys (which account for 65% of the shipping costs).

Other Expected Revenue
A21. Domestic revenue performance remains weak, providing less than 10% of the Island’s finances, with increasing opportunities to increase revenue over time when the tourism industry increases. This will be explored over this financial year. Previously revenue was generated by trade with passing ships and the production and marketing of stamps and commemorative coins, through agents in New Zealand. However, changes to trade routes in the last three decades have seen a marked reduction in the number of ships passing Pitcairn. Similarly, sales of stamps and commemorative coins have been declining steadily since the 1990s. Consequently, the accumulated reserves of the island were consumed by 2004, requiring the island to seek financial assistance from HMG to meet its reasonable assistance needs.

A22. Tourism continues to be a potential growth area and concerted efforts are being made to market Pitcairn as a tourist destination. Visitor numbers, travelling from Mangareva on the supply vessel, have increased significantly in recent years and the new shipping schedule with increased number of voyages should help meet the demand (which has outstripped supply). There are 12 homeowners who provide home stay facilities and pay an annual fee of US$50 to the Tourism Department. Given the probable increase in tourists using these facilities with the new shipping service, options will be explored around introduction of a tourist tax and increasing the annual fee paid by the homestay providers.

A23. Other key revenue strands recorded during 2018/19 continue to show a mix of results with a projected net income of NZ$583,000:

Stamps and Commemorative Coins: collectively these recorded a net loss of NZ$49,500 as the number of philatelists and coin collectors, globally, diminishes. The Deputy Governor and PIO have examined how revenues can be increased with a tender for a combined stamps and coins contract issued in late 2018.

Passenger fares and landing fees: These collectively raised NZ$325,000. Pitcairn attracts several cruise ships during the austral summer[6]. Whether passengers can land using the new breakwater facilities (which will be enhanced by a dedicated ship to shore vessel being procured with EDF10 funds) remains weather dependent and at the discretion of the ships’ captains. The islanders continue to work to increase the number of cruise ships visits and encourage visits by yachts through actively promoting Pitcairn, through attendance at various events, contact with operators in the region and via agents for Europe, Asia and Australasia. However, there are concerns that cruise ship routes are also changing with some of the ships scheduled to visit Pitcairn choosing not to stop or land passengers. The decision to stop/land passengers rests with the ship’s captain and is out with the control of the islanders; the situation continues to be monitored. With the new shipping service, passenger fare revenues in 19/20 are expected to increase significantly because of the new schedule which, assuming occupancy rates of 80%, will rise from NZ$235,000 to $1,375,000.
[6] http://www.visitpitcairn.pn/cruise_ships/cruise_ship_schedule/index.html

Internet domain registration has continued to flourish (mainly due to The Hunger Games film anthology, which uses the .pn domain as the “official” country code of the nation of Panem) with sales raising NZ$70,000.

Other income (i.e. rent from government buildings, telephone and electricity charges) raised a further NZ$237,500.

A24. Islanders pay contributions for two utilities (electricity and phone/internet access). Small revenues are generated from: (i) hiring of government equipment; (ii) nursery sales; and (iii) prescription charges and other medical fees. New businesses pay a small registration fee.

Employment
A25. Salaries for GPI posts, pensions and child benefit continue to account for a high proportion of annual on-island expenditure. HMG has raised concerns in recent years about capacity of the small island workforce given the tendency to create new posts. The proliferation of posts has now been largely addressed, but capacity issues remain, given the aging and shrinking population. There are currently 27 people in paid employment on Pitcairn between them carrying out 74 Government of Pitcairn posts on a part time basis (including 13 ad-hoc roles). This equates to 9.8 FTE, at a cost of around £116,658. The Administrator continues to work with the Mayor to keep the number of posts under review.

European Development Funds (EDF)
A26. Pitcairn has received EDF in recent years, provided as budget support direct to GPI, through PIO. Under EDF11 Pitcairn is expected to receive €2.4m. During any implementation period following the UK’s departure from the EU, OTs would continue to be able to access these funds in the same way they do at present. In the event of no deal, the UK government will guarantee funding for specific EU projects over their lifetime, should it be required; further details are set out in the Technical Notice[7], which was published on 12 October 2018.
[7] https://www.gov.uk/government/publications/funding-for-british-overseas-territories-if-theres-no-brexit-deal/funding-for-british-overseas-territories-if-theres-no-brexit-deal

Taxation
A27. The hourly wage paid to islanders employed by GPI is NZ$10 (roughly equivalent to UK £5.40, compared to the UK minimum wage for over 25s of £8.21 from April 2019). By contrast, the cost of the many essential goods which must be imported from New Zealand is high, as is the cost of travel off the island, for example for subsidised medical treatment, islanders are still required to pay for passage on the ship, followed by a flight to the hospital in Tahiti.

A28. There is no basis in the existing law of Pitcairn requiring a declaration of private earnings. Nor is there a requirement to contribute to governmental services (proportionate to income). Residents are reluctant to declare income they make from the sales of local crafts and this is impossible to track – bar through the few ships that share the records of credit card transactions with the Islanders. These amounts are not insignificant, with some curios (e.g. large-scale models of the HMS Bounty selling for to £100 - £200 each). PIO advises it banks around NZ$100,000 a year from money deposited with the Government Treasurer. And the increased tourism income will no doubt increase non-salaried incomes to many on the island spending on accommodation and food.

A29. The Divisional Manager for Economics and Finance is undertaking analysis of household income, generated from GPI and EU funded project work as well as private income such as homestays to determine whether there is scope to seek a salary increase and introducing a taxation threshold for those who earn more than NZ$17,000.

A30. On other islands with economies like Pitcairn’s (where information on incomes is hard to capture without a system of employment and PAYE, and where there is lot of subsistence living and self-employment), VAT or General Sales Tax (GST) is often used to raise revenue. Introducing GST would not solve the problem as:
- it could only be collected from a limited number of payments such as the shop receipts, and possibly charges made for homestays.
- this could encourage direct orders from New Zealand, to avoid being taxed.
- the cost of implementing GST laws and processes will likely outweigh the revenue for such a small community.

A31. With the onset of the new shipping service, Pitkerners are due to earn additional tourism income specifically by the accommodation providers on the island, who will see increases to their incomes from the near 50% increase in tourism. The increased number of journeys will enhance non-salaried incomes of many of the families on the island. HMG will begin discussions with Pitkerners on the potential for taxation from tourists driven activities before the next Financial Aid year.
Appraisal Case

B1. Given HMG’s responsibility to ensure Pitcairn’s reasonable assistance needs are met, feasible options to address this need are limited:

Option 1 - End Financial Aid: Without financial aid public services would collapse and the islanders would have to return to basic subsistence or leave the island. This option is ruled out because it would not meet the reasonable assistance needs
Option 2 - Take direct control of Pitcairn’s budget and adopt a projectised approach: This option is excluded because: (i) DFID would be required to devote substantially increased levels of administrative resource to ensure effective delivery; ii) DFID would hold all of the political and reputational risk without adequate control of implementation in the local context; and iii) it is very unlikely that it would deliver value for money for the UK tax payer in terms of the cost of public service provision
Option 3 - Devolve financial control to Pitcairn Island Office (PIO): this option would provide some value for money while leaving DFID still holding most of the political and reputational risk
Option 4 - Devolve control to Pitcairn Island Council: this option is discarded as carrying too high a fiduciary and operational risk for DFID and HMG more widely.
Option 5 - Provide Financial Aid (preferred option): The provision of financial aid is the only acceptable option as it provides the correct balance between direct engagement with PIO and Council as well as HMG oversight to ensure value for money.

B2. Theory of Change for Preferred Option: Financial Aid:

Outputs
1. Sustained budget management, in line with best practice
2. Public Service Provision maintained.
3. Regular, safe and reliable sea access to Pitcairn.
Processes
Annual financial aid review agrees budget settlement and monitors performance against previous budget settlement, as well as mid-year reviews of financial, policy progress and review of progress against log frame targets.
PIO on behalf of Council manages budget efficiently and effectively to deliver public services on island. Critical TA posts filled to ensure continued child safeguarding and provision of basic services
Shipping subsidy covers annual operational costs of the supply ship

Outcome
Efficient and effective management and delivery of public services provision.
Impact
HMG's obligation to maintain Pitcairn's reasonable assistance needs is met in a cost ffective manner.

Assumptions
The main assumptions are:
- No major incidents which impact on government expenditure. This includes diverse exchange rate fluctuations. Evidence - medium
- No major unexpected increase in direct and associated costs pertaining to current island legal proceedings. Evidence - medium
- No more than one emergency medivac per year and/or no more than average costs of routine referrals. Evidence - medium
- Ability to attract and retain suitably qualified professionals. Evidence – medium/high
- Stability in fuel prices Evidence - medium
- Vessels able to land in poor weather. Evidence – medium/high

Inputs
Finance – DFID funding of up to £3.60m. GPI revenues of £0.884m
HR – DFID advisory and programme management.
TA - on island to ensure continued child safeguarding and public service provision. Other TA as required

B3. Financial Aid continues to be the best Value for Money (VfM) option, providing the most efficient method for meeting Pitcairn’s reasonable needs. Our approach to VfM is based on the 4Es: Economy, Efficiency, Effectiveness and Equity.

Economy: The “expatriate” professional posts (policeman, FCA, teacher and doctor) are all recruited from the New Zealand or Australia employment market by PIO on behalf of the government of Pitcairn. Provision and maintenance of a range of basic public services (e.g. electricity, telecommunications, etc.) and provision of part-time public sector employment is also based on New Zealand costs.

Efficiency: The workforce of 27 carries out 74 GPI roles on a part time basis (13 of which are ad-hoc roles). This equates to 9.8 FTE, at a cost of around £116,658. The Administrator continues to work with the Mayor to keep the number of posts under review. The costs of PIO represent 15% of the financial aid costs. Two staff members operate the PIO, which is responsible for all off island logistics, including for example managing and liaising with suppliers and monitoring medical and legal expenditure. PIO also acts as the Treasury for Pitcairn, supporting banking services for the island, producing monthly financial reports. Support costs provided through PIO represent around 63% of PIO’s total costs. The Administrator, has management oversight of all divisional managers, thus improving performance monitoring.

Effectiveness: This intervention is critical to ensure the reasonable assistance needs of Pitcairn continue to be met, including a strong and continued focus on maintaining child safeguarding.

Equity: ensuring that benefits are distributed fairly. Salaries are paid at an hourly rate, ensuring all those employed are paid at same rate, regardless of gender.

B4. A detailed breakdown of the proposed budget is in the Financial Case. It is worth noting that in terms of funds expended on island, this equates to 13% of the financial aid settlement of £3.60m and equates to a per capita spend of £10,891. However, taking the entire budget into consideration, the overall per capita spend for the financial aid settlement increases to £83,720.

Commercial Case

C1. The proposed funding mechanism for support to Pitcairn continues to be Non-Budget Support Financial Aid (Financial Aid). In line with DFID’s Smart Rules, a Memorandum of Understanding (MoU) between DFID and Governor of Pitcairn will be used. As HMG provides 90% to 95% of Pitcairn’s budget requirements, funds will be paid quarterly in advance to PIO on receipt of call down requests for funds against the MOU, countersigned by the Governor’s Office.

C2. Government posts being funded through Financial Aid are open to fair and transparent competition with oversight of the process being provided by the Governor’s Office and the Administrator on island, including interviewing prospective candidates. Proposals for any new posts in the government structure must be agreed by DFID before competition takes place. Procurement of goods and services is managed by PIO in line with the agreement reached in 2010 when the new Constitution and new governance structure came into play.

C3. To recruit long term international technical assistance, PIO advertises in national New Zealand media as well as with key New Zealand Government departments (for police posts). If necessary the teacher, doctor and FCA posts will be advertised across a wider geographic region, including Australia and UK.

C4. The current island workforce, together with the expatriate professionals, can deliver the range of basic services required for the island. The PIO is responsible for the administration of all financial transactions undertaken of behalf of the government of the Pitcairn Islands and will maintain oversight of the budgets and manage the logistics in getting goods and services to the island.

C5. Following a feasibility study in early 2018, a robust procurement process was undertaken for a new shipping service to Pitcairn with key procurement features – separate technical and commercial panels; inclusion of the scoring methodology in the documents; a Q&A session for bidders with all information published for other bidders; independent marking by the six panel members; and panel discussions about the results. This process delivered two workable options and a final choice. The Bravo Supporter will provide Pitcairn’s new shipping service from 2019, with an increase in the number of passenger voyages from Mangareva Island to Pitcairn from 12 to 23 (with an additional 3 special tours to the outlying islands), while continuing to provide 4 freight runs between NZ and Pitcairn per year. The new service accounts for the largest expenditure (£2.623m) and represents 73% of the overall budget. .

C6. The shipping service is one of Pitcairn’s biggest risks. Part of the voyage to Pitcairn takes place in international waters, so international maritime regulations therefore apply. This is a complex and specialised area, well beyond the Government of Pitcairn Islands collective knowledge and experience. Both the Pitcairn Island Office (PIO) and expert help was sourced (a maritime consultant and specialist maritime lawyers) for the final legal drafting of the contract. That process has highlighted the need for some limited insurance to cover risks and where the responsibilities for passengers lie. The result is that we now are more confident than ever about the risk profile and have the right contacts to consult should there be issues in the future.

C7. We have also agreed with FCO for a review of the shipping service towards the end of the financial year which would cover progress on sales and revenues, what the projections are, and what that should mean for a) the number of rotations offered between Mangareva and Pitcairn, and b) how we approach the renewal negotiations towards the end of the two year period.  GPI has also agreed to look at increasing the ticket price from 2020, and maximizing opportunities to charter the vessel to reputable NGOs.

.

Financial Case
D1. The 2018/19 Financial Aid settlement for Pitcairn is £3.600m, provision for which is made in OTD’s programme (RDEL) budget. The table below provides a breakdown and the upper limit proposed for each area. There may be in year re-profiling of the budget and this will be done by PIO on agreement from DFID.
Expenditure 2019/20		NZ$		ER £ =1.9346
				(19/03/2019)
On island costs
Council		63,000		32,565
Community Division		74,500		38,509
Finance and economics Division		131,613		68,031
Natural Resources Division		13,800		7,133
Operations Division		264,500		136,721
Power Generation		59,600		30,807
Telecommunications		299,000		154,554
Total on island costs		906,013		468,321

GPI Salaries		225,687		116,658
Benefits (pensions/Child Benefit/disability)		73,507		37,996
Total Salaries/Benefits		299,194		154,654

Combined on island costs		1,205,207		622,975

PIO running and support costs		1,059,251		547,530

Recurrent budget deficit (on island and PIO costs)		2,264,458		1,170,505

Shipping		5,074,065		2,622,798

Technical Assistance		1,107,300		572,366

Total expenditure		8,445,823		4,365,669

Anticipated Revenue/Income		(1,710,000)		(883,904)

Capital Expenditure		187,000.00		96,661

		6,922,823		3,578,426
contingency for continued ER flux unexpected expenditure in year		41,737		21,574
Net Financial Aid requirement 2017/18		6,964,560		3,600,000

D2. PIO produces monthly expenditure reports as well as quarterly estimates of projected costs. Exchange rate fluctuations between sterling and NZ dollars will be closely monitored throughout the year to ensure reasonable assistance needs continue to be met. Should there be savings (in NZ$) as a result of sterling appreciation, DFID,GPI and PIO will discuss how this should be utilised or whether it should be returned to DFID. The final decision will rest with DFID.

D3. Running costs include the operation of PIO based in Auckland, New Zealand, which provides a treasury role as well as logistical and management support to the island, plus on island costs such as government of Pitcairn Island salaries and pensions and public services. The support costs account for around 63% of PIO’s costs and include boarding school fees, IT support, medical costs (including supplies and off island costs) and legal costs.

D4. As highlighted in the Commercial Case (paras C5 and C6) a new improved shipping service came into operation in 2019. While this has resulted in increased costs, the corresponding increase in berths available due to more frequent voyages is expected to increase revenues.

D5. The last Fiduciary Risk Assessment (FRA) was in 2016 and concluded that:
- The overall assessment of fiduciary risk is Low to Moderate.
- The assessment of corruption risk is Low and unchanged
- There is a credible programme of reform of PFM, strengthening domestic financial accountability and fighting corruption.

A mitigation strategy is in place and the most pressing of the risks identified in the FRA have been mapped onto the government’s internal risk register so they can be tracked.

The 2018 Annual Statement of Progress (ASP) confirmed the assessment remains stable with no new risks have been identified.

A new FRA will be commissioned during 2019.

D6. Approved recurrent expenditure will be monitored, reported and accounted for as follows:
- The Administrator conducts monthly reviews of the Treasurer’s Office and Post Office with the Island Auditor and New Zealand seconded Police officer. The Island Auditor carries out other periodic checks on the store and warehouse etc. The Administrator is working with the Island Auditor to ensure all financial entities and all Divisions’ assets are systematically audited.
- PIO produces monthly progress reports, comparing actual expenditure against the budget and providing explanations of variances. A more detailed report is provided in October. DFID provides feedback as necessary.
- An annual audit, including an island visit is carried out according to NZ and international standards by External Auditors (an independent firm of chartered accountants based in Auckland). The External Auditors will be expected to add their own comments and qualifications. The draft audited accounts are subject to review and counter signed by the Governor and the Head of the PIO. DFID provides comments on the audit reports.

The PIO is located within the office of the Deputy Governor (in the British Consulate in Auckland). All funding requests made by PIO are countersigned by either the Governor or their deputy who maintains a general monitoring and supervisory overview of PIO’s activities.

Management Case

E1. Daily management of the intervention will be undertaken by PIO with inputs on progress being received from the relevant Divisional Manager and the Pitcairn Island Council. The Deputy Governor, the Administrator on island and FCO’s OTD colleagues will also contribute to the control of the quality and quantity of the outputs for this intervention. The Administrator has management oversight of all divisional managers, thus improving performance monitoring. As outlined in the Financial Case, there are regular reviews of expenditure and DFID monitors progress throughout the year.

E2. The Pitcairn Programme Manager will be Senior Responsible Owner (SRO) for the implementation of the programme, supported by a Programme Officer (PO). The SRO and PO can call on the support of OTD’s Management and Advisory Team including:

- Head and Deputy Head of Department
- Senior Economist
- Social Development Adviser
- Health Adviser
- Governance Adviser

E3. This project will not be delivered under a Partnership Agreement or modality arrangement. However, funds are expected to be used for their intended purposes as laid out in the MOU that will be signed between DFID and the Governor of the Pitcairn Islands. A risk matrix is attached. The overall rating is moderate and therefore within DFID’s risk appetite.

E4. The provision of financial aid does not in itself facilitate a fundamental improvement in the quality or efficiency of service provision. Instead, it is expected to support “business, as usual”, in meeting reasonable assistance needs. Evaluation of this will be carried out at the end of the 12-month project and findings will be recorded in the Project Completion report.

E5. The Delivery Plan, Risk Register, Logframe and Delivery Chain will be updated as necessary throughout the year. All are stored on DFID’s electronic filing system.

PITCAIRN FINANCIAL AID 2019/20 RISKS WITH OWNERS
	Gross risk		Risk Owner		Net risk
Risk Factor	Impact	Likelihood		Mitigating Measures	Impact	Likelihood
1. Exchange rate fluctuation Falls in the £ against NZ$ means value of UK budget support in local currency falls below amount in estimates, resulting in need for additional HMG funds	Major	Possible	DFID (working with PIO)	There is no currency hedging in place. Sterling value has improved in last 12 months. However, to mitigate a fall DFID will include a small funding contingency to increase the £ value of the 2019/20 Pitcairn budget. The ER will be closely monitored throughout the year and discussions held where additional savings within the agreed settlement could be made in the event of a significant fall in the £ against NZ$.	Moderate	Possible
2. Failing standards of public service delivery due to lack of available workforce as a result of a declining population or serious injury	Major	Possible	FCO Administrator (working with Island Council)	As population ages and declines so does the ability to undertake 74 GPI part-time roles required to maintain standards of public service. / The Administrator line manages divisional managers to ensure standards maintained. / If required, the Governor will be asked to sanction introduction of workers in addition to those being funded through EDF to ensure effect delivery of public services.	Moderate	possible
3. Ability to attract and retain suitably qualified professionals	Major	Possible	Governor’s Office (through PIO)	Posts advertised more widely (currently in New Zealand, Australia with UK being considered if necessary)	moderate	unlikely
4. Lapse in child safeguarding measures with less children on island	Major	Unlikely	FCO Administrator (as Children’s Officer) working with HMG	Expatriate professionals continue to be deployed to implement all child safeguarding procedures and protocols, with oversight by HMG. / Regular child safeguarding reviews in place. / Island Council continue to make child safeguarding a priority.	moderate	unlikely
5. Lack of take up of berths on new shipping service, resulting in lack of income thus corresponding need for additional HMG funds	Major	possible	PIO (working with Governor’s Office and HMG)	PIO and Tourism Manager continue to actively promote Pitcairn as a tourist destination.	Moderate	possible