Business Case

Summary Sheet

Title: Strengthening Action Against Corruption Ghana (STAAC-Ghana)
Project Purpose: / To improve implementation of anti-corruption measures in Ghana from scrutiny to punitive action, increasing the risks for those engaging in corrupt activities.
Programme Value: £9.7 million		Country/ Region: Ghana
Project Code:	Start Date: May 2015	End Date: April 2020
Overall programme risk rating:	Medium
Quest Number:

Contents

# Intervention Summary

## What support will the UK provide?

The UK will provide up to £9.7m over five years (2015 – 2020) to improve implementation of anti-corruption measures in Ghana from scrutiny to punitive action, increasing the risks for those engaging in corrupt activities.

## What are the main programme activities?

UK support will be directed to four streams of activity:
1. Provide technical assistance and equipment to key agencies involved in fighting international and domestic financial and economic crime, to address current capacity gaps in relation to intelligence gathering, investigation, prosecution and judicial determination. It will adopt a chain-linked approach to anti-corruption that recognises no single agency can tackle corruption alone.
2. Strengthening the procurement regulatory system to enable a more robust approach to the endemic procurement failures.
3. Provide financial and technical support to leading think tanks, investigative journalists and media organisations to increase scrutiny of corruption through investigation, service delivery tracking, citizen reporting and research, develop robust evidence and analysis and disseminate findings through sustained intelligent media coverage until action is taken.
4. A Strategic and Technical Support Facility to respond to opportunities as they arise. This is likely to include support to government to address system weaknesses that are highlighted through investigations where there is political will to tackle corruption.

## Why is UK support required?

Although corruption in Ghana is commonly perceived to be less pervasive and destructive than in other Sub-Saharan African Countries, national surveys point to a significant deterioration in recent years. Overall trends are negative, with increased grand corruption, endemic and corruption across government and worsening petty corruption. Public perceptions reflect a growing awareness of, and concern about corruption across key sectors of government. With oil production doubling in the next 2 years, the risks of increased corruption are high. Tackling corruption is essential if Ghana is to achieve sustainable and equitable growth.

The UK is recognised as a leading donor on anti-corruption and is able to draw on extensive global experience of anti-corruption efforts. In Ghana, the UK is well placed to support law enforcement activities in part because the structure of the Ghanaian Law Enforcement Agencies and the judicial system are closely aligned to the UK and in part because of the close collaboration that already exists. DFID Ghana is also a key partner on civil society and citizens’ engagement in Ghana and the largest funder and strategic leader on Ghana’s flagship civil society programme, Strengthening Transparency, Accountability and Responsiveness in Ghana (STAR-Ghana).

## What are the expected results?

The results will be:
1. Improved identification and handling of corruption risks and cases by key oversight agencies.
2. More effective intelligence gathering and dissemination, financial crimes investigations and prosecutions.
3. Civil society strengthened to proactively engage with corruption issues and delivering substantive and sustained analysis and advocacy.

These will contribute to the outcome of strengthened anti-corruption and accountability institutions working together to tackle corruption more effectively.

The intended impact is more effective implementation of anti-corruption measures from scrutiny to punitive action, increasing the risks for those engaging in corrupt activities. This will contribute to reducing the impact of corruption on the poor in Ghana, both directly in terms of bribery and improved access to services and indirectly through reduced diversion of public resources.

## How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

Tackling corruption is a Ministerial priority and is clearly set out in the DFID Business Plan 2011-2015. It is highlighted in the 2012 ICAI report on corruption as critical. This programme also responds to the 2014 ICAI report which recommends that DFID should include in an expanded anti-corruption portfolio more programmes which specifically target the everyday corruption experienced by the poor and educate the population about the ill effects of corruption.

The DFID Ghana Operational Plan focuses on wealth creation, governance and accountability and human development. These areas are key challenges for Ghana’s future development aspirations and eventual graduation from aid. One of the key risks identified in achieving the goals set out in the Operational Plan and the Government of Ghana’s aims is increasing levels of corruption in Ghana. The programme is part of the action plan for DFID Ghana’s Anti-Corruption Strategy 2013-5.

Strengthening Action Against Corruption Ghana (STAAC-Ghana) complements other DFID Ghana governance programming, which engages in key areas that are important to the prevention of corruption, including public financial management, revenue reform, public sector reform, empowering citizens to hold the government to account and enhancing parliamentary scrutiny of spending, and strengthening oversight, enhancing regulation and improving revenue management of the oil and gas sector. This portfolio of programmes is implemented in close coordination with other HMG departments, in particular with FCO, NCA and UKTI.

## What are the key risks to the success of the programme?
The overall risk rating for this programme is Medium. Fiduciary and management risks are Low. The main risks are clustered around political support and institutional incentives:
- Political will and interference
- Strength of government partners and willingness of civil society partners to directly challenge entrenched elite interests
- Behavioural change – aimed at stopping officials requesting and accepting bribes and also citizens paying bribes - this sort of change takes time, and will not be fully achieved during the lifespan of this programme.

# Strategic Case
## A. Context and need for intervention[1]
[1] The strategic case is based on detailed and documented design work. Documented in QUEST file number 4572531.

#### Corruption challenges
  1. Progress in building democratic institutions and oversight functions in Ghana has not delivered the depth of corruption resistance, the quality of accountability or pace of reform that might have been expected. In particular, inefficiencies and financial management weaknesses undermine an effective fight against corruption in the public sector. Significant leakage of public funds is contributing to a growing economic crisis and the reduction in and quality of the delivery of public services.

  1. Political space is good by Sub-Saharan standards. Ghana has numerous political parties and various leaders regularly express views and opinions. During the last two decades, this has led to a stable political settlement around two major parties, the National Democratic Congress (NDC) and the National Patriotic Party (NPP). Elections are hard-fought along neo-patrimonial lines, with limited focus on substance or ideology. The patrimonial system puts pressure on office holders to accumulate state resources to reward their supporters and enable them to stay in power, driving political parties to do almost anything to win.

  1. Levels of ‘bureaucratic’ or ‘petty’ corruption are increasing. Corruption in interactions between low-to-mid level government officials and citizens encompasses bribes changing hands to avoid red-tape and speed up administrative procedures; to by-pass regulations (such as tax, customs assessments and traffic violations) or to obtain preferential treatment (in jobs for instance). It also includes illegal fees charged to citizens for accessing services such as connection to utilities, the acquisition of permits, health or education, including where these services are supposed to be free at the point of delivery. Petty corruption may only involve small sums but it is the form of corruption that most directly affects ordinary citizens.

  1. Grand corruption is also increasing and becoming increasingly predatory. The political process has come to be associated with competition for state capture. Windfall oil and gas revenue has created a wide range of opportunities for patronage and increased expectations on the part of supporters[2]. More favours are required to be granted to appease supporters as well as opponents, resulting in ever greater opportunities for corruption.
    [2] Many have argued that a consequence of rent seeking is poor economic performance among countries with abundant natural resources (Auty 2001: 3, Ross, 1999). Their arguments resonate again in Collier’s writing that natural resources are nothing more than a trap, in effect, a curse (Collier 2007: 38-52, Gelb and Associates 1998). Auty (1995: 19), in a later book, suggests that politicians receive resource rents and then waste the earnings. In regression after regression, Sachs and Warner correlations on abundant natural resources with poor economic performance (Sachs and Warner 1997, Sachs and Warner 1999, Sachs and Warner 2001). Auty and Pontara (2008) suggest the leadership of resource abundant economy can do little to avoid what they call “the staple trap”. The staple trap model asserts that rent seeking lowers capital accumulation necessary for sustainable economic growth (Auty and Pontara 2008: 59, Auty and Gelb 2001: 126-144). Acemoglu and Robinson (2012) have clearly analyzed the high costs to any society when rulers govern through what they call “extractive institutions.”

#### Anti-corruption institutions
  1. Although Ghana’s anti-corruption framework is moderately developed, its implementation is very weak[3]. The main anti-corruption bodies, Commission for Human Rights and Administrative Justice (CHRAJ) and Economic and Organised Crime Office (EOCO), have not successfully concluded a single major corruption case in the last 5 years. Anti-corruption institutions face a range of challenges including their own institutional weaknesses, an operating environment with minimal accountability and political and social barriers that block effective action. Media and civil society is vibrant, but not strategic leading to a situation of transparency without accountability.
    [3] 2011 Global Integrity Report: Ghana’s legal framework scores 79 point out of 100, but its actual implementation scores only 54 points.
#### The impact of corruption
  1. Corruption is a brake on economic development and a contributing factor to increasing inequality, a burden for the poor and a waste of valuable and limited resources. It poses a serious development challenge in Ghana, risking the country’s future development aspirations.[4]. The lack of trust in public institutions and public officials weakens the state citizen relationship and undermines democracy. There is a risk of a perfect storm, with oil revenues reducing accountability and undermining progress already made, thereby posing a risk to overall development and other DFID-objectives.
    [4] “The continent must embark on reforms to capture currently unexplored or poorly managed resources. This includes curtailing illicit financial flows and rather transforming those funds into a powerful tool for enhancing domestic resource mobilization, as a way of furthering the continent’s development,” said Carlos Lopes, Executive Secretary, of the Economic Commission for Africa, organiser of the ADF. Reported by CitiFM on 3 December 2014. http://www.citifmonline.com/2014/10/27/africa-has-to-block-illicit-financial-flows-for-real-development/#sthash.OVbETFKJ.dpuf

#### Corruption trends and Opportunities for reform
  1. Within an overall negative trend there are a number of reform drivers and opportunites. The emerging economic crisis is driving further public engagement. Media are free and widespread. Technology, incl. smartphones is relatively widespread, especially in urban areas. Ghana’s civil society are relatively strong in terms of capacity, but have traditionally not engaged very directly. Driven by crisis and an urban middle class who are increasingly expecting better governance and accountability.

#### Gender Regard Statement
  1. A 2008 NORAD-funded review[5] of the literature on corruption found very little empirical research on gender and corruption. In 2009, the Danish government commissioned a gender analysis of corruption in Uganda. This noted that the lack of gender-disaggregated data makes assessing the potential for gender-informed approaches extremely difficult. Research and evaluation undertaken within this programme will ensure that data is gender disaggregated.
    [5] Nordic Consulting group (NCG).
  2. A World Bank study on 150 countries concluded that women are more trustworthy and less prone to corruption than men. Transparency International’s Global Corruption barometer has consistently found that women are less likely than men to pay bribes. One explanation is that men and women have different risk–taking tendencies, which account for how they experience and deal with corruption. However, the 2012 U4 literature review on gender gaps in corruption did not find a substantive correlation in terms of the relationship between gender and institutional corruption.
  3. UNIFEM has presented quantitative evidence that women are more likely than men to perceive high levels of corruption and to feel that their lives are affected by it. They found these differences to be statistically significant and consistent across most regions[6].
    [6] Corruption, Accountability and Gender: Understanding the Connections; UNDP and UNIFEM 2010.
  4. There is wide agreement that women are more vulnerable to corruption in service delivery, particularly in health; and that corruption has a disproportionate effect on women, and poor women in particular. Women and children suffer disproportionately from public sector corruption which results in a lack of or poor quality basic services such as healthcare, education, water and energy, including in terms of opportunity costs. Bribes demanded for accessing services, such as charges for results, are a barrier in themselves, but can lead to even worse forms of abuse such as sex demanded in lieu of cash. Women and girls are put in extremely vulnerable positions, which compromise their voice, choice and control. This form of disempowerment negates progress on gender equality.
  5. Women are particularly badly affected by corruption in the health sector as they are likely to access health services during pregnancy and childbirth. The health sector in Ghana has been particularly badly hit by corruption at all levels. All contribute to creating a highly ineffective health system that serves the women of Ghana particularly badly. A high incidence of bribery in the health sector also discourages women from seeking assistance during pregnancy and childbirth.
  6. The impact of corruption is not restricted to delivery of basic services. Women and girls do not have the high levels of social capital and cash required to seek redress in the justice system affecting their access to justice, which is especially significant in relation to crimes of a sexual nature. The barriers posed by corruption to doing business also have a greater impact on women-owned businesses, hindering women’s economic empowerment.
  7. STAAC-Ghana intends to increase the risks for those engaged in corrupt activities, resulting in a reduction in the incidence of corruption at all levels. This will have a disproportionately positive impact upon women. As part of the design appraisal, consideration was given to a focus on specific sectors including health, education and the business environment but no suitable entry points were identified. Flexibility has been built into the design of this programme to enable this to be revisited if opportunities arise.

#### Overseas Security and Justice Assessment
This project has been assessed as Green (less than serious risk), against the Overseas Security and Justice Assessment guidance[7]. The context will be regularly monitored during programme implementation and a human rights risk assessment will be built into the evaluation process.
[7] Documented in QUEST file number 4876308.

## B. DFID’s Objectives and Comparative Advantage

  1. Tackling corruption is a Ministerial priority and is set out in the DFID Business Plan 2011-2015 and DFID’s Partnership Principles for support to government. It is highlighted in the 2012 and 2014 ICAI assessments of DFID corruption work.

  1. The DFID Ghana Operational Plan focuses on wealth creation, governance and accountability and human development. One of the key risks identified in achieving the goals set out in the Operational Plan and the Government of Ghana’s aims is increasing levels of corruption in Ghana. The DFID Fiduciary Risk Assessment 2014 assessed the fiduciary risk as persistently substantial and assessed corruption risks as high and persisting. The DFID-Ghana 2013 Anti-Corruption Strategy states priorities in addressing corruption in Ghana.

  1. Historically Ghana has had strong social and political ties to the UK. The legal system is based on the British system. Globally, the UK plays a crucial role in addressing money-laundering.

  1. DFID will work closely with key donor partners to ensure programming is complementary, identify top anti-corruption priorities. We continue to work with centrally-managed funding to multilateral anti-money laundering programmes, including the work undertaken by the IMF, World Bank and the Eastern and Southern African Anti-Money Laundering Group (ESAAMLG), in anti-money laundering and countering terrorist financing.

# Appraisal Case
## A - Feasible options

Programme Options considered
Option 1	Supply-side focus
Option 2	Demand-side focus
Option 3	Balanced support to demand and supply sides
Option 4	Do Nothing

## B. Appraisal of each feasible option programme
2.1 As part of the pre-appraisal, consideration was also given to support to Commission for Human Rights and Administrative Justice (CHRAJ) and the National Anti-Corruption Action Plan (NACAP). This has been saved on Quest and is available on request. Both options were gauged to be clearly sub-optimal and not analysed further.

2.2 A brief outline of the proposed options is considered in the following section, including the benefits and disadvantages of each. Our design work explored each feasible option in detail and is available on request.

#### Option 1 - Support to key national oversight agencies (the “supply” side)
2.3 The approach aims to provide support to all aspects of the anti-corruption chain – deterrence, detection and sanctioning. This approach places increased emphasis on coordination. The proposed ways of achieving better coordination amongst institutions is through joint training, regular issue-based meetings and pooled technical assistance to support joint priorities.

2.4 This option would provide a mix of technical assistance (both long-term embedded and short term), facilitation, training, equipment and limited externally-managed operational funding to improve the implementation of critical functions across the anti-corruption chain:
1. Intelligence gathering: Support to enhance the AML/CFT regime that is still in its infancy.
2. Criminal Sanctions (Investigation, Prosecution): Support for prosecution-led investigations implemented by joint teams (investigators and prosecutors), improved case management, enhanced technical investigation skills, witness protection and preparation, asset tracing and recovery.
3. Enhanced Judicial Performance: The focus would be on building the capacity of the judiciary in handling anti-corruption, economic and financial crime cases empowering the judiciary to be efficient in the delivery of justice in corruption and financial crimes cases.
4. Coordination across the anti-corruption chain: This will include joint work on specific core activities audit, intelligence, prosecution, judicial procedures. The focus would be on specific problem solving rather than on general coordination.
5. Improved procurement regulation and oversight: This would focus on strengthening the procurement regulatory system as a deterrent to fraud and corruption.
2.5 The proposed support to key oversight agencies would go beyond current donor efforts of donating resources and one-off training courses, to include hands-on capacity strengthening, longer-term provision of high quality expertise, and more sustainable transfer of technical skills.
2.6 By employing this chain-linked approach this programme should: recover stolen assets; increase the sanctioning of public service corruption and financial mismanagement; and ensure that more people are speedily and effectively dealt with by the criminal justice system. These results should increase deterrence by increasing the risks you will be caught and sanctioned and your assets confiscated[8], and thereby contribute towards long-term behavioural change within the public service.
[8] Becker emphasizes that individuals assess risks of being caught, potential sanctions, and weigh these variables against payoffs from dishonest action (1968: 184). Punishments have a deterrent effect on criminals’ calculations of a probability of being caught and whether it is worth committing a crime.

2.7 Public procurement, one of the largest areas of public spending[9], gives public officials wide discretion. Addressing corruption taking place in public procurement will have a positive impact on democratic party competition, provision of public goods, and economic development. Wider procurement reform will be picked up in the PFM programme.
[9] Expenditure of public procurement in Ghana represents between 50-70% of the government’s budget – sourced from PPA.
2.8 The UK is well placed to help in part because the structure of the Ghanaian Law Enforcement Agencies and the judicial system are more closely aligned to the UK than any other country. The legislation in place often mirrors that of the UK. The Justice Advisor based in the High Commission has managed to generate strong relationships with counterparts in the Ghanaian law enforcement agencies which this programme will seek to build on. Based on his advice, a secondment from the Crown Prosecution Service will be requested.

2.9 Taking a narrow focus on oversight institutions would keep the programme structure simple, and allow for concentrated effort but therefore have a more limited impact. It would fail to strengthen external demands on government, which are a critical part of motivating action. It does not tackle corruption in a way that will be felt directly by the poor, though recovered revenues would potentially improve service delivery. Procurement could focus on corruption vulnerabilities in key sectors that impact the most on citizens, such as health and education, but the results would be limited.
#### Option 2 - Support to citizen engagement and civil society to address petty and bureaucratic corruption (the “demand” side)
2.10 In this option, the emphasis would be placed on creating pressure on government to deliver improvements in preventing and addressing corruption. The approach would be to encourage intelligent public engagement and scrutiny through multiple strands of activity.
2.11 Option 2 assumes there are fewer opportunities for reform in state institutions because political leaders and stakeholders are content with the status quo and that whatever technical gaps exist can be overcome through other donor-supported programmes.
2.12 DFID will proactively identify issues in consultation with partners and work with them to ensure advocacy and oversight is based on high quality, evidence-based analysis and is well-targeted. Without proactive engagement there is a strong risk that activities will not be sustained sufficiently to deliver change.
2.13 This option would provide technical assistance and financial support to expand work undertaken by think tanks, CSOs and the media to monitor and report on the extent and modalities of corruption in Ghana and Government performance in relation to preventing and addressing corruption. Indicative activities include:
- Research: Including a survey on social norms and attitudes to corruption will be undertaken to get a better sense of the factors that influence petty corruption behaviours in Ghana from the perspective of ordinary citizens and officials. The findings will also be fed into DFID’s Anti-Corruption Evidence programme (ACE) and the qualitative research commissioned by DFID’s East Africa Research Hub on corruption attitudes and behaviours in East Africa. Building on Afrobarometer data, a survey to generate evidence on experiences of corruption among different segments of the Ghanaian society, including Ghanaian households to track ordinary citizen experiences, and corporate firms and professional elites to document business/corporate corrupt practices, will be conducted.
- Encouraging citizen engagement: This programme will include channels for reporting bribes demanded that provide anonymity, are simple to use, excite interest, use technology creatively, are low cost, minimise opportunity costs, and that “go with the grain”. The programme will also enable citizens to highlight good performers in public service. The failure of previous citizen reporting initiatives will be addressed by ensuring a robust feedback loop. It is envisaged that this would occur through three main paths: i) intelligent and sustained media coverage; ii) evidenced-based reports by think tanks and investigative journalists; and iii) submitted to law enforcement agencies as appropriate.
- Enhancing investigative journalism and research: focused on developing robust evidence and presenting the findings graphically to highlight the cost of corruption. Technical assistance and opportunities to partner with respected international advocacy institutions will be explored to build capacity and enhance the quality of products. The programme will also look to build a platform for dialogue between accountability agencies and civil society to improve accountability and share information.
- Advocacy: Civil society will be supported to monitor, review, and publicise the post-enactment enforcement and implementation of key pieces of anticorruption legislation. The programme will also bring to bear the influence of opinion leaders, traditional authority, religious leaders and other influential individuals to change attitudes and behaviours in relation to corruption.
- Media engagement: The programme will work with think tanks and the media to increase the quality and quantity of coverage of corruption and ensure sustained and intelligent coverage of corruption issues. This will include consideration of buying airtime across TV networks for a regular programme to air issues that have been identified through the research and monitoring strands of the programme. Evidence of corruption will be shared with relevant government agencies and professional bodies prior to disclosure to offer opportunities for them to respond or to commit to efforts to address the issues highlighted, and these will also be communicated in the TV programme and followed in subsequent shows.

2.14 As with Option 1, a narrow focus on accountability opinion formers would keep the programme structure simple, and allow for concentrated effort but therefore more limited impact. There is scope to target corruption in specific sectors where the public are most directly affected to build pressure for change. However, it would fail to strengthen technical capacity to enable government to address corruption. The lack of government capability to take action in response to enhanced awareness of corruption will most likely result in citizen fatigue and may even undermine the state-citizen relationship and democracy further.

#### Option 3 – Comprehensive support to the supply and demand side to improve scrutiny and enforcement of anti-corruption
2.15 Option 3 is divided into two key components combining strategic interventions in building supply-side public institutions (outlined in Option 1), with a more responsive and opportunistic element that supports demand-side accountability and empowerment actors (outlined in Option 2). These components will be complemented by a “Strategic and Technical Support Facility” (STSF – a rapid response fund) which will seek to identify further opportunities for supporting reform efforts and enhance synergies opened up by supporting both the supply and the demand side, such as constructive efforts to address identified opportunities for corruption.

2.16 A rapid response fund enables swift support to be provided to critical ad hoc requests and opportunities for delivering change as they arise. The approach recognises the value of maintaining flexibility, so that support can be adjusted as the political environment dictates and the programme progresses to ensure sufficient agility to respond to new opportunities where entry points present themselves for game-changing activities to happen.

2.17 The STSF will support four main components:
i) corruption trend analysis, improving the generation and analysis of local data to help guide anti-corruption efforts. This will build on and respond to gaps identified in the research proposed in Option 2.
ii) civil society/private sector dialogue, supporting coalitions and dialogue with government on systemic corruption issues of concern. Funding to CSOs as envisaged under Option 2 will be channelled through the STSF.
iii) advisory inputs and small scale financial aid – a demand driven resource to enable government to mitigate corruption risk, enabling a constructive response to the identification of corruption through the programme.
iv) Dialogue and external engagement - to facilitate a joint approach among international partners on anti-corruption and support government activity on priority areas for action, for example key legislation; to engage with the private sector on anti-corruption, for example, supporting common assessments and diagnostic work.

2.18 Generating ‘demand’ from society for ethical governance is the essential corollary to technical solutions on the ‘supply’ side. This option offers a ‘sandwich’ approach - with government in the middle responding to pressure from within/below from civil society and from without/above from international standards and the international community. It will support a closer relationship between government and civil society, state and citizenry, creating constructive relationships to increase accountability and collectively solve problems.

2.19 ‘Petty’ or ‘bureaucratic’ corruption appears to affect poor people more directly, but in some ways this is a false choice as ‘grand corruption’ (corruption by the political elites and large scale asset flight) can be equally or more draining of state resources. To tackle one end without attention to the other creates perverse impressions: tackling only petty corruption leaves the impression that leaders can get away with it; tackling only grand corruption leaves citizens still enduring the daily obstacles of officialdom. Corruption needs to be addressed along the entire spectrum.

2.20 Taking a more holistic approach that balances support to the supply and demand sides and programmatic and non-programmatic approaches to address both petty and grand corruption would be the most complicated to manage. However, it would be addressing all three of the factors identified as important in the theory of change, and as such would leverage the most pressure for change. It would also spread programme risk, so that if one area was making limited progress, more attention could be given to others that were showing more traction. The rapid response fund would be a critical element in developing synergies between the demand and the supply side interventions.

#### Option 4 - Do nothing (Counterfactual)
2.21 The do nothing scenario is the base case against which other options will be considered. Consideration was given to whether an anti-corruption programme should be designed and implemented or whether no further action should be taken. The ‘do nothing’ option assumes that:
1. Government of Ghana measures will be sufficient to build capacity of anti-corruption agencies and support the transformation to a locally accountable society;
2. Existing programmes and other donors will deliver sufficient support;
3. Or that it is impossible to make a meaningful impact on corruption given the political economy.

2.22 These are unlikely to hold true. Government entities have little incentive to change from the inside due to vested interests. Existing support is unsystematic and does not cover the areas identified as important for addressing corruption. The proposed interventions and results are based on an assessment of what is possible and realistic within the current context – strategically focusing on opportunities and working with progressive partners.

2.23 The consequences of not intervening, and should corruption run unchecked, include reversing gains to date, debilitation of service delivery and subsequent threat to MDG goals, fostering growing income inequality, and undermining democracy. Windfall oil and gas revenues have the potential to significantly exacerbate these risks.

Option 3 is the preferred Option.

## C. Evidence

2.24 The evidence of effectiveness of anti-corruption support is medium.

2.25 Overall there is a relative lack of evidence regarding the most effective strategies for fighting corruption[10] so it is difficult to establish a strong evidence base. Most success stories are case specific and based on qualitative evidence of impact. For rating these options we have drawn on extensive lessons learned from DFID’s central Financial Accountability and Anti-corruption Team (FACT) as well as lessons from other country offices. Additionally there are a number of reviews of the evidence base for “what works” in tackling corruption[11].
[10] Review of the State of Evidence on Anti-Corruption Interventions, 2012, U4
[11] Joint Evaluation of Support to Anti-Corruption Efforts 2002-2009, 2009, DFID, Norad, Sida, Danida and ADB; Review of the State of Evidence on Anti-Corruption Interventions, 2012, U4

2.26 There are three relevant studies that have been carried out. The first, a DFID commissioned systematic review of the effectiveness of anti-corruption approaches, tentatively concludes that prospects for success are greatest when oversight is combined with strengthened incentives not to be corrupt (such as performance related pay), and that oversight is most powerful when it is capable of both detecting and sanctioning corruption[12]. The second is a 2011 Joint Evaluation of Anti-Corruption Effectiveness (JEACE) sponsored by DFID and other partners. This draws on five country case studies and is more of a qualitative evaluation, examining a variety of programmes. The JEACE suggests that a comprehensive, system-wide approach to tackling corruption has the greatest prospect of success, and identifies the following as important for impact: stronger working across oversight institutions; the incorporation of anti-corruption in sectors and wider reform programmes such as public financial management; greater engagement of civil society; and more use by donors of international analysis and dialogue with government. A 2012 U4 study of the strength of evidence available on the impact of anti-corruption interventions found little evidence to back up an approach that cherry picks support to any one specific agency involved in tackling corruption, instead calling for a focus on “the interactions and interdependencies between different anti-corruption interventions[13].
[12] Hanna, R., Bishop, S., Durlacher, K., Nadel, S., Scheffler, G. 2010. ‘The Effectiveness of Anti-Corruption Policy: What has worked, what hasn’t, and what we don’t know – A Systematic Review Protocol,’ DFID Systematic Review
[13] Review of the State of Evidence on Anti-Corruption Interventions, 2012, U4

2.27 We have also drawn on the global evidence that informs DFID’s theory of change for empowerment and accountability. Key summary findings relevant for this programme include:
- Context matters – interventions are likely to have different impacts in different contexts (Gaventa and McGee 2013)
- Information by itself is not sufficient to promote accountability (Barr et al 2012)
- Bottom-up monitoring lacks bite unless it is linked to higher level enforcement mechanisms (Joshi 2013)

## D. Appraisal of Feasible Programme Delivery Mechanisms for preferred option

2.28 As part of the appraisal of options, it was clear that the programme of support proposed will need to be operated in a flexible way to make the most of opportunities as they arise, as well as to allow it to slow down work in areas where blockages are placed in the path of progress. This stop/start approach doesn’t always fit well with DFID programmatic requirements, so the choice of the right management and delivery options will be critical.

2.29 As part of the political economy analysis it was clear that a purely technocratic approach to tackling corruption will not succeed. The preferred option also requires a proactive approach to identify key focus areas and to work on them with CSOs and oversight bodies to ensure advocacy and oversight is based on high quality, evidence-based analysis and is well-targeted. This will require extensive strategic management by DFID, especially in the initial years of implementation.

2.30 Other considerations informing the appraisal of options were i) opportunity for partners to take responsibility and ownership and ii) fiduciary risk.

2.31 Three main options were considered as part of the appraisal:
- Option 1 – Direct support. Under this option non-budget financial aid and accountable grants would be provided directly to each agency on the basis of agreed plans and timeframes. Full management and financial accounting would be undertaken by the host agency. This option would contribute to host organisations taking ownership and responsibility and would build capacity to manage Technical Advisors (TA). However given the range of agencies proposed this would be operationally complex and require significant supervision by DFID. A number of potential partners are new to DFID with untested financial management capacity.
- Option 2 – Managing agent. This option would not be the usual service provider model that DFID often utilises but would only contract the management responsibilities out on a commercial basis through a competitive tender agreement. The managing agent would be responsible for the provision of TA and management of the STSF. Under this option, grants to CSO partners would be paid from the STSF. DFID would maintain the strategic management of the programme, finance the Justice Advisor from the Crown Prosecutions Service (CPS) and make disbursements to government directly. This option would provide clarity of management responsibility and confidence in financial management but would be slow in start-up. It would also provide the flexibility needed to manage changes to requirements and personnel.
- Option 3 – Direct management by DFID. This option would include: long and short-term TA procured through the Governance and Security Framework Agreement and PEAKS, a CPS Justice Advisor, non-budget financial aid to partner government institutions and accountable grants to CSOs, and management of grants under the STSF. Each implementing agency would be responsible for providing financial accountability. As with Option 1, there is an increased potential for financial mismanagement with fiduciary and reputational risks for DFID. There are also risks to implementation if long-term Advisors need to be replaced, resulting in gaps in assistance while a competitive tender was conducted. Under this option DFID would retain full management responsibility, which has significant management time implications.

2.32 Due to limited resource within DFID general management of the programme is not sustainable long-term. As such Option 2 is the preferred option as it will deliver better value for money, better control over results, and a greater chance of stimulating longer-term reform.

2.33 Diagram 2 below summarises the programme delivery structure that will be used.

Diagram 2: Summary of programme delivery structure

## E. Economic Appraisal for Anticorruption Business Case

2.34 All three options yield high and similar Benefit-Cost Ratios and Internal Rate of Returns (IRR). Option 2 shows marginally higher returns. However addressing both the supply- and demand-side corruption increases the likelihood of programme success making Option 3 the best option for DFID support.

2.35 Sensitivity Analysis:
- On the supply side the analysis is sensitive to changes in the expected efficiency gains from public procurement. If the efficiency gains are decreased from the expected 1 percent to 0.5%, the internal rate of return is reduced to 7% and BCR 1.19. If the expected efficiency is reduced to 0.4%, the BCR becomes less than 1. However, given the current level of inefficiencies in the procurement process, increasing efficiency by at least 1% from the current level is seen to be conservative.
- On the demand side, the analysis is only sensitive and BCR reduces below one when the expected efficiency gains are not achieved for both royalties with oil contracts and the improved service delivery. However, if the projected efficiency gains are achieved in only one area, the BCR is still above 1 and remains profitable for DFID intervention.

2.36	The key assumptions in the analysis are the following
- There are no benefits in year 1 of the programme and benefit extends to an additional 3 years after programme completion.
- The analysis uses the value of retrieved taxes from Malawi implementing a similar anti-money laundering programme. The benefits from Malawi are multiplied by 12, representing Ghana’s GDP as a factor of Malawi[14].
  [14] Malawi has a GDP of US$3.7b in 2013 while Ghana has US$48billion in 2013 according to the World Bank.
- The analysis attributes 15% of the retrieved taxes to the programme as some of the resources as considered as a transfer, by staying in the economy. However tax revenues help strengthen the macro fiscal position of the economy.
- A yearly public procurement value of 10% of non-oil GDP[15].
  [15] According to PPA 2010; Schweizerische Eidgenossenschaft 2010, government procurement in Ghana represents over 18 % of GDP.
- Increase in expected oil royalties of up to 5% of current projected as a result of transparency efforts from Civil Society.
- 5% of benefits from increased royalties is attributed to the DFID support.
- Improvement in the efficiency of spend of the district assembly common fund is used as a proxy for benefits from demand side accountability for improved local service delivery.
- A discount rate of 10% for costs and benefits.
- An exchange rate value of GHS5 to £1 according to the Bank of Ghana[16].
  [16] Rate for 6th February 2015

Table 1: BCR and IRR for the 3 options[17]
[17] A detailed economic appraisal has been documented, see QUEST document number: 4873573
	Option 1	Option 2	Option 3
IRR	45%	57%	48%
BCR	2.20	2.75	2.32

## F. Theory of Change for preferred option
2.37	There is no one widely accepted international theory of change on tackling corruption. The theory of change for this programme draws on a careful political and institutional assessment, consultations and relevant international evidence and academic literature. It is also aligned with the DFID’s global Theory of Change for tackling corruption.

2.38 The corruption problem identified in the Strategic Case is as follows:
Although Ghana has put in place most of the institutional structures necessary to tackle corruption, these are not fully deployed, and corruption levels remain significant, weakening government services, prospects for long term growth and development and democracy itself.

2.39 Analysis suggests three factors lie behind this:
- The rewards of corruption presently outweigh the risks. Despite Ghana’s progress on anti-corruption, there remain plentiful opportunities to commit corruption, and a low likelihood of being caught or sanctioned. Corruption is increasingly being seen as the norm rather than the exception, with citizens being complicit in the problem. This leads to a collective action problem: the more pervasive corruption is, the more it defines the ‘rules of the game’ and the greater the cost to the individual to challenge it[18].
  [18] See ‘The Failure of Anti-Corruption Policies’, Persson, Rothstein and Teorell 2010, and A Vicious Circle of Corruption and Mistrust in Institutions in sub-Saharan Africa, Cho and Kirwin 2007
- The weak capacity of the Ghanaian government system to actively implement anti-corruption and wider accountability measures[19][20].
  [19] See 2011 Global Integrity Report: Ghana’s legal framework scores 79 point out of 100, but its actual implementation scores only 54 points.
  [20] See ‘Governance and Anti-Corruption Reforms in Developing Countries: Policies, Evidence and Ways Forward’, Mushtaq Khan 2006, and ‘Developmental Patrimonialism? The Case of Rwanda’, Booth and Golooba-Mutebi 2011.
- Inconsistent and uneven levels of political commitment to tackle corruption. This is the case in high politics but also at an institutional level. Powerful economic and political interests benefit from corruption in Ghana and political will to tackle it therefore remains weak.

  1. This leads to the following hypothesis: Corruption levels in Ghana will reduce if there is more active implementation of anti-corruption measures, and this in turn will occur if there is[21]:
    [21] This discourse is underpinned by Klitgaard’s corruption formula (corruption = monopoly + discretion – accountability). Klitgaard, R. Controlling Corruption, 1988.
(A) improved technical capacity and joint working among oversight agencies – leading to more proactive detection and efficient handling of corruption risks and cases, and stronger collective action / less scope for political interference
(B) fewer opportunities and incentives to be corrupt - through government reforms that reduce opportunities for corruption. Also through increased likelihood of detection and punishment if committing corruption. These also need to be applied at sector level if they are to have a tangible impact on public experiences of corruption. Asset recovery is key as it addresses the motivation for corrupt behaviour.
(C) increased domestic and international incentives for government to tackle corruption – strengthening the voice and influence of domestic actors that have an interest in how public resources are used and increase public confidence that it is worthwhile acting against corruption. Using international levers to motivate government action, e.g. compliance with international standards and international corruption investigations.

  1. These three areas are mutually reinforcing, as the diagram below shows. The assumptions have been carefully assessed against existing evidence and tested with partners during design.

A new approach
2.42 In deciding where to target DFID support, current anti-corruption interventions were considered and evidence of what is most likely to have an impact. The programme envisages a multi-pronged approach that supports both the supply and the demand side, including:
- Actions to build a robust anti-corruption regime with critical functions[22] operated by strong institutions;
  [22] Such as audit and oversight; administrative sanctions; asset recovery; and criminal sanctioning processes.
- Support to beneficiaries, civil society and the media as drivers of accountability and progressive change, with particular efforts to develop an active middle-class citizenry, building on efforts under DFID’s Strengthening Transparency, Accountability and Responsiveness programme (STAR II);
- Efforts to maximise synergies between the two;
- Robust analysis to identify the critical interdependencies and determine what works and what should continue to be supported.

2.43 The approach will marshal three sets of pressure points on government: externally (leveraging compliance with international standards and the incentive to maintain a good international reputation, as well as collective policy action across HMG and in coordination with other donors), from below (enhancing citizen engagement and supporting accountability opinion formers including the media and CSOs to build pressure from citizens) and from the side (supporting key accountability bodies to provide successful domestic oversight).

2.44 Anti-corruption efforts will be supported all the way to resolution. If corruption is uncovered through citizen reporting, civil society scrutiny or accountability bodies, law enforcement will be supported to pursue cases to resolution. Leading civil society organisations will be supported to pursue issues for long enough for action to be taken.

2.45 The approach sees dealing with corruption as being a chain-linked process which is only as strong as its weakest link. No single agency can tackle corruption alone. Evidence suggests that approaches which only support high-performing institutions can increase bottlenecks in the system. Structuring support across the corruption chain will maximise impact. The approach will capitalise on the increasing appetite within anti-corruption and accountability institutions to recover stolen assets, and confiscate assets from associates of the corrupt.

2.46 The public bemoan the levels of corruption, but frustrations are not leading to effective action and change. Coverage in the media is superficial and sensationalist. Accountability and empowerment actors have to date been unable to generate the required demand for change. They have failed to coalesce sufficiently behind key issues to generate ‘strength in numbers’ and avoid being seen as politicised. Support to selected civil society partners will seek to ensure that interventions are based on robust analysis and strategic vision, and are followed through to a logical conclusion.

2.47 The programme will be holistic in approach and balance support to the supply side with focused and targeted support to the demand side. This will make innovative use of the rapidly increasing internet and mobile phone coverage in Ghana to promote reporting of corruption and communicate findings of corruption studies. It will also seek to engage the rapidly increasing middle-class, such as professional bodies, and influential opinion leaders.

2.48 The programme approach has drawn heavily on lessons and experience from DFID’s global programming, including similar programmes in the Caribbean, Tanzania, Uganda and Sierra Leone.

# Commercial Case

## A. Clearly state the procurement/commercial requirements for the intervention

  1. The diagram below summarises the procurement structure that will be used.

Diagram 2: Procurement Structure for Programme

  1. A managing agent will be directly procured to manage overall programme reporting, deployment of technical assistance, the Strategic and Technical Support Facility (STSF) and the monitoring and evaluation framework. DFID will directly fund the deployment of a UK Judicial Adviser from the UK’s Crown Prosecution Service (CPS). During the duration of the project DFID will also directly engage consultants and audit firms to conduct independent reviews and audits.

  1. There will be one indirect procurement through support to Government of Ghana oversight institutions under a non-budget financial aid mechanism.

## B. How does the intervention design use competition to Drive Commercial Advantage for DFID?

  1. DFID will conduct a mini-competition within the Governance and Security framework to select a managing agent. Suppliers have already demonstrated appropriate expertise at competitive costs. The mini competition will further enhance competition.

  1. Audit firms and consultants to undertake independent reviews will be procured in line with DFID procurement regulations, designed to drive commercial advantage. The timing is predictable and therefore an open competitive process can be conducted, and DFID is likely to be able to negotiate a cost-effective arrangement.

## C. How do we expect the market place will respond to this opportunity?

  1. The interventions that will be tendered within the direct procurement are within the scope of the framework arrangement and are all likely to attract a number of technically suitable suppliers. Contracts will stay within framework limits which are already negotiated and can be deployed rapidly. This option was chosen because the framework has a wide database of expertise relevant to the programme.

  1. Experience from other DFID-Ghana programmes suggests there are likely to be several CSOs interested in carrying out analytical and demand driven advocacy work through the STSF.

## D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?

  1. The key cost elements are: technical assistance, training and equipment, software and indirect costs such as recruitment, back-office administration etc.

  1. On the Technical Assistance, we will bring in the highest quality people possible at a reasonable price. Clear criteria will be specified for the quality of personal required, and their costs benchmarked against similar providers. Payment will be directly linked to performance and outputs. Terms of reference will give weight to the sourcing of local expertise that is available at lower cost.

  1. On procurement, the programme will ensure timely procurement of good quality equipment and materials that can deliver the tasks required at the best possible cost through monitoring the procurement undertaken by government partners to ensure that all purchases are competitively procured, represent value for money and comply with Government of Ghana procurement standards. Government agencies (GAs) will be supported to appoint a procurement agent who will monitor the procurement process with clear procurement plans. DFID will to give a no-objection letter of approval based on procurement plans and reports from the procurement agents. Procurement of high value goods, such as forensic laboratory equipment, will require international tender. Detailed specifications will be required. Experience has shown the importance of taking into account ongoing costs such as maintenance and licence fees and these will be factored into criteria for selection.

  1. On indirect overhead costs, the Programme team with support from Procurement and Commercial Department (PCD) will aim to negotiate a contract with the lowest possible management fees and with transparency of overheads.

## E. What is the intended Procurement Process to support contract award?

  1. The Procurement and Commercial Department will run a mini competition through the Governance and Security Framework. The DFID-Ghana Governance Team will develop detailed evaluation criteria with support from PCD and the Commercial Adviser. In order to attract high-quality bids, there will be a pre-bid meeting with interested bidders.

3.13 DFID-Ghana will evaluate the technical bids and PCD will undertake the financial evaluation. Any conflict of interest will be declared and appropriate action taken. Scoring of bids will be based on the ability to deliver the services specified in the terms of reference and based on pre-defined criteria.

## F. How will contract and supplier performance be managed through the life of the intervention?

3.14 All contracts will clearly describe the outcomes to be achieved and will include robust and reasonable implementation plans. DFID has clearly communicated to partners that support will be contingent on progress and results.

3.15 The management contract and supplier performance will be closely managed throughout the life of the programme. The contract with the managing agent will include payments authorised against satisfactory delivery of outputs, specific objectives and indicators/milestones. Alongside this, a range of performance-based Key Performance Indicators (KPIs) will be developed and revisited at set intervals including; i) the review at the end of the inception phase; ii) mid-term review at the end of year three ; iii) end of project review.

  1. The overall time-frame will be five years, with break clauses after the six month inception phase and at the mid-term point to allow for assessment of progress against output and to assess if the contracts and interventions are offering value for money. These reflection points will allow DFID to assess progress and determine programme focus.

  1. Measurement of progress against the KPIs, linked to measurement of performance against the log frame, will be undertaken on a monthly basis. Quarterly financial and narrative progress reports will be also be monitored against work plans and financial forecasts.

## G. What assurance has been obtained on capability and capacity to deliver?

  1. The most recent DFID Fiduciary Risk Assessment (FRA) for Ghana, completed in 2014, concluded that the risk of using Government systems was substantial. The assessment of corruption risk was high and persisting. With the proposed support to the partner Government Agencies, Ghana’s public financial management is considered adequate to provide assurances on appropriate use of these funds.
  2. DFID has previously successfully worked with Government institutions with no fiduciary risk materialising through close monitoring and support. The agencies identified as potential partners are already managing other donor funds. The tight financial management and monitoring arrangements set out below will further enhance the scrutiny of the GAs. As the support envisaged is non-budget support financial aid with tightly controlled financial management arrangements, DFID will not carry out a separate FRA for each before providing funding, but will refer to the broader FRA in providing financial aid to the targeted institutions.
  3. The CSOs that have been identified as potential partners during the design appraisal have received funding from DFID previously.

## H. Is there an opportunity to negotiate on anticipated costs?

  1. Yes. There will be continued dialogue on the costs that GAs can meet from its own resources, particularly as the programme evolves. Grants through the STSF will be robustly negotiated.

  1. There will also be continued dialogue on the costs with the service provider particularly as the programme evolves. Before agreeing grants with all CSOs, cost will be negotiated to ensure they are realistic and benchmarked against costs on similar activities in Ghana and elsewhere.

# Financial Case

## A. How much it will cost

  1. The estimated cost of the programme is £9.7 million over 5 years. The budget breakdown is provided below in Table 2. The estimated breakdown below is likely to be subject to change once detailed work plans have been developed with the GAs, CSOs, and the contract has been awarded to the selected managing agent.
  Table 2: Breakdown of estimated cost
Components	Estimates
Non-financial aid to State Institutions
EOCO	£900,000
FIC	£600,000
Public Procurement Authority (PPA)	£700,000
Judiciary	£500,000
Total	£2,700,000
Strategic & Technical Support Facility (Supply and Demand Side)
Research/ M&E	£250,000
Grants to CSOs	£1,500,000
CSO/Government dialogue and Demand Driven Inputs	£450,000
Support to IC coordination and international levers	£50,000
Technical Assistance	£1,550,00
Management fees	£1,500,000
Total	£5,250,000
DFID Managed
Crown Prosecution from the UK	£1,250,000
Management (monitoring, audits, risk assessments etc )	£500,000
Total	£1,750,000
Programme Total	£9,700,000

  1. The projections are indicative within the overall budget framework and actual allocations and spend between the budget lines will be adjusted based on i) functional reviews and assessments conducted in the inception phase; ii) partner performance and iii) changes in the wider political context. Annual Reviews will recommend appropriate adjustments to allocations.
  2. As part of the tendering process for the managing agent, the Service provider will be expected to provide credible estimates on the cost, which will be judged against similar DFID Programmes.
  3. Non-budget financial aid and budget for the Strategic & Technical Support Facility to be managed by the managing agent will be profiled on an annual basis and updated based on narrative and financial reports on a quarterly basis. DFID will keep a tight control over disbursement and forecast spend. Forecasting will be updated by DFID on a monthly basis.
  4. An indicative cost profiling and forecasting for the programme is in Table 3 below:
Table 3: Profile of Estimated Costs per year

Description	Years					Total
	2015/16	2016/17	2017/18	2018/19	2019/20
Non Budget Financial Aid	800,000	750,000	600,000	450,000	100,000	2,700,000
Strategic & Technical Support Facility	600,000	1,500,000	1,550,000	1,000,000	600,000	5,250,000
Crown Prosecution from the UK	250,000	250,000	250,000	250,000	250,000	1,250,000
Management cost ( Monitoring, reviews, risk assessment, audit etc)	50,000	200,000	100,000	100,000	50,000	500,000
Total	1,700,000	2,700,000	2,500,000	1,800,000	1,000,000	9,700,000

## B. How it will be funded: capital/programme/admin

  1. The intervention will be funded from programme resources (RDEL), under the DFID Ghana framework. About 18% of the funding will be provided within the current resource allocation which ends in 2015. The remaining funds will be bid for in the next resource allocation round and in accordance with the provision in the DFID Ghana CPRD.
## C. What is the assessment of financial risk?

  1. Overall financial risk and risk of fraud is medium. (See commercial case for details on FRAs, and the overall fraud context.)

  1. The financial risk of channelling funds through government will reduce as the system is strengthened, including through the interventions of this programme. The use of external experts will help mitigate the risk and build the capacity of the agencies to manage both external and internal funds.
## D. How expenditure will be monitored, reported, and accounted for?

  1. Project progress will be monitored according to standard DFID internal procedures, involving Annual Progress Reports and a final Project Completion Report. These will be based on progress against the log frame which may be amended during the course of the project.
  2. Non Budget Support Financial Aid will be disbursed, reported for and accounted for and managed quarterly and in line with an approved annual work plan and budget procurement plan. Quarterly disbursements will be made in advance based on quarterly summary financial reports from the ACAs, accounting for past disbursements, combined with fuller six-monthly narrative and financial reports.
  3. Specific MOUs will be signed with all the GAs detailing requirements for reporting progress and financial management. MOUs with Government institutions supported under the project will state clearly what DFID funds can and cannot be used for. Any expenditure that does not correspond to pre-agreed activities in the budgets and work plans will be required to be returned immediately to DFID. All remaining funds at the end of the project will be returned to DFID.
  4. Expenditure incurred by the managing agent will be invoiced to DFID quarterly in arrears, covering approved activities implemented during the quarter. Such invoices will be scrutinised for accuracy by a DFID programme officer and quality assured by the deputy programme manager; any inconsistency would be resolved prior to the invoice being paid by DFID Accounts Department.
  5. Any capital assets procured under this programme will be DFID owned and carefully monitored through an asset register and regular annual spot checks throughout the lifetime of the project. At the end of the project, DFID will decide how such assets will be disposed of.
  6. The project will undergo periodic financial and Value for Money audits of its operations and recommendations from these audits will be taken forward by the programme.
  7. Budget forecasts will be required for each institution receiving DFID funding. Further funding will only be provided once prescribed milestones have been met and previous funds accounted for.

# Management Case

## A. What are the Management Arrangements for implementing the intervention?

Oversight:
5.1 DFID will be responsible for oversight of this programme, through the Governance Advisor, with support from the Deputy Programme Manager. The Good Governance Team Leader will be SRO for this programme and ensure it delivers the quality outcomes intended.

5.2 Technical coordination and direction of programme will be provided by the DFID Governance Advisor leading on the programme with support from the managing agent. The programme of support with each Government agency and civil society partner will be agreed under strict conditions including clear commitments from the agencies and organisations themselves. Failure to meet those commitments, or to account on schedule for funds disbursed, will result in suspension of funding.

5.3 During the inception phase the managing agent in consultation with government partners will explore the feasibility and utility of setting up a Steering Committee to oversee support to Government partners. This would comprise members from: DFID, the managing agent, an eminent Ghanaian with knowledge of Ghanaian social dynamics, and representatives from all the key oversight institutions. Consideration will be made to whether it is appropriate to include the Public Procurement Authority (PPA) or to focus on the law enforcement agencies. Consideration will also be made to whether it should be chaired by a champion within Government or the FIC, who have the mandate for coordination and oversight of anti-money laundering efforts.

Management:
5.4 The managing agent will manage all funds and the programme with the exception of the non-budgetary financial aid and financing for the CPS Justice Advisor, and will make any direct payments.

5.5 An MoU will be signed with the Government of Ghana to provide non-budgetary financial aid for specific activities and equipment for selected government partners.

5.6 Once appointed the managing agent will undertake functional reviews of proposed partner agencies; refine work plans with partners; report on the plans, procedures and processes for implementing the programme; define and cost the implementation phase of programming in more details; and develop a system for monitoring programme impact including key performance indicators. Thereafter, the managing agent will be responsible for day to day programme management, which will include: programme planning; managing long and short-term TA; making sure programme management is carried out in line with standard DFID procedures; budgeting and forecasting; and submitting reports for the project.

5.7 Technical assistance will be provided by the managing agent in consultation with the supported agencies. Advisers, funded through this programme will be reporting to the agencies in which they operate. Their role will include helping manage the inputs and results of this programme whilst building the capacity of the agencies to implement the agreed programme and increase their accountability.

5.8 The managing agent will also administer the “Strategic and Technical Support Facility” (rapid response fund), which will include grants to CSOs. The managing agent will report to DFID on the management and administration of the entire suite of projects funded under the programme.

## B. What are the risks and how these will be managed?

Risk	Prob- / ability	Impact	Mitigation measures	Residual risk
1. Coordination efforts are frustrated by mandate and turf issues	L	H	The programme will identify those who champion better coordination and build on their influence and initiatives. / Programme design to encourage coordination and enable flexibility to focus on areas that can make progress. / The leadership of participating agencies will be encouraged to drive this process.	L
2. PFM reforms are not fully implemented, increasing fiduciary and corruption risk	L	H	DFID is currently designing a new PFM programme. / GIFMIS will continue to be supported by the World Bank and EU, providing substantial leverage.	M
3. Vested interests means constraints to addressing anti-corruption cannot be overcome	M	M	Influencing actions by HMG and the international community. / Support provided under strict conditions with clear commitments by Government agencies. Progress will be monitored closely and support will be altered or ceased if there is no traction. / The proposed support to civil society is aimed to awareness and to challenge negative societal attitude and acceptance of corruption. / Enhanced scrutiny should reduce opportunities for corruption and political interference. / Cooperation between law enforcement agencies will reduce opportunity for political interference. / Risk spread across programme / through multiple strands of activity.	M
4. Civil society and media organisations unwilling to follow up on corruption cases	H	M	Building coalitions will spread responsibility and risk. / Capacity development and close management through the programme. / Backstop support from international organisations if politically sensitive cases are identified or partners threatened.	L

## C. What conditions apply (for financial aid only)?

5.9 Partnership Principles will apply to the funds to be provided directly to the ACAs. The last in-depth assessment of the Partnership Principles (PPs) in June 2014 concluded that the Government had upheld all four PPs over the 2013/14 period. The most relevant PP to the programme is on the commitment to strengthening financial management, which was upheld albeit with concerns, in particular around the management of the macro-economy, and the slowdown of PFM reform. A range of PFM reforms have been initiated in Ghana. These include the introduction of the Ghana Integrated Financial Management Information System (GIFMIS) and improvements in budget formulation. DFID remains closely engaged in these, both on a programming and policy level.

5.10 Non- Budget Support Financial Aid will be provided directly to the Agencies and managed using Government systems and procedures. The overall assessment of PP principles (with particular focus on PFM) in any year will be considered before any Financial Aid disbursement is made. The financial and commercial cases set out specific and additional conditions attached to the disbursement of aid including what expenditures are eligible for DFID funding, adherence to detailed work plans and budgets and related return of funds should there be unexplained variances; and exit or reduction in funding to particular institutions based on feedback on audits (financial and procurement). These conditions and the conclusions of the general assessments of the PPs will guide disbursements.

## D. How will progress and results be monitored, measured and evaluated?

5.11 Programme progress will be monitored using DFID’s standard performance management. An annual review will be performed of progress against log frame indicators. It will also re-examine the assumptions in the theory of change.

5.12 Because of the multiple components of the programme a broader monitoring framework will be developed during the inception phase. An evaluation is currently considered unnecessary as Ghana has been identified as a focus country to be included in DFID’s Anti-Corruption Evidence programme (ACE) which will specifically consider what works and seek to understand the inter-dependencies between anti-corruption interventions.

5.13 Government and CSO partners will develop annual work plans for the specific areas that DFID will support, with a results framework. Funds will be disbursed on a quarterly basis, on the basis of submitted narrative and financial reports with progress against agreed quarterly targets. This will be managed by the service provider with support from DFID.