Annual Review - Annex / This Annex captures additional information to substantiate the annual review. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. / Title: Somaliland Development Fund (SDF) / Programme Value: Overall £38.9m / DFID’s contribution £20m Review Date: January 2015 / Project Code: Start Date: / December 2012 End Date: / August 2017 / B: PERFORMANCE AND CONCLUSIONS (1-2 pages) / Annual Outcome Assessment / Since the beginning of the Implementation Phase in April 2014, the programme has developed a steady and increasing momentum of activity and achievement: the available evidence of current and predicted progress indicates that the SDF will at least meet the Outcome target and achieve an A score. / OUTCOME Outcome Indicator 1 Baseline / (2013) Milestone 1 / (2014) Milestone 2 / (2015) Target 2016 Progress / Improved and better resourced core state functions for the people of Somaliland Number of beneficiaries of services attributable to SDF 0 0 750,000 1,300,000 The 2015 milestone of 750,000 beneficiaries will be achieved through implementation of the Hora Hadley and Ayaha Project (57,000) and roads rehabilitation project (700,000). / Outcome Indicator 2 / % of population who report direct experience of improved government service delivery 0 0 TBD TBD The main source of data for verification of this indicator is the perception survey which is being conducted in January 2015. / It is difficult to ascertain a precise assessment of the outcome statement, given the timing of this review very early in 2015, but outcome indicator 1 is well on track given the contracts for implementation of both the water and roads rehabilitation projects were awarded in August and October 2014 respectively and are well underway. / Significant progress has been made on outcome indicator 2, as the SDF established the Communication Hub project with a team based at the Ministry of Planning in October 2014. This team is already working with the various project teams in promoting SDF funded projects as Government of Somaliland development initiatives. / The administrative, decision making, tendering, project delivery, monitoring and evaluation frameworks are robust and proving effective in implementation. There is a strong partnership between the Fund managers and the counterpart Somaliland institutions, particularly with the Ministry of Planning and with the Minister personally. While, as is the case with many similar Funds, disbursement has been slower than hoped for, it is clearly accelerating; while retaining the robust systems in planning, procurement and financial control, as set out in the Fund’s operating manuals. / Ministers and officials in the beneficiary institutions that were interviewed in the course of this review were fulsome in their praise of the SDF processes and benefits. Numerous informants commented on the importance of the Government being in control of the prioritising and budgetary decisions. The profile and benefits of the SDF are frequently cited, including by President Silanyo at the High Level Aid Co-ordination Forum in November 2014. With four Donors now contributing to the Fund, and the EU committed to joining in 2015, the SDF is also developing into a platform for improved donor co-ordination and coherence under the New Deal. / Aggregate Output Score and Description / This review was conducted in December 2014/January 2015 in line with DFID procedures. However, there is ample evidence currently available to conclude that the aggregate Output score is A. / The infrastructure and livelihoods related Outputs (1 & 2) are on course to meet their milestones and end of programme targets; and in the opinion of key informants it will exceed these. Output 4 on: Enhanced citizen perception of Government priorities, actives and expenditure is behind schedule as the Perception Survey has been delayed but some important work has been undertaken with establishment of the Communications Hub. The capacity related Output (5) is also on course to meet its milestones and end of programme targets; and the evidence is that it will exceed these. With regard to Output 3: improved capacity of GoSL institutions to manage development projects; the Indicators do not adequately address the spectrum of achievements within this Output. When evidence of the wider context of activity and achievement is considered, the score for this Output is A+. / As the January 2014 annual review noted: ‘the main recommendation is that momentum needs to be maintained as expectations are high both from Government and other development partners’. Conversations with Ministers, Director Generals and Project Management Teams, DFID and DANIDA in December 2014 leads to the conclusion that donors and Somaliland stakeholders remain impressed with sustained momentum and the SDF continues to exceed the expectations of the Government and the Donor community. / Lessons / While it is still early days in the programme’s Implementation Phase, and while there are undoubtedly more to be identified as the programme progresses, there are already some evident points of learning. / A key positive lesson to be derived from the operation of the SDF is the importance of building productive partnerships with Government, following clearly defined and transparently applied decision making, project approval, tendering and implementation processes; all of which are evidentially present in the management of the SDF. The degree of transparency is particularly striking as is the degree of public interest generated by this and the media attention given to the President’s speeches in support of the Fund’s activities. / The size and scale of the projects selected for funding are of a sufficient scale to bring noticeable improvements, but also sufficiently modest as to be feasibly accomplished within the budgets and timescales available. / Actions / Improvements in the formulation of the Outputs and more appropriately specified Indicators would be of benefit to the operation, monitoring and evaluation and reporting of the SDF. As they are presently formulated there are overlapping or closely linked activities within Outputs 3 and 5. If Output 5 is intended to address the programme managers’ stewardship of their roles and responsibilities it should state this more explicitly and have Indicators that reflect the diversity of these. The log frame Indictors will also need to reflect the measurable progress in project areas such as forestry protection and the projects which are currently at concept stage. / Although the programme invests considerably in the cross-cutting areas of gender, environment and conflict these are not reflected in the log frame or its Output Indicators, nor are they given particular emphasis in the programme’s reporting. It would be useful if some attention could be given to rectifying this situation. / In the course of this review, government stakeholders, while acknowledging the fixed timelines for procurement processes were also keen to explore the possibility of reducing the 120 day timeline between concept note and project proposal completion. At the time of the review this was an issue that the programme team were already working on with a view to having the process completed in fewer days. Consistent with the view expressed by the Minister of Planning; additional long-term technical engineering support rather than draw-down from short-term consultants would be an element of this and this has now been addressed as the Managing Agents have recruited an in-house Engineer. / D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1-2 pages) / Donor contributions: / Donor 2012/13 2013/14 2014/15 2015/16 2016/17 Total (GBP) Total (USD) / DFID £200,000 £1,500,000 £ 4,553,780 £6,957,706 £6,788,514 £20,000,000 $ 33,000,000.00 / DFID CSP £300,000 £300,000 $ 495,000.00 / DANIDA £55,477 £6,500,000 £5,900,000 £12,455,477 $ 20,551,537.05 / Norway £1,500,000 £200,000 £1,300,000 £3,000,000 $ 4,950,000.00 / Netherlands 400,000 £1,600,000 £1,200,000 £3,200,000 $ 5,280,000.00 / Total £255,477 £ 9,500,000 £ 11,053,780 £10,157,706 £7,988,514 £38,955,477 $ 64,276,537.05 / Application of funds: / 2012/13 2013/14 2014/15 2015/16 2016/17 Total (GBP) / Management costs £ - £1,915,412 £1,915,412 £1,915,412 £1,915,412 £7,661,646 / Programme funds £255,477 £7,584,589 £9,138,369 £8,242,295 £6,073,103 £31,293,831 / Exchange rate £1.6500 / Available yearly $421,537 $12,514,571 $15,078,308 $13,599,786 $10,020,619 $51,634,821 / Available cumulative $421,537 $12,936,108 $28,014,416 $41,614,202 $51,634,821[1] / E: RISK (½ page) / Overview of programme risk / The Business Case and the Annual Review of January 2014 present a detailed tabulated account of the risks inherent to the SDF programme; relating to context, programmes and institutions. Within this there is an acknowledgement that engagement in a fragile environment such as Somaliland is inherently high risk, robust mitigating actions have been put in place. / The SDF managers have developed a risk matrix as part of the Operational Guidelines for the programme that addresses contextual, programmatic (including fiduciary risks) and institutional risks. The risk matrix was last reviewed in October 2014.The quarterly reports on SDF routinely review the risk environment and the steps taken to mitigate current and emerging risks and review of risk is also on the standing agenda for the six-monthly JSC. / The following are the key risks identified: / The Government ownership is well established and represents a low risk in terms of probability and continues to be medium in terms of impact. The SDF secretariat and donors will continue to invest in building relationships with new players when they enter into Government. They also will continue to maintain strategic relationships with Government at central, regional and district level; / The fiduciary risk continues to be medium/high and the strong mitigating measures continue to be robustly implemented. The secretariat continues to have full control of all expenditures and a robust and transparent procurement process has been established. The secretariat has developed rigorous management systems for the SDF ensuring optimal performance and a Fiduciary risk management strategy is in place. / Political Economy of Somaliland – risk that the SDF is captured by a single group or small number of groups within the government was considered in January 2014 to be high/medium. This continues to be the case. A political economy analysis was completed in December 2013 and an yearly review is due. SDF secretariat has put into place a robust and transparent procurement system. It also stimulating government to adopt a methodology for project prioritisation that ensures equality; / GoSL officials having received capacity building assistance leaving their positions to pursue better opportunities in other development agency programmes, NGOs or the private sector – This is considered to be medium/high. The risk remains given the nature of the labour market in this area. SDF Secretariat is liaising with the participating Government Ministries and organizations to ensure at least one full-time committed Project Manager from the Government side is working on each SDF project in target ministries by providing a temporary salary top-up. The Secretariat has set in place Learning Contracts for major training initiatives under SDF (e.g. CSP, training under SDF Project Capacity Development Outputs) specifying the obligation of the concerned trainee to stay with his/her Ministry/Agency for at least one year after completion of the training; / Non-delivery by the secretariat of the SDF, or by implementing agents is considered to be medium/ high, but given the strong performance of the managers during 2014, it would be appropriate to consider this to now be low. In mitigation, payments are made against agreed milestones. An expenditure verification audit was done in November 2014 by KPMG where the secretariat received a positive appraisal. A financial audit is scheduled to be done in September 2015. The Fund Manager has planned for an extensive third party monitoring in the Roads sector to mitigate the risk of is the Somaliland contractors’ ability to deliver effectively.
[1] The balance of USD 12,641,716 will be spent in the financial year 2017/18.