Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Agricultural Model Intercomparison and Improvement Project (AgMIP) -The future of food and farming in Sub-Saharan Africa
Programme Value: 9.97 million		Review Date: 23-28 February 2015
Programme Code: 202108	Start Date: 01/03/2010	End Date: 31/12 /2016

Summary of Programme Performance
Year	2011	2012	2013	2014	2015
Programme Score	-	A	A	A+	A+
Risk Rating	-	Medium	Medium	Low	Low

Summary of progress and lessons learnt since last review
Over the last reporting year the project has continued to perform strongly, delivering above expectations in all areas. During this period the project was extended by two years to December 2016. Achievements include a number of major findings (new and confirmed) in the areas of future vulnerability, impacts, and adaptation to climate change. These include:

A significant step forward in understanding and characterisation of vulnerability across a number of farming communities located in eight regions throughout Sub-Saharan Africa (SSA) and South Asia (SA).

- Finding that adaptation packages can raise incomes and lower poverty rates but do not always fully compensate for the adverse impacts of climate change;
- Confirmation that climate change will add pressure to many current small holder agricultural systems, even as CO2 concentrations increase and projections of rainfall changes are mixed;
- Likely future agricultural development pathways mean that impacts on future agricultural systems are expected to be different from those currently experienced. agricultural systems, due to agricultural development pathways;

The most significant outputs and products generated over the past year include:

11 peer-reviewed journal articles, 18 book chapters and 8 regional multidisciplinary datasets.

Publication of Handbook of Climate Change and Agroecosystems: The Agricultural Model Intercomparison and Improvement Project Integrated Crop and Economic Assessments (Parts 1 and 2). Contains 25 chapters describing methodologies and research results from global and regional assessments.

A number of methodological advances by the project have allowed a more robust climate change impact assessment for the agricultural sector of eight study regions across Sub-Saharan Africa and South Asia. These include:

An improved understanding of stakeholder needs and engagement modalities;

An improved understanding of strengths and weaknesses of 3 crop models across 8 regions including better calibration of each model to the conditions (e.g. soils, weather, crop variety) specific to each region;

The refinement of 20 future climate change scenarios utilising two different approaches that place varying emphasis on changes in climate variability;

- The development of new regional ‘Representative Agricultural Pathways’ (RAPs) of future agricultural development in light of broader economic developments and trends;
- The completion of eight individual regional integrated assessments of the socio-economic impacts of climate change on small-holder agricultural systems;

A significant improvement in the characterization of uncertainty in the projections of linked models taking into account crop, livestock, climate and economic factors.

The project also continued to deliver improvements in researcher and institutional capacity involving both technical and scientific expertise across participating countries and institutions in Sub-Saharan Africa and South Asia.

In addition to the scientific advances described above, lessons learnt over the past year also included a number related to programme and financial management approaches and the overall programme structure, both of which were found to be overly complex and in need of improvement. The main recommendations emerging from discussions with the leadership team and the programme managers are listed below.

Summary of programme-level recommendations for the next year (March 2015 - March 2016)

- Research methodology and focus:
  - Include additional elements of the farm system, such as livestock into the regional integrated assessment methods in order to better represent the complexity of small-holder systems found across SSA and SA.
  - Work to improve confidence in interpretation of results, in particular: determine the processes that lead to differences between crop models, understand how different climate change projections drive impact trajectories through heat and water stress, and elucidate the sensitivity of socioeconomic outcomes to elements of Representative Agricultural Pathways (RAPs) and adaptation packages.
  - Characterize impacts of extreme climate events that interact with mean climate changes in order to improve the reliability of crop yield projections and economic outcomes.
  - Work to link global and regional assessments to achieve wider geographical coverage, more comprehensive impact metrics, and more consistent messages to stakeholders.

- Stakeholder engagement:
  - Improve stakeholder engagement approach based on best practice examples and prior experience;
  - Engage stakeholders to organise regional integrated assessment of adaptation packages and integrative tools around stakeholder interests and concerns.

- Communications:
  - Develop and implement a communications strategy to motivate stakeholders, funders, and scientific community to share and disseminate project findings and information with wider audiences;
  - Develop a methodology and a set of indicators to measure effectiveness of communications.

Product development:
Focus on the development of web-based and accessible tools for visualising results, conveying findings, and improving uptake of evidence emanating from project;
  - Create functional prototype of AgMIP Agricultural Impacts Explorer.

- Financial/program management:
  - Implement recommendations from audit of Phase 1 (currently in progress);
  - Revise and simplify management structure of program to enable more streamlined transfer of funds between partner institutions.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3755603.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3640676.xlsx

Outline of the programme

Context
Agriculture is one of the most vulnerable sectors to the impacts of climate change. This is due to both direct impacts on crop yields and indirect impacts such as changes in water availability. As a result, climate change will tend to reduce global agricultural production and intensify the risk of hunger and malnutrition. The 4th and 5th Assessments of the Intergovernmental Panel on Climate Change (IPCC) confirmed that most of these impacts are likely to be felt in developing countries, where “even slight warming decreased yields in seasonally dry and low-latitude regions”.

This has significant implications for both food security and economic growth in many developing countries, where even with rapid urbanization; the majority of the poor are projected to continue to live in rural areas until 2040. Most depend on agriculture for their livelihoods, directly or indirectly. In large parts of Africa and South Asia, rural communities almost invariably tend to rely on rain-fed agriculture, so building their capacity to manage climate-related risks is a high priority. There is an expanding evidence base underpinning the need for strengthened climate risk management and climate resilience in the face of increasing impacts of climate variability on economic performance and livelihoods of the poor. Climate pressures will lead to shifts in patterns of household behaviour in response to shocks, including in relation to food security and exposure to infectious diseases.

Negative effects on agriculture in these areas are also likely to lead to impacts on growth and poverty reduction. Recent empirical evidence suggests that compared to growth from other sources, growth in agriculture generates welfare gains that are much stronger for the poorest parts of the population. Cross-country econometric work reported in the 2008 World Development Report shows that a 1% gain in GDP originating in agriculture generates a 6 % increase in overall expenditures for the poorest 10% of the population. GDP growth originating in non-agriculture sectors generates zero growth for the poorest 10% of the population.

DFID Support
DFID is providing £9.97 million over 6 years (FY2010/11-2016/17) to improve crop and agricultural economic models that help assess future climate impacts on the global agricultural sector and identify suitable adaptation strategies for developing countries in Sub-Saharan Africa and South Asia. Funding is channelled through the US Department of Agriculture (USDA), a funding partner and the International Crop Research Institute for the Semi-Arid Tropics (ICRISAT), an implementing partner.

Expected Outputs and Outcome
The project is expected to lead to a much improved understanding of the effects of climate change and development on agriculture and food security in Sub-Saharan Africa and South Asia over the coming decades. It will also generate improved evidence to evaluate priority adaptation strategies to enhance food security and agricultural productivity.

Planned outputs of the project include:
- Improved ‘toolkit’ for food security policy including crop, livestock and agricultural economics models, with specific outputs for Sub-Saharan Africa and South Asia;
- Reliable and accessible regional assessments of the impacts of climate change on crop production and associated economic implications;
- Identification and assessment of agricultural adaptation strategies;
- Development of an on-line platform for a global facility that will generate uniform, harmonised and openly accessible geo-spatial data on agriculture and the environment;
- Strengthened capacity of researchers in SSA and SA to access and use crop, livestock and economic models;
- Policy makers and planners in SSA and SA better able to access and use improved and relevant information on regional climate change impacts on agriculture.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The outcome for this intervention is: “reliable and accessible assessment of impacts of climate change on agriculture in SSA and SA and improved evidence on priority potential adaptation strategies”.

Overall, we found evidence that AgMIP has met and moderately exceeded its intended outcome and related milestones for the year. AgMIP Regional Research Teams (RRTs) have engaged with a wide range of stakeholders to convey and share project methods and results and to build lasting relationships that will enable continued evaluations of potential policies and adaptation strategies. Stakeholders, including government ministries, extension agencies, national research programmes, community leaders, farmers, crop breeders, donor organizations, and adaptation policy planners are collaborating with Regional Research Teams (RRTs) and utilizing AgMIP’s modelling framework to identify, test, and prioritize possible adaptation strategies and policies aimed at improving resilience to future climate conditions.

Vetting of preliminary socioeconomic results has resulted in more robust and accessible assessments of impacts of climate change on agriculture and potential adaptation strategies in sub-regions of Sub-Saharan Africa (SSA) and South Asia (SA). These results form the new state-of-the-art for regional integrated assessment of climate change impacts on farming systems in Sub-Saharan Africa and South Asia. This effort has led to increased demand in SSA and SA for additional assessment of adaptation and policy strategies related to agricultural development in light of vulnerability to climate change.

Overall output score and description
Overall AgMIP has continued to deliver strongly against all of its outputs and met or exceeded all of its milestones for this year leading to an aggregate score of (A+). A summary of the key points and accomplishments for all outputs is provided below.

The project has continued to deliver strongly against output 1. It delivered improved crop and agricultural-economic models that were calibrated and validated for the participating study regions in SSA and SA. This was made possible by expanding the current climate baseline period into the 2050s to utilise multiple Global Circulation Climate Models (GCMs) and downscaled climate scenarios for use in multiple crop models. The validation of these crop models was made possible by the assembly of 72 sentinel sites which generated observational historical data from past field experiments.

The project has also continued to make strong progress against output 2, and has significantly exceeded all milestones set for the past year. Among the most notable achievements were: the utilisation of results from multiple, connected models to enable stakeholders to understand how climate change will affect prevalent farming systems. This resulted in 14 publications in prominent international academic journals and in a two-part scientific synthesis recently published by a leading UK academic publisher.

The project has delivered well against all milestones in output 3 resulting in a sustained production of high-quality scientific publications by developing countries’ researchers. For example, economists from SSA and SA research teams collaborated with AgMIP Regional Economic Team leaders to improve the quality of farming system analyses looking at climate change impacts, including poverty rates under multiple policy and adaptation strategy scenarios. Capacity building activities in SSA and SA were also aimed at producing communications materials, including: policy briefs, blog posts, infographics, and publication graphics that could be used to disseminate the results of AgMIP to a wider audience of stakeholders.

Overall progress against output 4 has fostered regular interactions with stakeholder groups in the regions, which resulted in stakeholder workshops and outreach events that attracted local media interest (e.g. in South Africa, Pakistan, Zimbabwe). The issue of adaptation benefits under current climate conditions has emerged as a key regional policy question relevant for decision-makers balancing short- and long-term adaptation planning.

Key lessons
Lessons learnt over the past year were mostly related to programme and financial management approaches and the overall programme structure, both of which were found to be overly complex and in need ofstreamlining. We have analysed and evaluated this area of the project with the leadership team and the project managers and have identified a number of recommendations which are described below in the relevant outputs sections. Following this analysis we have modified the financial management and disbursement structure to remove unnecessary layers in the disbursement process and ensure that additional staff resources are in place to monitor and forecast financial flows in a more accurate and timely way for the remaining lifecycle of the project.

Following a review of strategic priorities and continued discussions with DFID advisers, the AgMIP leadership and Co-ordination teams identified a clear need to increase the level of engagement with a broader range of stakeholders. In response to this, additional resources were devoted to identifying relevant stakeholders and understanding how these should be engaged. This included the creation of a “Stakeholder Unit”, additional assessment of phase 1 stakeholder interactions, and the development of coordinated strategies for enhanced engagement with stakeholders in phase 2.

On a technical level, lessons were learnt with regard to the adaptation packages, which it was found, need to be tested in both future and current climate conditions in order to support decision makers balancing short and long-term adaptation planning.

Key actions
Following this annual review, we have agreed on a list of priority actions to be implemented over the next six months to address the high-level recommendations for the overall programme, as well as those made against each output below. These comprise the following:
- The AgMIP Leadership Team will establish protocols that enable teams to quantify confidence and skill improvement of models using standardised measures.
- The RRTs will simulate multiple Representative Agricultural Pathways (RAPs) and adaptation packages in the next phase of AgMIP to reduce and quantify uncertainty in the forecasting of the impacts of climate change on stability of agricultural production and related socio-economic impacts.
- The AgMIP Leadership Team will focus on the development of enhanced institutional capacity to create, disseminate and utilise regional integrated assessments in AgMIP Phase 2.
- The AgMIP Coordination Team will explicitly integrate communications into project design for regional research teams and AgMIP Coordination in Phase 2, culminating in an integrative tool for delivery of decision-relevant information for stakeholders.

Has the logframe been updated since the last review?

No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 1: Improved crop and agricultural economic models, as well as calibrated outputs for Sub–Saharan Africa and South Asia through model simulations of baseline period and model intercomparisons.
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	35
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
AgMIP team protocols and representative agricultural pathways developed and validated for Sub-Saharan Africa and South Asia regions.	Four protocols and one peer-reviewed protocol article. Development of 4 representative agricultural pathways and peer-reviewed article on Representative Agricultural Pathways (RAPs)	5 Protocols, 8 RRT chapters each describing regional RAP, and a RAPs chapter summarizing methods and lessons learnt across the 8 RRT RAPs published in Handbook of Climate Change and Agroecosystems. Protocol Handbook and Guide describing Climate Scenario Generation using the ‘R’ Computer Programming Language published as Appendices. Global Gridded Crop Model Intercomparison (GGCMI) protocols published in peer-reviewed journal. [Milestone Exceeded].
Number of agricultural locations and number of regionally important crops that demonstrate improved skill scores.	100 total in Africa and South Asia/ 2 major crops simulated including sugarcane and cotton.	Continued analysis of 1724 farming sites including 72 sentinel sites in ~20 regions, most with multiple crop/livestock models configured. Each RRT has now demonstrated calibration and noted skill scores for at least two crop/livestock models within their region. Temperature and rainfall trends analysed from at least 30-year observational records. Projected temperature and precipitation changes now tested for significance in deviating from historical variability. Additional vetting of accuracy for crop and economics modelling has increased confidence in results. [Milestone Exceeded]
Peer-reviewed articles on crop and economic model intercomparisons	4 (2 per region).	10 RRT and 5 Regional Integrated Assessment (RIA) methodology chapters published in “ASA Handbook on Climate Change” (Imperial College Press), as well as 10 additional chapters describing additional applications for global and regional assessment. Each RRT chapter includes multi-model climate, crop (and livestock in some cases), and economic simulations of climate impacts as well as the testing of adaptation packages. RRTs are preparing a much larger number of other peer-reviewed publications (at least 1 published, 5 submitted, and 4 in preparation). [Milestone Exceeded]

Key Points
The project continued to deliver strongly against this output. Main achievements include:
- The project delivered improved crop and agricultural-economic models calibrated and validated for the study regions in SSA and SA.
- Current climate baseline period and the 2050s have been simulated with multiple GCM downscaled climate scenarios and DSSAT and APSIM crop models.
- For the entire set of RRT study areas 72 sites have been classified as Platinum (2), Gold (25), or Silver (45). In addition a large number of additional sites (>1000) have been classified as being of Copper standard providing only baseline data that are calibrated to the household survey locations.

Summary of responses to issues raised in previous annual reviews (where relevant)
AgMIP produced a set of accessible 2-pager ‘policy briefs’ to communicate these findings to a wider audience. AgMIP produced briefs on the following topics:
- New findings on changing yields in SSA and SA.
- New crop projection uncertainty maps for W Africa
- New findings on the effects of climate change on agricultural income and poverty rates at local levels;
DFID RED shared examples of best practice.
AgMIP continued to develop its approach to visualising the regional findings (information graphics and policy briefs).

Recommendations
1. AgMIP would benefit from the development of a new version of project protocols for Phase 2.
2. It is recommended that AgMIP establish protocols that enable teams to quantify confidence and skill improvement using standardized measures.
3. Support from the AgMIP Leadership Team to RRT authors is highly recommended as it would provide additional motivation and assurance to achieve high-quality publications.

Output Title	Output 2: Improved regional projections of climate change impacts on crop production and the associated economic implications and identification and prioritisation of regional agricultural adaptation strategies.
Output number per LF		2	Output Score	A++
Risk:		Low	Impact weighting (%):	35
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Number of future scenario simulation years for multiple crops and sites run for SUB-SAHARAN AFRICA and S. Asia, based on improved models.	Completion of simulations for 100 sentinel sites for 3 future time periods for 2 emissions scenarios.	In 9 focus sub-regions based upon prevalent farming systems in SSA and SA, 1724 farms were simulated over 1980-2010 and 2040-2069 periods using ‘multi-model ensemble’ approach. RCP4.5 and RCP8.5 greenhouse gas concentration scenarios were examined, with climate change evaluated considering only mean climate changes as well as additionally factoring in variability changes; [Milestone Exceeded]
Peer-reviewed articles on implications of climate change on regional agricultural production and economies, including adaptation strategies.	20 publications.	18 chapters published in “ASA Handbook on Climate Change” (Imperial College Press) and at least 11 additional major publications from the project. Each or the 10 RRT chapter includes climate, crop (and livestock in some cases), and economic model impacts as well as the testing of adaptation packages. The RRTs have also indicated that they are preparing a much larger number of other peer-reviewed publications (3-10 per team). [Milestone exceeded]
Peer-reviewed articles on analysis of cascading uncertainties.	2 reports and 2 articles – one each per region.	Each RRT chapter includes an examination of uncertainties across 5 GCMs, at least 2 crop models, 2 RAPs, and with/without adaptation packages. An additional chapter is focused exclusively on uncertainty methods, and an additional 9 major publications have uncertainty as a major theme [Milestone Exceeded]

Key Points
The project continued to make strong progress against this output and has exceeded all milestones set for the past year. Notable achievements included:
- AgMIP researchers utilized results from multiple, connected models to enable stakeholders to understand how climate change will affect prevalent farming systems.
- In the past year, the quality of research produced under AgMIP has reached a level enabling publication in prominent international journals. Furthermore, project methods and results have been synthesized in a two-part volume that has been published by a leading UK academic publisher.
- The project has devoted considerable effort to quantify key sources of uncertainty in regional assessment of climate change impacts for SSA and SA, enabling more robust assessments and model improvements.

Summary of responses to issues raised in previous annual reviews (where relevant)
- Transformational adaptation was considered in the development and application of RAPs.
- RRT chapters include recommendations for practical adaptation development, and further evaluation of the plausibility of potential adaptation packages is a key element in the design of Phase 2.
- AgMIP has initiated a Stakeholder Unit to further develop strategies for continuing engagement and delivery of useful results to stakeholders within SSA and SA, which will help the project meet the needs of decision making processes.
- Policy briefs have been developed by several RRTs and summarizing results across SA and SSA. We have now agreed with AgMIP Leadership that a further 7-10 policy briefs will be developed in the coming year.

Recommendations
1. Simulation of multiple RAPs and adaptation packages will be helpful in enabling an investigation of additional sources of uncertainty and potential for future outcomes.
2. More detailed simulations, including additional sub-regions and farming systems beyond those identified in Phase 1, will allow more comprehensive assessment of climate change impacts and allow AgMIP results to contribute to a wider range of stakeholder decisions.
3. The next version of AgMIP protocols would benefit from explicit methodologies oriented at quantifying and visualizing uncertainty.

Output Title	Output 3: Strengthened capacity of researchers (PIs) in Sub Saharan Africa and South Asia to access and use crop and economic models.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	15
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Increased knowledge base and capacity to simulate impacts and adaptation of the SUB-SAHARAN AFRICA and S Africa researchers.	20 PIs capable of simulations, including adaptation strategies to the standard required.	This milestone was met in full at the time of the last AR. Additional achievements include substantial guidance on: the authoring of high-quality scientific publication, creation of effective communication products, and further economic model assessment. [Milestone Exceeded]
Number of calibrated crop and/or economic models actively run by each developing region PI.	Additional 1 – 3 calibrated models run.	This milestone was met in full at the time of the last AR. [Milestone Met]
Number of Sub-Saharan and South Asian researchers able to participate in AgMIP data analysis, research and/or assessment methods.	120 +	This milestone was met in full at the time of the last AR. Additional SSA and SA researchers have participated in project activities through the Coordinated Climate-Crop Modelling Project (C3MP). RRT participants have furthermore initiated new projects applying AgMIP methods and results in collaboration with new partners (e.g., the CGIAR Research Program on Climate Change, Agriculture, and Food Security, CCAFS). [Milestone Met]

Key Points
The project had previously met all milestones in this output at the time of the previous AR, however additional progress was made, including:
- RRT PIs and team members developed skills for authoring high-quality scientific publications, including academic book chapters and scientific journal articles.
- RRTs worked with AgMIP Coordination to produce additional communications materials, including policy briefs, blog posts, infographics, and publication graphics.
- RRT economists and PIs collaborated with AgMIP Regional Economic Team leaders to improve the quality of farming system analyses looking at climate change impacts, including poverty rates under multiple policy and adaptation strategy scenarios.
- AgMIP has attracted the participation of additional researchers through the C3MP activities, and has developed research applications with new partners such as CCAFS.

Summary of responses to issues raised in previous annual reviews (where relevant)
In response to the recommendation made in the last AR, project leadership has continued to analyse surveys of researcher capacity and has undertaken an additional survey focusing on how RRT members viewed their role in the project and their interactions with stakeholders. Analysis from this latter survey is ongoing, and is expected to play an important role in the development of Phase 2. The capability survey conducted in 2014 will be continued to provide a system that will monitor capacity gains over the course of Phase 2.

Recommendations
1. The project has demonstrated considerable gains in researcher capacity, and it has emerged that the next focus area for capacity building should be aimed at institutions.
2. AgMIP should focus on building skills that enable researchers to interact with relevant stakeholders and cultivate a productive relationship with high uptake of science-based information for decision-making.
3. AgMIP should explore methods for national scale assessments to meet the scale of information requested by key policymakers.

Output Title	Output 4: Researchers and end users in Sub Saharan Africa and South Asia better able to access improved and relevant information on regional climate change impacts on agriculture.
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	15
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Number of targeted briefs/ presentations for key regional policymakers.	8 presentations to policy makers.	This milestone was already exceeded at the time of the last AR (10+). Additional presentations and interaction with key regional policymakers have taken place over the last year, leading to more than 20 in total. [Milestone Met]
Key regional policy questions identified and guiding model simulations.	15 questions guiding continuing studies.	This milestone had already been exceeded at the time of the last AR; since then a key new policy question was developed to guide regional integrated assessment addressing the benefits of adaptation under current climate conditions. [Milestone Met]
Quantity of AgMIP data downloaded from AgMIP online system in Sub-Saharan Africa and South Asia.	3 GB	This indicator was also exceeded at the time of the last AR; however, following discussions with stakeholders and AgMIP team leaders, it was decided that this would become a crucial element in the infrastructure of an integrative tool that will be developed during Phase 2 to disseminate and illustrate results in a user-friendly platform. [Milestone Met]

Key Points
Overall progress on this output has continued apace. There were not significant changes from the time of the last annual review, except for the following:
- On communications, AgMIP research outputs have attracted local media interest (in South Africa, Pakistan, Zimbabwe) and the teams have produced numerous media-friendly products including a Vimeo film focused on South-eastern Africa for the Biosphere Defense Project.
- Regional research teams have continued regular interactions with stakeholder groups, holding several workshops and developing stakeholder-friendly presentations.
- The issue of adaptation benefits under current climate conditions has emerged as a key regional policy question relevant for regional decision-makers balancing short- and long-term adaptation planning.

Summary of responses to issues raised in previous annual reviews (where relevant)
- AgMIP further developed and reoriented its ‘Theory of Change’ to focus on stakeholder co-design, emphasize uptake, and deliver decision-relevant tools, evidence, and information.
- RRT researchers conducted additional workshops to continue and expand engagement with regional and national stakeholders (e.g. in Pakistan, Southern Africa, Kenya). These workshops featured new communication materials to increase uptake and use of evidence.
- FACE-IT and IT developments
- Improvement of communications products via policy briefs, infographics
- Re-orientation of Phase 2 with focus on stakeholder co-design and delivery

Recommendations
1. AgMIP should build on the policy briefs already delivered and produce at least 7-10 policy briefs (minimum one per team) and the key themes that will emerge as priorities for stakeholders in the regions.
2. Continue to create and improve communications, including infographics, blogs, audio-visual products, and web articles.
3. Develop protocol for team interactions and engagement with stakeholders and incorporate stakeholder input in the next set of products (engage stakeholder unit).
4. Create data platform to support integrative tool for delivery of decision-relevant information for stakeholders.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
AgMIP activities continued to be predominantly based on research and workshops and there have been no unanticipated cost drivers since the last AR.

With respect to previous years, over the past year there have been more significant fluctuations in exchange rates, which have generated some variations in income.  These would be initially captured by USDA, who is in direct receipt of the DFID funding and subsequently either re-invested into financing further programme activities to be agreed with the DFID lead adviser or returned to DFID.

VfM performance compared to the original VfM proposition in the business case
Over the course of its life AgMIP has been really active in engaging with a number of global partnerships, which included some of the leading international consotia initiatives (e.g. CCAFS, MACSUR, ISIMIP, Global Futures, Harvest Choices, Yield-Gap Atlas). The leadership team is working with GEOGLAM, CMIP and PROVIA to establish direct participation roles in all these initiatives.

AgMIP undertook a rigorous open competition for SA and SSA regional components at the beginning, and now other partners are examining and contributing to the methodology for use in their regions.

USDA worked effectively throughout the life of the project to accommodate all DFID requirements concerning program management and to meet all corporate reporting requests.

AgMIP partnered with ICRISAT to ensure regional salaries and expenses were kept withn appropriate levels and continued to monitor expenditures through the project reporting year.

Phase I of the project managed to achieve all of its objectives within budget and a total of approximately £300,000 in savings, which was accumulated because fo exchange rates appreciation and cost efficiency/savings in programme management, was reinvested into Phase II.

Assessment of whether the programme continues to represent value for money
Yes the project continues to offer very good VfM particularly because of its ability to leverage in-kind contributions from a very large pool of researchers and modellers worldwide.

Quality of financial management
Overall the quality of the financial management for the project was satisfactory and met DFID standards and requirements. These included the putting in place of fiduciary risk management measures and controls to count the occurrence of potential fraud or mismanagement of public funds. However, the management structure for the program caused, at times, significant delays in transfer of funds between partners on the ground, which in the end resulted in the accumulation of an underspend of approximately 500K (pounds). This issue has now been addressed and resolved and we have put in place a more streamlined management structure for Phase 2 to avoid the repeat of such occurrence.

Date of last narrative financial report	25/11/2014
Date of last audited annual statement	01/12/2014

E: RISK (½ page)

Overall risk rating: Low
The overall risk level has not changed over the past year and remains low. The financial management risk element remains as medium but it is accounted by a very low risk in the program delivery. There is, however, a potential element of risk concerning the delivery of phase 2 objectives within the set time period because of the delays in commissioning and signing of the MOU. These delays, which have now been resolved, were due to factors beyond our control and we will consider measures to amortize their impact over the remaining lifetime of the project.

Overview of programme risk
The risk associated with the delivery of objectives for phase 1 is effectively nil because all milestones have been met or exceeded. As outlined above, there is an element of risk for phase 2 due to delays in the commissioning of the funds, which we are looking resolving through a number of measures.

Outstanding actions from risk assessment
We have commissioned an audit of finances and management procedures for phase 1. We have received initial indications that financial management standards were met and relevant procedures followed.

Furthermore, ICRISAT carried out a review of all expenditures and financial reporting by the individual research institutions comprising the regional research teams in SSA and SA. This did not reveal any deliberate mismanagement or misappropriation of public funds, however it identified systemic delays in reporting. This issue has now been fully addressed and measures have been put in place for Phase 2 (including the removal of additional layers in the financial disbursement process) to ensure this is not repeated.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
By the end of the initial end date, the program had delivered against about 90-95% of its objectives. In light of this, and the significance of the results achieved by the program, DFID granted the project a 6-month no cost extension. The project made good use of the extension and all objectives and deliverables have been met, leading to a 100% completion rate.

Performance of partnership (s)
The DFID partnership with USDA was very effective and advantageous; USDA provided good fiduciary risk management and reporting. The partnership between USDA and Columbia was also very effective and it led to a good interaction and complementarity. It leveraged funding to ARS labs, and USDA hosted an N America AgMIP Workshop. USDA is now leading the AgMIP experimental model interface team, and is contributing to the global workshops.

The partnership between Columbia and ICRISAT was very effective in enabling transfer of funds to the region, delivery of objectives on the ground, and reporting. It also leveraged several workshops including multi-model crop modelling and regional economics model training.

Asset monitoring and control
N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
This is a centrally managed research programme which we are funding in partnership with USDA and implementing through Colombia University and a number fo other research institutions in the US, Europe SSa and SA. We do not explicitly use the partnership principles in monitoring and managing the programme, but we rely on USDA to monitor the performance of all implementing institutions.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
There have been no major changes in the evidence in this area of research since last year to determine any implications for the project or warrant any actions. Having successfully contributed to AR5, AgMIP is now gearing up to assemble evidence to contribute towards AR6.

Stakeholder feedback and engagement activities
Over the past year, researchers from the SSA and SA research teams engaged with stakeholders for feedback on interaction, including: co-development of trends in agricultural systems (RAPS); possible adaptation packages to test for climate change impact; and the sharing of results from the regional integrated assessments of climate change impact as expressed in likely yield or extent of poverty. The feedback included expressed interest in further engagement including these, and additional processes.

Discussions with farmer organizations in Lesotho, led them to collectively realise that they are already experiencing the effects of changing climate and that they should utilise their organisation to put pressure on their research organizations and policy makers to develop strategies that could mitigate effects – “to use the system to change the system”.

AgMIP RRT meetings in Namibia to present possible outcomes to Directors of Agriculture led them to commit to “help establish a platform to expose farmers to the model outputs through the Agricultural Extension services” provided by the Ministry of Agriculture.

Most stakeholders presume that climate change means adverse impacts. However, in some locations (for instance, high altitudes) there can be beneficial impacts. Consultations in Kenya on results of integrated modelling of upland farming systems in Embu district resulted in stakeholders comprehending that there can be both positive and negative impacts of climate change. For some, it was the first time they had considered that management under changing climate conditions can include “consideration of how to maximise opportunities presented by positive impact while minimising hardship associated with negative impact”. This is a departure from prior held perception that “climate change impacts are all negative”. These stakeholders identified a number of priorities going forward, including establishing a common platform at regional level for continuous dialogue; projecting climate change impact and timely advice on economic gains by adoption of different farming system modules; creation of a regional news letter to disseminate the knowledge to farmers; the need for additional capacity building for scientists; ways to facilitate linkages between the scientist and policy makers across the region by undertaking visits; and educating about the modelling approach for integrated assessment of climate change impact at the graduate level.

In Tanzania, stakeholder engagement contributed to the development of their Agricultural Climate Resilience Plan, which has since been completed.

Stakeholders in Southern Africa noted the many initiatives on climate change lead to many voices of action. They encouraged researchers to “collaborate and speak out of one voice, working with stakeholders to gather what they need, and disseminating findings that assist in planning and decision-making, with follow-up after meetings.” They encouraged increasing the number and frequency of stakeholder engagement.

Cross-site dialog from a feedback workshop with partners from Zimbabwe, Malawi, and Mozambique was useful to share information, create network spirit, and increase motivation. On-the-ground facilitators enabled more effective communication, coordination and engagement with (and from) decision makers. Researchers learned that stakeholders are not so interested in the science, but in the practical implications. Reaching stakeholders is time-demanding and immediate scientific rewards are not easily obtained.

Active discussions, visioning exercises on climatic change impacts, and willingness to try innovations were among the expressed areas for continued development from the south-east African stakeholders. One noted: “A lot that has been done regarding impact of climate change on crop production but the information is fragmented and confined to a few institutes and individuals”. There are still sceptics with regards to data or outputs from models mainly because of the associated uncertainties. Expressed uncertainty continues to undermine uptake of information by risk-averse policy makers.

In Pakistan, stakeholders noted: “results should be disseminated in national language in the form of brochures, pamphlets, booklets etc.” Stakeholders encouraged additional interaction through outreach activities, workshop, seminars and field days at farmers’ fields, including ‘pathway development’.

Upon learning that adoption of an adaptation package including advancing sowing dates could significantly increase net farm returns and per capita income in specific sites in the Meerut district of northern India (whereas continuation of current practices could result in significant declines in same), the Deputy Director General for the Indian Centre for Agricultural Research Natural Resource Management and Technical Expert for National Area Rainfed Authority requested the research team to enable others to identify and test adaptation strategies independently, as well as integrated way so that researchers, developmental officials and policy makers can put their own efforts to increase agricultural productivity and thereby increase the food security of the region. In addition, the Deputy Director General for Education stressed the need to: “incorporate more adaptation measures like selection of short duration, disease resistant varieties, site specific nutrient management, irrigation management system, conservation agriculture, resource mapping and integration with livestock to develop resource efficient and economic farming system module under the climate change scenario”.

Monitoring progress throughout the review period
Monitoring activities throughout review period consisted of a monthly iterative process by the leadership team to analyse datasets, model configurations and climate impacts results and interpretation. These were discussed regularly with the DFID advisers and any appropriate and relevant actions agreed to improve performance where needed.

Progress of regional research activities was monitored by participation of teams in regular calls, interaction with AgMIP team leaders and resource persons and participation at AgMIP events held on the margins of major international conferences. Furthermore results generated by the RRTs were peer reviewed as part of the publication of Phase I results in scientific journals and volume IV Part 1 and 2 of the Handbook of Climate Change and Agro-Ecosystems.

The Annual Review process consisted of a field visit to Columbia University were the leadership and co-ordination teams of the project are based and a final review of progress held at the AgMIP 5th global workshop.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process