Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Green Climate Fund – Admin budget – support to the interim secretariat and interim trustee
Programme Value: £3,000,000		Review Date: March 2015
Programme Code: 202737-102	Start Date: Mar 2013	End Date: Dec 2015

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A
Risk Rating	Low	Low

Summary of progress and lessons learnt since last review

During the last year UK support has helped enable the Green Climate Fund (GCF) to successfully (i) put in place all the essential measures needed for the Fund to become operational, and (ii) hold an Initial Resource Mobilization (IRM) process to begin mobilising funds for programming.

Among key achievements were:

1. GCF Board agreement on the essential design requirements for the Fund’s operationalisaton, including: an initial project approval process; an initial results management framework; a financial risk management framework; and an initial investment framework;
2. Setting in place a ‘readiness’ programme to support developing countries in their identification and preparation of projects and programmes for funding;
3. Successfully launching the IRM process, which has so far resulted in overall pledges of over US$10 billion (from over 30 countries, including up to £720m from the UK), reflecting the significance of this new Fund and the importance of its mission; and
4. Launching an accreditation process to identify implementing entities and intermediaries to be the Fund’s agents in deploying these resources.

Other key elements of progress include:

- The GCF Secretariat has transitioned from ‘interim’ status into a fully established Secretariat at the Fund’s Headquarters in Songdo, South Korea, able to support the work of the Board and move ahead with effective implementation and operationalization of the Fund;
- Significant progress in staffing the Secretariat (32 staff members recruited by February 2015) and improvement in the quality of papers being produced for the Board during the year;
- World Bank continuing to provide effective services as the Fund’s interim trustee (including financial and programme management, accounting and reporting)

Summary of recommendations for the next year

The final DFID payment for this programme (support to GCF design phase) was made in December 2014. In future, administrative costs associated with running the GCF will be covered from the contributions pledged during the IRM. DFID and DECC have recently completed a Business Case for a UK contribution of £720m over the IRM period (2015-18). This Business Case has been approved by DFID’s Quality Assurance Unit and DECC’s Investment Committee and is currently with Ministers for approval. It sets out the management and monitoring arrangements for a future UK contribution.

In 2015 the Secretariat and interim trustee need to focus on supporting the Board to make the key decisions needed to enable initial programme/project funding decisions to be made. The Fund should continue to benchmark its costs against comparable international institutions, and seek ways to make efficiency savings, as directed by the Board. The UK will continue to monitor and scrutinise GCF administration costs through our seat on the Board, including by pushing for policies and appointments that maximise VfM.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202737/
DevTracker Link to Log frame:

Outline of the programme

This programme supports the administrative budget of the GCF, a fund established under the UNFCCC with the intention that it will become the main multilateral mechanism for delivering climate finance. It is expected to deliver a significant portion of the $100bn/year that developed countries have committed under the UNFCCC to mobilising for developing countries by 2020. The Fund has been in its design stage, and – given the intended size and responsibilities of the Fund – it is imperative that it has the resources necessary to fulfil its mandate. To date resources have in particular been needed to cover Secretariat costs, Board meetings, staff salaries, new office and system set up costs, travel, and interim trustee services.

UK support has helped support the GCF design process so that the Fund can become operational, with the following expected key outputs from the Secretariat and/or interim trustee:

- Support for the Board in completing the design of the Fund through:
  - preparation of policy documents on Fund design
  - support for Board meetings and committee meetings (including logistical costs)

- Operationalizing the fund through:
  - Hiring of experts for country programming, mitigation and adaptation, private sector experts, communications and outreach and support services
  - Developing operational policies and procedures (including developing processes by which the Fund can be accessed, developing a results management framework and working with developing countries and intermediaries to develop a pipeline of proposals)

Provision of interim trustee services (financial and programme management, investment management, accounting and reporting, legal services, IT systems)

The UK’s contribution represented 8.75% of the needs of the Secretariat for 2014 (ie. £2.5m out of £28,555,780 requested by the Secretariat for 2014). This reflects the importance placed by the UK on a successful outcome for the GCF - aligned with UK strategic objectives per HMG’s International Climate Fund – in supporting a mechanism that will make a significant contribution to helping developing countries grow their economies in a low carbon, climate resilient way.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The programme is on track to deliver the expected outcomes by the end of the programme. This was to support the GCF Board to design a fund that delivers the necessary volumes of finance at scale, with the right geographical coverage, on the right terms and with sufficient leverage of private sector resources. Decisions taken by the GCF Board in 2014 to agree the essential design characteristics of the Fund mean that these features are now in place. This enabled the ‘Initial Resource Mobilisation’ phase to begin in 2014, which has so far led to total pledges of $10.2bn to the GCF, from over 30 countries. This impressive mobilisation of resources is a major achievement for the GCF, and reflects the confidence felt internationally in the progress made by the Fund in 2014 and the role it will play in future delivery of climate finance.

Overall output score and description

A – outputs met expectation.

UK support has helped key outputs to be achieved, notably:

- Support to the GCF Board to complete the design phase of the Fund, including through support to the Secretariat to prepare policy documents for the Board on GCF design, and support for the logistical costs of Board meetings
- Enabling operationalisation of the Fund through the hiring of relevant staff for the Secretariat (including experts on mitigation, adaptation, the private sector, country programming, and communications) and the development of operational policies and procedures to make the Fund effective.
- Effective provision of interim trustee services by the World Bank, including financial and programme management, accounting and reporting.

Key lessons

The programme has demonstrated the value of support to a new institution in its design stage. It has also underpinned the UK’s influence on the GCF’s design, helping to ensure a strong UK voice in securing our desired design outcomes (eg on the policies and modalities of the Fund).

Internally lessons have been learnt about the importance of drawing on broad expertise across the organisation in order to shape robust policies – eg. administrative and HR issues; procurement and commercial; legal.

We are already working closely with other multilateral leads to share experience and inform future positions (including through links to future MAR processes).

Key actions

- Subject to Ministerial approval, effective management of the UK’s £720m contribution to the GCF, as set out in the Business Case.
- Continued scrutiny of the Fund’s administrative budget and operations to assess cost-effectiveness and value for money
- UK to take up role on GCF’s Appointments Committee, to help ensure appropriate appointments are made on the right terms in 2015, including Heads of the Integrity Unit, Evaluation Unit, and Independent Redress Mehanism
- Team to work with CED’s new Commercial Adviser to further develop and strengthen the GCF’s commercial arrangements.

Has the logframe been updated since the last review?

No
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Policy documents for the Board
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Basic policies and programming approach, policies on financial instruments, policies related to the accountability framework, management policies and other administrative policies		Outputs met expectations in this area, with a large number of documents on the Fund’s basic policies and programming approach agreed during 2014.

Key Points

UK support to the GCF secretariat helped enable key decisions on the Fund’s design, operational policies and approach to programming to be agreed in 2014.

A major achievement was concluding Board agreement on the 8 operational policy design requisites to trigger the GCF’s resource mobilisation process, culminating with a pledging conference in November 2014. Key policies and programming approaches agreed included the Fund’s initial approval process, initial results management framework, initial investment and financial risk management framework, and process for assessing proposals for funding. Another key decision to guide the Fund’s approach to programming was on the intial allocation of resources (with the decision to aim for a 50:50 balance between mitigation and adaptation over time, and to maximize engagement with the private sector, including through a significant allocation of resources to the GCF’s Private Sector Facility).

Other policy documents produced/agreed during the year included the following: policies for financial contributions; a framework for accrediting implementing entities, including the Fund’s fiduciary principles and standards and environmental and social safeguards; administrative guidelines on procurement; and policies on HR and travel. Progress on these – and other – policies means that the GCF can now start to receive and programme funds.

Overall the Secretariat was required to produce a large number of documents in the year (including around 40 papers for the October Board meeting) – a challenge for a Secretariat that was still being staffed up as the year progressed. As the secretariat became better-resourced, the quality of work was seen to improve – notably the analysis carried out for the Board’d informal meeting in Jan 2015.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

No changes to Output 1 are proposed.

Output Title	Programming document for the Board
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Outline of policy priorities, expected results and scenarios to support contributions negotiations		Output moderately did not meet expectations in this area.

Key Points

The development of a specific programming document (ie. with potential programming areas and funding scenarios) was not explicitly achieved in 2014, although the secretariat did produce a ‘prospectus’ outlining the Fund’s role and position within the broader climate finance architecture. Progress was also made on a number of key essential items which will inform programming, notably agreement on the Fund’s Initial Investment Framework and its Initial Results Management Framework. These together set out what the GCF aims to achieve and how it will select projects and investments to achieve these aims.

Within the Results Management Framework, performance measurement frameworks to measure impact in agreed priority results areas (for both adaptation and mitigation) were agreed. Broad policies and criteria for the Investment Framework were also agreed, although further refinement of these is needed in 2015 to ensure the proposals that are best designed to achieve the GCF’s goals are selected for funding.

A combination of Secretariat staffing constraints and some resistance in the Board to the idea of a programming document (linked to concerns it could restrict the Board’s flexibility on project approvals) meant that such a document was not produced in 2014. However, the secretariat did prepare some initial analysis on the expected impacts and role of the Fund, identifying potential areas of impact (where opportunity coincides with unmet need) and highlighting potential priorities for programmiing. The Board requested further work on this – including options for determining the Fund’s investment portfolio – which is due for consideration by the Board at its meeting in March 2015. This fits with a ‘critical path’ timeline identified by Members of the Board, with the intention that the Secretariat’s impact analysis work will help to inform programming scenarios, ahead of the first funding decisions being taken in the Board’s third meeting in 2015 (scheduled for October).

The Secretariat and interim trustee provided good support to the contributions negotiations in 2014, culminating in agreement on policies for contributions which set out the types and terms of contributions to the Fund, as well as policies on the Fund’s effectiveness and triggers for future replenishments.

The Fund also started providing ‘readiness’ support to countries in 2014. This is aimed at helping countries to: develop strategies for national-level engagement with the Fund; coordinate national stakeholders; help national and sub-national institutions meet the accreditation standards of the Fund; and support the development of initial pipelines of programme and project proposals.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

No changes to Output 2 are proposed.
Output Title	Cost effective administrative support provided to the Board of the GCF
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Arrangements made for up to 6 Board meetings and for stakeholder engagement		The secretariat has now arranged 8 Board meetings (and one Informal Board meeting), with the 9th due to take place in March 2015. 3 ‘initial resource mobilisation’ meetings were also arranged.

Key Points

In the last year the GCF Secretariat has transitioned from ‘interim’ status into a fully established Secretariat at the Fund’s Headquarters in Songdo, South Korea, able to support the work of the Board and move ahead with effective implementation and operationalization of the Fund. Significant progress has been made in staffing the Secretariat (32 staff members recruited by February 2015), including the hiring of experts for country programming, mitigation and adaptation, private sector engagement, communications and support services. An improvement in the quality of the Secretariat’s work (eg. in producing Board papers) has been noted by Board members. However, further recruitment is needed to bring the Secretariat up to full complement, and there remains a risk that the secretariat is unable to attract and retain staff at sufficient levels of expertise and capability, leading to delays and/or higher costs.

In 2014 the Secretariat has prepared material for the full operationalization of the Fund and the work of the Board (in line with the GCF’s 2014 work plan and relevant Board decisions). This also included building the systems for and staffing the Secretariat, facilitating the initial resource mobilization process (IRM), and carrying out readiness outreach work with developing countries.

The Secretariat’s work included the preparation, development and follow-up for 3 Board meetings in 2014 (February, May and October). This enabled important milestones for the Fund’s operationalization to be reached, including – notably – the Board’s adoption of the essential requirements that made it possible to commence the IRM process so that pledges to the Fund could be made. The Secretariat was involved in preparing for the 2 IRM meetings (June/July and September) and the High-Level Pledging Conference in Berlin in November.

The Secretariat has also supported the different committees and panels of the Board, which were established to deliver expert input and guidance. This includes support to the Investment Committee, Risk Management Committee, Ethics and Audit Committee, Accrediation Committee and the Accreditation Panel, as well as the Private Sector Advisory Group.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

No changes to Output 3 are proposed.
Output Title	Cost effective trustee services provided to the Board of the GCF
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Provision of Financial and programme management, Investment management, Accounting and reporting, Legal services, IT systems		The World Bank has continued to provide effective services as interim trustee, including support to the IRM process as the Fund prepares to receive contributions for programming.

Key Points

The World Bank continued to serve as interim trustee in 2014 (with the Green Climate Fund Trust Fund established at the World Bank for this purpose). During the Fund’s design phase the interim trustee has received contributions into the GCF Trust Fund and made cash transfers as appropriate to cover the administrative costs of the Fund’s start-up and governance. It has submitted quarterly reports to the Board since June 2012. Once the Fund becomes fully operational the interim trustee role will become more complex, receiving contributions and transfering funds to accredited implementing entities for projects and programmes, as approved by the Board.

During 2014 the interim trustee also provided vital support to the IRM process – including on appropriate financial policies and procedures for contributions, and the design of provisions and agreements to enable the receipt of funds pledged by contributors (contribution arrangements).

The Board (and Secretariat) has been satisfied with the interim trustee’s performance, and at its October 2014 meeting the Board decided to invite the World Bank to continue serving as interim trustee until a permanent trustee is in place (no later than April 2018). This provides certainty on the interim trustee during the IRM period.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

No changes to Output 4 are proposed.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key administrative cost drivers have been staff costs for the GCF Secretariat; travel; logistical costs of Board meetings; and the cost of interim trustee services provided by the World Bank.

A detailed consideration of the GCF’s VfM is set out in the Business Case for the proposed new £720m contribution.

VfM performance compared to the original VfM proposition in the business case

Performance has been as expected. The administrative policies of the GCF are based on the well-established policies of the Asian Development Bank on the basis that: it was most efficient for the GCF to follow an existing model rather than developing its own policies; between the United Nations and MDB models the MDB policies would attract staff with the right level of expertise; and the ADB model is most relevant for the region given the location of the GCF Secretariat in Songdo, Republic of Korea. The DFID Multilateral Aid Review in 2011 scored the Asian Development Fund (the development arm of the ADB) as a 3 (Satisfactory) for cost and value consciousness. The 2013 MAR update noted further improvement in this area, with specific reference to the administrative costs of the ADB being low compared to peers.

Assessment of whether the programme continues to represent value for money

DFID has continued to monitor the work of the Secretariat and interim trustee through our position on the GCF Board. This includes review of narrative and financial reporting (UK led donor scrutiny of the Adminstrative Budget at the most recent GCF Board meeting in October). We assess that the programme continues to represent value for money.

Without UK support the GCF Secretariat and interim trustee could not have provided the services required by the Board to operationalise the Fund as effectively in 2014. This would have delayed (or possibly even derailed) progress by the GCF towards achieving its objectives, in line with UK goals, of supporting low-carbon, climate-resilient development in developing countries.

Quality of financial management

The World Bank as interim trustee provides good quality financial management and regular reporting to the Board. The Secretariat has also now recruited an experienced CFO, with a team of support staff, and a General Counsel and Legal Counsel to provide legal expertise.

Date of last narrative financial report	October 2014
Date of last audited annual statement	September 2014

E: RISK (½ page)

Overall risk rating: Low

Our assessment of financial risk and fraud remains low, given the World Bank’s robust systems for financial management, and monitoring and reporting of expenditures.

Overview of programme risk

Unchanged. A risk analysis for future operations of the GCF is included in the Business Case for the proposed £720m contribution.

Outstanding actions from risk assessment

None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Yes – the programme is delivering against the planned timeframe, with key design requirements of the Fund agreed by the Board and pledges received in 2014, paving the way for programming to begin in 2015. However, the timeframe for delivery has been tight, with Board papers at times delivered late and of questionable quality, making it harder for the Board to maintain progress. This highlights that without the UK contribution it is less likely the Fund could have reached agreement on all the requirements for operationalization by 2014.

Performance of partnership (s)

Strong partnership between DFID (as UK Member of GCF Board) and the GCF’s Secretariat and interim trustee (World Bank).

Asset monitoring and control

We retain a high degree of confidence in the management of GCF assets (given World Bank’s role as interim trustee). This aspect will become more complex once projects start being approved and programming begins.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The interim trustee maintains accounting records and financial data on the GCF Trust Fund and provides quarterly financial status reports to the Board. The GCF Trust Fund is also included in the World Bank’s annual Single Audit of trust funds, with the last report being provided in September 2014.

An Independent Evaluation Unit is being established to conduct independent objective evaluations of the performance of the Fund once programming begins.

The GCF also provides an annual report to the UNFCCC COP.

Monitoring progress throughout the review period

DFID has monitored the GCF secretariat’s performance throughout the review period primarily through participation in – and review of documents prepared for – Board meetings (Feb/June/Oct 2014). We have also had regular contact with the secretariat and interim trustee – and consultations with relevant NGOs and other stakeholders to monitor views on performance.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process