Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Palestinian Market Development Programme (PMDP) to Strengthen the Private Sector in the Occupied Palestinian Territories (OPTs)
Programme Value: £19.3 million		Review Date: 16/03/2015
Programme Code: 201828	Start Date: 21/10/2013	End Date: 31/11/2019

Summary of Programme Performance
Year	2013	2014
Programme Score	C	A++
Risk Rating	Medium	Medium/high

Summary of progress and lessons learned since last review

The PMDP scored C in its previous Annual Review in because of procurement delays in the start-up and overly ambitious milestone targets for the first year. Since then, however, the programme has become fully operational and during the reporting period (March-December 2014) it has substantially exceeded expectations at the outcome and output levels. This was assessed and scored according to the achievement of the targets under each indicator. Evidence collected shows the programme has exceeded its targets under most of the indicators.

The table below summarise 2014 Annual Review scoring.
	Output	Impact weight %	Score
1	Improved private sector skills and innovation	70%	A++
2	Market System failures addressed in specific sectors	15%	A
3	Strengthened trade and investment linkages with the international markets	15%	A+
	Overall output score		A++

Key lessons learned since last review

1. Given the dynamic political and economic situation in the Occupied Palestinian Territories (OPTs), the programme needs to continue be flexible and ready to respond to changes of the private sector’s needs and priorities. For example, PMDP was able to respond to help Gazan businesses which were physically damaged due to the Gaza conflict to make the repairs they need to get back into business.
2. We found it beneficial to look at the interconnections between different market systems in order to ensure more sustainability and scale of interventions. For example, under the market analysis of the Multinational Enterprise (MNE) software outsourcing to Palestinian companies, we looked into the interconnection with the market of the Palestinian diaspora’s Information and Communication Technology (ICT). We found attracting Palestinian diaspora to open offshore offices for their ICT international firms in the OPt has significant potential for expanding the total sales and exports of the ICT outsourcing sector.
3. In the process of development of market system analysis there is a need to engage experts in market system development at different intervals. This enhances the outcome of the studies.
4. We found it useful to engage with diaspora organisations that are not economically focused. Even though this required continuous dialogue and time, working with them on economic issues brought about change. For example, PMDP conducted continuous communications and meetings with the American Federation of Ramallah Palestine (AFRP) and the Ramallah Municipality that led to an initiative to establish an endowment fund and an investment company to invest in strategic projects in Ramallah with the involvement of the Palestinian diaspora.
5. Frequent change in the government could impact the implementation of the programme mainly in the activities that are expected to be implemented in partnership with the government; such as the Commercial and Trade Representatives (CTR) and the Palestinian Investment Promotion Agency’s (PIPA) components. We learned that when this does happen, it is important for DFID and PMDP to proactively engage with the new contacts and share the programme’s objectives and previous agreements to ensure smooth transition.
Progress against previous recommendations

In April 2014 we conducted the first annual review which covered only the inception phase (Oct 2013 – Feb 2014) of the programme. It recommended two main actions:

to ensure the inception report meets the programme’s objectives and the proposed implementation plan is in line with best practice.

DFID and DAI (programme implementer) to revisit the logframe and make amendments to reflect the findings of the inception phase including incorporating gender specific indicators based on the gender strategy that was developed.

We reviewed the inception phase, sought advice from advisers and provided comments and feedback to DAI including gender specific indicators which were addressed in the final inception report, implementation plan, and the revised logframe

Summary of key recommendations for the period Jan 2015 to December 2015:

1. PMDP and DFID will continue to monitor the volatile security situation in OPTs (especially in Gaza) closely and update the risk register quarterly.
2. Ensure the programme is flexible and use this to address specific needs in various sector/target groups through developing new interventions and / or modifying existing criteria.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3598717.doc / BC Addendum Quest #: 4850267
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4663450.xlsx / Revised logframe Quest #: 4663450

Outline of the programme
What need are we trying to address?
Although the Palestinian economy grew at an annual average rate of 8.2% from 2006 to 2011, this was largely driven by donor aid and public sector growth, and has failed to address high unemployment and high poverty rate. The Palestinian economy continues to be constrained by the occupation and remains vulnerable to external shocks. As international aid declined in the years running up to 2012, the government struggled to meet its financial obligations. This resulted in a deep fiscal crisis, during which delays in the payment of civil servants’ salaries were not uncommon. As a result of the recent conflict in Gaza, the Palestinian economy contracted by 4% in 2014 and unemployment reached 27% (17% West Bank, 43% Gaza)[1]. The figure is much higher among women, young people and Gazans. To absorb the growth of the labour force, the OPTs need growth to be sustained at 7-8%. This depends on the establishment of a dynamic productive and competitive private sector. Increasing GDP will in turn increase tax revenues for the Palestinian Authority (PA), promote fiscal sustainability and reduce donor dependence.
[1] Q4 2014 labour force statistics, PCBS

What we are doing to tackle the problem?
By October 2019, the UK will provide up to £15 million for the Palestinian Market Development Programme (PMDP) to strengthen the competitiveness of the private sector in the Occupied Palestinian Territories (OPTs). This includes £2 million which was approved in February 2015 to help Gazan businesses which were physically damaged in the conflict to get back into business.

The PMDP has a number of components: 1) Grants[2] and technical assistance to mitigate the risk associated with business development in the fragile context of the OPTs. 2) Market analysis to identify and address market failures. 3) Strengthen inward investment and transfer of ‘know how’ to Palestinian institutions. This is in line with our Operational Plan commitment to increase long-term growth and employment by addressing government and market failures.
[2] PMDP will encourage SMEs to take a risk to invest in developing new products or/and enter new markets by sharing the risk through matching the cost of the firms’ investment which may range between (25%-75%) of the total cost.

The EU is co funding the programme with Euro 5.3 million bringing the total budget of the programme up to £19.3 million. The EU’s contribution is channelled through a delegated agreement with DFID.

Expected results:
By 2019, the PMDP is expected to help 600 Palestinian firms (20% are managed or owned by women) to develop and improve 281 new products and enter 321 new markets. Over 300 companies will be expected to report improved performance on an annual basis, 120 to report increased exports and 120 to start using their own funds to develop their businesses. Our support will leverage a minimum of £100m of additional attributable sales. Further results will be added to the logframe to reflect the new approved support to Gazan’s firms and in line with programme’s Gender strategy.

Who implements the support we provide?
Development Alternatives Inc Europe (DAI Europe) implements the programme. The evaluation supplier is GDSI. We use the World Check Company to vet all recipient businesses against links to terrorism. The programme is being overseen by a Steering Committee from DFID, the EU, and the Palestinian Ministry of National Economy (MoNE).
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome statement is: Improved competitiveness of the Palestinian private sector

Outcome indicator data are collected on yearly basis to allow the project interventions under each output to realise change. The table below summarises progress made under the outcome level and key obstacles faced in the reporting period covering March – Dec 2014. The results show that the programme has substantially exceeded its 2014 outcome targets and that PMDP is currently on track to reach its 2019 programme objectives. For indicators 10-13, we will work closely with PMDP team and the Evaluation supplier to develop more robust methods to quantify and measure progress by mid of 2015

Contributing output	Outcome indicator	Planned	Achieved to-date	Description / planned 2019 and / % attained to date
Output 1: Improved private sector skills and innovation	Number of enterprises reporting improved annual performance	0	33	Substantially exceeded expectations for 2014. 33 companies reported improved annual performance 45% of which are owned or managed by women. / Planned for 2019: 300 / % attained to date: 11%
	Number of enterprises reporting either increased exports or exporting for the first time	0	20	Substantially exceeded expectations for 2014. The amount of reported export sales reached £1,378,162. / Planned for 2019: 120 / % attained to date: 17%
	Number of jobs created (net)	10	80	Substantially exceeded expectations for 2014 / 50 Males, 30 Females / Planned for 2019: 1000 / % attained to date: 8%
	Value of additional sales attributable to Palestinian Market Development (£m)	0	3.1	Moderately exceeded expectations for 2014. / 56% of the increase in sales was from local sales and 44% was from export sales. / Planned for 2019: 100 / % attained to date: 3%
	Total numbers of new domestic and foreign markets entered	0	44	Substantially exceeded expectations for 2014. / Grantees reported a total of 44 new markets entered of which 82% are export markets including the US, EU, Russia, and Ukraine. The rest (18%) are local markets. / Planned for 2019: 321 / % attained to date: 14%
	Total number of foreign and domestic markets entered by women owned/managed firms	0	16	Moderately exceeded expectations for 2014. / Female owned or managed enterprises entered 16 new markets, 6 of them were local markets and the rest were export markets. / Planned for 2019: 33 / % attained to date: 48%. This will largely exceed higher original target on current trend
	Total Number of improved Products and services developed	5	39	Substantially exceeded expectations for 2014. / Fourteen products were developed and 25 products were enhanced during the previous 10 months. / Planned for 2019: 281 / % attained to date: 14%. This will achieve higher original target on current trend
	Number of new or improved products and services developed by women owned/managed firms	0	19	Moderately exceeded expectations for 2014. / Planned for 2019: 28 / % attained to date: 68%. This will achieve higher original target on current trend.
	Number of enterprises using own funds to pay for Business Development Services	0	5	Moderately exceeded expectations for 2014. / Five of the current grantees used Business Service Providers (BSP) services using their own fund. Female owned or managed enterprises were the majority of them. / Planned for 2019: 120 / % attained to date: 4%.
Output 2: Market system failures addressed in specific sectors indicator.	Extent of positive change in knowledge, attitude, or practice among the targeted group in analysed market systems.	No target	Not assessed	For 2014, PMDP has not reported achievement. This is due to the fact that three market system studies have been completed relatively recently and it was premature to gauge the effect of these studies on the analysed market systems. By mid-2015, the evaluation supplier will assess the contribution of studies and the followed interventions.
Output 3: Strengthened trade and investment linkages with international markets	Extent of improving Palestinian Investment Promotion Agency’s (PIPA) capacity	No target	Not assessed	It is premature to assess the improvement of PIPA’s capacity at this stage given that the PMDP’s engagement with PIPA started only in the past 10 months. According to the GDSI, PIPA’s management appeared to have valued PMDP’s support in the development of the Strategy and the Action Plan. It has been noted that a comprehensive and structured approach to the development of PIPA’s capacity is a fairly new measure for PIPA but it is nonetheless a desirable approach for them going forward. Achievement under this indicator will be influenced by PIPA’s and PA’s ability, commitment and continuity to deliver change. DFID will continue to work closely with the PA to implement PIPA’s strategy. / In mid-2015, DFID and PMDP will work closely on defining more robust methods to quantify and measure progress on this indicator.
	Extent of customer satisfaction with the Commercial Trade Representative’s (CTR) function	No target	Not assessed	The indicator was not assessed. In mid-2015, DFID and PMDP will work closely on defining more robust methods to quantify and measure progress on this indicator.
	Number of case studies show knowledge, attitude, or practice change among targeted Diaspora people	0	0	The indicator was not assessed. In mid-2015, DFID and PMDP will work closely on defining more robust methods to quantify and measure progress on this indicator.

Overall output score and description

	Output	Impact weight %	Score
1	Improved private sector skills and innovation	70%	A++
2	Market System failures addressed in specific sectors	15%	A
3	Strengthened trade and investment linkages with international markets	15%	A+
	Overall output score		A++

Summary of progress

The first output substantially exceeded its targets, while the second and the third outputs met and moderately exceeded their targets respectively. On average the programme substantially exceeded its targets.

The three outputs of PMDP are proving to be very complementary with significant engagement between output two and outputs one and three. Output 2 systemic analysis has identified opportunities for the other two outputs to target some of their interventions on improving overall market efficiency.

Finally, PMDP has ensured that the programme outputs are gender sensitive and included women and marginalized areas in line with the gender strategy’s recommendations. Communications and Outreach activities continued throughout the year. The PMDP produced press releases, developed flash news, monthly factsheets, and engaged with targeted groups through the programme’s website and social media.
Key actions
General:
1. PMDP and DFID to amend the logframe to add new results to reflect the new approved support to Gazan’s firms that sustained physical damage as a result of the conflict by May 2015.
2. In mid-2015, DFID and PMDP will work closely on defining more robust methods to quantify and measure progress on outcome indicators 10-13 (PMDP’s M&E officer, Senior Policy and Programme officer, Evaluation supplier, and MENAD Statistics and Evaluation Adviser).
3. PMDP and DFID will continue monitor the volatile security situation in OPTs (especially in Gaza) closely and updating the risk register quarterly.
4. Evaluation supplier to hold a one-day Theory of Change workshop with the engagement of DFID and PMDP by October 2015.
5. Evaluation supplier to undertake a full external Value For Money (VfM) assessment as part of the 2016 annual assessment with the engagement of an external international VfM expert.
Output 1:
1. By April 2015, PMDP to recruit the required resources to ensure fast and efficient delivery of assistance in Gaza.
2. PMDP will propose new interventions or/and amendment to criteria to address specific needs in various sector/target groups by October 2015. These will be subject to the steering committee approval.
Output 2:
PMDP to assign local experts in market system development in each Market System Analysis (MSA) at different intervals.
Output 3:
1. PMDP and DFID to continue monitoring quarterly progress and commitment of PIPA’s Board of Directors (BoD) and management towards implementing its strategic framework.
2. PMDP to facilitate understanding between MoNE and MoFA regarding Commercial Trade Representatives (CTRs) component programme by October 2015
3. PMDP to propose new additional delivery options to the CTR component by October 2015

Has the logframe been updated since the last review?
The logframe was revised after the first annual review on two occasions;
In May 2014, DFID, evaluation supplier, and PMDP revised the logframe’s milestones to reflect the findings of the inception phase report. In addition, further gender related indicators where developed in line with the programme’s gender strategy.

In October 2014, Ministers approved a £2 million cost extension for the programme - £1.5 million to enable the programme to help an additional 120 companies under output 1 bringing the total target from 480 to 600. The remaining £ 0.5million will support the establishment of the new Palestinian Authority (PA) Delivery Unit that will provide oversight and implementation of government reform measures and coordinate government efforts in the design and implementation of the Initiative for the Palestinian Economy.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved private sector skills and innovation
Output number per LF		1	Output Score	A++
Risk:		Medium	Impact weighting (%):	70%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Total number of enterprises assisted	30	73
1.2 Number of women owned or managed enterprises assisted	6	26

Key points

1.1: The programme substantially exceeded its target for output 1.1 assisting 73 companies of which 41 are in the West Bank (WB), 4 in East Jerusalem (EJ) and 14 in Gaza in different sectors. The process of selecting and assisting the companies included:
- Conducting 44 information session and outreach workshops directed towards the private sector throughout the West Bank and Gaza.
- Receiving 233 applications from all regions in the West Bank, East Jerusalem and Gaza and represented 12 different sectors.
- Processing 144 applications (105 WB, 39 Gaza), and approving 95 (75 WB, 20 Gaza).

The demand on grants in Gaza declined after the recent conflict in summer 2014 which caused physical damage to more than 500 companies. The private sector needs changed from technical assistance to finding ways to get back to business. The programme launched a new grants window targeting partially or fully damaged companies to help the companies to get back to operation. The window was launched in November 2014 and received 499 applications, representing 11 sectors, by the end of 2014.

2.1: The table shows that the programme assisted 26 companies (21 in WB, and 5 in Gaza) that are women owned or managed, thus substantially exceeding its target (6). In line with the Gender Strategy of the programme, PMDP have given 5 extra points to the scoring sheet of the businesses which are women owned or managed. According to the Evaluation Supplier’s Annual Report, women owned /run firms have been more successful at the outcome level, outperforming their male counterparts during 2014.
Summary of responses to issues raised in previous annual reviews (where relevant):
Based on the last Annual Review recommendations, DFID and PMDP team reviewed and amended the logframe indicators and milestones to reflect the findings of the inception phase and gender strategy.

Recommendations
PMDP to put in place a faster and more efficient processing mechanism for grants to better respond to the emergency situation in Gaza by April 2015

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Market System failure in specific sectors addressed
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Number of market system studies completed	3	3
2.2 Number of interventions based on completed market system studies	2	3

Key points

2.1 The 2014 milestone was met. Three market system studies were completed. These include:
1. The first market system analysed was Multinational Enterprise (MNE) software outsourcing to Palestinian companies.
2. The second market system study analysed the Business Service Providers (BSPs) sector to encourage these companies to acquire quality certification for the Management Consultants Service Providers (MCSPs).
3. The third market system study was an emergency market mapping and analysis (EMMA) for the irrigation water in the eastern areas of Khan Younes in Gaza. The EMMA study recommended market driven approaches for the immediate rehabilitation of the irrigation water system and damaged cement tanks.
2.1. The 2014 milestone was moderately exceeded. PMDP originally planned to conduct two interventions by the end of 2014. However, PMDP managed to conduct three interventions related to the first system study. The interventions are:
- Facilitating and launching a working group with relevant stakeholders to coordinate efforts on addressing market gaps including quality of engineers and access to markets.
- A partnership agreement was signed with the Palestinian Information Technology Association of Companies (PITA) to invite 11 Diaspora individuals in to improve their access to information and expose them to software offshoring investment opportunities.
- Supporting activities at the 2014 Expotech exhibition in Gaza including helping 20 local ICT companies in Gaza to participate and interact with their clients. This served as a hub to promote Gaza ICT companies that have been impacted by the last war on Gaza to get back to business.
Summary of responses to issues raised in previous annual reviews (where relevant)
The last annual review highlighted the need to ensure that studies and interventions will address gender issues. PMDP have responded, for example, the first market system analysis identified several constraints related to gender inclusion in the ICT sector and MNEs where women have almost no representation in the work force. PMDP considers targeted grants to provide professional training on best practices for starting and sustaining women owned/managed/focused Business Service Providers (BSPs).

Recommendations
1. PMDP to ensure all studies will include a section to specifically address and analyse gender issues.
2. PMDP to ensure experts in market system development approaches are assigned at different stages of the market system analysis. This enhances the outcome of the studies and further increases the knowledge and experience among local Business Service Providers (BSPs).
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened Trade and Investment linkages with international markets
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Number of activities completed by PMDP within the framework of support provided to PIPA and key market institutions	5	6
3.2 Number of diaspora engaging activities conducted	4	6
3.3 Total number of people trained on trade and investment promotion	0	0
3.4 Number of women trained on trade and investment promotion	0	0
3.5 Number of CTRs placed	0	0

Key points
  1. The programme has moderately exceeded its targets under indicator 3.1. It completed 6 interventions in support to PIPA. PMDP was successful in assisting PIPA to develop and approve a strategy framework, which for the first time has agreed a defined and measurable set of goals towards employment generation and value of new investments facilitated by PIPA. The strategy’s supplementary work plan would facilitate PMDP continued assistance.

  1. The 2014 milestone for indicator 3.2 was moderately exceeded. PMDP conducted 6 engagement activities to strengthen trade and investment linkages with Palestinian Diaspora. These include:

1. Attending “Turkey the gate for Palestine to the world’ investment conference with the aim of conducting research, networking, presentation of PMDP and establishing contacts for the work on improving trade and investment linkages
2. Participating in a regional workshop organised by the MedGeneration project in Jordan that aims to mobilise economic Diasporas
3. Taking part in PalTrade’s Advocacy mission to Amman and Brussels ‘What you don’t know about Palestine – Export and Investment Opportunities, Engines for Private Sector-Led Growth’
Summary of responses to issues raised in previous annual reviews (where relevant)
During this year, we ensured that the PMDP plans for PIPA and the CTRs meet the programme’s objectives. We sought advice from DFID advisers, met monthly the PMDP team and the MoNE to discuss these plans. Also we reflected the findings of the inception phase report in the logframe.
Recommendations
1. PMDP and DFID to continue monitoring quarterly progress and commitment of PIPA’s Board of Directors (BoD) and management towards implementing its strategic framework
2. PMDP to facilitate understanding between the Palestinian MoNE and MoFA regarding Commercial Trade Representatives (CTRs) component by October 2015.
3. PMDP to propose new additional delivery options for the commercial and trade representation in different export markets by October 2015.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The main cost drivers of the programme are the staff costs, running expenses, and the matching grants. These cost drivers were identified during the development of the business case and will continue to drive the cost of implementation of the programme. For the evaluation supplier’s contract, in addition to the staff cost rate and expenses, the evaluation plan’s methodology (travel to geographical locations, and printing materials) was another key cost driver.

VFM performance
Many grants supported by PMDP have only recently been completed or are work in progress. Whilst outcomes are only now starting to emerge, PMDP established a mechanism for conducting in-depth VfM analyses starting from the first year of operations. The VfM performance was assessed against three measures including 1) Economy (i.e. inputs), 2) Efficiency (outputs), and 3) Effectiveness (outcomes).

VFM assessment (See Annex 1 for full analysis under each measure) of PMDP against previous DFID funded project Facility for New Market Development (FNMD) benchmarks for markets entered; and product developed/improved show relatively low VfM. The reason for this is twofold:

- The front loaded costs associated with PMDP’s launch in 2014. PMDP has been in operation for 10 months. During this period, PMDP has invested in launching the programme identification and hiring staff, and outreaching to potential clients. This explains the low vfm calculations when dividing inputs costs over outputs.
- The PMDP’s figures are obtained after 10 months of operation and then compared against the fourth year of FNMD’s benchmarks. Again this explains the low VfM when compared to FNMD.

It is worth noting that spend is front heavy with results expected later in the life of the project, this does not mean that the project is poor value for money. Therefore, VfM analysis may at this stage appear unrepresentative of PMDP performance in the long-term.

Recommendation: Evaluation Supplier to undertake a full external VfM assessment as part of 2016 annual assessment. At that point, PMDP will have launched/completed a sufficient critical mass of activities/grants needed to complete what should hopefully then be a more representative VfM analysis.

Assessment of whether the programme continues to represent value for money
We believe that the programme continues to represent value for money as it is performing well and has delivered its expected outputs with an overall score of A++. However, given it is still difficult to judge on VfM at this early stage, further robust VfM analysis will need to take place in 2016 annual assessment.

Quality of financial management
DAI provides quarterly financial reporting, as well as monthly invoices which include an updated quarterly expenditure forecast. The total spent during the reporting period was £1,980,833 (about 100% spent against its budget). The table below shows the breakdown of expenses:

PMDP finances during reporting period (March - December 2014)
Item	Spend
Implementation Supplier (DAI Europe)
Fees & Expenses	£1,114,293
Grants	£126,450
Evaluation Supplier costs	£72,907.62
Vetting costs	£20,000.00
DFID B2 Programme officer embedded in the project site.	£25,687.00
Total	£1,980,833

This brings the total programme spend from the start of the project to £2,410,088

Date of last narrative financial report	31Jan 2015
Date of last audited annual statement	Due in 15 June 2015

E: RISK (½ page)

Overall risk rating: Medium/High

We assess the overall risk of the programme needs to be changed from Medium to Medium/High given the emerging risk identified below.

Overview of programme risk

In addition to updating the risks in the original Business Case (See Annex 2), we have also identified the following emerging risks which are continuously measured and monitored:

Change of Palestinian government due to reconciliation, elections, dissolution or collapse.	As the current PA Interim Technocratic Government is comprised of technocrats, UK’s ability to fund the PA is not affected. However, we continue to monitor this very closely. The UK will only work with a government committed to non-violence.
Instability and violence	2014 saw sustained violence in the West Bank and the Gaza/Israel conflict. The current political situation is fragile and fuelling tensions on the ground. We will continue to monitor closely and provide options in the event that we are not longer to provide support through our current modality.
Israel withholds Palestinian clearance revenues contrary to its legal obligations.	Israel announced a freezing of the transfer of half a billion shekels ($130m) in tax revenues collected on behalf of the Palestinian Authority. These funds compose 70% of the PA’s revenue base and are worth the entire wage bill. PA civil servants were not paid their December 2014 salaries due at the beginning of January 2015. The PA’s ability to operate without timely and sustained receipt of these revenues is extremely limited. This impacts the overall economic situation and increases the risk of lack of investment in the private sector. Businesses will be reluctant to access technical assistance and contribute their share in the matching grant. A mitigation measure is to increase PMDP’s share of the grant up to 75% (upper ceiling). Moreover, PMDP could possibly focus the technical assistance component to access new markets and improve the export potential.
Restrictions on Gaza will not allow construction materials to enter Gaza and support repairs to factories and businesses.	DFID is attempting to mitigate this risk through our support for the Gaza Reconstruction Mechanism, which has facilitated the entry of some materials;
Lack of infrastructure in Gaza.	Damaged infrastructure and lack of quality electricity supply in Gaza due to the political situation will remain a difficult challenge to overcome by Gazan firms.

Outstanding actions from risk assessment (N/A)

Risks continue to be treated in line with the Risk Matrix. There are no outstanding actions from risk assessments.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme has delivered its targets within the planned time scale, and it is on track to deliver its 2019 objectives.

Performance of partnership (s)

DAI Europe (Implementation supplier) and GDSI (Evaluation Supplier) continue to meet commercial partnership requirements. Recently we have conducted a Contract Performance Review (CPR) for DAI Europe; the review concluded that the supplier is delivering efficiently and effectively.

Asset monitoring and control

PMDP and DFID project officer monitors and keeps updated track of the programme asset record.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The PA Ministry of National Economy is a member of the Steering Committee of the programme. In addition, PMDP works closely with the Ministry on the Commercial Representatives component of the programme. Finally, PMDP supports the Palestinian Investment Promotion Agency (PIPA) to improve its capacity and attract investments.

DFID assess the PA against DFID’s Partnership Principles quarterly. We also assess the PA’s commitment to these principles annually through a formal meeting with the PA. On 19 March, DFID and the PA held their annual policy dialogue as set out in the Memorandum of Understanding (MOU) between the UK and the PA. This meeting commended the PA for progress towards key reforms and urged them to continue strengthening government institutions and continue its efforts to reduce poverty.

Commitment to additional discretionary Partnership Principle: We consider that the track record of the Palestinian leaderships shows their genuine commitment to non-violence and a negotiated two-state solution. We believe that the Palestinian Authority under President Abbas and Prime Minister Hamdallah is a firm partner for peace, they remain clear that they continue to work to achieve peace.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Evidence & Theory of Change

We conducted a workshop to test and review the ToC. The Evaluation Supplier and PMDP have checked the logical pathways of change from inputs to higher level results. Each individual assumption was discussed and tested for relevance with inputs from component leads to ensure that existing assumptions fully and clearly describe factors that may influence a logical pathway to PMDP’s outcomes going forward. The review indicated that ToC remains valid. However, ToC test identified a number of areas that may require further discussion, analysis and possibly revision. New assumptions have emerged that may affect logical pathways to change; and evidence levels for some assumptions may require re-assessment. Details of the workshop outcome are attached in Annex 3

Recommendation: Evaluation supplier to hold a one-day Theory of Change workshop with the engagement of DFID (Steering Committee) and PMDP by 2016. The purpose of the workshop would be to collectively test the validity of the ToC, the underlining assumptions and review scope for any revisions of the ToC that may be necessary.

Evaluation:
The external Evaluation supplier GDSI have quality assured PMDP results on quarterly basis and conducted an annual assessment at the end of the reporting period. The Evaluation suppliers will continue to carry out this work every year, and a final evaluation at the end of the programme.

Monitoring progress
The programme comes under the portfolio of the OPTs Economic Development team and is managed by Project officer, Senior Responsible Owner (SRO), and the Team Leader.

The team monitors progress through:
- Weekly meetings with DAI Europe
- Quarterly progress and financial reports by DAI Europe.
- Regular meetings with PA Ministry of National Economy at both Ministerial and technical levels.
- Quarterly Steering Committee meetings
- Independent Evaluation supplier’s reports.

Annual review
The annual review has been completed by the DFID Economic Development Pillar’s Senior Policy and Programme officer and project officer in Jerusalem with input from relevant DFID advisers. DFID’s Deputy Head of the Palestinian Programme based in Jerusalem quality assured the review.

The review was based largely on the Annual Report submitted by the implementing partner DAI Europe, and the annual assessment prepared by the independent Evaluation supplier.

ANNEX 1: External Light Touch Review of Value for Money (VfM)
Approach: Economy, Efficiency and Effectiveness
The Evaluation supplier adopted the independent UK audit agencies’, such as NAO, Audit Commission ‘3E’ framework of ‘Economy, Efficiency and Effectiveness’, approach, which follows the same categorisation as the Audit Commission’s definition and approach to VfM. Their definition of Value for Money is:
“VfM is about obtaining the maximum benefit over time with the resources available. It is about achieving the right local balance between economy, efficiency and effectiveness, or, spending less, spending well and spending wisely to achieve local priorities...VfM is high when there is an optimum balance between all three elements, when costs are relatively low, productivity is high and successful outcomes have been achieved’’.
Further to this definition, the NAO have produced the following definition and analytical framework that states that: “Good value for money is the optimal use of resources to achieve the intended outcome”.
The assessment of VfM thus involves examining each of the 3 elements of VfM, identifying the links between them and drawing conclusions based on evidence about how well they perform together. Interestingly, the definitions also refer to an optimal balance, as contrasted with a ‘maximum’ productivity ratio, suggesting that it is not the case that the cheapest option always represents better value for money, and pointing to the conversion of inputs-outputs and outputs-outcomes as the subject of real interest in value for money judgements.
Scope of VfM analysis

The analysis is based on the review of the VfM conducted by PMDP and measures to assess VfM against the parameters included in the PMDP Business Case and Intervention Summary.

PMDP has commenced operations in October 2013 followed by a four months inception phase. Therefore, in December 2014, PMDP has been in operation for 10 months. During this period, PMDP has invested in launching the programme, identification and hiring staff, outreaching to potential clients (both businesses and BSPs), rolling out information sessions, fine tuning TAMIS, generating client pipelines and putting other performance management systems in place. PMDP has also operated during the Gaza War 2014 and worked with clients and partners who were affected by its consequences.
The assessment of VfM thus involves examining each of the 3 elements of VfM, identifying the links between them and drawing conclusions based on evidence about how well they perform together.
Performance on VfM measures
Many grants supported by PMDP were only recently been completed or are work in progress. Whilst outcomes are only now starting to emerge, PMDP established a mechanism for conducting in-depth VfM analyses starting from the first year of operations. Given that outcomes have not yet had the time to emerge; VfM results are not likely at this stage to be representative of actual programme performance.
Economy
The main administrative cost driver is staff costs. Local staff costs fee rates charged by PMDP are similar to those paid by other similar projects in country including DFID’s previous FNMD project. For international consultants, their daily fee rates appear to be comparable with that paid for other DFID market development projects around the world. DAI tender was awarded on the basis of representing best VfM for DFID.
Efficiency
For Output 1, the Business Case envisaged to monitor the cost per market entered and the cost per product improved/developed. The performance is benchmarked against DFID previous project Facility for New market Development (FNMD), which cost £12,020 per market entered and £5,976 per product improved/developed. FNMD final report provided some benchmarks against which PMDP values are presented in the following tables. The costs of market entered and product improved/developed by FNMD are at this junction appear to be significantly lower than that developed by PMDP.

Given actual high costs of launching the programme versus relatively small number of grants awarded, it is currently plausible to assume that these parameters may not be entirely representative of the efficiency of the programme in the longer term. It is also plausible to assume that as the pipeline of grants unfolds more rapidly in 2015, the value of VfM indicators would be expected to regress towards the mean.

Evaluation Supplier is proposing to undertake a full external VfM assessment as part of the next 2016 annual assessment with the engagement of an external international VfM expert. At that point, PMDP will have launched/completed a sufficient critical mass of activities/grants needed to complete what should hopefully then be a more representative VfM analysis.
Table 1: Cost per market entered

Indicator	Calculation	PMDP value (£) as of year 1	FNMD value (£)[3] as of year 4
Cost per new market entered (without grantees’ share)	(PMDP’s share of the grant costs spent on entering new markets)  (Number new markets entered)	12,930 / (36)	12,020
Cost per new domestic market entered (without grantees’ share)	(PMDP’s share of the grant costs spent on entering new domestic markets)  (Number new markets entered)	85,975 / (4)	16,205[4]
Cost per new foreign market entered (without grantees’ share)	(PMDP’s share of the grant costs spent on entering new foreign markets)  (Number new markets entered)	13,680 / (32)	8,705
Cost per new market entered (with grantees’ share)	(Total grant costs spent on entering new markets)  (Number new markets entered)	14,113 / (36)	17,988[5]
Cost per new domestic market entered (with grantees’ share)	(Total grant costs spent on entering new foreign markets)  (Number new markets entered)	91,767 / (4)	36,014
Cost per new foreign market entered (with grantees’ share)	(Total grant costs spent on entering new foreign markets)  (Number new markets entered)	14,867 / (32)	17,105
[3] Converted from $USD rates featured in the FNMD Cost effectiveness Analysis at FT current rate (18 February 2015)
[4] ICT and media
[5] Agribusiness sector

Table 2: Cost per product improved/developed

Indicator	Calculation	PMDP value (£) as of year 1	FNMD value (£)[6] as of year 4
Cost per new product developed (without grantees’ share)	(PMDP’s share of the grant costs spent on developing new products)  (Number new products developed)	61,123 / (4)	20,563[7]
Cost per existing product developed (without grantees’ share)	(PMDP’s share of the grant costs spent on improving existing products)  (Number new products developed)	138,814 / (3)	12,591
Cost per new product developed (with grantees’ share)	(Total grant costs spent on developing new products)  (Number new products developed)	64,039 / (4)	28,996[8]
Cost per existing product developed (with grantees’ share)	(Total grant costs spent on improving existing products)  (Number new products developed)	150,298 / (3)	24,132
[6] Converted from $USD rates featured in the FNMD Cost effectiveness Analysis at FT current rate (18 February 2015)
[7] Agribusiness sector
[8] Ditto

For Output 2: Evaluation Supplier has reviewed records of the Steering Committee meetings. The records indicate that PMDP progress reports were approved which indicates that the cost per study may have met the required VfM criteria. Evaluation Supplier has closely examined the content of the market failure studies and considered the quality of the studies high.

For Output 3: It was not possible to comment on this indicator as at the time of assessment CTRs have not yet been trained or mobilised.

Cost effectiveness
Output 2: The Business Case refers to a set of criteria available for measuring cost, drawing on the ‘Ratings and weightings’ approach suggested by ITAD[9]. This involves scoring interventions against criteria such as Leverage/replication, Theory of Change, and Relevance and Robustness of Indicators. In the VfM Scoring Sheet, scores 1 to 5 are awarded (Weighting X 3) meaning that the total maximum score for cost effectiveness criterion is 45 points (see Table 13).
[9] Chris Barnett, Julian Barr, Angela Christie, Belinda Duff, and Shaun Hext, Measuring the Impact and Value for Money of Governance & Conflict Programmes, Final Report, December 2010 (Figure 5: VFM Scoring Sheet)

Leverage/Replication: Evaluation Supplier considers that it is currently premature to measure leverage/replication, as there is no or little evidence available in this regard at this phase of the programme. On this basis, we recommend a score of 9:

- Some leverage of activities /investment and wider effects identified
- Limited potential for additional benefits (e.g. scale-up, multiplier or replication) identified
Theory of Change: Evaluation Supplier recommends awarding a score of 9:
- Outputs are necessary and sufficient to deliver purpose. Some assumptions about externalities realistic and credible; some questions about coverage and/or depth
- Some risk of underachieving but managed to enable achievement of purpose
Relevance and Robustness of Indicators: Evaluation Supplier recommends awarding a score of 15:
- Indicators are relevant and robust.
- Relevance=clear, rule- driven, causally linked, gendered, pro-poor and cross-sectoral. Robust=data to support indicators (including base- line) are available, accessible, credible, own- able and disaggregate-able.
Output 3: It was not possible to comment on this indicator as at the time of assessment CTRs have not yet been trained or mobilised.
Table 3: VfM Scoring Sheet – Effectiveness
Criteria	Descriptors					Scores
	1	2	3	4	5	(Max.45)
Leverage/ Replication / (Weighting X 3)	•No leverage or wider effects identified / •No or very low / potential for additional benefits (e.g. scale-up, multiplier or replication) identified	•Some leverage of activities /investment and wider effects identified / • Limited potential for additional benefits (e.g. scale-up, multiplier or replication) identified	•Leverage of activities/ investments described and supported by some evidence / •Some potential for additional / benefits (e.g. scale-up, multiplier or replication) identified	• Leverage of activities/investments and wider effects described, and supported by strong evidence / • Considerable potential for additional benefits (e.g. scale-up, multiplier or replication) identified	• Leverage of activities/investments activities /investments and wider effects described with evidence that shows significant potential for expansion or replication / • Very high potential for additional benefits (e.g. scale-up, multiplier or replication) identified	9
Theory of Change (Weighting X 3)	• Little or no likelihood outputs will deliver purpose / • Too little information on assumptions to assess effects on outcomes / • Risk of not achieving purpose very high	• Outputs do not meet ‘necessary and sufficient’ rule / • Assumptions are questionable and insufficiently detailed / • Risk of not achieving purpose high	• Outputs are necessary and sufficient to deliver purpose Some assumptions about externalities realistic and credible; some questions about coverage and/or depth / • Some risk of underachieving but managed to enable achievement of purpose	• Outputs are necessary and sufficient to deliver purpose / • Realistic and credible / assumptions about externalities, good coverage and depth • Low risk of underachieving; likely will achieve purpose	• Outputs are necessary and sufficient to deliver purpose / • Realistic and credible assumptions, analysing key externalities in sufficient depth / • Probable will achieve or exceed purpose	9
Relevance and Robustness of Indicators (Weighting X 3)	Indicators are largely neither relevant nor robust. / Relevance=clear, rule- driven, causally linked, gendered, pro-poor and cross-sectoral. / Robust=data to support indicators (and base- line) are available, accessible, credible, own-able and disaggregate-able.	Indicators have many significant weaknesses in terms of relevance and robustness. Relevance=clear, rule-driven, causally linked, gendered, pro-poor and cross-sectoral. / Robust=data to support indicators (and base-line) are available, accessible, credible, own-able and disaggregate-able.	Indicators have some weaknesses in terms of relevance and robustness. Relevance=clear, rule-driven, causally linked, gendered, pro- poor and cross-sectoral. Robust=data to support indicators (and base-line) are available, accessible, credible, own-able and disaggregate-able.	Indicators are mostly relevant and robust. Relevance=clear, rule-driven, causally linked, gendered, pro- poor and cross-sectoral. Robust=data to support indicators (and base-line) are available, accessible, credible, own-able and disaggregate-able.	Indicators are relevant and robust. Relevance=clear, rule- driven, causally linked, gendered, pro-poor and cross-sectoral. / Robust=data to support indicators (including base- line) are available, accessible, credible, own- able and disaggregate-able.	15
					33

ANNEX 2: Risk Matrix

PMDP Risk Matrix

Updated / revisited on March 2015

Risk	Probability	Impact	Mitigation
Macroeconomic and country risks
Movement and access restrictions deteriorate in the West Bank and Gaza.	Medium	High	Equip DFID with evidence and case studies from project to help their dialogue with relevant authorities (OQR, EU, UN, FCO). Adjust programming if needed to respond to emerging needs as a result of more restrictions.
Gaza conflict between Israel and Hamas.	High	High	Adjust programming to respond to emerging needs as a result of conflict, informed by lessons learned from FNMD. In November 2014, PMDP launched the Gaza Back to Business window to help companies that sustained physical damage as a result of the conflict.
Escalation of conflict in the OPTs.	Medium	High	Adjust programming to respond to emerging needs as a result of conflict, informed by lessons learned from FNMD.
Aid flows sharply decline reducing economic growth.	Low	Medium	This project is designed to enable a robust economy independent of aid. Sustainability is one of the main principles of the M4P approach that will be applied.
Aid coordination remains weak and the proliferation of donor programmes undermines sustainable market development efforts.	Low	Medium	Support DFID in their donor coordination efforts. DAI’s longstanding relationship with key donors and stakeholders in the OPTs, as well as current implementation projects, will help facilitate coordination.
The programme introduces its own market distortions.	Medium	Medium	Direct support can cause distortions and the Palestinian market already suffers from abnormally high risk which itself creates distortions. This scheme is specifically designed to compensate for these distortions by addressing the root causes of market failures and distortions.
PMDP not sufficiently changing root causes of market failures.	Medium	Medium	PMDP alone cannot change the root causes of market failures. The project will work very closely with MONE, the EU, the World Bank, and other major donors to ensure that concerted efforts are exerted to enable maximum impact.
Major economic shocks, such as global economic stagnation, take place.	Low	Medium	The programme is sufficiently flexible to work on both export oriented businesses and domestic industries and services. During economic crisis, businesses will be encouraged to focus more on improving competitiveness of local products and services to enable import substitution, rather than exports.
Results- and activities-level risks
Inadequate performance or impartiality of PMDP’s management, administrative, and technical staff.	Low	Medium	DAI has assembled a carefully selected and vetted team with significant combined experience working on similar projects. In addition, DAI’s robust project management systems ensure checks and balances on all our staff and help us monitor performance and conflicts of interest.
Insufficient business interest in or ability to make use of the matching grant scheme.	Low	High	PMDP is going to take proactive measures to maintain and encourage more demand. PMDP will use effective marketing and communication tools to reach clients across over oPT taking into consideration marginalized areas and areas named by “Area C”.
There is overwhelming interest in Gaza and the PMDP assessment team is not able to keep up with the demand.	Medium	High	PMDP will recruit the required resources to ensure fast and efficient delivery of assistance in Gaza.
Inappropriate (fraudulent) or ineffective use of grants provided.	Low	High	Procurement of services by the grantees will be carried out jointly by the recipient firms and DAI in order to minimise fiduciary risk. This will result in joint accountability between the client and the programme staff on cost, value for money and quality of services. Periodic audits will be conducted. In addition to that, PMDP will have an assessment panel that will approve each grant.
Palestinian BSPs do not provide sufficiently high quality services.	High	Medium	This issue has been identified as a market failure to be addressed in the programme. Local BSPs with certification (supported through the programme) will be included in the roster from which firms can select to provide services. In addition to that, PMDP will conduct performance evaluation per grant to update the qualified BSP roster. On the other hand, PMDP will take into consideration the feedback provided by the grantees after each assignment.
Direct/indirect financial benefit to terrorist organisations through: a) grant funds being used to help businesses with links to such organisations; .b) businesses use funds in contravention of EU/UK terrorist financing law; or c) taxing or extorting businesses for funds.	Low/ Medium	High	a) DAI will vet all recipient businesses using World Check similar to procedures used under FNMD. This procedure will prevent businesses with clear link to such organisations from receiving grants or any kind of support. b) DFID’s contract with DAI will ensure compliance with EU/UK terrorist financing law, with grant agreements with recipient companies committing them in writing to not provide direct or indirect financial benefit to terrorist organisations. c) This is covered under b).
Measuring of PMDP results biased and not objective.	Medium	Medium	This risk will be mitigated through hiring a separate contractor to measure results throughout the lifetime of the project. These results will be compared against results produced by DAI and action will be taken in case of major discrepancies. DFID staff will also conduct field visits and will verify first-hand the quality of the results collated by both contractors.
The MONE are incapable to provide support to business representatives abroad once the project is completed.	Medium	Medium	This will be mitigated through a formal memorandum of understanding signed by the PA to ensure that the PA will pick up the activity and cost of commercial representatives after the end of the programme. This activity will also be closely assessed on an annual basis to ensure viability and results before proceeding into the next year of support.
Agreement on reporting and support structure for commercial trade representatives is not reached between MoNE and MoFA	Medium	Low	Move CTR component closer to be managed by private sector organization.
Lack of support from trade and investment support organizations such as PIPA and Paltrade	Medium / high	High	Continues engagement early on during the programme implementation will eliminate the probability of happening. / Currently we are lobbying with the MoNE to move this issue forward.
Diaspora are not willing (hesitate) to cooperate due to previous reputation.	Medium	Medium	Activities should not link to achieve fast linkages and achievement. This is a continuous activity to build trust, perception to utilize Diaspora network and referrals to open the doors for other investment not necessarily by Diaspora themselves.
Government push for centralizing diaspora’s efforts	Low	Low / Medium	Build synergies with the newly established centre.
Grantees are not willing to report periodically on supported projects	Medium	Medium	The PMDP grants agreement will include an article which indicates that each grantee should report periodically on grant intervention.
Change management in PIPA is not fully adopted by PIPA’s management, staff and MoNE	Low	High	Keep a high level and continuous engagement with PIPA re-enforcing the need of change.
Frequent changes in government leading to the need to re-establish project momentum.	High	Medium	Will need to formalize all agreements on engagements and next steps with Gov. counterparts.
Instability in PIPA as a result of any court’s decision forcing management changes and associated risks	Medium	Medium	Conducting PMDP as professional as we can and precede engagement with caution.
Programme management risks
The capacity of the implementing partners to deliver the programme is inadequate.	Low	High	Careful selection and screening of project partners will avoid this risk. Selection will be made on evidence of past high quality delivery experience in similar programmes. After selection, close monitoring of results and implementation quality will enable DAI to flag out issues early enough to enable corrective action.
Environmental, social, and governance risks
Project has a detrimental effect on the environment, either directly or indirectly through its beneficiaries.	Low	Low	An ESG risk policy will be developed for the project. This will trickle down to our agreements with partners and beneficiaries.
Failure to deliver intended benefits on women and marginalized areas	Low	Medium	PMDP draw gender strategy to target women and small businesses in marginalized areas. In addition to that, PMDP will use the most effective communication tools to reach out all peripherals areas across over the oPT.

ANNEX 3: PMDP Theory of Change Workshop outcomes

Theory of Change

Evaluation Supplier used a structured approach for the workshop. The discussion basis and discussion points where shared with PMDP and DFID prior to the workshop. At the workshop, Evaluation Supplier and PMDP have cross-walked through the logical pathways of change from inputs to higher level results. Each individual assumption was discussed and tested for relevance with inputs from component leads to ensure that existing assumptions fully and clearly describe factors that may influence a logical pathway to PMDP’s outcomes going forward.

The discussion has led to a broad consensus between Evaluation Supplier and PMDP on the validity of the ToC and relevance of the assumptions featured in the ToC. The workshop participants agreed that, overall, the current version of the ToC remains valid. As a result of the ToC test and ToC-to-result chains crosswalk, however, Evaluation Supplier identified a number of areas in the ToC that may require further discussion and analysis with PMDP and DFID. Working with ToC requires performance management approaches to accommodate uncertainty and flexibility and may impact the design (i.e. evaluation questions) for the full final impact evaluation of PMDP. The areas for a potential review include both assumptions and the perceived levels of evidence for some assumptions (i.e. “strong”, “medium” and “weak”).

Evaluation Supplier recommends (see section 7. Key Recommendations) to hold a one-day Theory of Change workshop with the engagement of DFID (Steering Committee) and PMDP as soon as feasible and practical in 2015-2016.

In particular, the following areas have emerged as basis for a further discussion and analysis:

Output 1 – Improved Private Sector Skills and Innovation

The ToC features several results at the inputs to outputs level that relate to the Result 1.1.3: “Grantees attitude towards the value of BSP enhanced”. Related assumption for this is currently “Firms and BSPs willing and able to invest in skills improvement and innovation”. This will be measured by Indicator 1.1.3: “Number of enterprises using own funds to pay for BSP”.

The underlining assumption linked to the Result 1.1.3 may be clarified as “Grantees attitude towards the value of BSP will not be enhanced unless BSPs invest to improve and innovate their services’’.

Output 2 – Market System Failures in Specific Sectors Addressed

1. At the input to output level, the ToC features the result “Market failure analysis shared with other donors & market players”. This result is directly relevant in its rationale to the result featured under Output 1: “Success stories and best practices made available publicly”. The logic indicates that the ToC result may be clarified as ‘‘Market failure analysis, success stories and best practices are shared with other donors & market players”.
2. At the output to outcome level, the ToC features one assumption “Market players willing to adjust their behaviour as a result of studies, facilitation, observation and personal experience”. Whilst this assumption remains valid the evidence that is currently available for this assumption may appear as “Weak” as opposed to “Medium”. There may also be scope explored for the introduction of additional assumptions. The current single assumption does not appear to fully describe the complexity of the assumptions behind the intended outcome. Additional assumptions may include the following:
- “Business enabling environment and regulatory framework improves”
- “Value chains linked to Israel can be influenced by provision of programme support”

Output 3 – Strengthened Trade and Investment Linkages with International Markets

The ToC features inputs/interventions as ‘TA and system development for PIPA, research and build Diaspora & train commercial representatives’. There is scope to clarify this as “TA and system development for PIPA, mapping and engagement of Diaspora & training of commercial representatives”.

At the input to output level, the ToC features one assumption ‘PIPA and PA have political will to embrace change’. Whilst this assumption continues to be relevant, evidence for it is currently likely to be “Weak” rather than “Medium”. There appears to be scope for the introduction of the new assumption “PIPA and PA demonstrate ability, commitment and continuity to deliver change”. It may currently appear prudent to assume that evidence for this possible new assumption would also be “Weak”.

At the output to outcome level, the ToC features the result “Diaspora and investors transfer knowledge and invest to improve Palestinian products and services”. This result relates to R 1.3.3: Diaspora attitude towards trade, investment and know-how enhanced”. The latter is to be measured by Indicator 1.3.3 “Number of case studies show knowledge, attitude, or practice change among targeted Diaspora people”. It appears that PMDP has introduced additional, higher level, result: R 1.3: “Money amount of trade and investment increased”. Whilst this result is plausible, it may need to be clarified to what extent the achievement of this result may be influenced by the achievement of lower level results featured in the result chains (“R 1.3.1: PIPA’s capacity improved; R 1.3.2: Well-functioning CTR’s placed; and R 1.3.3: Diaspora attitude towards trade, investment and know-how enhanced”). From the evaluation perspective, it would be important to consider how R 1.3 is to be measured (i.e. baseline; sources; methods) and how or to what extent the achievement of this new result may be attributable directly or indirectly to PMDP.

Result chains

Within the framework of the workshop, Evaluation Supplier has reviewed, in conjunction with PMDP, new result chains. It has been discussed and agreed that the result chains for each Output include sighting to higher, output to impact, pathways of results. In particular,

- Component 1 result chain – establish link between outcome and impact results.
- Component 2 result chain – establish link between output results and outcome and impact results.
- Component 3 result chain – establish link between output results and outcome and impact results.