## Template
PROJECT TITLE | Strengthening Public Financial Management, Anti-Corruption and Accountability Institutions in Sierra Leone
IMPACT | Impact Indicator 1 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
A more effective and accountable executive that raises, allocates and uses public resources transparently to drive inclusive and sustainable development | GoSL is on track with an approved IMF programme. | Planned | Sierra Leone went off track with the IMF shortly after an ECF was approved in June 2017. Discussions underway on a new programme. | First review successfully concluded. | Second review successfully concluded. | Third review successfully concluded [subject to resumption of ECF - this has been temporarily put on hold given the macro-fiscal shocks relating to Covid-19] | Fourth and Fifth Reviews successfully concluded. | Programme successfully concluded [sixth and seventh reviews].
|  | Achieved |  | Achieved. | On track. The Second Review was approved by the board on 17th April. | The ECF programme has been paused given the impacts of C19 on the macro-fiscal framework. Sierra Leone received an RCF disbursement in May 2020 and remains in good standing with the IMF.
Source
IMF Reports
| Impact Indicator 2 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
| Improved public perception of corruption | Planned | 30/100 (2018) | N/A | Improvement | N/A | Improvement | Improvement | Improvement
|  | Achieved |  | N/A | Achieved. 33/100 (2019)
Source
Transparency International Index score (released annually in January)
OUTCOME | Outcome Indicator 1.1 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023 | Assumptions
Stronger public expenditure management, revenue, oversight and anti-corruption institutions resulting in increases in revenue, increasingly effective action on corruption, and improved public financial management. | Revenue as a % of non-iron ore GDP | Planned | 13.8 | 14.5 | - | 15 [to be updated in line with latest IMF targets] | 15.8 | - | - | - GoSL political will to implement reforms across PFM, Revenue, Anti-Corruption and Accountability continues - DFID support is able to bolster, shape and support the implementation of these reforms - GoSL remains open to external Strategic/Technical Advice and to engagement with civil society actors in support of its reform agenda - Other development partners, in particular the World Bank, IMF and EU, continue to provide support to GoSL including direct provision of funds to finance implementation of their plans - There are no major internal or external shocks (like the Ebola crisis) that significantly affect Sierra Leone's ability to implement reforms
|  | Achieved |  | The Government was on track against both the IMF and its own (more ambitious) revenue targets in the first half of the year. The next update will be available from the IMF mission in October 2019. | - | 13% [The estimate for the year of 13% given in the supplementary budget is in line with forecasts in the IMF RCF documentation, Jan-Jun collection was 6.4% of non-iron ore GDP]
Source
GoSL reports, targets will be updated in line with the IMF programme.
| Outcome Indicator 1.2 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
| PEFA, TADAT and Open Budget Index reports [exact timings TBD]. | Planned | - Open Budget Index Score: 38 out of 100 in 2017 (52/100 in 2015; 39/100 in 2012) - PEFA scores in March 2018 Report, based on 2016 data - TADAT scores reported in 2017 TADAT | No data available at this milestone | Open Budget Index Score for 2019 (expected Jan) higher than 38/100 | No target for this period. Next PEFA due in 2021. TADAT timings TBD. | Positive trend on PEFA / TADAT (timing tbc) | Open Budget Index Score for 2021 (expected Jan 2022) higher than 2019 Positive trend on PEFA / TADAT (timing tbc) | Positive trend on PEFA / TADAT (timing tbc)
|  | Achieved |  | N/A | Achieved - 39/100 | -
Source
Open Budget Index: https://www.internationalbudget.org/open-budget-survey/results-by-country/country-info/?country=sl PEFA: https://pefa.org/assessments/sierra-leone-2018
| Outcome Indicator 1.3 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
| Implementation of the PFM Reform Strategy | Planned |  | 70% of Priority 1 Annual Targets met; 40% of Priority 2 Annual Targets met. | N/A - no further annual reporting expected since last milestone | By end-June: Revised PFM reform strategy implementation plan in place, including monitoring mechanisms.
|  | Achieved |  | Information not available. See Annual Review. | - | Strategy revision has not been fully rolled out. Monitoring mechanisms are not functioning.
Source
Ministry of Finance annual reporting against PFM Reform Strategy Implementation Matrix
| Outcome Indicator 1.4 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
| Number of grand corruption cases investigated, and prosecuted by Anti-Corruption Commission, and adjudicated by the Anti-Corruption Court to completion. | Planned | <5 (2017) | Independent AC court legally constituted, appoints judges, and begins hearing cases | 4 | 6 | tbc | tbc | tbc
|  | Achieved |  | The Anti-Corruption Division of the High Court was formally established in April 2019. In August 2019, five specific judges were nominated to hear Anti-Corruption Court cases and they have begun hearing cases. | Of the 43 cases inherited by the ACD in December 2019 upon its operationalisation, two (2) cases have been completed and rulings delivered in three (3). | 5 additional cases were completed between March and June 2020, making 10 completed cases in total.
Source
Reports from ACC and Juduciary.
| Outcome Indicator 1.5 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
| % of Commitment Matrix achieved | Planned | N/A (no commitment matrix) | 70%, including 50% of the High Priority actions | 70%, including 50% of the High Priority actions | 70%, including 50% of the High Priority actions
|  | Achieved |  | 80% of High Priority actions are considered ‘Green’. But overall only 50% of all actions are ‘Green’, with 30% ‘Amber’ (reflecting some progress but delays against timelines), and 20% ‘Red’. For three, we were unable to get the necessary data about their status. | 46% RAG rated green and 42% amber. Of the high priority actions 75% are green. | 50% RAG rated green and 42% amber. Of the high priority actions 67% are green.
Source
GoSL reports, TA reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
£3.5m
INPUTS (HR) | DFID (FTEs)
3 (across 6 staff members)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023 | Assumptions
Strategic and technical assistance that successfully supports and influences strategic direction of Government reforms, builds GoSL capability and supports delivery of key reforms. | # Advisers reporting to GoSL and mutually agreed to be performing satisfactorily at break point | Planned | 0 | 4 (minimum) | 5 (minimum) | June 2020: 6 (minimum). Sept 2020: 1 (minimum) | tbc depending on design of Phase II | tbc depending on design of Phase II | tbc depending on design of Phase II | - DFID's contracted supplier is able to find suitably qualified and experienced Advisers to work in Sierra Leone at short notice - GoSL counterparts are open to TA, listen to advice provided and act upon it - GoSL institutions have sufficient clarity about their reform plans to be able to work with the Advisers to identify clear deliverables within the agreed timeframe - Advisers' work in a collaborative and constructive manner to enhance capacity of GoSL counterparts, despite the short timeframe of the Phase I contracts
|  | Achieved |  | 11 | 7 | June:7 September: 5
Source
Reports from OPM vertified through meetings with GoSL
| Output Indicator 1.2 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
| % Advisers' workplans with concrete deliverables (including on capacity building) agreed within 6 weeks of mobilisation | Planned | 0 | 70% | 80% | 100% of advisers starting after March 2020 (or following contract extension beyond June 2020) | tbc depending on design of Phase II | tbc depending on design of Phase II | tbc depending on design of Phase II
|  | Achieved |  | 75% | 57% (although all advisers had workplans in place, only 4 out of the 7 work plans were in place within 6 weeks of mobilisation) | 80% (it took longer than 6 weeks to secure an agreed workplan for the adviser starting in April 2020, however following the contract amendment in June 2020, all four updated work plans were submitted within 6 weeks)
Source
Reports from OPM vertified through meetings with GoSL
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
60% | % workplans delivered on schedule and with clear evidence of GoSL engagement / buy-in | Planned | 0 | 70% | 80% | June 2020: 80%. Sept 2020: 80% | tbc depending on design of Phase II | tbc depending on design of Phase II | tbc depending on design of Phase II
|  | Achieved |  | 86.5% | 86% | June: 82% September: 85%
Source
Reports from OPM vertified through meetings with GoSL
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
| £2m |  | £0 direct contribution | 0 | £2m |  |  |  | 100%
INPUTS (HR) | DFID (FTEs)
2 (across 6 staff members)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - September 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023 | Assumptions
Civil society and accountability organisations supported to hold executive to account, including through generating critical data. | Availability and use (by GoSL and civil society) of data on citizens' understanding of the cost of corruption, perceptions of corruption, and on sector-specific corruption. | Planned | No recent data | 2 studies completed, in close partnership with GoSL and findings published. District level engagement with citizens on the findings has commenced. | Data used by GoSL and CSOs to inform future citizen engagement work. District level engagements continue. | At least 2 TV and radio dissemination campaigns, at national and district levels done. | Data suggests citizen understanding of corruption has improved | tbc depending on design of Phase II | tbc depending on design of Phase II | - Increased availability of reliable data strengthens civil society's ability to hold government to account - Government is willing to engage with civil society in conducting some of the exercises and / or utilising the findings to improve their own systems and performance - Citizens and media demonstrate a level of interest in the data and evidence gathered by civil society organisations
|  | Achieved |  | No studies finalised (but 2 commenced and reports will be produced in October) | Two studies complete and report handed over to ACC which is leading the dissemination and citizens engagement with support from the consortium. | Four radio and four TV discussions were held with the ACC and other relevant public sector partners to discuss both studies and their respective findings.
Source
Reports from Christian Aid civil society consortium
| Output Indicator 2.2 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
| Availability and use (by NRA and other stakeholders) of data on taxpayer knowledge, attitudes and practices. | Planned | No recent data | Revenue KAP survey conducted | KAP survey findings (incl. recommendations) disseminated to GoSL (NRA, MoF, state house) and development partners |  | tbc depending on design of Phase II | tbc depending on design of Phase II | tbc depending on design of Phase II
|  | Achieved |  | Not met (but work has begun, and report will be produced in Octobe) | Met (survey completed and report launched/disseminated to GoSL and development partners)
Source
Reports from Christian Aid civil society consortium
| Output Indicator 2.3 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
| # of informed dialogues on budget credibility and reach of public information products; availability and use of information from public expenditure tracking exercises in education, health and agriculture. | Planned |  | 1 - based on robust analysis of FY19 mid-year outturn Finalised PETS report on education sector. | 2 - based on robust analysis of FY19 full year outturn Dissemination dialogues on all three PETS conducted. Evidence of Gov't and CSO follow up. | By June 2020, evidence of at least 1 government action taken to respond to audit follow-up work. At least 15 multi-media (print, social and electronics) engagements with the public on revenue, the utilization of CoVID-19 resources, or other related information. At least 2 reviewed statements of income, expenditure, procurement processes/procedures produced and shared with government focused on C19 response. At least 3 revenue generation analysis updates produced. At least 6 media engagements held to update citizens on impact of Covid-19 on domestic revenue generation. Evidence of Gov't and CSO follow up on PETS. | tbc depending on design of Phase II | tbc depending on design of Phase II | tbc depending on design of Phase II
|  | Achieved |  | Achieved - reports produced in September. | Not met. Delays were experienced in finalising both the PETS and the budget credibility reports. | June 2020: Met. Ministry of Finance developed and published actions plans to ensure implementation of the audit recommendations. Audit recommendations included in the ministerial performance contract (But information not made public). September 2020: Met. 23 radio engagements and 5 TV engagements completed. One income and expenditure statement analysis done for COVID-19 and one on track to be completed by end-Sept. One revenue analysis done and another one in the draft stage, which will be completed in September 2020. PETS recommendations adopted by the Cabinet.
Source
Reports from Christian Aid civil society consortium and from Institute for Governance Reform
| Output Indicator 2.4 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
| # of government actions to strengthen the transparency and legitimacy of duty waivers attributable to consortium influencing | Planned |  | Policy briefs and influencing strategy developed | 2 substantive actions taken by government. | 2 substantive actions taken by government (cumulative) | tbc depending on design of Phase II | tbc depending on design of Phase II | tbc depending on design of Phase II
|  | Achieved |  | Not met (but work has begun, and report will be produced in Octobe) | Met. The Government delayed the process for finalising the duty and waivers policy to allow time for adequate consultation and recommendations made by the CSO consortium have led to changes within the policy. | Met. The Government delayed the process for finalising the duty and waivers policy to allow time for adequate consultation and recommendations made by the CSO consortium have led to changes within the policy.
Source
Reports from Christian Aid civil society consortium
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline - Sept 2018 | Milestone 1 - Sept 2019 | Milestone 2 - March 2020 | Milestone 3 - Sept 2020 | Milestone 4 - Sept 2021 | Milestone 5 - Sept 2022 | Target - Sept 2023
40% | Availability of information to support C19 response procurement compliance to prevent fraud and corruption | Planned | N/A | N/A | N/A | A copy of simplified laws relating to financial management transparency in emergencies produced and shared with NEOC. Minutes of ACC Task Force deliberations indicate measures to address fraud in the Covid-19 response. At least 4 media engagements to inform citizens on simplified financial management/procurement laws.
|  | Achieved |  | N/A | N/A | Partially met. The simplified laws are in draft form and will be finalised in September 2020. Although minutes from the ACC Task Force have not been shared, the Task Force has been monitoring the response, including at district level, and has identified instances of due process not being followed in recruitment, procurement and records management. Recommendations have been made to address this. As the simplified laws have not been finalised no media engagement has taken place on these.
Source
Reports from Christian Aid civil society consortium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | DFID SHARE (%)
| £1.1m |  | £0.2m | 0 | £1.1m |  |  |  | 85%
INPUTS (HR) | DFID (FTEs)
1 (across 6 staff members)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Outcome | Outcome revised with details of indicators and milestones added | Annabel Charnock | 2019-05-01
2 | Outputs 1 and 2 | Both outputs added along with indicators to reflect agreed DFID-funded activities under Phase I of the programme | Annabel Charnock | 2019-05-01
3 | Outcome Indicator 1.1 | Edited Sept. 2020 target to indicate that this needs to be revised in line with the latest IMF targets from programme reviews. | Roisin Parish | 2020-02-01
4 | Outcome, Indicator 1.2 | Changed Sept. 2020 target from "Positive trend on PEFA / TADAT (timing tbc)" to "No target for this period. Next PEFA due in 2021. TADAT timings TBD." | Roisin Parish | 2020-02-01
5 | Outcome, Indicator 1.3 | Changed Sept. 2020 target from "70% of Priority 1 Annual Targets met; 40% of Priority 2 Annual Targets met." to "By end-June: Revised PFM reform strategy implementation plan in place, including monitoring mechanisms." | Roisin Parish | 2020-02-01
6 | Outcome, Indicator 1.4 | Changed March 2020 target from tbc to 4 and Sept target from tbc to 6 | Jerusha Ouma | 2020-03-20
7 | Outcome, Indicator 1.5 | Changed Sept. 2020 target from "tbc" to "70%, including 50% of the High Priority actions" | Roisin Parish | 2020-02-01
8 | Output Indicator 1.1 | Changed Sept. 2020 milestone from "tbc depending on design of Phase II" to "June 2020: 6 (minimum). Sept 2020: 1 (minimum)" | Roisin Parish | 2020-02-01
9 | Output Indicator 1.2 | Changed Sept. 2020 milestone from "tbc depending on design of Phase II" to "100% of advisers starting after March 2020" | Roisin Parish | 2020-02-01
10 | Output Indicator 1.3 | Changed Sept. 2020 milestone from "tbc" to "June 2020: 80%; Sept 2020: 80%" | Roisin Parish | 2020-02-01
11 | Output Indicator 2.1 | Target at Sept 2020 changed to June 2020 | Jerusha Ouma | 2020-03-20
12 | Output Indicator 2.2 | Changed Sept. 2020 milestone from "tbc depending on design of Phase II" to "By June 2020, KAP survey findings discussed at the district level. At least 1 example available of NRA follow-up actions." | Roisin Parish | 2020-02-01
13 | Output Indicator 2.3 | Changed Sept. 2020 milestone from "tbc depending on design of Phase II" to "By June 2020, evidence of at least 1 government action taken to respond to audit follow-up work. Evidence of Gov't and CSO follow up on PETS." | Roisin Parish | 2020-02-01
14 | Output Indicator 2.4 | Changed Sept. 2020 milestone from "tbc depending on design of Phase II" to "2 substantive actions taken by government (cumulative)" | Roisin Parish | 2020-02-01
15 | Output Indicator 2.1 | Changed Sept. 2020 milestone from "At least one national campaign, as well as district level engagements done." to "At least 2 TV and radio dissemination campaigns, at national and district levels done." reflecting C19 social distancing requirements | Roisin Parish | 2020-06-01
| Output Indicator 2.2 | Removed Sept. 2020 milestone "By June 2020, KAP survey findings discussed at the district level. At least 1 example available of NRA follow-up actions." to reflect C19 reprioritisation. This work will be picked up in phase 2. | Roisin Parish | 2020-06-01
16 | Output indicator 2.3 | Changed Sept. 2020 milestone to add reference to "At least 15 multi-media (print, social and electronics) engagements with the public on revenue, the utilization of CoVID-19 resources and other related information. At least 2 reviewed statements of income, expenditure, procurement processes/procedures produced and shared with government focused on C19 response. At least 3 revenue generation analysis updates produced and shared with GoSL. At least 6 media engagements held to update citizens on impact of Covid-19 on domestic revenue generation." | Roisin Parish | 2020-06-01
17 | Output indicator 2.5 | Introduced output indicator 2.5 "Availability of information to support C19 response procurement compliance to prevent fraud and corruption" with a Sept. 2020 target of "A copy of simplified laws relating to financial management transparency in emergencies produced and shared with NEOC. Minutes of ACC Task Force deliberations indicate measures to address fraud in the Covid-19 response. At least 4 media engagements to inform citizens on simplified financial management/procurement laws." | Roisin Parish | 2020-06-01
18 | Output indicator 1.2 | Added to target "(or following contract extension beyond June 2020)" | Roisin Parish | 2020-06-01

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.