Business Case

Summary Sheet

Title: / The OPHI Multi-dimensional Poverty Index and Sustainable Development Goal monitoring
Project Purpose: / To produce the 2018 update of the global Multidimensional Poverty Index (MPI) dataset; reports summarising MPI trends and patterns; and support uptake by global and national policy makers including a launch at the UN General Assembly (UNGA) in September 2018.
Programme Value: up to £300,000		Country / Region: Global.
Senior Responsible Owner: Tim Conway (Senior Social Development Advisor, Governance, Conflict and Social Development (GCSD) Research Team, Research and Evidence Division (RED).
Project Code:	Start Date: July 2018	End Date: 15th March 2019
Vault Number:

Intervention Summary (2 Pages)

Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver

Funds are needed to support the production of the 2018 updates to the Oxford Poverty and Human Development Initiative (OPHI) global multidimensional poverty index (MPI) dataset; the production of reports summarising MPI trends and patterns; and the launch of these reports at the UN General Assembly (UNGA) in September 2018.
The SDGs expanded the list of poverty reduction targets and focussed attention on the need to ‘leave no-one behind’ in achieving all of the goals. Supporting these shifts, the global MPI developed by OPHI is a useful complement to the global consumption poverty measure ($1.90 per capita per day) in that, while individual SDG targets track progress on particular dimensions of human welfare, the MPI captures the number of people who experience deprivation simultaneously in more than one of the selected component aspects. With the SDGs explicitly urging countries to reduce the proportion living in poverty in all its dimensions by 2030 (Target 1.2), the global MPI represents a useful metric for monitoring the progress to this target and allowing for international comparisons.
DFID will provide up to £300,000 to support OPHI in updating and refining calculations of the global MPI for over 100 countries, based on revisions to the methodology, agreed between OPHI and UNDP, which reconcile the use of the MPI in UNDP reporting with the technical approach recommended by OPHI. It will also increase the coverage of the MPI with the addition of new country estimates, including for the first time adding MPI estimates for India down to the District level. This programme of work is taking place from May through September 2018, culminating in the launch of the global report at UNGA. Additional analysis will be conducted after UNGA to consider in detail the changes over time in multidimensional poverty, as well as further disaggregations of the results (e.g. by age groups, ethnicities, or religion).
A team of 27 researchers is needed to process data from the latest available national surveys (mainly DHS and MICS) to generate new global MPI estimates. These should be ready in printer-ready tables by the end of July. Analysis of trends and patterns will be completed by the end of August, at which point materials will go to layout, print and translation.
Outputs will be (i) a global report on MPI trends and patterns, to be launched at the UNGA by OPHI’s Director and UNDP’s Administrator; (ii) four academic papers (two on newly-available data for India, one on aligning the MPI with the SDGs, and one on the case for an internationally comparable asset index); (iii) an updated and expanded interactive database of MPI measures; and (iv) dissemination of MPI analysis at the UNGA and other meetings, such as the Annual Meeting of the Multidimensional Poverty Peer Network (MPPN).
The outcome will be that policy makers (multilateral and bilateral donors, LIC and MIC governments and NGOs), implementing organisations and researchers will have access to data and analysis on trends and patterns in multidimensional poverty.

The impact will be that this information supports better targeted and more effective investments in policies and programmes for poverty reduction.

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the Department’s Business Plan?

Reducing extreme poverty is central to UK development policy and DFID’s mandate:
- ‘Tackling extreme poverty and helping the world’s most vulnerable’ is one of the four pillars of the 2015 UK Aid Strategy, as is the commitment to ‘leave no-one behind’.
- This reflects UK commitment to (and leadership in developing) the global Sustainable Development Goals (SDGs), and SDG Goals 1, 2 and 10 in particular.
- The 2002 International Development Act defines poverty reduction, along with responding to humanitarian emergencies, as the overarching purpose of DFID spending.
The 2016-2020 Strategic Defence and Security Review (SDSR) identifies social inequality and exclusion as amongst the factors undermining state stability.

What percentage of DFID’s Single Departmental Plan (SDP) results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
As a research programme, this will not deliver results directly but will contribute to better design and delivery of programmes that address SDP targets. The budget is appropriate to the need, opportunity and RED management capacities; and to the time available to complete the work.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
Yes: it supports the SDG monitoring framework and tracking of target 1.2.2 in particular. The programme is driven by the UNGA timetable and will conclude within the current FY.
Has the programme considered working with HMG Departments and accessing cross-HMG funds?
Other HMG Departments are not working on poverty measurement and analysis in low- and middle-income contexts; but there is a demand for this data for cross-HMG scenario planning.
How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
The programme will build on and complement existing DFID investments. DFID supported the initial development of the OPHI global MPI and, through grants under the DFID-ESRC Joint Fund for poverty alleviation, production of academic papers analysing MPI trends and patterns[1].
[1] The DFID-ESRC Joint Fund for Poverty Reduction research (in which DFID contributed two-thirds and ESRC one-third of funding) has in the past supported two research projects with OPHI relating to the global MPI. The first (ES/I032827/1) was ‘Multidimensional poverty: enriching methodologies of measurement and policy analysis’ (£387,000, 2011-2014); the second (ES/N014812/1) was ‘Engaging international institutions in multidimensional poverty’ (£70,000, 2015-16). Currently, this Joint Fund is supporting project ES/N01457X/1 "Integrated Policies to Reduce Poverty in its Many Dimensions” (£400,000, 2016-2019).
Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
This is a modest investment in a time-bound set of activities. There will be some flexibility around the number and location of launch events to be supported by the programme.
Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
Yes. Overall risk is assessed as minor / moderate and primarily to do with perceptions that DFID is opting for one poverty measure over another: this can be managed with careful messaging. Funds will go to an established body (based in Oxford University) with robust systems for managing delivery, finance and risk.
Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with UK aid logo and recognise UK Government funding – and, if not, why not?
Reports and the online database will acknowledge support from DFID and be branded accordingly.
Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
We are confident that the supplier (OPHI) can deliver high quality research which can shape policy and practice. DFID has engaged with OPHI in the past, including funding earlier work through the DFID-ESRC Joint Fund for Poverty Reduction Research.
Do the SRO and team have the capability and resources to deliver this programme?
Yes. The SRO has a background in poverty analysis and experience in managing poverty research. He will be supported by an experienced programme manager, and report to the GCSD Team Leader.

Strategic Case
Reducing extreme poverty is central to DFID’s legal mandate and public commitments, both domestic (the International Development Act and UK Aid Strategy) and international (the Sustainable Development Goals and commitment to ‘leave no-one behind’)[2]. This has been reiterated in the 2016 Bilateral Development Review and in public statements by successive Secretaries of State[3].
[2] The DFID commitment clarifies what is meant by ‘leave no-one behind’ as follows: “People who are furthest behind, have least opportunity and are the most excluded must be prioritised. Unless a sustained and concerted effort is made to include people who are the poorest, most excluded and hardest to reach, there is a risk that they will continue to be denied the opportunity to progress socially and economically.” DFID (2017) Summary narrative: what leave no-one behind means for the UK’s work overseas. p. 2.
[3] “Our objective – helping the world’s poorest while furthering UK strategic interests” (Penny Mordaunt, ‘I believe in aid’, 15th November 2017); ‘My department’s raison d’être is to end extreme poverty forever’ (Priti Patel ‘UK will do more, not less, to help the world’s poorest’: Financial Times, letters, October 27th 2016); “There is no task more urgent than defeating poverty” (foreword from the Secretary of State, p. 4 in DFID (2016) Rising to the challenge of ending poverty: the Bilateral Development Review 2016).

Extreme poverty is critically important not only in its own right, but as a contributor to other global challenges to UK security and prosperity. The DFID Chief Economist’s Office notes that “Security, fragility and poverty are highly intertwined, and there will be many places where to engage with security and fragility will require we engage with poverty”[4]. Reflecting this, DFID’s bilateral programmes focus on countries characterised by extreme poverty.
[4] Ranil Dissanayake, Stefan Dercon, Nick Lea and Sam Fell (2017) Three worlds in 2050: scenarios for poverty and development. DFID Chief Economist’s Office, 20th October 2017 p. 1.

To deliver on this mandate, DFID decisions need to be guided by accurate, consistent, timely and granular measures of poverty. Poverty - and extreme poverty - can be defined in a variety of ways. None are perfect: all reflect trade-offs between conceptual clarity; data availability (sample size and frequency of survey interval) and coverage; comparability between locations and over time; cost and capacity requirements; and timeliness (lag between data collection and reporting).

While income- or consumption based measures remain central to understanding the ways in which economic growth and transformation do- or do not- translate into jobs, livelihood opportunities and real incomes for different groups amongst the poorest, there are significant difficulties in using these measures to compare or aggregate between countries. National poverty lines based on country-specific consumption surveys that remain consistent between rounds provide a robust means of tracking national trends and within-country patterns. However, when attempting to compare levels and trends in poverty between countries, or aggregate national counts into regional or global totals, (i) even small differences between countries in how consumption data is collected and processed can significantly change the level of poverty that is reported and (ii) the purchasing power parity (PPP) exchange rate values that are used to convert national data into a common metric are far from perfect and introduce significant uncertainty into the comparison of poverty rates between countries.

As a result, while estimates of poverty as measured against the $1.90 international poverty line are necessary and useful, they can and should be complemented with other approaches to the estimation of extreme poverty which address some of the most significant real experiences of living in poverty that monetary measures miss. A global composite multidimensional poverty index is one approach to doing this[5]. Drawing on the indicators available from Demographic and Health Surveys (DHS), Multiple Indicator Cluster Surveys (MICS) and others, the global MPI designed by OPHI captures multiple deprivation in 10 indicators under three domains[6]. In 2010 the UNDP adopted OPHI’s ‘global MPI’ to report on progress in the country data tables included in the annual Human Development Report (HDR)[7].
[5] In addition, reflecting evolving thinking on how to balance absolute and relative (country-specific) understandings of poverty in a global monitoring framework, 15 countries now use their own national, country-specific MPIs for policy and planning purposes.
[6] The ten weighted indicators are of OPHI’s global MPI are nutrition and child mortality (under the health dimension); years of schooling and school attendance (under the education dimension); and cooking fuel, improved sanitation, safe drinking water, electricity, flooring, and assets (under the living standards dimension).
[7] The evolution of the OPHI global MPI methodology is described in Sabina Alkire and Maria Emma Santos (2013) Measuring acute poverty in the developing world: robustness and scope of the Multidimensional Poverty Index. OPHI Working Paper No. 59, March 2013 and Sabina Alkire and Gina Robles (2017) Global Multidimensional Poverty Index 2017 OPHI Briefing 47.

In recent years, however, some differences in computations led the UNDP Human Development Report Office (HDRO) and OPHI to calculate separate measures, reflecting differences in thinking about the imputation of missing data and related differences in country coverage[8]. In early 2018, HDRO and OPHI agreed to adjust and unify their methodologies on poverty measurement in order to better monitor the Sustainable Development Goals (SDGs), calculating a joint global MPI which will cover over 100 developing countries in future HDRs. The revisions that are to be supported by DFID through this Business Case aim explicitly to address this need and better align the global MPI to SDG monitoring.
[8] In 2014, UNDP introduced an innovation to the calculation of the Index as reported in the HDR (the imputation of values for children to the scores for child-less households) which diverged from the approach employed by OPHI. While imputation is a valid approach, there were questions about the suitability of the sample weights used in this process. The most recent OPHI update of the global MPI in winter 2017-2018 was calculated for 104 countries; while the most recent (2016) HDR calculated the global MPI for 102 countries.

The outputs will be:
A global report which will be launched by the UNDP Administrator at or just before the UN General Assembly in September[9]. This is likely to show a considerable decline in global multidimensional poverty, driven by gains in South Asia including India between 2006 and 2016.
[9] UNDP have proposed additional launches in India, Rwanda, and perhaps Thailand and Latin America.

Four major academic papers:
- India / South Asia MPI changes over time
- India MPI by districts
- Aligning the global MPI to the SDGs: methodological revisions and ongoing data gaps
- “The quixotic necessity for an internationally comparable asset index”.

An updated and expanded interactive database of global MPI measures.

The outcome will be that policy makers (multilateral and bilateral donors, LIC and MIC governments and NGOs), implementing organisations and researchers will have access to data and analysis on trends and patterns in multidimensional poverty.

The impact will be that this information supports better targeted and more effective investments in policies and programmes for poverty reduction and helps to realise the SDG commitments, including Leave No-One Behind.

Gender Equality
The proposed research programme is fully compliant with the 2014 Gender Equality Act. The OPHI global MPI provides another lens on gendered dimensions of poverty. While it cannot support analysis of intra-household differences in outcomes (in common with the majority of income or consumption poverty measures, the unit of analysis is the household), it is possible to compare the incidence and severity of MPI poverty between male- and female-headed households[10]; and, when such differences are observed, enable an unpacking of the index to understand which of the component deprivations are responsible for welfare (MPI) differences between male- and female-headed households, contributing to identifying pockets of poverty and leaving no one behind.
[10] # See for example Michael Rogan (2016) ‘Gender and Multidimensional Poverty in South Africa: Applying the Global Multidimensional Poverty Index (MPI)’ Social Indicators Research April 2016, Volume 126, Issue 3, pp 987–1006
Terrorism and financing
Our assessment is that the risk of programme resources being used to fund terrorism is close to non-existent, and acceptable. Funds will support the staff time of researchers and casually-contracted workers employed by research institutes (the majority located in Oxford), plus small allowances for online and hardcopy communication materials and travel and travel-related expenses, with minimal opportunities for misappropriation.
## Appraisal Case

OPHI has submitted to DFID a proposal to deliver this work.
There is limited scope for competition in the sourcing of this work. Alternative multi-dimensional poverty indices have been developed by other institutions, but have not achieved the institutional acceptance and uptake of the OPHI MPI. This proposal is based upon acceptance of the following premises:
1. a global MPI which supports between-country comparisons in terms of a summary measure of welfare in non-income dimensions is a useful complement to other global poverty measures (such as the $1.90 international poverty line)
2. the OPHI MPI is the best-known global MPI, for which values are now available for many countries over a long period. Its use by the UNDP gives it considerable reach and stimulates debates on how to further refine poverty measurement for policy and programming.
3. the current opportunity to reconcile the OPHI and UNDP methodologies which diverged in 2014 is to be welcomed, and supported, as it provides greater confidence in the MPI values reported in the Human Development Reports.
On this basis, options to achieve the strategic case (for a relatively small commitment of funds to support the update of the global MPI measures) are as follows:
- Lobby others to fund this work. In principle, this work might best be funded by UNDP. However, UNDP has indicated that they do not have funds available for this (although they have offered to make available half a FTE staff position for six months to assist).
- Commission others to undertake this work. While most the survey data from which the OPHI global MPI is compiled is in principle publicly available, OPHI has developed and tested the MPI approach in question; invested considerable time in collating, cleaning and standardising this data from c.120 countries; and developing the analytical programming (Stata do-files), data management workflow and relationships with national statistical offices required to generate, quality assure and sense-check the MPI measures. Asking another organisation to replicate OPHI’s work and collaborate with the UNDP would be neither technically nor politically feasible (and a violation of principles of intellectual property and good DFID-supplier relationship management). This option should be discarded.
- Commission OPHI to produce the 2018 MPI estimates, reports and dissemination. Our assessment is that at present only OPHI has the capability to deliver the revisions to the global MPI dataset - particularly on the timetable required for launch at UNGA.
We assess that only OPHI can deliver this work.
OPHI’s proposal represents good value for money: staff and non-staff costs are proportionate to the volume of work involved, and a commitment of a relatively modest sum of funds builds on earlier years of OPHI work to deliver a strategic result which should broaden the options for global poverty / SDG monitoring.
It is recommended that DFID should proceed to agree a final workplan and budget to ensure delivery and negotiate an Accountable Grant with OPHI.
Commercial Case

OPHI has submitted a proposal for this work with an associated budget of £300,000.
DFID will draw up and Accountable Grant agreement with OPHI. OPHI has previously received grants from DFID both directly and indirectly through the ESRC-managed DFID-ESRC Joint Fund for Poverty Reduction research. We will conduct a due diligence assessment that will test financial systems and safeguards.
Value for money will be ensured by agreement of a clear, time bound delivery plan (see management case below); and oversight by DFID advisors. We will benchmark costs such as fee rates, and logistical costs for publications and policy engagement events to ensure that these maximise value for money against DFID’s ‘4 Es’ framework.
## Financial Case
The request from OPHI includes the indicative budget laid out in Table 1[11]. The bulk of funds will be required to calculate and check the new MPI estimates and then produce 104 country briefings, 13 regional, thematic and methodological briefings, four papers and one global report. Research communication and uptake activities (web-based outputs, publications, and launch events) account for c. 25% of estimated total costs.
[11] This reflects the budget in the proposal received in May; plus additional costs for interactive database development in subsequent email communications.
Table 1: Indicative budget
Category	£
Project management and leadership	43,263
Data management and production of estimates	99,385
Quality assurance and report writing	43,107
Research communication and uptake*	69,476
Overhead (10%)	25,523
total	280,754

* including travel and subsistence for launch events

On this basis, RED’s GCSD team will provide financial and management resources up to £300,000. RED has resources in place to procure and manage the project. OPHI comes under the fiduciary responsibilities of the University of Oxford, is subject to the University’s audit procedures and employs the University’s financial management and accounting systems. Prior to disbursement, DFID will complete a Due Diligence assessment for OPHI, which will remain valid for three years.
DFID will disburse funds in arrears in two tranches on receipt of invoices. The first payment is likely to be on or soon after 15th October; the second on or soon after 15th February.
Modest co-funding has been secured from other sources. The Swedish International Development Agency (Sida) is supporting the project with 50% of the time of two researchers and the University of Oxford has provided a small sum (c. £10,000), but more is needed to complete the work. The costs in Table 1 are net of these other contributions.

## Management Case
OPHI has submitted a proposal to DFID which has informed the content of this Business Case.
On the basis of this proposal, DFID will sign an Accountable Grant (AG) agreement with OPHI including Terms of Reference and workplan to cover the following:
- Overall budget
- Scope and methodology
- Key staffing
- Schedule for production of outputs (data, reports) and dissemination activities
- Reporting arrangements

The outputs will be:
- A global report on trends in MPI poverty, destitution, and vulnerability
- Four academic papers covering regional and methodological issues
- An updated and expanded interactive database of global MPI measures.
- A launch event at the UNGA (and possibly regional launch events, to be agreed).

The project will run from July 2018 to March 2019. The bulk of the work under this programme is expected to be concluded in October 2018, and the months after this will allow for refinement of the more technical outputs following the UNGA launch. OPHI has provided a draft workplan leading up to the UNGA (Annex 1). The first stages of this have been completed, drawing on existing non-DFID funds; but funding is required to complete Stages 3 onwards.
OPHI will provide DFID with three brief progress reports (one- to two-page note plus phone or VMR discussion if necessary) on or around 4th September 2018; 10th October 2018 (which will include a short report on the UNGA launch and follow up); and 10th January 2019. It will also provide a brief end-of-project report in an appropriate format to support DFID staff in drafting a proportionate Project Completion Report (PCR), which will have to be approved and loaded on DFID’s systems by 30th June 2019 (three months after project end).
The project will be managed by a Team Leader at OPHI under the overall leadership of the Director.
In DFID, the project will be managed within GCSD by a Senior Responsible Officer (SRO) and a Project Manager (PM). The SRO will be responsible for the quality and delivery of the programme, ensuring it meets with expectation. The PM will be responsible for all corporate compliance.

Risks

Delivery risk. Failure to deliver the global report in time for launch at UNGA at the end of September 2018 would be a significant lost opportunity. The timeframe is tight and will require close management by OPHI. However, OPHI has strong incentives to complete on schedule and a sensible workplan to keep them on track. This workplan reflects their experience in conducting earlier rounds of global MPI updates, and well-developed institutional capacity for data processing and report production workflow.
Political / relationship risk. There is an active and complex set of debates regarding suitable methodology and data for the definition and measurement of poverty, particularly at the international / global level. This has included a strongly polarised debate between advocates and critics of OPHI’s composite multi-dimensional poverty index[12]. It is also true that the OPHI MPI is not the only global / cross-country MPI in existence, and different indices have different relative strengths and weaknesses with regard to conceptual basis, data availability (country coverage and length of trend data) and technical properties (e.g. ability to disaggregate into component indicators)[13].
[12] See the debate on Oxfam’s From Poverty to Power website between Martin Ravallion (2010) Guest blog: World Bank research director critiques the new UN poverty index; and response from Sabina Alkire (2010) The co-creator of the UN's new Multidimensional Poverty Index defends her new baby; Martin Ravallion (2010) Mashup indices of development. World Bank Policy Research Working Paper No. 5432; Sabina Alkire, James Foster, Maria Emma Santos (2011?) The value added of multidimensional poverty measures.
[13] See for example Nicole Rippin (2011) A response to the weaknesses of the Multidimensional Poverty Index (MPI): the correlation-sensitive poverty index (CSPI) German Development Institute Briefing 19/2011.
As such, it is important that DFID is understood to support the OPHI global MPI as one of several important elements of global poverty / SDG monitoring, complementing other elements (including but not limited to the $1.90 international poverty line).
DFID is not taking sides in favour of the OPHI MPI above the other possible measures currently in existence or recommended for development (as in, for example, the recommendations of the Atkinson Commission report[14]).
[14] The Atkinson Commission report (World Bank Group (2016) Monitoring global poverty: report of the Commission on Global Poverty), released in October 2016, made 21 recommendations, addressed primarily to the World Bank, regarding improvements in global poverty measurement. Recommendations 18 and 19 addressed the issues around the use of an MPI as part of a set of poverty indicators to complement consumption-based estimates. (Recommendation 18: “The World Bank should establish its own requirements with regard to the measurement of nonmonetary poverty, for inclusion in the Complementary Indicators (including the overlapping poverty measure) and in other World Bank uses, and ensure that these are fully represented in the activities of the international statistical system, particularly with regard to the proposed SDG indicators”; Recommendation 19 “The Complementary Indicators should include a multi-dimensioned poverty indicator based on the counting approach.”) The World Bank management response to these two recommendations acknowledged the value of an MPI, but diverged from the OPHI approach in proposing to include consumption within the index. (“We plan to implement this suggestion by tracking non-monetary deprivations in three specific domains where relative market prices are typically either unavailable or uninformative as natural aggregators, namely: educational outcomes; access to health care; and access to basic services, such as water, sanitation and electricity. We are particularly interested in the overlap among these different deprivations, and between them and monetary poverty. We will therefore include our measure of monetary poverty (with respect to the IPL) as one of the dimensions covered by the index. This has substantial implications for the data sources that can be used to monitor global poverty, and thus for how the other dimensions can be measured. It implies, in particular, that we will rely on household surveys of the kind we currently use to measure monetary poverty, and measure deprivations along other dimensions using variables that are available in the same surveys (even if this implies some limitations in coverage and quality). These dimensions will be aggregated using a member of the class of multidimensional poverty indices proposed by Alkire and Foster (2011).”) For initial thinking on how to respond to the recommendations of the Atkinson Commission regarding a global MPI within the SDG monitoring framework, see Maria Ana Lugo (2016) Integrating multidimensionality in global poverty monitoring. Presentation by the World Bank Poverty and Equity Global Practice, 10th November 2016.
DFID messaging, including branding around the UNGA launch, should reflect this balance. More broadly, the new DFID research programme on extreme poverty, approved by Ministers in January 2018 and currently starting procurement processes, contains a budget of c. £3 million for design and trialling of new methods for collecting, processing and presenting data for measuring extreme poverty. This provides a clear signal that DFID will continue to invest in a broad spectrum of methodological approaches and innovations, which may include trialling one or more alternative MPI for comparison with both the international poverty line and the OPHI global MPI.
Fiduciary and safeguarding risk. As the work involved will largely involve data processing and report drafting within an established research institute with strong systems and controls in place, safeguarding and fiduciary risks are considered minimal.
OPHI will be asked to alert DFID to any change in risk exposure (probability or magnitude of impact); the SRO will escalate this information within DFID as necessary.

Annex 1: Draft schedule for completion of work

Stage 1: Finalise GMPI 2.0 indicators
- Produce two working papers that test trial measures using data from 12 - 15 countries
  - Paper 1: Assets and multidimensional poverty
  - Paper 2: Aligning the GMPI indicators with the SDGs: possibilities and feasibilities
- Agree on the final GMPI 2.0 indicators
- In parallel, open for consultation and receive feedback

Stage 2: Standardise 104 datasets
- Finalise 3 prototype GMPI 2.0 do-files to be adopted for DHS, MICS and PAPFAM datasets
- Implement data preparation and standardisation of indicators for 104 countries (across 6 regions) following the prototype do-files (Support: 11 RAs)
- Prepare excel table that allows for comparison of published GMPI and recently produced GMPI 2.0 results by country. Carry out additional data checks for problematic country results

Stage 3: Data analyses
- Analyse 104 country datasets
- Produce H, A, MPI, raw headcount, censored headcount, contribution of indicator, vulnerability, severity, destitute and inequality estimates for national, urban, rural and subnational
- Merge with WDI data: country population, $1.90 a day and GDP pc
- Finalise data tables

Stage 4: Finalise 104 country briefings
- Make revision to the master frame of the country briefing in LaTex so as the content matches changes in GMPI 2.0 (This task will start in Stage 2)
- Produce high quality subnational maps for each of the 104 countries, 6 regional maps and 1 global map. (This task will start in Stage 3)
- Start on the production of the 104 country briefs
- Proofread figures and maps of each country brief
- Send out to MPPN members/UNDP country office/country statistic office for validation by 15 July. Any issues in relation to the numbers must be received or highlighted by 01 September

Stage 5: Write Report and Briefings and methodological note
Start drafts of 10 briefings which are also Chapters of a Report:
- Brief 1: 16 pager
- Brief 2: 2 page summary from the 16 pager
- Brief 3: India brief: key district findings
- Brief 4: Child brief
- Brief 5: Regional brief (with map): Arab States
- Brief 6: Regional brief (with map): East Asia
- Brief 7: Regional brief (with map): Europe & Central Asia
- Brief 8: Regional brief (with map): Latin America
- Brief 9: Regional brief (with map): Sub-Saharan Africa
- Brief 10: Regional brief (with map): South Asia
- Start draft methodological note
- If time permits 3 other briefings, but can do this after launch as well:
- SDG-GMPI brief
- Comparison of GMPI and GMPI 2.0
- Comparison of $1.90 a day and GMPI 2.0 + GDP pc and GMPI 2.0

Stage 6: Proofreading, layout & design
- Send out the finalised 10/11 OPHI briefings for initial proofreading by 15 August
- Finalise briefings for layout and design
- Finalise data tables for website update
- Finalise GMPI 2.0 methodological note for website

Stage 7: Work on press release & prepare power-point presentation for launch
- Draft press release with HDRO
- Work on presentation for launch

Stage 8: Printers and web update
- Finalised materials must go out to printers, the latest, on 10 September
- Printed materials must reach OPHI, the latest, on 21 September
- Assemble printed materials to be carried to UNGA on 21 and 22 September
- Website updates should be lined up between 21-24 September

Annex 2: abbreviations and acronyms

AG	accountable grant
CSPI	Correlation-Sensitive Poverty Index
DHS	Demographic and Health Survey
ESRC	(UK) Economic and Social Research Council
FY	financial year
GCSD	(DFID) Governance, Conflict and Social Development research team
GDP	gross domestic product
HDR	(UN) Human Development Report
HDRO	(UN) Human Development Report Office
HMG	Her Majesty's Government
IPL	International poverty line
LIC	low-income country
MICS	Multi-Indicator Cluster Survey
MICS	high-income country
MPI	multi-dimensional poverty index
MPPN	Multidimensional Poverty Peer Network
NGO	non-governmental organisation
OPHI	Oxford Poverty and Human Development Initiative
PAPFAM	Pan-Arab Project for Family Health
PCR	(DFID) Project Completion Report
PM	(DFID) Programme Manager
PPP	purchasing power parity
RA	research assistant
RED	(DFID) Research and Evidence Division
SDG	(UN) Sustainable Development Goals
SRO	(DFID) Senior Responsible Officer
UNDP	United Nations Development Programme
UNGA	UN General Assembly
WDI	World Development Indicators

Endnotes