Annual Review – post April 2018

Title: Title: Support to Improved Water and Sanitation Project in Rural Areas of Zimbabwe
Programme Value £ (full life): £50,500,014		Review Date: June 2019
Programme Code: 202691	Start Date: July 2012	End Date: October 2019

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019
Programme Score	B	B	A	A	A+	A	A
Risk Rating	Moderate	Severe	Severe	Moderate	Moderate	Moderate	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717554.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202691/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)
The Support to Improved Water and Sanitation Project in rural areas of Zimbabwe programme (hereafter referred to as the Rural WASH programme or RWP) started in 2012 in response to increased exposure to Water, Sanitation and Hygiene (WASH)[1] related diseases amongst the poor and vulnerable people in rural Zimbabwe. It followed the catastrophic cholera outbreak of 2008/9 that resulted in over 4,000 deaths and a cumulative caseload of 98,592[2] due to a collapsing WASH service delivery system and the ailing economy. At outcome level the programme specifically seeks to (1) reduce the burden of WASH related diseases, unbearable workload and stress women and girls face in collecting water, (2) improve basic education outcomes and strengthen gender equality through providing equitable and sustainable access to clean water, and (3) improved sanitation and adoption of good hygiene practices in forty-five targeted rural districts in Zimbabwe. The districts were chosen based on low water and sanitation coverage and vulnerability to effects of climate change such as drought and floods.
[1] Water Sanitation and Hygiene
[2] Evaluation of the WASH Response to the 2008-2009 Zimbabwe Cholera Epidemic and Preparedness Planning for Future Outbreaks

This programme has been running in two (2) distinct phases. In Phase one (July 2012-October 2016), the programme delivered WASH infrastructure and services in thirty-three districts, of which three were funded by the Swiss Agency for Development and Cooperation (SDC). They co-financed this programme with US$4.2 million.

Phase two (November 2016-October 2019): a £12 million extension was approved in October 2016 for work in a further twelve districts following the success of the first phase. This brought the total number of DFID Zimbabwe funded programme districts to forty-two and the programme total to forty-five. In this second phase, DFID is helping all programme districts with technical and policy support to sustain the achieved results in view of the ever-changing operating context.

Through UNICEF and eight Implementing Partners (IPs)[3], the programme is supporting government ministries and communities to cope with effects of climate change and variability across all districts, given the depletion of water sources and the exposure of WASH infrastructure to extreme weather events.
[3] Africare, Care International, Christian Care, Farm Community Trust of Zimbabwe, Welthungerhilfe, Mvuramanzi Trust, Plan International and World Vision

Expected programme results
By October 2019 this programme planned to:
- Reach over four million people with improved access to safe water supplies through drilling 1,460 new boreholes and rehabilitate 15,063 non-functioning boreholes and forty-two Piped Water Schemes (PWSs) that were not adequately maintained prior to the programme across the selected districts.
- Reach over 960,000 people with improved access to safe sanitation facilities through facilitating the construction of self-sponsored household and school latrines.
- Help at least 3,250 villages to attain Open Defecation Free (ODF) status, reducing the risk of diseases.
- Reach over two million people with hygiene promotion activities
- Strengthen the capacity of local, subnational and national WASH governance structures to manage WASH infrastructure and services. These include Ward Water & Sanitation Sub Committees (WWSCs), District Water and Sanitation Sub Committees (DWSSCs), Provincial Water and Sanitation Sub Committees (PWSSCs) and National Coordination Committees.
- Establish a viable community based Public Private Partnership (PPP) model for rural water and sanitation as a way of improving the supply chain of WASH services and commodities.

The expected results will directly contribute to the UK’s global commitment to help at least 60 million people with access to improved clean water and sanitation[4].
[4] UK Aid Strategy, November 2015

Summary supporting narrative for the overall score in this review (1/2 page)
This review looks at progress between July 2018 and June 2019. During this period, the programme was delivered under a difficult political, economic and environmental context. There was a slowdown on programme activities in both pre and post July 2018 general elections. The macro-economic outlook also deteriorated significantly, resulting in activities being either suspended or delayed mainly for two reasons: (i) ensuring that we protect the value of UK funding by paying the right price for goods and services, therefore maintaining good Value for Money (VfM) and (ii) in some instances certain commodities such as fuel and construction material were not available on the market. A cholera outbreak and tropical cyclone Idai are major disasters that affected the country and inevitably disrupted the implementation of this programme. Despite this, the programme performed well, scoring an A mainly because:

The programme continues to perform above expectations on people being supported with improved access to safe drinking water because of water supply infrastructure developed in the past year as shown in fig 1 below. Rehabilitated Piped Water Schemes (PWS) are contributing significantly to education, health and local economic outcomes.

Fig 1:People supported with improved water supplies
        Fig 2: No.of people with improved sanitation facility

Over 23,400 people were helped with toilets, of which 9% are disabled women and men. Although the programme did not meet expectations on villages attaining Open Defecation Free (ODF) status at this stage, the number of people with improved sanitation has in the past year slightly increased as shown in Fig 2 above. There is a positive trajectory, despite the difficult operating context.

The programme successfully responded to two WASH related emergencies over the past year, helping over 170,000 people with access to safe water, sanitation and hygiene. Since September 2018, it has been responding to a cholera outbreak in several districts across the country and another emergency WASH response is being provided to Cyclone Idai in Chimanimani and Chipinge districts.

The Rural WASH Information Management System (RWIMS), widely regarded as an important management tool that helps in rural WASH sector planning and timely response to breakdowns continues to improve although there is slow progress in getting RWIMS SMS Notification Response (SNR) component to phase 1 and Mashonaland East districts.

Unlike in previous years, the programme made a significant contribution to equitable access to water and sanitation. At least 12% of people reached by water and sanitation interventions live with disability.

Recommendations for the year ahead (1/2 page)
Based on this review, the following are key recommendations the programme need to consider to make a significant contribution to the intended outcome. Specific output-based recommendations are provided in Section B, under relevant outputs.

A twelve (12) month no cost time extension to enable the programme to deliver outstanding activities that were mostly delayed due to external factors such as the declining economy and unforeseen disasters. The extension will also be used to ensure the expected outcome is sustainable. UNICEF/DFID by 30 July 2019.

Continue to lobby for increased government WASH sector financing to improve WASH service delivery. The ongoing sector Joint Sector Review (JSR) should create a good basis for engaging the government to improve WASH sector financing. UNICEF/ PMT by October 2019

Intensify monitoring and technical support to districts to ensure all set out outputs are delivered on agreed timelines and in good quality. UNICEF to work with the Programme Management Team (PMT) and PWSSCs to develop a programme delivery acceleration plan by 1 July 2019.

Integrate disaster response plans in district WASH plans. This is in view of recurring emergencies in many of programme districts. Programme districts such as Buhera have in the past two years experienced cholera outbreaks and remain vulnerable. Climate/weather related disaster are more frequent than before and are destroying WASH infrastructure and interrupting WASH service delivery. UNICEF/ PMT by 30 July 2019

Intensify district support on data management and evidence-based reporting. Based on this review, some districts such as UMP and Tsholotsho did not have substantial evidence to support results. For example, positive outcomes such as reduced walking distance to fetch water, improved water point functionality rate and reduced diarrhoeal diseases were not adequately supported by documented evidence. UNICEF/ PMT by 30 July 2019

Provide orientation to DWSSCs on key WASH policy and standards to ensure consistency in and quality delivery of WASH projects. There are cases where there was no reference to approved standards in construction of WASH facilities.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Rural populations have access to safe water supplies and improved school sanitation facilities
Output number per LF		1	Output Score	B
Impact weighting (%):		30%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review (June 19)	Progress	Score	% Log frame Achievement
1.1 Number of new protected water supplies established in rural communities and schools, disaggregated by type	1,460	1,452	B	99.5%
1.2 Number of water supplies repaired or rehabilitated in rural communities disaggregated by type (borehole/piped water scheme)	15,063	14,988	B	99.5%
1.3 Number of schools receiving new or improved sanitation facilities disaggregated by school type and level of construction, i.e. new or rehabilitated facilities)	1,537	1,529	B	99.5%
1.4 Number of rehabilitated piped water schemes supported with low carbon technology (solar system)	32	20	C	62.5%

Provide supporting narrative for the score
There was a drop in performance on this output compared to the last annual review. All indicators achieving less than 100%. In the last review, indicator 1.2 achieved a 132% compared to 99.5% achieved in the year under review. Output indicator 1.4 performed beyond expectations in the previous review, compared to 62.5% achieved in the past year. The drop in performance is largely attributed to the suspension of activities due to difficult external factors that include both the unavailability and increased cost of toilet construction and water supply material by over 100% and in many cases did not give good value for money had the programme procured at prevailing market rates. Political events and unexpected emergences also had a huge effect on programme performance.

Despite a decline in the overall performance of this output, a 100% functionality rate was reported for Piped Water Schemes (PWSs) rehabilitated in Phase 1, compared to 89% functionality rate of rehabilitated boreholes equipped with B-Type Bush pump during the same period. The emerging trend is that PWSs have a higher functionality rate compared to B-Type Bush pumps. Also, 99.6%[5] of tested water samples met the WHO drinking water standards. Water points that failed to meet the drinking water quality were disinfected by the Ministry of Health and certified for drinking.
[5] 4077 out of 4094 water samples met the WHO drinking water quality standards

Another notable achievement under this output in the past year, has been the positive contribution of PWSs towards health and education outcomes. In addition to improved access to household portable water access, nearby schools, rural health centres and rural business centres have benefited from established piped water schemes. Although more evidence is yet to be collected across the programme districts, two schools in the visited districts during the review, reported improved school attendance, especially from girls. Availability of water has also made work at rural health centres a lot easier, especially in the maternity sections. Water infrastructure in some districts is also being designed to meet the needs of people living with disabilities. Image 1 below is a stand water pipe at Masvova piped water scheme in Makoni district. It is fitted with a ramp and supporting rail to improve access to users with walking and seeing disabilities. Image 2 show Early Childhood Development (ECD) learners easily accessing drinking water an Masvosva school. Both images demonstrate programme efforts to use water supply technologies that ensure equitable access to safe drinking water.

Image 1:Disability friendly water point Image 2: Improved access to water for ECD learners

PWSs are widely reported as contributing significantly to reduced time and walking distance to fetch water, however the programme is not collecting enough quantitative data of reduced walking distance and time to fetch water to demonstrate the effectiveness of the intervention. The main constraints being lack of financial and technical capacity in many districts.

This review identified the following issues that could negatively affect the programme ability to deliver the intended outcome:

Delays in rehabilitating 24 PWSs largely due to distorted prices and time taken in exploring alternatives that could still help the programme delivering at good VfM. The programme has however opted to split feasibility and actual works, mainly to determine the actual specifications and get quoted the right price for each individual PWS, given the variations in scale, size and works required for each scheme. UNICEF has engaged the University of Zimbabwe and the National University of Science and Technology (NUST) to do technical assessments, designing and costing. The cost of this is within the range of the initially budgeted amount.

Use of poor-quality water supply material resulting in frequent interruption of water supply. This is a case of Masvosva piped water scheme in Makoni district.

Lessons identified this year, and recommendations for the year ahead linked to this output
- A no cost extension should be considered to enable the programme to deliver outstanding PWSs.
- As the programme prepares to deliver the remaining PWSs, pre-delivery inspection of material needs to be done to ensure the project gets quality and durable material. Piped water system designers need to be part of the procurement process to provide guidance on specifications and type of material.

Output Title	Rural population have access to safe sanitation facilities and have knowledge on safe hygiene practices
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress	Score	% Log frame Achievement
Number of additional people with access to an improved sanitation facility	937,769	923,571	B	98.5%
No of schools with hygiene promotion programmes	1,701	1,975	A+	116%
Number of people including school children reached with hygiene promotion activities	2,236,100	2,364,811	A+	105.7%

Provide supporting narrative for the score
This output gets an A score, mainly because two of the three indicators performed above expectations, while the other indicator scored 1,5% below expectations because of slow progress in delivering the self-sponsored latrines across the 12 new districts. This is largely being attributed to significant increase in the cost of latrine construction material to levels beyond the reach of many poor communities targeted by the programme. However, there is good progress in delivering subsidised latrines for the vulnerable groups. The overall programme target for subsidised latrines was met in the past year. Combined progress of both self-sponsored and subsidised latrines has contributed to 96% achievement of villages declared open defecation free (ODF) across the 12 phase two districts. However, it is unlikely that the remaining 4% of the programme ODF target will be met in the remaining four months before the project is completed, unless acceleration plans are put in place. Makoni district has an acceleration plan that involves increased mobility and presence of Environmental Health Technicians in targeted villages to speed up ODF certification and latrine construction which could be also be done by other districts.

Momentum on villages being declared ODF has slowed down in Phase 1 districts such as Tsholotsho mainly due to lack of financial resources to support monitoring and community mobilisation. Most districts were unable to maintain the delivery pace after the Non-Governmental Organisations (NGOs) partners pulled out of districts.

The programme has provided support to school health clubs to promote good hygiene behaviour in schools and local communities. Active school health clubs that were visited during the review displayed knowledge and confidently articulated hygiene topics taught through health clubs. This include hand washing, safe disposal of faeces, safe water sources and types of germs.

Additional funding given to this programme in July 2018 is helping in strengthening WASH in schools through construction of 26 additional toilets, with strong focus on improving equitable access for all children, including those living with disabilities, boys and girls. Key features include facilities to improve menstrual hygiene management and privacy.

The upgradable Blair Ventilated Improved Pit (uBVIP)[6] standards are not consistently applied across the programme. For example, in Tsholotsho, one bag was used and in other instances two bags were used for constructing the substructure. In the same district, sub structures were lined with tree logs, against the standard of lining with cement and bricks. There is lack of adequate monitoring on performance indicators of this output. For example, behaviour change to ensure appropriate support is provided to avoid slippage is not regularly tracked in some districts. Uzumba Maramba Pfungwe (UMP) and Tsholotsho are some of the areas where there was no enough evidence to show this is happening.
[6] This is an incremental approach to build a Blair Ventilated Improved Pit (BVIP) a government approved standard toilet for rural Zimbabwe. The approach provides community flexibility in building toilets and has been used to support the demand led sanitation approach.
  Lessons identified this year, and recommendations for the year ahead linked to this output
- Ensure the Ministry of Health and Child Care (MoHCC) district focal teams are adequately trained on demand led sanitation and have adequate resources to ensure sustainability of results already achieved, such as villages already declared ODF.
- Speed up the rolling out of the ODF sustainability framework to avoid slippage.
- Implement acceleration plans put in place to deliver outstanding targets.

Output Title	Community based Public- Private sector Partnerships (PPPs) supported for sustainable operation and maintenance of rural water supplies
Output number per LF		3	Output Score	A+
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress	score	% Log frame Achievement
Percentage of new/repaired water sources with trained and functional gender parity (WPCs)	90%	95%	A+	95%
Percentage of Water Point Committees established by project raising funds for operation and maintenance of water points	90%	95%	A+	95%
Percentage of Water Point Committees established by project with access to trained and equipped Village Pump Mechanics (VPM’s){1 VPM for every 5 WPC's)	100%	112%	A+	112%

Provide supporting narrative for the score
An A+ score is given on this output because all indicators performed above expectations. However, the prevailing difficult economic environment made it difficult for the programme to fully establish a viable PPP model, especially with well-established businesses. In few cases where the programme seems to have established partnerships, there are no written agreements with local suppliers, implying the partnerships are informal and not binding.

All water points established this month have access to a trained and equipped Village Pump Minder (VPM). This is an improvement from the last annual review, although in some districts such as UMP VPM tool kits were delivered late. Water Point Committee (WPC) capacity to raise operation and maintenance fees is threatened by the prevailing harsh economic environment. The value of monetary savings is being eroded due to rising inflation. However, there are community initiatives to protect their savings that must be applauded and must be encouraged throughout the programme districts. WPCs in in some districts are storing their values in livestock and sell when the need to pay for repairs arise.

Lessons identified this year, and recommendations for the year ahead linked to this output
- Consolidate evidence on best practices on PPPs as experienced by the programme.
- DWSSCs to continue providing WPCs with Operations & Maintenance planning and budgeting especially in using calculated cost drivers to determine user fees.

Output Title	Rural Water Supply and Sanitation Institutions strengthened to legislate, coordinate, plan and monitor scaling-up of rights- and gender-sensitive interventions to promote safe drinking water, adequate sanitation and good hygiene practices
Output number per LF		4	Output Score	B
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review (June 19)	Progress	Score	% Log frame Achievement
Water Policy Developed and Approved, National Sanitation and Hygiene Policy and Strategy developed and approved	Draft National Water Policy Strategic Implementation Plan; and Draft WASH Sector Investment Plan endorsed by NAC	Joint Sector Review Processes commenced. Plans to be produced as part of the JSR, National Sanitation and Hygiene Strategy approved / National Sanitation and Hygiene Draft Policy endorsed by NAC and awaiting approval by the Cabinet	B	Joint Sector Review Processes commenced. Plans to be produced as part of the JSR
Number of districts and provinces capacitated for enhanced WASH service delivery	42 districts and 8 provinces	42 districts and 8 provinces	A	42 districts / and 8 provinces
Number of District and Provincial WASH Governance Structures developing and overseeing for WASH plans	42 districts and 8 provinces	42 districts and 8 provinces	A	42 districts / and 8 provinces
Number of districts with an established Rural WASH Information System (RWIMS)	45	45	A	100%
Percentage of districts with an established Rural WASH Information System (RWIMS) updating data monthly	40%	36%	B	90%
Percentage of breakdowns attended to by VPM through RWIMS SNR in 12 RWP target districts	60%	23%	C	38%

Provide supporting narrative for the score
Although the programme has invested in strengthening the capacity of WASH institutions to effectively manage WASH interventions across programme provinces and districts, there was lack of progress on key indicators directly linked to programme sustainability, therefore scoring a B on this output. It has not met expectations in reaching out to additional districts with RWIMS and getting them to regularly update WASH data. There was also lack of good progress on water point breakdown repairs linked to RWIMS SMS Notification and Response System (SNR). During the review period only 17 out of 45 targeted districts are updating regularly and only 23% of breakdowns have been responded to through the against a target of 60%. However, Rural WASH Information Management System (RWIMS) continues to demonstrate its potential as a good WASH planning and management tool. A good example is when the RWIMS SMS Notification and Response System (SNR) was used in the rapid assessment of the impact of Cyclone Idai in Manicaland Province. RWIMS as a planning tool may however be less effective if (i) Local Authorities do not adequately finance the operation & maintenance of the system, including buying internet bundles. (ii) Handover and takeover process between enumerators is not properly managed. In Tsholotsho, it seemed there has not been a good handover process or orientation from one enumerator to the other. This could result in huge gaps in reporting/updating data.

Additional support provided by the programme to WASH government institutions in the past year include (i) helping the Ministry of Health and Child Care in developing a national ‘Demand Led Sanitation upscaling strategy’ that will see the adoption of the approach in other districts not reached by the programme to increase national sanitation coverage and (ii) strengthening the government’s capacity in groundwater development and monitoring. This is expected to manage groundwater abstraction given the depletion of ground water resources due to various factors, including climate change and variability.

The ability of subnational WASH structures to coordinate and monitor WASH service delivery remain constrained by inadequate government or local authority financing although some districts such as UMP have increased their budgets by over 100%, following a government directive to increase WASH funding. Despite an increase in WASH budget allocation in district council budgets, District Water and Sanitation Sub committees (DWSSCs) are failing to effectively deliver their sustainability plans. Examples include, (i) failure by some districts such as Tsholotsho to support communities to attain ODF certification. At the time of the annual review visit, the district had last certified a village ODF in 2017 with a success rate of 34%. (ii) limited resources to operate and maintain RWIMS in district districts such as Tsholotsho. RWIMS is supposed to help VPMs to quickly respond to water point breakdown and reduce the water point downtime.

Another negative indicator is the failure by some districts such as Tsholotsho to meet at least once a month to discuss WASH specific issues.

Provincial Water Supply and Sanitation Sub Committees (PWSSCs) are also limited in terms of monitoring and providing technical backstopping to districts.

Lessons identified this year, and recommendations for the year ahead linked to this output

- RWIMS need to be rolled out in Mashonaland East province.
- PWSSCs to (i) ensure District Sustainability plans are more Specific, Measurable, Achievable Relevant and Time specific and (ii) closely monitor and support the implementation of sustainability plans considering that the programme will be closing and focusing on sustainability in the remaining months to protect the gains already achieved.

Output Title	Improved preparedness and response to WASH related emergencies
Output number per LF		5	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review (June 19)	Progress	Score	% Log frame Achievement
Number of people affected by WASH-related emergencies accessing basic water supplies	84,000	178,375	A++	212%
Number of people affected by WASH-related emergencies reached hygiene promotion	275,000	626,700	A++	228%
Number of health facilities/CTCs supported with sanitation facilities in emergencies	3	3	A	100%

Provide supporting narrative for the score
Flexibility in this programme has enabled it to respond to two major emergencies that occurred in the past year. The targets for two of the three indicators were substantially exceeded while the other indicator reached a 100% mark, giving an overall output score of A+. Key success factors include the programmes ability to anticipate a cholera/typhoid outbreak and preposition hygiene kits in hotspots. This enabled a timely response, while resources to provide short-medium term water and sanitation were being mobilised.

Lessons identified this year, and recommendations for the year ahead linked to this output
Integrate disaster response plans in district WASH plans. This is in view of recurring emergencies in many of programme districts. Programme districts such as Buhera have in the past two years experienced cholera outbreaks and remain vulnerable. Climate/weather related disaster are more frequent than before and are destroying WASH infrastructure and interrupting WASH service delivery.

## THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)
Figure 5 below illustrates the programme Theory of Change (ToC). DFID funding is supporting the implementation of WASH activities and delivery of outputs that help to increase equitable and sustainable access to protected water supplies, sanitation facilities and adoption of safe hygiene practices by the poor and vulnerable people in rural Zimbabwe. Since the last annual review, the only change to this ToC is the increase in programme inputs by £ 4,500,000 to increase outputs and improve the programme ability to respond to WASH and climate related emergencies. The programme design and rationale remain relevant and there has not been any known evidence challenging it. However, the operating context in which original assumptions were made has changed in the past year. The deteriorating macro-economic environment and increased frequency and intensity of disasters such as cholera, droughts, tropical cyclones associated with heavy rains and strong winds are affecting implementation of selected activities and outputs, therefore undermining the programme chances of delivering a sustainable outcome. Some of the initial assumptions include (i) the government continues with the sector reform process and provide favourable environment for the Private Sector to assist with WASH service delivery (ii) increased government funding to support WASH interventions across all districts (ii) sustained Private Sector Partnership with sufficient turnover and margins to encourage local entrepreneurs and (iii) communities and local entrepreneurs are responsive to the Community Based operation and maintenance linked to Rural WASH Information System (RWIMS).

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Progress towards achieving the Outcome
The table below shows good progress towards achieving the outcome, with three of the five indicators surpassing the target at this stage. However, the sustainability of this outcome remains a big concern due to lack of enough government/local authority financial investment in WASH operation and maintenance systems, upscaling of demand led sanitation and disaster preparedness given the vulnerability of WASH infrastructure and services to climate related risks. To help address this, DFID and UNICEF will continue engage the government and senior level to increase funding on WASH and getting local authorities to do the same. The programme is also funding the wider WASH Joint Sector Review (JSR) that has already identified bottlenecks to the sector which the programme will also use to help the government in setting up WASH funding priorities and sector reforms needed to ensure sustainability.

Outcome Increased equitable and sustainable use of protected water supplies; use of improved sanitation; adoption of hygiene practices, among the rural population in 42 targeted districts		Programme Target	Progress June 2019	%ge Achievement
	Outcome Indicator 1:Number of additional people using improved protected water supplies in targeted rural districts, disaggregated by input (i.e. using a new water supply, or a repaired or renovated water supply)	4,215,960	4,311,946	102%

	Outcome Indicator 2: Water point ‘down time’ (restored within 2 days)	12%	13.70%	114%

	Outcome Indicator 3: Number of newly established ODF villages in targeted districts	3,250	2,954	91%

	Outcome Indicator 4:Number of additional people with functional handwashing facilities and soap / ash at their toilet in targeted rural district	771,787	710,570	92%

	Outcome Indicator 5: Number of people supported by the RWP with sustainable water supplies to cope the effects of climate change	4,215,960	4,311,946	102%

Progress towards achieving the Outputs
The programme is generally off track to deliver some expected outputs by October 2019. It lost a significant amount of implementation time due to the prevailing difficult macro-economic, environmental and political environment. More than eight months, which could have been used to design and deliver water supply infrastructure and demand led sanitation activities were lost to a prolonged 2018 general election process following the court challenge, intensified cholera outbreak response between September and December 2018, civil unrest in January 2019 and the March 2019 tropical cyclone Idai that required the involvement of key WASH programme staff to help out in the response. Technical assessments and delivery of twenty-four (24) piped water piped water schemes could not be delivered as planned as the cost of doing this work increased by more than 100%. Delivery at this rate did not give good value for money, resulting in this activity being put on hold, while other delivery options were being explored. This also took up some of the programme implementation time. Due to weakened local authorities’ revenue base and central
government’s failure to disburse to local authorities, DWSSCs in districts supported by this programme have not consistently been able to support communities on key activities promoting demand led sanitation.

UNICEF has worked out an alternative plan to deliver piped water schemes at good value for money, while districts are coming up with acceleration plans to complete the outstanding activities, especially on demand led sanitation. To help the programme achieve the intended outcome, at least a twelve month long no cost extension is required to compensate for the lost time and allow the programme to use some of the alternative delivery models and strengthen sustainability efforts.

Explain major changes to the logframe in the past year (1/2 page)
In July 2018, a month after the last annual review, an additional £4 million was approved for the programme. This was mainly to reach additional people in unserved areas, improve the sustainability of WASH infrastructure and enhance the programme capacity to respond to climate change and variability. As a result, the LogFrame was amended to reflect these changes. Below are key changes to the logframe:

1. Outcome indicator 1: Target for additional people using improved protected water supplies in targeted rural districts, increased to 4,215,960 up from 4,191,960.
2. Output indicator 1.1: Target for new protected water supplies established in rural communities and schools moved from 1447 to 1460. The programme initially did not plan to drill new boreholes, however due to increased number of unserved communities in Muzarabani district, the programme got an approval to drill new borehole to increase water district coverage.
3. Output indicator 1.3: Target for schools receiving new or improved sanitation facilities increased from 1500 to 1516 to improve schools’ sanitation coverage in targeted districts. This also resulted in changes to output indicators 2.1, 2.2 and 2.3.
4. Output indicator 1.4: Target for rehabilitated piped water schemes supported with low carbon technology (solar systems) were increased by 24, following the additional funding.
5. An additional indicator, Output indicator 4.6 : Percentage of breakdowns attended to by VPM through RWIMS SNR in 12 RWP target districts was added to Output 4 to track the performance of RWIMS in responding to breakdowns.
6. Output 5: ‘Improved preparedness and response to WASH related emergencies’ has been added to the Logframe in the past year to improve the programme flexibility to respond to recurring WASH related emergencies.

Describe any planned changes to the logframe as a result of this review (1/2 page)
As a result of this review the following changes are planned:
1. Adding an output indicator on ground water monitoring support the programme is giving to the Zimbabwe National Water Authority (ZINWA). This indicator will be added on the LogFrame under Output 4 on rural water supply and sanitation institutional strengthening.
2. Planned targets under Output 5 will be increased to reflect the additional £1000,000 recently approved to support the cyclone Idai WASH response in Manicaland province.
3. Revising targets for the next review period for some indicators that have surpassed the programme targets.
4. Increasing the weighting on output 3 and 4 in the remaining period or in the extension since a significant amount of effort will be on ensuring sustainability. New weighting will be discussed and agreed with partners.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
Ensuring value for money continues to be a key priority of the RWP in Zimbabwe. Based on a VfM recommendation made in the 2018 RWP DFID Annual Review, UNICEF is refining the RWP VfM framework and indicators to strengthen VfM monitoring including consolidating the impact of emerging dimensions such as disability mainstreaming. Selected key indicators are monitored against an internal set of benchmarks to assess VfM.

Zimbabwe has continued to experience unpredictable economic environment and currency regime. In response, the Government introduced new monetary policies during the period under review setting up interbank market exchange rates of bond/RTGS$ to USD as well as modifications on foreign currency accounts which impacted on capacity of suppliers to procure materials from offshore. To mitigate impacts of unpredictable economic landscape including currency reforms, UNICEF continued its routine monitoring of the external programme environment, including markets and the general economic and liquidity situation in the country. UNICEF also maintained regular monitoring of the quality of programme implementation, to ensure best VfM is realised by the RWP. Regular engagements were held with Government authorities including banking institutions on the available monetary measures to reduce the potential risk on the programme arising from the on-going liquidity crisis, currency reforms and increasing inflation in Zimbabwe.

Economy:
Procurement of goods and services constitute a sizable proportion of the RWP budget and centralised procurement process has contributed to the economy and efficiency dimensions of the programme by driving down costs through economies of scales. Economies of scale due to harmonised procurement system enabled savings of $ 3,180,108.71 to 2016 and an additional 2063 water points to be rehabilitated and hence reaching an additional 1,287,260 people. $469,908 has been realised due to the appreciation of the GBP premiums against the USD based on the funds transferred to date. However as shown in the table below, there has been an increase in the unit costs of borehole rehabilitation and piped water systems (PWSs) due to market price distortions. To ensure the programme still delivers at good value for money and paying the right price, the programme suspended the procurement of these services while exploring other options. The unit cost of cement and community mobilisation dropped by about US$25 because it did not include triggering (community mobilisation) which was done in the previous year. The table below shows the programme performed on key VfM economy indicators.

Indicator	Description	Performance
Unit cost per borehole rehabilitated	unit cost of each borehole rehabilitated PDIs and certification, including delivery of spares- - Including WPC and VPM and transportation to district
Unit cost per household latrine constructed for vulnerable households	Cost for the bag of cement and labour provided as subsidy to vulnerable households.
Unit cost per PWS repaired	Unit cost of rehabilitating piped water scheme including delivery of spares, water quality tests- - Including WPC.

Efficiency:
The RWP is being implemented in a challenging economic and market environment which impacted the efficiency of borehole rehabilitation. Although the rate of borehole rehabilitation decreased over the reporting period, borehole rehabilitation remains on track at 99.5% completion level, with a total of 14,988 out of a target of 15,063 completed. While costs might have marginally increased across interventions due volatile economic and currency situations, the programme managed to achieve outputs with reasonable costs. Percentage of new/repaired water sources with trained and functional gender parity WPCs was maintained at 100% in 2019; Percentage of rehabilitated piped water schemes supported with low carbon technology (solar systems) increased from 25% in the last annual review to 56% in 2019.Solar powered PWSs have a higher initial cost compared to B-Type Bush pump. However, PWS are more efficient because the cost is recovered over time due to low operation and maintenance costs. Despite reduced frequency and cost of replacing moving or worn out parts and use of solar energy, other efficiency indicators are reduced time and distance to fetch water and improved water quality. Percentage of WPCs established by project with access to trained and equipped Village Pump Mechanics (VPM’s) (1 VPM for every 5 WPC's) increased from 86% in 2016/18 to 100% in 2019.

There was a gap in programme implementation between November 2016 to June 2017 due to administrative processes in terms of planning for the extended programming into the 12 new districts. Contract amendments with respective NGO partners stretched from December 2016 to June 2017, only about a third of those partners had signed by quarter 1 2017. Inception processes in the additional 12 new Districts and procurement of supplies also impacted the pace of delivery of the programme output deliverables. Hence reporting of VFM milestones for 2016-17 was combined.’’

Effectiveness:
In terms of VfM, the programme continued to be effective in improving access to safe drinking water. It has reached a total of 4,311,946 people with safe water against the current logframe milestone of 4,191,960 people. Percentage of certified ODF villages has increased substantially to 91% of the RWP target of 3350 villages demonstrating improving VfM of the Community Led Total Sanitation (CLTS) approach and its potential impact on accelerating sanitation coverage. The effectiveness of the sanitation component is, however, possibly being impacted by the current economic situation being faced by households as well as capacity of DWWSC to continue engaging communities. However, the draft National Hygiene and Sanitation Strategy which encompasses demand led approach to sanitation serves as an indication of the acknowledgement of the potential effectiveness of the approach by the government. The waterpoint downtime baseline was 7 days and the median in 2016/18 remained at 7 days meaning that the RWP did not demonstrate impact in reducing water point downtime, although this could be a result of data on reduced walking distance not being collected and analysed. The indicator on percentage of people using improved water sources seem to be on a downward trend, but still performing above expectations across all years except 2016-18. This reflects the level of annual investment on water supply infrastructure over the year. Since the programme started up to October 2016, the programme has been spending approximately £5 million per year on infrastructure which has dropped to about £4 million between 2017- 2018/19.

Equity
In addition to the 3 Es above, the fourth ‘E’ Equity is also considered to ensure the RWP ‘maximise the impact of each £ spent to improve poor people’s lives’. Of the 1,518,686 number of additional people using improved protected water supplies 9% constitute people living with disabilities, while 3% of people helped to have improved sanitation are also disabled. About 62% of the Water Point Committee (WPC) members are female while 67% Community Health Clubs (CHCs) members and 53% of the Sanitation Action Group (SAGs) are female members who are playing critical roles in sanitation and hygiene promotion at community and household levels. While equity in distribution and access of WASH services is clearly demonstrated in the programme, equity in some financing models such as demand led sanitation may require more attention to reduce unintentional financial burden and exclusion of vulnerable and poor households. Local Authorities (LAs) financial contributions for WASH services have remained significantly low because (i) they have not received the government allocation and (ii) they are failing to collect expected revenue, which is a factor of prevailing macro-economic challenges. For instance, in 2018 UMP district budgeted $61,000 towards WASH but only managed to disburse $1,522 with the district budgeting $1,165,995 for 2019 with no actual disbursement in May. Also, while the central government is mandated to allocate 5% of the National Budget to Local Authorities, visited districts reported that they had not received their allocation from the government. However, having LAs reflect WASH services in their budget is an important process indicator which demonstrates government buy-in. Also, the programme should support communities to establish equitable financing models for interventions such as PWSs by ensuring that households or institutions (schools, business centres and health facilities) pay based on consumption.

Key cost drivers
Key cost drivers based on programme budgets and expenditure trends are:
- Rehabilitation of piped water schemes which has increased from a baseline of $35000 to $43,145 in 2016/18. PWS cost increases are also due to solarisation which ranges from around $8,000 to $15,000.
- Prices of cement has increased significantly impacting self-sponsored latrines. In some areas the price of cement was increased up to about 200% i.e. from $12.50 to $65 per bag with other retailers pricing in foreign currency making it difficult for communities to access.
- Percentage of admin cost to total budget has decreased from 4.4% in 2012 to 3.8% in 2016/18 excluding 7%/8%of programmable amount to HQ.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

Recognizing that the RWP is being implemented in an economic environment that has remained largely unpredictable, there is good evidence that the programme encompass the 4Es of DFID VfM framework including consolidation of equity in access and utilization of WASH services such as disability and leaving no one behind. While costs of interventions have generally increased due to changes in monetary policies and currency reforms there is evidence that the programme has sought to rationalize costs without compromising quality so that services are maintained at an affordable cost in the long run. For interventions that have evolved into key cost drivers such as the PWSs, UNICEF has devised innovative approaches such as partnering with the academic institutions to achieve reasonable service costs while maintaining quality. With diligent targeting of interventions such as PWSs, the RWP has benefited other social sectors such as health and education. For instance, Masvosva PWS in Makoni district is benefitting 1687 members from the community, school and health centre. Also, the RWP has contributed to decrease of water borne diseases as well as reducing the burden of work for women allowing them to invest time in other productive initiatives.

Given the high-risk operating context, characterized by recurring disease outbreaks, increased frequency and intensity to climate/weather related disasters, a programme with such flexibility should continue.

Key VfM recommendations
- Need to ensure that data for VFM analysis is collected and documented on a routine basis.
- IPs to work together with local authorities to support communities to develop equitable financing models for interventions such as PWSs to ensure equity in financing is commensurate with consumption levels
- Ensure local authorities allocate and disburse funds to support WASH services to ensure continuity and sustainability of accrued RWASH gains.
- IPs to exercise due diligence in procurement of spares for the RWP to avoid risk of procuring sub- standard materials that will tear out quickly increasing financial burden to households.
- The RWP to consider documenting the running costs of RWIMS as a VfM indicator.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
The overall risk rating for the project is major and is within the DFID Zimbabwe risk appetite. The risk register details 12 active risks and associated mitigating strategies and is updated on a six-monthly basis as part of the formal reporting to DFID. In addition, DFID and UNICEF review key or emerging risks which are presented in a more detailed form by output during monthly partnership meetings. UNICEF discuss risks with downstream partners during quarterly meetings. DFID has been discussing with UNICEF the need to ensure that some of the key risks are discussed with the Government to ensure ownership of mitigation actions. The recently held workshop on the WASH Bottleneck Analysis in readiness for the Joint Sector Review is expected to highlight challenges with the sector and ensure ownership of challenges as the programme ends. Within DFID, key risks are reviewed at quarterly meetings scheduled by the DFID Zimbabwe, Commercial, Accountability, Results and Evidence team. While there have not been any major changes to the risk register as set out in the risk matrix, four risks stood out in 2018/19:

Currency Fluctuations
Prices escalated beyond the provisions of the budget, particularly for high value interventions such as the PWSs for which costs escalated to over 134% of the budgeted amounts. Works on the PWS had to be delayed, while the UNICEF team explored more cost-effective ways to deliver this output. This involves UNICEF working with academic institutions to conduct feasibility studies for 24 PWS. At downstream level, prices shoot up for locally procured commodities like cement for construction of latrines, thereby affecting uptake of the demand led sanitation and the timely attainment of ODF as the capacity of households to construct their own latrines is constrained in this environment of economic hardships. However, for the targeted vulnerable households, UNICEF’s downstream partners have decided for payments to be made into FCA accounts thus enabling costs to remain within the budget.

Outbreak of Waterborne diseases
In the reporting year, the country experienced a continued cholera and typhoid epidemic. The repeated cholera and typhoid emergencies resulted in a significant amount of programming time diversion for UNICEF, key government and NGO partners to respond to these emergencies.

Tropical Cyclone Idai
Post the cholera response (September 2018-February 2019), the programme also provided immediate WASH response to Cyclone Idai from March 2018 to date, although the level of staff engagement has since dropped in May 2019. In response to the devastating impact on WASH services caused by the Cyclone Idai in some parts of Zimbabwe, DFID supported UNICEF with an additional funding of GBP 500.014 to implement critical life-saving WASH interventions such ensuring access to water and sanitation for the affected populations.

Loss of Government capacity
The economic situation has constrained the capacity of government to carry out critical work to support the programme. For example, there is an absence of appropriate levels of engineers and the Rural District Councils and a shortage of Environmental Health Technicians who are critical to health and sanitation whose allocation should be one per ward but currently is based on for 3 or 4 wards. UNICEF continues to maintain close links with government structure and donors to ensure a more effective coordination and networking of sector players. These risks have culminated in the RWP losing effective time and possibly the ability by communities to implement some of the expected deliverables

Social and Environmental safeguards
Given that the programme works closely with communities and has activities such borehole drilling and PWS rehabilitation, that could harm the environment, the programme continued to track risks on both the community and the environment and ensure there are appropriate mitigation measures. In the past year there were no risks reported. To ensure environmental sustainability, DFID provided additional resources to support ground water monitoring to improve management of water resources given the impact of climate change on ground water resources and promote the use of solar energy to power PWSs instead of diesel.

Update on partnership principles (1/2 page)
The RWP project is in line with the DFID policy that no UK funds should be managed by or be under the direct control of Government of Zimbabwe (GoZ) using its own financial systems and procedures.
Where funds have been channelled through the government systems, this has been for activities, and within the agreed cost percentages pre-approved by UK Ministers. In accordance with the Guidance Note, it is therefore not appropriate to undertake an assessment of the Partnership Principles as part of the monitoring of this project. The Zimbabwe country-level Partnership Principle assessment is regularly updated, and the outcomes are fed into ongoing management of project activities and risks.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)
There has been good financial management for the RWP. The total approved DFID budget for the project is £50,500,014.23 and this has been fully disbursed to UNICEF. The unspent balance held by UNICEF, of approximately £4.8m reflects the challenges of high margins of price increases which do not present good value for money resulting in UNICEF delaying implementing the affected high value outputs while more cost-effective alternatives are being sought. UNICEF is expected to send a proposal to DFID on delivery mechanisms and timeliness by the end of June.

In the meantime, an addendum for a further £500,000 for Cyclone Idai has been approved by DFID. As part of ensuring no payment is made in advance of need, UNICEF will be requested to utilise an equivalent amount of the unspent balance and to only request further payment after utilising the funds already disbursed.

The annual certified financial accounts for the year ended 31 December 2018 have been received and are in good order. These have been reviewed by the Programme Manager and Finance Manager and are deemed to compliant the financial reporting standards.

Performance of partnership(s)
The project is being delivered through an MoU between DFID Zimbabwe and UNICEF which has a cooperating agreement with the Zimbabwe Government called the Zimbabwe United Nationals Development Assistance Framework, and they sign a cooperating agreement with Government on a 5-yearly basis. UNICEF maintains close links with government structures to ensure effective coordination and networking with stakeholders in the sector and other related sectors, e.g. the Health sector. NGOs sign MoUs with respective Rural District Councils to enable them to implement the project in these districts.

Part of the requirements set out in the MoU with UNICEF is the need for adequate branding. This was flagged in the 2018 review as an area requiring strengthening. Monitoring visits show an improvement in addressing this, for example villages that obtained ODF and PWS sites have sign posts reflecting the partnership between the district, UNICEF and DFID using logos, including for UKAid. Presentations by community beneficiaries from the districts visited are acknowledging the partnership and have more awareness of DFID support.

Asset monitoring and control
Vehicles and motorbikes provided for the projects are seen in use during field monitoring visits. UNICEF has installed tracking devices to monitor vehicle movements. The PAC agreed that these reports should be shared on request and if there is any misuse of the vehicles, the issue will be taken up with the concerned district.

Date of last narrative financial report(s)	31/05/2019
Date of last certified financial statement (s)	24/04/2019

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)
Monitoring (1/2 page)
Field visits, quarterly review meetings and progress report analysis are the main activities being used to monitor programme performance including assessing the operating context. The deteriorating operating context demanded that DFID increased its level of stakeholder engagement and frequency of progress meetings with UNICEF to ensure the programme has appropriate strategies to mitigate against emerging risks.

Both the Programme Advisory Committee (PAC) and Programme Management Team (PMT) held quarterly review meetings as scheduled. In addition to progress review, the PAC meetings continued to look at strategic and policy issues affecting the programme and the WASH sector. In the past year, DFID continued to engage the government on issues that include (i) approval of the National Sanitation and Hygiene policy (ii) WASH sector financing and accountability and the (iii) the ongoing Joint Sector Review. The PMT also met regularly to discuss operational issues that include quality of construction in some districts not being up to standard and strategies to improve ODF sustainability. The PMT also in the past year facilitated a ‘look and learn’ field visit as part of the end of year review meeting held in Mutare between 19-21 November 2018. It targeted the 12 new district stakeholders to learn best practices on ODF and self-sponsored latrines, borehole rehabilitation and hygiene promotion and WASH in schools.

Data used for this annual review was collected through field visits to three districts, key stakeholder consultations and review of key documents including UNICEF progress reports. Tsholotsho is one of the three districts visited during this review. It is a phase 1 district selected to assess the capacity of the DWSSC to at least sustain the gains achieved during programme implementation and manging the district WASH activities. The other two districts visited, UMP and Makoni are new districts, but with different characteristics. They helped in drawing a comparative analysis on how socio-economic and political context can influence programme performance. RWIMS is also being used across the programme to monitor functionality rate of water points. Besides, DFID and UNICEF, some DWSSC officers have active RWIMS accounts and use the system in their routine planning.

Evidence (1/2 page)
DFID has in the past year insisted on evidence-based reporting and this has improved the quality of data collection and reporting. Most results reported by UNICEF in the past year are supported by source documents that include a list of water points with geo coordinates, beneficiary data disaggregated by sex and disability. Stories of change, that include how the programme has reached out to people with disability have also been provided and are part of UNICEF’s six-month reports received in the past year.

While there is an improvement at programme level to generate and use evidence, other districts need to be supported. Unlike Makoni district, UMP and Tsholotsho districts did not provide adequate evidence backing reported outcomes such as reduced water points down time or walking distance to fetch water. To help improve this, UNICEF has engaged a data specialist working on standardising data collection tools, consolidating evidence in different programme areas such as the effectiveness of driving demand-led sanitation at community levels, framework for the sustainable scale-up of solar powered PWSs in the Zimbabwe and National Formative Study on Menstrual Hygiene Management (MHM) . This is expected to help the programme generate credible evidence that could be used for future WASH interventions and support the ongoing Joint Sector Review (JSR).The programme has in the past year provided funding through UNICEF for a WASH Sector Joint Sector Review. The JSR has just completed a detailed Bottleneck Analysis that is expected help in identifying sector challenges and how they can be addressed. The success of the JSR is expected to use a lot of evidence within and outside the programme to provide effective solutions to WASH sector constraints.

Learning (1/2 page)
This programme has over the years used learning as a strategy to improve delivery. Current strategies to deliver phase two of this programme is based on lessons learnt in phase one. These include use of evidence through baselines, technical assessment and reviews in choice of interventions or upscaling of tried and tested approaches. The decision to provide additional funding towards PWS in July 2018 was based on the programme ability to learn technologies that provide sustainable results. The programme team has also demonstrated ability to use experience learnt elsewhere to help decision making. The decision to engage an independent technical quality assurer in delivering PWS, is based on programme experience from other infrastructure works. Other main learning points gained over the past 12 months are:

WASH programmes delivered in vulnerable contexts like Zimbabwe should build in flexibility at design stage to respond to inevitable emergencies. This programme has in the past year been used to provide immediate/lifesaving WASH support in two emergencies, namely the cholera outbreak and Cyclone Idai.

Government or local authority financing is an essential sustainability factor that will enable sustainable WASH service delivery. Tsholotsho and UMP, two of the districts visited during the annual review are unable to fully implement their sustainability strategies due to lack of funding. As a result, they are unable to frequently monitor WASH activities and provide communities with much needed technical support. There are already signs of slippage because of this. In Tsholotsho support for demand led sanitation, helping communities to attain ODF status stopped in 2017. There is a good chance that districts originally declared ODF, might have lost this status due to lack of monitoring and technical support.

In the remaining programme period and perhaps the following year, provided it is granted a no cost extension, potential learning areas include:

- How the government uses the findings of the JSR to improve the WASH sector in Zimbabwe
- Effectiveness of the ODF protocol/ anti slippage strategy.
- Potential of future partnership with Universities/institutions of higher learning. This follows the engagement of University of Zimbabwe and the National University of Science and Technology in doing technical assessments and designing of the remaining 24 PWS. The programme is keen to learn if this provides better outcomes and good value for money compared to the private sector.
- How to ensure sustainability in a difficult macro-economic and political environment.

Progress on recommendations from previous reviews (1/2 page)
The table below provides a summary on progress made in addressing recommendations from the previous annual review.

	Recommendation	Action	Status
1	Sustainability of RWP
	Working with Government of Zimbabwe (GoZ) and communities, UNICEF to develop and implement a detailed and costed Transition Plan that shows (i) how outstanding outputs will be delivered in the remaining programme period and (ii) how the outcome will be sustained beyond the programme implementation period	1.1 Develop transition plan by July 2018	Completed
		1.2 Re-orientation of stakeholders (across the supply chain) on PPP model by Sept, 2018	Completed
		1.3 Develop cost guide for user contributions and savings towards preventative maintenance by August 2019	Work in progress.
		1.4 Evidence based budgeting -Advocate for allocation and ring fencing of funds for WASH activities (RDCs, National Government)	Ongoing, UNICEF advocated for increased investment in WASH during the 2019 budget consultative processes; PMT strongly advocate for increased and ring-fenced budget for WASH during monitoring visits to the RDCs; WASH Sector Budget Advocacy Brief Note that gives key has been developed
		1.5 Engage government (MoHCC) on approval of sanitation and hygiene policy	Ongoing
2	Quality
	UNICEF to enhance quality assurance in the full cycle (planning, design, implementation and operation) of water supply and sanitation works of RWP. A quality assurance plan may be developed to guide this	2.1 Develop quality assurance plan (to include sustainability checks) by July 2018	ODF sustainability check tool finalized. Data collection using the adopted sustainability check tool is in progress starting this month.
		2.2 Develop/Collate/Review tools for technical assessment of bush pump boreholes and wells, by August 2018	Done
		2.3 Standardize and harmonize borehole repairs completion certificates and training certificates by August, 2018	Done
		2.4 Review PWS protocol, by October 2019	Still pending. Task incorporated on contract for designing and construction supervision for PWS.
		2.5 SOPs for PWS handover by September 2018	Work in progress.
		2.6 Develop and roll out a water quality testing guideline/protocol by October, 2019	ongoing
		2.7 Upscaling exchange visits between SAGs/ WWSSCs/Districts	Ongoing
3	Evidence
	In addition to human interest stories shared in progress reports, the programme should develop case studies and evidence-based papers on experiences in using interesting approaches that are under debate in the global WASH sector including demand led sanitation, community-based PPPs and disability mainstreaming.	3.1 Identify case studies/research papers to be done and methodology - cutting across demand led sanitation, community-based PPPs and disability mainstreaming by October 2019	*Ongoing, through RWP partners in producing documentary and short clip videos and technical brief notes/reports.
		3.2 Develop TOR & engage a consultant to help with guidance on data collection and analysis by October 2019	Ongoing. Data analyst consultant engaged. Data validation reports being produced and shared with partners.
		3.3 Secondary Analysis of data gathered through baseline and endline surveys, October 2019
		3.4. Investigate the level of subsidy for sanitation on the uBVIP and implications on the vulnerable, by October 2019	Ongoing, through PMT.
4	Risk
	UNICEF to improve communication with DFID on emerging risks and other factors likely to significantly affect programme delivery and results.	Update risk matrix (financial, economic, political, environmental and social risks) - Quarterly or when need arises	Ongoing as agreed. So far updates given during monthly updates meetings and during quarterly PAC meetings.
5	‘Leave no one behind’
	UNICEF need to use the outstanding work in the 12 phase two districts to strengthen disability mainstreaming and disability data disaggregation. The review team recommends the use of the six (6) Washington Group Questions[7] (WGQ) in beneficiary data collection	Orientation on assessing disability using the WGQ by July, 2018	Done.
		Use of the 6 Washington Group of Questions on beneficiary data collection, by July, 2018	Done, however adoption of the new reporting tools by most Districts remains a challenge.
6	Value for Money
	DFID and UNICEF to revise the programme’s VfM framework and indicators as necessary to strengthen VfM monitoring including underlying assumptions and impact of emerging issues such as disability mainstreaming	Review the VfM framework …. Disability factor and unit cost for rehabilitation and repairs, by October 2019	Collection of data to inform VfM framework ongoing.
[7] Questions on difficulties in seeing, hearing, walking, remembering, self-care (inc washing) and communicating