Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Ghana Oil and Gas for Inclusive Growth
Programme Value: £17,250,000.00		Review Date: 12 March 2015
Programme Code: 204330	Start Date:12/03/2014	End Date:31/03/2019

Summary of Programme Performance
Year	March 2015
Programme Score	B
Risk Rating	Medium

Summary of progress and lessons learnt since last review

Due to procurement delays and complications the contract with the service provider was only signed in November 2014, with work starting in December 2014. As such, the review covers only around 2-3 months of work by the Service Provider. The logframe was designed with an expectation that the service provider would have been in place for 5-6 months. The accountable grants with ACEP and NRGI are ahead of what was initially expected.

The contextual background has been mixed. On the one hand there have been incremental improvements in a number of technical areas and capacity of staff. On the other hand, there are indications of systemic weaknesses e.g. in terms of processes related to contract negotiations.

Against this background the key lessons and progress include:
1. Operational lesson 1: Allow sufficient time for procurement – align the logframe milestones accordingly.
2. Operational lesson 2: Maintain regular contact with partner agencies when awaiting procurement – and, importantly, manage expectations.
3. Engagement: The combination of technical/policy in-house capacity, close and regular dialogue with partners – especially the civil society partners – and relevant parts of the UK government has helped maintain strong, high-level policy engagement.
4. Programme progress: The service provider has had a good start and is on schedule (according to the ambitious milestones agreed during contracting).
5. Programme progress: The 2 civil society partners supported directly by DFID have made significant policy and technical strides.

Summary of recommendations for the next year

1. Coordination and collaboration: The inception phase and the parallel start-up of the Western Region Coastal Foundation as well as the design of the anti-corruption and taxation programmes clearly demonstrate the need for close coordination, collaboration and lesson sharing.
2. Take point of departure in each partner’s plans and issues, allow time to build trust and understand the context (technical and political).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	4269520
DevTracker Link to Log frame:	4269501

Outline of the programme

After more than 20 years of exploration activity, commercial quantities of oil and gas were discovered off the coast of Ghana in 2007. Production from the Jubilee oil fields began four years later and presently stands at 100,000 barrels per day (bpd) and will reach 190,000 bpd by 2016. In comparison, relative to the size of the economy, that’s roughly the same proportions as in Nigeria. If well-spent, oil revenue can accelerate development in Ghana. Yet, there are risks that oil and gas revenues will promote a culture of short-term political decision-making that could hinder the opportunities for long-term growth and benefits for the people of Ghana.
The Programme: Ministers approved the Ghana Oil and Gas for Inclusive Growth (GOGIG) Programme business case in December 2013. The intervention helps in the delivering of the G7-Ghana partnership on Extractives launched by President Mahama and the Prime Minister in June 2013. The intervention is based on the Natural Resource Charter. Effective use of oil and gas revenue, and careful management of the attendant risks, will be crucial to ensure Ghana’s Oil resource helps to drive forward Ghana’s growth, lift its population out of poverty and sustain the plural democratic political settlement.
Three key outputs, pivotal for maximising benefits of oil and gas for Ghana, form the basis for the programme design, as follows:

- Strengthening oversight and enhancing regulation of the sector. Clear policy, robust legislation and an effective and accountable regulatory body are necessary prerequisites to regulate private sector operations, and ensure the best possible development progress is achieved from the use of natural resources.
- Improving revenue capture is critical to maximising the direct benefits from the oil and gas sector. The Government’s ability to do so will depend on the clarity of the fiscal regime and the technical capacity of authorities to collect royalty payments and tax revenues.
- Improving revenue management is important to ensure transparency and avoid adverse macroeconomic consequences associated with natural resources windfall gains, such as drawing too heavily on revenues in times of high oil prices to meet budget deficits, and the so-called Dutch Disease (large inflows of revenue associated with the resources extraction leads to an appreciation of the real exchange).
This programme cut across core element of DFID Ghana’s Governance and Economic development work, two of the three pillars of the Operational Plan.

A key element of the approach is to provide high-level technical and strategic advice. The programme will succeed or fail by the level and quality of that strategic and technical advice. Such advice is costly, but deemed crucial in this case. The programme includes a long-term adviser to the Minister of Energy in Ghana.

The programme is implemented by a Service Provider, Oxford Policy Management, complemented by two accountable grants – to Africa Centre for Energy Policy (ACEP) and the Natrural Resources Governance Institute (NRGI) - managed directly by DFID. The inception phase started in December 2014.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

There has been progress towards outcomes, broadly in line with milestones. Technically, the revenue milestone has been exceeded (USD700 mill was collected by September 2014). The regulatory environment remains stable with risks and opportunities around the Petroluem Exploration and Production Bill and the possible Petroleum Revenue Management Act revisions. A degree of attribution can be claimed by the project, through the accountable grant, where ACEP has been strongly engaged on the Petroluem Exploration and Production bill and NRGI on the revenue modelling.

The revenue milestone will be harder to reach in 2015 and potentially onwards if the crude oil price remains low.

Overall output score and description
Score: B. This score reflects delays in procurement rather than performance gaps. The main project components are on track and in some cases performing significantly above expectations (e.g output 1.3).

Key lessons
See page one.

Key actions
The inception review will have to refine the methodology for estimating attribution to outcome milestone 1 on additional revenue collection.

Has the logframe been updated since the last review?

NO. This is the first review of the programme. The inception phase includes tasks on refining the logframe.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Sector oversight enhanced and effective regulation
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	60%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones for year 1	Progress
Fully independent and resourced Petroleum Commission (PC) effectively carrying out statutory duties	Draft PC Corporate plan sets direction; Organisational Structure and procedures agreed; financing plan for PC discussed with Ministry of Energy (MoEn) and industry.	Score A/B. Draft PC corporate plan completed.GOGIG support now focused on prioritisation and implementation.
Sector policy and strategy for development of sector with stronger leadership, inclusive processes and implementation plan	Consultations for energy sector policy for oil and gas commenced, including roles and responsibilities. Timetables and targets for implementation defined.	B. Preliminary work commenced (supported by MoE adviser)
Strengthened capacity of Parliament, Civil Society Organisations (CSOs), media, so they can monitor developments, ensure public accountability and increase exposure of mismanagement or corruption.	Number of training and capacity building sessions for Parliamentary Secretariat and researchers and journalists on oil and gas. Number of investigative and analytical studies that strengthen accountability. Industry and professional bodies are encouraged to organise and become active lobbyists for improved regulation	A+. Substantial progress and achievements through the ACEP and NRGI partnerships, e.g. on fiscal implications of oil price fluctuations, advocacy on Exploration and Production bill and establishment of a contracts database. Finally, there has been constructive engagement with media.

Key Points
Performance: the milestones were based on an assumption that the Service Provider would be in place by September 2014 and work for 6 months. Indicator 1.1 is on track although further refinement of implementation and financing is required. Indicator 1.2 is moderately behind schedule, although important progress has been made. Indicator 1.3 has performed well, both in terms of the specific definition of the indicator (capacity building, analysis) and above all in terms of effective ways of engagement with authorities, the media and other stakeholders.

Risks: the risk rating remains medium. Justification: Technical capacity is improving and public pressure and engagement has increased, which reduces risks. At the same time political pressure and rent-seeking remain a risk; potentially with a worsening trend.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
- Refine milestones and agree by end of inception phase.
- Balance trust-building and technical support to Petroleum Commission.
- Coordinate engagement with PC closely with other DFID programmes.

Output Title	Ensuring revenue capture
Output number per LF		2	Output Score	C
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Greater tax compliance (number of audits resulting in additional revenue collected)	Audit assessments plans prepared and related training needs identified. Training started	B. Some process-level progress made, but with limited GOGIG involvement until January 2015. Good engagement on training needs.
Ghana Revenue Authority (GRA) Petroleum Unit more effectively engaging with industry	Tax policy amendments identified by GRA; tax policy and administrative capacity reviewed	C. As above (but further away from target in terms of policy amendments).

Key Points
Performance: the milestones were based on an assumption that the Service Provider would be in place by September 2014 and work for 6 months. Both output indicators have seen progress. The partner institution, GRA has started work and OPM support on training and capacity development has started well.

Risks: the risk rating remains low. Justification: Technical capacity is improving and with fiscal pressures, the policy and political environment will be conduicive.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations
- Refine milestones and agree by end of inception phase.
- Coordinate support closely with upcoming DFID tax programme (approved, but not yet started)

Output Title	Improving Revenue Management
Output number per LF		3	Output Score	C
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Greater fiscal oversight of oil and gas sector by Minsitry of Finance (MoF)	Minsitry of Finance (MoF) drafts and agrees monitoring processes with all key stakeholders involved (MoF/Ministry of Energy/GRA/Bank of Ghana)	C. Process level progress achieved (limited GOGIG attribution). Further refinement required (which is part of on-going GOGIG work).
Revenue modelling capacity of Real Sector Division of MoF enhanced	Fiscal Model refined and capacity building to use it initiated	B. MoF has continued work on their model. NRGI have developed a parallel model. Further refinement required.

Key Points
Performance: the milestones were based on an assumption that the Service Provider would be in place by September 2014 and work for 6 months. Both output indicators have seen progress. The partner institution, MoFEP has started work and OPM support on training and capacity development has started well.

Risks: the risk rating remains Medium. Justification: Technical capacity is improving and with fiscal pressures, the policy and political environment will be conduicive.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations
- Refine milestones and agree by end of inception phase.
- Coordinate support closely with upcoming DFID tax programme (approved, but not yet started)

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The programme is output-based with milestones driving payments to the suppliers.

The principal cost drivers are:
1. Consultancy fee rates for technical experts (a mix of Ghanaian and international consultants)
2. Direct expenses relating to the provision of consultants (e.g. travel, accommodation, visas, etc.)
3. Indirect overhead costs of administering the project through a management team. These will include amounts within each fee to contribute to the costs of being in business, such as corporate operations, managed costs, recruitment, back office administration, headquarters, Ghanaian office, etc.

The key cost drivers have not changed. The partners and service provider have been incentivised to maintain focus on cost drivers.

In the period under review, the key cost drivers were office set-up costs and and consultancy fees.

VfM performance compared to the original VfM proposition in the business case

The VFM measures expected to be measured over the lifetime of the project set out in the Business Case have not changed.

Assessment of whether the programme continues to represent value for money
It is too early to assess performance on VFM measures. A key milestone (month 6) during the inception phase is for the service provider to develop a framework/strategy for mainstreaming VFM.

Quality of financial management
The programme with the service provider is output-based with milestones driving payments to the suppliers. The report for the first milestones has been received and the supplier has fully delivered on the milestone.

 It is too early to fully assess the quality of financial management at this stage.

There have been some weaknesses, such as spending savings made without proper authorisation, but these has been addressd with the partner and systems put in place to ensure they are not repeated.

Quality of financial management at the Government level will be fully assessed when the Non Budget Financial Aid begins during implementation

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Low/Medium/High
The overall risk rating for the programme remains Medium.

Overview of programme risk
The key risks identified in the Business Case are set out in Table 1 below. These risks remain unchanged. The service provider will revise the risk register and develop a risk management strategy as a key deliverable of the inception phase.

At the operational level, procurement and management of (unforeseeable) complicated contracting issues caused delays. This has delayed the programme and achievements by 3-4 months. These risks are now overcome and will not cause further delays. There is, however, a lesson; build in appropriate, conservative timeframes into procurement processes, especially for complex programmes.

Table 1: Risk Matrix

Threat or risk Likelihood Likely impact Mitigation Measures Assessment/Status / Capture of state regulatory bodies by corrupt interests Low Medium Manage and encourage CSOs to remain vigilant. Support international accountability The risk has not been realised to date but remains relevant. The support to the CSOs has started and they are engaging with these regulatory bodies and making inputs to key policy issues. They are also bringing out issues of public interest thereby keeping the issues open and on media agenda. / Insuffcient commitment by Office of President Medium Medium Develop high-level engagement strategy. Use direct, G8, media and CSO avenues. The risk has not been realised to date but remains relevant. / Manipulation of licenses and agreements Low Medium Improved systems in MoE and PC. Support CSO analysis and media. The risk has not been realised to date but remains relevant.The supplier has started a functional and needs assessment of PC and is developing activites to improve their systems. A technical adviser has also been procured for the Minister of Petroleum to advise the Minister on petroleum regulation and management / Political interference in management or operations of Petroleum Commission Medium Medium Encourage heightened influencing and monitoring by CSOs The risk has not been realised to date but remains relevant. / Ministry of Energy and GNPC resist transfer of responsibilities to Petroleum Commission Medium High Technical support to MoE and PC. Key focus area of advisory unit and CSOs. The risk has not been realised to date but remains relevant. / Funding of Petroleum Commission operations not sufficient Medium Medium Technical support to PC (budget preparation), CSO and media engagement. Budget support and G8 engagement. The risk has not been realised to date but remains relevant. Africa Centre for Energy Policy (ACEP), one of the CSOs being supported, has conducted a VFM audit of the use of funds from the oil revenue till date and is constantly monitoring funding to PC and their operations to ensure they are independent

Outstanding actions from risk assessment
Not applicable.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme experienced significant delays in the tendering and contract process for the Service Provider. This resulted in the Service Provider starting work 11 months after the Business Case was approved. The Civil Society component of the programme however started on time. The programme has progressed smoothly since the Service Provider commenced work and the deliverables are on course to be achieved in the inception phase.

Performance of partnership (s)

The two Civil Society Organisations (CSOs) have performed well so far.

They have exhibited a great knowledge of Ghana’s oil and gas sector. This is evident in the relevance of project activities carried out so far. The CSOs have abided by the timelines agreed for submitting quarterly reports and their forecasts have been timely. They have been very responsive to other requests and deadlines. Their engagement with DFID has been good.

Asset monitoring and control

The service provider has established an office in Accra and is in the process of acquiring assets. An asset inventory template has been sent to the supplier to enable them record all assets acquired under the programme from the start. The service provider has committed to ensuring that assets acquired are clearly labelled and identified with the UKAID logo, are well maintained and used solely for the purpose of the programme. The programme team carried out a physical verification of these assets on the 16th of March 2015 and all the asset are available and being used for the purpose of which they were bought.. As part of our on-going monitoring and control, the supplier will be submitting an updated asset inventory as part of the quarterly report.

The two Civil Society Organisations have also been given the asset inventory template to record all assets purchased for the programme. They have also committed to ensuring that the assets are maintained and used solely for the purpose of the programme. A physical verification of the assets have been agreed to be conducted bi-annually. One such exercise has been conducted on one partner. The next one is due April 2015 for both partners.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The last in-depth assessment of the Partnership Principles (PPs) in June 2014 concluded that the Government had upheld all four PPs over the 2013/14 period. The most relevant PP to the programme is on the commitment to strengthening financial management, which was upheld albeit with concerns, in particular around the management of the macro-economy, and the slowdown of Public Financial Management (PFM) reform. A range of PFM reforms have been initiated in Ghana. These include the introduction of the Ghana Integrated Financial Management Information System (GIFMIS) and improvements in budget formulation. DFID remains closely engaged in these, both at programme and policy level.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Due to the the multiple components of the programme, which may not all be reflected in a logframe, the Business Case envisioned a broader monitoring and evaluation framework will be developed and monitored by DFID. A key milestone during the inception phase is for the OPM to develop a framework for monitoring the programme. The process for this has already begun.

Monitoring progress throughout the review period

DFID holds weekly meetings with the GOGIG programme team to closely monitor inception activities and to ensure appropriate linkages with related programmes. In addition there are meetings with advisers and consultants engaging on the programme during visits. One monthly progress update and the first milstone report have been submitted by the supplier since commencement of the programme.

DFID also holds monthly meetings with the CSOs partners to closely monitor and provide technical support to them. We have had one expenditure verification exercise with ACEP. This revealed some weakness in their internal control systems which has been addressed. ACEP and Natural Rsource Governance Institute ( NRGI) have also submitted three and one quarterly progress and financial reports respectively. An annual progress report is expected from them at the end of March 2015.

This Annual Review was undertaken by the DFID Ghana programme and advisory team (lead adviser, deputy programme manager and project offier) based on consultations and desk review of documents submitted by the GOGIG supplier and the CSOs. No external consultants or reviewers were used. It is anticipated that in subsequent years the review will be undertaken by external consultants and personnel from the DFID advisory cadres, given the innovative nature of the programme.