Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support for the European Bank for Reconstruction and Development (EBRD) to provide technical assistance to Middle East and North Africa reform countries
Programme Value: £5,000,000		Review Date:March 2015
Programme Code: 203056	Start Date:March 2012	End Date:December 2015

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	B	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

The Southern and Eastern Mediterranean (SEMED) Multi Donor Account (MDA) Program of the European Bank for Reconstruction and Development (EBRD) progressed well during 2014. DFID remains the largest of multiple bilateral contributors to this successful open-ended fund. Some of the achievements of the program are captured in the program’s performance indicators, but many of the beneficial impacts will emerge after some time, and DFID’s contribution to stimulating EBRD’s investment operations in key infrastructure and environmental sectors, in particular, should not be forgotten.

A major program highlight during 2014 was the agreement and launch of an MDA Results Framework to monitor MDA activities. A revised DFID Logframe was extracted from this, and is now being used. EBRD is reporting under four components, but guided by DFID’s priorities, DFID is focussing on three, which all made good progress during the year.
- the “Strengthened SME Sector” component launched 46 new small business advisory projects for a program total of 95, of which 17 percent were majority woman-owned enterprises (MWOEs).
- MDA projects in the “Improved access to public services” area leveraged over €375 million in EBRD investments giving a program total of roughly €600 million thereby achieving the overall program outcome target.
- Good progress was also made on the “Policy dialogue and institution building” component.

Thanks to the MDA’s foundation work to build EBRD’s knowledge of the region, and support infrastructure investment preparation projects EBRD is now firmly established in the region with investments of some €1.5bn as of the end of 2014, of which €600mn have been facilitated by the MDA program. These investments have focussed on green energy, water resources and transport, in particular, areas supporting inclusiveness and efficient economic growth and wealth creation.

Summary of recommendations for the next year
During 2015, the final year of the program for DFID’s involvement, the focus will be on continuing MSME and Infrastructure preparation and implementation activities, and on capturing project impacts.
- For MSMEs this means measuring the sales and employment impact of advisory activities as projects mature; and reviewing the progress on reducing the subsidy element of the support provided.
- For infrastructure and public services investments supported by MDA activities this means investigating further how successfully EBRD has leveraged non-EBRD investment through PPPs and co-financing. We will also gather more examples of how infrastructure and public service activities have promoted greater social inclusion, climate and environment, and contributed to conflict mitigation (e.g. rural electrification, regional water and wastewater programs).
- DFID staff will increase field engagement at a time when many projects are beginning to have their full impact, in order to properly capture the program’s success. DFID will carefully review implementation results at the mid-year reporting point
- Following discussions at the March 2015 Contributors Assembly Meeting, DFID will review and discuss 2015 targets expected from EBRD during April/May, and revise the logframe accordingly..

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203056/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203056/documents/

#### A1. Outline of the programme
The UK is providing £5m (€5.97m) to the European Bank of Reconstruction and Development (EBRD) to enable it to provide technical advice and assistance to countries in the Middle East and North Africa (MENA) Region, specifically Egypt, Tunisia, Morocco and Jordan. The UK’s funds are contributing to the EBRD’s Multi-Donor Account (MDA) for technical cooperation in (what the EBRD titles) the ‘Southern and Eastern Mediterranean’ (SEMED) region. Donor contributions to the MDA as at 31 December 2014 were €24.2m. During 2014 roughly €1.5m of new money was received from bilateral contributors, and €6.0m was contributed by the EBRD from its net income through the Shareholders Special Fund (SSF). The UK remains the largest bilateral contributor to the MDA.

The MDA began operations in March 2012 with the objective of supporting expansion of EBRD’s investment activities into the SEMED region, through the provision of high quality technical advice to public and private clients in the region. The MDA supports activities including: strengthening business management of small and medium sized enterprises (SMEs) and increasing their access to finance; improving the productivity of agricultural businesses and widening their range of local input suppliers; developing projects for the financing of socially desirable and environmentally acceptable infrastructure improvements; reform of legal, social and environmental policies to achieve stronger, more inclusive and more sustainable growth.

During 2014 20 new technical cooperation (TC) projects were approved with total financing of €8m of which €1.5m was provided under SSF co-financing. Of the 20 new projects approved during 2014, 13 will directly back preparation of EBRD investment projects; six approvals were granted in support of policy dialogue work, and one to enable the continuation of advisory services to MSMEs under Small Business Support.

This brings the total MDA portfolio (approved, disbursing, closed) to 59 projects for total MDA support of €21.7m, with 19 projects successfully completed, and 20 newly approved during 2014. EBRD estimates that MDA-funded Technical Cooperation (TC) has supported 20 EBRD investment operations valued at roughly €600 million. This is a significant achievement meaning that MDA-funded TC has supported approximately one-third of the number and value of investment operations in SEMED to date.

A2. UK Development Objectives
DFID’s contribution to the SEMED MDA addressed the need for more inclusive and sustainable growth in MENA countries, in particular Egypt, Tunisia, Morocco and Jordan. Poverty remains a significant challenge despite the middle income status of these countries, and the impact of high unemployment amongst young people, in particular, is a cause of socio-economic stress nationally, as well as of regional instability. Accordingly, this program is focussed on the outcome of increased investment and private sector growth in the four target countries.

Early phase TC projects focussed on building a foundation of financial and other sector knowledge to support the expansion of EBRD’s core lending activity in the region. They also engaged in providing financial and managerial advice to micro and small and agricultural enterprises to support their growth and ability to absorb future investment. Over 2014 there has been a greater focus on TC projects relating to infrastructure projects – particularly in the water, energy and transport sectors – such as feasibility studies and tender documentation.

A3. Regional Context
EBRD activity has continued to build activities in the SEMED region (four countries) with the investment portfolio exceeding €1.5bn by the end of 2014. For example, investment in Egypt grew from €151m in 2013 to €593m even though Egypt is not currently a full Country of Operation, and despite challenges posed by changes in government.

Advisory activities to MSMEs have remained active, and the need for infrastructure investments both to accommodate additional demand from migrants, and to create the socio-economic infrastructure to promote cohesion and economic opportunity, is significant. EBRD’s primary focus on energy, water and other socioeconomic infrastructure will make an important contribution to promoting stability and prosperity in the region.

A4. Revised Results Framework Implementation
In March 2014, MDA contributors approved a Results Framework for the MDA, which is the first fund-level results framework ever established for an EBRD-managed multi-donor fund.

The MDA has target technical areas of operation but since it did not, at the outset, have a specific set of projects to be funded, it was almost impossible to align lograme indicators with projects that were unknown until designed and proposed. Moreover, since each contributor was able to veto programs DFID could not ensure selection of programs that addressed primarily UK development objectives.

After much discussion in March 2014 a new set of output indicators was agreed amongst all contributors, which contained targets for 2014 only, and from that was extracted revised logframe indicators for DFID, as below.

	Output Indicator	NEW sub indicators	Note regarding change from OLD sub-indicators
1	Strengthened ability of SMEs to grow sustainably	1.1 Number of directly assisted enterprises (of which majority female managed) receiving business advice / 1.2 Percentage of business advisory projects scoring as successful or highly successful	Enterprises under Business Advisory Services (BAS), Enterprise Growth Program (EGP), and Local Enterprise Facility (LEF), consolidated into one indicator (1.1)
	(Food supply chain output indicator DROPPED)
2	Strengthened conditions for financing socially desirable and environmentally acceptable infrastructure / (previously Indicator 3)	2.1 Cumulative number of MDA supported investment projects (of which number of projects addressing gender or inclusion through an associated TC) / 2.2 Expected number of end benficiaries of infrastructure investments / 2.3 Percentage of studies and projects for which environmental, climate risk and social impact assessments completed according to best practice	Description of indicator 2.1 was clarified / broadened to include all types of investment projects (not just PPPs) and all types of pre-project support (not just feasibility studies) / Indicator 2.2 changed to a general beneficiary measure / Indicator 2.3 unchanged
3	Strengthened capacity of governments entities to implement legal, social and environmental reforms to support inclusive and sustainable growth (previously Indicator 4)	3.1 Annual number of sovereign clients receiving high quality advice from EBRD / 3.2 Percentage of projects having achieved (or on track to achieving) defined / outcomes as per the respective Results Matrices	Indicator 3.2 changed from old logframe
	(Output indicator collection and dissemination of priority policy needs DROPPED.)

A5. Expected Results
The UK’s funding is expected to support inclusive and sustainable growth in the MENA region. It will do this by, in combination with contributions from other donors, delivering the Outcome of Increased investment and private sector growth in Egypt, Tunisia, Morocco and Jordan. Four Outcome Indicators were identified, and slightly revised in parallel with the agreement of the MDA Results Framework for 2014.
- £500mn (c. €600m) total cumulative EBRD investments resulting from donor-funded technical cooperation
- Cumulative increase in employment (of which women) in businesses receiving direct, donor-funded, EBRD financial and technical assistance of 4250 (2125) jobs
- £400mn (c. €480m) cumulative total of investments leveraged from non-EBRD sources
- At least 60 percent of sovereign and private sector clients implementing legal, social and environmental policy reforms advised by EBRD

These outcome targets were set up in the original DFID Business Case, but the duration of the DFID program is until December 2015. By then DFID’s £5mn contribution will have been fully spent and intended outcomes will in some cases have been very comfortably exceeded.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome Indicators	Target 2014	Achievement 2014
Total cumulative EBRD investments resulting from donor-funded technical cooperation	£500m (c. €600m)	€600m
Cumulative increase in employment (of which women) in businesses receiving direct, donor-funded, EBRD financial and technical assistance	4250 (2125)	Too early to measure (a)
Cumulative total of investments leveraged from non EBRD sources	£400m / (c. €480m)	Pending (b)
Percentage of sovereign and private sector clients implementing legal, social and environmental policy reforms advised by EBRD	60%	Too early to measure; EBRD monitoring
(a) Many of the MSME assistance programs are either still operating, or closed early in 2014. Per OECD DAC guidelines EBRD notes that the employment impact of the assistance is likely to be seen 12 or more months after the end of assistance (see Section C below).

Outcome 1. In 2014 EBRD committed €385 million in investment across Municipal and Environmental Infrastructure (MEI), Transport Infrastructure, Financial Infrastructure (FI), Energy Efficiency and Climate Change (E2C2) Infrastructure, and Power and Energy (P&E) Infrastructure. In the year to December 2013 EBRD made similar commitments of roughly €224 million, for a total by December 2014 of roughly €600 million. The major Abu Rawash Wastewater Plant in Egypt – an expected € 107mn, and originally in the pipeline for 2014 – will materialize during 2015, thereby guaranteeing that the original program target 600 min in cumulative EBRD investments being leveraged will be comfortably exceeded.

(a) Outcome 2. This indicator relates to the provision of advisory services to Small and Medium Enterprises (SMEs) under the Small Business Services (SBS) and Local Enterprise Facility (LEF) sub-programs of the MDA. The SBS sub-program has two components: Business Advisory Services (BAS) projects for enterprises with less than 150 employees; and Economic Growth Project (EGP) activities for enterprises with 150 to 300 employees. This outcome indicator assesses the employment impact of this support. However, according to OECD DAC guidelines, employment (and other) impacts of advisory services are ideally measured at least 12 months after the completion of the advisory support. Accordingly, since the first wave of SBS clients only finished receiving advisory support at the end of 2013, EBRD is only now beginning impact assessments. The first set of employment impact figures will be reported in the next semi-annual review (to be reported to DFID by September 2015).

However, an indication of likely progress can be gained from the results of assessments carried out for an earlier similar set of SBS clients (similar selection process but predating MDA funding for this support). The results for a set of 20 BAS clients showed an increase in employment one year after the provision of advice of 600 employees. By the end of 2015 with 95 advisory clients (including larger clients under the EGP sub-program) we can calculate a likely lower end approximation of the employment impact of MDA advisory services to SMEs of roughly 2850 new direct jobs. This would be lower than the target of 4250 in place for 2014, but still a substantial achievement.

(b) Outcome 3. This figure has not been reported, but there are clearly significant non-EBRD Public Private Partnership (PPP) and non-PPP investment (i.e. cofinancing) amounts to be counted. The previous Annual Review noted no non-EBRD investments as a result of MDA preparation activity in the year to December 2013, but that some €1bn of non-EBRD MDA-related investment was anticipated during 2014. DFID will follow up on this with EBRD.

Outcome 4. It is still too early to identify the percentage of sovereign and private sector clients implementing legal, social and environmental policy reforms advised by EBRD. This could be reviewed during 2015 as part of the Project Completion Review. DFID will follow up with EBRD.

Overall output score and description
The overall Output Indicator Score is A.

Output Indicator	Score	Weight
1. Strengthened ability of SMEs to grow sustainably	A	45%
2. Strengthened conditions for financing socially desirable and environmentally acceptable infrastructure	B	40%
3. Strengthened capacity of governments entities to implement legal, social and environmental reforms to support inclusive and sustainable growth	A	15%
OVERALL	A	100%

Progress on Output 1 met expectations reflecting the maturity of this component, with a strong portfolio of projects closed, implementing and in preparation. Performance with respect to number of majority woman-owned enterprises is notably above expectation. Over the next six to twelve months EBRD will receive performance information on sales, employment and other indicators for the first cohort of SBS companies whose support ended in late 2013 or early 2014.

Progress on Output 2 fell marginally short of target. The number of MDA-assisted projects that led to investments fell marginally short of plan due to delayed implementation and the odd cancellation. Although such things are to be expected it was largely beyond the control of the SEMED MDA program, although it has been noted that early year disbursement was slower than originally hoped.

Progress on Output 3 was well above expectations. A cumulative total of 46 instances of high quality policy advice to sovereign clients was achieved. This was achieved across all three components, but primarily on Components 2 and 3. This comfortably exceeded the target of 30 instances. All active policy projects under Component 3 were on track to, or had already achieved, the Results Framework objectives for each project.

Key lessons
Developing an agreed Results Framework with EBRD for the MDA was challenging, undertaken late in the program, and has limitations; but it was an important step and could usefully have been undertaken at the outset. EBRD is new to the principle of results frameworks, and the nature of the MDA – with sub-projects not decided in advance, and being subject to vetos from other contributors with other outcome aspirations – makes it difficult, sometimes even illogical, to have one. Nevertheless, an agreed Results Framework was incorporated in April 2014, and EBRD is now reporting against it. Having an agreed Results Framework from the beginning might have avoided some of the issues associatied with changing donor preferences, and might have prevented some of the early vetos.

SME advisory activities must be given time to have an impact, and for those impacts to be measurable. Reporting frameworks need to take this into account: it may take six months to design and set up the intervention and identify the first clients; 12 months to deliver a proper program of advisory support; and 12 months for the increased sales or employment to be realized. In other words, a program of this kind will begin to show results after 2.5 years; programs need to have adequate duration. SME outcomes attributable to DFID’s MDA contribution will only be available in the last year, and this poses challenges for incorporating the best indicators in a logframe.

The MDA-type arrangement – multiple contributors with a fungible pool of funds distributed according to moderately rigorous guidelines – was a sensible programming choice. The DFID Business Case also considered a bilateral contribution for a specific purpose to EBRD. The stand alone approach would not have achieved the same scale of impact, or achieved a collaborative voice behind EBRD’s expansion in the SEMED region. Agreeing on program performance indicators has been difficult, but the larger impact of having EBRD invest €1.5bn in the region, and leverage much more, is a great achievement.

The mix of SME advisory activities, infrastructure investment support activities, and some more limited policy advice has worked well. The region needs significant assistance developing the SME sector, and nurturing a high-quality business advisory sector (assuming the subsidy element declines, and the sector is sustainable) is very useful if it demonstrates employment and demonstration impact. In parallel, supporting EBRD’s core expertise of infrastructure investment was a good use of funds for DFID. The two activities addressed DFID core priorities for the region.

The open-ended nature of the SEMED MDA fund has advantages and disadvantages. It allows long run benefits of early interventions to be captured whilst the program is still active. To remain fresh and relevant in its objectives it needs to be flexible. On the other hand this can make it more difficult to measure performance against constant indicators. By the end of 2015 (current project end), DFID’s contribution will be able to be considered disbursed and used, although continuing monitoring, for example through DFID’s EBRD representative, could be considered.

Working with EBRD requires a flexible approach to job creation objectives, and both EBRD and DFID can learn from each other in this regard. For DFID job creation is an important policy objective, and SBS-type programs address this objective in a relatively traditional fashion, even if measurable impacts do take some time to come through. EBRD, meanwhile, is more reluctant to measure employment impacts, especially in infrastructure sectors where restructuring and efficiency may lead to job reduction. However, the efficiency impact of lower costs, better distribution, less wastage and so forth, will have longer run and more inclusive benefits for the broader population. For example, men and women benefit more equitably from public infrastructure services; wealth creation opportunities improve through better access or pricing for electricity; and health and sanitation improve through water-related service improvement leading to a more productive population. The mixed approach can incorporate both direct employment objectives (measured in thousands) from the MSME component, and broader benefits to the population (measured in millions) from the infrastructure component.

Key Actions / Issues
DFID should increase field interaction and follow up on MDA projects and final beneficiaries in time for the Project Completion Report (PCR). So far there has been relatively little to “see”, with MSME support being viewable, but the impacts not yet visible; with knowledge foundation projects having EBRD rather than local institutions as the beneficiaries; and with infrastructure projects steadily moving beyond preparation into implementation. During 2015 MDA projects this will change and field visits will begin to show some of the real outcomes and impacts..

Some questions need to be raised at the donor meetings on 26 March, and thereafter. Questions include:
- Requesting follow up and response on the advisory service subsidy component issue raised in the previous Annual Review
- More detail on MSME final impacts as and when available ahead of the next semi-annual review.
- Clarification on the number of sovereign clients as primary or partial beneficiaries of advisory activities.
- More detail on investments (or loans) leveraged from non-EBRD sources into EBRD-involved investments, whether for PPP or other projects.

Some medium term follow-up activities relating to Program Outcomes could include:
- A review of the possible indirect jobs impact of MSME activities, as well as a broader final beneficiary assessment of infrastructure-related activites. An IFC methodology may be useful for the jobs dimension, but that analysis needs to be seen in parallel to the longer term facilitating infrastructure impact, and the social inclusion and more balanced gender impact of socio-economic infrastructure.
- An investigation, in line with Outcome 4, of MDA projects’ impact on sovereign and private sector clients to undertake legal, social and environmental policy reforms.
- A stocktake of how much non-EBRD investment has been leveraged by MDA activity.

Has the logframe been updated since the last review?
Yes. Please see discussion above and below.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened ability of SMEs to grow sustainably
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	45%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones 2014	Progress 2014
1.1 Number of directly assisted enterprises (of which majority female managed) receiving business advice	95 (10) cumulative	95 (16)
1.2 Percentage of business advisory projects scoring as successful or highly successful	80%	80% [a]

Note: (a) Final performance data for business advisory projects will begin to be available in early 2015, and increase through the year. Actual final performance data for projects receiving advice towards the end of 2015 will not be available until a year or so after that. However, EBRD expect at least 80% based on the performance of a similar earlier cohort of client enterprises (launched prior to MDA funding) for which data are available.

The revised DFID logframe, based on the revised Results Framework from EBRD uses only the above two Output Indicators to determine the Output Score. The table below is provided for reference only, and its indicators are in the EBRD Results Framework, but not all in the DFID logframe. However, the more specific indicators in the Results Framework will be provided to MDA contributors in due course, and will offer a richer depth of understanding of the outcome and impact of the SEMED MDA.

Indicator 1.1. The Results Framework cumulative target for December 2014 for directly assisted enterprises was 95. This cumulative target was achieved with the addition of 46 new SBS projects in 2014. The cumulative target for majority woman-owned enterprises (MWOEs) by December 2014 was 10 according to the revised DFID logframe. Five of the projects launched in 2014 were MWOEs for a total achievement of 16 MWOEs assisted, or 17 percent of total directly assisted enterprises.

Indicator 1.2. EBRD expects reasonably that at least 80% of SBS projects are successful or very successful. This is based on a very similar cohort of earlier clients supported under the same conditions but by a different donor/contributor; this proxy is used because the actual companies supported with DFID/MDA funds are not yet able to report on performance – their results will begin to be available in early 2015, continuing for roughly two years after that with an approximate one year lag from the conclusion of advice implementation . Result highlights from the earlier group of 20 similar BAS clients include:
88 percent of assisted enterprises reported an increase in annual turnover, on average by 60%
- 64 percent reported an increase in the number of employees, on average by 50 percent; this is equivalent to 600 new jobs.
- 28 percent of enterprises had accessed finance within the year following project completion, for a total of €1.1mn
- 36 percent of enterprises employed a consultant again with in a year of project completion.

Key Points
Forty-six Small Business Support (SBS) projects were launched during 2014 marginally exceeding the predicted number for the year, and bringing the cumulative total for MDA-funded advisory services to 95. Cumulatively, seventeen percent of SBS projects (16) assisted MWOEs, exceeding the target of ten.

SBS operations combine the activities under the Business Advisory Services (BAS) for smaller enterprises (less than 150 employees), and the Enterprise Growth Programme (EGP) for slightly larger enterprises (150-300 employees). EBRD is tracking sub-indicators in more detail (increased turnover, employees, financing, and rehiring of consultants) for both groups, but results are not yet available. This is because the anticipated lag between support finalization and impact on enterprise performance is expected to be 12 months for smaller BAS projects with the first full evaluations being carried out in January 2015. EGP projects have an 18-24 month lag. Thus, the first results for MDA-supported assistance to BAS enterprises will be available for the EBRD Semi-Annual Review covering the period to 30 June 2015.

Output 1: SEMED MDA Results Framework Indicators (of which selected are relevant to relevant to revised DFID logframe)

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous Annual Review made two recommendations: (1) to revise DFID’s logframe for the remaining period of its support to the MDA in light of the new Results Framework; and (2) to review the SBS programme to ensure the subsidy component continues to be targeted appropriately and not be excessive.

EBRD is not yet able to report on the overall subsidy component of SBS support, but is being asked for further information on this. However, as with other sub-indicators some insights can be gained from SBS projects that closed earlier but which were not funded from the MDA. The 20 BAS projects funded from other donor sources reported that 36 percent of enterprises employed a consultant again with in a year of project completion (without BAS subsidy component).

As discussed above, the Results Framework has been thoroughly overhauled in consultation with other contributors and the EBRD, and this has been translated into a revised DFID logframe.

Recommendations for Output 1
a) DFID should conduct additional field monitoring visits under this component as more projects are completed and project-level outcomes are visible (by September 2015).
b) DFID should request EBRD for more information on subsidy component of SBS assistance to large and small firms, and its progress over time (by June 2015).
c) EBRD should provide additional reporting on advisory client performance in next semi-annual report (covering period to June 30, due in September 2015).

Output Title	Strengthened conditions for financing socially desirable and environmentally acceptable infrastructure
Output number per LF		2 (formerly 3)	Output Score	B
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones 2014	Progress 2014
2.1 Cumulative number of MDA supported investment projects (of which number of projects addressing gender or inclusion through an associated TC)	16 (2)	11 (2)
2.2 Expected number of end beneficiaries of infrastructure investments [cumulative]	9.9 million	3.1 million – on track to achieve at least 7.4 million by December 2015.
2.3 Percentage of studies and projects for which environmental, climate risk and social impact assessments completed according to best practice	100%	100% / Environmental and Social Action Plans (ESAPs) are completed or in process where required by EBRD rules; elsewhere clients follow agreed environmental and social measures.

The revised DFID logframe, based on the new MDA Results Framework uses only the above three output indicators to determine the Output Score. The table below is provided for reference only, and the indicators in it are contained in the MDA Results Framework. Updates on all indicators will be provided to MDA contributors in due course; and will offer a rich depth of understanding of the outcome and impact of the SEMED MDA.

Although this Component is ranked “B” based on performance against logframe targets, it is in fact performing well, and the impact and growing reach of EBRD’s infrastructure investment in the region is extremely satisfactory. The MDA’s role in preparing EBRD’s infrastructure investments in the region is at the heart of its value proposition, and represents enormous leverage on a small DFID investment. Instead of a few thousand direct jobs (which the program could also achieve), the infrastructure component of the program is directly supporting sustainable energy, water, sanitation, transport and other infrastructure investments. These will impact millions of people including the poorest, and in the context of MENA probably a significant refugee population. The MDA investment is also leveraging non-EBRD financing, and helping improve financial systems and instruments further adding to the multiplier effect. This work to transform the context of economic opportunity and improve living conditions for large parts of the population is critical in a region where millions of individuals reach productive working age each year.

It is therefore surprising that this component is scored as “B” but this is because of extremely ambitious targets. Infrastructure investments are also complicated processes, and lag times and delays are constant risks, as here. Many performance figures, such as ‘end number of beneficiaries’, are also very subjective; and, for example, a much higher beneficiary figure could probably be justified with a slightly different measurement approach.

Indicator 2.1. By the end of 2014 EBRD had signed 11 MDA-supported infrastructure projects, which was short of the 16 envisaged in the Results Framework. This was due to a lower number of Local Enterprise Facility (LEF) deals (four instead of seven), the longer time required to prepare the Abu Rawash Wastewater Treatment plant (now expected in early 2015), and the cancellation of two Municipal and Environmental Infrastructure (MEI) projects (Yamouk Water and Cairo Buses).

Indicator 2.2. EBRD estimates that up to 2.5 million people will benefit from MDA-assisted infrastructure projects singed in 2014, and up to 3.1 million will benefit from all MDA-supported infrastructure projects signed to date. This number is expected to increase to at least 7.4 million upon finalisation of the Abu Rawash Wastewater and other investments. Nevertheless, with EBRD’s approach to beneficiary calculation the figure may still fall short of the 9.9 million forecast in the Results Framework.

Indicator 2.3. All MDA-supported EBRD investments have followed best practice in the completion of environmental, climate risk and social impact assessments. The EBRD Environmental and Social Policy requires that Environmental and Social Action Plans (ESAPs) are developed and implemented where the project does not meet the performance requirements set out in the Policy. The ESAP constitutes an integral part of the financing compliance of the agreement and typically includes a series of measures that are needed to achieve the required standards. Other projects will have been reviewed to be in accordance with the Policy, and therefore would not have required an ESAP. This approach is best practice.

Six MDA-supported infrastructure projects have had ESAPs prepared: three in Egypt, two in Morocco, and one in Jordan. Two of the ESAPs were in the final stages of reporting at the time of December 2014 reporting, but had substantively been implemented with no delays or deviations from plan.

Key Points
For the SEMED MDA Results Framework, six indicators were identified relating to “improved access to public services” in Municipal & Environmental Infrastructure (MEI), Transport, Power & Energy Utilities (P&E), Financial Institutions (FI), and Energy Efficiency & Climate Change (E2C2). The Results Framework’s target of signing €512 million in MDA-supported investments was exceeded, but this appears in DFID’s targets as an Outcome (see above) rather than an Output. Meanwhile, targets for number of MDA-supported infrastructure projects signed, and for number of final beneficiaries reached, were not yet met, as discussed above.

Of the 11 signed investments to date, two projects are addressing gender and inclusion through an associated TC – in line with the Results Framework target. This includes work with the National Bank of Egypt (NBE) on innovation in financial products accessed by women. Also, the Egyptian National Railways (ENR) investment was accompanied by TC to ensure equitable access to services for men and women.

Additional information on specific TCs and related investments is provided in the SEMED MDA Semi-Annual Report (to December 2014).

Output 2: MDA Results Framework – Improved Access to Public Services including Energy (includes three DFID logframe indicators)

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous Annual Review noted DFID should seek additional information on subsidy component of TC projects under this component. This recommendation is more relevant to the MSME program (Output 1) but DFID will clarify plans for regarding cost-sharing of pre-investment costs such as feasibility studies and tender documentation.

Recommendations for Output 2
a) DFID should continue to monitor end beneficiary and total investment count over the remaining duration of DFID support for the MDA (by December 2015).
b) DFID should conduct additional field visits to TC-supported investment projects over the remaining period (during 2015).

Output Title	Strengthened capacity of governments entities to implement legal, social and environmental reforms to support inclusive and sustainable growth
Output number per LF		3 (formerly 4)	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones 2014	Progress 2014
3.1 Annual number of sovereign clients receiving high quality advice from EBRD	30 (cumulative)	46 (cumulative)
3.2 Percentage of projects having achieved (or on track to achieving) defined outcomes as per the respective Results Matrices	70-80%	100%

The MDA Results Framework includes only Output Indicator 3.2, while DFID has chosen to keep Output Indicator 3.1 relating to sovereign clients.

Indicator 3.1. MDA projects have provided high-quality advice to numerous sovereign clients in various ways – with well over 30 such clients since program inception. MDA projects interact with sovereign clients in a variety of ways:
- advice on physical infrastructure programs (Ministry of Finance PPP Units, Line Ministries)
- advice on financial infrastructure programs (Ministry of Finance, Central Banks, Commercial Court System)
- regional or national policy projects with one or more sovereign clients in each country
- high quality advice to sovereign clients can take the form of in-house capacity building, assistance with technical documentation (on-the-job advice), and substantive off-site training.

Examples of such interactions include:
- In Morocco, EBRD is in the 2nd Phase of assisting an interministerial working group to design and implement a Secured Transactions Reform program, which by improving the legal environment and establishing a Pledge Registry will help MSMEs increase access to finance through the mobilization of fixed assets as collateral.
- The Water Along the Food Chain project in Jordan provided advice on stimulating the flow of investment for enhanced water productivity in Jordan. Through this research project, EBRD provided advice to the Ministry of Agriculture (on policies from user side), and to the Ministry of Water and Irrigation (on policies from supplier side). The project brought these and other stakeholders together to develop concrete policy recommendations with a focus on upgrading water efficiency in specific agricultural value chains.
- The Abu Rawash Wastewater Treatment Plant (Assistance to Financial Close) project in Egypt is advising the Ministry of Finance (PPP Unit) on international good practice in PPP project design for this wastewater facility, and also the the Ministry of Water and Wastewater Utilities on maximizing the effectiveness of PPP arrangements in this utility sector.
- Critical Assessment of the Sub-sovereign Financing Framework in Tunisia researched the extent of fiscal decentralization in certain infrastructure service sectors to the subnational level, and the extent to which the legal and regulatory framework facilitated or hindered it. This advice was provided to the Ministry of Finance and other Ministries.

Indicator 3.2. EBRD, through Project Officer interaction and regularly project reporting, regularly confirms that projects under this output have achieved or are on track to achieving project level target outcomes. Amongst policy dialogue projects the Local Capital Market Development project was finalised; other projects are progressing well, and on track to achieve the agreed results, although some have minor implementation delays.

Key Points
Some seven projects fall directly under this output area of policy dialogue and institution building (especially given the consolidation of output areas from the previous AR), but essentially all infrastructure projects involve the provision of high quality advice through on-the-job training and involvement in the preparation of feasibility studies and tender documentation. Water utilities, for example, typically operate as an arm of national government, and the relevant Ministry will always be involved. It is worth noting that EBRD has also emphasized seeking out opportunities for projects and investments at the sub sovereign level; this is clearly an important strategy, but not captured by “sovereign client” terminology.

Summary of responses to issues raised in previous annual reviews (where relevant)
The main issue raised in the previous Annual Review was to review the logframe indicators, in particular with regard to private sector clients. This was dropped and the indicator restricted to sovereign clients.

Recommendations for Output 3
a) DFID to continue to monitor performance of this indicator, and in particular which projects fall under the “sovereign client” catchment, including gathering beneficiary feedback on the advice provided (December 2015).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers are:
- The types of projects that are supported through the Multi-Donor Account and the kinds of consultant expertise required. Some are more expensive than others, with international consultants conducting feasibility studies and preparing bidding documents for infrastructure investments being amongst the most expensive. This is to be expected.
- The balance between the use of local staff and consultants and London-based (or international) staff and consultants. The latter are typically more expensive, and this shift is somewhat inevitable as the MDA becomes more involved in preparing and supporting major infrastructure investments.
- The extent of other costs incurred, including travel and security costs. EBRD now has a fully staffed office in Amman, for example, which has helped reduce some travel costs. More importantly, for EBRD to operate effectively and scale up in the region, a local presence is essential.

Value for Money (VfM) performance compared to the original VfM proposition in the business case
Two key value for money measures were identified for this programme.

Cost per job. Given lack of evidence collected by the programme to date it is not possible to assess value for money in terms of the cost of jobs created as a result of direct, donor-funded, MDA assistance to businesses.

Comment: Given the different types of advisory services (knowledge building, small business advice, infrastructure investment preparation), cost per job measures (these will be available in due course) could in any case only give a partial VfM picture. Once job creation results are available for a subset of MSME projects, and extrapolated to the whole set of MSME projects, and spending on the MSME component isolated and standardized for DFID’s contribution, it may be possible to have a reasonably useful figure for that sub-component.

Similarly, a measure for the effectiveness of the infrastructure preparation activities could be spend per final beneficiary (which will be at least 7.4mn people by December 2015 according to EBRD estimates).

Investments leveraged. As of December 2014, a total of roughly €600m of EBRD investments had been signed for investments supported by MDA technical assistance. Based on the size of the MDA at the end of 2014, the UK can claim that its contribution to the MDA has leveraged at least 26% of this investment value, representing a leverage ratio of over 25:1 (compared to to ratio of 15:1 at the end of 2013). The current ratio will grow significantly over time as advisory projects turn into realized investments.

Assessment of whether the programme continues to represent value for money
The project continues to represent Value for Money.
- The leverage effect of infrastructure investment preparation advisory services is already clear and will continue to grow over the life of the project and well beyond as more projects mature.
- Other aspects of Value for Money cannot be fully assessed until more project level results are in, especially for the MSME business services component.
- Over 2015 it will also become clearer whether and how the EBRD BAS and EGP projects, in particular, are reducing the subsidy component of advisory support.

Some non-quantifiable VfM considerations should also be mentioned.
- DFID’s contribution and the MDA have been instrumental in getting EBRD involved in MENA with offices in the region that are now doing much more than MDA work and associated investments. The vast majority of investment activity in Jordan, for example, is in green energy and water preservation / distribution, activities with enormous socio-economic benefits for Jordanians and the refugees it is likely to host for many years.
- EBRD has made investments of roughly €1.5 billion of which the MDA has now been associated with €600mn – in other words, a significant supporting presence.
- Successful MSME capacity building and infrastructure pre-investment activites have large demonstration effects around the region, showing governments and investors alike what can be done (assuming successful implementation).
- From the start, EBRD sought to investigate the feasibility of sub-sovereign financing, and this has laid the foundation for investors and donors to seek out potential projects at the subnational level with clear inclusiveness benefits.

Quality of financial management
The financial management of the program has been strong, and the EBRD team has been responsive to DFID processes and requests for information.

Date of last narrative financial report	N/A: all funds disbursed
Date of last audited annual statement	May 2014 (for 2013)

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk
Delays in implementation of technical assistance projects. The EBRD could experience further delays in implementation of some activities, for instance due to delays in recruitment or further problems with consultant performance. Also, the spend rate has picked up from earlier low levels. Good consultants are becoming known on MSME activities, and infrastructure consultancies are professionally tendered.

EBRD assistance not sufficiently focused on economic and social inclusion priorities. There are risks, particularly with the pressure to implement quickly, that EBRD technical assistance and investments will not be targeted to produce outcomes that enable full economic participation, including for women and young people. Such focus could also be affected by board level discussions on the EBRD’s mandate.

Results framework indicators capturing engagement with MWOEs, and tailoring of financial instruments to women’s needs have performed well. Also, socio-economic infrastructure activities provide benefits to rural and urban populations, and to women and men more equitably – more so than is the traditional norm in business support activities where getting 50 percent female participation in programs is very difficult.

EBRD is becoming more familiar with DFID’s priorities and the partnership has been strengthened through this programme, through the DFID social development expert working part time out of EBRD, and through sustained interaction on the importance of economic and social inclusion priorities in the Results Framework.

Lack of coordination. There remain risks around lack of coordination of EBRD assistance with that of other IFIs and donors. The EBRD played a strong role in the Deauville Partnership, and served as the Secretariat for the Deauville IFI Co-ordination platform, but has now handed over this role to the European Investment Bank (EIB). Also, now that EBRD has regional offices, and is focussing on core competencies in energy and water, the chances of coordination and efficient division of labour are higher.

Deterioration in SEMED country conditions. Deterioration or lack of progress in building political conditions for economic reform in countries could limit the impact of the EBRD. The EBRD has demonstrated, however, its ability to operate with a range of clients in countries notwithstanding problems with the political and policy environments.

Climate and Environment Risk. Climate and environment risk remains Medium. The programme is funding technical assistance linked to investments in areas that pose environmental and climate risks: infrastructure development, and business growth. Environment and climate assessments are routinely carried out to EBRD standards, and the process was previously assessed by a DFID climate adviser as being robust. In several cases, EBRD activities are aimed at reducing risks of climate change and at promoting environmental sustainability. For instance, with MDA funds, the Bank is: advising public and private clients in Morocco on improving energy efficiency, carrying out preparatory work for a new regional energy efficiency fund, and providing technical assistance for better management of scarce water resources in Jordan.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

As of December 2014 the MDA portfolio stood at 59 projects, representing commitments of €21.7m, an increase of €8 million (€ 6.5m from the MDA and €1.5 million from the Shareholder Special Fund). Accordingly, almost the whole original MDA budget was committed by December 2014. The extension to December 2015 will allow final commitments to be made with the UK portion, and the results of these advisory investments will begin to be seen.

Delivery of individual projects has largely been smooth although project flow was hampered in the early stages by the use of contributor vetos.

Performance of partnership (s)
The EBRD is the implementing partner for the programme and has responsibility for ensuring that projects are implemented smoothly, monitored well, and managed in cost-effective ways. Many of the projects are managed by Program Officers out of London, in coordination with field staff.

DFID and other MDA contributors are responsible for strategic guidance of the programme through consideration of project proposals / fiches, and through participation in semi-annual donor meetings.

The EBRD’s Donor Co-Financing Department provides Semi-Annual updates on progress with the implementation of the project portfolio, and henceforth also reporting against the agreed Results Framework. Assembly Meetings are now held on an annual basis.

The Principal Manager of the Donor Co-Financing Department is the DFID’s main counterpart. The various Program Officers are all extremely knowledgeable, and have been professional in explaining and sharing the performance of their programs, in providing information, and in arranging field interaction.

Asset monitoring and control
Not applicable.

G: CONDITIONALITY (½ page)

Update on partnership principles
Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The theory of change supporting DFID’s intervention through the MDA is as follows

Technical cooperation and assistance can help to deliver improved policies and performance in private sector development, infrastructure and the agricultural sector		Strengthened private sector development, infrastructure and agricultural sector performance are important for promoting inclusive growth		“Inclusive” growth in MENA is important for reducing unemployment, poverty, conflict and fragility

The EBRD has proven able to deliver effective TC projects in a way that would not have been possible through a private contractor. EBRD has expanded its presence in the region, and improved delivery capacity. It has delivered effective bottom-up support through SME advisory services, and will continue to do so through the open-ended MDA fund. It has specialized in its main infrastructure competency areas, and used the MDA to drive this agenda forward through initial knowledge-building projects, and thereafter through feasibility studies and preparation of documents that have led to €600mn in infrastructure investments (by EBRD with additional non-EBRD investment leveraged) with significant inclusion benefits.

A bilateral program with only DFID funding would not have achieved the same leverage and visibility. In some ways it has been more difficult to manage, but sacrifices made on DFID-specific reporting, and pace of disbursement, have been worthwhile for the medium and long term impact being achieved.

The theory of change still holds, and the largest impacts from DFID’s contribution, from MDA resources as a whole, and from EBRD’s significant and increasing presence in the MENA region will be seen in the medium and longer term.

Monitoring progress throughout the review period
The principal monitoring mechanism during 2014 as with previous review periods was the regime of semi-annual MDA reporting through the Donor Co-Financing Department of EBRD. This has been effective with comprehensive reporting across the portfolio.

However, the main challenge, discussed above, was the absence of a Results Framework for reporting on progress of the MDA. Business advisory support provided to SMEs is tracked at the project level, but with significant lag (following OECD DAC reporting guidelines), on the principle that the sales and employment performance effect of advisory support can be seen only one year or more after the delivery of support. On infrastructure investment, monitoring can be more difficult still since EBRD does not normally track job impacts on the (reasonable) principle that improved efficiency in service delivery may involve restructuring and job cuts. Consequently, it was a major achievement of DFID and other MDA contributors to encourage the production of EBRD’s first Results Framework for a multi-donor account. Moreover, agreed targets included a variety of social and economic inclusion measures thanks, in particular, to DFID influence.

There was regular program oversight from the DFID Project Manager (Private Sector Adviser) beginning with field visits to some SME beneficiaries early in the year, and regular interaction with EBRD project managers thereafter, both directly and through the DFID Representative to EBRD.