Type of Review: Annual Review

Project Title: Building a stronger regional climate research effort in South Asia (202125)

Date started:	13th January 2014
Date review undertaken: 13-31 Jan 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
We will provide £2.6 million over 4.5 years (2010-2015) to support the development of more coordinated and higher quality climate research and information services in South Asia. This support will cover four areas of activity: / coordination and strategic dialogue among funders of research; / commissioning high quality evidence reviews (including systematic reviews) of key subjects of policy importance; / commissioning small-scale research addressing key topics; and, / building capacity of South Asian climate researchers to publish papers in high impact journals. / These areas reflect the recommendations from an expert framing paper in 2011 that set out the key issues and recommended responses to improve coordination and coherency in climate research in the region.

What are the expected results?
CRISSA is expected to lay the foundations for a regional research strategy by facilitating a process to agree regional research priorities among international and national research funders and develop a division of labour among international funders. CRISSA will improve the quality of the available evidence-base by commissioning high quality reviews of evidence and policy and programming relevant research on key topics. In addition, CRISSA will support South Asian researchers publish their findings in high-impact peer reviewed journals to influence international processes such as the IPCC, and support the development of national research platforms to take forward more coherent programmes at country level.

What is the context in which UK support is provided?
The UK provides significant support to climate research and policy in South Asia and has strong relationships with partner Governments, other donors, and the research community. We have been directly approached by Government of India to support their efforts to work more closely with their neighbours on climate change and have been requested by other Governments in the region to help improve their research and evidence base in climate change. The presence of the DFID South Asia Research Hub, the RCUK office and the FCO Science and Innovation Network in Delhi provides a strong focal point for action around research collaboration that other research funders do not have, as their research commissioning departments are commonly based in their headquarters. In addition we have close relationships with other donors active in the climate arena. This places the UK in a unique position to help develop and drive forward coordination around climate research.

## Section A: Detailed Output Scoring

Output 1: Coordination of research funders
Output 1 score and performance description: C / Little progress has been made on donor co-ordination, in large part because of lack of specialist staff to lead this programme for half the year. There is a wider question however about whether SARH is the right body to co-ordinate research funders in the region. This needs to be discussed and agreed between the DFID India / FCO Energy, Climate and Growth Unit; the RED Climate and Environment team; and the Asia Regional Climate Advisers. Depending on the outcome the log frame will need to be reviewed and revised as appropriate.
Progress against expected results: / Output Indicator 1.1 - Agreed process to develop a regional climate research strategy for South Asia agreed / No process has been agreed, but discussions were held with IDRC and WB at a Roundtable on the research response to the Uttrakhand floods in Sept 2013. / Output Indicator 1.2 – ‘Division of labour among international funders’ with a 2013 milestone of Draft division of labour prepared based on comparative advantage and interests. / Discussions have not taken place. / Output Indicator 1.3 - Number of jointly funded research programmes’ with a 2013 milestone of `2 additional jointly funded climate research projects [since 2012]’. / IDRC jointly funded the ISET project and ADB theIntegrated Flood Management under Climate Change. However, these projects have already been counted as jointly funded research programmes last year in which case they could not count as two new and additional ones for 2013. / Recommendations: Discussion should take place with the DFID/FCO Energy Climate and Growth team and the DFID Asia Regional Climate team to agree where responsibility for research co-ordination should lie / Impact Weighting (%): 20% / Revised since last Annual Review? Y/N No / Risk: Medium / Revised since last Annual Review? Y/N No

Output 2: Quality of evidence base available for policy makers and programme managers
Output 2 score and performance description: B / Two projects, with ISET (with IDRC) and International Alert have been completed, disseminated and reports prepared and loaded on R4D. The Precipitation Study is still work in progress, timeframe delayed due to the project team having to change location from western Himalayas to Nepal, for security reasons. / International Alert have published their findings on their website, including 4 country reports and an overview executive summary. One article has been published in a peer reviewed journal and they have submitted another to ‘Development in Practice’. / The ISET Impact of the Indus Floods in Pakistan project responded to the need to generate new knowledge on climate related hazards and their impacts on marginalised communities, along with analysing the factors that enable recovery following floods in the Indus Basin in Pakistan. Specific causes of vulnerability were diagnosed and opportunities for building resilience identified. / There are reasonable prospects for policy makers and programme managers using the information generated through the ISET and International Alert projects, but producing briefs as well as academic papers would help make the findings more accessible. The ISET project has delivered some relevant outputs, however, it does not appear that these have been widely communicated beyond a research audience. Whilst clearly a high standard of research has been achieved (two distinctions awarded for the Masters theses arising from this project and one peer reviewed paper produced and another submitted), these types of outputs are not widely accessible to decision-makers. ISET recognises the need for briefs and other communications material, but there is no report of additional material being produced.
Progress against expected results: / Output Indicator 2.1 – ‘High quality systematic reviews produced on key subjects on policy relevance’ with a 2013 milestone ‘Commissioned systematic reviews completed and disseminated’ / No SRs commissioned – The Annual Review conducted in 2012 mentions that a series of systematic review questions will be generated and commissioned through the South Asia Water Initiative. These were not commissioned and the project needs to review what the current needs are and make appropriate plans for taking this activity forward over the next year. / Output Indicator 2.2 - Evidence on the needs of users climate information with a 2013 milestone Review submitted and disseminated / WRI reports were written and published on R4D but have not been extensively disseminated beyond this. / Output Indicator 2.3 `Rigorous research findings available on key topics on policy and programming importance’ with a 2013 milestone `Projects completed and reports and journal papers prepared’; / Integrated Flood Management under Climate Change (ADB): There is an Interim Report (which identifies concrete research topics as well as opportunities for operational research, Section 8.5), and a draft Final Report for Phase 1 (which is a scoping study including a literature review of best practice). However, if the milestone refers to final reports then there has been no progress against this indicator. / Groundwater resources in the Indo-Gangetic Basin: resilience to climate change and pumping (BGS): There have been some project outputs, such as from the workshop held in Delhi in Nov 2013. / There are several outputs from the ISET Impact of the Indus Floods in Pakistan project which make a contribution to improving the quality of evidence available: / - a report on ‘Findings from the Field – Role of Access to Basic Service in Building Resilience’. This report has the potential to be developed into a peer reviewed paper. It has also provided insights for policy makers and project managers on how to construct adaptation strategies for more effective responses to climate related disasters in developing countries. There is no information available in the technical report as to whether the findings have been presented and communicated in relevant fora. / - A simple human vulnerability index to climate change related hazards in Pakistan was developed as part of a MPhil thesis, for which the student earned a distinction and a paper was published from this work in a peer reviewed journal. This indicates high standard of research, however, this type of work will not be easily accessible to policy makers/project managers and more work would be needed to ensure that this research is communicated and made available to a practitioner community.(NB this achievement should also be reported under output 3 as this was put together by a student of Quaid-i-Azam University in Pakistan and therefore contributes to capacity building and climate science papers publication. / - A Master’s thesis on the demographic dimensions of flood vulnerability in Rural Charsadda in Pakistan. This piece must also be of high quality as the Masters gained a distinction. No papers published from this work, but ISET should be encouraged to communicate this to the researchers. / - A meta-analysis of all the reports produced on the recovery effort post floods in 2010, which placed special emphasis on understanding the institutional issues. / The International Alert project has produced a series of reports (an overview and for each of the four study countries India, Nepal, Bangladesh), see http://www.international-alert.org/resources/publications?f[0]=field_topic%3A13. There have policy briefs produced, a workshop and various other activities to enable better uptake of the work. One article has been published in a peer-reviewed journal: ‘Vulnerability to Environmental Risks and Effects on Community Resilience in Mid-West Nepal and South-East Pakistan’ in ‘Environment and Natural Resources Research’ and another has been submitted to ‘Development in Practice’. / Recommendations: / Integrated Flood Management under Climate Change (ADB): We should ensure that the new ADB team is clear on DFID contact points; have realistic expectations for our level of engagement; and maybe agree turnaround times for comments, taking into account our staff capacity. ADB team should have the overall CRISSA programme explained to them so that they know which project deliverables we care about most. SARH should also explore engagement with DFID state programmes in Bihar and Orissa, as well as the DFID India World Bank Trust Fund, and other ECGU programmes. / Groundwater resources in the Indo-Gangetic Basin: resilience to climate change and pumping (BGS): This is a very interesting and potentially highly significant study. The BGS team should have a wider discussion with HMG in the relevant countries and think through policy and dissemination possibilities to ensure that the work goes beyond the technical. Consideration of policy applications and dissemination will need to be sensitively done. / Future research commissioned through SARH should ensure that there is wide dissemination among relevant stakeholders and that outputs are produced that are accessible to practitioners and not just an academic community / Impact Weighting (%): 50% / Revised since last Annual Review? Y/N no / Risk: Medium / Revised since last Annual Review? Y/N no

Output 3: Capacity of south Asian climate community to produce high-quality and influential research
Output 3 score and performance description: C / There have been contributions to this output from the research projects funded under the CRISSA programme, but the main intervention which was to have delivered the milestones and target for this output was the SICRISA project of ‘writeshops’ and writing fellowships to support south Asian researchers to get their work published in the international peer-reviewed media. / After a separate review in March it was recommended that the SICRISA programme be stopped, as it was not delivering articles which were likely to be publishable. In many cases the research design was poor and the writeshop intervention would not be able to address that. The log frame needs to be revised to reflect the removal of this intervention. / The ISET work enabled two Pakistani students to gain Masters degrees both with distinction. The project also strengthened research skills across the ISET network and enabled the establishment of ISET Pakistan. The International Alert work has strengthened the knowledge base of links between climate change and conflict, through the research work itself which has been disseminated through a wide range of conferences and workshops regionally and internationally. The project also organised a high level regional policy dialogue in Kathmandu in July 2013, and has disseminated findings through the SANSAC network – which is the South Asia Network on Security and Climate Change and is a member based network of experts and relevant institutions dealing with these issues in the region. A few news articles have also been published from this work, (http://www.trust.org/item/20130709160228-luhwf/?source=hptop and http://www.trust.org/item/20130509103349-hfcla/) / The ISET and IA projects have resulted in two papers published in peer reviewed journals. It does not appear that there will be more papers published in peer reviewed journals from these two projects. However, the target for 2014 was 50 papers published (note what have other projects published and need to say something about how CRISSA will achieve this target, and why not yet etc).
Progress against expected results: / Output Indicator 3.1 `Number of papers on climate science published in high impact journals with South Asian lead or sole authors’, with a 2013 milestone of 5 `writeshops’ completed (and 50 papers by 2014). / Two writeshops (in Kathmandu and Delhi) were completed before the SICRISA project was closed in March 2013. / Integrated Flood Management under Climate Change (ADB): Three papers planned for 2015; none published so far as the project is not yet complete. / Groundwater resources in the Indo-Gangetic Basin: resilience to climate change and pumping (BGS): Aiming for 3 papers from this case study – Dr Krishan (NIH) said that one had already been accepted for publication. / The ISET floods project and the work on the human vulnerability index has resulted in a peer reviewed paper, with South Asian lead and sole authors. (ref Khan, F. A and Salman, A (2012) A simple human vulnerability index for climate change related hazards for Pakistan. Published in International Journal for Disaster Risk Science, September 2012. The International Alert work has also resulted in a paper published in the peer-reviewed journal Environment and Natural Resources Research titled ‘Vulnerability to Environmental Risks and Effects on Community Resilience in Mid-West Nepal and South-East Pakistan’. / Both ISET and International Alert have submitted papers to ‘Development in Practice’ / Output Indicator 3.2 - National climate research platforms / No progress under this output. Whether SARH is the right body and has the capacity to co-ordinate research funders in the region needs to be discussed and agreed between the DFID India / FCO Energy, Climate and Growth Unit; the RED Climate and Environment team; and the Asia Regional Climate Advisers. Depending on the outcome the log frame will need to be reviewed and revised as appropriate. / Recommendations: / The log frame needs to be revised to reflect the removal of the SICRISA intervention and of discussions between SARH, the DFID India / FCO Energy, Climate and Growth Unit; the RED Climate and Environment team; and the Asia Regional Climate Advisers. / Impact Weighting (%): 30% / Revised since last Annual Review? Y/N no / Risk: High / Revised since last Annual Review? Y/N no

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y/N No / This review has identified that the LF needs review and significant changes are recommended. These need to be agreed in discussion with the DFID India / FCO Energy, Climate and Growth Unit; the RED Climate and Environment team; and the Asia Regional Climate Advisers and this should be done as soon as possible / 1.2 Overall Output Score and Description: B / Outputs moderately did not meet expectation / 1.3 Direct feedback from beneficiaries / The ISET report was welcomed by the humanitarian team in DFID Pakistan which found the study’s focus on livelihoods and resilience very helpful for their work.
1.4 Summary of overall progress / This programme has now delivered on 4 projects with one closed and 4 on-going. Those that have finished have produced final reports available on R4D and some articles have already appeared in peer-reviewed, more have been submitted. As the other projects finish they will generate more evidence. SARH needs to give more thought to how this evidence is disseminated beyond academic literature to other stakeholders in the region.
1.5 Key challenges / The key challenge during the past year has been the availability of technical staff within the SARH. A candidate was appointed who left after 6 months’ probation period. The lack of technical leadership has limited SARH’s capacity to take on a leadership role in regional climate research as was envisaged in the Log Frame.
1.6 Annual Outcome Assessment / The outcome is ‘more coordinated and coherent regional approach to research’. This outcome should be reviewed and restated more clearly as part of the discussion on the project and log frame with the RED Climate and Environment Research Team, DFID/FCO Energy Climate and Growth team and the DFID Asia Regional Climate team. Given changes in the technical skills in the SARH team it is important to agree with these other stakeholders how to take forward research co-ordination on climate change across Asia Region. / The first outcome indicator is ‘level of duplication of research efforts’ and the milestone for 2012 is ‘International funders agree to share research plans to reduce potential for duplication’. This indicator has been partly achieved through closer working and information sharing, but research plans have not formally been exchanged. There is no milestone for 2013 but the milestone for 2014 is ‘Regional research priorities agreed among national and international funders’. Given current progress this milestone may not be achieved in the coming year. / The second outcome indicator is ‘Improved evidence base available to regional decision makers from jointly funded research and high quality evidence reviews’. The 2013 milestone is ‘key research and reviews produced that are disseminated and discussed with decision-makers’. The programme is producing good quality evidence but the SARH could to more to ensure this reaches decision- makers.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N Yes / The project spend on ARIES shows that the project is on track against the forecasts for the review period. It should be noted that for a programme of this nature, it is difficult to identify the full set of research activities to be undertaken at the start of the year. A request or a need for a new research study can arise at any time, and the programme has to maintain flexibility to be able to respond. The team is getting better with forecasts through regular review and close tracking of AG and contracts. Going forward, a systematic schedule of consultations with partners could help in streamlining planning for the year and develop best estimates. / So far, the programme has spent over 50% of its allocation since the start of the programme. Of the remainder about £716,000 is committed to be spent on on-going studies and plans are in place for the remaining funds.. / Some of the earlier activities planned for donor coordination and evidence reviews have spent less. The team will need to factor this in as they make plans for the next year, which will be the final year of support. / 2.2 Key cost drivers / The key cost drivers have essentially been academic and researcher’s time on capacity building and commissioned research activities. The proposals are reviewed in consultation with PrG and RED policy guidelines to ensure competitive rates are agreed. The other cost driver is the equipment procured for specific studies such as the precipitation study and the integrated flood management study. Procurement clauses covering international good practice are inbuilt into the suppliers/grantee contract and MoU which are to be complied with. / 2.3 Is the project on-track against original timescale: Y/N No / The project period was extended by two years from March 2013 to March 2015 and it also included topping up of funds. This was to facilitate commissioning of policy-relevant research, which included research projects co-funded with the Asian Development Bank on the Satluj river basin; a study into groundwater vulnerability to climate change which builds on previous PRF funded work; and, a study into conflict sensitive climate programming. / The project logframe was revised in line with the recommendations from the last review held in 2013. The slowdown of output 1 and 2 needs to be reviewed and accordingly plans to be developed to ensure realistic commitments are made for the remainder part of the programme.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There have not been any significant changes in evidence around climate change in S Asia in the past 2 years. This programme includes a number of projects which are collecting primary data on climate change which will significantly add to the evidence around climate and environment in S Asia. / 3.2 Where an evaluation is planned what progress has been made? / No evaluation of the programme is planned

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / Overall this programme is judged medium risk. / There are risks in the collection of good data: some the projects involve working in difficult environments (high altitude precipitation) and others require inputs from different government partners which can be hard to co-ordinate (ground water resilience). These risks have been judged to be manageable by the implementing partners. / In addition there is considerable risk around SARH’s technical capacity to deliver the level of ambition in the LF. It is recommended that this be reviewed in discussion with the DFID India / FCO Energy, Climate and Growth Unit; the RED Climate and Environment team; and the Asia Regional Climate Advisers and this should be done as soon as possible / There is a big amount to be spent in the remainder year of the programme. Plans outlining funding lines for various activities have been identified by the team. This will need urgent development and close monitoring by the team to ensure that the committed budget is spend by the end of the programme. Sustainability is another important aspect that the team will need to think about post programme funding.
Risk of funds not being used as intended / DFID makes disbursements in arrears against invoices (except in the case of the MoU with ADB). Payments on contract with suppliers are linked to delivery of milestones. Payments for Accountable Grants are linked to submission of progress report and expenditure statement. An annual audited statement of accounts is further submitted at the end of each financial year. Contractors and grantee are required to maintain inventory list of items that have been procured with programme funds and provide periodic updates. For strengthening fiduciary assurance, SARH should make visits to the programme, undertake due diligence and PrG led post procurement audits of the suppliers. / 4.4 Climate and Environment Risk / This project is considered low risk as it is seeking to gain further knowledge as to how to manage climate and environment risks.

5. Value for Money
5.1 Performance on VfM measures / The key measures identified as a measure for vfm in the business case include amount of research that is designed either jointly or explicitly taking into account other funder activities, metrics to assess quality of outputs (papers) and influence (through pathways to impact) and cost-ratio per paper from the support to publications. These are still applicable and in the absence of not having been able to institute a peer review mechanism due to cost and time reasons, it is difficult to make such an assessment. There was little evidence of a focus on systematic reviews uptake and the impact of capacity building or research outputs on policy/programmes. / 5.2 Commercial Improvement and Value for Money / Contracts are let through either Research Procurement Unit or PrG so Value for Money for these agreements is reasonably well assured. Each individual project is commissioned against a detailed terms of reference which specifies clear purpose and expected outcomes with timelines. The contracts signed are output based that have milestones and have to follow an agreed reporting arrangement. For larger projects, implementing partners need to develop logframes and report progress against it. For contract amendments, clear proposals with budget and outcomes are required along with description of the additional deliverables. / VfM in AGs is ensured through SARH monitoring tools, regular contacts with suppliers and linking quarterly payments (in arrears) to progress reports. / 5.3 Role of project partners / In general the project partners have performed well against the indicators in the logframe and are largely on track to deliver the agreed outputs. / 5.4 Does the project still represent Value for Money : Y/N yes / The project continues to represent value for money as it helps in addressing the significant duplication and research gaps in research in the South Asia Region. The project has been able to facilitate greater interaction among funders of research, the research community and end-users. The expert framing paper has set out a clear agenda for future action which is influencing DFID and other funders. The commissioned research and reviews are all addressing key issues for which there is a wide audience among the research community (including funders) and policy makers. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / None in place

7. Conclusions and actions
Output 1: / Discussion should take place with the RED Climate and Environment Research Team DFID/FCO Energy Climate and Growth team and the DFID Asia Regional Climate team to agree how to take forward research co-ordination on climate change across Asia Region and the LF be revised accordingly. / Output 2: / Integrated Flood Management under Climate Change (ADB): We should ensure that the new ADB team is clear on DFID contact points; have realistic expectations for our level of engagement; and maybe agree turnaround times for comments, taking into account our staff capacity. ADB team should have the overall CRISSA programme explained to them so that they know which project deliverables we care about most. SARH should also explore engagement with DFID state programmes in Bihar and Orissa, as well as the DFID India World Bank Trust Fund, and other ECGU programmes. / Groundwater resources in the Indo-Gangetic Basin: resilience to climate change and pumping (BGS): This is a very interesting and potentially highly significant study. The BGS team should have a wider discussion with HMG in the relevant countries and think through policy and dissemination possibilities to ensure that the work goes beyond the technical. Consideration of policy applications and dissemination will need to be sensitively done. / Future research commissioned through SARH should ensure that there is wide dissemination among relevant stakeholders and that outputs are produced that are accessible to practitioners and not just an academic community / Output 3: / The log frame needs to be revised to reflect the removal of the SICRISA intervention and of discussions between SARH, the DFID India / FCO Energy, Climate and Growth Unit; the RED Climate and Environment team; and the Asia Regional Climate Advisers .

8. Review Process
A team of three DFID staff members conducted the AR at the invitation of SARH to review the CRISSA programme. This was a desk based review of available documentation which involved review of Business Case, logframe, reports from commissioned work, proposal and contracts for commissioned work, and consultation with DFID project implementers, advisers across the three country Offices (India, Bangladesh and Nepal) and the SARH team. / The review team consisted of: / Gregory Briffa – AR Lead, Team Leader Climate & Development, India Energy, Climate and Growth Unit / Izabella Koziell- Senior Climate and Environment Adviser, Asia Regional Team reviewed outputs of the International Alert and ISET projects. / Sandeepa Sahay – Programme Management, DFID India