Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	January 2015

Title: / Support for Electoral Reform of Pakistan (SERP) 2012-2014 (jointly funded with EU and Canada and programme continues til 2016.)
Programme Code: 203039	Start Date: April 2012	End Date: December 2014 (DFID funding),

Summary of Programme Performance

Year	01/2013	05/2014	01/2015
Programme Score	A+	A	A
Risk Rating	Medium	Medium	Medium

Financial Position

Original Programme Value	£5.68 million (of a total of $20.4 million funded jointly with Canada and the EU)
Extensions/amendments	N/A (The project has been extended until mid-2016 with funding from Canada)
Log-frame revisions (with dates)	Following the first Annual Review (January 2013), main changes include: / Output 1.2 (Coordination with international community for the advocacy of electoral reforms) was introduced in recognition of IFES’s role as Secretariat to the Elections Support Group (ESG); / Procurement of ballot boxes became a distinct indicator for Output 2.4 (Enhanced operational capacity of the ECP) / The initial Output 2.1 (Strengthened institutional capacity of the ECP to manage the electoral process) was removed (as this coincides with Outcome 2) / The indicator associated with the initial Output 2.1 (Number of IFES-supported objectives of the ECP’s Strategic Plan achieved) was moved to Outcome level as indicator 2.2 and was changed to reflect partially achieved objectives of the ECP Strategic plan (Percentage of the ECP Strategic Plan achieved, including objectives that are completely achieved and in progress) / Note: The activities initially envisaged under Output 2.1 were retained and were included under Output 2.2
Total programme spend	£5.5m

Follow up actions required following closure

Feedback lessons learned, externally through the Voice and Accountability Group and Elections Support Group and internally with the DFID Pakistan Governance Group, across the DFID Pakistan office and with Policy Division (GOSAC). Principally this will feed into phase II design of the joint donor election support and the DFID/FCO Conflict, Stability and Security Fund design for the democracy strategy.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717012.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3393568.docx

Outline of project and what it has achieved
The SERP project provided technical assistance to the Election Commission of Pakistan (ECP). Its specific objective or outcome is ‘more credible, inclusive elections’ through strengthened electoral legal framework and electoral management capacity, and increased voter and civic education outreach. SERP is co-funded (to a total of $20.4 million) by the Canadian International Development Agency (CIDA), UK/DFID and the European Union (EU) and forms part of a broader multi-donor electoral support programme co-funded with Australia and Norway.[1] SERP is implemented by the International Foundation for Electoral Systems (IFES).
[1] This PCR was carried out within the scope of a joint donor evaluation of five projects constituting this broader programme. It assesses SERP’s performance as an individual project but contains analysis related to the broader support strategy. For the UK/DFID, SERP complements Supporting Transparency, Accountability and Electoral Processes in Pakistan (STAEP), through which DFID provided support to FAFEN between August 2010 and December 2014, including for election day observation activities. STAEP is outside the scope of the joint donor evaluation.
The overall final score is A
Prior to 2008, there had been a number of elections that failed to meaningfully contribute to the consolidation of democracy in Pakistan. The 2008 elections brought a civilian government to power with the formation of a coalition government that was amenable to electoral reform, although the transition remained fragile. The ECP faced a number of challenges including limited independence and accountability, weak transparency and credibility in its processes, and weak technical capacity. In this context, to contribute to the democratic process, legal framework reform and ECP capacity support were seen as important including by the ECP itself.
Against this background the work of IFES (and UNDP through one of the other election projects supported by the EU) helped the ECP to conduct an election that was accepted, even if problems were and continue to be evident. The 2013 elections were seen as an improvement on 2008 and ultimately enabled the first peaceful civilian handover of power in Pakistan’s history. This was a critical achievement to which SERP contributed directly. It also contributed to increased confidence in the ECP and in the overall electoral process.

Main SERP achievements include (UNDP/UN Women project also contributed to those marked with an asterisk):
- The adoption of Codes of Conduct (for candidates, polling staff, observers and security forces), which are said to have established some basis for accountability and, thus, enhanced confidence in the process.*
- Overall, 55% of registered voters cast their votes in the general elections, in comparison to only 44% in 2008, which suggests increased pre-election voter confidence in the process. This may have been due in part to improvements in the voter list, although attribution is difficult: other factors have a role to play[2].
  [2] For example reforms put in place since the last elections and socio-political factors unrelated to confidence in the system
- Training of 241,630 polling staff for the May 2013 general elections on behalf of the ECP[3] , which supported the electoral process and brought incremental improvements in polling station operations, thus contributing to the election’s overall acceptance.
  [3] For this activity, IFES received supplementary funding from the FCO.
- Improved enfranchising of Internally Displaced Persons (IDPs), enabling the participation of over 350,000 IDPs, most of whom would have otherwise been disenfranchised.
- Continued incremental improvements in the voter list,[4] building on previous (IFES) advice that significantly improved the list by basing it on the civil registration database of the National Database and Registration Authority (NADRA). The improved voter lists were one of the key contributing factors to increased confidence in the electoral process.
  [4] This report refers to ‘electoral rolls’ as voter lists as this is more accurately reflecting that they are extracted from another dataset and are not currently kept as a permanent roll by the ECP.
- The ECP post-election review which identified lessons learned from the 2013 process to enable future process improvements, and the ECP’s second Strategic Plan (2014-2018) which allows for further ECP institutional development in a strategic manner.*
- Creating the basis for gender mainstreaming within the ECP and its processes.*
- Enhanced ECP strategic and planning capacity with development of the Second 5 year Strategic Plan (14 – 18); Increased organisational technical/administrative capacity to deliver elections as a results of training and BRIDGE[5] workshops with increased understanding & ownership by the ECP of the importance of building its own training/capacity development.
  [5] BRIDGE is a well-established elections’ training methodology
- 880,000 people reached through the voter education activities of four local organisations to which IFES provided sub-grants under SERP.

SERP working with the ECP, contributed to more inclusive elections, to increased public confidence in the electoral process, and overall to the acceptance of the 2013 elections, resulting in the first historic handover of power from one civilian government to another.
Whilst celebrating the above achievements and some key improvements, these now require consolidation. It is broadly recognised that electoral reforms are in their early stages. Weaknesses still need to be addressed, lessons need to be learnt, and momentum for electoral reforms needs to continue so that Pakistan’s emerging democracy can be strengthened. This was one of the key demands of the 4 months’ protests led by the PTI opposition party from August 2014 in Islamabad and other major cities.
Areas for continued attention include the electoral legal framework, other aspects of electoral reform and strengthening the capacity of the ECP.
The ECP’s strategic and operational capacity (transformation of institutional culture, assertiveness and independence in more politically sensitive areas of reform, implementation of the electoral law, and the ability to carry out hefty operational tasks such as training of polling officials) have understandably only made some progress over the lifetime of this short-term support, with some necessary capacity substitution by IFES and UNDP.
Challenges to reform include both internal and external factors. Given the highly complex and changing political context; and the structural barriers, vested interests and disincentives for shifting the status quo, the slow pace of reform is not unsurprising, and is necessarily a long-term process.
More can be done going forward to address these issues including through better collaboration between the supply and demand sides with other partners, political dialogue and an approach that is informed by political economy analysis. This will need to be better incorporated into any future support and programme design.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

Indicator(s)	Targets	Progress
Percentage of international and domestic observer missions that report that the legal framework provides a sound basis for credible elections	All main observer groups	44% of observer groups mentioned the quality of the legal framework in their observation reports (i.e. four of the nine groups mentioned the quality of the legal framework)
Perception of international and domestic observer missions, political parties and citizens report confidence in the capacity of the ECP	All key observers and main political parties; 60% of citizens	57% observers; 48% of citizens
Percentage of registered voters participating in the general elections is increased	50% turnout for general elections; 40% of registered women voters (requiring that women votes are calculated separately)	Overall turnout 55%[6] / Official figures for female turnout not available. FAFEN Parallel Vote Tabulation (PVT) estimates 50.7% turnout in female polling stations (9% increase)
The percentage of ECP’s Strategic Plan achieved, including objectives that are completely achieved and in progress	85% of the Plan achieved with +10 objectives achieved completely and 47 objectives in progress (this target was for early 2014)	By end 2013, 79% achieved; 68 objectives achieved completely, 12 partially and 34 in progress / In May 2014 the ECP developed a new Strategic Plan (2014-2018). Future progress will be measured against this plan.
Number of parties, domestic observer groups and percentage of citizens with confidence in the electoral rolls	20 organisations (16 political parties in the ECP consultative group and 4 observer organisations, of which at least 1 is a women’s group); 65% of citizens	46.2% of citizens; 4 observer groups
[6] The official voter turnout rate for 2008 was 45%, but the true turnout rate was higher because the ECP cancelled a large number of unverified votes. The Impact Evaluation estimates that there was a positive change in the outcome indicator even if the scale of change is likely to have been more modest than suggested by official data.

Impact is inherently difficult to attribute and sustainability as difficult to assess. Nevertheless, the Impact Evaluation of DFID’s electoral programmes in Pakistan (September 2014) found that SERP ‘made a minor but significant contribution to the broader goal of democracy strengthening through its assistance to the ECP’. At outcome level, the Impact Evaluation found that ‘SERP was able to achieve some important landmarks in collaboration with the ECP and its role was generally viewed as positive by stakeholders, however, not in the way envisaged by the programme.’
These findings are supported by the EU/joint donor evaluation (Aug-Dec 2014), which found that the contribution made by IFES alongside other stakeholders resulted in more confidence in the electoral process, ultimately achieving the political imperative of the first transfer of civilian power through elections that were peaceful and accepted overall in Pakistan’s history. Electoral operational achievements for 2013 could be attributed to a large extent to the persistent and well-directed assistance received from IFES and UNDP/UN Women. They were made possible through previous IFES work (voter list, strategic planning) and highly strategic advocacy work undertaken by Democracy Reporting International (DRI) (with EU funding) and complemented by FAFEN (Free and Fair Elections Network) (with UK funding).[7]
[7] SERP’s contribution to the outcome cannot be disentangled from that of other projects implemented by FAFEN, UNDP/UN Women and DRI.

Output Score and Description

A – Outputs met expectations. This reflects the fact that on the whole, output-level targets were achieved. However, the indicators were often unambitious and inadequate measures of whether or not the output itself was achieved. Scoring against the logframe therefore does not adequately capture all of the project’s strengths and weaknesses, nor does it reflect the extent to which the project’s performance was affected by factors outside its control, mainly related to the political environment.
More generally where the outputs (the ‘what’) met expectations, three recurring factors have meant that achievement was less effective than could have been:
First, the EU/joint donor evaluation noted that there could have been better coordination of ECP support by implementing organisations (IFES and UNDP) and donors. This affected project performance across the board.
Second, IFES’s approach was to position itself very closely to the ECP to gain traction. Whilst this had some real benefits, it also restrained IFES’ ability to advocate more independently and effectively for reform where there was ECP reluctance, and/or weak capacity.
Third, there are several examples across the different outputs of IFES substituting for ECP, for example: undertaking training of polling officials, writing manuals or procuring ballot boxes, rather than building ECP ownership, capacity and helping to embed reforms and thus sustainability.

Lessons and how these have been shared

Key Lessons Learned:
- The sustainability of SERP (and UNDP) achievements hinges on ECP’s ownership of the systems and processes promoted. Continued support for at least another electoral cycle, accompanied by demand-side support, is required for sustainability.
- Factors mainly outside the control of SERP prevented the project from delivering against all targets. These included weak political will and incentives for reform from Parliament and the ECP, delays in holding local government elections, and political uncertainty during the August – December 2014 protests which meant reforms were stalled.
- Including advocacy for reform in complex political contexts in the same project providing supply-side technical assistance may be counterproductive. To deliver, IFES positioned itself strategically close to the ECP. This allowed SERP to drive some ECP reform but, at the same time, it undermined IFES’s ability to advocate for reform outside the ECP and to some extent affected IFES’s ability to push the envelope on reform within the ECP. Greater access and dialogue between the ECP and donor and diplomatic community could have helped reinforce key reform messages, and shown support to the ECP when it came under criticism during the protests, by encouraging it to embrace the lesson learning and the opportunity to build on the reforms it had started. Future programming should take such risks into account and should support a more systematic dialogue between the ECP and the international community and partners.
- Advocacy for electoral reform should continue and be expanded, including outside ECP support. Given IFES’s need to maintain allegiance to a still reform-hesitant ECP, coordination of this advocacy should not be required of IFES but should belong with the main, higher-level advocacy support project. This will need a change in the Electoral Support Group (ESG) and of IFES’ role as secretariat, with supplementary mechanisms, such as like-minded donor meetings.
- Weakening supply-side cooperation and coordination affected performance post elections. The absence of a formalised overarching fund or associated governance features led to increased silo working. Coordination and effective cooperation between IFES and UNDP reduced post elections. This reduced project performance, led to duplication of effort, undermined programme effectiveness and ultimately, value for money.
- Significant ECP capacity had to be substituted (by IFES and UNDP) in preparation for the 2013 elections. This should be acknowledged as a realistic feature of a very difficult political and institutional context in which the project had to operate and is likely to remain true for future elections. It should therefore be build into future project design. That said, a joint IFES-UNDP strategic capacity development plan, based on a capacity assessment undertaken with full ECP ownership, would have provided a sounder basis for more sustainable capacity building in the ECP.
- Provincial and lower level field support needs boosting. Local government elections have been and are likely to continue to be sensitive and controversial and, thus, support to improve the supply side could have significant value in smoothing the democratic rollout in Pakistan. While this support remains essential at ECP HQ level, more operational support and capacity development is needed at the provincial level to improve future effectiveness.
- Gender and social exclusion remain critical areas to be addressed through clearly spelled out efforts in future support to and outside ECP to ensure inclusion of women, minorities and youth.
- Increased civic education efforts are needed outside the ECP and ECP assistance projects to complement the work of the ECP. Both voter and civic education efforts need to be based on pre-assessments, including in relation to CSO capacity development needs. Efforts need to be long-term and expanded – but not necessarily under the same project as support to the ECP.
- More effort is needed to foster high-level policy engagement with the ECP, to bolster advocacy for reform. This includes ECP consultations with political parties, civil society and the media, as well as better donor coordination. Whilst recognising that incentives for dialogue with partners and donors decreases in between elections, this is an important time to build relationships. Donors, IFES and the ECP all could take more responsibility for keeping the dialogue going. In addition, ECP decision making that does not appear to support election reform and capacity development needs to be documented alongside IFES’s specific input/advice, to inform donors of trends related to ECP reform and shape dialogue.
- Insufficiently strategic definition of outputs, indicators and risks led to the project not being able to always control effectiveness as per the defined logical framework. Future support should isolate discrete risks at both outcome and output level to better inform support strategies. The logframe should also reflect a more strategic approach to indicators, lifting performance assessment at a higher level.
- A mid-term review might have mitigated some project and coordination shortcomings. If undertaken for the overall programme after the May 2013 elections, it could have provided some remedial action that may have reduced coordination and collaboration weaknesses in the post-election period.
- A more politically nuanced and reflective approach is needed to support electoral reform in the medium to long term. It will be important to recognise and seek to address structural barriers and disincentives to reform including through more effective joint strategising and political dialogue with implementing partners, donors and embassies.
How shared:
Project-related matters have been addressed in SERP Steering Committee meetings. DFID annual reviews, the Impact Evaluation of SERP and STAEP, and this PCR were shared with IFES, and discussed with comments received. This PCR will also be shared with Policy Division (GOSAC).
Electoral reform advocacy issues have been shared in the ESG and sub-committee meetings more substantive discussions are needed going forward.
Within DFID, lessons will be shared with the DFID Pakistan Governance Group and more widely across the DFID Pakistan office and the FCO. As a joint donor funded programme it will also be shared with the EU and Canada and other relevant implementing partners. The lessons will feed into the upcoming scoping and design of DFID Pakistan’s Election Phase II programme and the Conflict Stability and Security Fund scoping and design.
C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved legal framework that ensures transparent electoral procedures that promote genuine and competitive elections
Output number per LF		1.1	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N (revised previously)

Indicator(s)	Targets	Progress
1. Number of new and revised regulations drafted with IFES assistance that improve the electoral process, and the number of these approved by the ECP	4 drafted (2 approved)	47 drafted; 37 approved by the ECP
2. Number of laws or amendments designed to improve credibility of elections that were drafted with IFES assistance and approved by the ECP, including recommendations that have been advocated for by local organizations with IFES support and by international stakeholders based on international standards.	4 drafted (2 approved)	48 amendments drafted; 38 approved by the ECP (including at least 6 EU EOM recommendations)

Key Points
Although the output targets have been overachieved, they are not very meaningful and do not give a holistic picture of the strengths and weaknesses. We have scored this output an A because:
1. Overall, IFES made substantial contributions to proposed legal framework reforms under the remit of the ECP (first indicator).
2. Its role in enabling reform outside the ECP (second indicator) has been less successful: the law is still not passed and does not meet international standards. However, this has been primarily (but not exclusively) for political reasons outside the project’s direct remit[8], and in our view reform outside the ECP should not have been included in the SERP logframe. In future there needs to be greater recognition by IFES, the international community, and other key electoral stakeholders of the role of complementary support to encourage meaningful and informed dialogue around electoral reforms to help embed reforms. This would require on all sides better collaborative working and joint strategising, building on the value added of all partners and understanding the opportunities and constraints faced be each e.g. civil society, donors, political sections of embassies, ECP, Parliament, IFES and others.
  [8] The EU/joint donor evaluation found that weaknesses in delivering this output relate to the fact that the project appears not to recognise sufficiently that, in Pakistan, the mandate for electoral framework reform belongs for the most part not with the ECP but with Parliament. Thus, the output was overly ambitious as well as relying on unrealistic assumptions, many of which should have been rather identified as risks.
SERP made substantial contributions to legal framework reforms despite weak ECP buy-in and legal framework inconsistencies limiting reform options. This contributed to the first historic handover of power from one civilian government to another
IFES was instrumental in supporting the development of Codes of Conduct issued by the ECP, This brought about procedural improvements for the 2013 general elections. Alongside other internal factors (including a significantly improved voter list attributable to IFES though mainly but not only before SERP) and a host of external circumstances, these are deemed to have had a positive role in enhancing confidence in the process, likely increasing voter turnout and reducing inter-party violence.
IFES also worked on unifying electoral rules. This helped the ECP respond to a Supreme Court Judgement,; flagged priority areas for reform; and worked with DRI (Supporting Advocacy for Reform 2012-2014) to feed recommendations into the Parliamentary legislative process. In preparation for the 2018 elections, IFES and the ECP organised an international conference on increasing the inclusion of persons with disabilities in the electoral processes and held consultative sessions on women’s reserved seat system.
IFES also assisted the ECP draft constituency delimitation regulations for Sindh and Punjab Government and cantonment authorities to revise electoral legal frameworks. This led to removing the restriction against non-Muslims competing for general seats on cantonment board; six amendments to the SLGA and 28 new/revised election rules.
However, it is important to note that the establishment of local government election framework takes place at provincial level, which is problematic as it fundamentally weakens ECP control over the administration process and allows for variations at provincial level in adherence to international standards. Even though the ECP has remained reluctant to call for increased legislative powers, IFES worked with the ECP to identify priority areas for harmonisation in local government election legislation and some standardisation is reported to have been achieved – although this extended only to non-controversial, operational matters.
In the post-election period, IFES was commendable in promoting reform through ECP internal processes
IFES was at the core of the ECP’s drive for a post-election review. This was a remarkable step in fostering ECP ownership of electoral process weaknesses and of a potential solid drive for furthering reform. Despite the fact that the process has not been adequately embraced by the ECP – and has even been partly disowned publicly by the institution because it has been perceived as too self-critical – such approaches are commendable, as they are required to enhance the sustainability of reform and consolidate the project’s outcome.
These are all highly positive contributions for the 2013 elections contributing to the first civilian to civilian hand over of power. However, these changes are not yet sustainable. They now need to be made more systemic and fully embraced and consolidated by the ECP.
Electoral framework reform outside the scope of the ECP and should therefore not have been included in SERP
IFES (and UNDP) worked with the ECP to produce a unified draft electoral law with many improvements adopted internally by the ECP support (26 amendments proposed by IFES). The submission to Parliament was however delayed and therefore was not enacted before the 2013 elections, which limited its impact. However, it is important to note here that electoral law reform belongs primarily with Parliament and not the ECP and, thus the scope of support should belong with associated and advocacy projects. This was recognised by the EU and DRI, in the form of two subsequent advocacy projects. While IFES flagged priority areas for reform and worked with DRI to feed recommendations into the legislative process in Parliament, SERP retained a similar law reform goal of its own.
After the 2013 elections, with IFES (and UNDP) support, the draft unified law has been updated for submission to the Parliament’s newly established (in July 2014) Joint Electoral Reform Committee. However, there remain weaknesses in the draft law which does not meet all international standards including, for instance, the safeguarding of observer access to the process - a primary transparency issue. There was also a lack of broader consultation with key stakeholders, including political parties and civil society. In this regard, IFES was not able to meet the 2013 annual review recommendations for enhanced ECP-stakeholder consultations.
Going forward, more systematic consultation will be important for creating broader buy-in, transparency and support for reforms and improved regulatory framework. The ECP with IFES and UNDP support, are encouraged to build on the past positive experience of consultations around the 2013 Codes of Conduct.[9]
[9] Consultations have taken place for the post-election review but not for the law drafting process.
Weak cooperation in promoting reform with other partners
Before the 2013 general elections IFES cooperated with DRI to support legislative reform in Parliament, and similarly with FAFEN on advocacy for reform. However, this cooperation has since weakened . This has not helped SERP encourage ECP to consult and enable comprehensive, meaningful reform. Going forward more focus is needed to support the ECP to engage more with Parliament, political parties and civil society as well as with the media to promote reform and ensure dissemination of factually correct information. In particular IFES is encouraged to be more proactive in helping strengthen the relationship between the ECP and FAFEN.
IFES closely aligned with the ECP, limiting independence and ability to promote reform
In hindsight, including law reform per se in SERP’s indicators was problematic given that, to deliver against the core of its objectives, IFES needed to retain allegiance to the ECP while the ECP was known to be reticent in promoting legal framework reform on its own. IFES positioned itself strategically close to the ECP. Undoubtedly this strategy allowed SERP to drive some reform –UNDP was able to do so too without such strategy. At the same time, it affected IFES’s ability to push the envelope to promote reform with the ECP and limited IFES’s ability to advocate for reform outside the ECP. For future support it may be better to separate these two aspects so that UNDP and IFES are positioned to advocate for more internal ECP reform whilst not having to pursue overarching law reform. IFES faced similar issues in its ability to engage in advocacy outside the ECP limited by its allegiance and, potentially, perception reasons alike.
Overall, as noted by all main observer missions, the elections fell short of a number of international standards, including in relation to ‘electoral dispute resolution system, candidate scrutiny process, gender equality measures, rules for observers, campaign finance, and results compilation and consolidation mechanisms, among others.’[10] These relate to both primary (law) and secondary (regulations) legislation. The (only) local government elections held in Balochistan (in December 2013) were reported by DRI (through a Local Government Elections Assessment) to have been ‘systemically weaker than the general elections,’ including in relation to the legal framework. While these elections were called within a timeframe that did not allow for framework changes, all other local government election framework assessments undertaken by DRI point to pervasive regulatory problems.
[10] NDI/ANFREL (National Democratic Institute/Asian Network for Free and Fair Elections) observer report.
Reform agenda potentially undermined by insufficient understanding of politically complex reform process requirements
A DRI/RSIL assessment of Pakistan’s overall electoral framework identified numerous areas of weaknesses and inconsistencies with Pakistan’s international commitments.[11] Neither the project document, nor the logframe include any references to ICCPR, CEDAW or any other instrument ratified by Pakistan.[12] This is surprising given the traction obtained by DRI in advocating for reform based on these commitments and the need to sustain and reinforce this traction – even providing a model to be emulated by the ECP. The same discussion is applicable to some fact sheets (see Output 2.2 below).
[11] DRI, Research Society for International Law (RSIL), Pakistan Election Laws and International Standards - A Reference Guide on Legislative Gaps and Vulnerabilities, Nov. 2013 (‘These include subjective candidacy criteria and the presence of a separate electoral roll for the Ahmadi community, a religious minority. Furthermore, there is a lack of legal provisions to safeguard certain commitments such [as:] Enhancing transparency of the election administration and electoral processes; Establishing administrative mechanisms for access to remedy; Availability of sex-disaggregated data; and Promoting routine consultations with groups representing women and Persons with Disabilities. Additionally, certain areas of election-related legislation were identified as vulnerable, where the law is weak and does not strongly provide for compliance with Pakistan’s international commitments. Strengthening the law in these areas could help prevent problems in administrative practice and demonstrate Pakistan’s commitment to improved democratic functioning, and strong commitment to fulfilment of human rights obligations. Among various issues detailed in this report; some key issues of vulnerability include the requirement for “presidential approval” in functions of the election administration and the overlapping of judicial and executive functions.’)
[12] Pakistan ratified the International Covenant on Civil and Political Rights (ICCPR) in 2010, the International Convention on the Elimination of Racial Discrimination (CERD) in 1966 and the International Convention on the Rights of Persons with Disabilities (CRPD) in 2011; and acceded to the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW) in 1996.
IFES produced useful fact sheets to facilitate understanding of electoral/reform concepts and issues. These, such the one on the Local Government: Balochistan could have been more informative if they had made reference to some of the shortcomings with regard to international standards thus strengthening the reform debate.[13] Similarly by agreeing to pilot electronic voting machines (EVMs) arguably to demonstrate also how these machines cannot be the solution to integrity problems, IFES may inadvertently be advancing their introduction which in the long run is risky. .
[13] The existing legal framework is described positively, without mentioning the critical need for an oversight role of the ECP in formulating legislation for a standardized cross-country approach. It describes the December Baluchistan 2013 elections as ‘successful, although the credible & evidenced DRI assessment (Balochistan Local Electoral Framework Assessment – LEFA) highlighted major weaknesses. By including factually correct but controversial provisions, the fact sheet misses an opportunity to support a more informed debate..
Missed opportunities to promote more reform
Given IFES’ strong relationship with the ECP and the high level of approval by ECP of IFES’ proposals, it may also have been beneficial for IFES to make more legislative reform proposals that may not be approved but may nevertheless help increase understanding of legal framework issues. In this vein, more concept notes on strategic positioning of the ECP in various scenarios and more engagement in this and general matters with the ECP Commissioners may have been useful avenues to consider.
Focus on delivering improved 2013 elections, necessarily detracted from long-term capacity development and sustainability
IFES was directly involved in the actual drafting of various legal documents. This has helped achieve the first immediate expected result of strengthened democratic legal framework but it detracted from achieving the second immediate expected result of strengthened electoral management capacity of ECP to conduct credible elections. Going forward this balance will need to be reviewed.

Summary of responses to issues raised in previous annual reviews (where relevant)
IFES had agreed to explore options for legal drafting capacity development in the post-election period, through training or mentoring. However, this has not happened either at Secretariat or province level despite obvious imminent needs.
Increased consultations with political parties in addressing the regulatory framework were also not able to be fostered under SERP.
IFES had agreed to explore ways to advocate for passage of electoral reform, including the draft Unified Electoral Law, by strengthening synergies with partner organisations, including DRI and FAFEN; and to continue to use ESG and the Election Project Implementers Committee (EPIC) as platforms for encouraging organisations to advocate for approval of legal reform proposals. However, while coordination with DRI and FAFEN took place before elections, the post-election period witnessed deterioration in the relationship between IFES and UNDP. IFES’ relationship with FAFEN and DRI weakened, too, although to significantly lesser extents. At the same time, DRI/IP3, FAFEN and UNDP have stepped up their advocacy efforts in the post-election period. As explained, IFES’ relationship with the ECP has rather prevented SERP from engaging in advocacy for reform (see also Output 1.2 below).
While targets have been greatly exceeded, the continued legislative shortcomings in core aspects of the electoral processes mean that overall score of A (output meets expectations) has been given. This excludes the second indicator from score calculations.

Recommendations for future programmes
Future project formulation should recognise that:
- the scope of support for electoral law reform belongs primarily with Parliament and associated and overall advocacy projects and that the ECP needs to be supported to engage more with Parliament, political parties and civil society in the reform process;
- that ECP assistance providers’ ability to engage in advocacy outside the ECP may continue to be limited in their efforts, for both allegiance and, potentially, perception reasons alike.
1. Project and logframe formulation should identify objective and realistic expected results and outputs that adequately support the theory of change. Indicators should remain measurable and, where possible, more qualitative. Pakistan’s human rights obligations should be included in the indicators. And risks should be identified more realistically, including political risks and project-internal risks, together with an associated mitigation strategy.
2. Future ECP support should also recognise the extreme difficulties inherent to striking a delicate but adequate balance between ensuring a close relationship with the ECP and pushing boundaries to achieve more meaningful reform. Finding this balance and at value for money may result in excluding advocacy for reform in complex political contexts from the project providing supply-side technical assistance. Both institutional allegiance and specific expertise would indicate the need to address these areas distinctly.
3. The ECP’s reluctance to advocate for meaningful reform on its own should be mitigated by fostering their understanding that a more transparent process would allow them to defend their action and to sanction, and that accountability brings along institutional credibility; and that separation of remits with the judiciary or the executive could pre-empt the ECP’s reputation being affected by third parties.
4. Consultations between reform stakeholders should be fostered and efforts should be made to mend relationships between the ECP and civil society and to enhance the ECP’s media profile.
5. ECP technical assistance providers should also recognise that directly driving legal drafting may trigger a problematic association with insufficient reform.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Coordination with international community for the advocacy of electoral reforms
Output number per LF		1.2	Output Score	B
Risk:		Low	Impact weighting (%):	5%
Risk revised since last AR?		N (revised previously)	Impact weighting % revised since last AR?	N (revised previously)

Indicator(s)	Targets	Progress
1. Scale of the outreach of ESG meetings per year	100 in 2013 / 100 in 2014	256 in 2013 / 152 in 2014
2. Number of times the electoral stakeholder speaking points are revised and officially endorsed by members	4	5

Key Points

The output quantitative targets were exceeded. However, these do not capture the qualitative aspects. IFES was initially successful in providing information to donors and the diplomatic community especially in the run up to the 2013 elections. However, an overall score of B is given because after 2013 this became technical and factual, overly focused on detail as opposed to key headline messages to support reform. This was reflected by a drop off in participation including of embassy representation as discussion was not seen as sufficiently relevant to the political context particularly during the 4 month of protests. This was an opportunity to discuss key reform priorities and communication messages to counter potential misinformation which risked undermining progress to date. . However, we also recognise that as with the previous output, IFES was placed in a difficult situation of having to deal with possible conflicting interests. Going forward it may be better that IFES is not placed in the position to coordinate advocacy efforts.

IFES was in a difficult position of both supporting the ECP and coordinating advocacy efforts from outside
This output was introduced after the first annual review in recognition of IFES’s work as secretariat to the Electoral Support Group (ESG)[14]. Owing to IFES’ professional approach, the ESG has been regarded as one of the most functional donor forums in Pakistan. In preparation for the 2013 elections the ESG was successfully used for coordinating advocacy action and (joint) speaking points for interested parties.
[14] The ESG is a donor and implementing partner group supporting electoral processes in Pakistan, which also serves as a technical and political information and analysis forum for the wider like-minded donor and diplomatic community and as a loose donor coordination platform. It was established as a successor to the (typical) UNDP-established Technical Working Group on elections, which had been discontinued upon the completion of the UNDP project in support of the 2008 elections. IFES offered to act as secretariat to the ESG and, since 2008, has played a major role in facilitating monthly meetings and ensuring its smooth operation, as widely recognised by all members.
The 2013 annual review emphasised that efforts to have coordinated messaging on reform would be of increased importance in the remaining part of the project as the period between elections is an optimal time for reform (when there is reduced operational pressure). This was important also given that the advocacy undertaken by DRI would no longer be complementing the work of IFES and others working with the ECP (as the main DRI advocacy project was completed in March 2014). Broad advocacy was necessary also because the advocacy continued under a separate but related DRI project (Improving Parliamentary Performance - IP3) was limited by its allegiance to Parliament.
However, the same reasons that prevent IFES from engaging too deeply in the reform debate appear to constrain its ability to serve as a close adviser to donors and the diplomatic community. In the post-election period, the ESG debate became increasingly technical and factual and decreasingly analytical and political; as a result, the participation of political affairs advisers decreased even though the 4 month street protests were related to both 2013 electoral problems and reform.
For IFES, its role as secretariat enables it to provide in-depth information about the electoral process. This is true: collecting pre-meeting information and making it available in a comprehensive manner has had its obvious benefits. On the other hand, at times the focus on technical discussion seemed to ignore the political context, and the opportunities and constraints for supporting reform. ESG members have been seen to raise more political issues and relevant implications for discussion. This was observed during the evaluation mission and raised by the vast majority of ESG members.
It is unclear whether these problems arose because IFES’ relationship with the ECP became stronger in the post-election period or because in the pre-election period the drive for delivering the elections did not require as much perception cautiousness.
These issues notwithstanding, it has to be noted that responsibility for the quality and ultimate effectiveness of the ESG meetings rests as much with the donors and implementing partners as it does with IFES.

Thus, with the advantage of hindsight, the recommendation in the first annual review to include coordination of reform advocacy efforts as a new indicator for the first output appears misguided given the politically sensitive context in which IFES was operating with the ECP. The second annual review acknowledged that coordination of advocacy efforts lacked depth but limited its recommendation solely to enhancing these. The EU/joint donor evaluation mission found that in the post-election period there was a marked regress in SERP’s ability to meet expectations as accepted by IFES through logical framework revisions. For this reason, that overall score of B (output moderately did not meet expectation) has been given.

Other responses to annual reviews
The recommendation to update the ESG website has not yet been acted on.

Recommendations for future programmes
1. Advocacy for reform is essential in the coming short- and medium-term period. A separate project should be put in place to continue DRI’s efforts. (While FAFEN has been successfully engaged in advocating for reform from a domestic CSO perspective, it is ideal that donors also fund an international project that brings international comparative expertise and neutrality value). This was recommended to the EU within the scope of a scoping for transitional EU support for 2015 – and there is a high likelihood for a new project to be funded bridging the gap to larger, multi-annual programmes to be scoped out by both DFID and the EU in the spring of 2015.
2. Advocacy for reform and coordination thereof should also continue in the ESG, but under a reformed structure, where IFES should no longer act as (permanent) secretariat to the ESG. Here, functionality should not trump substance and the ability to provide insightful, politically sensitive analysis to donors and other implementing parties:
- The coordination function should belong to the same organisation whose core remit is to support advocacy for reform. This would be respected by all implementing partners.
- Alternatively, the Secretariat function could be rotated on a six-monthly basis among implementing partners. This would provide an additional benefit of organisational capacity development for partners like FAFEN.
- In either case, the Chair function should also rotate on a six-monthly or yearly basis among donors providing core support to the electoral process in order to ensure ownership of the proceedings and build a relationship with the Secretariat for optimal, smooth but meaningful functioning.
- Organisations that do not belong in the ESG but that are important in relevant domains should be invited to present thematic issues or join certain debates.
- The ESG should not be regarded as a project coordination forum for the respective donors and implementing partners. Project-related donor and implementing partner coordination should be addressed specifically through a comprehensive structure that includes a multi-donor, multi-project governance board, including a distinct one for the supply side, as well as a separate donor group.
- Within as well as outside the ESG, donors and the diplomatic community should have unlimited access to advice and candid analysis from the implementing projects and this should be provided proactively.
In the same vein, IFES’ intention to engage in broader advocacy itself in the future may also need to be very carefully considered, in line with Recommendation no. 3/Output 1.1.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased professionalism and competence of election officials
Output number per LF		2.2	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N (revised previously)

Indicator(s)	Targets	Progress
1. The percentage increase in the performance of temporary election staff on election day as a result of IFES trainings	An average of 75% of PrOs and 40% of ROs performed their Election Day duties correctly during Pakistan’s General Election	An average of 83% of PrOs performed their Election Day duties correctly. Information not available for RO performance / Note: IFES reports that this figure is based on FAFEN’s Election Day Process Analysis but that when FAFEN published their report for the 2013 general elections they had removed all but two measurements relating to RO performance in the process, so the information in FAFEN’s report is not a reliable indicator of performance of the ROs. According to FAFEN’s Final Election Day report, a total 71,397 irregularities and violations in the day's proceedings were observed in a maximum of 38,274 polling stations observed.
2. Percentage increase in job skills and knowledge for the permanent ECP staff through the trainings supported by IFES	An average 15% increase in knowledge	An average 17% increase in knowledge
3. Number of permanent and temporary ECP staff trained with support from IFES	Total ECP Temporary Staff: 238,000 (15% female) / Total ECP Permanent Staff: 300 (33% female)	245,769 temporary staff (61,713 [25%] female) / 1,272 permanent staff (1,172 male and 100 female) 100% of female permanent ECP staff.

Although the targets were exceeded, the score of A takes into account the qualitative findings of the Impact Evaluation and the delays in rolling out training.
Key Points
Polling staff training undertaken on behalf of the ECP brought incremental improvements in polling operations and supported the electoral process altogether, contributing to the elections’ overall acceptance
Even though IFES (and UNDP) ended up substituting ECP capacity in training polling officials, this was an absolute imperative to be achieved given the vital political significance of the 2013 elections.
The polling staff trainings undertaken by IFES (as well as those undertaken by UNDP) brought incremental improvements to polling station operations, which is likely to have contributed to the elections’ overall acceptance.
 Nevertheless, on polling day there were a number of challenges and irregularities which were outside the control of IFES Evidence found by tribunals and observer reports, such as FAFEN’s, shows that serious irregularities occurred in polling stations due to for example last minute replacements of ROs & DROs.;[15] and that serious malpractices occurred in some areas due to ROs.[16] Indeed, the Impact Evaluation noted that polling staff underwent ‘sub-par training’ and that ‘[a]ctual election management on the day also mattered, but only insofar as polling day violations deterred already mobilised voters from actually voting.’
[15] EU EOM 2013 Final Report.
[16] FAFEN, 2013 General Elections – Observation and Analysis of Election Day Processes. Irregularities or violations of the legal proceedings were found by FAFEN in 55% of the Polling Stations. Similar findings were reported by ANFREL/NDI and supported by EU EOM.
This points to the need for sound ECP data on the performance of polling staff or the Returning Officers (ROs) on polling day so that the ECP can track improvments, and understand the problems and act to address them. This data was not available. Secondly responsibility for management of polling is deferred to ROs, who in turn are seconded from the judiciary, rather than the ECP itself. This represents a potential conflict of interest which needs to be addressed as part of the reform of the legal framework and strengthening the ECP’s independence and accountability.
Despite improvements, continued need for training and stronger ECP management and accountability mechanisms remain necessary
These problems indicate that further measures are needed to control the work of ROs, including different appointment modalities. FAFEN research and analysis found that, ‘in general, the polling officials received sufficient training to carry out their duties’[17] but that ‘the ECP should improve the training process for the next elections.’[18] Thus, whatever improvements there have been, continued need for training and stronger ECP management and accountability mechanisms remain necessary to mitigate similar problematic situations in future elections (particularly if results are overall less accepted).
[17] FAFEN, 2013 General Election Observation and Analysis of Pre-Election Processes.
[18] FAFEN, 2013 General Elections – Observation and Analysis of Election Day Processes.
The ECP agreed with UNDP (as backed by IFES)’s initiative to introduce the collection of gender-disaggregated polling data. However in practice this was not sufficiently realised with large numbers of polling staff failing to fulfil gender reporting requirements.
Effective training was limited by RO management decisions
IFES has driven the setting up of the Federal Election Academy (FEA) and prepared handbooks and materials as well as organised and implemented training for temporary officials (ROs, polling staff and for tribunals). This was based on a useful strategy that entailed piloting of different systems of cascade training during three by-elections in order to assess the most effective method for ensuring high quality. Based on IFES’ planning, training for polling staff was divided with UNDP on a geographical basis. Accordingly, IFES delivered training in Balochistan, KP/FATA and Sindh, whereas UNDP took the larger but single province of Punjab. IFES was responsible for printing training material.
IFES also provided training for Lead and Master trainers for election day training. As some of these trainers were included in the cascade training alongside the outsourced trainers, additional capacity development was accomplished. Achievements have been assessed through post-training questionnaires: ninety-one percent of Presiding Officer participants were reportedly satisfied with the training. IFES’s third-party monitoring of 27% of trainings was positive in providing a check on how later stages of the training were conducted. But the real test will be these trainers’ performance in ECP’s own training of polling staff in future elections, including by-elections. It is not clear whether IFES has yet used such evaluations.
IFES worked under time pressure with the ECP to develop and dispatch the District RO (DRO)/RO handbook for the Balochistan local government elections in December 2013. However, this was only in English, which according to DRI interviewees made it difficult to use, and there was no accompanying training.[19] DRI noted that this compounded the already problematic fact that the ROs were seconded from the civil administration ‘which resulted in accusations of partisan bias, [as the] lack of written instructions from the ECP left [parts of the process] open to subjective interpretation and inconsistent application.’ IFES also drafted the D/RO handbook for the local government elections for reserved seats in Balochistan and began the development of the DRO and RO/ARO handbooks for local government elections in KP.
[19] DRI, Balochistan Local Government Elections Assessment, January 2014
Both in the case of the general elections and the Balochistan local government elections, IFES activities appear to have been undertaken according to plan and have responded to ECP interests, but ECP and RO management decisions have limited the effectiveness of IFES assistance.
IFES (and UNDP) needed to substitute ECP capacity in providing polling staff training; the Federal Election Academy has not yet been embraced by the ECP
Even though it remains the case that IFES and UNDP provided the training rather than supporting the ECP in delivering it (although some ECP master trainers were involved), this is consistent with the project’s focus on immediate general election delivery needs and should be acknowledged as a realistic feature of a very difficult political and institutional context. It is important to note that Pakistan does not benefit from an obvious electoral down-time period where capacity development is easily enabled. This is due to the uncertain political environment which means there is a need to prepare, delay and prepare anew the conduct of already very complex local government elections. The question that arises regards the assumption in the project document (as well as in UNDP’s) that the ECP had the capacity to own institutional development measures and take on considerable operational tasks on its own – and pay for these from the ECP budget, too. The capacity development component of the project document – and the workplans – needs to be based on a comprehensive and realistic capacity assessment relating as much to issues of technical expertise as to those of organisational behaviour (responsiveness/accountability etc.) Whilst there are clear improvements, there is still room for greater ECP ownership of FEA and greater ECP involvement in and responsibility for training and capacity development to ensure sustainability and consolidation.
Capacity development was more successful at Secretariat than in the field; the approach to some capacity development exercises at field level could be strengthened
A number of BRIDGE[20] trainings were also provided to the ECP. These covered pre-election activities and other thematic areas (EDR; electoral systems and constituency delimitation; political finance; voter registration; election technology; external voting; gender and elections voter education etc.). These could have been more customised to the Pakistan context: adjusted to the capacity levels of the participants (e.g. Political Finance); increased trainings made available to the provinces earlier on., [21]
[20] Building Resources for Democracy, Governance and Elections (BRIDGE) is a global training curriculum for election administrators developed by the Australian Electoral Commission, UNDP, IFES, and International IDEA.
[21] This situation improved towards the end of the project (fall 2014) demonstrating IFES responsiveness to feedback.
At province level, only 23 male and three female staff received BRIDGE (i.e. substantive) trainings as most field staff were trained in job skills first. Coupled with the fact that IFES decided to use professional trainers rather than electoral experts to impart knowledge in the provinces, capacity development at field level lags significantly behind the Secretariat.
IFES and UNDP agreed that they would divide capacity development activities based on ECP’s hierarchy levels (with UNDP covering mid-level officers, including in the field, and IFES covering job-skills trainings for entry-level ECP staff in the field offices and workshops for senior ECP staff on specialised BRIDGE modules; and both organisations coordinating the delivery of skills trainings for mid- level officers at the Secretariat). This division of labour does not allow for leveraging the different comparative advantages of the different organisations and introduces the potential for mixed messages.
Capacity development in gender mainstreaming should be mainstreamed across the board and should not just be targeted at female
IFES conducted two trainings exclusively for female employees. There are clear merits in ensuring that female specific concerns could be addressed in these trainings and that all women could receive the training faster in a combined session. However, it should be carefully considered whether such approaches may not in fact reinforce segregation. This is especially valid as the bulk of the training content was gender and elections and job skills. It is therefore questionable whether women-specific issues could not have been addressed simply by extending a mixed training with specific sessions added separately, if necessary. Moreover, a basic but fundamental element of the gender mainstreaming agenda is for it to be driven by men. In the same vein, IFES also reports that many trainings and BRIDGE workshops have not been attended by any women and this includes trainings in the post-election period and, thus, not urgent. IFES could have explored the option of delaying such workshops until female ECP participation had been secured.
Scope of capacity development needs expanding
For instance, the ECP capacity needs includes areas which the programme did not tackle such as needs-based budgeting, international procurement (see output 2.4 below), improving cooperation with NADRA or enabling the ECP to obtain the civil registration dataset from NADRA[22] and enhancing consultations with political parties, CSOs and, the media (UNDP includes media relations in its plans but from a PR perspective). It also needed infrastructure upgrading which could have been addressed through a needs-based budgeting process.
[22] For instance, the ECP has had an ongoing dispute with NADRA over the civil registration dataset for the electoral rolls and it appears that NADRA refuses to provide it to the ECP without any legal grounds. When asked what support has IFES provided to the ECP in this respect, IFES commented that they would not advise the ECP to take legal action against NADRA because ‘the ECP should know that themselves.’ Such an approach does not build either the capacity or the confidence of the ECP.
Capacity development should expand beyond BRIDGE
More capacity development could take place through mentoring. This was recommended in the first annual review but SERP found it difficult to use such an approach because mentoring requires greater habitual presence at the ECP, including in the provinces. Advice and mentoring would be particularly effective in targeting capacity of the Commissioners on a more sustained basis. And more support is required for legal drafting skills development instead of drafting on behalf of the ECP.
Capacity development should build improved stakeholder relations
There is a clear need to improve the y poor relationship with stakeholders – and in particular with civil society watchdogs, such as FAFEN. However, the project was not able to foster meaningful consultations with stakeholders. In fact, the relationship between the ECP and FAFEN deteriorated after the elections. And even though FAFEN may have inadvertently contributed to this, IFES’ role was not to protect the ECP from FAFEN but rather to enable mending fences between the two. The ECP could be assisted to establish regular consultations with the political parties, civil society and open up – also more strategically – to the media.
Yet, valuable approaches to capacity and organisational development were developed but these were not captured by the logframe
Some of the capacity and organisational development that took place was not captured by the logframe. For instance, IFES’ support for the (UNDP-driven) introduction of tamper evident bags and the Results Management System, for instance, are good approaches of developing capacity – and instituting an integrity system. IFES also commissioned an electoral integrity assessment. The assessment itself served as a valuable tool for the ECP and electoral reform stakeholders, providing indirect capacity development to the ECP. Another example is, the study on women’s access to civil registration (see below) which led to action. Equally important were the strategic planning and the post-election review processes which helped the ECP assess its strengths, priorities and areas for improvement.
Undermining ECP ownership detracts from capacity development
More care needs to be given to developing ECP ownership. There are a number of examples where ECP ownership was limited which could have been avoided. These include: IFES co-signing and transmitting the letter announcing the launching of the second Strategic Plan; IFES (and UNDP) being mentioned as having assisted with the formulation of the Strategic Plan; and, most strikingly, IFES being mentioned as the assistance provider to the ECP in the state budget document for 2014-2017.[23]
[23] Federal Medium Term Budget Estimates for Service Delivery 2014-2017.
The indicators for this output had been revised following the first annual review to reflect also the mechanism through which election day training was provided, as this was a major contribution of IFES. However, as mentioned, the indicators do not reflect organisational development efforts (strategic planning or surveys into barriers to diversification of workforce, continued advocacy for the institutionalisation of gender mainstreaming etc.), which IFES did undertake and which constitute highly relevant and adequate building blocks for ECP’s institutional and technical capacity development, even if ECP’s ultimate ownership of these may not be clear. On the other hand, related to both ownership and capacity development, the practice of IFES participating in interview panels for the recruitment of staff (as was the case, for instance, with the Political Finance Analyst/Director for the Electoral Finance Unit (EFU) position) detract severely from ownership and should not be continued.
The definition of this output, too, may be too ambitious even though the indicators mitigate this. ‘Professionalism’ entails a degree of will, which is by default outside the control of the project.

Summary of responses to issues raised in previous annual reviews (where relevant)
IFES agreed to design monitoring and evaluation tools to measure the performance of the IFES-trained ECP Master Trainers.
In the post-election period, IFES encouraged the ECP to focus its energies on staffing policies, including recruitment for FEA. While FEA recruitment continues to lag behind, some progress has been made in other areas.
IFES also encouraged the ECP to take on a larger role in the provision of trainings of both temporary and permanent staff, specifically the training of polling staff for by-elections immediately following the general elections. However, the ECP remains reluctant to assume ownership of this duty, too.
IFES agreed to continue to work with the ECP to encourage recruitment and strategies for the allocation of in-house resources – particularly to FEA – to contribute to sustainable capacity building, including by seeking opportunities for cost sharing with the ECP for training activities. IFES has also started exploring ways to implement structural change with buy-in from ECP management at various levels. IFES agreed to work with cooperating partners to encourage the ECP to utilise its existing powers and assert its role to enforce codes of conduct, taking action against complaints and addressing electoral fraud, etc.

Recommendations for future programmes
1. A comprehensive capacity development plan should be formulated jointly with IFES, UNDP/UN Women and in partnership with the ECP. This should be based on a thorough preliminary assessment undertaken jointly with the ECP, as much as possible, to foster enhanced ownership over activities and facilitate measuring. Project design should recognise constraints to sustainability. Much more efforts should be dedicated and better approaches should be used for capacity development for PEC and district electoral staff and to facilitating the transfer of responsibilities to FEA. These efforts should expand beyond BRIDGE.
2. In future programming, the competence of permanent ECP staff could be attempted to be measured not only against trainings received – also because ideally future programming will include mentoring. As already recommended in the 2013 annual review, increases in capacity should be measured in actual performance milestones as well as using the preliminary assessment as baseline.
3. Increased focus on supporting ECP management of polling officials (as opposed to deferring this responsibility to ROs). For example through requiring training to be mandatory, record-keeping, routine supervisory checks, active investigation of possible problems arising, and responding to malpractices.
4. Future programmes should:
- increase training of polling staff in general as well as to provide gender-disaggregated data (as required for national elections and as pervasively recommended);
- use by-elections and local elections to promote ECP capacity development through increased ECP involvement in and responsibility for training of polling officials;
- document actions by the ECP that are or are not consistent with the ECP establishing its own capacity rather than relying on donors;
- use logical framework indicators that can measure all capacity as well as organisational development efforts.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved and accurate electoral rolls
Output number per LF		2.3	Output Score	B
Risk:		High	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N (revised previously)

Indicator(s)	Targets	Progress
1. Number of procedures to improve the management of the electoral roll developed by IFES and the number of these accepted by the ECP	4 drafted (2 accepted) (at least 1 procedure based on the recommendations of international observer missions including EU EOM)	5 drafted (2 that address recommendations by international observer missions) and 1 approved

Key Points

The score of B reflects the fact that the targets were moderately not achieved. However, the voter list was significantly improved ahead of the 2013 elections. Although most of these improvements were made by IFES before SERP, IFES’ role in helping ECP collaborate with NADRA definitely contributed.
Improvements in the voter list likely increased pre-election confidence in the process
As key informant interviews from DFID’s Impact Evaluation found, improvements in the voter list were regularly cited as one of the main improvements in the 2013 general elections.
IFES has been assisting the ECP to produce a significantly improved computerised, duplicate free electoral roll based on voters’ national identity card data and with photographs; however, the bulk of key improvements was made by IFES before SERP. On the other hand, the improvements generated in 2013 were also in large part attributed to the involvement and actions of NADRA (responsible for civil registration), and IFES, along with FAFEN, played a key role in supporting the ECP to open up its doors and work in positive collaboration with NADRA.
High quality IFES advice requires more ECP engagement
Under SERP, IFES produced concept papers for the ECP prior to the general elections, although there was limited engagement on these. In the post-election period, IFES submitted four highly relevant concept papers to the new ECP management responsible for the voter list. IFES also worked with the ECP to develop a Standard Operating Procedure (SOP) to regulate the voter registration process and updating the voter list, which was approved by the ECP, and which will help minimise the level of discretion given to registration officers by standardising the procedure across the country. Voter registration trainings were provided in this regard. These were accompanied by a specialised BRIDGE workshop,[24] where participants scored some of the highest increases in participant knowledge, possibly indirectly indicating IFES’s long-standing performance in this area.
[24] The ECP’s earlier door-to-door exercise (to allocate voters to the correct location) was subject to criticism by FAFEN. (“10 million citizens missing on the draft electoral rolls 2011,” undated)
As recommended in the first annual review, IFES conducted a German-funded survey on women’s CNIC registration to support conversations with the ECP and NADRA on coordinating efforts aimed at increasing the number of registered women (see also output 2.2 above).
Tremendous efforts toward cooperation with NADRA affected by lack of political will by NADRA
IFES deployed tremendous efforts to bridge the differences between the ECP and NADRA (to ensure that NADRA submitted the civil registration dataset to the ECP).IFES and the ECP should build on the post-election leadership change in NADRA[25] to create an institutionalized mechanism to create the voter list from the civil registration dataset so that there is a systematic process for establishing accurate and updated lists in the future.
[25] This change is highly politically controversial leading to concerns regarding NADRA’s cooperation with the ECP in the future.
Basic voter list data was not made available for the Balochistan local government elections, for example on the total number of registered voters. There is a risk that the voter lists will be controversial in any other local government election that may take place and in by-elections as there will have been a long gap in updating the lists since the general election. This is particularly valid for local government elections as also smaller constituency sizes mean that small inaccuracies in the voter lists can more easily affect the results.
Within this context where short-term improvements had a major impact, it is also important to recognise that further improvements and consolidation are critical for the strengthening of the electoral process. The voter list is critical to electoral integrity and confidence in the administration. The political ramifications of a problematic voter list can be seen from the 2008 controversies. Continued advice accompanied by advocacy are therefore important given the severe negative impact there can be and the time it takes to establish and update a reliable inclusive voter list. The same advice and advocacy are required for bridging the gap between men and women registering with NADRA to vote.
Note: Whilst there have been some clear short term improvements in the voter list which made a difference to the 2013 elections as outlined above, setting a precedent to follow and build on in the future, the ECP’s full acceptance of suggested procedures is beyond IFES’s control.

Recommendations for future programmes
1. Future programmes should continue to advocate for implementation of necessary advancements presented in IFES’ concept papers and also support advocacy by others, particularly in relation to the reform process taking place in Parliament. This could include advocating for legislating (including, if necessary and feasible, through a court procedure) a requirement for NADRA to provide the dataset to the ECP within specific timeframes relating to each set of elections. Advocacy with political parties and CSOs could be used to promote a sustainable solution while efforts should continue to be made to ensure better cooperation from NADRA. Research could also be undertaken to show the risks and problems arising if enduring agreed mechanisms for creating an accurate and updated voter list are not found.
2. Donors, the diplomatic community and electoral stakeholders, including the Parliamentary Reform Committee should be made aware of the current voter list problems timely and pro-actively. Update efforts should focus on female civil and voter registration, as well as on death record removal.
3. Should the ECP or NADRA be unresponsive to implementation of positive concepts promoted, it is recommended that future programmes consider alternative strategies for mitigating the existing risks and blockages. This could include political lobbying, advocacy and debate in the media and by civil society to help put the issues on the public agenda and galvanise momentum and ownership for reform.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Enhanced capacity of the ECP to conduct electoral operations
Output number per LF		2.4	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1. Number of electoral operations systems and procedural improvements proposed by IFES, and the number of these approved by the ECP	7 drafted (including one concept note on integration of gender in ECP’s operations) and 4 approved (at least 2 of the improvements will be based on the recommendations of international observer missions including EU EOM)	7 drafted, 4 approved, 1 in progress
2. Number of ballot boxes procured for elections through SERP	41,000 ballot boxes used for general and other elections	41,000 ballot boxes used for general and other elections

Key Points

Although the targets were achieved, it is worth noting that the indicators do not really reflect enhanced long-term capacity of the ECP to conduct electoral operations. ECP capacity to conduct electoral operations needs further consolidating and the ECP remains dependent on external support. This is not surprising given that the programme is coming up against deep structural and political barriers and disincentives to reform. Indeed, the Impact Evaluation found that SERP ‘was not effective in meeting many of its outputs related to improving the capacity of the ECP’ due to external factors as well as, to some extent, insufficiently assessed risks and incomplete indicators.

Nevertheless, there have been some improvements through SERP. The EU/joint donor evaluation found that IFES (together with UNDP/UN Women) laid the ground for systemic transformations in ECP’s organisation and operations – even if only some of these transformations materialised in concrete improvements in the integrity of the 2013 elections through no fault of the project’s. For example, SERP’s support to ECP organisational development, particularly strategic planning, the post-election review, and the integrity assessment, and efforts to improve women’s registration (survey) were important achievements that are not captured in the logframe. These now need to be built on.

ECP internal weaknesses and disincentives to pursue meaningful reform limited commendable IFES input
During the election year IFES supported the ECP with seven guidelines. Four were approved – on IDP voting, uniform voting/closing/results procedures for local government elections, appeals before Appellate Tribunals and the tribunal process. Three were not approved (candidate nomination scrutiny, out-of-country voting options, a complaints process handbook). These became controversial and the ECP’s lack of guidance and provision for consistency in candidate registration and for complaints was subject to criticism by the observer missions.
One of the keys to ensuring smooth operations lies with the ECP field structure, where capacity is lower than with the Secretariat, and with the ROs. As the Balochistan local government elections proved, there are still huge capacity challenges with the ECP to conduct electoral operations on its own.
IFES excellent proactive approaches were overshadowed by reactive or inadequate support
IFES commissioned an electoral integrity assessment, which served as a valuable tool for the ECP and electoral reform stakeholders (see output 2.2 above), including in relation to electoral operations. IFES also provided the ECP with IDP enfranchisement guidelines. However, these were produced reactively, as a result of Peshawar High Court’s order that the ECP establish polling stations for IDPs in the Jalozai camp. It was the ECP who took this requirement a step further, extending this right to all IDPs across the province, which shows ownership on the side of the ECP.
IFES also agreed to support the ECP in pilot-testing the introduction of Electronic Voting Machines (EVMs). While IFES has explained the pros and cons of such introduction, which is not recommended in the current context in Pakistan, the agreement to support this pilot introduction may in fact contribute to the EVMs’ approval and is not considered value for money. It may have been safer and a stronger advocacy method to refuse to support such an activity.
IFES procured supplementary translucent ballot boxes on behalf of the ECP. The ECP’s dependence on the international community for a basic predictable election commodity such as ballot boxes raises questions about the ECP’s capacity to plan for its own needs and of sustainability. By procuring ballot boxes for the ECP, IFES resorted again to capacity substitution, particularly when the EU/joint donor evaluation found that the Caretaker Government would have been able to authorise this procurement directly by the ECP through a fast-tracked procedure. The EU/joint donor evaluation assessed that this activity was not necessary, did not represent value for money and was not in line with the findings of the Evaluation of Donors’ Support for Elections in Pakistan 2005 to 2008 (Lincoln Mitchell and Adrian Morrice, July 2008). While the 2013 annual review found that procuring ballot boxes provided DFID/donor leverage on ECP reform, it is questionable that the ECP will have returned to procuring opaque ballot boxes to cover its supplementary needs or that this activity was able to enhance donor leverage.
IFES also supported the ECP in upgrading its infrastructure with IT equipment procurement and instalment. The same question remains whether IFES could not have pursued options for promoting an ECP procurement process, based on needs-based budgeting. In both cases, the ECP was not even involved alongside IFES in the procurement process. Again, this is an activity that is not assessable in the logframe.
There continues to be a lack of linking of constant and fluctuating ECP election administration costs to the federal budget and insufficient clarity over responsibility for the financing of local elections. As mentioned in output 2.2, IFES did not include needs-based budgeting assistance to the ECP in the project activities, despite acknowledging that it should consider this in the response to the annual review.

Additional responses to issues raised in previous annual reviews
IFES agreed to continue to work with the ECP to encourage recruitment and strategies for the allocation of in-house resources – particularly to FEA – to contribute to sustainable capacity building. IFES will explore ways to implement structural change with ECP buy-in. IFES undertook to work with cooperating partners to encourage the ECP to utilise its existing powers and assert its role to enforce codes of conduct, taking action against complaints and addressing electoral fraud etc.

Recommendations for future programmes
Future programmes should:
1. Continue to support the ECP by proposing improvements in key operational systems and procedures (based on lessons learned) and for local and by-elections; ensure that there is a close link between design/approval and supported implementation, possibly, among others, by involving the ECP field structures in the design process; and explore mentoring options, including at field level and through pilot projects.
2. Place greater focus on advancing ECP’s planning capacity and on securing state funding for basic election commodity items, unforeseen circumstances and, potentially, upgrading infrastructure.
3. Explore options for adapting ECP approaches to designing and modifying systems, possibly through increasing in-house capacity for drafting concept notes with international assistance.
4. Support the ECP in addressing issues of RO independence and consistency. Given that ECP interest in asserting itself more strongly, and in taking more responsibility for constituency-level actions, may be limited, explore options for achieving this through wider advocacy efforts.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened ECP capacity in the conduct of voter/civic education
Output number per LF		3.1	Output Score	B
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N (revised previously)

Indicator(s)	Milestones	Progress
1. Number of components in its voter/civic education plan(s) implemented by the ECP with the support of IFES	Adoption and beginning of voter education plan / 6 components of the voter education plan implemented, 2 of the civic education plan implemented; 1 civic education focal person appointed/designated	Adoption of the voter education plan and 5 major implementation steps taken. / 6 components of the voter education plan implemented; / a Voter and Civic Education Plan 2015 has been drafted, but not yet submitted to the ECP

Key Points

This output scores a B because the targets were moderately not achieved. However, this review questions whether the targets around civic education should have been included at all and argues that civic education should have been outside SERP’s remit.

Commendable support for ECP voter education not always reflected in indicators
For the general elections, IFES formulated the voter education plan, which covers inclusion of women and marginalised communities and a handbook for CSOs, both of which were embraced by the ECP (and IFES exceeded its target). It also supported the ECP in establishing a media centre, which is not reflected in the indicator and made constructive attempts to build ECP capacity on civic/voter education, through BRIDGE training on civic and voter education, which included a focus on the participation as voters and candidates of women and other marginalised groups.
IFES also used findings in its 2013 survey identifying barriers to civil registration by women in order to design for the ECP a well-tailored voter education campaign aimed at increasing relevant awareness among women, which would lead to improved civil and voter registration and ultimately enhanced participation of women in the electoral process. While this was highly positive in itself, it was also useful in terms of creating internal ECP awareness of strategic outreach options and approaches.
More efforts could have been made to foster ECP cooperation with FAFEN
However, IFES was not able to foster ECP cooperation with FAFEN, which volunteered to use its vast network to collect pamphlets from the ECP district offices and disseminate them at the grassroots level. The ECP’ unwillingness to partner with FAFEN to distribute ECP material indicates underlying problems with the ECP’s overall professionalism and ability to reform. It is not clear whether efforts to involve donors in this situation through a soft approach would not have been able to sow some incipient understanding of the need to improve cooperation and collaboration with FAFEN. This approach would have ideally taken the form of joint ECP-implementing partner/s-donors coordination mechanism but such mechanism was also not pursued through the project.
Limited impact of campaign for Balochistan elections
For the local government elections in Balochistan, again for time-constraints reasons, IFES also directly produced and financed the broadcasting of a TV ad that, although based on an ECP script, was reportedly approved by the ECP above the Secretariat management, directly with the Commissioners. DRI’s assessment of these elections also noted that “The low turnout and high number of invalid ballots for the 2013 general elections put an onus on targeted voter education initiatives. [UNDP] assisted the ECP in production of voter education posters and IFES with spots for the electronic local media. However their impact appears to have been limited with stakeholders generally unaware of any such initiatives.”
Significant ECP voter information and education efforts continue to be necessary
IFES conducted a survey to assess the impact of ECP voter education efforts, which concludes that 47% people had the information about voting procedures and how to mark the ballot paper and 39% have enough information on where and when to vote and that the more focus is required on other aspects of electoral process, including voter registration and candidacy and candidacy. These results are concerning and indicate that significant efforts continue to be necessary by the ECP as well as other stakeholders, including political parties and civil society. Both the ECP and IFES need to use the opportunity provided by the post-election period to amplify and target this campaign.
Gender-inclusive messaging was useful but had limited ownership
IFES also adapted voter education planning to cater for delays in other local government elections and, instead, focused on CNIC and voter registration for women. IFES continued providing recommendations to the ECP on ways to include gender-inclusive messages in their general voter education and outreach.
However, the plans and documents for the general elections were formulated in-house by IFES and centralised in Islamabad, even though before finalisation input was also requested from the field and from gender specialists. Even though it should be acknowledged that delivering fast was necessary to ensure the success of the elections, this remains another area of capacity substitution. Other weaknesses include that, in an effort to deliver fast for the Balochistan local government elections, internal ECP procedures were by-passed, as mentioned, allegedly resulting in the plans not being adequate for the local context. While this is difficult to verify, such approaches should be avoided as they ultimately detract from ownership and capacity development.

IFES voter/civic education planning substituted ECP capacity and duplicated UNDP efforts
It should be noted that this is a very non-controversial area of activity of the ECP, coinciding also with high personal interest of the outgoing ECP management. It should also be noted that this is an area where activities have been shared with UNDP but there is no formal strategy as to how activities should be divided between the two organisations. Instead, at the end of 2014, IFES began the process of developing an ECP Civic and Voter Education Plan for 2015, without coordination with UNDP. Claims that two organisations will ‘try to coordinate’ are not sufficient and both IFES and UNDP need to identify a clear mechanism to agree cooperation and a division of labour in the most effective and efficient manner (i.e. with most benefits for the ECP and voters and only secondarily for the projects).[26]
[26] Since December 2014 there has been consistent and firm messages for the need for better coordination and since February 2015 DFID and EU instigated a series of joint sessions to improve coordination and develop a shared framework between partners to tackle this problem
Civic education is not the remit of the ECP and should not be supported through the project
Likewise, while the merit of having coordinated messages for voter education is acknowledged, civic education is not the remit of the ECP. In fact, for the foreseeable future, there may be a conflict of interest in the ECP undertaking civic education. Civic education efforts are best conducted by organisations with expertise in governance as well as in public outreach. In addition to specialised capacity, their legitimacy should also rest in their neutrality. This is especially valid as civic education should also target significant improvements in the ECP’s attitude towards transparency, accountability and capacity development. It is thus not adequate that ECP support should include a civic education component undertaken under the same project (see also Output 3.2 below).

Recommendations for future programmes
1. Future programming should include increased focus on developing ECP capacity to provide voter education, rather than on delivery and should include working on ECP planning for costs involved and advocating for such funding.
2. By-elections and local elections should be used to promote ECP involvement in and responsibility for development and delivery of voter education.
3. Specialised voter education may be advisable to show any improvements the ECP is undertaking to mitigate against election fraud, in order to counter the on-going narrative of fraud in the general elections that continues.
4. Actions by the ECP that are or are not consistent with the ECP establishing its own capacity rather than relying on donors should be documented.
5. The participation of women (in coordination with organisations supporting gender equality) and other vulnerable groups should be increasingly promoted, as should specific targeting of the youth.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased voter outreach by local organisations
Output number per LF		3.2	Output Score	A+
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N (revised previously)

Indicator(s)	Targets	Progress
1. Number of voter/civic education campaigns conducted supported by IFES	+4 in 2013 / +7 in 2014	7 in 2013 / 8 in 2014 / 15 in total
2. Number of citizens reached by voter/civic education campaigns conducted supported by IFES	550,000	880,000 in 2013 / 69,660in 2014 / 949,660 in total

Key Points

This output scores A+ because the targets were significantly exceeded, particularly in terms of number of citizens reached. However, it is not clear whether this contributed to achieving the outcome.

Voter education campaigns reached large numbers of citizens, although more after the general elections

For the general elections, IFES supported the Center for Communication and Programs in Pakistan
(CCP) social mobilisation through students and Ulema, Mindmap and PAK Women voter education and advocacy for people with disabilities. The Center for Peace and Development Initiatives (CPDI) was also funded to manage the PakVoter website, although the website could not be launched before election day. Campaigns were varied in the mediums used, for example in working with religious scholars and social media. IFES reported that a minimum of 30,321 women were reached by the campaigns, which is a modest number relative to the total and to need (with over 11 million less women registered than men). IFES also noted that the actual number reached is likely to be much higher given that a significant number of women would have seen banners, heard radio campaigns etc.
In 2014, IFES conducted a voter education campaign for the local government election in Balochistan and a NIC/voter registration campaign across Pakistan including Balochistan, reaching in total 949.660 people. These campaigns used a mix of media (SMS, radio, cable and print) and continued the social media and PakVoter campaigns launched in 2013. With eight campaigns exceeding the initial target of seven for the entire project, IFES realised a much larger public outreach than initially envisaged. However, much of these achievements were post the 2013 general elections and they were not without weaknesses.
In 2012 IFES assisted DRI to establish the EPIC platform, but has not followed it up since the DRI project closure. And the Voter Education Group (VEG) meetings facilitated by IFES in 2012 and 2014 have also faded away in 2014.
The value of voter education lies also in its transformative and preventive dimensions

The engagement of a variety of CSOs in voter outreach is positive to avoid over-reliance on a few NGOs. The use of smaller local NGOs may also have particular use in addressing issues of severe under-participation by women in certain parts of the country – as long that is well correlated with local socio-political dynamics. According to the logframe both milestones were strongly exceeded. But the value of voter education lies also in its transformative and preventive dimensions, as the more knowledgeable about the process, the less likely voters are to be subjected to manipulation or to allow irregularities.[27] This value did not translate in significantly improved general elections or even in moderately improved local government elections in Balochistan. In any case, the logframe does not include any qualitative measurement of these activities and IFES has not been able to undertake one either.
[27] This is corroborated by the Impact Evaluation: ‘Key informant analysis indicates that rather than substantially supporting voter education, donor assistance may be more effectively utilized in promoting an overall improved electoral process in which there can be more confidence.’ (Hannah Roberts, op. cit.)
Summary of responses to issues raised in previous annual reviews (where relevant)

In its response to the annual review 2012, IFES agreed to continue to use EPIC and VEG as platforms for cooperation and coordination with implementing partners to ensure that broader lessons learned are integrated into IFES programming. However, this has not been followed through.

The 2013 annual review also recommended that civic and voter education campaigns be more targeted to women and other under-represented groups, adapted to local patterns of participation – and that on-going work in this area may be undertaken in regards to by-election and any local government elections that take place. The project responded well to this (see in the previous output and herein above) within the limits of the timeframe available.

Recommendations for future programmes
1. Extensive on-going support for civic education will continue to be required in Pakistan for the long term. Voter information and education should be supported as undertaken by the ECP and thus within the scope of support to the ECP, whereas civic education should be supported outside this.
2. More consistent efforts and joint strategizing are need to leverage expertise and reach of partners like FAFEN in the area of voter education, using valuable observer findings for useful campaigns.
3. Both types of support should be based on a comprehensive needs based strategy and a CSO capacity assessment to target different needs and leverage their comparative advantages for more meaningful future engagement. This also requires extensive coordination with the myriad efforts supported by multiple donors in Pakistan, including in relation to local government elections. Coordination will be even more relevant for voter education, including for by-elections and any local government elections that may take place.
4. Civic and voter education campaigns should be more targeted to women and other under-represented groups and adapted to local patterns of participation. Youth is also an important segment of the society that needs to be increasingly targeted in both civic and voter education.
5. Voter (as well as civic) education efforts should also be able to be assessed in terms of quality and not only quantitative reach.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

DFID covered 40% of the overall programme budget $8m out of a $20m. Despite exchange rate fluctuations, IFES spent 99% of the DFID allocated funds. Since DFID’s funds (unlike the EU) were not earmarked, DFID’s support was able to cover all line items in the budget ensuring, flexibility, continuity and effectiveness.

The shared donor coordinated funding and reporting mechanisms allowed for streamlined reporting and significant transaction cost savings. It also meant IFES ensured some cost-sharing benefits across the donors whilst also implementing a longer-term and more comprehensive programme.

The following table shows actual expenditure against the original budget. It is important to note, however, that this only covers DFID’s portion of the project. DFID funds were not always used proportionally across all budget lines, so an analysis of VFM that focuses only on use of DFID funds may be incomplete.

	Budget	Spend	Difference
International staff	1375952	1807885	-431933
Local staff	1492736	1477264	15472
Consultants	918557	395148	523409
Travel	436657	546102	-109445
Furniture, equipment, supplies, office expenses	482798	538961	-56163
Commodities (programmatic)	743200	231774	511426
Sub-grants (programmatic)	779080	1371732	-592652
Special event expenses	750552	597749	152803
Other	75245	224538	-149293
Total Direct	7054777	7191153	-136376
Project Administration	945224	862938	82286
TOTAL	8000001	8054091	-54090

The key cost driver is clearly wages and benefits for international and national staff. On the latter, IFES has spent more than envisaged. This is due in part to more use of in-house IFES technical advisers than originally envisaged, which is balanced by equivalent savings under the Consultants budget line. IFES have also spent more than envisaged on sub-grants, which IFES explain is due to sub-contracting CTC-ECI to conduct cascade poll worker training prior to the 2013 elections.

VfM performance compared to the original VfM proposition in the business case

N/A

Assessment of whether the programme represented value for money
Economy
Based on the figures in table 1 above, it is hard to calculate overhead costs as a proportion of the total. For instance, given that IFES used in-house technical advisers, we do not know what portion of international and local staff costs should be included in overheads, and what proportion were genuinely externally facing, providing programmatic inputs of benefit to the ECP. As per the DFID grant terms, a 12% overhead was applied to the total direct costs. However, we estimate that overhead costs including staff salaries for this project were between 25% and 55%, which is clearly very high but only slightly higher than envisaged in the original budget. This will need to be reviewed carefully for any future support.
Efficiency

At contract stage, as a jointly funded programme, it was agreed that the SERP programme budget be broken down based on a comprehensive budget template of programmatic and operational line items rather than an output based structure. It is therefore very difficult to assess efficiency since we do not know costs by output. Nevertheless, based primarily on SERP’s achievements, our assessment of the project’s efficiency and VFM at output level is mixed.

Output 1.1: Support to the legal framework for electoral processes within the ECP is likely to have represented good VFM. The value of having Codes of Conduct was high (especially given the human, political, security/stability and economic costs of electoral violence that they may have contributed to preventing), while the cost of developing them is unlikely to have been significant. By contrast, support to the legal framework enabling reform outside the ECP represented poor VFM: the laws are still not approved and lack in substance. IFES added limited value and its inability to cooperate with DRI and close alignment with ECP may have contributed to the law’s limitations.

Output 1.2: This output may have represented reasonable VFM until 2013 because it achieved strong coordination of donors (both technical and political sections of embassies), but value to donors subsequently decreased as IFES became increasingly technical / factual and less analytical / political. Given the close involvement of the IFES Country Director in the ESG Secretariat, the cost of delivering this output would not have been insignificant, so VFM is likely to have been poor.

Output 2.2: We estimate the cost of training to have been £7.86 per trained polling staff. Our assessment is that the training undertaken by IFES and UNDP brought incremental improvements to polling station operations, which in turn contributed to the elections’ overall acceptance. On that basis, the training of polling staff provided good VFM, even if at times IFES had to substitute for ECP capacity. By contrast, the approach to training ECP staff appears to have been sub-optimal from a VFM perspective, with BRIDGE training not customised to Pakistan, not adjusted to participants’ capacity levels or needs, and undertaken in an ad-hoc, uncoordinated and duplicative way (in competition with UNDP/UN Women) that undermined ECP ownership.

Output 2.3: Without disaggregated data on spend by output we cannot calculate cost per voter registered. Even without cost data, however, the VFM for this output is likely to be good given that improvements in the voter list were so critical to increased voter confidence in the process. Although not all these improvements are attributable to SERP, IFES’ role in helping ECP collaborate with NADRA did contribute. If the agreement between ECP and NADRA is formalised, allowing the ECP to have access to a continuously updated electoral roll, the VFM of SERP’s intervention under this output will have been high.

Output 2.4: The narrative in section C suggests that activities funded under this output, in particular pilot testing of EVMs, procurement of ballot boxes and IT procurement, did not represent good VFM. The assessment of ‘how’ this output was delivered is also negative, with more examples given of duplication with UNDP and capacity substitution. Even if SERP laid the ground for systemic transformations in ECP’s organisation and operations, ECP strategic and operational capacity did not change notably over SERP’s lifetime.

Output 3.1: IFES undertook a number of useful activities under this output, but these were not measured or reflected in the logframe so it is therefore unclear to what extent they contributed to the output of strengthened ECP capacity, or to successful voter education. On the former it appears that once more IFES often substituted for ECP capacity, and on the latter IFES found that despite voter education efforts, only 47% of people had information about voting procedures and only 39% had information about where and when to vote. This suggests that this output represented poor VFM.

Output 3.2: If we take the data at face value, it appears that through its sub-grants to local organisations, SERP was able to reach a total of 70,540,000 people, at a cost per citizen of less than £0.012. This calculation excludes the costs of IFES management and oversight of the sub-grants, which are likely to be significant, but given how many more people were reached than originally envisaged, it is safe to conclude that the VFM for this output was good, and certainly higher than originally envisaged.
Effectiveness

Our assessment of overall programme effectiveness and of VFM at outcome level is more positive. This is because many of the project’s activities and actual outputs are poorly captured by the logframe.

With SERP and other support, the ECP has undertaken many reforms, including the introduction of monitoring committees, codes of conducts for electoral stakeholders, training for temporary election staff, and a nomination booklet for contesting candidates, a comprehensive voter education plan and improved arrangements for internally displaced persons. Many of these improvements were highlighted in the media and helped improve voters’ trust in the electoral process. This may have contributed to increased voter turnout, although attribution is very difficult to demonstrate.

Ahead of the 2013 General Elections, IFES worked with the ECP and UNDP to conduct training for polling staff across the country. Although the value was short-term and the benefits unlikely to be sustained, these trainings present value in contributing to a relatively improved process for the general elections, which ultimately enabled a peaceful civilian transfer of power.

SERP’s effectiveness and VFM with regards to ECP capacity development are poor, with such assistance and activities essentially deferred by the ECP until after the general elections and continued lack of genuine ownership by the ECP over the agenda. It has to be recognised that some of this is due to structural barriers and political disincentives within the ECP and very difficult to tackle. However, a more politically nuanced approach that recognised this and built strategies to support institutional reform and create incentives for change may have helped mitigate some of the risks better. Equally this was compounded by delays and weaknesses in IFES’s approach to capacity development in the field, and many instances of capacity substitution. For instance, the procurement of ballot boxes was meant to reinforce integrity but it is questionable from a value for money perspective. There is no intrinsic value in purchasing ballot boxes while the extrinsic value (i.e. donor leverage) is not evident. To this day, the ECP remains unable to organise elections without external support. The ECP’s performance in the Balochistan local government elections shows the need for sound documentation and independent assessment of performance in order to verify the extent to which the ECP has been effectively using the support from IFES and UNDP/UN Women. Clarity on shortcomings may then be used as a basis for political messaging for reform to prevent further problems.

That said, since the 2008 elections, there has been an appreciable evolution in the ECP’s view of training and capacity building. By consistently demonstrating the value of training and capacity building, IFES has helped change the mindset of the ECP on the subject. The ECP leadership proactively has started to request support from IFES to help conduct training activities that routinely involve ECP trainers. The ECP now sees training as an integral part of election operations, since trained temporary staff perform their election duties better than untrained staff. Although this has not yet translated into enhanced capacity of the ECP, the building blocks are there for any further support to be more effective in this area.

Although the efficiency of IFES’ sub-grants to local organisations for voter education was highlighted above, this support was not shown to be effective in translating into increased turnout, a significantly improved general election or even a moderately improved local government election in Balochistan.

Quality of financial management during programme

Date of last narrative financial report	30/12/2014
Date of last audited annual statement	30/4/2014

IFES spent 99% of the DFID allocated budget £5.5m out of a total of £5.68m, managing exchange rate fluctuations well. IFES consistently provided timely quarterly and annual technical and financial reporting with accurate quarterly and annual forecasting against the agreed budget template of programmatic and operational budget lines. IFES also provided good financial oversight and due diligence for awards of sub-grants. IFES were always responsive to additional information and explanation requests about costs and or programme activities.

IFES corporate policy regarding procurement of goods and services is based on regulations of United States Government (USG). It also takes on board donor policies, rules and regulations governing the accountable grant agreements. IFES’ procurement principles conform to parameters of the procurement guidelines as outlined in DFID’s Blue Book, Section D, and UK procurement policies. Where procurements are intended for international use for overseas programme implementation, IFES comply with the principles of Value for Money.

IFES procurement activities adhere to following principles:
1. Full and open competition
2. Fair and reasonable price
3. Fair and objective evaluation of offers
4. Responsible suppliers
5. Documentation

IFES regularly reports the process of all major procurements completed in the quarter in SERP quarterly progress report.

Under the accountable grant agreement IFES is required to carry out external audit of SERP funding. The 2014 audit report covering 2013-2014 reporting period was received on time. This report did/not have any -observation regarding misuse of funds. IFES is a well-established and credible partner with sound financial and due diligence systems and practices in place. The next financial audit report is due in April 2015.

IFES report that for procurement of consumables to be provided over one calendar year, annual market research is conducted. Major procurement actions conducted under the project included ballot boxes, poll worker trainings, establishment of long-term blanket ordering contracts, and post-election review workshops. IFES report that procurement activities adhere to principles of 1) full and open competition, 2) fair and reasonable prices, 3) fair and objective evaluation of offers, 4) responsible suppliers, and 5) documentation. A minimum of three formal quotes are collected for each procurement action, in accordance with an advertised request for quotations (RQF).

E: RISK (½ page)

Quality of risk management over the life of the programme
The political context in which the project was established created unavoidable risks for the project’s performance and sustainability. This meant that
1. the level of ambition, as defined in outcomes, outputs and indicators had to cater for the context,
2. sufficient mitigation measures needed to be put in place,
3. that reporting, analysis and information sharing needed to describe real achievements and potential for failure/underachievement and threats to sustainability.
This was not the case. Although the project document defined three main components/results and related outputs to be achieved these did not correlate with potential risks.
The risks identified included donors’ potential association with elections that are not credible, the potential for jeopardising sustainability in the absence of donor pushes for cost-sharing (e.g. for training), lack of coordination between donors and implementing partners and the potential for early elections. These did not include the more political risks inherent to Pakistan’s context.
Instead, project and logframe formulation identified evident risks as assumptions and failed to recognise sufficiently that, in Pakistan, the mandate for electoral framework reform belongs for the most part not with the ECP but with Parliament. This led to underachievement in the first component (strengthening democratic legal framework). Unwarranted assumptions include that the political will for reform existed within the ECP; that Parliament would pass amendments to legal framework incorporating observer recommendations and in a timely fashion; that the ECP was willing to engage with stakeholders and to fund training of temporary staff, to approve and implement proposed procedures etc.
The project also relied on the assumption that NADRA and the ECP would continue to collaborate. This was a fair assumption at the time of project formulation and despite its lapsing; IFES has made significant efforts to remedy the situation.
The project also did not foresee significant delays in holding local government elections but, instead, maintained throughout 2014 the risk of holding (any, including local government) elections too early. Moreover, in its progress reports, IFES appears not to fully acknowledge the need for holding local government elections, linking the ‘driving force behind’ it solely to ‘insistence by the Supreme Court’s [former Chief Justice Chaudhry]. This indicates that SERP may not sufficiently understand the political context in which it operates or the higher governance and democratic advancement needs of the country. This is another reminder that IFES may not be best positioned to coordinate advocacy for reform.[28]
[28] As comments to this report, IFES claims that different messages have been communicated regularly in by-weekly reports and ESG and Steering Committee meetings, a review of which falls outside the scope of the SERP evaluation. Beyond the minimum requirement to revise the project’s overall risk log, SERP could have undertaken more analysis/mapping of the likely emerging political scenarios and evolving political environment.
As most of the risks to the project are political, the insufficient ability to foresee these, points to an underlying inability to plug the project solidly in the political context. This, in itself, is a risk in such a fragile and fluid context like Pakistan’s.
No project-internal risks were identified, either, including over budgeting or factors leading to underspending. This notwithstanding, owing to inbuilt flexibility, IFES was indeed able to adjust its course by reorienting activities when necessary. Nevertheless, this resulted in maintaining spending levels on target from DFID funds but, highly problematically, underspending massively (in excess of 50%) from EU funds. This was due in part to over budgeting and in part to insufficient HQ experience in working with donors other than USAID. Moreover, this may also be due to the absence of joint workplans with UNDP.
Perhaps this could have also been mitigated by speeding the rollout of capacity development in the post-election phase through facilitating international expertise to the provinces instead of using professional trainers that needed first to undergo their own electoral capacity development, thus creating delays. Another option could have been to invest in promoting and facilitating an audit of the voter list. IFES could have also considered commissioning a study to identifying options for moving the voter list process forward with or without NADRA. This is particularly important in diminishing risks for local government elections should they take place.
The project also did not recognise that the inclusion of UNDP in the support package would pose some risks to coordination and overall effectiveness and, hence, did not put in place any mitigation strategy. This led to duplication of activities and a clear potential for confusion of messages and providing undesired opportunities for the ECP to leverage competition negatively.
On the backbone of not foreseeing ECP’s unwillingness to reform sufficiently, another main risk not identified by the project was that the desired close relationship with the ECP could pose perception threats to IFES’s image as a neutral advocate for reform. In fact, the inherent nature of IFES (and to a large extent, UNDP)’s engagement with the ECP hampered in the post-election period IFES (and UNDP)’s ability to forcefully advocate for some/reform issues outside the ECP. But while UNDP maintained some distance to the ECP, IFES’s closeness to the ECP has started hampering even its ability to push the envelope with the ECP. Compounded by the competition with UNDP, this also affected considerably IFES’ role to coordinate advocacy through the ESG. Acting as secretariat to the ESG while being perceived as too closely associated with the ECP has also led to limiting donors’ and the diplomatic community’s access to politically sensitive information on reform. This was also compounded by the fact that IFES’s role in the ESG exceeds that of a usual secretariat, extending into responsibilities that belong commonly to the forum’s chair.
The project should have updated its risk log more comprehensively, to include more political risks and a mitigation strategy.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The project benefitted from a flexible implementation arrangement, which allowed it to navigate some risks and increased its effectiveness. The political context imposed that workplans remain fluid – but this should have not pre-empted drawing flexible joint plans with UNDP.
Some delays in delivery were caused solely by external factors (e.g. indefinite delays in holding local government elections) while others, by the project’s strategy of choice (e.g. approach to expanding capacity development at province level).

Performance of partnership(s)
IFES’s reporting has been exemplary in terms of issues covered, extremely efficient turnaround timelines and frequency (by-weekly, monthly, quarterly and annually). However, reporting lacks sufficient self-criticism as well as sufficient clarity regarding joint achievements with UNDP/UN Women.
The Impact Evaluation covered IFES SERP and the FAFEN STAEP projects and lessons learned are intended to feed into the Voice and Accountability Group and DFID (and other donors’) future electoral support including through the CSSF .
Within DFID, lessons will be shared with the DFID Pakistan Governance Group and more widely across the DFID Pakistan office. This PCR will also be shared with Policy Division (GOSAC).
DFID also participates in the ESG, which is meant to allow for sharing of substantive, political information and identify advocacy synergies.

Asset disposal and value obtained by DFID

The project has been extended with CIDA funding until mid-2016 with effective and efficient transfer of assets for programme continuation

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Annual reviews, beneficiary feedback a DFID elections evaluation and the joint EU donor evaluation were undertaken during the life of the programme.

The SERP logframe was revised based on annual review recommendations. However, the project document was never revised to account for the introduction of UNDP. Thus, the initial logframe, which followed the project document, has remained tight despite revisions. In fact, only some revisions have been beneficial (e.g. streamlining outputs/outcomes). Instead, others did not take the context sufficiently into account and have placed inadequate burdens on IFES’s ability to deliver (e.g. coordination of advocacy for reform). Yet others have not added any value to the project of the donors’ money (e.g. purchase of ballot boxes).

The EU/joint donor evaluation notes that scoring against the indicators as defined in the logical framework does not always reflect IFES’s intrinsic performance. For instance, outstanding approaches to the ECP’s organisational development (strategic planning, post-election review, integrity assessment) or efforts towards gender mainstreaming are not captured at all in the scoring, even in terms of technical capacity development. In parallel, weaknesses in approaching some activities or in identifying considerable risks adequately are also not assessable in the framework. This is a general problem arising from the need to quantify progress in qualitative, political processes, which the annual reviews attempted to correct only to some extent.
The findings of this evaluation will feed into the EU and UK’s (and potentially other donors’) formulation of multi-annual electoral support programme/s to be initiated end 2015/beginning 2016. This should include a specific focus on a shared strategy, joint M&E framework and a governance structure to foster mutual accountability and collaboration.

See also E. Risks and F (Performance of Partnerships) above.

Monitoring progress throughout the programme
IFES carries out monitoring and evaluation of its programme activities. This includes the pre- and post-tests of trainings support to ECP officials. For sub-contracts, IFES outsources the M&E function to third party monitoring/survey companies and findings of these reports feeds into the quarterly progress reports. However, more evidence is required to evaluate the qualitative aspects of voter education and to document ECP’s uptake of technical advice.
IFES has not undertaken any internal project review during the course of SERP but has regularly provided reports (bi-weekly, monthly, quarterly and annually) to donors. These reports are extremely thorough and timely but they do not always account for distinct IFES vs. UNDP efforts and they are intensely activity-oriented, which inherently dedicates more space for input compared with immediate or overall outcome.[29] To some extent, this type of reporting may also be driven by the logframe design although this alone should not prevent more political, analytical or introspective narratives. Additionally, in the absence of sufficient introspection, the level of detail provided is also unnecessary, perhaps leading to information overload, whose added value (for either the project or the donors) is not discernible.
[29] For example, the 2014 Annual Report states in one section that ‘The revised unified law, developed with IFES assistance, will ensure improvements to the legal framework if it is adopted by the legislature,’ without providing any qualifications or caveats, while in other sections it clarifies that the draft law falls short of sufficient integrity measures etc.
These findings are supported by the 2013 annual review, which also recommended that reporting be strengthened to more clearly identify:
- Attempts made by IFES to undertake activities focused on reform and self-sufficiency/sustainability, and ECP responses, including any negative response and reasons for this, in order to better understand ECP interest and ECP and IFES effectiveness in this critical area.
- Increased focus on the risk log to record a greater number of risks, including to individual activities and the electoral process overall.
- Increased information on problems and shortcomings encountered and reasons and measures being undertaken to prevent recurrence.
- Coordination being undertaken with UNDP and others working with the ECP.
While some progress could be seen with regard to the first and third recommendations, the ones related to the risk log and coordination do not appear to have been sufficiently followed through.
Coordination deserves special attention in relation to SERP. The 2013 annual review noted that there were coordination problems between IFES and UNDP and recommended that coordination between IFES and UNDP increase so that there can be coordinated messaging and actions and mutual learning; and that IFES keep UNDP fully informed of IFES actions and invite comment and involvement.
The EU/joint donor evaluation noted that IFES has made valuable attempts at coordination during the initial phase of the project (pre- and election period), including by sending the two UNDP Chief Technical Advisers pre-arrival information packages containing IFES documents. Regular meetings used to be held, albeit on an ad-hoc basis, but these have all but disappeared in the post-election period – ostensibly on grounds of professional competition between the projects. This competition is seen to extend to FAFEN and possibly, even DRI/IP3, although to a much lesser extent. While this type of reluctance to cooperate has been seen in most contexts in which IFES and UNDP provide electoral assistance jointly, this does show a lack of understanding of organisational remit or that elections are not commercial processes where intellectual property rights are important. In fact, electoral processes are support areas where significant documentation repositories can be found publicly/online (IDEA, Ace project (which includes contribution by IFES), IFES’ own website, NDI’s website etc.).
As mentioned, while the inclusion of UNDP in the support package was both requested by the ECP and meant to leverage on comparative advantages, insufficient acknowledgment of the need to coordinate ECP support systematically contributed to unnecessary competition between the two organisations. This affected project performance to some extent and even IFES’ ability to advocate for reform outside the ECP (where it actually takes place). This was compounded by the fact that, in order to get traction with the ECP, IFES’s approach was to position itself very closely to the ECP while the ECP’s reputation has remained rather opposed to advancing reform. In fact, this closeness has started to affect IFES’s ability to promote reform even inside the ECP.
It should also be mentioned that the ESG is a donor and implementing partner information and analysis sharing and (loose) coordination platform and not a project coordination forum.
These issues notwithstanding, it should also be noted that responsibility for the quality and ultimate effectiveness of the ESG meetings rest with the donors, too, perhaps even more so than with IFES or other participating implementing partner/s. IFES has repeatedly raised coordination issues with donors, in meetings as well as in reports.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process