Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	31/03/2015

Title: Support to the International Centre for Trade and Sustainable Development
Programme Code: 203524	Start Date:10/12/2012	End Date:31/12/2014

Summary of Programme Performance

Year	2013 (AR)	2014 / (PCR)
Programme Score	A+	A+
Risk Rating	Medium	Medium

Financial Position

Original Programme Value	£5,150,000
Extensions/ amendments	N/A
Log-frame revisions (with dates)	ICTSD updated its overall logframe for period 2013-2015 which was used as basis for 2013 AR and for this PCR
Total programme spend	£5,124,970

Follow up actions required following closure

None. New business case for further phase of support (£8.5m over 5 years, 2015-19) was approved in October 2014. Recommendations to be taken forward as part of that programme.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203524/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203524/documents/

Outline of programme and what it has achieved

Over a three year period (2012-14) DFID provided a grant of £5.1 million to the International Centre for Trade and Sustainable Development (ICTSD), building on earlier phases of support since 2000. Our support constituted around 30% of ICTSD’s funding, other key donors being Sweden and the Netherlands.

ICTSD is a Geneva-based independent think-tank and knowledge broker. It plays a critical role in providing information and impartial, evidence-based advice to developing countries, to help them to understand developments in international trade, formulate effective trade policies, and negotiate more successfully in trade talks. Along with contributions from other donors, the funds contributed to ICTSD’s core costs. They were used to monitor events in international trade which affect developing countries, carry out independent research, and share information with partners.

Over the period of our support we expected to see increased participation in regional and global trade by developing countries. This is essential to drive economic growth, create wealth and jobs for men and women. Our funding allowed ICTSD to continue expanding its established work-streams which contributed to delivering the following results as set out in the original business case:
- Increased and more effective participation by developing countries in international trade negotiations
- Better food security for developing countries;
- Developing countries better able to advance their development priorities in aid for trade and multilateral trade negotiations;
- Developing countries better able to innovate, and access technology;
- Domestic policies that promote climate change mitigation and adaptation;
- Trade rules that promote the sustainable use and management of natural resources;
- Policy makers, negotiators, and others are better able to determine and advance their own interests in regional and international trade policy processes.

During the course of the programme 3 major achievements have come to fruition, agreement on the Trade Facilitation Agreement (TFA) at the WTO 9th Ministerial in Bali in December 2013 and its subsequent ratification in 2014, substantial progress towards the operationalization of the LDC Services Waiver, and the agreement on the Economic Partnership Agreements in West, Southern and East Africa. All are expected to bring benefits to developing countries. The World Economic Forum for example estimates that reduced supply chain barriers to trade (regarding border administration and transport and communications infrastructure) could increase global GDP by nearly 5% and trade by 15%.[1] Important gains can be achieved in Africa through trade facilitation reforms. In particular, improvements in trade logistics to cut trade costs for the less advanced African countries to a level comparable to more advanced countries in the region could be more important in terms of trade expansion than a reduction in tariffs.[2]
[1] World Economic Forum (2013): Enabling Trade: Valuing Growth Opportunities
[2] Portugal-Perez, A. and Wilson, J. 2009. “Why trade facilitation matters to Africa,” World Trade Review, Volume 8, Issue 03

All these agreements had substantial input from ICTSD, with significant growth in their outreach and very positive feedback provided by key stakeholders during the 2014 Strategic Review.[3]
[3] 2014 Review of the International Centre for Trade and Sustainable Development: Saana Consulting 13th August 2014.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

The key outcome to be achieved by this programme was that “the international trade system is influenced to advance the goal of sustainable development through enabling, supporting and facilitating effective stakeholder engagement, particularly from LDCs and other developing countries”[4], with ICTSD dialogues and knowledge products increasingly used to achieve that outcome.
[4] From the original logframe, although the logframe was subsequently developed to more fully reflect ICTSD’s 7 main goals that were linked to the result areas referred to in part A.

Over the course of the programme ICTSD achieved highly against all of their output indicators. Their dissemination through their website, subscription lists, social media and their stakeholder engagement is impressive. With a current subscription list of 25,030 and their network into WTO and other big organisation allows ICTSD to influence both sides of the development agenda and are especially popular with LDCs.

ICTSD established the E15 initiative, which has gathered high praise for its innovative nature. The group meet over 26 times during the course of the programme. As a result of this expert group 2 final overview papers were published with a further 18 in draft stages. A lot of ICTSD work has focused on the production and dissemination of knowledge and using this to influence the trade policy landscape through the WTO, regional agreements and national policy. They have also continued their work in creating dialogues on reforming Agricultural Trade Policy and ensuring that debates and discussions on intellectual property rights have a strong development focus. Several key events and dialogues are highlighted under outputs 3 and 5 below.

In 2010, ICTSD undertook a review of its findings and results of gender mainstreaming and subsequently developed a specific gender policy to enhance understanding of gender issues and to incorporate gender-based considerations in strategic programme design and implementation. In late 2013, ICTSD commissioned an extensive baseline assessment of its achievement and status in relation to its gender-policy objectives, and then prepared a Gender Action Plan to further advance the goals of the gender policy. Following this ICTSD have now developed a toolkit which contains necessary information, guidelines and training to build the capacity of ICTSD staff, have assessed their existing programmes to identify realistic opportunities to mainstream gender, and have also developed a scoring sytem to help evaluation of gender impacts in future programmes. On poverty more broadly, ICTSD do limited work on the analysis of poverty impacts in specific countries, but do pay particular attention to the needs and concerns of least developed countries.

The latest independent 2014 Strategic Review[5] concluded that “ICTSD has performed well in terms of delivery of activities and outputs over the last two years. It has a very strong reputation, an impressive network and is regarded to be a world class think tank. It has adjusted its focus and activities to remain relevant and “ahead of the game” within its field. It is a trusted partner on trade and sustainable development and it is seen by stakeholders as both professional and impartial. Whilst it is very difficult to attribute ICTSD’s direct contribution to sustainable development, based on the evidence reviewed and stakeholder feedback the Review concludes that ICTSD has made a significant contribution to the trade and sustainable development agenda over the last 2 years”.
[5] 2014 Review of the International Centre for Trade and Sustainable Development: Saana Consulting 13th August 2014.

This difficulty in measuring ICTSD’s contribution at the outcome level was a key theme through the Strategic review of ICTSD; one recommendation is to include a “Lessons learned” section to the annual impact assessment, as outlined in the Strategic review. This section could focus on ICTSD activities that went well and what was not so successful and to reflect on why this was. Another suggestion is to feature case studies, on several countries, in their Impact assessment. This way ICTSD’s influence and their interactions could be tracked as the case study develops.

Output Score and Description

A+	All outputs have met or exceeded their targets.

This is based on an assessment that focuses on five outputs and their associated indicators extracted from ICTSD’s larger overall logframe (updated for 2013-2015) that were judged to be most relevant to DFID’s support. But the assessment and scoring also takes account of performance against a wider set of indicators from the five outcome areas under which these outputs sit. This is the same approach as applied for the 2013 Annual Review.

In summary:
1. Regional stakeholders actively pursued trade policy issues with numbers of regional dialogues, citations, and growth in ICTSD’s subscribers, followers and web visits all exceeding targets;
2. Stakeholders have engaged intensively through the establishment of the E15 Initiative (expert groups in 15 key areas) as well as capacity building in trade law for LDC negotiators;
3. A number of papers and policy proposals tackled the question of high and volatile food prices and their implications for trade policy, while others considered agricultural trade, food security and climate change;
4. Significant progress was made with operationalising the LDC services waiver, while other initiatives facilitated successful conclusion of the Economic Partnership Agreements;
5. A number of events were held to ensure that development considerations are better integrated into international deliberations on intellectual property.

Lessons and how these have been shared

Five key lessons and recommendations are as follows:

- For future programme, it is recommended that DFID and ICTSD agree on more suitable logframe targets. The Meta logframe that was supplied to DFID as a monitoring tool by ICTSD is considered out of date and includes targets that ICTSD feel are unsuitable for measuring their performance for some outputs. We would recommend that ICTSD update this, in collaboration with DFID and other donors as soon as possible considering the programme’s current extension has been agreed. Narrative reports could also be improved to ensure that progress against logframe output and outcome targets can be more easily monitored;
- Attributing the impact of ICTSD’s activities and outputs to ultimate changes in the trading system will always be difficult. ICTSD are working to improve their monitoring and evaluation systems, but a more rigorous approach to track and monitor the use and impact of research papers and dialogues would be beneficial. More broadly, taking forward the Strategic Review’s recommendation to include a “Lessons learned” section to the annual impact assessment will be important;
- As also noted in the 2014 Strategic Review, the production of annual efficiency reports are welcome evidence of ICTSD’s commitment to VfM, but new measures should be tracked and savings reported annually as part of the Annual Review process;
- More generally, management’sresponse and follow up to the findings and recommendations of the 2014 Strategic Review (most of which have been agreed or are being considered) should be considered at the next meeting with core donors;
- It is important that ICTSD keeps their independence and impartiality in order to best influence trade policy through the multi-lateral system.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Regional stakeholders are active in pursuing trade policy issues.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone	Progress
Region-specific trade policy is analysed and discussed at regional levels with regional experts	5 Regional Dialogues / (65% regional partners)	6 / n/a
Regional discussions on trade and sustainable development cite ICTSD regional publications and research.	30 Citations	182 Citations in 2013 Citations for 2014 are unknown

Key Points

This output measures ICTSD’s outreach through their regional dialogues held through their Regional Trade Agreement (RTA) exchange and input to wider regional discussions, and is one of several that fall under ICTSD’s wider impact area of empowering stakeholders to engage effectively in issues of trade and sustainable development.

a) Commentary on above indicators

- While the number of regional dialogues appears to have fallen from the 18 stated in the 2013 Annual Review[6], the number of “International Dialogues that have a regional focus” increased from 4 in 2013 to 6 in 2014, exceeding the logframe target of 5.
  [6] From recent discussions with ICTSD it is hard to determine what constitutes as a “regional dialogue” as ICTSD does not use this definition for internal lists.
- ICTSD’s work was cited 182 times in 2013, however the numbers for 2014 will not be known until the release of the 2014 impact assessment. The logframe target for this was 30 citations in 2014 (cf 13 in 2012 baseline year), which ICTSD are well surpassing.

b) Commentary on other indicators related to this impact area

Other output indicators measure the success of the periodicals through the number of subscribers and their location, and the growth in and diversity of ICTSD’s contributors and followers:
- During the 3rd quarter of 2014 ICTSD radically updated their website and database for managing their subscriptions (which included the removal of duplicate and invalided entries). At the end of 2014 the overall number of subscribers totalled 29,686, with the total number of individual subscribers (excluding duplicate addresses) amounting to 25,030. This represents a 17% increase over 2013 (cf target growth of 5%).
- The total number of page visits grew by 15.2% (cf target 5%) to 977,075.
- Data on the number of LDC authors contributing to the Bridges periodicals in 2014 is not yet available but was 69% (cf target 63%) in 2013.
- ICTSD’s Linked-In group has grown by 25% in 2014 (cf target growth of 5%) adding a further 570 to their member network. As the use of social media grows, ICTSD have increasingly moved towards sharing their work through outlets such as Facebook and Twitter. At the beginning of 2013 ICTSD had 575 followers for their main Facebook page, 1674 followers of their periodicals and 1011 followers of their programmes. By the end of 2015 their following had increased by 221% to 1846 followers and their periodical and programme followers by 50% and 75% respectively. There was a similar increase in the twitter followers, growing by 316% for their main page, 72% for their global periodicals, 49% for the regional periodicals and 149% for their programmes. Bridges achieved over 9415 likes through Facebook and 21852 followers on Twitter in 2014.

The 2014 Strategic Review concluded that “ICTSD continues to provide high quality, policy-oriented analysis to a broad range of stakeholders, both in developed and developing countries. ICTSD’s research and dialogues were seen, almost unanimously, as objective and evidence-based. The Centre is regarded to be an important impartial voice in the international trade policy ecosystem”.[7]
[7] 2014 Review of the International Centre for Trade and Sustainable Development: Saana Consulting 13th August 2014.

Summary of responses to issues raised in previous annual reviews (where relevant)

None, there were no issues raised in the 2013 annual review.

Recommendations for future programmes

None.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Stakeholders engage in dialogue about potential innovations and opportunities for governance and institutional reform of the Multilateral Trading System
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
No. informal discussions among key experts and policy-makers on solutions for governance and/or institutional reform of the Multilateral Trading System	5	16 in 2014

Key Points

This output contributes to ICTSD’s wider impact area of ensuring the multilateral trading system provides equal opportunities for all countries to advance their sustainable development goals.

Commentary on above indicator

Achievements for this output have been exceeded. In 2013 ICTSD alongside the World Economic Forum launched a series of initiatives and innovative responses to identify solutions for governance and/or institutional reform of the Multilateral Trading System. These included the E15 initiative – a multi-stakeholder dialogue process consisting of a series of 15 expert groups, each made of roughly 20-25 top thinkers. The E15 contains expert led discussion groups on Trade and Investment in natural Resources/Extractives, Competition Policy, International Subsidies, Investment policy, WTO, Regional Trade Agreement, Regulatory Coherence, Global Trade Architecture, Digital Economy, Global Value Chains, Climate Change, Industrial Policy, Trade and Innovation, Trade Finance and Development, Agriculture and Food Security, Clean Energies, Extractives, Oceans and Fisheries and Services.

The various E15 initiative expert groups have formally convened 26 times over the course of the programme (16 in 2014), with many more informal discussions on the side-lines of events such as the WTO ministerial in Bali. During the final quarter of 2014, the E15 Initiative published 2 overview papers (on services and fishing), disseminated through their website, with a further 18 overview papers in the first draft stage that should be completed and published in 2015 under our next tranche of funding.

Commentary on other indicators related to this impact area

Other output indicators assess the ability of countries to better defend their trade interests through enhanced legal capacity:
- Through their International Trade Law programme, ICTSD have hosted and organised numerous events to highlight best practice, share knowledge and experience.
- During this year ICTSD produced a further 46 publications referring to Trade Law and institutional deficiencies, and also invested in building the legal capacity of officials involved in WTO dispute settlement.
- On 31st March 2014, ICTSD co-organised a workshop with WTO and Advisory Centre on WTO Law (AWCL) on Managing Trade and Environment Disputes. This workshop served as a forum for developing countries to share their experiences and exchange views on managing trade and environment disputes. The workshop was widely recognised as a success.
- ICTSD co-organised a workshop with ACWL and WTO on 29th – 30th September entitled “Africa Dialogue on Managing Trade Concerns. The goal was to enhance the capacity of African countries through best practice and experience sharing. In total 48 countries attended, predominantly from Africa who are dealing with non-tariff barriers to trade. Overall the event was well received with feedback stating that most attendees had a much better understanding of the subject and would help improve their work back at home.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were no issues raised in the previous annual review.

Recommendations for future programmes

The 2014 Strategic Review highlighted that the E15 Initiative was proving to be an innovative way of enhancing outreach. It has been suggested that ICTSD actively track and monitor the use of further overview papers to assess their impact. It would be useful to know who these papers are reaching and whether or not they are considered useful to LDCs, and if they influence their policy making decisions as the Bridges periodicals have. It would be useful for the quarterly narrative reports to list events and citations of these overview papers under their own impact sections for each goal.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	International cooperation addresses the negative impact of high food prices and excessive price volatility on consumers in poor net-food importing countries
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Specific policy measures are put forwards in international discussions	3 examples	3

Key Points

The purpose of this output was to measure the influence of ICTSD in highlighting the negative impacts of high food prices and excessive volatility on consumers in poor net-food importing countries. ICTSD’s success is determined by how many specific measures are put forward in international discussions based on their research and ideas. This output contributes to ICTSD’s wider impact area of ensuring the global agricultural trading system supports food security and the sustainability of natural resources.

a) Commentary on above indicator

In 2013 ICTSD helped The Group of Net Food-Importing Developing Countries (NFIDCs) draft a proposal for a work programme on trade and food security, and also published analysis on how food security could be improved through new disciplines on agricultural export restrictions. Over the course of 2014 ICTSD published 6 key documents and 5 information notes on this issue, widely disseminated through their website[8]. This research and analysis influenced a number of policy proposals from different groups:
[8] Three key documents were: The 2014 Agricultural Act: U.S. Farm Policy in the context of the 1994 Marrakesh Agreement and the Doha Round. By Prof. Vincent Smith. June 2014. ICTSD, Geneva. - Food Security and WTO Domestic Support Disciplines post-Bali. By Prof. Alan Matthews. June 2014. ICTSD, Geneva. - Public Stockholding for Food Security Purposes: Scenarios and Options for a Permanent Solution. By Raul Montemayor. June 2014. ICTSD, Geneva.
1. US industry groups warn Congress that trade distortions in the Farm Bill could affect developing countries, drawing on legal analysis based on ICTSD research;
2. EU environment and development groups draw on ICTSD analysis of decoupled farm subsidies to inform parliamentarians negotiating new Common Agricultural Policy;
3. ICTSD analysis of India's Food Security Act informed domestic debate and international negotiations over a new 'peace clause' to shield food stockholding schemes.
In addition, four of the informal submissions put forward at the WTO during the course of 2014 related to topics highlighted in ICTSD’s recent work on agricultural trade. These included three separate communications by the US and by Japan on the topic of agricultural export restrictions - which ICTSD analysis has suggested can undermine food security in net food-importing developing countries, especially during price spikes - and one US proposal on elements for a work programme on trade and food security at the WTO.

b) Commentary on other indicators related to this impact area
Other related output indicators assess the extent to which domestic policies and international agreements include discussions about appropriate measures to achieve food security and environmental goals, and the extent to which the impact of farm trade policy finds a place at the United Nations Framework Convention on Climate Change (UNFCC):
- During 2014, ICTSD held 11 informal discussions with a cross-section of climate negotiators from developed and developing countries and international agency officials that took into account agricultural trade and food security concerns.
- In addition, ICTSD analysis informed the LDC statement at a first-of-its-kind technical workshop on agriculture and climate change at the UNFCCC Warsaw COP19, and ICTSD was asked to join a global research network to inform policy-making on agricultural trade, food security and climate change, initiated by the FAO.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were no recommendations or issued raised from the first annual review

Recommendations for future programmes

N/A

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	LDCs enjoy improved market access conditions
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
A significant portion of the LDC Package at the WTO is operationalised by 2015	Multiple elements	Multiple

Key Points

This output is designed to measure the influence ICTSD have exerted on operationalization of the WTO LDC package, and contributes to ICTSD’s wider impact area of ensuring that trade contributes to reducing poverty and promoting growth in LDCs.

a) Commentary on above indicator

ICTSD information notes and capacity building events had helped ensure that agreement was reached to operationalise the LDC services waiver[9] at the MC9 in Bali (December 2013). The LDC Group tabled a ‘request’ through the WTO in July 2014 (in part funded by the DFID TAF) outlining how they would like the Waiver to be operationalised. This request covered market access (with some sector-specific requests), liberalisation of visa rules, recognition of professional qualifications and capacity building. Non-LDC WTO members (including the EU) were given six months to respond to the request by signalling what they would be prepared to offer on unilateral, non-negotiated, preferences for LDCs’ services exports. During this time ICTSD supported the LDC group in their preparation of the collective requests by producing 16 country assessments of LDC services exports and 5 target market studies. The studies were then used in conjunction with regular consultations within the WTO, highlighting the key influence ICTSD have when formalising the LDC request. Many WTO members presented their responses and offers in February 2015, and agreement is expected later this year.
[9] The Waiver (agreed in 2011 at MC8 but not operationalised) allows WTO members to treat the exports of services from the Least Developed Countries (LDCs) in a preferential manner compared to other WTO members’ exports of services; i.e. it waives the usual non-discrimination rules.

During the WTO Bali Ministerial Conference in 2013 negotiators agreed to adopt The Bali package, in particular the trade facilitation agreement (TFA). This agreement holds significant promise for generating new trade, with the World Economic Forum estimating that reduced supply chain barriers to trade (regarding border administration and transport and communications infrastructure) could increase global GDP by nearly 5% and trade by 15% (a larger gain than from the complete elimination of tariffs). In the run up to this event, ICTSD worked with negotiators to deepen the understanding of the trade and food security issues raised by the proposal on public stockholding by the G33 developing country group: “this was central to the ACP countries’ cogitation on the MC9”, according to one WTO trade official.

b) Commentary on other indicators related to this impact area

Other related output indicators cover the ability of LDCs to better articulate and negotiate proposals relevant to their interests, and the development of concrete options for LDCs to improve their integration into global value chains:
- ICTSD delivered a very well received project on Aid for Trade that fed into the Fourth Global Review of AfT in July 2013, drawing on assessments of AfT effectiveness in eight countries (Bangladesh, Cambodia, Malawi, Nepal, Chana, Guatemala, the Philippines and Peru) and providing recommendations on how to improve the impact of AfT.
- Additionally, ICTSD responded to a request from the ACP states to provide examples outlining how they could better understand how AfT opportunities can enhance their integration into global value chains (GVCs)[10]. One of the expert groups in ICTSD’s E15 Initiative focuses on the expansion and consolidation of global value chains and their effect on global trade governance. The group has published various pieces of research and proposed options on how the system can promote the effective integration and upgrading of countries, including LDCs, in a global economy increasingly relying on Global Value Chains.
  [10] 2014 Review of the International Centre for Trade and Sustainable Development: Saana Consulting 13th August 2014.
- ICTSD also conducted a series of stakeholder dialogues across Africa (Oct 2013-Feb 2014) to help break the negotiation deadlock on Economic Partnership Agreements (EPAs). These dialogues helped key stakeholders, including LDC government negotiators to share and articulate their views and develop policy options to move the negotiation process forward. In a concluding meeting in March 2014 ICTSD presented its findings to the European Commission and offered options going forward. While it is hard to attribute an impact directly to ICTSD, the negotiating partners from Africa and Europe subsequently noted that the intervention by ICTSD and the findings of these dialogues had been incredibly helpful in advancing the process of the EPAs. The West, South and East Africa EPAs have now all been signed and are awaiting ratification.

Summary of responses to issues raised in previous annual reviews (where relevant)

None, there were no issues or recommendations in the previous annual review.

Recommendations for future programmes

It is essential that ICTSD keep their relationship with LDCs at the highest level and ensure their work remains as unbiased as possible. Their success is largely down to the trust LDC’s place in ICTSD to provide them with accurate, unbiased information, even when disliked by LDCs. While noting that areas of work under this output appear to be highly successful, the Strategic Review also noted that it wasn’t clear what follow up work was planned, and recommended that ICTSD should refine and focus its strategy in relation to LDCs and Africa under this goal and avoid a situation where projects set priorities. Priorities could be better linked to an enhanced outreach strategy, with a Theory of Change developed to support this and to frame strategic choices, clarifying where ICTSD is best placed to add value.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Development considerations form an integral part of international deliberations on Intellectual Property (IP)
Output number per LF		5	Output Score	A+
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Development considerations form an integral part of international deliberations on IP	3 examples	5

Key Points

This output measures the impact that ICTSD have in shaping the development side of Intellectual Property Rights negotiations and ensuring that such agreements have development considerations integrated into them.

The main achievements, including the Marrakech treaty are explained fully in the previous annual review but the outputs for 2014 are detailed below. Over the year ICTSD, successful organised or participated in 5 different events where development was tabled as a major concern, comfortably exceeding programme targets, although the impact of these events is yet to be fully assessed:
- On 21st March ICTSD co-organised the “First Geneva Dialogue on Traditional Knowledge” with the Institute for Sustainable Development and International Relations (IDDRI) and the Australian Centre for Intellectual Property in Agriculture (ACIPA). The objective of this dialogue was to provide an informal space to debate key issues relevant for the effective development and implementation of an international regime for the protection of Traditional Knowledge (TK), with a primary focus on the ongoing process at the IGC.
- On the 27th March ICTSD co-organised a dialogue “International Technology Transfer: Current implementation and future course of action” with the Centre for Global Development (CGD). Improving technology transfer flows and arrangements directed towards developing countries and LDCs has emerged as an important priority in a number of international forums such as the WTO, WIPO and beyond.
- Also in May, the G-20 presented a draft report addressing, among other topics, the role of agricultural innovation in boosting farm yields, and the controversial issue of whether and how the protection of patents and plant breeders' intellectual property rights could spur innovation. The draft report recommended helping developing countries to enforce their international obligations and harmonise their IP systems.
- On 18 and 19 September 2014, ICTSD organised a multi-stakeholder dialogue to examine the implementation of the 2007 WIPO Development Agenda (DA) recommendations. The Dialogue, which marked a decade from the launch of the DA proposal, invited participants from country delegations, academics, and officials working with WIPO in the implementation of the DA to identify the achievements and ongoing challenges to date. The event highlighted key governance questions and issues of WIPO institutional reform which, if resolved, would help to realise the spirit of the DA recommendations.
- At the WTO’s annual public forum (1-3 October 2014), ICTSD co-hosted an event on Innovation, IP and the role of the informal sector in Africa’s development. The event showcased new research, by Open African Innovation Research and Training (Open AIR), which emphasizes building complementarity between Africa’s formal and informal sectors through sui generis models of IP protection.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were no issues or recommendations in the previous Annual review.

Recommendations for future programmes

N/A

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Key cost drivers over the course of the programme were mainly staffing costs (including associated travel costs) and programme management costs. ICTSD have provided evidence of their salary scales and the 2012 NGO Remuneration Survey for the NGO sector in Switzerland. From these documents it is evident that ICTSD pay 9.2% less than similar organisations in their field. Given the past performance and expertise of ICTSD, this represents good value for money, although this comes with the risk that talented staff, especially within the finance positions, may leave for more lucrative packages elsewhere. However this risk is strongly mitigated given their strong recruitment procedures.

VfM performance compared to the original VfM proposition in the business case

The original business case proposition stated that providing core funding to ICTSD is good value for money considering their already established outreach and reputation. ICTSD produces an “Efficiency Report” to report on outputs in relation to resource usage that provide a range of value for money metrics, focusing on the number and cost of full time equivalent (FTE) staff, and key outputs in terms of numbers and unit costs of periodicals, publications and dialogues

The key message from ICTSD’s 2013 Efficiency Report is that while the primary input (staff FTEs) have slightly declined, albeit with a small increase in costs, ICTSD has been able to increase its outputs thanks to more efficient use of resources. These figures provide evidence to suggest that ICTSD is improving its efficiency and delivering increased value for money of DFID funds. This conclusion is largely endorsed by the 2014 Strategic Review, which noted that staff costs have fallen from 69% to 55% of total expenditures since 2011 as ICTSD have kept total salaries flat for a number of years; changed fixed contracts for some senior associate staff into associate contracts and built the intellectual base by offering honorary fellowships and making strategic hires. Although these added to the salary cost base, they also strengthened ICTSD’s competence and reputation, thereby enhancing VfM.

Assessment of whether the programme represented value for money

The Independent Strategic Review 2014 carried out by Saana Consulting concluded that ICTSD is a well-functioning organisation that has achieved a lot given their available resources and the complex environment in which they work, and that ICTSD has made a significant contribution to the trade and sustainable development agenda in recent years. It applauded ICTSD’s efforts to limit the growth of staff costs, reduce programme costs and improve organisational efficiency, noted that high levels of output had been sustained despite cost containment measures between 2010 and 2012, and concluded that “The general conclusion from the Review is that ICTSD performs well in terms of value for money”. The Review does recommend however that progress and milestones on VfM/efficiency savings should be reviewed annually by the Board and communicated to donors, and that there could be greater focus on how to achieve better VfM by refining strategic choices (including what to stop doing) and enhanced outreach in cost effective ways.

Quality of financial management during programme

DFID are ICTSD’s largest donor but other core donors include Sweden, Netherlands, Denmark and Finland. Switzerland also contributes to major programmes and the rest of ICTSD funds are raised through other donors for smaller projects which include Australia and the WTO.

ICTSD has strong IT systems appropriate for their size and have appropriate cash balances. They employ Price Waterhouse Cooper to conduct an annual audit and produce management reports. There is no perceived weakness in ICTSD's financial stability however DFID express the need to continue their strategy to diversify their donor base.

Variance reports are generated as part of the Quarterly Management Reporting pack. The Managing Director, Director of Operations will discuss all material variances directly with the respective programme managers, to determine/confirm the causes of the variance, and to formulate an appropriate action plan if required. It has been noted that all recent audits has shown ICTSD to have robust financial management.

With each request for funds, ICTSD have supplied DFID with expenditure reports, broken down into activity levels. As the requests are for payments in Advance, forecasting for this programme spends has not been an issue.

Date of last narrative financial report	13/11/2014
Date of last audited annual statement	10/04/2014

E: RISK (½ page)

Quality of risk management over the life of the programme

ICTSD periodically conducts a review of its organisational risks and shares this with key partners. Risks related to the specific impact areas are identified in the ICTSD Logical Framework. They include continued political will, engagement and interest in collaborating on identified topics and interests and engagement from other stakeholders as well as macroeconomic and geopolitical conditions.

The main operational risks identified in the original business case were that key staff leave ICTSD, and that other donors decide not to continue funding, undermining ICTSD’s financial position, and perhaps compromising its perceived impartiality. This programme was rated as being of medium risk, but given improvements in the financial sustainability of ICTSD and its strengthened approach to risk management, the successor programme (approved October 2014) has been rated low risk. The main risks are that key staff leave, other donors may stop funding, the organisation growth is not well managed and that ICTSD have cash flow issues that have happened in the past. But these are now being adequately mitigated (eg through recruitment processes and a successful programme of diversifying the funding base).

Fiduciary and reputational risks to DFID are also considered low based on ICTSD’s past performance and effective oversight. A due diligence exercise conducted for the new ICTSD support programme in Dec2014 noted that the Managing Director (Director of Operations) Deborah Vorhies has oversight of the internal control, risk management and corporate systems, and concluded that the organisation demonstrates strong governance and control procedures and has the capacity to effectively administer UK aid.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

All outputs were delivered on time and to cost.

Performance of partnership (s)

DFID has been supporting ICTSD since 2000, initially funding specific pieces of research, but more recently through core funding. This has provided ICTSD with a greater degree of both predictability and flexibility to respond to emerging issues and been a key part of ICTSD’s financial strategy, endorsed by the latest Strategic Review. This funding agreement (£5.1m over 3 years 2012-2014) represented around 30% of ICTSD’s budget, though this falls to 20% over the new programme ((£8.5m over 5 years, 2015-2019) approved in October 2014. The partnership is considered as very important and as the results show, is beneficial to influencing the world of trade policy. An important element of the partnership is ICTSD’s independence that allows it to be so effective in influencing LDCs and policymakers in the Multi-lateral system.

Asset disposal and value obtained by DFID
N/A
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The overall budget included £50,000 reserved especially for monitoring and evaluation. During 2014 DFID Trade for Development commissioned Strategic Review of ICTSD activities so far, which helped inform both ICTSD management and supporting donors and provided a key input to the development of the DFID’s successor programme of support.

ICTSD have also produced annual Efficiency Reports (reporting on ICTSD outputs in relation to resource usage and representing a key tool for senior management in demonstrating value for money) and Impact Assessments (reporting on progress towards ICTSD goals). Plans for a further independent Strategic Review of ICTSD’s programme and performance, which have been undertaken every 2-3 years with the last in 2014, will be discussed with project partners at the next donor meeting in July 2015.

Monitoring progress throughout the programme

In addition to the 2014 independent Strategic Review, an annual review for this programme was completed internally by DFID in January 2014 (scoring an A+). ICTSD has also submitted detailed quarterly narrative reports which have helped DFID monitor their progress against their logframe. However, further refinements to the logframe are required to ensure that more suitable indicators and targets are set, and the narrative reports could also be improved to ensure that progress against logframe output and outcome targets can be more easily monitored.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against VfM measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How risks were managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process