Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to International Agricultural Research Centres that benefits Poor People
Programme Value: £40,093,715		Review Date: 12/03/2015
Programme Code: 202748	Start Date: 01/04/2012	End Date: 31/03/2015

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	A+	A	A
Risk Rating	Low	Low	Low

Summary of progress and lessons learnt since last review

Overall progress is on track, and the programme scores an A. The four international agricultural research centres which receive funding under this programme currently are largely meeting expectations against the main indicators relating to research delivery and scaling of technologies. One of the 4 funded centres (CABI), received a performance bonus due to having fully met or exceeded the milestones for the key deliverables with an excellent performance against organisational and quality of research. The three other centres were largely on track against agreed deliverables and milestones. The main recommendations to centres following the mid 2014 review related to impact evaluation, gender analysis and mainstreaming and strategies and partnerships for uptake of technologies. Performance against organisational behaviours (i.e. financial management, environmental management systems, gender sensitive HR systems and policies) was good.

This review is a light touch one, since DFID has commissioned an external evaluation of the programme which is currently underway. This evaluation is expected to feed into future decisions in DFID agriculture research programme on use of performance management systems.

Summary of recommendations for the next year

Where research centres have a strong presence and are scaling up technologies in specific countries, they should approach the Agriculture Research team to discuss how this overlaps with bilateral programme priorities, and where appropriate facilitate an introduction to Country Offices (DFID to follow up via communication to research centres in March 2015).

Lessons will be drawn during the next Annual Review (due February 2016) on the effectiveness of this new mechanism to assess quality of research by the DFID Review team, drawing on feedback from centres.

DFID Agriculture Research team should formally draw attention of the partners to their availability for follow up discussions on partnership or aspects of performance (recommendation #3) (March 2015).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202748/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-3719418/

Outline of the programme

The UK is investing up to £40 million in international agricultural research over four years from 2011-2015. In 2011, a business case was approved to provide £30m to scale up our core funding to four international research centres, i.e. CABI, icipe, AVRDC and GFAR, who were all pre-assessed as providing good or very good value for money to DFID. Funding to Crops for the Future (CFF) was discontinued as it could not demonstrate that it continued to provide value for money to DFID. However, one final allocation was approved, apportioned over 2012/13 and 2013/14 financial years to allow them time to attract alternative sources of funding.

Each of the selected research centres identified 3 or 4 key objectives, e.g. new improved vegetables lines with good nutritional and/or disease resistant properties, roll out of new national plant health systems in 30 countries, scaling up of “push-pull” control of striga in cereals in Africa and an integrated pest management technology for control of African fruit fly and mechanisms for tracking investments in AR4D and for building user feedback into international agricultural research systems. Based on their performance against the agreed key objectives and good governance measures, i.e. robust financial systems, an environmental management system with targets for reducing carbon footprint, metrics on energy use, etc, and HR policy and operational plans for ensuring gender balance in organisational structures and research processes implemented. DFID undertakes a review of each centre’s performance annually against the key objectives and organisational behaviours. On the basis of the performance review, a decision is made whether or not to award a 20% performance bonus for demonstrating good performance.

In November 2012, a business case was agreed to provide additional funding of £10m to two centres, CABI and icipe, which had demonstrated evidence of excellent research quality with development impact and value for money for DFID during the inaugural performance review. These centres also showed that they could scale up their work to meet strong Ministerial interest in the use of science and innovation in tackling poverty and in new forms of partnership with the private sector to deliver development outcomes.

During 2012, a new funding arrangement was finalised with ICIMOD, following an assessment of the value for money they present to DFID’s agricultural research programme. Funding to GFAR ceased from 1 April 2014.

An external evaluation of the performance management system is currently underway. The budget for this evaluation is £96,750.

Table 1 shows expected total expenditure for the programme.

Table 1

Centre	2011/12	2012/13	2013/14	2014/15	2015/16	Total
AVRDC	340,000	1,440,000	1,520,000	1,520,000	380,000*	5,200,000
CABI	900,000	4,403,600	4,970,000	4,962,000	992,000*	16,227,600
icpe	353,033	3,515,367	4,070,000	3,248,000	812,000*	11,998,400
GFAR	90,000	240,000	240,000	-	-	570,000
ICIMOD	-	1,098,000	1,098,000	1,113,270	123,697*	3,432,967
CFF	-	217,500	82,500	-	-	300,000
Project Evaluation	-			72,563	24,187	96,750
	1,683,033	10,914,467	11,980,500	10,940,020	2,307,697	37,825,717

* 14/15 bonus: decision on whether bonuses are paid will be taken after 2015 performance review in June/July 2015.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The two previous Annual Reviews assessed performance in the Outcome Assessment based on two components. Firstly, are the centres performing as expected, meeting deliverables and is the assessment against outcomes on track?

Against the first of these criteria, the annual outcome assessment is an A. Both outputs scored an A, with centres largely meeting expectations against the main indicators relating to research delivery. One of the 4 funded centres received a performance bonus (CABI) due to having fully met or exceeded the milestones for the key deliverables with an excellent performance against organisational and quality of research. The three other centres were largely on track against agreed deliverables and milestones.

For all centres, in order to leverage improved performance, specific recommendations for follow up action were made following the mid 2013 performance review. These were set out in greater detail in mid 2014 than in previous years. These recommendations identify areas where further work is required if the centre is to obtain a bonus in the following year. The main areas identified in the performance reviews for follow-up relate to impact evaluation, strategies and partnerships for scaling technologies, and gender analysis and mainstreaming work.

The second aspect of the assessment looks more broadly at the introduction of a new performance based management systems. Is the system performing effectively, and meeting the objectives set out in the Business Case of using multi-year performance related funding to leverage higher performance, value for money, and closer alignment with DFID values and priorities? The review team finds several positive aspects to the performance funding system (stronger partnership and dialogue, clearer results) and the research partners have themselves identified benefits too. However, not all centres are achieving their performance bonus, and the performance reviews have identified areas of weakness, particularly in relation to robust impact evaluations, and gender analysis and mainstreaming. This suggests that the performance management system is not delivering the step change intended, particularly in relation to impact evaluation. However, as this is currently the subject of an external evaluation, this Annual Review does not undertake a more detailed analysis of this aspect of the programme.

The external evaluation looking at this in more detail was commissioned in 2014, and the evaluators are due to deliver their report in May 2015. As this evaluation is currently underway, the review team has not commissioned additional feedback from the centres themselves for this exercise. This review therefore sets out progress by each centre, rather than assessing the effectiveness of the performance managed management aspect more broadly.

Overall output score and description

Four centres were reviewed this year, as funding to GFAR was dropped in the first quarter of 2014. CABI showed good performance, and received its bonus. AVRDC, icipe and ICIMOD demonstrated satisfactory performance but did not obtain a performance bonus.

All the centres delivered well against the core deliverables that they committed to at the beginning of the partnership, primarily around development and upscaling of new technologies. This output scored an A. Notable achievements including further development of Plantwise health clinic model at country office level, supported by the global Knowledge Bank facility, delivery of new vegetable varieties and technologies, upscaling of striga control technologies in East Africa, and generating of knowledge on the impact of climate change on agriculture in the mountain regions of South Asia.

Measured against the specific output indicators in the logframe, all centres have shown good performance in the number of research publications and those published in peer reviewed journals (see Table 2). All of them have produced at least one case study to demonstrate and communicate impact. On an aggregate level, we assess progress against outputs as meeting expectations.
The purpose of the performance management funding system is to leverage improved performance in particular areas. One of these focused upon in this performance review was gender, and this was prioritised as an area for improved performance in 2014. The mid 2014 review also focused on impact evaluations, with a review of all impact evaluation studies submitted as part of that review process and detailed feedback to all studies.

In terms of performance against organisational behaviours (financial management, implementation of Environmental Management systems, gender sensitive HR policies), centres better understood expectations than in previous reviews, and were largely able to demonstrate improved performance. This output scored an A.

Key lessons

Links with Country Offices

Some centres have continued to make direct contacts with DFID country offices, often facilitated or in collaboration with the Agriculture Research team (e.g. CABI in Myanmar and Nepal). The DFID Agricultural Research team has also shared outputs from these centres to country office, via the new Agriculture Research team’s Country Briefs, or via visits to Country Offices, in order to raise visibility of relevant research outputs.

A visit to Nepal in January 2015 enabled links to be made between ICIMOD and DFID Nepal, and this may lead to further exchange and discussion on Nepal specific issues. In Nepal, the Agriculture Research team is considering a pilot which would test the added value of a research-country office partnership and co-funding arrangements. This may include CABI. Where research centres have a strong presence and are scaling up technologies in specific countries, they should approach the Agriculture Research team to discuss how this overlaps with bilateral programme priorities, and where appropriate facilitate an introduction to Country Offices (recommendation #1).

Summary of responses from previous Annual Review

An update on actions taken in response to the previous Annual Review is included below.

1. For all centres there is still much scope for improving gender analysis across the portfolio, including more gender disaggregated data, and for more explicit focus on gender in future publications. This is reflected in the centre specific recommendations in the earlier section of this report.

This was a centre level recommendation, reviewed and reinforced in the annual performance reviews. Feedback was provided to centres based on their programme report against recommendations in February 2015 specifically on the gender dimensions, as part of the exchange on a possible one year costed extension.

2. AVRDC still does not have a clear gender strategy; this needs to be developed next year in order to demonstrate how it will operationalise gender across its research programme. It also needs to identify the training needs for staff on gender research and gender champions to push gender integration across the research programme.

A review of progress undertaken in February 2015 indicated that AVRDC has made progress in embedding gender analysis into their work. However, the gender strategy is still relatively new and it will be important to track progress in terms of operationalising the strategy. For example, the gender strategy includes accountability mechanisms on gender. At an individual level gender objectives will be included in workplans and monitored in performance reviews. Themes and projects will include gender-specific objectives and at an institutional level a more gender-sensitive monitoring and evaluation system will be developed. It will be valuable to monitor implementation, and resources (funding and staffing) dedicated towards strengthening its gender capacity. A follow up discussion on this will be arranged before end April with AVRDC (see also recommendation #3).

3. DFID undertook a field visit to icipe in 2013, which helped ground truth findings from the performance reviews and strengthen mutual understanding between DFID and the centre. DFID should aim to complete field visits to AVRDC, ICIMOD and CABI during 2015.

Andrew Clayton from the Agriculture Research team visited AVRDC and CABI in Tanzania in mid 2014, looking specifically at gender and other dimensions. Rachel Lambert from the Agriculture Research team visited ICIMOD in January 2015 and spent time with DFID Nepal Livelihoods Adviser.

4. DFID should proactively share the results of the performance management system with donor representatives involved in each of the centres, and best practice on organisational behaviours from each centre with the others.

DFID has invited a representative from the Swiss Agency for Development and Cooperation (SDC) to join the advisory committee of the External Evaluation, and the evaluation report will be shared with other funders.

5. The 2014 External Evaluation should look not just at the log frame indicators for this programme but also at the added value of the performance funding mechanism as a whole.

This has been incorporated into the objectives for the External Evaluation.

6. There may also be value in stimulating a discussion within the Association of International Research and Development Centers for Agriculture (AIRCA) on how to strengthen impact evaluation across the international agriculture research centres and setting out and benchmarking direct/indirect costs.

This has been shared with the centres themselves, and a working group on M&E established.

Has the logframe been updated since the last review?

No.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Centres generating high quality research outputs.
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	70%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestones
Centres on track with agreed deliverables.	The milestones are centre specific and too many to list here.

Only four centres have been assessed in this year’s annual review, as funding to GFAR ceased in the first quarter of 2014, and GFAR was not therefore involved in the annual performance review. Overall the centres are all on track in terms of delivery against their core deliverables, as determined by each centre at the start of the programme. Where a centre has exceeded targets or is off track, these are captured in the response from DFID to each centre following the performance review. This output is therefore judged to score an A.

The section below draws on the formal response from DFID to each centre, following the performance review held in June/July 2014. The review Panel for each centre involved DFID Agriculture Research team members, a Senior Research Fellow, and other parts of DFID (DFID India for ICIMOD, Livelihoods Head of Profession for CABI and AVRDC). The performance review challenges the centres to strengthen their work in specific areas, particularly in strategies and partnerships for technology scaling, impact evaluation, gender analysis.

The World Vegetable Centre (AVRDC)

The Panel noted that AVRDC maintains its core strengths in its genebank and plant breeding work. The AVRDC Annual Report documents several examples of significant scientific achievements (development of germplasm core collections, breeding of pest and heat tolerant vegetables, development of integrated pest management strategies for legume pod borer, promotion of soybean in India).

Last year, the Panel made specific recommendations in 3 areas (gender, M&E, uptake strategy for flagship technologies). The Panel commends AVRDC for its commitment to addressing these in various ways and for addressing these directly in the review discussion.

Progress by AVRDC against most of the technology-related deliverables and milestones is good. There is continued progress on reaching specific milestones on extending key technologies (grafting, home gardening) to new areas and working with new partners, from government, civil society and the private sector. AVRDC has been able to demonstrate good progress on uptake of improved tomato varieties in eastern Africa, and is developing partnerships with private sector seed companies.

AVRDC has given thought to its technology uptake strategies. Partnerships are expanding (for example with the Global Alliance for Improved Nutrition (GAIN), SNV, BRAC, Punjab University), including valuable work with the private sector, particularly seed companies. Finding ways to track ‘reach and adoption’ of technologies remains challenging. There are also inherent difficulties around confidentiality of data on the part of seed companies. The Panel was told that there are plans to do more to track adoption rates and economic impacts in the next 2 years. Further work is required to define results on reach and adoption in the next few years, to articulate clear pathways to impact, and use those to identify researchable questions. This work may make generating evidence of success easier. Without clearer indicators for measuring reach and uptake, accompanied by clear strategies for scaling up technologies, it is very hard to judge progress in developing uptake strategies and pathways to impact.

The Panel welcomed the AVRDC’s response to last year’s recommendation on M&E, in particular the approval by the Board of a new M&E strategy, the establishment of an M&E Unit with a dedicated staff lead and associated budget. M&E clearly now has greater visibility and profile within the organisation. The Panel were pleased to learn about a number of studies currently underway to identify the impact of a range of interventions. A review of the available studies (including the tomato grafting study completed in 2013) highlighted that all current impact studies are observational and all therefore have significant shortcomings in identification of appropriate counterfactual (non-intervention) groups and in robust attribution of impact. With the exception of the study on home gardens in Bangladesh, the quality of the current project write-ups was relatively low. The strategy of the M&E Unit for selecting and designing robust studies to measure impact is unclear.

The progress achieved to-date on M&E is welcomed, however the Panel believes that more efforts are still required in particular on developing a strategy for selecting interventions to be evaluated, designing evaluations that are able robustly to identify the impact on nutrition and health outcomes of selected interventions, and strengthening capacity either internally or with strong mutually-supportive collaborations. The available budget and the amount of expert staff dedicated to the M&E group should be increased and expanded, and the establishment of an external group to provide independent oversight of AVRDC M&E efforts should be considered (see Annex 1).

CABI

The Panel agreed that CABI has demonstrated another strong year, showing good performance against programme deliverables and represents very good value for money for DFID. CABI has continued to perform well against its main programmatic milestones (Plantwise, Knowledge Bank, scaling up of digital based mobile advisory services). CABI is on track to meet the main outputs/deliverables, with the majority of indicators met or exceeded.

However, the reach targets for Plantwise are off track, primarily due to lower anticipated numbers in Tanzania and India. These will need to be addressed, and there is merit in further consideration of Plantwise metrics and how they are collected. The Panel welcomed work on mapping sustainability indicators across all Plantwise countries. Coverage of clinics at the local level remains an issue, and whilst digital technologies can enhance reach, more could be done to address issues around coverage and sustainability of the business models.

The Panel noted continued progress on embedding more rigorous monitoring and evaluation in its programmes, with evidence of strong organisational commitment and funds. Despite earlier delays in the external Plantwise evaluation, this is now progressing well and the planned externally-led evaluation with a step-wise RCT design should deliver rigorous evidence of impact, cost-effectiveness and sustainability. Whilst a similar approach to all other programmes is not necessarily appropriate, CABI should continue to explore how to embed rigorous monitoring and evaluation in all its programmes, prioritising a few for external evaluations, and demanding rigour in design for all studies. The Panel commends CABI’s willingness to respond to recommendations in developing high quality impact evaluation and encourages continued leadership in this area to ensure this is fully embedded in the organisation and extended to all programme areas.

ICIMOD

ICIMOD maintains a strong reputation for delivering good science outputs, particularly around its contributions to the scientific debate on issues related to glaciers, snow and permafrost that has captured global attention. The Panel noted new work on black carbon, forest fire early warning systems and the gender transformation change work, as well as new partnerships with IFAD on climate change adaption and agriculture.

ICIMOD has made reasonable progress on its core deliverables. The Panel noted that it is establishing important partnerships both on policy and scaling up technologies, although there is no clear outcome indicator on scaling up technologies reported against.

Last year, the Panel made specific recommendations in 3 areas: gender analysis in research, greater detail on ICIMOD’s work on agriculture and the linkages between water, ecosystems and livelihoods, and approach to M&E. Whilst the discussions indicated that work is underway on agriculture and the linkages between water, ecosystems and livelihoods, this did not come out well in the written report. Further work is needed to demonstrate to DFID over the next year, that ICIMOD is delivering results in relation to agriculture and food security, both through its publications and through measurable impacts on the livelihoods of poor people.

The Panel considered that ICIMOD has demonstrated its commitment to improving the quality of its science, and strengthening M&E. The Panel welcomed the strong organisational commitment in this area, and evidence that ICIMOD is stepping up efforts in internal capacity building, monitoring frameworks, and working with others on impact evaluation. A dedicated M&E unit has been established with a budget of between $350,000 – $500,000 p.a.

The Panel were pleased to learn about a number of studies currently underway or completed to identify the impact of a range of interventions, although there was no clear strategy provided for the selection of interventions to evaluate. A review of the 3 available studies noted that 2 were observational and had weak study designs with significant shortcomings in identification of appropriate counterfactual (non-intervention) groups and in robust attribution of impact. The third study has been published in J Environmental Management (Impact Factor 3.1), and whilst an interesting paper, was largely qualitative with little robust analysis of impact. The authors themselves conclude that the “sample size was small, and the findings are therefore symbolic only”.

The Panel welcomed the ongoing randomised controlled trial on promoting maize intercropping in Nepal conducted by ICIMOD in collaboration with J-PAL. The Panel encourages ICIMOD to ensure that the full protocol for this trial is prepared, and ideally published, and that the trial is registered on an international trial register to improve research accountability and transparency.

icipe

The Panel agreed that icipe has continued to make good overall progress on its core science work, with some positive research outputs, including those outside the deliverables which DFID tracks – genome mapping of the tsetse fly, new work on insects for feed and food, and work on bee health. For the most part, icipe has made good progress on its technology deliverables. icipe is on track with its major deliverables and targets for striga push-pull technology, fruit-fly and bioacaricide development, with milestones achieved or exceeded.

Last year, the Panel made specific recommendations in 3 areas (gender analysis, uptake of new technologies, and impact evaluation). The Panel was disappointed that there was little evidence of a response to the Panel’s recommendations from last year. In the view of the Panel, the action points set out in the 2013 letter from DFID to icipe remain highly pertinent and as valid this year as in 2013.

In terms of M&E, the Panel welcomes the development of the socio-economic unit with a dedicated staff lead. However, the strategy of the unit for selecting and designing robust studies to measure impact was unclear. A review of the available impact studies noted that 2 of the 4 were observational and therefore have significant shortcomings in identification of appropriate counterfactual (non-intervention) groups and in robust attribution of impact (i.e. they looked at adopters versus non-adopters). Two studies are RCTs, which while interesting are relatively poorly described: full protocols for these RCTs should be prepared, and ideally published, and they should be registered on an international trial register to improve research accountability and transparency. Overall there has been little visible effort to raise the quality of scientific impact evaluation in icipe over the year. Developing the evidence base on key technologies should, in the view of the Panel, be integral to strategies for up-scaling key technologies.

Indicator	Milestone
Research publications including in peer reviewed journals.	Ratio of peer reviewed publications to total publications is stable or increases.

Overall, the centres have continued to show good performance in the number of research publications and those published in peer reviewed journals – see Table 2 below.

The World Vegetable Centre (AVRDC)

AVRDC has maintained a strong pipeline of research outputs and continues to exceed the baseline figure. The proportion of research publications in peer reviewed journals has fallen slightly but the proportion published in journals with an impact factor >2 has almost doubled. The DFID panel acknowledged at the performance review AVRDC’s comments on the appropriateness of the metrics used by DFID (i.e. specialist horticultural journals not included in the Thomson list).

CABI

CABI’s report to DFID indicates an increase in the number of research publications since last year but a decrease in the proportion of research publications in peer reviewed journals with an impact factor >2. A possible reason for this decline is in part the increasing use of open access journals with low or no, as yet, impact factor. The DFID review panel took on board the comments from CABI at the performance review about the potential disincentives of metrics used by DFID for assessing the quality of research outputs (i.e. % publications in impact factor journals vs. open access journals), and will be piloting a revised approach from 2015 onwards.

ICIMOD

ICIMOD has achieved its own targets for research publications and has significantly increased the number appearing in peer reviewed journals, although this is in a context of increasing staff numbers.

icipe

icipe has maintained a very strong pipeline of research outputs the proportion appearing in peer reviewed journals and in a journal with an impact factor >2 on a par with last year.

Table 2: Publications by centre

Centre	Baseline		2012-13		2013-14
	No of Research Publications	No in Peer Reviewed journals	No of Research Publications	No in Peer Reviewed journals	No of Research Publications	No in Peer Reviewed journals
AVRDC	186	40	286	96 (8 in a journal with an impact factor >2)	242	81 (12 in a journal with an impact factor >2)
CABI	148	122 (26 in a journal with an impact factor >2)	100	93 (37 in a journal with an impact factor >2)	121	102 (18* in a journal with an impact factor >2)
ICIMOD	89	19	19	11 (5 in a journal with an impact factor >2)	65	38 (28 in journals using an impact factor)
icipe	86	80	123	96 (48 in a journal with an impact factor >2)	125	88 (40 in a journal with an impact factor >2)

Metrics for quality of research

Several centres commented last year on the shortcomings of the metrics of quality of research that are used in the performance review. A new pilot to assessing quality of research, alongside the existing quantitative metrics will be trialled. For the mid year performance review in 2015 and 2016, centres have been asked to provide:

- 3-7 best research publications (depending on the size of the research output of each centre), judged by the centre to represent high quality research and development relevance; and
- 2 Impact case studies which demonstrate the impact of research conducted with funds drawn wholly or partially from DFID and in areas in which the centre is still active.

These outputs will be peer reviewed as part of the annual performance review and the results fed into the overall assessment. Lessons will be drawn during the next Annual Review on the effectiveness of this new mechanism to assess quality of research by the DFID Review team, drawing on feedback from centres (recommendation #2).

Indicator	Milestone
High quality case studies.	At least 1 case study a year published on R4D and the centre’s website.

The purpose of setting this indicator was to incentivise centres to provide DFID with impact case studies on a regular basis to assist DFID with briefing and communicating agricultural research. At least one case study per centre has been achieved – see below. The case studies have helped to raise the profile and publicise the work done by the centres through DFID’s support.
The World Vegetable Centre (AVRDC) / “Tomato grafting creates economic opportunities for farmers in Vietnam” http://avrdc.org/wpfb-file/dfid-story-of-change_avrdc-tomato-grafting-jh-1-pdf/

CABI

- Marije Boomsma (2013) The keys to more effective PPPs http://www.wageningenportals.nl/sites/default/files/kit05_ppp_paper.pdf. Also in CFC (2012) CFC annual report  http://www.common-fund.org/fileadmin/user_upload/Publications/Annual_report/ANRPT_2012.pdf CABI coffee quality in Rwanda and Ethiopia is one of 3 case studies
- CABI (2013) Coffee credit guarantee scheme in Rwanda and Ethiopia http://www.youtube.com/watch?v=3CnV9h4uN3E
- CABI (2013) Seeds of Success: CABI project success stories http://www.youtube.com/watch?v=TQVdRfZ0sIQ
- CABI (2014) The Green Invasion - Destroying Livelihoods in Africa http://www.youtube.com/watch?v=ggqseLRvlfY
- WrenMedia (2013) Improving access to quality seeds in Africa http://www.eiard.org/media/uploads/File/Case%20studies/2013_SDC%20funded/CABI%20-%20Improving%20access%20to%20quality%20seeds%20in%20Africa.pdf
- Pshenichnaya N, Palmer T. (2013) mKisan Baseline Report Executive Summary: A snapshot of the mKisan service in March 2013 http://www.gsma.com/mobilefordevelopment/wp-content/uploads/2014/01/mKisan-Baseline-Report-Executive-Summary.pdf

ICIMOD

- Policy and Institutions in Adaptation to Climate Change: Case study on tree crop diversity in China, Nepal, and Pakistan - Working Paper 2013/3
- Analyzing gendered responses to drought: A case study on adaptation and resilience to water related hazards in Yunnan Province, China. Environment Science.
- Policy and Institutions in Adaptation to Climate Change: Case study on flood mitigation infrastructure in India and Nepal - Working Paper 2013/4: This study in Nepali conducted for the World Bank on climate change adaptation and vulnerability in the Chepang community of Chitwan ( 2013).
- Climates of Food Insecurity in the Hindu Kush Himalayan Region: Impacts of changing agri-food system transformations on food security - Himalayan Climate Change Adaptation Programme (HICAP) (2014)

icipe

- Science-led innovation protects livestock from the Tsetse fly in Kenya case study http://ec.europa.eu/europeaid/documents/case-studies/kenya_agriculture_tsetse_en.pdf
- The Muliru Farmers Conservation Group, which contributes to the conservation of the Kakamega Forest through the domestication of indigenous medicinal and insecticidal plants case study http://www.equatorinitiative.org/images/stories/winners/110/casestudy/case_1348163412.pdf
- icipe - Linking insects to forest conservation through honey and silk was published by EIARD at http://www.eiard.org/keydocuments/impact-case-studies/2013/

Indicator	Milestones
Gender specific research outputs.	1. At least two outputs with a gender focus. / 2. At least one peer reviewed publication with a gender focus published.

The analysis below is extracted from the letters to the Centres following the performance reviews held in mid 2014:

The World Vegetable Centre (AVRDC)

“AVRDC has made good progress on gender since last year. From a recent DFID field visit in Tanzania, it was evident that this issue is taken seriously. The AVRDC Board approved a gender strategy in 2014. Each region has a gender focal point to lead on integrating gender into the research. We welcome a broadening of the agenda from the central role women play in vegetable production, to understanding constraints to access to and adoption of technologies and their role in different aspects of the value chain. Capacity building activities have been undertaken; guidance tools are being prepared for staff. We also welcome the introduction of gender indicators into individual appraisals, action on gender balance in staff, and awareness work with staff and the AVRDC Board. We look forward to seeing progress on generating gender analytical research outputs. This will need to be monitored in future annual reviews, but so far the signs are positive that AVRDC will significantly strengthen its gender work.”

CABI

“CABI has demonstrated evidence of serious commitment to gender, with work on capacity building, strategy and specific analysis on gender access in Plantwise, and work to embed gender in seed and other work. However, the field visit by Andrew Clayton indicated that much more needs to be done to embed this at the field level in their work in Plantwise, ensuring that gender analysis in agriculture is undertaken at the outset, and that women farmers are able to access services.”

ICIMOD

“We have commended ICIMOD on very good progress on gender, with strong evidence new research outputs, that unpack the gender dimensions of their work, are being generated. It has exceeded its targets, producing 11 research outputs relating to gender, several of which are journal publications. There seems to be a strong commitment to gender, and this is feeding into the commissioning and research record.”

icipe

“Whilst icipe has had a strong emphasis on gender within its HR strategies, we did not find evidence of the integration of robust gender analysis into research, particularly into the development and up-scaling of technologies. The indicator on generating at least 2 outputs with a specific focus on gender dimensions was not met. Gender studies currently appear to be largely limited to research efforts from MSc and post-doctoral students. We would encourage icipe to give greater consideration to building its capacity in gender analysis, and ensuring high quality research outputs in this area.“

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Organisational behaviours which underpin effectiveness and value for money for DFID are strengthened.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

All centres were able to demonstrate a positive trajectory on the organisational behaviours indicators (financial management, Environmental Management Systems, gender sensitive HR policies and behaviours), justifying an A score for the output, although the rate of progress is variable across centres. This will be analysed further by the evaluation team.

There are three indicators.

1. Robust financial systems and sources measured by:

a) Indirect/direct cost ratio, i.e. this ratio seeks to measure how much research programme activity a centre is able to support on its institutional cost base.
b) Audit opinion, i.e. an external auditor’s opinion on the centre’s financial statements indicates whether the centre’s financial accounting and reporting processes meet required standards. Depending on the nature of any qualification made, it may indicate financial “going concern” issues, the ability of the centre to account for its financial or physical assets, or the appropriateness of computations and estimates used in preparing the financial statements. Although an unqualified opinion does not provide absolute assurance about the reliability of the financial statements, a qualified opinion indicates an increase in the risk that the statements do not fairly present the true financial picture of a centre.
c) DFID costs as % of total funds, i.e. the ratio of DFID costs to total costs gives us an indicator of how dependent a centre is on DFID and how diversified its funding source. However, we note that these figures can vary considerably year to year and so 40% is set out as an indicative threshold and basis for discussion rather than an absolute figure over which we should not go.

The World Vegetable Centre AVRDC

AVRDC has continued to maintain a downward trajectory in its ratio of indirect/direct costs – 0.19 (2013) compared to 0.21 (2012) and 0.23 (2011). AVRDC’s annual audited accounts have been signed off by external auditors, who have provided an unqualified report. DFID’s funding as a proportion of AVRDC’s total income has increased slightly to 13.5% (2013) from 13% (2012) and 7.4% (2011).

CABI

CABI’s ratio of indirect/direct costs has reduced from 0.14 (2011) to 0.13 (2013). CABI’s external auditors have given an unqualified opinion in its annual audited accounts. DFID funding (including membership fees) has remained steady at 25% of CABI’s total income.

ICIMOD

ICIMOD has been maintaining its target internal cost ratios within the required level. ICIMOD’s ratio of indirect/direct costs have reduced from 17% (2012) to 0.14 (2013) whilst, at the same time, achieving the desired results from its operations. Its external auditors have provided an unqualified opinion in its 2013 annual audited accounts. DFID funding has remained fairly static at 9% of ICIMOD’s total income.

icipe

icipe’s indirect/direct cost ratio has reduced to 0.18 from 0.28 (2012) and 0.23 (2011). The external auditors, Ernst and Young, issued an unqualified opinion on 2013 financial statements with no issue on internal controls. They however raised two audit issues on need to have a financial system capable of handling growth being experienced and need to have a succession plan in place. The two issues are being addressed by Management. We mention, under Quality of Financial Management, the governance issue which allowed certain staff to approve their own expenses claims. This issue has been suitably addressed by Management. In 2013, icipe’s revenues totalled US$ 26.96M. DFID contributed US$ 7.96M of this total or 29.53% of icipe’s total revenues.

2. A clear plan and strategy (Environmental management system) in place that incorporates:

a) specific targets for reducing the carbon footprint and wider environmental impact
b) metrics on energy use, waste, travel and transport
c) Processes for regular reporting to the Senior Management team

AVRDC, CABI and icipe all have environmental management plans in place. ICIMOD, which received funding under this programme after the others, has been developing its environmental management plan.

AVRDC has reduced its carbon footprint from energy use by 8%, surpassing its target of 2% for 2013. This was achieved in spite of an increase in research activities. Management will continue to monitor and put measures in place for improving travel efficiency and minimize wastage.

CABI monitor monthly UK energy usage and quarterly GHG emissions. Overall per capita reduction in year on year GHG emissions is shown below.

icipe is implementing its ‘Green Energy Supply of icipe, Kenya’ which entails energy efficiency measures and solar energy systems. The overall objective is to reduce the electricity consumption of its premises in Kenya and to balance the remaining demand by environmentally friendly technologies.

3. HR policy and operational plans for ensuring gender balance in organisational structures and research processes implemented

All centres reported that they have either maintained or increased the ratio of female to male staff. AVRDC has developed recruitment guidelines that include consideration of gender issues and improvement in gender balance among its staff. Selection panels are briefed on how to look for potential female candidates and take decisions that lead to an improved gender balance. A better success rate in the recruitment of female staff has followed. CABI is developing a Gender Strategy Plan, with DFID input, to implement a set of gender balance indicators, ensure measurable objectives are sustainable and provide a progress report to stakeholders. ICIMOD are also developing a gender strategy and have reported that 50% of staff recruited in 2013 was female. With DFID support, the number of female scientists recruited by icipe as Postdoctoral Fellows has grown dramatically. And, the number of female interns has matched the number of male interns.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

DFID is providing multi-year core contributions to the centres with an annual performance payment based upon their achievements against some key deliverables and generic organisational behaviours set out in the logframe. DFID will continue to fund these centres for the period of the business case providing that there is satisfactory performance against these indicators. Following the 2012 performance assessment meetings, DFID notified GFAR that it would stop funding unless it is able to demonstrate:

1. Clear, concise reporting of results;
2. An effective strategy to measure impact;
3. Significant progress towards the reforms indicated in its Governance Review; and
4. Evidence of cost effectiveness.

A further review discussion was offered in early 2014 if GFAR consider it has sufficient evidence to show progress. DFID met with GFAR on 9th January and heard its case for continued DFID support. DFID subsequently concluded that it was not satisfied that GFAR had met the conditions set out above and funding stopped from April 2014 as it did not represent value for money for DFID’s research funds.

Table 3: VfM performance compared to the original VfM proposition in the business case

Centre	Centres meet internal targets for cost ratio / Baseline 13/14		Unqualified opinion from external auditors on financial statements	DFID funding no more than 40% of centre’s overall funding
AVRDC	0.23	0.19	Yes	13.5%
CABI	0.14	0.13	Yes	25%
ICIMOD	0.17	0.14	Yes	9%
icipe	0.23	0.16	Yes	29.5%

All of the centres have continued to demonstrate good financial management and value for money through further decreases in the ratio of their indirect/direct cost. The proportion of DFID funding to AVRDC and ICIMOD is significantly less than 40%, which shows that they have a wide funding base and not overly dependent on DFID. The figures for CABI and icipe have been inflated because DFID made an additional payment to them in January 2013 and both earned a performance payment. Nonetheless, they are still well below 40%.

Assessment of whether the programme continues to represent value for money

DFID commissioned an external evaluation of the multi-year performance management arrangements introduced for research funding to the international agricultural research centres during the period 2011 to 2015. The study also considers the outcomes and prospective development impacts of these centres. Landell Mills was chosen to undertake this work after a competitive process under DFID’s Global Evaluation Framework Arrangement. A copy of the ToR for the evaluation is attached at Annex 2. They have been provided with background documents, held interviews with DFID staff, peer reviewers, other donors, stakeholders and end users. They have also made field visits to each of the five centres who have received funding through this programme and interviewed Board Members, Senior Management and staff and collected data through surveys to inform their decisions. A draft report will be presented to the Agriculture Team and others on 12th March and the final report is due by end of April.

Quality of financial management

All core payments have been made as planned with the centres submitting six monthly invoices on time. The centres provided a copy of their annual audited statements in time for the annual performance review. Payments from DFID were duly recorded and all of the accounts had been given an unqualified audit opinion by an internationally recognised accountancy firm. The annual performance reviews took place during June / early July and centres were notified by the end of July about our decision to award a performance payment. DFID determined that three centres did not meet the qualifying criteria for a performance payment. And, a performance payment was made to CABI in August. The unspent funds, including the final year core payments to GFAR, have not been re-allocated.

One year costed extension proposal

Currently, DFID is considering a one year costed extension to the programme. The intention would be to provide an additional year of performance related funding to the four international agricultural research centres, the World Vegetable Centre (AVRDC), CABI, icipe and ICIMOD to scale up results. In addition to scaling up results, the additional year of funding will allow a continuation of multi-year predictable funding to these centres, whilst DFID reviews the evaluation findings and considers the benefits and approach of a new phase of support. This would be aligned with the nature of the funding mechanism, which aims to provide predictability of funding within the performance management system.

Date of last narrative financial report	June/July 2014
Date of last audited annual statement	31 December 2013

E: RISK (½ page)

Overall risk rating: Low

Research and Evidence Division has recently revised the way in which it categorises risk within research programmes – looking at management risk, output risk and intellectual risk. During this Annual Review, the risk profile of the programme was reassessed using this categorisation. Overall risk is identified as low.

Management risks are categorised as low overall. This is core funding (linked to specific performance measures) to well established organisations with good governance and strong finance and management systems. DFID works closely with other donors to these centres – in the case of icipe a full management audit was undertaken by Sida, and donors have worked together closely to ensure a coordinated response and follow up to the case of a former employee accused of claiming expenses to which they may not have been entitled.

Output risk is low. There is a high likelihood that the centres will all deliver on their core deliverables, structured around development of new technologies and scaling these up. However intellectual risk is identified as medium. This relates to the additional challenge given to the centres to make a step-change in impact measurement in particular, developing a coherent approach to monitoring and evaluation and delivering robust impact studies and evaluations of past or ongoing research and development programmes. The premise of the programme is that the performance funding management system will lead to higher performance in key areas. This is something that is currently being evaluated by a DFID commissioned external evaluation.

Outstanding actions from risk assessment

The main actions from the risk assessment are to ensure clear communication from DFID to the centres on the expectations in relation to the actions arising from each performance review, ensure that these actions or recommendations are specific, measurable and time bound so that progress can be tracked. With this in mind, more detailed feedback was provided to centres in mid 2014. In early 2015, the costed one year extension provides an additional opportunity to provide mid-year feedback on progress against recommendations.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe and Performance of partnership (s)

The project is proceeding as intended with all four of the remaining centres performing satisfactorily or better. DFID will receive an independent assessment of the programme’s performance from the external evaluators in mid-March when draft findings will be available. Further analysis based on this evaluation will be available for the next Annual Review.

Asset monitoring and control

N/a

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

In 2014, using the Global Evaluation Framework Agreement, DFID commissioned an evaluation of the multi-year performance management arrangements introduced under this programme. The study is now underway, and is due to deliver the final report in April 2015. The evaluation has two main objectives:
1. To assess the effectiveness of DFID’s performance management funding mechanism in delivering high quality research, delivery of results and value for money.
2. To make recommendations to DFID’s Research and Evidence Division on performance management funding of research, including metrics.
It is envisaged that the immediate and main users of the evaluation are DFID’s Agriculture research team, and other parts of DFID’s Research and Evidence Division. It is also expected that it will be of value to the international agricultural research centres themselves, and will have relevance to discussions within the CGIAR system on value for money.

It is anticipated that the findings of the study will feed into discussions by the Agriculture Research team on future performance funding to international agricultural research, from 2016 onwards, as well as research funding more broadly in DFID. It is expected that the findings of the evaluation will also be of wider interest to other donors and funders of research.

Monitoring progress throughout the review period

The main focus of monitoring is the annual performance reviews. However, DFID is available for additional dialogue and exchange with each centre between formal review periods. The extent to which different centres have taken up this opportunity has varied. Field visits to the centres have been important in strengthening the partnership and a two-way dialogue. DFID Agriculture Research team should formally draw attention of the partners to their availability for follow up discussions on partnership or aspects of performance (recommendation #3).

I Review Process

This annual review draws upon the performance review of the four centres undertaken in mid 2014. It is also informed by a field visit to AVRDC and CABI projects in Tanzania made by Andrew Clayton in June 2014, visits to ICIMOD made by Alan Dangour in November 2014 and Rachel Lambert in January 2015. The review process was led by Alasdair Swift (Deputy Programme Manager) and Rachel Lambert (Senior Responsible Owner/Lead Adviser).

The annual performance review of each centre was led by an internal DFID team (Rachel Lambert, Alasdair Swift), supplemented by inputs from the two Senior Research Fellows, Maggie Gill and Alan Dangour and drawing on inputs from a Social Development Adviser (Andrew Clayton) and other Agriculture Research Team members. Paula Challinder (Head of Profession, Livelihoods) joined the performance review meetings for AVRDC, CABI and icipe. The South Asia Research Hub and DFID India participated in the ICIMOD review meeting. The overall assessment for each centre was agreed by the performance review panel.

The performance review involved each of the five centres providing a written report of their progress against the key deliverables and milestones in the logframe. Each centre was invited to give a presentation to the performance review team based upon their report. This allowed each centre to elaborate on the information provided. And, the performance review team to ask questions to inform the discussion about how each centre had performed. Following the presentations, which were held on 5th, 6th & 30th June and 4th July 2014, the performance review team shared their findings and produced an agreed overall assessment. Each centre was notified of this assessment which included feedback. The performance review team decided which centres, if any, merited a 2013 performance bonus.

Documentation (Quest No)
Business case (3717589)
Logical framework (3719418)
AVRDC 2013 Performance Report (4554926)
CABI 2013 Performance Report (4555447)
ICIMOD 2013 Performance Report (4555456)
icipe 2013 Performance Report (4555048)
AVRDC 2012 Annual Audited Accounts (4851464)
CABI 2012 Annual Audited Accounts (4626189)
ICIMOD 2012 Annual Audited Accounts (4626199)
icipe 2012 Annual Audited Accounts (4851474)
BTOR - Visit to Agricultural Research Partners in Tanzania, June 2014 (4548393)
BTOR - Meeting with ICIMOD, Kathmandu, 19 – 20 November 2014 (4746816)
BTOR – Visit to Nepal: Including ICIMOD (4870303)
Submission on funding to ICIMOD (3856329)
Submission to Secretary of State for Additional funding (3794820)
Letter to AVRDC about Panel’s Assessment of 2013 Performance (4680616)
Letter to CABI about Panel’s Assessment of 2013 Performance (4680612)
Letter to ICIMOD about Panel’s Assessment of 2013 Performance (4680614)
Letter to icipe about Panel’s Assessment of 2013 Performance (4680618)
Terms of Reference (4851685)
Annual Review Scoring Sheet (4826484)

Annex 1

DFID expectations with respect to impact evaluation

One of the explicit aims for DFID’s performance funding to international agricultural centres is to stimulate an increase in the conduct of robust impact evaluations by centres. The outcome indicator in the log frame against which to track progress on this aim is “robust system for ex-post impact in place”, with each centre asked to undertake or initiate at least one impact assessment per year that is able to robustly demonstrate the impact of an agricultural technology or intervention on productivity, incomes, nutrition and livelihood indicators.

In order to demonstrate a case for good or very good value for money, DFID has asked centres to raise the quality of their impact assessment. In particular, DFID is asking centres to:

1. Make more use of experimental approaches in order to capture attribution;
2. Monitor measures of cost-effectiveness as well as impact;
3. Integrate gender specific analysis;
4. Generate research outputs from impact evaluations leading to publication in peer-reviewed journals;
5. Make greater use of external evaluation teams and advice to strengthen credibility;
6. Enhance dedicated internal capacity for monitoring and for designing scientifically robust evaluations, with skills in both social and natural sciences. These staff must be linked into the latest thinking on evaluation methods in agriculture;
7. Develop a strategy for selecting technologies or interventions on which to conduct impact evaluation studies;
8. Provide sufficient internal resources to address adequately M&E needs and/or a strategy to attract external resources.

ANNEX 2 TERMS OF REFERENCE

Evaluation of DFID’s Performance Management Funding of International Agriculture Research Centres

Overall Purpose
DFID wishes to commission an evaluation of the multi-year performance management arrangements introduced for our research funding of specific international agricultural research centres over the period 2011 to 2015. The study will also consider the outcomes and prospective development impacts of these centres.
Introduction and Context

DFID is a substantial investor in international agricultural research. A significant proportion of this investment is channelled through a network of international agricultural research centres, known as the CGIAR system. Additionally, current investments include a programme to support other selected agricultural research centres, titled ”Support to International Agriculture Research Centres that benefits Poor People”.

The original programme approval was for £30m. An extension was approved taking the programme total to £40m over four years from 2011-2015. The intended impact of this programme is agricultural growth that contributes to poverty reduction and improvements in nutritional status. Under this funding, DFID planned to scale up its support to high performing international agricultural research centres, linking funding to delivery in order to leverage higher performance, particularly around scaling up and robust systems for impact measurement.
The intended outcomes of the programme as a whole are:
- New technologies, products and knowledge to address agriculture yield gaps, hunger and malnutrition;
- Technologies, products and knowledge put into use at scale;
- A step-change in systems to measure impact.
The programme adapted the value for money assessment framework used in the DFID Multilateral Aid Review (MAR) in order to prioritise research centres, and to structure the deliverables against which each centre is measured. The methodology used to prioritise centres uses a set of rigorous criteria reflecting both cost and value for money, results focus, performance, accountability & transparency, gender & environmental considerations, and research excellence.

Based on these assessments, core funding was initially allocated to 3 research centres, representing an increase in levels of funding to these centres:
- CABI
- World Vegetable Centre (AVRDC)
- International Centre of Insect Physiology and Ecology (icipe).

Funding of another centre, the Global Forum on Agricultural Research, was also continued, but at a reduced level[1].
[1] An early decision was taken not to continue funding one centre, Crops for the Future (CFF), formerly the International Centre for Underutilised Crops (ICUC). For this reason we consider this centre not to be amongst those falling within the scope of this evaluation. However, funding was phased out, allowing CFF time to seek other donors, so it did receive 0.75% of the total programme budget.
During 2012, based on an additional value for money assessment, using the same methodology, funding of a fifth centre commenced:
International Centre for Integrated Mountain Development (ICIMOD)

In November 2012, additional funding of £10m was made to two centres, CABI and icipe, taking the total programme from £30m to £40m. This additional funding was made in response to the inaugural performance review, which had demonstrated evidence of excellent research quality with development impact and value for money for DFID. These centres also showed that they could scale up their work to meet strong Ministerial interest in the use of science and innovation in tackling poverty and in new forms of partnership with the private sector to deliver development outcomes.

The Performance Funding Mechanism
A key feature of the programme is a commitment to multi-year funding, as well as to an increased level of DFID funding to most centres. This phase of support represented a shift in approach for DFID, away from the previous funding to these centres, which involved ad hoc annual core funding allocations, with limited partnership dialogue and engagement. This had the intention of enabling centres to plan strategically and maximise use of DFID resources. Greater security of baseline funding was intended to enable centres to maximise and commit staff resource and map out individual and programme budgeted work plans over a longer timespan than would otherwise have been possible.

The performance funding mechanism involves the following features:
- Multi-year funding: to enable improved planning of resources by centres, resulting prospectively in more effective use of DFID resources.
- Performance related element: scaling up funding to high performing centres. Funding to comprise of a guaranteed minimum core contribution plus an additional scalable element. The additional element will be allocated on the basis of performance against 3-5 high level deliverables for each centre.
- Value for Money: based on a systematic approach to assessing value for money and organisational behaviours across each centre. Funding would be linked to specific conditions related to organisational behaviour (including gender responsive organisations, climate smart behaviour, and results focus) and maximising delivery and influence.
- Strategic: it would enable DFID to use our funding to leverage results and to direct additional resources to emerging DFID research priorities.

The implicit theory of change in implementing this new approach has been that longer term funding, a tighter set of agreed deliverables, a mechanism for regular dialogue and partnership, and a performance bonus will improve performance of the individual centres in specified areas, and lead to results more closely aligned to DFID priorities.

Within this programme, DFID’s Agriculture Research team have adopted a distinctive approach to performance reviews. Each centre is assessed annually against 3 or 4 key objectives (which they identified) and organisational behaviours (see box). The centres write a performance review report which is followed by a presentation to and questioning from the performance review team of DFID staff supported by peer reviewers. The review team then share their findings and produce agreed assessments. Centres have the opportunity to respond formally to each review.

This process has been introduced and is specifically designed to monitor and drive up performance and, hence, value for money. It incorporates an incentive of a 20% performance bonus awarded to those demonstrating sufficiently good performance.

The first performance review of four centres was held in July 2012 and the second performance review of these centres plus ICIMOD was completed in mid-2013.

This novel approach to programme management, i.e. an annual performance review of each centre coupled with an annual review of the programme, together with periodic external reviews of the organisations commissioned by their Boards, means that a large volume of programme documentation has already been collated and will be available to the evaluation team from the outset. It may also be – a hypothesis – that the rigour of assessment and quality of DFID documentation is enhanced because a decision on the bonus is a mandatory output of each review.

In the judgement of the DFID staff carrying out the latest annual review of the programme, the new approach to multi-year performance management funding is working effectively. However, there is explicit recognition that this ‘needs to be assessed independently of DFID’ within this external evaluation.

Objectives, Scope and Evaluation Questions

  1. Objectives

The evaluation has two main objectives:
1. To assess the effectiveness of DFID’s performance management funding mechanism in delivering high quality research, delivery of results and value for money.
2. To make recommendations to DFID’s Research and Evidence Division on performance management funding of research, including metrics.

DFID funding is the focus of these objectives, but it is important to recognise that DFID is one of several funders of each of these centres and does not fund specific areas of work or projects.

3.2 Scope

The scope of this evaluation covers the period of funding from October 2011 – May 2014.

3.3 Evaluation Questions
The primary evaluation questions are:
Do DFID and each of the centres share an understanding (implicit Theory of Change) of the aims, operation and expected effects of the multi-year performance funding mechanism?

What has been the response of the centres and the reaction of other donors and stakeholders and, in their judgement, how effective to date is this mechanism proving to be?

1. What is the evaluators’ (independent, evidence-based) assessment of the intended and unintended, positive and negative effects of the funding mechanism? How can it be made more effective? The assessment should cover both delivery of the centres against their core research deliverables as set out in the agreement with DFID, as well as the cross cutting issues of gender, environmental management systems and value for money.
2. To what extent has this funding mechanism delivered or improved the quality of research outputs, with particular regard to deployment of technologies and robust measurement of impact, in relation to more conventional funding mechanisms (both project funding and core unrestricted funding)?

What are the lessons from this experience of performance management funding of research, and on performance metrics, which could be of relevance within DFID Agricultural research and DFID research more widely?

What progress, if any, have the centres made towards demonstrating their outcomes and ultimate impacts through improved documentation, internal studies and commissioned evaluations?

What evidence (selective but robust) of achieved or prospective development impacts (or lack thereof) has been generated through this evaluation?

Note that while the logframe outcome and impact (singular) are within scope of these questions, the evaluation will range across outcomes and impacts (plural, including unintended and generic).

3.4 Users and audience of evaluation

It is envisaged that the immediate and main users of the evaluation are DFID’s Agriculture research team, and other parts of DFID’s Research and Evidence Division. It is also expected that it will be of value to the international agricultural research centres themselves, and will have relevance to discussions within the CGIAR system on value for money.
It is anticipated that the findings of the study will feed into discussions by the Agriculture Research team on future performance funding to international agricultural research, as well as research funding more broadly in DFID. It is expected that the findings of the evaluation will also be of wider interest to other donors and funders of research.

4. Methodology

Tenderers should spell out as fully as possible the evaluation design and methodology they propose to use, the allied potential risks and challenges for the evaluation and how these will be managed. DFID has not endorsed particular methodology(ies) for the conduct of this research programme evaluation, but in this case would expect a design that takes a multiple methods approach and systematically triangulates evidence. Therefore, while we suggest some options below, tenderers are invited to propose an approach and methods which they believe will most effectively and efficiently meet the purposes of the study within the time available. The successful tenderer will then refine this proposal within the first month or so of the contract, in consultation with DFID and other relevant stakeholders. Please note that we are committed to quality and rigour in line with international good practice in evaluation.

Theories of Change (ToC) both overall for this DFID programme funding and for each centre are currently implicit within the extensive documentation. During the inception phase we should like the evaluation team to develop a straightforward ToC (diagram and narrative) specifically for the multi-year performance funding mechanism (i.e. the package of support include multi-year core funding, performance funding built around core centre deliverables and cross cutting issues). We do not require full ToC for the programme and centres, though tenderers may propose to incorporate ToC work into their study as they see fit.
We anticipate that there will be one or more comparative element(s) to the evaluation, potentially in respect of DFID support for these centres prior to the introduction of the performance management system, concurrent experience of other donors operating more traditional funding models and/or experience at other research centres.
The methods and assessment frameworks employed for this evaluation should facilitate the collection and analysis of data, be relevant to the questions outlined above, and make optimal use of existing data. The evaluation may need primarily to use retrospective evaluation methodology techniques, although some baseline data does exist in previous reviews. Particular attention should be paid to documenting both quantitative and qualitative progress on the areas identified. Should robust evidence emerge of changes resulting from DFID’s recent engagement with these centres, the evaluation team will need to tackle the further challenge of assessing the extent to which these are due to the performance management mechanism as a whole, and/or simply reactions to increased, longer-term funding.

Sources that will be used in the evaluation would, at a minimum, include:
Document review: Review of key documents including those outlined in Section 2. A table of key programme and project documents will be prepared for the evaluation team by DFID and the international centres, with further assistance available, if required.

Interviews with key partners and users: Interviews with each of the research centres. Also interviews with other funders, Board members and stakeholders including end users and close collaborators may be considered. These interviews may be done in person if feasible, but most likely by telephone or internet based communication.

Interviews with DFID staff and peer reviewers: interviews with the DFID staff involved in overseeing the funding mechanism, and those involved the annual performance reviews including Senior Research Fellows.

Visits to centres and field: Face-to-face meetings should be held with a minimum of three out of five research centres.

Surveys or other data collection methods: to solicit input from additional stakeholders external to DFID. If surveys are used, these should be rigorously designed with appropriate sampling methods and expectation of acceptably high response rates. Alternative or complementary approaches, such as online discussion fora, could be considered.

For VFM assessment, data should primarily be drawn from the administrative reporting systems of the centres. Comparisons could be made with other similar programmes such as centres of the CGIAR and research programme consortia including Future Agricultures Consortium, International Growth Centre or Leveraging Agriculture for Nutrition in South Asia (LANSA).

Tenderers may wish to make use of the following online resource, though (to re-iterate) we are seeking a rigorous approach without preconception of the detailed methodology: http://www.ukcds.org.uk/resources/evaluating-the-impact-of-research-programmes
The evaluation should ensure that it adheres to the ethical evaluation policies of DFID and the evaluation principles of accuracy and credibility.

Timetable and Milestones

Please propose a detailed timetable, having regard to the following:

Primary Activity	Deadline
Evaluators selected and contracts put in place.	September 2014
Inception Report Submitted to Management Group / Approach should be finalised in consultation with DFID. This Inception Report should include a Theory of Change, suggestions on refinements/amendments of the evaluation questions, the full methodology, implications for the degree to which the evaluation questions can be answered using a credible and robust evidence base, assessment frameworks, identified sources of data and risk management strategy. Plus a communications plan for the evaluation.	By 10th October 2014
Management Group provide feedback and approval.	By 17th October 2014
Data collection and analysis	To be started by mid-October 2014
Draft Final report submitted for comment. / Report should include (though not necessarily in precisely this structure): / Cover page. / Table of Contents. / Executive Summary: maximum four pages. / Purpose of Evaluation. / Evaluation approach and methodology. / Response to evaluation questions with supporting evidence. / General findings, key messages and potential implications. / Annexes – additional supporting evidence as relevant; detailed methodology.	Mid-February 2015
Single presentation to Management Group (and others) to discuss draft findings	February 2015
Final Report / Final report should take into account comments on the draft report from DFID	End of February 2015

5. Evaluation Outputs
The Evaluation Team will produce the following outputs:
- Inception Report including refinements/amendments of evaluation questions, full methodology, Theory of Change, assessment of which evaluation questions can be answered using a credible and robust evidence base, identified sources of data and risk management strategy, and a communications plan.
- Draft Final Report
- Presentation to Agriculture research team and others
- Final report for publication including Executive Summary that incorporates feedback obtained on the draft report
- Appendices with details on the methodology, informants, etc.
- A “policy brief” summarising the main findings of the evaluation for circulation to stakeholders.

Please note that the inception report and/or the final report may, at DFID discretion, be forwarded for external quality assurance / peer review (which generally takes 10 working days). However, we expect not to apply this to the inception report unless unanticipated key issues arise during this phase.

6. Evaluation Management Arrangements
The evaluation will be overseen by a Management Group. This group will be responsible for approving the evaluation outputs and commenting on draft reports.
The Group will include the following DFID staff:

Alasdair Swift (lead contact), Rachel Lambert, Andrew Shaw

The team will also provide the link between the evaluation team and the Centres themselves, and coordinating information inputs from DFID.
Liaison between the Management Group and the evaluation team will include up to three meetings and two presentations by the evaluators (one to present and discuss the inception report/evaluation plan; and a second for the draft report). These meetings will take place in London or East Kilbride, and may involve teleconferencing or video conferencing.

7. Documentation

Annex 1. Business Case
Annex 2. Logframe.
Annex 3. 2011 Annual Review.
Annex 4. 2012 Annual Review.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process