Annual Review

Title: Better Jobs in Bangladesh (205275)
Programme Value £ (full life): £ 6.6 million		Review Date: 08 August 2018
Programme Code: 205275-101	Start Date: 01 July 2017	End Date: 31 December 2023

Summary of Programme Performance
Year	2018
Programme Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/9085375.odt
DevTracker Link to Log frame:

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

Better Jobs in Bangladesh is a £6.6 million six and a half year programme to improve the working conditions and safety standards in the Ready Made Garments (RMG) sector of Bangladesh. This is the successor of the emergency response programme that DFID funded post Rana Plaza collapse in 2013. This collapse was one of the largest industrial disasters of Bangladesh that caused an estimated death of 1,134[1]. The UK, along with the Netherlands and Canada will spend up to $24.5 million until December 2023 through the International Labour Organisation (ILO).
[1] https://en.wikipedia.org/wiki/2013_Savar_building_collapse

The previous programme (Supporting the National Action Plan for the Garment Sector in Bangladesh, 2013-17) was successful in completing remediation assessment of factories (1379 factories, about 38% of the industry) that were not covered by the two international initiatives called the Accord[2] and Alliance[3]. The learning from it was that only assessment of the factories is not enough and the Government of Bangladesh (GoB) requires the right capacity to inspect the factories on a sustainable basis and enforce laws so that factories make the required remediation. So, this programme is supporting GoB to set up systems and process and develop capacity to inspect factories on its own, enforce laws in terms of safety and labour standards and mainstream occupational health and safety. This will provide assurance to the brands and buyers, sourcing from Bangladesh, on workplace safety and support Bangladesh to improve international competitiveness and secure jobs. The RMG sector generates more than 80% of the export earning of the country and employs about 4 million people, the majority of them women. Bangladesh aims at doubling its exports by 2021, which potentially means additional jobs for the poor.
[2] http://bangladeshaccord.org/
[3] http://www.bangladeshworkersafety.org/

The programme works in four areas: (1) Remediation of Factories (2) Developing National Inspection Capacity (3) Mainstreaming Occupational Health Safety and (4) Supporting Better Works Bangladesh. This support will continue until 2021 during which time GOB will gradually take on more responsibilities, and only backstopping support will be provided until the programme exits in 2023.

Other than funding this programme through ILO, the UK is also part of a platform called the 3+5+1 where three GoB Secretaries (Labour, Commerce and Foreign Affairs) and five Ambassadors (UK, USA, Canada, EU and one on rotating basis) along with ILO meets at regular intervals to discuss safety standards and labour rights issues of the RMG sector. UK also plays a strong role in the EU’s Sustainability Compact[4] that works on labour rights, workplace safety and responsible business conduct.
[4] http://www.ilo.org/dhaka/Whatwedo/Projects/WCMS_396191/lang--en/index.htm

Summary supporting narrative for the overall score in this review (1/2 page)

This Annual Review (AR) scored an ‘A’. The programme substantially met many of its expectations in year one though it missed some of the targets. This is to note that the programme logframe uses June 2017 as baseline and December of each year for reporting results. In this review the output indicators are scored based on whether the programme is on track or showing early indication to deliver the targets by December 2018.

A key pillar of the programme is to develop capacity of the Remediation Coordination Cell (RCC) so that it becomes an independent government inspection agency that will be both credible to the brands and buyers and will force the factories to remediate. It is important for GoB to support RCC as this is also one of the preconditions for Accord and Alliance to exit from Bangladesh. The capacity of this organisation as an independent and credible entity has been raised in both 3+5+1 and the recently concluded Sustainability Compact assessment in Brussels[5]. The programme needs to work on finding the right incentive for the factories to collaborate more with RCC. This incentive model will help RCC to become sustainable in the long run. The number of inspection is going up, but the number of remediated factories is not progressing as rapidly. The output related to RCC inspection scored an A but the output related to the sustainability of RCC scored a ‘B’ in this AR.
[5] http://trade.ec.europa.eu/doclib/events/index.cfm?id=1853

The programme has been able to make Occupational Health and Safety (OSH) a priority for GoB so it scores an ‘A’ in this AR but to mainstream it, the programme needs to continue to set up the Safety Committees at factories. These safety committees enable the RMG workers to understand workplace safety better and inform management on remediation requirements.

In Better Works Bangladesh (BWB) component the factories have not started benefiting from a reduced numbers of audits and compliance costs. The number of factories registered with BWB is not yet adequate to create the impact it intends to do. BWB needs to speed up in recruiting factories and make it a commercially viable model. This component scores a ‘B’ in this AR and in the next one year the programme needs to make an assessment of whether to continue to support BWB or not.

Based on the overall performance, the programme is on track to deliver the outcome targets so it scores an ‘A’.

Recommendations for the year ahead (1/2 page)

Based on this review the recommendations for each section have been outlined in Section B, but overall the programme needs to prioritise the following:

- Work on improving the capacity of RCC, find the right incentive model for the factories to cooperate more with RCC and make it a credible organisation to the brands and buyers by mid-2019.
- Closely work with Department of Inspections for Factories and Establishments (DIFE) and RAJUK (responsible for building permits in greater Dhaka) to ensure the risky factory premises that are closed by DIFE, are not being used for other commercial purposes.(report it as part of the quarterly reports).
- The root cause of challenges related to access to finance needs to be identified. If ‘providing information’ is not working, then the approach needs to be changed by mid-2019.
- The factories need to benefit from improved compliance and reduced number of audits through Better Works Bangladesh (BWB). If BWB cannot achieve the scale needed then make an assessment before the next AR whether to continue supporting BWB or not. This component will do a midline impact assessment in July 2018. The outcome of this assessment will support in making this decision.
The logframe of the programme needs to be revised to align it with what the programme can deliver on ground and also with the review period of the programme by December 2018. As part of this exercise, the programme can also explore options of addressing disability through its different components.
## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	A Remediation Coordination Cell (RCC) is established / Employers, workers and buyers are better equipped to support and sustain remediation efforts
Output number per LF		1	Output Score	A
Impact weighting (%):		35%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 (a) A compliance and escalation protocol in place	Baseline (June 2017): Compliance Protocol introduced for discussion / Milestone (Dec 2018): Compliance Protocol is fully adopted	Moderately did not meet expectation / The compliance and escalation protocol was approved by DIFE and awaiting enforcement by the MoLE.
1.1 (b) Proportion of relevant cases examined by the Review Panel for immediate action	Baseline (June 2017): / Baseline tbc based on RCC forecast of remediation items / Milestone (Dec 2018): 100% of the relevant cases examined by the Review Panel for immediate action	Met Expectation / 100% of the relevant cases examined by the Review Panel for immediate action.
1.1 (c) Frequency of visits to factories by RCC representatives	Baseline (June 2017): 40 / Milestone (Dec 2018): 40 by Dec-2017, 900 by Dec-2018, 1500 by Dec-2019, 1500 by Dec-2020, 1500 by Dec-2021	Met Expectation / 755 National Initiative (NI) factories under remediation were visited more than once.
1.2 (a) Information provided to factories by the RCC on remediation and access to finance (per factory, based on priority)	Baseline (June 2017): 0 / Milestone (Dec 2018): Information provided to 1500 factories by the end of 2018	Did not meet expectation / 300 factory representatives were informed on remediation and access to finance

Provide supporting narrative for the score
This output scores an ‘A’ in this annual review.

The objective of the indicator is to set up a functional Remediation Coordination Cell (RCC) that has the right capacity to do inspection and enforce remediation of all garments factories in the industry. RCC needs to build confidence amongst the buyers as a credible government institution that can enforce law and ensure workplace safety in factories. Another core responsibility of RCC is to coordinate all the remediation activities undertaken by Accord, Alliance and National Initiative (NI- supported by DFID) since the Rana Plaza collapse in 2013 and take on responsibilities from Accord and Alliance as they gradually exit from Bangladesh.

The programme supported GoB to set up the RCC in the first phase (ended in 2017) and the following was done during first year of the current phase:
- A task force and a core body for RCC were set up to develop and monitor the principals and action plans of RCC. This will guide RCC on its next course of action.
- The programme provided skills training to enhance technical knowledge of the RCC engineers. Within June 2018, 43 engineers and inspectors received training on understanding preliminary assessment reports, Correction Action Plan (CAP) formulation, orientation on Detailed Engineering Assessment (DEA) Guidance Manuals of fire, electrical, and structural safety. This contributed in capacity development of RCC engineers with the right skill to assess the factories.
- Department of Inspection of Factories and Establishments (DIFE- works with RCC) reported that among the 640 factories they visited in 107 factories remediation works were 100% completed, in 111 factories it was at 80% and in 422 factories it was at 50%.
- In the first phase it was identified that access to finance is a key challenge for remediation- so in this phase 300 factory owners/representatives were reached through different sessions and 10 factory owners conducted follow-up one-to-one discussions with Bangladesh Bank on the application process for accessing remediation financing.

The programme worked very closely with Ministry of Labour in developing the capacity of RCC and is on track to deliver the results for December 2018. The challenge is to improve the acceptability of RCC as a credible inspection body in the long run.

Lessons identified this year, and recommendations for the year ahead linked to this output
Lesson learnt:
Finding the right incentive for the factories to remediate the CAP suggested by RCC/ DIFE is important. Only law enforcement is not sufficient to make this happen. Remediation took place quicker at Accord and Alliance factories because brands are signatories in those initiatives and there was a risk of losing business. The factories under the remit of RCC, in most of the cases, do not have direct contracts with the brands and fall quite low in their supply chain. So, they do not have the right incentive for remediating as quickly as others. These factories also fall in the mid to bottom tier of the industry where the compliance is quite weak.

Recommendation for the year ahead:
- The capacity of RCC is termed weak by Accord, Alliance and the international brands. This also came up in the Sustainability Compact of EU held in Brussels in June 2018. On the other hand GoB is discussing the gradual exit of Accord and Alliance and has strong commitment to strengthen RCC. So the programme needs to work on finding the right incentive for the factories to remediate the CAP suggested by RCC/ DIFE and put it into strategies and action immediately to complete these.
- The programme needs to make a thorough analysis of the problem related to access to finance for remediation financing, find the root cause of low uptake of the available finances and provide solutions that will bring up the number of remediated factories.
- The three regulators responsible for safety, the Department of Inspections for Factories and Establishments (DIFE) and the Fire Services and Civil Defence (FSCD) have made progress on, while RAJUK (responsible for building permits in greater Dhaka) has not. As a result, the programme has to rely on private sector engineering companies to complete building inspections and support the development of CAPs. The programme needs to be clear on what can be accomplished by the different agencies, particularly RAJUK, and plan strategies accordingly. This is to note that while DIFE has the authority to inspect factories and close them; it does not have the authority to close buildings. That responsibility lies with RAJUK.

Output Title	One-stop-shop for industrial safety and compliance established and functional / Gender sensitive labour inspection capacity developed
Output number per LF		2	Output Score	B
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 (a) One-stop-shop (Single Window Service) proposal and business processes recognised and agreed by all relevant ministries	Baseline (June 2017): Single Window Service concept agreed in principle by stakeholders / Milestone (Dec 2018): One-stop-shop piloted	Did not meet expectation / The ToR for the National Steering Committee (NSC), which will lead the one-stop-shop, was approved by the DIFE. But one-stop shop not piloted yet.
2.1 (b) Recommendations for harmonised building and fire safety policies in line with international standards and practices issued	Baseline (June 2017): Single Window Service concept agreed in principle by stakeholders / Milestone (Dec 2018): Review process established	Met expectation / DEA Guidance Manuals developed; / GoB Remediation Strategy developed and endorsed.
2.2 (a) Proportion of labour inspectors who report increased knowledge and skills acquired through practical training (disaggregated by sex)	Baseline (Jun 2017): 72% / Milestone (Dec 2018): / No target	No target for 2018 / Trainings have not been initiated yet.
2.2 (b) Proportion of trained staff within DIFE who report increased knowledge on gender issues (disaggregated by sex)	Baseline (Jun 2017): Will be collected during the first round of trainings. / Milestone (Dec 2018): 10% percentage point increase from the previous year	Did not meet expectation / The training was not initiated by the programme, so not expected to generate results by December 2018.

Briefly describe the output and provide supporting narrative for the score
This indicator scores a ‘B’ in this annual review.

The objective of this indicator is to ensure the right governance structure is there for GoB to effectively regulate industrial safety (not only garments) with staffs that are credible and accountable. To do that the programme is supporting to set up a one-stop-shop for industrial safety.

The following was done during the year:
The programme supported RCC management in developing the ToR for the National Steering Committee (NSC). This body will be responsible for the oversight of remediation of garment factories and will serve as a coordinating body to address inter-ministerial decisions.
The long term strategy for RCC is to transition into an Industrial Safety Unit (ISU) that will oversee factory safety of all industries. The NSC will serve as a coordinating body for factory safety in all industries.
- DIFE, with the support of the programme, developed Labour Inspection Management Application (LIMA), which improves the capacity of the inspectors to collate information and assess the status of the garments factories more effectively. The next step is to improve LIMA to do inspection across all industries to maintain consistency in inspection and scoring.
- Gender Strategy and Action Plans were developed by the programme and communicated to DIFE for their input.

RCC is yet to establish itself as a credible inspection authority for the garments sector. It will require long term strategy and engagement to make it an umbrella organisation for other sectors. The programme worked in developing those strategies in this year, but the progress was quite limited.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons:
- The concept of RCC and its role is new to GoB and the RMG sector is yet to benefit from it. Expanding its remit across all industries and making it credible to the stakeholders will require long term engagement.
- There is lack of understanding across the policymakers/ regulators on the importance of gender mainstreaming in an industry that is dominated by female workers but managed mainly by males. Women generally are at the level of operators (lower level jobs) rather than supervisors and the industry neither has a good practice nor a law that supports capacity development of female workers to take up higher level jobs.

Recommendation for the year ahead:
- Finalise the business process of RCC that takes into consideration the transition plan to include all industry inspection activities under one umbrella. But as recommended under output 1, RCC needs to find the right incentive for factories to follow on the CAPs that it puts into place. Similar incentive models need to be identified for other industries as well.
- The Gender Strategy of the programme needs to be ambitious but also practical in terms of what it can achieve within the timeline and the remit of the programme. DFID has a Skills and Employment programme that works on systemic change in the RMG sector to improve the skills of female RMG workers and recruit them at higher paid jobs. ILO should avoid duplicating the efforts, concentrate on their strengths and strategise on making the best use of resources.

Output Title	National OSH policies reviewed to ensure proper application of the BLA / Stakeholders' capacity and awareness on OSH built in a gender inclusive manner
Output number per LF		3	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 (a) Recommendations for review of national OSH policies and standards including assessment of gender specific issues	Baseline (Jun 2017): Existing OSH policy and profile / Milestone (Dec 2018): Review process established	On Track / Discussions started with GoB on review of OSH standards and formulation of OSH National Action Plan. Support for capacity development provided to GoB.
3.2 (a) Safety Committees established through support of OSH units (BGMEA, BKMEA, DIFE)	Baseline (Jun 2017): 100 Safety Committees / Milestone (Dec 2018): 250 safety committees established	On Track / Data will be available early 2019 through DIFE Annual Inspection Report. / But the information available from Better Works Bangladesh supports the progress in it.
3.2 (b) Number of workers trained on OSH (disaggregated by sex)	Baseline (Jun 2017): 800,000 / Milestone (Dec 2018): 1,000,000	Did not meet expectation / Trainings not started yet, so not expected to deliver the targets by December 2018.

Provide supporting narrative for the score
This indicator scores an ‘A’ in this annual review.

The objective of this indicator is to improve Occupational Safety and Health (OSH) both in policy and in practise and also to assess OSH committees working in accordance with Bangladesh Labour Act (BLA). As a result of the first phase of the programme, Bangladesh now has a National OSH Day and observes it each year.

The following was done during the year:
- The programme engaged with GoB counterparts to develop a mechanism to review OSH standards and preparing OSH National Action Plan.
- To promote OSH culture and recognise achievements towards safety and health, DIFE started ‘OSH Good Practices Award’ from OSH Day 2018, which will eventually be converted into ‘OSH Excellence Award’ from next year.

The programme is on track to deliver the output targets by December 2018 and continues its effort to mainstream OSH in the RMG sector. And because of this the government (Labour Minister) also committed to introduce the awards mentioned above.

Lessons identified this year, and recommendations for the year ahead linked to this output
Lessons:
While the OSH Committees at the factories work closely with the workers, to mainstream OSH good practices it requires engagement of the factory management as well.

Recommendation for the year ahead:
- The programme needs to engage directly with the employers’ association to mainstream OSH activities and speed up the process of setting up Safety Committees at factories. These committees also need to have the right skill set to understand about safety standards and practice it at work. The employers need to capacitate the Safety Committees and a standard needs to be set on the roles and responsibilities of the employers to make it sustainable.
- The component is supposed to look into both the workers safety and wellbeing. In the wellbeing part, whether the workers are facing any gender based violence needs to be prioritised. More tangible results need to be accomplished and shown before the next annual review.

Output Title	Core service delivery model applied / Engaging stakeholders to contribute to responsible business practices
Output number per LF		4	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 (a) Number of compliance assessment reports completed in the reporting period	Baseline (Jun 2017): 170 / Milestone (Dec 2018): 250	Exceeded expectation / Total 276 Compliance assessment reports have been completed.
4.1 (b) Percentage of training participants reporting that the training was useful for their job	Baseline (Jun 2017): 50% / Milestone (Dec 2018): 60%	Substantially exceeded expectation / Approximately 90% of the training participants reporting that the training was useful for their job.
4.1 (c) Number of labour inspectors participating in coordinated factory visits with EAs	Baseline (Jun 2017): 0 / Milestone (Dec 2018): 50	Did not meet expectation / No progress has been made as of yet.
4.1 (d) Number of workers impacted by the programme (disaggregated by sex)	Baseline (Jun 2017): 0 / Milestone (Dec 2018): 400,000 / 55% female	Met expectation / Approximately 451,436 workers have been impacted by the programme among which 56% of them are female.
4.2 (a) Number of buyer/ buyer associations affiliated with BWB	Baseline (Jun 2017): --- / Milestone (Dec 2018): 25	Did not meet expectation / 18 buyer/ buyer associations affiliated with BWB.
4.2 (b) Number of factories recruited to the BW programme	Baseline (Jun 2017): --- / Milestone (Dec 2018): 300	Did not meet expectation / 216 factories have registered with BWB, 156 of them are active factories
4.2 (c) Programme revenue generated	Baseline (Jun 2017): --- / Milestone (Dec 2018): USD 596,530	Did not meet expectation / During July 2017 to June 2018, the programme generated revenue of USD 441,208 from factory registration fee

Provide supporting narrative for the score
This indicator scores a ‘B’ in this annual review.

The objective of this indicator is to increase compliance standards in factories in line with Bangladesh Labour Act (BLA). This works both on factory safety and labour practices. The ultimate aim is to bring up the level of compliance in factories and reduce the number of audits the factories go through by the buyers. This will establish Better Work Bangladesh (BWB) as a platform that is valued by buyers (brands), employers and workers. BWB is part of a global initiative of ILO and International Finance Corporation (IFC) and operates in Bangladesh, Cambodia, Vietnam, Ethiopia, Egypt, Haiti, Jordan, Nicaragua and Indonesia.

BWB seeks to demonstrate the industry that there is a link between improved working conditions and increased competitiveness. It is not aimed at working with the whole industry rather to become a model of compliance for the garment sector. The following was achieved during the year:

216 factories and 18 buyers were signed up with the programme that resulted in revenue of USD 441,208. Though this does not meet the logframe target for the year but it shows that factories and buyers are willing to invest in a programme that will help them to reduce the number of audits and increase efficiency in terms of managing compliance issues.

To increase its effectiveness, BWB worked with factories on other issues like- skills training, maternity benefits etc. While workers benefited from these services, it did not help factories with reduced compliance cost. The low number of factories registered with BWB is also not helping it to achieve the required impact.

Lessons identified this year, and recommendations for the year ahead linked to this output
Lessons:
The factories need to benefit from reduced audit duplication by the brands and the brands need to benefit from increased compliance- unless this happens, the business model of BWB is not going sustain in the long run.

Recommendations for the year ahead:
- The programme needs to speed up recruitment of factories engaged with BWB through brand, factory and employer engagement to reduce the audit duplication. This has become even more important as GoB is keen to exit Accord and Alliance and the brands/ buyers require assurance that safety is not being compromised at factories.
- If BWB is not being able to achieve the scale, then the programme will consider whether to continue with this component before the next annual review. The component will do a midline assessment in July 2018. The outcome of it will help in making this decision.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The theory of change (ToC) did not change over the past year and it is based on the fundamental logic that enabling policies and organisational capacity are required to drive a reform. When labour inspection reform takes place, when RMG factories are remediated and when OSH is improved in policy and practice - these will all lead to safer and decent working conditions. This in turn will contribute to safeguard competitiveness of the sector and contribute in improving the quality of jobs.

Outcomes will translate into impacts if:
- Bangladesh’s garment sector continues to stay competitive and the global trade regime remains favourable.
- The government continues to prioritise reforms related to the garment sector and puts in place the required financial and human resources.
- International stakeholders continue to stay engaged and pursue for improvements.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The programme has the right components and action plans in place to achieve the outcome level targets. The operating environment of the programme is highly influenced by the political scenario of the country. As more than 80% of Bangladesh’s export earning is dependent on this industry, it has the right level of government priority as well. Globally no other country, especially garments producing countries, has any platform like the 3+5+1 or Accord/ Alliance or Sustainability Compact. While the priority is there, multiple stakeholder engagement also makes it a difficult environment to bring a change. Though this AR is for assessing the output targets of year 1 but we need take into consideration the political economy to assess whether it will achieve the outcome targets.

The programme will miss some output targets for December 2018 because of dependency on GoB willingness to reform in a pre-election period. So, this AR recommends fine-tuning the logframe this year to update and make it better aligned with the changing conditions and what it can practically achieve on the ground. This will not affect the results at outcome or impact level. If the programme continues to provide the support to GoB for capacity development and DFID continues to influence through its wider one HMG work in this sector, the programme will achieve its outcome level targets. But the programme needs to follow through the recommendation of this AR and find the right incentive model for RCC to make it credible to the brands and external stakeholders.

Explain major changes to the logframe in the past year (1/2 page)
N/A

Describe any planned changes to the logframe as a result of this review (1/2 page)
The programme reviewed the logical framework and made recommendation to fine-tune some indicators (at output and outcome level) in order to more succinctly capture the results the programme aims to bring about. This will not change the assumptions or the results of the programme. This review also suggests that the delivery of results needs to be aligned with the programme review period. Based on these, the logframe revision will be done by December 2018.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
The ‘Better Jobs’ Business Case set out a number of possible indicators for Value for Money (VfM), which were divided into economy, efficiency and effectiveness and were aligned with the logframe results. These are primarily around best practice of procurement, savings generated from different negotiations, selecting the most appropriate provider, increasing efficiency and maximising benefits (the list is given in the below table). The business case also sets out that the final VfM indicators will be agreed with ILO and other donors before the first annual review. This was not completed in year one but the VfM indicators will be redesigned after the logframe revision (by December 2018). This will also include developing indicators for ‘Equity’. From next Annual Review onwards there will be a better analysis of VfM.

	Good Practice	Example
Economy	Use of best practice procurement processes for big ticket items	$ saved
	Savings generated from contract negotiations	$ saved
	Outsourcing functions which can be done more cheaply externally	$ saved
Efficiency	Selecting the most appropriate private technical service providers for RCC balancing costs and quality	Number of factory visits conducted by RCC staff
		Number of factories provided information about remediation financing
	Development of capacity of government staff by ILO and private contractors	Ratio of government staff to private contractors in RCC
	Maximising the value of partnerships with sector associations and trade unions	Number of safety committees established
	Increasing the efficiency of BWB	Number of trainings and factory visits conducted by BWB.
		Number of additional programmes undertaken by BWB in factories.
Effectiveness	Building capacity of government to deliver services and ensure sustainability	Number of in-house trainings provided to newly recruited inspectors (DIFE, FSCD)
		Number of inspections completed by labour and fire services inspectors
	Building the capacity/ incentives of stakeholders to ensure sustainability	Number of Safety committees established by the trade unions and sector associations
	Maximising wider socio-economic benefits beyond the measured outcomes	Number of non-garment factories provided services relating to safety and working conditions

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

Through this programme, ILO provides technical assistance to key stakeholders to sustainably improve safety standards and workers’ rights and conditions in Bangladesh. There are multiple larger programmes operating in the garments sector of Bangladesh with funding from donor community and international initiatives. But neither of these programmes are working to improve the wider safety standards in the sector or working to improve the capacity of the government to make its inspection capacity credible and sustainable or to mainstream OSH culture.

The programme value is $24.5 million for six and half years. DFID is providing one third of it (£6.6million) while Netherlands and Canada are providing the rest. This funding also leveraged UK’s position on the 3+5+1 platform and influenced GoB to reform its labour rights standards which directly benefits the UK brands and their supply chain.

In terms of spend, in the wider portfolio, this is a relatively small scale programme but in terms of impact and influence it is high. The programme just completed the first year of its seven years and continues to build on the momentum and confidence it gained from the first phase. Though it is too early to say confidently, it is likely that the programme will be able to deliver its business case results if it continues to push the reform agenda. RMG will remain the priority sector for Bangladesh in medium to long term that now provides for 4million jobs and 80% of export earning of the country. So, strategically it is a good place to be and in terms of VfM DFID is achieving value through both the financial support and the influence.

Recommendation
1. VfM strategy to be agreed with the programme by December 2018. This will cover the revised VfM indicators as well.
2. The programme will incorporate achievements against VfM indicators in its quarterly report (from 2019 onwards).

E: RISK (½ to 1 page)

Overview of programme risk
The programme risk in increased from Minor (at approval level) to Moderate in this review. The programme operates in a politically influential environment. A lot of the reforms the programme is pushing for will only come if the government is also willing to support it. A national election of Bangladesh is coming up by the end of 2018 and it is expected that the programme will gain slower traction with the government on the reform agendas during this time. But as RMG remained a priority sector irrespective of government change in Bangladesh, the reforms will not be affected in the long run.

One of the key risks of the current phase is that, Canada has not yet received their internal approval for the fund commitment of this programme. Their office in Dhaka is committed to work in this space and they are the current chair of the 3+5+1 platform as well. Their headquarter was awaiting the fraud report before finalising approvals. Now that it is closed, it is expected that the fund commitment will come through by end of this quarter (September 2018). DFID and the Netherland have brought forward the second payment of 2018 to cover the cost of the year, but the programme needs to make an assessment to the impact of this on the results and timing in case the Canadian commitment does not come through.

ILO assesses the risks, its likelihood and anticipated impact on the programme and records these in the monthly Risk Management Framework. The programme’s main risks and their mitigation strategies are summarised in the Risk Register on Aid Management Platform (AMP).

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial and financial issues (1-2 pages)
The total budget of this programme is USD 24.5m with the UK, Netherland and Canada are contributing 33.33% equally. As of 30 May 2018, total disbursement from the donors to ILO was £ 3.59m (DFID £2.00m and Netherlands £1.64m). As of 25 May 2018, the programme spent £2.02m which represents 11% of total budget. The following table shows the budget/ allocation and actual expenditure since inception by components. Of the total commitment by all the donors of the project, 17% have already been disbursed while the expenditure is 11%. The contribution of Canada is still pending.

Table 1: Budget Allocation, Utilisation and Forecasts (2017-2018)

The key cost elements of the programme were service contracts/implementation agreement with partners, the purchase of equipment, communications, human resources, operational expenses and programme support cost with 15% in human resources and 13% in programme support cost (operation/ technical/ M&E).

Quality of financial management
ILO sends written requests to DFID to release funds for the programme implementation. At the end of each financial year, ILO also provides with audited financial statements that provides the breakdown of the expenditure.

Disbursements are made in annual tranches in coordination with the other two donors; flexible payment schedules have been adopted to prevent payments being made in advance of need. A Due Diligence Assessment (DDA) was done in August 2017 prior the funding commitment was signed. Canada has not yet committed the funds for the programme so this impacted the financial forecast and disbursement schedule for DFID. One instalment of the payment was brought forward this year which was not projected in the beginning of the year. ILO needs to improve its financial forecast and take into consideration situations like this where the delay in Canadian commitment might affect the delivery of the programme. On top of that, the programme so far has only spent 56% of the disbursed fund by the two donors and the Dutch second instalment will only be paid once ILO provides satisfactory response on the financial projection and necessity of funds.

As per the contract with the donors, ILO will provide annual Technical Progress Report and Certified Financial Statement by the end of September each year. The first report is due in September 2018.

Date of last narrative financial report(s)	n/a
Date of last audited annual statement (s)	30 June 2018 (expected to receive by September 2018)

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
As per the M&E strategy of the project, ILO applies five processes for monitoring the progress, performance and impact of the project.
- The first of these processes is internal routine programme monitoring, which is done to understand the extent to which the project has achieved the results set out in the logical framework and the activities committed in the work plan.
- The Strategic Area (SA) managers are responsible for day-today monitoring of project implementation in relation to agreed schedules and expected results. In their day-to-day monitoring activities, the SA managers review project progress through the analysis of the reports submitted by the implementing partners (IPs). They collect activity level monitoring data through regular contacts with the IPs by e-mail and telephone and through regular monitoring visits and attending important events.
- The National Programme Officers and Finance Officer jointly perform spot checks in relation to the payment claims of the IPs and to verify timely management of delivery as per work plans laid out in the implementation agreements (IAs).
- The programme also reports to all its donors according to agreed quarterly reports that records progress.

Evaluation (1/2 page)
The first round of evaluation of the programme is scheduled in 2020. In addition, BWB aims to have a midline impact assessment (only for the the BWB component) by the end of July 2018. This midline assessment will help to understand the results of the component and based on that it will be decided whether to continue with the component or not.

Learning (1/2 page)
Learnings under each of the components have been captured in Section B. on top of these:
- Continued effort and understanding the key incentives of the stakeholders to support the reform is important.
- The RMG industry of Bangladesh has grown rapidly, while the supportive trade regime (both in country and international) came in later. To bring reform in an industry of this size requires consorted effort from all stakeholders. While the programme is funding the capacity development in the inspection front and OSH culture of the country, it is also important to continue the soft influence the UK plays in platforms like 3+5+1 and the Sustainability Compact. Emphasising to GoB to bring reform is important along with influencing the brands to take more responsibility for their supply chains.

Progress on recommendations from previous reviews (1/2 page)

Not applicable as this is the first review.

This Annual Review was conducted during July 2018 by the SRO and Programme Officer of Better Jobs. The review team assessed reports and inputs provided by the programme team and cross checked it with the information provided by the Ministry of Labour in its presentations. The team also interviewed representatives of RCC and DIFE and visited the office of RCC and a Better Works factory in Ashulia, Dhaka.
GLOSSARY

AMP	Aid Management Platform
BFSCD	Bangladesh Fire Service and Civil Department
BGMEA	Bangladesh Garment Manufacturers and Exporters Association
BKMEA	Bangladesh Knitwear and Exporters Association
BUET	Bangladesh University of Engineering and Technology
BWB	Better Work Bangladesh
CAP	Corrective Action Plans
DDA	Due Diligence Assessment
DEA	Detailed Engineering Assessment
DIFE	Department of Inspection of Factories and Establishments
GoB	Government of Bangladesh
IFC	International Finance Corporation
ILO	International Labour Organisation
MoLE	Ministry of Labour and Employment
NI	National Initiative
NTPA	Tripartite National Plan of Action on Fire Safety and Structural Integrity
OSH	Occupational Safety and Health
RAJUK	Rajdhani Unnayan Kartripakkha (Dhaka/Capital Development Authority)
RMG	Ready-made Garments
RCC	Remediation Coordination Cell
ToC	Theory of Change
ToR	Terms of Reference