Business Case

Summary Sheet

Title: Kenya Devolution Support Programme – KDSP
Project Purpose: This projects aims to contribute to building more capable and accountable county governments. This means county governments that are reliable, open, inclusive, fair, provide good regulation and have integrity.
Programme Value: £23.5m (Includes £6.5m from the UK International Climate Fund –ICF)		Country/ Region:Kenya/Africa
Senior Responsible Owner: Sarah Cooper
Project Code:	Start Date: May 2015	End Date: December 2019
Quest Number:

Intervention Summary (2 Pages)

What support will the UK provide?
The Kenyan Constitution, adopted by referendum in 2010, introduced far reaching devolution to 47 newly-established counties. Devolution was formally introduced in March 2013 and has directed resources down to the local level. Hopes are high that it will improve accountability and service delivery and contribute to poverty reduction.

The UK will provide £23.5m (including £6.5m from UK International Climate Fund - ICF) to build the capacity of the Kenyan county governments. This builds on UK support over the last two years that supported the transition to this new level of government. The aim is to ensure that counties have the minimum capability required to manage the significant financial and human resources which they are now responsible for and deliver better public services.

The project aims to improve county government planning, budgeting, human resource management, results, performance management and citizen engagement. In each of these areas UK support will focus on governance, health, climate change and local economic development. The programme will help to ensure that basic services continue to be delivered, while sustainable systems are developed. This support will be delivered through the existing devolution support programmes of the World Bank, USAID and UNDP and is anchored in a National Capacity Building Framework agreed between Kenya and the development partners.

What are the main programme activities?
The activities will be jointly funded with other donors and in partnership with Kenyan Government institutions. Some activities will be common across all counties while others will be on a demand basis, given counties are starting from different bases and needs. No funding will go into the Government of Kenya’s financial system. The activities include:

Training for county government staff in areas such as planning, budget preparation, financial accounting & reporting, audit, performance management and citizen engagement to cite a few. We recognize that there are urgent short terms training needs but that Kenya needs a long term sustainable solution to training and capacity building. To address the urgent needs, UK support will provide some direct training in priority areas identified with Kenyan partners but also focus on long-term investments to institutionalize training – this includes curriculum development, training of trainers and improving systems at the Kenya School of Government.

Technical Assistance – County governments have fed back on the importance of learning by doing and that training should be complemented with coaching and mentoring. This programme will support a pool of experts available on demand to assist counties in a number of areas. Examples include how to do programme based budgeting, participatory budgeting and planning, incorporate climate change risks and opportunities into planning, increase county revenue collection, sustainable natural resources management and draft county laws.

Knowledge and Analysis – Implementing partners such as the World Bank will conduct and commission analysis on the implementation of devolution. This includes World Bank County Public Expenditure Reviews and sectoral expenditure reviews that provide comparative analysis of how county governments are spending, trends and impact. The UK will also support the Kenya Government institutions to do annual reports on the status of implementation of devolution, work with county governments to map natural resources and revenue enhancement measures, work with UNDP and UNWomen on gender audits of county plans and budgets. The programme will support south-south learning and exchange of ideas with other countries that have gone through similar devolution – so far there has been a lot of interest from county governments about the experiences of South Africa, Ghana, Nigeria and Brazil.

Systems & Policy Development e.g. the UK will support the National Government and counties to develop and implement automated performance management systems that include progress dashboards available in real time to the county leadership and with a public interface. The national government will be supported to update human resource management policies, and develop minimum norms and standards that all counties need to adhere to in recruiting and managing staff.

Why is UK support required?
Devolution is arguably the single most important governance reform since the reintroduction of multiparty politics in Kenya. It came about as part of the constitutional reforms to address the underlying causes of the 2007/8 post-election violence in Kenya. It enjoys huge public support as it is seen as an opportunity to address some of these underlying causes of conflict as well as other development challenges, e.g. regional inequality, improve accountability and public expenditure allocation. Devolution however bears risks such as disruption of public services, especially in these early years, devolution of corruption and nepotism that plagued the previous system, local level conflict over resources and elite capture and further marginalisation of women, youth, and minorities.

This is a monumental change with 47 new county governments that require support to get on their feet. Kenya has adopted an ambitiously short, and possibly unprecedented, timeline to transition – results in the first two years have had mixed but largely encouraging. Kenya cannot do this alone and requires the support of all partners. Kenya needs financial support but also technical support from other countries given the novelty of devolution in Kenya. Within the sectoral division of labour amongst Kenya’s development partners, the UK is considered by the Government of Kenya as a key technical and financial partner in the governance sector, as a whole, and devolution specifically.

What are the expected results?
The programme will contribute to building more capable and accountable county governments in Kenya. This means county governments that are reliable, open, inclusive, fair, provide good regulation and have integrity. These attributes should be clear to the local population, and offer better services than former arrangements. The expected programme outputs are- strengthened county-level planning & public financial management (PFM) systems; improved county performance management; strengthened citizen participation systems; improved capacity at county level to manage human resources and improved fiscal management and revenue collection

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?
The programme aligns with DFID’s 2011-2016 Operational Plan (OP) which, amongst other results, focuses on supporting people to have choice and control over their own development and to hold decision-makers to account. It commits to explore ways of working with the new county governments. This agenda supports the ‘Golden Thread’ of stable government: lack of corruption, human rights, the rule of law, and transparency. Devolution potentially contributes to long term stability by ensuring a more equitable distribution of resources. It also takes government closer to the people and therefore makes it easier for people to engage with, and hold government to account.

What are the key risks to the success of the programme?
The key risks are mainly political in nature. Devolution entails a redistribution of power and resources which has winners and losers – which creates possible resistance, conflict and dispute. The success of this programme will depend on Kenya’s ability to manage these disputes. Already disputes have arisen, e.g. between national and county governments over functions and budgetary resources or between county governments and the Senate on the role of the latter in holding county governments accountable. There are disputes at the county level between the county executive and county assembly over budgets and resources. This programme will, to a limited extent, address some of these risks, e.g. by holding joint programmes with county executive officials and the county assembly to help them understand their respective roles. We recognise the limitations of such technical interventions if the political incentives and interests are not aligned.

Other related risks include corruption risks – this is not about project funds but rather that forces of corruption within county governments could undermine the reforms introduced under this programme. This programme and other DFID Kenya governance programmes will invest in transparency and accountability measures to counter this. Ultimately there is promising evidence that shows that, in the medium to long-term, devolution will introduce the possibility of the public holding local leaders to account
Strategic Case

Context
Kenyans approved a new constitution in August 2010. This constitution fundamentally changed the Kenyan governance system from a highly centralised state to a devolved state with two levels of government – National and 47 County Governments. The two levels of government are distinct but inter-dependent and are required under the Constitution to conduct their mutual relations on the basis of consultation and cooperation.

The Government of Kenya in its second Medium Term Plan (MTP 2013-2017) identifies devolution as the most challenging constitutional commitment that Kenyans have made to themselves and that “making devolution work” will be the running theme, and key flagship project, of the Political Pillar under the Second MTP

While the constitution was passed in August 2010, county governments only came into force in March 2013 after the general elections. Most functions were transferred to counties by July 2013, somewhat earlier than expected. County governments consist of the County Executive headed by a governor, and a County Assembly (legislature) made up of elected ward representatives.

The objectives and aspirations in shifting to a devolved system of government are best captured in articles 174 and 175 of the 2010 constitution. These articles emphasise that devolution should: allow for self-governance by the people; promote the democratic and accountable use of state power as well as public participation in decision making; promote and protect the rights and interests of minorities and marginalised groups and; promote social and economic development and the provision of easily accessible services throughout Kenya. These objectives are onerous and citizen expectations are very high – they want to see immediate changes. Translating these objectives into reality is an enormous challenge especially since Kenya has had to create an entirely new tier of government.

Why support devolution?

In summary devolution presents:
An opportunity:
- To reduce inequality – there is vast inequality between and within counties in Kenya;
- To improve accountability through matching resources and responsibility for local service delivery with greater accountability to local communities,
- For better public expenditure allocation, based on local priorities, as opposed to nationally driven priorities.
Risks of:
- Service disruption especially in the early years;
- Devolution of corruption and nepotism that plagued the previous system;
- Local level conflict over resources;
- Elite capture and further marginalisation of women, youth and minorities.

Devolution is seen as a vehicle for addressing inequality[1] and moving away from the post-independence governance framework, which was characterised by poor governance, as evidenced by corruption, ethnic conflict, insecurity, political uncertainty; and poverty. Some of the negative outcomes of previous administrations include: the alienation of large portions of society and geographical areas from the mainstream economy; wasteful public investments; massive poverty and ethnic animosity; and cut-throat political competition and intolerance[2]. The new constitution and the devolution provisions within it, were part of a package of reforms to address exclusion, inequality and governance gaps that were among the underlying drivers that led to the 2007/8 post-election violence.
[1] Republic of Kenya (2010), Constitution of the Republic of Kenya
[2] Republic of Kenya (2011), Final Report of the Taskforce on Devolved Government

With the exception of primary and secondary education, the constitution devolved most other service delivery functions, such as health and agricultural services, to counties while retaining policy functions such as health policy, agricultural policy, macro-economic policy, internal security and defence at the national level. The argument being that county governments’ proximity to citizens would give them a better sense of local needs and allow for greater allocative efficiency and responsiveness. This proximity would also make it easier for citizens to participate in and oversee the affairs of government.

Broadly, the challenge is twofold;

- Risk management and managing the transition (the here and now):as the new county and devolution structures ‘bed in’, Kenya will need to minimise service delivery disruption and ensure a minimum standard of public financial management; public sector management; social accountability and; avoid breakdown of inter and intra governmental dialogue and collaboration. The hope is that most of these are transitional teething problems and, with sufficient effort, would stabilize in the medium-term.
- Transformation (where counties want to be in 5-10 years): to deliver against the promise of devolution as enshrined in article 174 of the constitution, i.e. greater local level economic development, equity, better service delivery and accountability.

In reality, these two challenges are neither linear nor neatly sequenced. Public expectations of devolution are high and county governments have to deliver against both challenges simultaneously. The constitution had envisaged a phased transition where counties would first establish their public administration structures and capacities and, once they demonstrated capability to take on devolved functions, these would then be devolved to them. Under these arrangements there would have been asymmetrical devolution as some counties would have been able to take on devolved functions earlier than others. However political pressure from counties saw Kenya forego the phased and asymmetrical approach, and instead adopt a “big-bang” approach, with most devolved functions being devolved to counties by July 2013, less than 6 months after the county governments came into office.

If we take the health sector as an example, there has been rapid progress since the election and subsequent moves to devolution, with progress on county level management and planning most notable. A recent World Bank report states that in this transition period health outcomes and utilization of health services have improved significantly: child mortality has reduced, more children are being immunized, and the impact of communicable diseases has lessened[3]. But not everything is rosy, a considerable number of political and institutional issues still remain due to: the speed of change; the continued need and scale up of capacity building linked to devolution; and the on-going uncertainty concerning roles and responsibilities between national and county administrations. This includes emerging concerns about the ability of counties to maintain the standards of key health institutions, e.g. hospitals at county and sub-county levels. (This varies from county to county). It is recognized that there is still much work to be done to ensure that the necessary skills and resources are in place to effectively manage the devolved health system, and prevent service delivery interruptions.
[3] World Bank, 2014 Kenya Public Expenditure Review: Laying The Foundation For A Robust Health Care System in Kenya

Current DFID support to Devolution
The UK has already been supporting devolution in Kenya. The bulk of dedicated devolution programming has been under the governance portfolio, but there has also been support from the investment climate, health, climate change and programmes operating in the arid and semi-arid lands (ASALs). This goes to show the cross-cutting nature of the devolution challenge.

In the governance sector, the UK has so far invested more than £8.5m in support of devolution through several mechanisms including:

- The World Bank managed Kenya Accountable Devolution Programme – KADP, (£4.8m for 2012-2015),
- The USAID-managed Bridge Devolution Programme – BDP, (£1.2m from September 2013 – March 2014) and;
- UNDP’s devolution support programme (£0.5m from July 2014-June 2015.)
- £2m to Civil Society through the Drivers of Accountability Programme (DAP) to support citizen participation and oversight in county governance. DFID is developing a new Deepening Democracy Programme (DDP), to succeed the DAP. DDP will provide significant support to county assemblies and to citizen demand in counties – see paragraph 27)

Most of this support so far was short term programming to support Kenya in the first two years of the transition to devolution, especially around planning, budgeting, public financial management, revenue enhancement and capacity building. The KADP programme largely worked at the national level and some key achievements included: supporting the development of public financial management training to county officials; providing on the ground technical assistance to help four counties develop their 2014/15 budgets and support citizen engagement in this process; and development of model county revenue laws in collaboration with the Commission for Revenue Allocation and the Kenya Law Reform Commission – the laws are already being adapted and domesticated by a number of counties. The Bridge Devolution Programme worked more at the county level and helped train 2162 county officials e.g. induction training for county assembly members and staff, county executive members; county education officers were trained on strategic planning; supported the development of legislation in five counties; and strategic and spatial plans in six counties. The UNDP programme has supported the Kenya School of Government develop curriculum in five areas – county planning, leadership and management, performance management, monitoring and evaluation, and human resource management. It has supported the Council of Governors secretariat to develop a communications strategy and recruit staff for knowledge management and monitoring & evaluation. Lastly it has supported inter-governmental dialogue on financial management by helping the Inter-Governmental Budget and Economic Committee convene various meetings with Senators, Governors, County Executive Committee members in charge of finance to either share lessons or negotiate on various budgetary issues. The choice of the multiple implementation channels was because the challenge of devolution was so huge that no single programme could adequately meet the needs. Paragraph 65 summarizes some of the key achievements.

Much of the UK’s development programming operates at the county level. For example the DFID Kenya Investment Climate Programme (implemented by the IFC/World Bank) aims to improve the business environment by: reducing burdensome red-tape; ensuring effective competition among and between firms in markets that are essential for growth; as well as creating a supportive environment for the private sector to participate in the provision of infrastructure, which is needed for employment and growth. In particular World Bank/IFC works with several counties including: Mombasa, Nairobi, Kisumu, on these and related matters. DFID also works through the Trade Mark East Africa (TMEA) to implement the Kenya regional economic integration programme which aims to: strengthen regional integration; reduce the cost of transport and barriers to trade in order to increase trade and access to markets, and hence enhance growth, principally in three major trade and logistics counties, including: Mombasa, Busia and Taita Taveta, and on the main transport arteries between Mombasa and Kampala. DFID's Kenya Markets Assistance Programme (MAP) also works closely with several counties to: enable selected markets to be inclusive and work better for the poor; improve investment prospects; and to assist counties work toward a better investment climate locally. DFID also works with the Ministry of Industry and Enterprise Development (MoIED), the Ministry of Devolution and Planning (MoDP) and Kenya Investment Authority, to establish a framework for business climate reforms at the county level and to benchmark good practice.

As Kenya has devolved the majority of health sector functions to the county level, all DFID’s health related support in Kenya has had to address the implications of devolution in one way or another. However, DFID Kenya has also provided targeted support to counties to assist the transition. For example, DFID’s support through the World Health Organisation (WHO) helped establish, orientate and build capacity of county health management teams (CHMT). WHO supported the development of county level tools for strategic planning, annual planning and annual performance monitoring that were subsequently used by all counties. WHO also undertook a survey to look at ‘Service Availability and Readiness Assessment Mapping’ (SARAM) that provided valuable information for counties on the availability and capacity of their health facilities to provide basic health services

Under climate change programming DFID Kenya has supported an Adaptation Consortium to work with five arid and semi-arid counties in helping communities cope with the effects of climate change. This has involved the creation of County Adaptation Funds to support climate resilience projects. More importantly the project aims to ensure that climate change is mainstreamed in county plans – a model that we plan to build on for this programme. This approach is in line with the Government of Kenya approach to climate change which recognises the importance of strong governance and citizen participation. In 2010, the Government of Kenya launched the National Climate Change Response Strategy which enhanced understanding of the global climate change regime and the impacts of climate change in Kenya. The Strategy was Kenya’s first climate change agenda guide as it provided a basis for strengthening and focusing nationwide action towards climate change adaptation and mitigation. The development of the National Climate Change Action Plan in 2013 marked another step by the Government towards addressing climate change vulnerability. It encouraged people-centred development, ensuring that climate change risks and opportunities are integrated in the Medium Term Plan and thus supporting Kenya’s achievement of development goals. However, there remains much work to do to implement this vision in enabling citizens to work in partnership to address the climate change challenges (in climate sensitive sectors like agriculture, energy, water, livestock etc.) which directly impact upon their lives.

Need for further DFID Intervention

Paragraphs 1-10 highlight that a lot has been invested into devolution by Kenyan taxpayers (close to £2bn a year) and with some support from donors. The outstanding needs and challenges are still significant and DFID continues to receive requests for support from the county governments. Building capacity across 47 county governments will require significant resources. No single donor can meet this challenge. DFID is one of few donors willing to invest, alongside EU, USAID and the World Bank. Other players in Kenya have limited resources.

As Government spending account for about 25% of GDP in Kenya, devolution can be a key driver towards reducing regional inequality[4]. It is too early to see the outcomes but there is definitely increased public investment especially in the marginalised and poor counties that should lead to a decrease in equality. Already we have seen some examples of devolution making a difference e.g. with devolution Mandera county has seen the first birth by C-section and the first tarmac roads since Kenya’s independence in 1963. Devolution of power and service delivery provides a real opportunity to: reduce regional inequality; increase efficiency of GoK spending through better accountability; create space for innovation; reduce risk of conflict by reducing the stakes over which tribes are in power nationally. With the devolution of powers to the county-level, where ethnic groups are more homogenous, hopes are high that ethnicity will weigh less in the political debate. There is some prospect that the politics of ideas could emerge over time as a growing force against the politics of ethnicity.
[4] One study found that decentralization helped reduce income inequalities in countries where government accounted for more than 20% of GDP - Sepulveda & Martinez-Vazquez (2010) -The consequences of fiscal decentralization on poverty and income equality

Devolution matters to DFID - the benefits of successful devolution would impact positively on all of our areas of programming - Annex 1 describes in detail the impact of devolution on all our priority areas. Specifically discussions with key stakeholders identified governance (open and inclusive states), health (no one left behind) Climate Change and inclusive economic development as the four priority areas for this devolution programme.

Governance–The Commission for the Implementation of the Constitution (CIC) and the Office of the Controller of Budget in their reports[5] [6] on the first of devolution highlighted a number of governance challenges - some examples listed below - national and county governments have requested support from DFID and other donors to address the challenges.
[5] Republic of Kenya, 2014, Office of the Controller of Budget, Annual Budget Implementation Report
[6] Republic of Kenya 2014, Constitution Implementation Commission, Assessment of the Implementation of Devolution

- Low development expenditure absorption, standing at only 36.4% of the budgeted amount
- Counties were yet to finalise all six key plans required by the County Government Act, 2012, i.e., Transition Implementation Plans (once – in year one), County Integrated Development Plan (five years plan), County Sectoral Plans (ten years plan), County Spatial Plans (ten years), Cities and Urban Areas Plans, and County Development Plan (annual).
- The engagement of citizens in the development of these plans was found to be unstructured. CIC further reports that a number of counties had not put in place key mechanisms including civic education, public participation and citizens’ service centres to facilitate public participation.
- Slow implementation of the mandatory Integrated Financial Management Information System (IFMIS) in some counties. All the 47 counties have established functional county treasuries, and installed IFMIS. These systems are however not yet decentralised, beyond the county’s headquarters. Operations of county assemblies have largely remained manual despite most county Assembly staff having been trained in IFMIS and the necessary infrastructure provided.
- Unrealistic county revenue projections and low revenue collection. In FY 2013/14 counties collected only 48.5% of their revenue targets.[7]
  [7] Four counties, namely: West Pokot, Kericho, Marsabit and Tharaka Nithi exceeded their annual revenue targets by raising 155%, 109.7%, 104.6%, and 101.6% respectively. Bungoma County raised the lowest revenue as a proportion of the annual local revenue target, which stood at only 6.6 %. Kakamega and Mandera counties achieved 11.6 % at 20.6 % respectively. A total of 43 counties did not meet their local revenue target for the year

Kenyans want county governments that better manage resources (human and financial) and better engage citizens in order to deliver on the devolution promise. The potential benefits of having government closer to the people can only be achieved if that government listens to and is responsive to the people. In an environment of constrained resources the Kenya government has traditionally underinvested in citizen engagement and this is an area that development partner support can be critical, especially in the formative years before participation is institutionalised in law and processes. Counties will also require more support to build the systems for planning for, and managing, money and people. Devolution was designed to reverse exclusion in national politics – counties will require support to ensure inclusive politics at the county level. It is noteworthy that Kenyan law provides that county assemblies need to have at least one third women and this was achieved at the last election. Furthermore women were at least 33% in a majority of county Executive Committees (the county equivalent of ministers). There have also been attempts to ensure representation of youth, the disabled and minorities. However the task ahead is to ensure that plans, budgets and programmes reflect the priorities of these groups.

Health – Development partners have a role to play, both in helping maintain public services and supplies in the transition period, and also to help develop capacities and systems needed to ensure counties can sustainably implement local health services (both preventive and curative) going forward. Institutional development will be key to accelerating progress towards the Millennium Development Goals (MDGs) and the post-2015 framework and preventing stagnation in key areas, such as: maternal and neonatal mortality decline; uptake of modern contraception; reduction in HIV prevalence etc. Development partners can play an important role in supporting positive institutional development both at Ministry of Health and county levels. Another important area for institutional change under this programme will be establishing a more effective private sector and ensuring that there is improved regulation by government and independent professional bodies. Maintaining adequate health financing will be a critical challenge going forward, as funding from the national health budget is not earmarked at the county level. Politicians have incentives to focus on short term interventions, with readily visible results, and questions remain on: how to maintain investment in prevention and in primary health care services; sustain previous health gains; and how to increase investment in neglected, sensitive areas/issues including sexual and reproductive health services such as family planning. Counties require support to ensure that service delivery is inclusive and this is particularly true of health – county health budgets and priorities need to reflect the priorities of women, children and other vulnerable groups. The accountability mechanisms need to give adequate voice to these groups. An October 2013 Ministry of Health report shows that across health facilities the mean availability of essential medicines for children stood at only 49% while the mean availability for essential medicines for mothers stood at 28%.[8]
[8] Ministry of Health – Kenya Service Availability and Readiness Assessment mapping (SARAM) – October 2013

Inclusive economic development - Huge disparities across and within counties require sustained efforts to address. To illustrate, 82% of the population in Turkana Country is illiterate, compared to 11% in Nairobi. According to the 2005/2006 Kenya Integrated Household Budget Survey (KIHBS), the latest available data, 46% of the population is estimated to be poor. Counties with the highest poverty rates include: Turkana (92.9%), Mandera (85.7%), Wajir (84.4%), Marsabit (79.3%), Samburu (77.7%), Tana-River (75.4%), Kwale (72.9%), West Pokot (68.7%), and Kilifi (66.9%). The Commission for Revenue Allocations’ County Development Index (CDI) sets criteria for marginalised areas based on indicators such as: e.g. poverty index, life expectancy, access to energy, educational attainment. This identified 21[9] counties where the CDI score falling below the national average. The range is from a low score 0.27 in Turkana to a high score of 0.77 in Nairobi.   To address marginalisation Kenya has adopted a redistributive revenue allocation formula that has seen marginalised counties get a good share of revenues e.g. Turkana has the second highest allocation of all 47 counties. While this is a good first step, counties will require support to promote inclusive economic development that benefits all. Beyond public investment, counties need to attract private investment. This means: assessing their investment policies, tax and fiscal stance to identify factors constraining investment; evaluating scalability of Micro Small and Medium Enterprises (MSMEs) and how these could be supported.
[9] In descending order or marginalization – Turkana, Migori, Wajir, Bomet, Mandera, Taita Taveta, Marsabit, Busia, Samburu, Kilifi, West Pokot, Trans Nzoia, Tana River, Tharaka Nithi, Narok, Homa Bay, Baringo, Garissa, Kwale, Kitui

Climate Change (funded through the UK International Climate Fund (ICF) - Kenya is highly vulnerable to drought, which currently costs 2.4%[10]of GDP per annum, and may rise with the effects of climate change. Kenya’s vulnerability to climate change is further affected by governance issues, including: relatively weak institutional capacity, low resource management capabilities, inadequate technology and information infrastructure as well as land degradation, which combined, pose serious hurdles to effective climate change responses. Another issue is the inequity in access to natural resources (for example, land and water) leading to conflict over resources and lack of capacity to manage the scarce resources. If not addressed, climate change will hamper progress towards the MDGs and their successor and disproportionately impact vulnerable groups, especially women and those living in the arid and semi-arid lands and coastal regions.
[10] The World Bank calculates that on average, every seven years Kenya experiences a flood that costs about 5.5 percent of GDP), and every five years experiences a drought that costs about 8 percent of GDP. This translates to a direct long-term fiscal liability of about 2.4 percent GDP.

While DFID has other programmes with a specific focus on resilience, it will be critical that the planning and budgeting support DFID will provide to counties in Arid and Semi-Arid Lands (ASALs), also incorporates resilience. The 22 ASAL county governments bring new impetus to improve the livelihoods of ASAL citizens, including reducing their vulnerability to drought. Under the highly progressive revenue sharing formula adopted by Parliament, historically marginalised counties (almost all of which are ASAL counties) receive significantly larger per capita transfers than do the historically privileged counties. At the same time, devolution brings multiple new challenges and risks to initiatives aimed at reducing drought vulnerability and building resilience. These include: challenges in delineating roles between national and county governments; fragmentation of functions devolved to counties (e.g., livestock disease surveillance, fodder storage, agricultural extension, water management – as former regional water boards are split up); and setting up effective inter-county and national-county coordination mechanisms. Most significantly, ASAL counties, in particular, face major capacity challenges – they start from a lower base of human and physical capital; costs of infrastructure provision are high due to dispersed populations; there are persistent conflicts over natural resources and other matters; and it is more difficult for them to attract and retain qualified staff. For example, Kiambu County has 1.6 times the population of Mandera County but 10 times the number of health personnel – as of October 2013 Kiambu county had nine obstetricians/gynaecologists and Mandera had only 1[11]. In summary, ASAL counties have significant new financing available (significantly larger than donor funding), but converting these resources into productive investments and services that reduce vulnerability to drought and improve resilience, is a major medium-term challenge. There is also a legacy of donor and government funds that have primarily supported emergency drought responses rather than long-term resilience. Strengthening climate resilience in the context of devolution is a major institutional challenge.
[11] Ministry of Health – Kenya Service Availability and Readiness Assessment mapping (SARAM) – October 2013

Context in overall DFID Kenya Governance and Security Portfolio

Going forward DFID Kenya’s governance portfolio will consist of three programmes;
- Deepening Democracy Programme (DDP);
- Improving Community Security (ICS) Programme;
- Kenya Devolution Support Programme (KDSP) – the subject of this business case

There are links between the three. Specifically, KDSP will work mainly with the government (national and county).This will include helping county governments to create an enabling environment for citizens to engage in, and monitor, the implementation of public policy. It will be complemented, on the citizen demand side, by the Deepening Democracy Programme (DDP), currently under development, that will provide direct support to civil society. The DDP programme will also provide support to county assemblies which hold the county executives to account, thereby further complementing the KDSP programme. Budget making will be a key focus of the KDSP programme and county assemblies have a critical role in the process, thereby providing another area for complementarity between the two programmes. In the medium to long-term, civic education efforts under DDP should contribute to raising awareness about the roles of different county leaders, and the ambition is that the 2017 elections, as well as subsequent ones, will see gradual improvements in the quality of county leadership. DDP will also support building the capacity of national level accountability institutions including the National Assembly, Ethics and Anti-Corruption Commission, and the Kenya National Audit Office among others. Effectiveness of these institutions will be key in creating an enabling environment for the success of devolution.

Security is not a devolved function; however one strategy to reduce local level conflicts is to ensure devolved governments are inclusive. In that respect the programme will complement the recently approved Improving Community Security Programme (ICS). There is also ongoing national dialogue on the need to involve the county leadership in county security and conflict management. Many conflicts in Kenya are identity based, borne out of exclusion and fights over resources – with devolution, more resources are being controlled at the local level and this creates the risk of local level conflict. KDSP programming therefore will build in conflict sensitivity and ensure that inclusivity is emphasised in planning and budgeting and through the attendant citizen participation processes. This will increase the likelihood of successful ICS outcomes.

Results

The desired impact is to contribute to building trustworthy devolution institutions and especially county governments. Trust in public institutions is important for the success of a wide range of public policies that depend on the co-operation and compliance of citizens[12]. Trust is also necessary to increase the confidence of investors and consumers; and essential for key economic activities, most notably finance.
[12] OECD - http://www.oecd.org/gov/trust-in-government.htm

The outcome is to have more capable and accountable county governments. This means county governments that are reliable, open, inclusive, fair, provide good regulation, and have integrity.

The expected programme outputs are:
1. Strengthened county-level planning & public financial management (PFM) systems;
2. Improved county performance management;
3. Strengthened citizen participation systems;
4. Improved capacity at county level to manage human resources (HR); and
5. Improved fiscal management and revenue collection.

NB. Health, local economic development and climate change issues are mainstreamed across these outputs and will be reflected in the indicators. The programme will contribute to ICF Key Performance Indicator 13 – Level of integration of climate change in national planning as a result of ICF support. This will be part of output 1 above.

Institution building and reform takes decades to realise satisfactory impact and even outcome level results. Some of the higher level results of this programme may not be observable in its five years lifetime. While the UK’s aim is to exit from aid in Kenya, the UK’s experience of devolution may argue for this programme to remain and adapt beyond its first phase. .

If we look at the performance of existing DFID funded devolution programming as an indicator of future performance - DFID’s Kenya Accountable devolution Programme (World Bank implemented) which comes to an end this year has scored an ‘A” in the past two annual reviews; The project completion report for the USAID implemented Bridge Devolution Programme showed that the programme exceeded expectations on delivery of outputs and met expectations on the outcome.

Gender Equality Impact Statement:
Devolution holds great promise for women and children in Kenya. Water and sanitation, health, early childhood education, child services and agriculture are amongst the major devolved functions. All these functions have a significant impact on the well-being of women and children. A gender analysis will be conducted during the mobilisation phase to inform a gendered approach to the programme and will consider the impact on gender equality for all interventions.

Kenya’s maternal mortality rate stands at 488 deaths per 100,000 live births. This figure varies from county to county, with the highest rate being in many of the ASALs of Northern Kenya, which has an estimated maternal mortality rate of 1000-1,300 deaths per 100,000 live births[13]. Some progress is being made – at a recent Development Partnership Forum it was reported that in the last two years the number of births in a health facility in Wajir County have increased from 1 in 20 to 7 in 20. However this is still woefully inadequate. To address such issues, counties must make deliberate investments that respond to the concerns of women and children. One of the key challenges with regard to health care has been the provision of quality services. In order to provide quality services, facilities need to have the right inputs and skilled health care workers. One study found that public providers followed less than half (44%) of the correct treatment actions to manage maternal and neonatal complications. Over 29% of health workers were absent.[14] The study recommended that , in addition to increasing budget allocations for health, county governments would need to also address the skills of health care providers and their productivity[15]. This is not always easy and the trend has shown a focus on curative health care at the expense of preventive health care[16]. The mobilisation phase of the programme will design interventions supporting county Health Departments to ensure that service delivery is inclusive, county health budgets and priorities reflect the priorities of women, children and other vulnerable groups and citizen feedback mechanisms for health service delivery have adequate representation of women and other marginalised groups.
[13] UNWOMEN Closing the Gap Devolution Factsheet
[14] World Bank, 2013 Education and Health Services in KENYA Data for Results and Accountability
[15] UNWOMEN Closing the Gap Devolution Factsheet
[16] World Bank, 2014 Kenya Public Expenditure Review, Decision Time: Spend More or Spend Smart?

In Kenya women provide close to 80% of the agricultural labour but only have access to 1% of available agricultural credit. Improving equal access to farm inputs for women farmers could significantly increase their yields. One study found that, if women farmers in Kenya had the same access to farm inputs, education, and experience as their men counterparts, their yields for maize, beans, and cowpeas could increase by as much as 22 percent. Increasing productivity within female-headed farms by 20 to 30 percent would raise national productivity by 2.5 to 4 percent in developing countries, which, in turn, could lift as many as 100 to 150 million people out of chronic hunger[17]. We will require that implementing partners demonstrate how the work on local economic development will deliver for women.
[17] UNWOMEN Closing the Gap Devolution Factsheet

Devolution is prone to elite capture and in fact the voices of women and other marginalised groups can in some cases be more muted in local decision making than in national processes. The 2010 Constitution and other laws have secured significant gains for women in county governance – as mentioned above, women now constitute at least one third of all county assemblies. This is a significant improvement from the past and indeed is currently not the case in the National Assembly. Representation on its own is insufficient and there needs to be greater participation of women in decision making. This programme will specifically work to amplify the voice of women in county participation processes but also ensure that training provided to county administrators in areas such as budgeting and planning incorporate gender issues. The programme will also support gender audits of budgets and plans as well as in Public Expenditure Reviews. The county performance management systems developed under the programme will also disaggregate gender data. The high profile World Bank Public Expenditure Reviews will provide a useful avenue to highlight some of the county public investment choices and their impact on the poor and vulnerable. The programme will:
- Ensure activities related to social accountability and participation involve women, people with disabilities and marginalised groups, in compliance with legal and constitutional requirements for equality, non-discrimination and inclusion.
- Promote gender responsive planning and budgeting in engagement with national and county governments and suggest measures for improving policies and programme for gender equality.
- Support accountability reforms that increase transparency, set performance monitoring standards for service delivery, increase public sector actors’ gender awareness and increasing compliance with constitutional provisions on equality, non-discrimination and inclusion.
- The County Performance Management System developed with support from the programme will have gender disaggregated results.
- Ensure inclusion of women in training programmes at national and county level.
- Ensure the development of policy, implementation guidance, and training curricula at national and county levels include gender aspects.

There are great opportunities in ensuring that clean energy, resilience to disasters and natural resource management issues are designed to be responsive to the specific needs and vulnerabilities of women and marginalised groups, under this programme. During the inception phase, partners will more explicitly define how they plan to identify and engender climate mainstreaming activities within the programmes. A key focus will be on promoting longer-term resilience to drought and other climate induced shocks through: (i) building human capacities including women’s capacities; and (ii) improving planning capacities and processes, including county planning documents (CIDPs) to respond to chronic and acute needs of women and marginalised groups in the ASALs; and improving women’s agricultural productivity.
Appraisal Case

As stated in paragraph 32, institution building and reform is a long-term process. It is evident that these formative years of devolution present a period of rapid change[18] – some positive and some negative, and that there is an opportunity to ride this positive momentum to accelerate the positive changes before reform inertia sets in.
[18] The constitution envisaged a three year phased transfer of functions to counties but most were transferred within six months of the county governments coming into force.

DFID Kenya has identified three key priorities that the overall portfolio will need to address to contribute to improved governance in Kenya.

- Ethnicity-based politics: As already noted, Kenyan political discussion and voting is highly ethnic (where citizens generally vote along tribal lines, rather than on an issues base). There is little evidence that policy ideas and performance in office play any role in voter’s decisions[19]. This gives tribal elites political and economic power, and has resulted in conflict, weak accountability, high corruption and limited incentives to reduce poverty and address gender inequalities[20].
  [19] Gilbert M Khadiagala (2010) Political movements and coalition politics in Kenya: entrenching ethnicity, South African Journal of International Affairs, 17:1, 65-84
  [20] Ibid
- Weak oversight institutions: oversight institutions can play a role in limiting ethnicity-based politics, and the 2010 Constitution provides an opportunity to strengthen them. As an example, the Constitution reduced the discretion that the President had to hire senior state officers – recruitment is done by bodies such as the Judicial Service Commission, Public Service Commission and special selection committees with the President’s role limited to appointment. It also provides for parliamentary vetting for many of these positions which has meant that the political viability of the recruitment choices depends to an extent on the degree they reflect the diversity of Kenya. All these reduces (but doesn’t eliminate) the degree to which the executive can use recruitment for patronage.
- Weak policies and capacity at county level: improving county governments’ ability and accountability to promote growth, provide services and manage urbanisation is essential for growth transmission and social policy.

DFID’s Governance and Security programming is designed to contribute to these three priorities. Through the DDP, we will focus on oversight institutions and support to civil society which will monitor the performance of the county governments. Through the KDSP, we will focus on improving county policies and capacities. We are taking into account ethnicity in most of our programming. Devolution was introduced in part to address ethnic based politics by devolving power from a national elite to 47 counties. Interventions under this programme will contribute to reducing exclusion and county level elite capture by supporting inclusive county governance.

Theory of Change (ToC)

To address weak policies and capacity at the county level, the programme will focus on strengthening county systems in the areas below:

1. Planning and budgeting
2. Fiscal management including revenue collection
3. Public financial management
4. Human resource management
5. Performance management
6. Transparency, accountability and public participation.

Even with the initial teething problems, public support for devolution remains high, with 82% of Kenyans polled in a July 2014 National Democratic Institute (NDI) survey believing that implementation of devolution is ‘very important’ or ‘somewhat important’. This support is driven by the belief that devolution will lead to more equitable, inclusive and prosperous societies with county governments, that are better able to understand the needs of local populations and allocate resources more efficiently to meet those needs.

While support for devolution is high, Kenyans’ satisfaction in county governments is falling – for instance, in August 2013, 43% of Kenyans were either ‘very satisfied’ or ‘somewhat satisfied’ with their Governor’s performance, but this fell to 34% in July 2014 (NDI, 2014.) This could in part be an understandable correction given unrealistically high expectations of devolution, but there are also valid concerns about performance of county governments so far that erode public trust.

The OECD identifies five key elements for any government to build trust[21]. These elements broadly align with the five output areas under this programme:
[21] OECD - http://www.oecd.org/gov/trust-in-government.htm
- Reliability of Government: The ability of a government to minimise uncertainty in the economic, social and political environment; set direction and make policy, monitor and evaluate implementation, achieve sound fiscal management and finally manage risk and crisis.
- Better regulation: The regulatory system must work for everyone in society. For citizens: It is important for justice, fairness and the rule of law as well in delivering public services. For businesses: It is important to have reliability and confidence in regulatory governance for investment and growth. For public administrations: It is important to have the confidence of stakeholders to act and trust in the efficiency and appropriate use of public resources for equal benefit for all citizens’ well-being and environmental protection.
- Open Government Policies: Citizen engagement and access to information can help increase public trust. Measures range from access to information, open budgets, to consultation processes, to full-fledged open government policies.
- Integrity and fairness: Evidence suggests a link between trust in politicians, both from the business community and citizens, and the perception of corruption.
- Inclusive policy Making: Concerns over the undue influence of vested interests over decision making has led to increasing demands for more transparency and a greater commitment to safeguarding the public interest. Efforts to guarantee that the policy making process is open, inclusive and fair would improve the quality of policy decisions.

The table below presents some of the possible interventions under this programme. The length of the list reflects the fact that this programme is designed as a technical assistance facility, offering a wide menu of support, ranging from small, single-county consultancies to large multi–county/national initiatives. A downside is that this makes the programme more challenging to manage and aggregation of results is complicated. This complexity is largely unavoidable as it is a reflection of the many diverse needs and multiplicity of institutions involved in the devolution process. Different counties will have different needs at different times. In some programmatic areas, it will be possible to provide a generic and minimum package of support across counties. This is especially around statutory and mandatory processes, such as budgeting, audit, procurement etc. The programme will also have space for bespoke, demand driven support based on county or institution specific needs. The transition to devolution is highly political and the context rapidly evolving and experience from the KADP programme is that not all programmed activities may take off, and some may do so, but slowly. This programme will therefore need to have flexibility and programme management processes to allow it to drop activities that stall, but also to take advantage of new unforeseen opportunities.

Table 1: Overview of Programme Outputs and Related Activities
KDSP Outputs	The programme will support;
Strengthened county-level planning & public financial management systems	Technical assistance, analytical products and training to counties to improve their County Integrated Development Plans (CIDPs) and to develop sectoral and economic plans. Support counties to integrate climate change adaptation and disaster risk reduction in their CIDPs. / Development of county public financial management systems, through training and technical assistance, e.g. on financial reporting and audit. / Improve the quality of counties’ overall and sector budgets and transition to systems, such as the Integrated Financial Management Information System (IFMIS), and the use of programme based budgeting. / Work with the Public Procurement Oversight Authority (PPOA) to assist counties develop robust procurement systems in line with good practice. / In partnership with Kenya School of Government and the Council of Governors. support counties to adopt evidence based policy making with a focus on health, climate change and economic policy. / Training programmes to ensure that counties strengthen their ability to assess their disaster risks, potential impacts of climate change on communities’ livelihoods, clean energy access/opportunities, existing natural resources and develop strategies to address the identified needs. / Inter and intra-governmental coordination structures for better dialogue coordination and dispute resolution. / Support the Council of Governors to ensure better consultation amongst county governments on performance, joint projects; and resolve disputes between counties
Improved county performance management;	Our existing funding has helped develop a county performance management system with online dashboards providing real time progress. This programme will broaden this beyond the original five pilot counties and also work to make the system publicly accessible. / The work would track performance in service delivery but also improvements in public sector management. / Some of the indicators e.g. in health will be gender disaggregated.
Strengthened citizen participation systems. / NB. The focus here will be on working with government institutions to make them more open and help them develop participation mechanisms. The Deepening Democracy Programme will complement this by working with citizens and NGOs to strengthen their capacity to participate.	Develop counties’ public participation processes along all project cycle management steps from planning, budgeting to areas where there has been less success in public participation such as implementation, monitoring and evaluation. There will be focus in a number of counties on public participation on climate change risks and opportunities to ensure that projects that make it into county plans contribute to enhancing resilience. / Work with Kenya School of Government to develop training for counties on participatory methodology – including content on gender and marginalisation. / Counties to develop, publicize and implement service delivery standards and charters, especially in the health sector. / Counties to develop beneficiary feedback and participation mechanisms for service delivery points, e.g. health centres. / Integration of social accountability in PFM and performance management systems. / Counties to implement grievance redress mechanisms. / Ministry of Devolution and Planning to develop a national policy on public participation; and support accountability measures in county procurement systems.
Improved capacity at county level to manage human resources	Review of HR policies and development of a government HR strategy. / Capacity building support to the County Public Service and Assembly Boards.[22] / Roll out of performance contracting amongst county employees. / Work with the Salaries and Remuneration Commission on a sustainable wage policy. / Support the national government to develop and roll out national public service norms and standards to guide public service management in the counties. / Support County Public Service Boards to achieve equity in distribution of opportunities among underrepresented groups, including women, youth and people with a disability[23]. Research has shown that placing women in the front line of service delivery has a positive effect on women’s access to those services.
Improved fiscal management and revenue collection	Building on the development of a handbook of revenue laws, and support for reform of property rates in Nairobi, provide advice to county and national governments on broadening sub-national tax bases; and narrowing the tax gap, including through cost-effective use of ICT, and considering alternative collection arrangements, including up-sourcing to the central revenue authority. / Support counties to develop and amend regulations governing property tax administration, update the property valuation roll, implement technology systems to support the administration of property taxes and build the capacity of county staff to implement and sustain reform recommendations. / Help counties better support business entry and reduce the cost of doing business for Small & Medium-size Enterprises. / Continuous fiscal health analysis to determine the impact of revenue sharing arrangements on counties and their ability to deliver the devolved functions. / Work with former marginalised counties on how they can make best use of their untapped fiscal space i.e. their recurrent spending is relatively small share of the total leaving them with huge funds (70% of more) for development, operations and maintenance.. / County borrowing framework that manages risks. / Development of a conditional grants framework starting with the health sector. / Advice to county and national governments on broadening sub-national tax bases; and narrowing the tax gap.
[22] County Public Service Boards and County Assembly Service Boards are charged with recruitment for the county executive and county assembly respectively.
[23] At present women account for 47% of the county workforce. In some counties such as Lamu, Wajir, Turkana, Samburu and Mandera women account for less than 30% of the workforce. A further review reveals that in over 70% of the counties, women make up less than 30% of the workforce in some sectors related to planning, agriculture, infrastructure and water. These are key sectors responsible for decisions with far reaching implications for reducing inequalities between women and men.

Based on the OECD framework for building public trust.

Options

In November 2013 the national government, county governments and donors signed up to a National Capacity Building Framework (NCBF.)[24] This document broadly articulates the needs that counties have and outlines an intervention strategy. DFID and other donors have committed to work under this framework and the real options therefore are about how to deliver against the NCBF, i.e. what delivery mechanisms would work.
[24] Republic of Kenya 2013 National Capacity Building Framework

The options available to DFID are
- Option 1:Design a standalone DFID devolution support programme.
- Option 2:Strategic partnership with one of the existing donor devolution support programmes.
- Option 3:Portfolio approach involving strategic partnerships with a mix of the existing donor devolution support programmes.
- Option 4:Do nothing more.

During the early stages of design we considered Option 1 - setting up a standalone DFID managed devolution support programme - but we rejected this based on feedback from the Government of Kenya on the difficulties of coordinating the existing donor devolution support programmes and on the basis that our intended scope of work was already covered in these existing donor programmes. DFID is a member of the Devolution Sector Working Group and has been involved in the development of the NCBF. The interventions envisaged under this programme are not different from those being carried out under existing programmes so it makes more sense to work collaboratively to achieve economies of scale. This is in line with the UK’s commitment to the aid effectiveness principles of harmonisation and coordination. DFID has been the biggest donor to some of the existing devolution programmes (e.g. World Bank and UNDP) so there is sunk cost especially in building the technical capacity and relationships that we would have to establish afresh with a standalone programme. The main argument here is that a new player doing the same programmes as existing players would be disruptive and instead of building capacity may end up draining capacity in terms of the extra amount of time Kenyan counterparts would need to spend negotiating, coordinating, building relationships etc. with a new partner.

We have also opted not to fully appraise Option 4 - doing nothing more. The arguments for this are clearly set out in the Kenya Accountable Devolution Programme (KADP) business case approved in 2012. KADP was a transition programme and the business case made both the case against doing nothing and also anticipated a future more comprehensive programme. It argued that the transition to devolution was likely to be messy and with great need for good governance, transparency and accountability - we hold that these arguments are still valid today. It further argued that a doing nothing option would be valid if there was sufficient support to devolution from the Government of Kenya and other donors or if the transition to devolution was proceeding smoothly with little need from counties – none of these conditions are currently the case. Donors continue to receive numerous requests for support from county governments and capacity gaps are evident.

We have therefore opted to appraise Options 2 & 3 as our real and viable options. Both of these options involve strategic partnerships with either one or more of the existing devolution support programmes namely.

- The World Bank’s Devolution Partnership Facility for Kenya
- UNDP’s Integrated Support Programme to the Devolution Process in Kenya
- USAID’s Agile Harmonized Assistance for Devolved Institutions (AHADI)
- The EU’s Instrument for Devolution Advice and Support (IDEAS)

We use a two-step process where we first assess the existing donor programmes based on the strategic criteria below to decide whether to choose one delivery mechanism or a mix. The second step will be to proceed to do the cost benefit analysis, financial and management case for the preferred option. Step 1 considers :
1. The targeted results under each programme and fit with DFID Kenya’s priorities in governance, health, climate change, and economic development.
2. The appropriate mix of national and county level interventions.
3. The approach to gender and conflict issues.
4. Delivery capacity.
Table 2: Highlights of Existing Devolution Support Programmes (See Annex 2 for a more detailed summary)
	World Bank - Kenya Devolution Partnership Facility (KDPF) / (2015-2019)	UNDP’s Integrated Support Programme to the Devolution process in Kenya (2014-2018	USAID’s Agile Harmonized Assistance for Devolved Institutions (AHADI)	The EU’s Instrument for Devolution Advice and Support (IDEAS)
Programme Description Objectives	The programme started in 2012 with funding from DFID and Australia – some key results achieved so far are outlined in paragraph 65. / In summary the focus of this phase of the programme is to / Provide data and analysis on macro Fiscal Impacts of Devolution / Support county public financial management and human resource management Reform / Support county governments to develop county performance management tools and open data / Capacity for citizen and stakeholder participation / Support for devolved sectors / Learning and Knowledge	The programme is also anchored in a joint one UN strategy for devolution. / DFID support would go towards the following three programme objectives: / Strengthened policy and legal framework for devolved governance; / Strengthened and aligned capacities at national and county levels; / Enhanced service delivery mechanisms at the County level	Currently single largest donor programme on devolution. The objectives are ; / Targeted counties provide higher quality services through improved governance; / Improved representation of citizen interests and oversight of targeted county government performance; / Functionality and effectiveness of the devolved system increased through improved intra-government engagement and cooperation	This programme aims to; / Improve national institutional capacities to support participatory fiscal decentralization. / Increase capacity at the county level to facilitate participatory planning and local economic development / .
National and County Partners	The programme will provide some support to counties on a demand or pilot basis, the main approach is to work at the national level on system-wide fixes. / Key partners will be the National Treasury, Ministry of Devolution and Planning, Controller of Budget, Kenya National Audit Office, Commission for Revenue Allocation and the Council of Governors and the Kenya School of Government / It leverages existing and larger amounts of WB funding - a good example is with the climate change component of the DFID funding, the programme would provide technical assistance to the £50m Regional Pastoral Livelihoods Resilience Project, which provides support to 14 ASAL counties	Targeted support to a maximum of sixteen (16) counties. / It will also support the Council of Governors to provide a mechanism for consultation amongst county governments; / Other institutions to be supported include: the Ministry of Devolution and Planning to; the Intergovernmental Budget and Economic Council; the Commission on Revenue Allocation; the Intergovernmental Technical Relations Committee	Will work with both national and county institutions. It will support national and county legislative and policy making processes; county capacity building around human resources, planning, budgeting and service delivery and performance management; help counties identify under-exploited and new potential revenues, improve revenue collection and recording systems; work with Kenyan Government institutions and other stakeholders to develop a citizen engagement framework.. / County grant funds will be targeted to specific operational needs for the county executive and legislatures.	Will work with both national and county governments and will provide; / A grant to the World Bank to support the National Treasury. A grant to SIDA to support the National Audit Office. Technical assistance to the Commission for Revenue Allocation and the Ministry of Devolution and Planning. A service award to the Kenya School of Government. A grant to the Ministry of Devolution and Planning to conduct civic education and to oversee the LED projects
Budgets & Donor Commitments	Current commitments are £7m which includes DFID (£1.3m) (from the existing KADP programme), the EU (£1.8m), Sweden (£1.3m), USAID (£1m), and Finland (£1.5m). / The WB has provided indications of the areas for growth if more funds available.	Funding gap - £17m / This is a multi-donor programme with a total budget of £22.7 of which £5.7 is funded - (£0.5m), DFID from an existing accountability programme, Sweden(£2.2m) Norway (£0.7m) and USAID (£2.3m).	£32m currently funded by USAID. The programme has identified the county level work as an area where additional donor contributions could help deepen the support or cover a few more counties	£21m fully funded by the EU. / No budget gap expressed.

Table 3 summarizes our assessment of each of the four existing devolution support programmes based on the criteria set out in paragraph 52. The assessment is based on the proposals submitted, past performance under DFID funded programmes, and the strategic dialogue ongoing in the Devolution Sector Working Group and with beneficiaries such as the Council of Governors and Ministry of Devolution and Planning

Programme	Assessment
World Bank’s Kenya Devolution Partnership Facility (KDPF)	The WB programme is the second phase of an existing DFID funded programme which has scored an “A” in the last two annual reviews. The programme therefore has a track record of delivering results and the new programme will have many lessons to draw from. / The KDPF covers the core governance functions (PFM, budgeting, planning, HR, M&E, citizen participation) and has also built in interventions to address governance in devolved sectors such as health. It also provides an opportunity to support the IFC and WB deepen the sub-national doing business work started under the DFID’s Building Reliable Investment Climate in Kenya (BRICK) programme. On climate change the WB will have a particular advantage in providing fiscal analysis and public investment management advice to ensure that the increased budgetary allocations to ASALs translate to tangible results. / The WB has a comparative advantage in providing technical and analytical support. The WB has been the partner of choice in such technical areas as revenue enhancement, wage policy, sub-national debt policy etc. Amongst donors working on devolution, the WB is regarded as the lead technical agency on public financial management. / The WB and GoK are designing a parallel WB credit funded devolution Programme for Results (PforR) to incentivise results in capacity building. The PforR will reward achievement of capacity building results regardless of attribution (i.e. even results under KDPF and other programmes) and as such this will have a multiplier effect on the KDPF and other capacity building programmes. Working with the WB means that a relatively smaller amount of DFID funding influences much larger WB health programming, Regional Pastoral Livelihoods Resilience programme and the IFC’s doing business work. / Given its national systems-wide approach, the programme will not work as intensely in the counties. There would therefore be need for complementary approaches to ensure implementation at county level of training materials, models, guidelines and systems developed through WB support. This approach is already starting in areas such as PFM where other donors have agreed to use WB produced budgeting and financial accounting & reporting training materials. / Key lessons from the current DFID funded programme is that the WB will need to improve on the systematic monitoring and tracking of results; improve coordination with the UNDP, USAID and EU funded programmes to avoid duplication. / The WB project is weak in addressing gender issues and more can be done to include conflict sensitive approaches. We have raised these issues with the WB under our current support and they have started to incorporate but more still needs to be done. / In terms of delivery the WB has a strong in-country technical team working on devolution both in terms of numbers as well as subject matter specialists. The Kenya team also has access to the WB’s global network and knowledge. The team however needs to beef up programme management capacity
UNDP’s Integrated Support Programme to the Devolution Process in Kenya	This programme has been in implementation since January 2014 with some initial $1m funding from Norway. The programme will address the core governance functions (PFM, budgeting, planning, HR, M&E, citizen participation) / UNDP has a long history managing public sector reform programmes in Kenya and elsewhere. National and county government officials (CoG) highly rated UNDP for its responsiveness and flexibility in responding to their requests. / The programme is anchored on a one-UN devolution strategy which means that UNDP as the lead agency will have access to the expertise, networks and programmes of other UN agencies to implement the programme e.g. WHO on health, UN women on gender issues. / However the programme will not be directly working on local level economic development which is one of key focus areas for this programme. / Compared to the World Bank, UNDP is best suited for rapid response technical assistance to the Government due to their capacity and experience supporting training and enhancing capacity of individuals and institutions within the Government. The World Bank is engaging more in analytical work like fiscal analysis, and revenue enhancement among others. / UNDP will be working in 16-20 counties and is better equipped to get staff working at the county level than the WB and they already have structures to support implementation at the county level. There are opportunities for complementarity with WB developing models, training materials that UNDP and others can roll out intensively in counties. UNDP, USAID and EU have mapped the counties and agreed a division of labour amongst each other on who will work in what county. / The UNDP programme has a good focus on gender. Specifically key result area 7 - “gender equality, women empowerment and human rights strengthened” with the lead agency being UNWomen. / Commendably, the programme also highlights conflict and resilience issues through key result area 5 “Enhanced resilience and capacities for disaster risk management, peace building and conflict prevention.” UNDP has co-chaired the conflict donor group with DFID been active in supporting conflict management and peace building. In the specific context of counties UNDP has been actively involved in resolving the county conflict in Marsabit County. / In terms of capacity to deliver, UNDP has a dedicated devolution programme analyst and have recently recruited a devolution adviser. This team will be a bit stretched, though they also work with other team members in their governance team, finance and procurement units.
USAID’s Agile Harmonized Assistance for Devolved Institutions (AHADI)	USAID has been supporting devolution since it started in March 2013. This was through bridging funds pending commencement of this new longer term programme. As highlighted in paragraph 12, DFID Kenya channelled £1.2m through USAID’s Bridge Devolution Programme. The projection completion report showed that the programme exceeded expectations on delivery of outputs and met expectations on the outcome. In the Bridge Devolution Programme USAID proved to be a reliable partner providing sound programme management and timely and quality reporting. USAID and DFID have also had a very successful partnership in Kenya supporting the Parliamentary Support Programme (PSP.) which was also managed by the State University of New York (SUNY). / AHADI, will work in depth in 21 counties - within a division of labour agreed with UNDP and EU. This offers an opportunity for DFID and other donors to channel support through USAID for any of the 21 counties and the same for counties where UNDP or EU are leading. / AHADI meets all four of our programmatic priorities though admittedly the focus on economic development is limited. It covers the core governance functions (PFM, budgeting, planning, HR, M&E, citizen participation.) Capacity building will also target county institutions aligned to USAID sectoral work (health, youth, food security, climate change, education and participation.).It will particularly support the involvement of producer based civil society in county governance, e.g. farmers associations, business groups, and professional associations. / The programme will also address conflict risks and work with counties on conflict sensitive approaches. Selected counties will be provided with a special grant and technical assistance to establish a Conflict Analysis Unit to champion conflict sensitive approaches to county governance and to work with local conflict management CSOs in the county. The unit will also work closely with district peace committees, community policing committees, and the more recent Nyumba Kumi Initiative[25] to promote reconciliation. / The programme document does not explain in much detail how the programme would address gender issues. / A significant advantage of the AHADI programme is that it already has significant funding from USAID, unlike UNDP, and to a lesser extent WB basket funds that are fundraising from other donors. DFID funds would allow USAID to scale up coverage across counties or achieve greater depth in a specific county. We would need to carefully assess how much extra funding the programme can absorb and assure quality programming. / AHADI has a strong programme management and an equally strong procurement team. Procurement will be done following USAID rules.
The EU’s Instrument for Devolution Advice and Support (IDEAS)	This programme is awaiting final approval from GoK. / The largest component (52%) of the programme will be allocated to Local Economic Development (LED) projects in 10 counties. The approach of learning by doing is interesting, and undoubtedly focusing on governance in the implementation of an LED can produce improved governance in the implementation of that project and maybe even within the implementing departments - however at this stage it is difficult to say whether these governance gains could spread wider in the county government for that scale of investment. Given the scale of need across a county government, we would prefer to work more on system-wide changes. / The programme will therefore cover the core governance functions (PFM, budgeting, planning, HR, M&E, citizen participation) but through one LED project. / While the DFID devolution programme intends to address local economic development, the thinking was more around supporting inclusive economic planning, improving the investment climate rather than a single project approach. Other DFID sectoral programmes may be better placed to deliver projects in the counties. / The PFM work will be conducted through the WB programme described above and it makes more sense for DFID to engage the WB directly than through the EU. / The IDEAS programme will not work on health which is one of the three DFID focus areas under this programme. / At this stage it is unclear how the component on technical assistance to the Ministry of Devolution and to Commission for Revenue Allocation will work. The EU intends to procure a firm to provide Technical Assistance, but this hasn’t been done, so not possible to appraise the delivery capacity.
[25] Nyumba Kumi is a Swahili word meaning “ten households” and is a community security initiative based on clusters of ten or so households.

In summary;
- The WB programme provides a good option working at the national level to address system-wide policy issues, develop systems, curriculum and models. It is also well suited to work at county level on specific technical issues e.g. revenue enhancement. The programme is not designed to work over a long period of time in specific counties providing the broad and flexible capacity building support counties need. The links to the WB sectoral work offer good opportunities to work on governance of the health sector and economic development in counties.
- USAID and UNDP offer good options for flexible needs based county level capacity building support. They offer similar support but cover different counties. Both also offer capacity building support to national level institutions supporting the devolution process. Both offer some opportunity to work on governance of the health sector in counties but offer limited opportunity to work on economic development.
- The EU programme’s instrument for building county capacity will be local economic development grants – an interesting but risky approach. This approach is not suited for flexible and broad capacity building support to counties. As with the other programmes, the EU will also provide support to national level institutions supporting devolution. The EU programme is not expressly designed to work in the health sector.

Table4- Advantages and Disadvantages of Option 2 (Strategic partnership with one of the existing devolution support programmes)
Advantages	Disadvantages
Efficiency savings from managing just one partner meaning one set of results, one monitoring and evaluation framework, one set of management and governance arrangements. Less burden on DFID Kenya’s advisers and programme management staff. / Possibility of working at depth in a number of counties or issues. / Better coordination with one partner and into the Devolution Working Group	Devolution and the needs around it are very broad that no single mechanism can adequately cover them or work in all 47 counties / Dangers of straining the management capacity of a single mechanism - absorption risks; inattention to detail, monitoring and evaluation, fiduciary risks. / The different mechanisms have different strengths – UNDP, EU and USAID and their county work WB on the national level policy work, as well as technical competencies in public finance, health system strengthening. / DFID support less visible to GoK

Table 5 - Advantages and Disadvantages of Option 3 (Portfolio approach involving strategic partnerships with a mix of the existing devolution support programmes)

Advantages	Disadvantages
A portfolio approach benefitting from the strengths of the different mechanisms and spreading the risks. This includes the specific strengths of their devolution programmes but also their institutional advantages e.g. the World Bank has a strong relationship with the National Treasury, strong competencies on knowledge and analytical work. UNDP has a strong tradition providing flexible and timely technical assistance to GoK. / Greater coverage both in terms of counties and issues – this is important given that in this early stage of devolution all counties require support and the range of issues is broad. / Greater flexibility as different mechanisms can respond to different needs. / By investing in more than one mechanism DFID is able to influence and leverage the much larger amount of funds existing in all those mechanisms. DFID programming would also benefit from the access, information and lessons emerging from each of the programmes. / An opportunity for DFID to encourage coordination amongst the different mechanisms.	Complex to manage with different management and governance arrangements as well as different results frameworks that need aggregation; heavier burden on DFID advisers and programme management staff. / Diffused programming with many activities / DFID support less visible to GoK

Preferred Option

In light of the amount of work required in these first years of devolution and the need for flexible demand driven approaches the Preferred Option is to fund a mix of the WB, UNDP and USAID programmes (Option 3). The EU programme is interesting but risky and with limited scope. This option offers flexibility and an opportunity to support national level policy processes and system development through the World Bank and provide practical needs based support to counties through UNDP and USAID. Under this option – the WB would be the preferred partner for health and economic development work-streams though this would not limit UNDP or USAID interventions in these areas. All partners would be required to include a focus on gender and conflict. Burden share and Influence - even though we don’t have specific allocations yet, we do know what other donors have pledged and given the overall size of our programme we expect that DFID will be the biggest contributor to the WB and UNDP projects and a minority shareholder in the USAID programme. DFID previously accounted for 80% of phase one of the WB programme and this share is likely to reduce. This is positive as it shows that we have managed to ‘crowd in’ new donors from the success of phase one.

Mobilisation phase –This programme will fund existing and fully developed programmes – however pending approval of the business case we couldn’t agree with UNDP, WB or USAID on the specifics of DFID support. This limited the extent to which we could set out specific results beyond the broad results framework outlined in paragraphs 29,30 and 31 i.e. impact, outcomes and outputs outlined. We therefore propose a mobilisation phase where the first six months of the programme would be spent assessing the detailed proposals and individual results and budgets from each of the three to determine the optimum allocations for each of the programmes. The SRO will submit spending submissions for each partner to the Head of Office for approval. Within nine months the team will prepare a final results framework for the programme based on the broad results framework approved under this business case but with detailed indicators and targets. WB, USAID and UNDP programmes have all designed and shared with DFID and GoK detailed programme documents – the mobilisation phase would therefore not involve design but rather negotiations and contracting.

Costs
The programme budget for Option Three would be up to £23.5m (includes £6.5m from the ICF) and would be allocated as follows;
- £22.5m contributions to WB, UNDP and USAID. This would also include the cost of any programme funded secondments. As set out on paragraph 58 the exact contributions to each mechanism would be worked out at the mobilisation phase.
- £1m for long term learning and evaluation component.

Option Two (maximum £17m) – this option would fund only one mechanism and would therefore have a lower budget. UNDP, USAID and WB all have different programmes and funding gaps, and as such the exact option 2 budget would vary depending on the selected mechanism. Based on our knowledge of the programmes and their existing funding, we expect UNDP to have the greatest funding needs. The current UNDP funding gap is £17m ($26.6m) and it is likely that this would decrease with time as new donors contribute or with increments from existing donors. USAID and WB don’t have a fixed funding gap, they have budgeted for the funds already committed and then identified areas they would scale-up with extra funding.

Under both options we will not be providing and support through government systems. The main categories of direct costs will be:

- Technical assistance to support counties and bodies such as the Kenya School of Government, Council of Governors, Ministry of Devolution and Planning; development of draft laws, policies and plans. This will be predominantly local consultants.
- Training: for county government staff: paying trainers, venue and accommodation costs, development and printing of curriculum and teaching materials. In line with Government of Kenya policy, implementing partners will ensure that as much as possible training is done in government facilities and especially the Kenya School of Government (KSG) facilities. This has the double effect of lowering costs but also building the capacity of KSG which is one of the intended programme beneficiaries. No per diems would be paid.
- The standard administrative fees: (UNDP 8% of the contribution, WB 2%, USAID 0%), salaries and other overhead costs incurred by the implementing agency or agencies. While USAID charges no administrative costs for managing DFID funds – DFID would have to make a proportionate contribution to the administrative costs of the USAID contracted management agent (SUNY). From previous experience, the total of administrative and overhead costs can go up to about 30% of the total – of this amount some of the salary costs are more of a programme cost than administration e.g. salaries of technical experts employed full time by the programmes but involved in actual delivery of programme outputs. We will split this out during the mobilisation phase to present a true picture of the administration costs.

Benefits

It is not easy to monetize the benefits of a capacity building programme of this nature and even harder to ascertain the contribution of donor programmes, mainly because :
- capacity is one of many factors that influence the achievement of the desired impacts and outcomes. Many of the other factors such as political will, civil service culture, and tolerance to corruption are outside the control of donors. These factors interact differently in different contexts even to produce the same result.
- the Government of Kenya is by far the largest funder of devolution in Kenya. The allocation to counties in the FY 2014/15 budget was £1.7bn. Counties are spending a lot on capacity (people, systems, tools, skills), e.g. in FY 2013/14 about 46% (£600m) of county government expenditure went towards personnel payments[26]. This is in one year only and is significantly more than the £90m to be spent over five years through the UNDP, USAID, WB and EU programming. We would however argue that our return on investment will judged by the extent to which the £23.5m helps Kenya get a better return on the more than £7bn to be spent on devolution over the next four years..
  [26] Republic of Kenya, Controller of Budget - Annual Budget Implementation Review Report, 2014

Some of the quantifiable benefits of improving county public financial management, human resource management, performance management, public participation and planning & budgeting include:
- Increased absorption against county budgets: especially with regards to the development budget – In FY 2013/14, the expenditure absorption rate was 82.7% for recurrent expenditure and 36.4% for development expenditure. Kenya’s Office of the Controller of Budget (OCOB) reports that “budget implementation by county governments was faced with various challenges. These included: failure to fully implement IFMIS by some County Governments; low absorption of development funds; inadequate capacity in most functional areas; and failure to submit financial reports on a timely basis. The OCOB recommends full adoption of IFMIS by all County Governments, and timely submission of financial returns to enhance budget monitoring and reporting. County Governments should also prioritise and implement development activities to enhance absorption.” These recommendations are in line with this programme’s focus. Absorption data is available by county so it should be possible to get data on counties benefitting from the programme. Admittedly absorption on its own does not guarantee the quality of outcomes so such information would need to be triangulated with other data e.g. citizen satisfaction survey data.
- Increased county revenue collection: In FY 2013/14 counties, on average, collected 43.1% of their targeted own revenues. This programme would help counties better estimate revenue collection but also recommend measures to enhance revenue. This low revenue collection also contributed to the low absorption rates referenced above as county revenues did not match their expenditure plans. Data on revenue collection is available by county.
- Increased productivity of county governments: A recent WB public expenditure review report shows that in the last decade Kenya has seen increased capital expenditures in a number of sectors, such as health, but this has gone hand in hand with decreasing efficiency. In an areas such as health, this inefficiency derives from skewed allocation of resources across geographic areas, but also a preference for curative over preventive care; absenteeism by health professionals is a major factor; stocks out of drugs and medical supplies. This programme will contribute to improving this through better planning and budgeting, human resource management reforms to deal with issues like absenteeism, better performance management both at county and service facility level, increasing mechanisms for citizen feedback and redress. Future WB public expenditure reports funded under this programme will help track progress. Given Kenya’s huge budgetary investment towards devolution small changes in productivity would yield good enough returns for our investment.
- Savings due to improved procurement and financial management: helping counties improve their public financial management should produce savings due to improved procurement and reduced leakages/corruption. However such improvements are hard to track given the hidden nature of procurement malpractice and corruption. It is possible to use the annual county audit reports to see whether individual counties have acted on the recommendations of the previous year, but this may not necessarily provide enough information on the savings as a result of such action.

Economic Appraisal

Small improvements in any of the quantifiable outcome level benefits above would more than cover the costs of this programme. If the programme spends on average £5m annually– this is equivalent to a 2.7% increase in the annual county revenue collection or a 1.9% increase in development expenditure (using FY 2013/14 baseline). In addition we suggest that capacity building has long-term pay-offs that outlast the initial investment period e.g. once a worker is trained he retains those skills for the rest of his working life; a revenue law continues to provide return on investment even after the drafting period. Another way to look at the revenue example is that break-even can be achieved with a series of small changes over time - £5m investment in the first year is equivalent to less than a cumulative 0.5% annual growth in county revenues collected over a 10 year period (discounted at 10% annually.) These points are illustrative as the programme will spend in many areas and not on a single issue e.g. revenue. We are also cognizant that we are not the only players on any of these issues; that capacity is just one of the constraints; and that attribution is difficult. The main point here is that if this programme is successful we can leverage our relatively small investment against the much bigger investment Kenya is making towards devolution to get satisfactory returns.

The flexible nature of this programme makes it hard to predict the precise interventions it will support. Given we have worked with the WB and USAID before on devolution we can use past performance as a predictor of future programme delivery. These programmes have had positive VFM assessment during annual reviews and end of project evaluations. To illustrate
- With £1.2m through the USAID managed Bridge Devolution Programme (BDP) we delivered training to 2162 county officials with over 90% positively rating the training; five counties were provided technical assistance to develop master plans for varying sectors; six counties were provided technical assistance to draft legislation; three counties were supported with assistance for improved records management systems.
- With £2.6m through the WB managed KADP Programme we have supported design of a county performance management tool that is being piloted in five counties; design of the Kenya Open Data Initiative, 40 data sets uploaded and over 1 million page views per year; in partnership with GoK, developed a Budget Preparation training module and a Financial Accounting, Recording and Reporting (FARR) module. The FARR module has been delivered to approximately 250 county accountants; developed model revenue laws that are being domesticated and used by counties; public participation frameworks in use in at least five counties; four counties supported to develop the 2014/15 budgets. Additionally the programme has led to a greater focus on devolution within the WB and specifically the development of a new WB funded $100-200m devolution programme.

Commercial Case

Strategic Partnerships Approach

We have opted for a strategic partnerships approach as opposed to a competitive procurement process. As discussed in the appraisal case, the option of having a standalone DFID managed devolution support programme was ruled out in the early stages of programme development. This was in recognition that there are four existing programmes all working towards the same general objectives DFID wished to support, and that adding a fifth mechanism would make coordination even more difficult than it already is and increase the transaction costs for national and county government counterparts (who would have to engage with five different mechanisms).This approach is shared with other donors, e.g. Denmark, Sweden Norway, and Finland who have pooled their funds in either the UNDP or WB programme. Even the US and EU who have their own standalone programmes will also contribute to the WB and UNDP pooled funds.

Existing DFID funds have allowed the WB and UNDP to build up their technical capacity on devolution, including international and local staff, but also accumulated knowledge, analysis and research. The strategic partnership approach allows DFID to reap the benefits on this investment as opposed to building it afresh in a new contract.

In terms of delivery against results and programme management, paragraph 53 (Table 3) clearly outlines the pros and cons of each of the strategic partners and the decision process used to decide on which ones to fund.

Value for money through procurement
As stated before the main cost drivers under this programme will be:
- Consultancy fees and staff costs: This will be predominantly local consultants with limited international consultancies. All programmes will seek at least three quotations per assignment. The programmes will also ensure that consultancy rates are within the range prescribed for each organisation. Our experience so far with the WB and UNDP is that these rates are below DFID rates. For the WB programme, an additional control is that rates above the mid-point of each range require Director approval.
- Training for county government staff: we will achieve VfM by training trainers who can train others in counties at minimal cost. Coordination will also be key, e.g. modules and curricula developed by the WB can be used by UNDP and USAID in training they fund. In line with Government of Kenya policy, implementing partners will ensure that as much as possible training is done in the Government of Kenya facilities and especially the Kenya School of Government (KSG) facilities. This has the double effect of lowering costs but also building the capacity of KSG which is one of the intended programme beneficiaries. No per-diems will be paid.
- The standard administrative fees and other overhead costs incurred by the implementing agency or agencies. UNDP and WB management fees are negotiated centrally so limited room for negotiation. USAID will not charge us a management fee. The SRO and the team will scrutinise salaries and other overhead costs to ensure that they deliver value for money.

UNDP - This project will be managed within the framework of National Execution (NEX) modality but taking into consideration recent lessons and risks from other NEX arrangements here in Kenya. These risks are mainly around GoK procurement so in this case UNDP will procure all goods but work with GoK counterparts in recruitment of personnel. UNDP has robust global procurement practices that are used across many DFID funded programmes globally. Major procurement decisions will also be tabled at the programme steering committee where DFID will be represented and have an opportunity to raise concerns if necessary.

World Bank – This is a WB executed Trust fund and DFID has made it clear that no DFID money should be spent through recipient (GoK) executed trust funds ie. go into GoK systems. Procurement for the programme will be carried out in accordance with the World Bank's "Guidelines: Procurement of Goods, Works, and Non-Consulting Services, under IBRD Loans and IDA Credits & Grants by the World Bank Borrowers "dated January 2011 and "Guidelines: Selection and Employment of Consultants under IBRD Loans and IDA Credits & Grants by World Bank Borrowers" dated January 2011, and the provisions stipulated in the Trust Fund Grant Agreement. World Bank in Kenya already has a well-developed procurement capacity.

USAID/AHADI – all procurement will be done by the fund manager, SUNY, and grants to counties will be in kind. SUNY have proven procurement capacity including in the joint DFID/USAID funded Parliamentary Support Programme.

Financial Case
Table 6: The spend forecast for the lifetime of the programme (inclusive of ICF funds):

No	Partner	Project elements	FY1 15/16 / £m	FY2 16/17 / £m	FY3 17/18 / £m	FY4 18/19 / £m	Total (£) / £m
1	World Bank, UNDP& USAID	PFM, Budgeting, Planning, HR Governance in devolved sectors, Technical assistance to the Government, Gender, Conflict and Resilience, Citizen Participation	3.9	6	7	5.5	22.5
2	Service Providers/Consultants	Data collection and learning	0.1	0.2	0.5	0.3	1.0
Grand Total			4	6.2	7.5	5.8	23.5

The above forecast remains an estimate based on a projected pattern of spend – and historical spend from the existing programmes. We will have a more accurate picture once partner agreements are in firmed up. The SRO will work closely with programme partners, to ensure accurate and timely forecasting. The G&S team will convene once a month to review quarterly and annual forecasts to identify any inaccuracies and risks of over, or under-spend. Slippage against the budget will be monitored monthly through a dashboard approach, which will include active risk monitoring and mitigation.

Costs incurred by implementing partners

Table 7: Implications for third party costs.
Partner	Costs
World Bank	WB charges a management fee of 2% (agreed under central MoU)
UNDP	UNDP charges a management fee of 8% (agreed under central MoU)
USAID	No management costs but where we core fund we will share the management costs incurred through a third party like SUNY

Conditionality
The programme does not involve financial aid to governments (both national and county). DFID Kenya has judged that the partnership principles do not apply in the detailed management and monitoring of this programme.

Affordability
Funding is available for FY 15/16 through the current Governance and Security resource allocation of around £4m

Financial and fraud risk assessment

In terms of financial and fraud risk this programme is low risk as it will be implemented through UNDP, WB and USAID systems which are relatively robust.

DFID’s policy on fraud, bribery and corruption is one of zero tolerance. No level of fraud or corruption is acceptable. As already noted, we will ensure that robust due diligence is followed in accordance with DFID’s Due Diligence framework. Where third party contractors are involved we will ensure due diligence assessments are carried out.

We will act to prevent duplication of interventions through the Devolution Sector Working group. The partners will also be required to provide quarterly financial reports and proof of expenditure, a detailed annual financial report, an annual project audit and a post project completion report, with a full project audit, within three months of the project finishing. Audit arrangements are governed by the standard administrative arrangements with each of the partners.

All agreements will specify DFID’s requirement and timelines for reporting fraud or corruption, or any suspicions of fraud or corruption. Any DFID or partner concerns about fraud and corruption will be reported within the required timeframe to the Head of Internal Audit or the Counter Fraud and Whistleblowing Unit.

Monitoring, reporting and accounting for funds
As SRO the Head of the G&S team is ultimately accountable for the expenditure of funds against this business case (including decisions on which organisations will be funded). DFID’s ARIES system will be used to monitor, report and account for expenditure. An ARIES “project” will be established for this business case, with separate components for each programme and/or any contracts managed directly.

The G&S Programme Officer will be responsible for producing reports on actual and forecast spend against each of the components on a monthly basis. These reports will be reviewed by the G&S team, including the Head. If any inaccuracies, risks or issues are identified this will trigger a discussion with project partners. G&S level financial management will also contribute into division-wide monthly expenditure monitoring and reporting which is reviewed by the senior management team in DFID Kenya.

Financial accounting considerations
All required resources will be programme funds. This is part of the budget allocated within the Operational Plan for G&S covering the period from 2015/16 to 2018/19. Payments will be made under the arrangements set out for each partner (above). The SRO will authorise disbursement of funds based on the agreed funding profile set out in the funding agreements and contracts and the assessment of partner performance and reporting.

The implementing partners selected are well-established and respected organisations with a good reputation and track record. They have strong financial and administrative systems. The government is also comfortable working with UNDP and World Bank. They are open, transparent and accountable and have a positive track record with DFID.

Funded projects will be monitored as per the funding agreements. The partners will discuss progress with DFID on a quarterly basis (via regular bi-lateral meetings & donor basket forums) and will provide Annual Reports including annual financial reports that have been certified by an internal partner’s senior financial officer. There will be a full analysis where performance and/or financial targets are not met.

Rigorous monitoring and accounting of expenditure will take place using the partner’s systems. The Senior Responsible Officer (SRO) and the programme management team will monitor reports on a quarterly basis (financial and progress) to ensure Value for Money and compliance rates. Audit reports will identify DFID funding and show any unspent balances. We will also carry out an annual spot-check.

Any assets procured under this project, e.g. office furniture, IT equipment/ software will be disposed of in line with the respective administrative arrangements.

Management Case

The Senior Responsible Officer (SRO) for the programme will be DFID Kenya’s Senior Governance Adviser. The SRO will engage with UNDP, USAID and WB during the mobilisation phase to discuss their detailed funding proposals and ensure spending submissions are drafted for each of them for approval by the Head of Office. The SRO will have programme management support from the team’s programmes management team of two people. The SRO will ensure that DFID is adequately represented in the governance structures of our implementing partners as well as the overall donor and GoK coordination structures.

The programme has a multidisciplinary approach and the governance team will draw heavily on support from DFID Kenya’s health and private sector development teams. The programme will also, from time to time, draw on cross-cutting support from the conflict and social development advisers.

The UNDP, USAID and WB project documents have elaborate governance arrangements as summarised below. These are ongoing programmes and in fact DFID Kenya’s governance team is part of the governance structures of the UNDP and WB programmes through previous funding and therefore the team has experience handling these many implementing partners.

UNDP Integrated Support Programme to the Devolution Process in Kenya
This is an ongoing multi-donor pooled fund. UNDP is the lead agency providing the secretariat – each participating UN agency, will appoint a focal person on devolution to coordinate with UNDP. Project management and oversight will lie with the Project Steering Committee (PSC). The PSC is the highest authority of the project, responsible for making management decisions on a consensus basis for the project. The PSC reviews project progress and results and may adjust activities according to the needs in a changing implementation environment. UNDP rules require that PSC decisions ensure the best value to money, fairness, integrity transparency and effective international competition. The PSC is co-chaired by UNDP and the Ministry of Devolution and Planning. The PSC shall meet on a quarterly basis. The membership to the Steering Committee includes the following: the Ministry of Devolution and Planning, UNDP and funding donors, the Council of Governors, Commission on Revenue Allocation (CRA), select sector ministries, departments and agencies. The Transition Authority will represent the interests of Kenyan citizens who are the ultimate beneficiaries of the project intervention. (NB. DFID is already a member of the PSC by virtue of a £0.5m contribution to this project from the ongoing DFID Kenya Drivers or Accountability Programme)

UNDP will use the existing capacity in its Kenya country office and will also engage technical expertise both locally and internationally to establish a Project Support Team (PST) to manage the implementation of the project. UNDP will further collaborate with the United Nations Volunteer (UNV) office, to tap into the volunteering mechanism to support devolution. UNVs will be engaged as needed to provide specific technical support within counties. The PST will comprise of a Technical Advisor on Devolution, to provide high level policy and technical advice on devolution; a Programme Manager, to provide overall management and coordination of the integrated programme; one Programme Officer to liaise with national level partners and county governments; and a Monitoring and Evaluation Officer, to coordinate monitoring and evaluation (M&E) activities of the programme and ensure timely M&E results reporting by all stakeholders; and a Finance Officer to manage project finances; and a Procurement Officer to manage all project related procurement and a Project Assistant to undertake administrative responsibilities.

World Bank Kenya Devolution Partnership Facility (KDPF)

1. The overarching structure for coordination of KDPF activities, policy dialogue and reporting is the Steering Committee which includes representatives of all donor partners, the World Bank Country Director for Kenya and World Bank Senior Manager(s) of the Global Practices contributing to the execution of the programme. The Steering Committee will endorse the Annual Work-Plans, will receive and endorse the annual reports of the KDPF and engage the Government of Kenya departments as required. It is anticipated that the regular quarterly Steering Committee will be attended by the lead technical staff in both the contributing Donors and the WB, while the Heads of Mission and World Bank Country Director only will attend on an annual/need-to basis.
2. The programme will also rely on guidance from and coordinate with the Devolution Sector Working Group, an existing coordination mechanism that brings together the Government of Kenya and the donor partners related to devolution.

USAID’s AHADI Programme

Unlike the UNDP and WB programmes, AHADI was not designed as a multi-donor programme. It is currently 100% funded by USAID and DFID’s contribution is unlikely to go over 15% of the total programme. Given this and our previous satisfactory experience with the USAID managed Bridge Devolution Programme, we propose a silent partnership with DFID buying into the existing USAID decision making, management and oversight arrangements. DFID and USAID would agree upfront on what components or results DFID money can be spent on and USAID would commit to providing quarterly, annual progress reports as well as a comprehensive end of project evaluation. This approach will reduce the management burden for DFID Kenya’s governance team which has to engage actively in the UNDP and WB governance structures.

USAID has contracted the State University of New York (SUNY) to implement the programme, SUNY will assume overall managerial responsibility for AHADI. SUNY’s management approach provides for significant technical and managerial responsibility for AHADI’s implementation to GOK institutions to advance the ownership and sustainability of the project. SUNY has partnered with both Kenyan and international institutions to deliver the programme. These institutions, and their roles under AHADI, include:
- The Kenya School of Government (KSG) will carry out training and capacity-building activities with targeted county executive branch units.
- The University of Nairobi Institute for Development Studies (IDS) will lead the AHADI project’s learning and research tasks.
- The Centre for Parliamentary Studies and Training (CPST) will develop modules and undertake training and mentoring of county assemblies.
- The Urban Institute (UI) and Local Development International (LDI) are SUNY subcontractors who will work directly under SUNY’s supervision to provide specialized expertise in comparative global and African experience on local governance, decentralization and devolution as requested by AHADI beneficiaries. They will provide technical capacity to develop service delivery improvement technical assistance and undertake learning and knowledge dissemination. In addition, they will provide technical assistance as requested and where necessary in participatory county planning and budgeting and improving the national devolution fiscal architecture.

SUNY/AHADI has a Nairobi office consisting of technical and policy staff covering various thematic areas as well as programme management and procurement staff. This office will ensure strategic and coordinated programming across objectives and partner institutions. They will also support locally-driven field programming and evaluation.

Coordination:
Coordination is one of the challenges that GoK and donors are facing in supporting devolution. GoK has created a Devolution Sector Working Group (DSWG), chaired by the Ministry of Devolution and Planning and with representation from Kenya’s National Treasury, Council of Governors, donors and other bodies involved in devolution. This body meets monthly at the technical level and is meant to meet twice a year at the level of heads of institutions. We regularly attend the DSWG and see this as the principal forum for coordination amongst the devolution support programmes. The DSWG is still evolving and a lot still needs to be done to improve it and ensure it plays it role effectively.

A second coordination structure is the Devolution Donor Working Group (DDWG.) This brings together donors working on devolution allowing for more in-depth discussions on the respective door funded programmes and agreeing common donor positions for dialogue with national and county governments. This forum also allows for frank dialogue and challenge amongst donors and is proving to be a useful forum for coordination. Helpfully the group is co-chaired by a troika of UNDP, USAID and WB so this should help with coordination of their three respective programmes.

On a day to day basis, DFID will actively participate in these two structures and rely on them for coordination of the programmes funded under this BC. This approach allows for coordination with other programmes not funded under this BC and reduces the number or parallel meetings discussing similar issues. DFID will also convene as necessary coordination meetings with the implementing partners especially around the annual review and mid-term review processes.

Mid-Term Review
The current phase of the National Capacity Building Framework (NCBF) runs until the year 2017. Kenya’s next national and county elections are also scheduled to happen in August 2017. The six months starting September 2017 to March 2018 therefore provide a perfect opportunity to review the programme and make any changes to accommodate the next iteration of the NCBF and any new priorities emerging post-elections. We expect that UNDP, WB and USAID will all be reviewing their

Risk Management
The overall programme risk rating is Medium.

Devolution means a transfer of power, functions and resources from the national level of government to county governments. This process has winners and losers which can create resistance to change. As such, the main risks to the success of devolution this programme are political risks. The Constitution Implementation Committee in its first annual assessment of the implementation of devolution stated that “Some of the primary threats to the effective implementation of the system of devolved government identified are: (i) politicization of the process of institutional reforms coupled with inadequate focus on institution building; (ii) delays in undertaking a number of critical transitional activities; (iii) a tendency of both levels of government to discharge (in some cases finance) functions that are not within their purview; (iv) policy, legislative and institutional frameworks that are not cognizant of devolution and; (v) low levels of capacity and skills.”

The table below summarizes the risks facing this programme and the mitigation actions.

Table 8: Risk Assessment and Mitigation Action
Risk	Probability	Impact	Mitigating action
Programme delivery
Reduced political commitment to devolution reforms before and after the 2017 general elections.	Medium	Substantial	Constant political and technical dialogue with GoK, including the High Commissioner as necessary. Build on any commitments/process emanating from the planned high level development partners forum between donors and GoK in Feb 2015 that will be chaired by the deputy president and focus on devolution. / A mid-term review is planned for late 2017 after the general elections. If there is a significant change in support for devolution, the programme will be revised as needed. / DFID aims to be conflict sensitive in its programming. We will require all partners to understand the operating context, understand the interaction between their interventions and the context, and act upon this understanding to avoid negative impacts and maximise positive impacts on conflict factors. (This request has been made under current funding to WB and UNDP) / Ensure constant citizen demand for reforms and accountability through our Deepening Democracy Programme.
Inertia as a result of political challenges in inter and intra governmental coordination	Medium	Moderate	Leverage our implementing partners’ positions as co-chairs of DDWG to encourage constant dialogue between national and county governments. / Provide support through UNDP and WB to strengthen inter-governmental dialogue structures e.g. Council of Governors, the Intergovernmental Technical Relations Committee.
Vested interests and elite networks push back on accountability and transparency initiatives.	High	Substantial	DFID will fund through the Deepening Democracy Programme demand side accountability as a complementary approach to this programme - Citizen demand should work as a counterweight to elite networks and vested interests.
Breadth and depth of capacity building initiatives insufficient to build enough of a critical mass of capable county officials to deliver results.	High	Substantial	This risk has informed the decision to work with others rather than have a stand-alone DFID programme. / DFID support to the WB is contributing to the development of a much bigger $200m WB programme for results that will learn, build on and scale up results achieved under DFID funded programming. The programme will seek to incentivize the national and county governments to invest in capacity building.
Programme Management
Loss of UKaid from financial mismanagement or fraud	Low	Medium	No direct funding of GoK. Monitor UNDP, USAID and WB risk assessments, financial reporting and procurement practice. Major procurement decisions to be tabled at UNDP and WB quarterly steering committee meetings. Spot checks.
Poor Performance by implementing partner	Low	High	We will review implementing partner performance quarterly and during annual reviews. / The Lead Adviser will engage actively in the Devolution Sector Working Group and with the individual members as this provides an opportunity to get feedback on implementation. / During the mobilisation phase we will consider if to allocate all funds or retain some that may be available to partners based on performance.

How will progress and results be monitored, measured and evaluated?

Results Framework - Experience so far with devolution programming is that there will be some result areas where it is easy to set indicators and targets in advance and others that are less predictable given the political nature of devolution – some entry points will open or close unexpectedly and the programme needs to adapt as necessary. There is also a complex relationship between capacity building and the desired outcomes that is not easily captured in linear results frameworks – one has to take into account the political environment, institutional and cultures. This context is different across counties and is also constantly changing. This reality requires nimble programmes with continuous dialogue, review and reprioritization with partners and government.

We have a clear sense of the broad results at impact, outcome and output level, we also have a good idea of the range of possible interventions that can contribute to meeting each of the output areas (see table 1). However, until we firm up funding proposals from each of the partners it is impossible and inadvisable to further elaborate specific indicators, milestones and targets. The indicators will be clearer after the mobilisation phase once we agree specific results and deliverables from each partner.

Flexible programming presents somewhat of a moving target and therefore challenges in monitoring and evaluation. In this respect we will develop and implement a suitable results monitoring framework for the programme which will include some hard deliverables (where targets and milestones can be set) and a supplementary system that allows us to assess those objectives and outputs that will have moving targets. This framework will triangulate data from different kinds of assessment to build a more complete picture of progress e.g. perception surveys, year on year analysis of audit reports, expert panels etc. Initial discussions with other donor funded programmes show that there would be interest in designing some of these tools jointly e.g. a County Governance Index. The idea is for this to be of value to Kenyans in monitoring devolution and as an advocacy tool i.e. not just limited to tracking project results.

We will use the mobilisation phase to firm up the individual results each of our partners will deliver and design this overarching results framework working with DFID Kenya’s Accountability and Results Team (ART). We expect the following M&E deliverables after the mobilisation phase:
  1. Firm up concrete deliverable for those areas that are easy to measure and set targets and milestones for which may easily lend themselves to a log-frame format
  2. A framework for how we can better capture the impact of hard to measure inputs such the technical assistance and training as well as contribution for higher level outcomes such as on policy areas or on new laws etc.
  3. A broader results framework that captures not only the deliverables we can sign up to in advance but those where there are moving targets or those where we have been flexible and taken opportunities of changing circumstances reflecting the demand driven nature of some components.
  4. A results system that is well coordinated with that of other stakeholders and includes a range of tools for collecting information.
  5. The climate change results under this programme will be reported against the ICF Key Performance Indicator 13 and any others that may be identified once the programmes firmed up.

We have set aside £1m funds to cater for both our own monitoring and evaluation and developing the broader county governance index.

Partner Monitoring & Evaluation

UNDP, USAID and World Bank all have elaborate monitoring plans as part of their programme design. They will be responsible for providing DFID with quarterly and annual progress reports. In the case of UNDP and WB these reports will be considered at the Project Steering Committee meetings and Quarterly review meetings respectively. All the programmes have personnel charged with Monitoring and Evaluation. The USAID AHADI programme and the counties will work collaboratively to set performance benchmarks and incentives which will be re-assessed annually. AHADI field office and technical staff working at the county level will maintain regular contact with county interlocutors and continuously evaluate progress, challenges, and opportunities to ramp up assistance.

Different tools supported under this programme will be useful in tracking county performance – examples are the county performance management systems and County Public Expenditure Framework Assessment supported under the WB programme. Performance management and M&E will be both a programme deliverable contributing to county capacity as well as programme management tool to help us track results – as an example USAID’s AHADI programme has designed a participatory Monitoring, Evaluation, Reporting, and Learning and Adaption (MERLA) system which will build capacity through a participatory approach. Programming will start by discussing expected results with partners and how they will jointly achieve and measure those results. AHADI will ensure the participation of county executives and assemblies, women, youth, marginalized ethnic groups and CSOs. Participatory M&E will leave improved capacity within the target counties and CSOs, providing partners and communities with more efficient and effective methodologies to collect, share and information on program outputs and outcomes, best practices, and effective networking models. Continuous dissemination will support learning, programmatic adaption and partner empowerment

Annex 1. Impact of Devolution on DFID Kenya’s Priorities
DFID Kenya Priorities	Challenges, Needs and Opportunities
i. Political settlement, institutions and citizens	Devolution offers an opportunity to build a more inclusive national political settlement by devolving power and resources from a small national elite to 47 regional more evenly shared. For this to be actualised it is useful to get the revenue sharing right and support intergovernmental dialogue, coordination and structures. The revenue allocation process is largely funded by the Kenyan government but donor financial and technical assistance is needed to support intergovernmental coordination structures such as the Council of Governors, Intergovernmental Technical Relations Committee, the Senate and County Assembly Speakers Forum. / However there will be need to ensure inclusivity at the county level and to avoid national elites being replaced by local level elites. The constitution envisages greater participation by marginalised and minority groups in county decision making. It is good that county assemblies have all met the minimum threshold of at a third of members being women. Donor support is needed to ensure this does not become tokenistic and that it goes beyond representation through plans, budgets and implementation. More work is also needed to involve the youth, ethnic minorities and the disabled. DFID through the World Bank has supported four counties do participatory budgeting and new funding would help deepen and scale up such work. / Performance, merit and issue based politics may have more traction in county level elections especially where there is significant ethnic homogeneity or majority. Donor support has been developing plans, policies, legislation and this support needs to continue over the medium term, however more attention will now be needed to support counties in the implementation of those plans and policies as well as developing performance and results management systems. Governors are under immense pressure to track and communicate results and there is a window in these formative stages to lay the foundation for a results culture in the counties. With DFID funding, the World Bank is already involved in helping counties design performance management systems and new funding would help implement and scale up this work. / Devolution has been good for political accountability as there has been greater scrutiny over public programmes at the local level. This is both internal scrutiny by the county executive but also external scrutiny by county assemblies, media, civil society, the Senate etc. DFID funding has helped with induction of county assemblies and strengthening of the Senate but as these are still new institutions more needs to be done. The Senate offers great possibilities for oversight over county governments and there is huge scope to expend of the current parliamentary support programme. / There remains great risk of corruption at the county corruption and already the first year county audit reports from the Kenya National Audit Office (KENAO) have raised significant issues. Many of the audit queries have been around procurement and this is an area that donors can provide technical support. Donors can also support oversight institutions such as KENAO, the Controller of Budget and the Ethics and Anti-Corruption Commission to not only oversee and publicize their findings but also to work with counties to help them devise strategies to counter corruption and mismanagement.
ii. Conflict	With more power and resources controlled away from the centre, devolution could decrease the political stakes to capture the presidency and therefore decrease chances of national electoral conflict. This however increases the stakes for local level politics and Kenya has already started experiencing violent communal and resource conflicts linked to county governance, particularly in the north and coastal counties. Recentralization from districts to County could reopen old communal conflicts that had been resolved through carving out districts for aggrieved ethnic minorities; inter-county boundary disputes - (impact of conflict on women and children.) Donor support can help counties counter this through inclusive and participatory governance with a specific focus on conflict sensitive budgeting and planning.
iii. Core state capability	Kenyan counterparts consistently raise the strengthening public financial management (PFM) as a key priority for donor funding. There are significant amounts of Kenyan public funds now devolved to new county governments. Donors have been helping counties develop their PFM systems. Predictably a lot of emphasis was on planning and budgeting but there is now need to do more on accounting, internal controls and audits. DFID support is helping develop training modules for some of these but there will be need to provide counties develop and implement systems. There are opportunities to learn and build from previous PFM reforms in Kenya and elsewhere in the world / Devolution has led to a significant reorganisation of the public service in Kenya. County governments have three different categories of staff – previous national government staff, formal local government staff and new recruits. These 3 sets of staff have different skill levels, ways of working, terms and condition and counties will need support to harmonize all this and develop standards and norms to ensure their county public services are fit for purpose. Such support will include building the capacity of the newly established county public service boards but also supporting national government develop national standards and norms to guide counties. / Counties have two major sources of revenue – transfers from national government and revenues raised locally. Sustainably increasing the amount of revenues raised locally by counties will be critical if they are to meet the significant public expectations. DFID through the World Bank has helped develop model revenue laws for counties and has also worked with some counties such as Nairobi of their property rates regime. There is significant demand from counties for this support. Donors can especially help counties develop efficient and equitable revenue enhancement strategies that deliver revenue without significantly stifling business. Donors can facilitate lesson learning from other countries.
iv. Growth environment	Kenya’s economy remains resilient and the growth outlook is positive but with perennial shocks and a weak growth environment that have caused it to lag behind its peers. While sound macroeconomic policies have enabled Kenya’s economy to achieve more balanced low growth in recent years, despite various domestic and external shocks, the average real growth of 4.4% between 2009 and 2013 was lower than in Uganda (5.1%), Tanzania (6.7%), and Rwanda (6.9 %). / The overall growth outlook remains positive and annual growth is forecast at 4.7% for 2014 and 2015, primarily driven by continued stability in the macroeconomic environment (inflation remains within the CBK’s target band and the country’s currency has relatively stabilised), growth in both public and private investment (partly due to growth in credit to the manufacturing sector and renewed foreign investor interest, notably in the extractive industries) and robust aggregate demand. However, the government’s reform program to improve the ease of doing business in Kenya is pivotal in achieving faster growth in the medium term. / However, risks remain particularly with regard to negative shocks arising from the effects of the anticipated drought, the deteriorating security situation that continues to affect tourism, the government’s fiscal policy (including rising fiscal pressures), and tighter global credit as the U.S. Federal Reserve winds down its expansive monetary policy[27]. / Notably, sound monetary and fiscal policies will remain critical to maintain growth in the near term and increase it in the longer term[28]. As reflected in debt and deficit levels, fiscal pressure is rising and started building before the roll out of devolution. This is however still sustainable (at 53% of GDP and the fiscal space should expand further to 53% of GDP once the ongoing GDP rebasing exercise is completed in the last quarter of 2014. At the County Government levels, inherited costs continue to constrain fiscal space for development with half of total expenditure[29]. / Additional challenges revolve around corruption and service delivery particularly in light of the devolution challenge, budget absorption and execution at both the national and county levels, declining investment efficiency despite increasing development spending, low investment to GDP ratio (27%), low exports and trade balance challenges that are likely to worsen given the failed EPA negotiations. / There is also the need to deepen fiscal consolidation without reducing infrastructure spending. Fiscal buffers could be rebuilt by reducing duplication at the national level of activities being undertaken by county staff; managing and rationalizing the number of national and county staff; and increasing the efficiency of public spending in education and health, two sectors in which public expenditure tracking surveys have identified wastage. Expansion in the engines of growth to include not only consumption but also investments and exports should also be prioritised. Over the medium term, Kenya needs to boost productivity and regain its competitiveness.
v. Growth transmission	Kenya’s economic growth continues to be broad based, driven by all main sectors and with all main sectors of the economy contributing to growth in 2012 and 2013 for instance[30], however, (although evidence is weak due to a lack of a household budget survey since 2005), the growth elasticity of poverty reduction is low and the trickle down effects of growth and shared prosperity have not been realised as evidenced in high poverty rates (national poverty rate is at 46%[31]) and increasing inequality. / Growth has not (consistently) translated to reduction in poverty and/or inequality. Changes in mean income, rather than redistribution accounted for the largest variation in poverty; and economic growth in Kenya is not always accompanied by poverty reduction. In particular, growth was pro-poor over 1997–2006 but less so over 1994–1997; and there are instances where growth seems to have been pro-rich with factors such as access to fuel, water, and educational attainment having the largest positive impacts on levels and growth in well-being in addition to being key drivers of inequality. Institutional endowment as well as access to institutional services has important implications for pro-poor growth in Kenya[32]. / Inequality is widening, and is driven by a multiplicity of factors – geography, politics, gender, demography, the (lack of) inclusiveness in policy process as well historical factors. In 2011 for instance, the richest 10% of Kenya’s households spent on average 14.3 times more than the poorest 10% of households. Similarly, 10% of Kenya’s wealthiest households control 42% of the total income, while the poorest 10% control just 1%. Over 64% of Kenya’s population live on or spend KES 7,200 (USD 83) or less per month and the gap in educational attainment between middle income and poor Kenyan children is about 40-60% wider than it was about three decades ago. To illustrate disparities in regional development, 82% of the population in Turkana Country is illiterate, compared to just 11% in Nairobi County[33]. / Notably, growth in the country’s agricultural sector has higher direct effects on the incomes of rural households; while manufacturing sector led growth has higher direct effects on the incomes of urban households. Nevertheless, current growth levels are inadequate to reduce poverty and economic growth needs to accelerate to absorb Kenya’s burgeoning labour force and reduce poverty, and mainly tends to benefit the richest urban household deciles who own most of the factors of production. Kenya will need to focus not only on economic growth but also on reducing inequality in order to effectively address the country’s poverty. / Key themes and instruments to achieve this in the new devolved situation will include and greater focus on how to increase the investment and value added role of the private sector, enabling - off farm jobs, i.e. capital investment in processing, skills and enterprise in ancillary services, and promoting mechanization; and in activities that increase the productivity of labour in production i.e. skills, market led extension, agglomeration and sharing of assets, removing subsidized production in favour of subsidizing catalysts for investment. / For this, Counties need to build their economic vision, skills and capabilities, better engage the significant private sector, and promote private investment, PPP and outsource economic activities. / Consistent with this, Counties will have to carefully consider the impact of tax and fiscal stance on incentives for economic development, investment and growth. A recent report provided evidence that over 20 new private sector taxes, fees and charges had been created at County level. Seen in isolation this would tend to imply that economic development is low on County priorities.
vi. Social policy and service delivery	On the political side the major issue has been that of establishing the new Ministerial level organisation and management, the merger of two Ministries into one, and the link with the devolution of authority to the 47 counties. This is the major area of both uncertainty and risk to health services and health outcomes in the next two years. More still needs to be done by government to clarify roles and responsibilities and to put in place the systems, capacities and infrastructure to ensure devolution creates a positive environment for change and not one that disrupts services. Development partners have a role to play both in helping maintain services and supplies in the transition period and also to help develop capacities and systems needed to ensure counties can better manage and implement local health services (both preventive and curative) going forward. / Institutional development will be key to accelerating progress towards the MDGs and preventing stagnation in key areas where progress is needed such as maternal and neonatal mortality decline, uptake of modern contraceptives, and reduction in HIV prevalence amongst MARPs etc. DPs can play an important role in supporting positive institutional development both at Ministry and County levels. Another important area of institutional change will be establishing a more effective private sector and ensuring that there is improved regulation by government and more independent professional bodies. / Maintaining adequate health financing will be a critical challenge going forward, as funding from the national health budget is not earmarked at county level. Politicians have incentives to focus on short term interventions with readily visible results and questions remain on how to maintain investment in prevention, how to maintain investment to sustain previous health gains and how to increase investment in neglected, sensitive areas/issues? / Technical challenges remain. These are numerous but some related to DFID’s current areas of support can be highlighted as an illustration. How to prevent malaria resurgence? How to improve malaria diagnosis? How to translate net ownership into consistent net usage especially among pregnant women and children? How to better address the unmet need for family planning? How to ensure counties follow public health policy and how to prevent and tackle public health emergencies that cross county boundaries?
vii. Resilience	Kenya is highly vulnerable to drought which currently costs 2.4% GDP per year and may rise with climate change. While DFID has other programmes with a specific focus on reducing vulnerability it will be critical that the planning and budgeting support we provide to counties in Arid and Semi-Arid Lands also incorporates building resilience / One paradox of devolution is that while it is meant to address spatial inequality in the short term it may worsen it as areas that were previously marginalized may lack the necessary human resource capacity and revenue base to realize the gains of devolution. In Kenya ASALs may not always be able to attract staff and have a huge infrastructure deficit. There is consensus amongst devolution donors on the need to prioritize these counties.
[27] and 8 World Bank Budget Presentation to the Donor Partner Group (DPG), July 15, 2014.
[28] World Bank Kenya Economic Update: June 2014, Edition No. 10; 89269 v2.
[30] and 11 World Bank Kenya Economic Update: June 2014, Edition No. 10; 89269 v2.
[32] J., Kabubo-Mariara, D., Mwabu and G., Ndeng’e. (2013). “Pro-poor Growth, Inequality, and Institutions in Kenya”. The GDN 14th Annual Global Development Conference on Inequality, Social Protection and Inclusive Growth. June 19- 21, 2013. Manila, The Philippines.
[33] The Start Newspaper (Kenyan Media), 3 December 2013: http://www.the-star.co.ke/news/article-145901/inequality-kenya-can-be-resolved

Annex 2: Detailed Summary of Existing Devolution Support Programmes.

World Bank’s Kenya Devolution Partnership Facility (KDPF)
The programme has current commitments of £7m and will provide analytical and technical support for Kenya’s devolution process. It will complement and inform new World Bank lending operations, and enhance ongoing programmes in devolved sectors. The programme has run since 2012, with the first phase ending in February 2015 – this was funded by DFID, Australia and the World Bank. The current phase was signed off in December 2014 and has attracted new donors with funding from DFID (£1.3m) (from its existing business case in support of KADP), the EU (£1.8m), Sweden (£1.3m), USAID (£1m), and Finland £1.5m).

The development objectives are - strengthened core devolved governance systems at both national and county level through:

- Resource allocation, budget discipline and management, informed by data and analysis,;
- Analysis of the division of functions related to climate resilience between national and county institutions, and identification of capacity and coordination bottlenecks and possible measures to take;
- Strengthened county-level PFM systems and capacity by contributing to the formulation of PFM guidelines, regulations, manuals and templates, related assessments and studies;
- Improved capacity at county level to manage human resources by providing support to the roll-out of public service standards, norms, and HR manuals;
- Improved capacity for evidence-based decision-making and M&E establishing systems to monitor and incentivize county performance, identify capacity gaps, and avail comparative county data to citizens;
- Strengthened citizen participation systems by support to guidelines on transparency and public participation, capacity development, and civic education. Building capacity of ASAL counties to prioritize and implement investments and services that reduce vulnerability and improve climate resilience, as part of participatory county planning, budgeting, and investment management processes;
- Enhanced regulatory, policy and operational framework for devolved sectors through support to the World Bank sector operations.

Some of the results the KDPF is expected to deliver in the six priority areas include: adherence by counties to fiscal discipline rules and regulations increases annually by 5%; development of an operational framework to support county borrowing; PEFA-light framework adopted and applied in 20 selected counties; harmonized county remuneration and benefits guidelines, 47 counties trained by 2017; roll-out of public service standards and norms to 15 selected counties by 2017; roll-out of county performance management system with social accountability indicators in-county to 15 selected counties by 2017; national standards and guidelines on public participation developed and rolled out to 20 selected counties by 2017; sector specific support to improve planning, budgeting, performance management, and social accountability systems.

While the programme will provide some support to counties on a demand or pilot basis, the main approach is to work at the national level on system-wide fixes. This is contrast to UNDP, USAID, and the EU who will have dedicated efforts in a number of counties.

It leverages existing and larger amounts of WB funding - a good example is with the climate change component of the DFID funding, the programme would provide technical assistance to the £50m Regional Pastoral Livelihoods Resilience Project, which provides support to 14 ASAL counties to strengthen natural resource management (primarily water points and pasture management, plus improve conflict resolution mechanisms); improve market linkages; strengthen pastoral risk management (early warning; pasture management). It also includes a sub-component focused on helping the 14 counties incorporate climate resilience investments into their County Integrated Development Plans, budgets, and capacity (given that the county financing is far larger than what is coming through the project). The reality however is that building the capacity of the project and county team leaders to provide this support to counties, and to coordinate with the National Drought Management Authority and other actors, will take a significant investment which WB supervision budgets will not cover and that this programme can contribute to

UNDP’s Integrated Support Programme to the Devolution process in Kenya (2014-2018)

This is a multi-donor programme with funding from DFID (£0.5m), Sweden ($3.4m) Norway ($1m) and USAID ($3.5m), totalling $8.4m out of a budget of $35m. The DFID contribution is from the Drivers of Accountability Programme. The programme has been discussed and agreed with the Government of Kenya. It is also anchored in a joint one UN strategy to devolution.

DFID support would go towards the following three programme objectives:
a. Strengthened policy and legal framework for devolved governance;
b. Strengthened and aligned capacities at national and county levels;
c. Enhanced service delivery mechanisms at the County level

The programme will provide targeted support on building systems and processes for service delivery to a maximum of sixteen (16) counties during the four year programme period. It will also support the Council of Governors to provide a mechanism for consultation amongst county governments; share information on performance of the counties in execution of their functions; facilitate capacity building for Governors; and consider reports from other intergovernmental forums on national and county interests.

Other institutions to be supported include: the Ministry of Devolution and Planning to implement the NCBF; the Intergovernmental Budget and Economic Council, to provide a forum for consultation and cooperation between National Government and County Governments; the Commission on Revenue Allocation to make recommendations on the equitable allocation of the revenue generated nationally between the national and the county governments; the Intergovernmental Technical Relations Committee for the day to day administration of intergovernmental relations; the Commission on the Implementation of the Constitution to ensure that policies, laws, structures, systems and administrative procedures developed and applied at all levels are consistent and in accord with the letter and the spirit of the Constitution.

UNDP will partner with the World Health Organisation (WHO) to provide capacity building in core administrative functions for the County Health Management Teams (County Executive Committee member in charge of health, MCAs in the health committee, Chief Officers and Directors in the health departments).

Under the county planning component of this programme, UNDP would work with five county governments in the Arid and Semi-Arid Lands (ASALs) on Natural Resource Management (NRM) and disaster risk reduction. Specifically this would involve supporting counties to i.) domesticate and integrate climate change adaptation and Disaster Risk Reduction (DRR) into county planning and budgeting process; ii) effectively manage existing natural resources and to reduce the impacts of natural disasters especially for women and children; and iii) support County Governments to establish/strengthen coordination mechanisms which will involve county government, non-state actors, and communities. The coordination structures will guide inventions and investment in natural resource management and disaster risk reduction to ensure coherence and synergy with national level strategies; iv)develop comprehensive land use and county spatial plans that will guide investment of county resources in NRM while taking into account climate change adaptation and disaster risk reduction.

EU Programme – Instruments for Devolution Advice and Support (IDEAS)

The EU will invest €28.6m into the IDEAS project. IDEAS has two components which are based on two key principles of the EU's Agenda for Change: inclusive growth and accountable governance. IDEAS is also consistent with the 10th EDF Country Strategy Paper (2008-2013) which underlines improved governance through the promotion of economic growth and enhanced public participation in local service delivery. The project aims at two results: (i) improved national institutional capacities to support participatory fiscal decentralization ;(ii) increased capacity at the county level to facilitate participatory planning and local economic development.

Besides capacity building at the national and county levels for participatory fiscal decentralisation, the project will support capacity development for administration and public financial management at the county level. It will also offer county level grants for Local Economic Development (LED). The idea is to combine both the tangible economic outcomes of LED projects with governance outcomes by adopting a learning by doing approach, i.e. these projects would need to demonstrate good participatory planning, coordination and policy dialogue between the centre and the counties; and alignment between public and private processes for wealth creation and transparency in use of public resources. Lessons learnt during LED implementation will be fed back into policy dialogue.

Result 1 - Improved national institutional capacities to support participatory fiscal decentralization will include:
•	A grant to the World Bank to support the National Treasury;
•	A grant to SIDA to support the National Audit Office;
•	Technical assistance to the Commission for Revenue Allocation and the Ministry of Devolution and Planning;
•	A service award to the Kenya School of Government;
•	A grant to the Ministry of Devolution and Planning to conduct civic education and to oversee the LED projects.

Result 2: Increased capacity at the county level to facilitate participatory planning and local economic development will involve an iterative process of learning-by-doing at both levels of government – at the Ministry of Devolution and Planning and the county levels. A Technical Facilitation Unit (TFU) will support the Ministry and the counties in the process of implementation. Ten counties will receive LED grants of Euros 1.5 million each. Criteria for selection include: 20% or above urban population in the county; county poverty rate of 45% or above; ASAL; county ability to co-finance 10% of LED costs. Discussions with the Ministry and Council of Governors will guide the selection process.

USAID -Agile and Harmonized Assistance to Devolved Institutions (AHADI)

At $50m over five years this programme is the single largest donor devolution support programme. It is managed by a competitively sourced management agent - the State University of New York (SUNY.) AHADI’s purpose is to ‘assist Kenya achieve the promise of devolution: a governance system that is more transparent, accountable, effective in service delivery and responsive to empowered citizens.’ To achieve this, the project has been divided into the following objectives:
- Objective One: Targeted counties provide higher quality services through improved governance;
- Objective Two: Improved representation of citizen interests and oversight of targeted county government performance;
- Objective Three: Functionality and effectiveness of the devolved system increased through improved intra-government engagement and cooperation.

The programme will work with both national and county institutions with a flexible and demand driven approach. It will support national and county legislative and policy making processes; support county institutional capacity building, i.e. systems that improve human resources, planning, budgeting and service delivery and performance management; help counties identify under-exploited and new potential revenues, improve revenue collection and recording systems and analyse and develop their own fiscal capacities; work with Kenyan Government institutions and other stakeholders to develop a citizen engagement framework to address the critical issue of supply and demand for public expenditure; and to help citizens appreciate the legal and procedural mechanisms envisaged by the constitution for public participation.

County grant funds will be targeted to specific operational needs for the county executive and legislatures. These could support communications, record keeping and public participation mechanisms. Awards could be made as one-off, un-competed strategic grants or as in-kind grants to meet specific, verified needs. A second portion would be awarded to the counties to support specific devolved sectors such as youth, food security, climate change, health, education and participation. A third portion would be allocated to support capacity development priorities that emerge from the comprehensive needs assessments. This may include a set aside for Quick Payback Revenue Enhancement Grants to incentivize improved revenue performance and to demonstrate to other counties that investments in improved billings and collections can be recovered in the same fiscal year. Funds could support a mentoring programme, by and for, elected women officials and senior managers or specific training to assembly members on budgets and expenditure analysis. Grants to enhance citizen engagement may include strengthening the capacities of citizens in target counties around issues of participation, accountability and transparency. Another portion may be grants to engage citizens on national issues and to stimulate their involvement and participation. Finally, grants to develop linkages that would directly support the national entities that have a role in devolution to facilitate both inter-governmental and county-to-central-government relations.