Project Completion Review

Title: Global Health Support Programme (GHSP)
Final Programme Value £ (full life): 12m	Review Date: / 31 May 2019
Programme Code: 20278	Start Date / 24 September 2012	Final End Date: / 31 March 2019

Summary of Programme Performance

Year	2012	2013/4	2014/5	2015/6	2016/7	2017/8	2018/19
Programme Score		A	A	A+	A+	A	A
Risk Rating	low	low	low	low	low	low	low

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717707.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5161696.xls

A. Summary and Overview

Context

The China-UK Global Health Support Programme (GHSP) is a partnership based on China’s progress in improving health outcomes and its potential to make a greater contribution to global health. The business case was based on the assumptions that: a) China has experience to share in health with other countries; b) a UK-China partnership will enhance China’s effectiveness in the provision of development cooperation for health; c) the partnership will increase China’s role in global health policy and governance; and d) the effectiveness of applying Chinese experience could be demonstrated in pilot projects in third countries.

The timing of GHSP has been fortuitous. Support across the Chinese government for engagement in global health as a key element of foreign and development policy has grown significantly. High-level support for China to engage in the response to the West African outbreak of Ebola in 2014 was an important watershed. This was followed, inter alia, by: major financial commitments by President Xi to improving health in Africa; the inclusion of health as a major focus of a new South-South Development Cooperation Aid Fund; acknowledging the idea of a Chinese Global Health Strategy in the Healthy China 2030 Framework; hosting the 9th Global Conference on Health Promotion in Shanghai; integrating health concerns into the Belt and Road planning, including an MOU with WHO; and, most recently, establishing the China International Development Cooperation Agency (CIDCA) to increase coordination across government for development priorities.

Achievements

Following the end of DFID’s bilateral programmes, GHSP has enabled China and the UK to sustain a fruitful partnership in global health during a critical period of policy development and re-orientation of China’s global engagement. This was through research, capacity-building programmes, pilot initiatives in third countries, and regular high-level government-to-government dialogue. The UK-China Global Health Dialogue is highly valued by Chinese counterparts and it is evident from the most recent dialogue (January 2019) that both parties wish to build on achievements and further enhance cooperation in the future.

Programme-supported institutions in China have produced a significant body of research and analysis in two key areas: a) synthesizing China’s own experience in improving health through controlling infectious diseases, improving care for mothers and children, and strengthening health delivery and financing systems; and b) critically exploring China’s current engagement in health and development in third countries. The former studies have informed the pilot projects and are available as a public good through academic papers and policy briefs for all parties interested in applying lessons from China in low income countries. Work on China’s overseas engagement has contributed to the development of a draft Global Health Strategy (see below). The rapidly changing policy environment has created a growing demand for research and analysis from GHSP-supported agencies and an independent review rated five out of 30 policy briefs as being of interest to the highest levels of government. However, the independent evaluation did not find evidence of a direct link between GHSP-funded research and specific changes in policy.

GHSP has helped in building institutional capacity in global health through support for the China Global Health Network and the development of a draft Global Health Strategy. The Global Health Network brings together a range of stakeholders beyond those directly involved in GHSP: academic institutions, private companies and the Chamber of Commerce specialising in pharmaceuticals, and government research bodies and think tanks. It has also managed a programme of small research grants. While concerns remain about its financial sustainability, the network has the potential to be an important legacy of GHSP. The China Global Health Strategy was originally seen as a means of getting cross-government buy-in to an evidence-based approach to guide future policy. In the event, despite a strong body of research, growing interaction across government on global health issues, and being referenced in the Healthy China 2030, the strategy itself has not been adopted by key ministries (MOFCOM, MFA) and exists only as an internal document in the NHC.

Pilot projects have been implemented in three countries: Tanzania, Myanmar and Ethiopia (closed before project ending in 2017). In each case – and in line with the original project design – some short-term improvements in health outcomes could be demonstrated. These included a decrease in malaria prevalence in the pilot area, increased rates of institutional delivery, and increased uptake of family planning, in the three countries respectively. However, the main achievement of the pilot projects has been to provide a real-time learning platform for China with regard to: a) the complexities of working overseas, not least to show that adapting lessons from one country to another requires sensitivity and attention to context; and b) systems for planning, appraising, negotiating and managing projects, as well as deploying and supporting project staff, which are critical for success but currently seriously under-developed.

GHSP has been an experimental programme with few precedents. Making a significant investment in an independent evaluation - conducted at stages throughout the period of implementation - has paid significant dividends in terms of institutional learning. The report by the ePact Consortium captures important lessons for the future – from the programme itself, and in relation to the broader environment in China, the UK and globally. In the words of the evaluation report, “GHSP can be viewed as a probe, helping create understanding of the constraints and possibilities for China’s increased global health engagement and for new forms of China-UK collaboration.”

Partnership performance

Partnerships operated at several levels within GHSP.

1. Between the governments of China and the UK: interactions conducted through the UK-China High Level Dialogues. This aspect of partnership is highly valued by both sides, but it is important to note that the relationship on the Chinese side has been primarily conducted by the National Health Commission with relatively limited involvement of the Ministry of Commerce or other government agencies concerned with development policy.
2. Between the Project Management Office (PMO), managed by the Centre for Project Supervision and Management of the National Health Commission (NHC), and the Project Implementing Agencies (PIAs): the PMO has effectively ensured that activities have been carried out on time and on budget. In an excellent final report, prepared for the completion meeting in December 2018, the PMO synthesized some of the lessons learned about China’s development assistance. Ideally, these lessons should be disseminated beyond the NHC to bodies such as CIDCA.
3. Between DfID, MOFCOM and NHC: through bi-annual meetings of the Strategic Oversight Committee. This mechanism could have been more effective in linking discussion on issues arising from the programme itself with issues discussed at the UK-China High Level Dialogue and vice-versa. Engagement of MOFCOM was strongest at the outset of the programme.
4. Between the Technical Advisory Group (TAG) and the PIAs (managed by the PMO): Chinese members of the TAG have positively influenced the quality of research and analytical outputs. The UK members’ roles have been limited, except when attending meetings in China.
5. Between project partners and multilateral agencies working on global health: there was positive interaction between the PIAs/NHC and UN agencies such as WHO and WFP. This was not developed substantially into active collaboration in the field or cooperation at a more international level.

The future

Discussions on a possible next phase of the programme began between DfID and NHC in mid-2017 at a point when most of the work under Outputs 1-3 was already complete. However, due in part to resource constraints on the DfID side progress has been limited. No-cost extensions were agreed to allow continued support for two of the pilots (in Myanmar and Tanzania) through to their completion in mid-2018 and for the China Global Health Network, initially to September 2018, and subsequently to the final GHSP completion date of March 2019. Following a successful completion workshop (exceptionally well organized by the PMO) in December 2018, a process of information gathering was initiated to inform the preparation of a new business case for the next phase of collaboration. Design of a next phase remains on-going at the time of completing this report, seeking to build on GHSP’s achievements and the experience gained to build a strategic and transformative new programme on global health. This should include a more outward focus on China’s role in the world, working with key multilaterals involved in global health.

Acronyms

ACDC	Africa Centers for Disease Control and Prevention
AWP	Annual Work Plan
BRI	The Belt and Road Initiative
CGHN	China Global Health Network
China CDC	Chinese Center for Disease Control and Prevention
CIDCA	China International Development Cooperation Agency
CoEs	Centers of Excellence
CPSM	Center for Project Supervision and Management
DFID	UK Department for International Development
DIC	Department of International Cooperation
GAVI	Global Alliance for Vaccines and Immunization
GHSP	Global Health Support Programme
MDGs	Millennium Development Goals
MOFCOM	Ministry of Commerce, P.R.China
MOH	Ministry of Health
MoU	Memorandum of Understanding
NAO	National Audit Office
NCDs	Non-communicable diseases
NHC	National Health Commission, P.R.China
NHDRC	National Health Development Research Center
NHFPC	National Health and Family Planning Commission
NIPD	National Institute of Parasitic Disease
PCM	Project Completion Meeting
PIAs	Project Implementing Agencies
PMM	Programme Management Manual
PMO	Project Management Office
RMNCH	reproductive, maternal, newborn and child health
SDGs	Sustainable Development Goals
SOC	Strategic Oversight Committee
SPH	School of Public Health
TAG	Technical Advisory Group
UN	United Nations
WHO	World Health Organization

## B: DETAILED OUTPUT SCORING

Output Title	Increased ability to distil and disseminate Chinese experience in improving health outcomes and strengthening health systems that is relevant to Low Income Countries
Output number per LF		Output 1	Output Score	A+
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	No

Indicators	Target	Achievements*
Output indicator 1.1: Number of Chinese individuals and institutions supported by the programme with strengthened capacity to distil Chinese experience in improving health outcomes and strengthening health systems	10 institutions + 34 individuals	11 institutions + 98 individuals
Output indicator 1.2: Number of publications supported by the programme disseminating Chinese experience in improving health outcomes and strengthening health systems in a way that is relevant to LMICs	See Table 1
Output indicator 1.3 :Number of research partnerships between Chinese and LMIC institutions	10 research partnerships	26
Output indicator 1.4 Number of research dissemination events with LMIC partners, to include researchers and public health officials	10 research dissemination events	17
Output indicator 1.5 Chinese Institutions develop capacity to use evidence on clinical effectiveness to make proposals for policy and clinical guidelines to improve allocative efficiency in the health sector (NICE).	2 institutions (use of clinical pathways etc.)	4
Output indicator 1.6 Chinese institutions share experience of improving allocative efficiency with LMICs (NICE).	2 institutions (share experience on allocative efficiency)	4

Table 1: Publications for all GHSP outputs

PIA	Papers at international conferences	Working papers	Policy Briefs	Articles in international journals	Article in domestic journals	Books/chapters
OP 101 NIPD	6	17	6	28	7
OP 102 Fudan	14	17	8	3	1	1
OP 103 PKU	4	9	7	7
OP 104 CNHDRC	4	3	1
OP 201 PKU	1				6	3
OP 202 CNHDRC				3	9	1
OP 203 NIPD	3				5	3
OP 301 PKU	4	18	1	5	12	4
OP 302 Fudan	4	15	7	7	22	2
OP 401 Fudan	6			2
OP 402 NIPD				2
Others					3	1
Sub-total	46	79	30	57	65	15	292
Targets	60	35	30	24	45	6	200

Financial data (GBP ‘000)
Output 1	PIA	Total Contract Value		Accumulated Spending by June 2019
GHSP-CS-OP1-01	National Institute of	387.12		330.56
Disease Prevention and Control	Parasitic Disease, China CDC
GHSP-CS-OP1-02	Global Health Institute,	425.20		352.08
Reproductive Health / Maternal and Child Healthcare	Fudan University
GHSP-CS-OP1-03	School of Public Health,	456.38		357.73
Health Systems Strengthening	Peking University
GHSP-CS-OP1-04	National Health Development Research Centre	674.55		535.04

Supporting narrative

Synthesizing China’s experience: The volume of work carried out by the PIAs has been impressive. The institutions welcomed the opportunity to document China’s experience, which in the absence of GHSP support would have been hard to finance. An earlier annual review recommended that, given the diversity of products, it would have been useful to pull together an overview of key research findings. This has not been done.

Increasing quality: The two tables show that for OP1 and for publications across all GHSP outputs, the PIAs have exceeded the targets set in the revised logframe. This is reflected in the final output scoring for the 2017/18 annual review, which also recognizes improvements in quality, particularly in relation to the Policy Briefs. The independent evaluation report (7th December 2018) assesses – positively – the quality of English language journal articles, in terms of their impact score and citations, though notes that it has not been impossible to show changes in citations, downloads or impact factors over time.

Lessons learned (OP1 and OP2)

Note: While OP1 is primarily concerned with synthesizing Chinese experience and OP2 is more about understanding best practice in international development, they have much in common given their focus on research and published outputs. There is thus a significant degree of overlap with regard to lessons learned and recommendations for the future. The following points are relevant to both outputs.

From peer-reviewed articles to policy briefs: The second annual review noted that the PIAs gave highest priority to publication in peer reviewed journals. This was further encouraged by their partners in UK universities. Few, if any, PIA staff had experience in writing concise policy briefs. An early recommendation was therefore to provide training and individual feedback to authors. This process, managed by the PMO, has paid off and an independent review of policy briefs suggests that at least a proportion are now being written in a form and with content that will attract the attention of high-level decision makers. A 2-day writing workshop took place in March 2019 to facilitate the publication process of outputs from the project. Fostering the development of the skills needed to convert research findings into convincing policy briefs will also be an important part of future collaboration.

Health and its determinants: Much of the published material on China’s experience in public health focuses on health in isolation from of its determinants. A notable exception is some of the work carried out by PKU to inform the China Global Health Strategy which looks at environmental, trade, food safety and other aspects of international relations.

Exposure to new ideas: While these outputs focus on published materials, the research process has in itself been valuable in exposing PIA staff to new ideas. This is particularly true in relation to increased understanding of development policy and processes in other countries. An extract from the 2016 AR illustrates the range of issues covered by one department in PKU:

“….an analysis of Global Health Strategies prepared by other countries, showing that all countries seek benefits to their own populations (a concern raised by DHC in response to the first draft of the China Global Health Strategy); work by PIA staff on the strategy for the engagement of non-state actors with senior staff of the WHO’s Director-General’s Office; a detailed analysis of the successes and limitations of Chinese supported malaria control in Comoros, with findings to be applied in Malawi and Togo; proposals for changing current policies for the deployment of Chinese Medical Teams based in part on work in Uganda; analysis of cross-border work on malaria in Yunnan Province; and training in global health (particularly in the area of disease control) for a growing number of provincial officials”

Synthesizing China’s experience: The idea underpinning the synthesis work was that it would inform the pilot projects specifically and, more generally, be available as guidance to other low-income countries. The question that arises, however, is what actually makes China’s experience in health exceptional? Much of the work on MCH and disease control – in part as a result of China’s pre-existing global involvement – is already reflected in global best practice. In a purely technical sense, there is thus relatively little that is truly exceptional. What is different is the institutional mechanisms and political context in which disease control and systems-building has taken place. In this arena there is much to learn from China, but making this experience relevant in different national environments will obviously be more challenging. Whatever experience and lessons are applied from other countries and contexts need to be evidence-based and to be adapted to local circumstances.

Involvement of UK institutions: Most of the work carried out under OP1 and OP2 was by Chinese institutions working alone with UK financial support. Involvement of UK partners – primarily academic departments – fell away early in the programme, with the result that there were few opportunities for officials and academics to learn from each other and exchange experience. This essential aspect of GHSP as a genuine partnership has been relatively neglected. Any future phase of this programme should seek to ensure sustained partnerships between UK and China institutions.

Recommendations for future collaboration (see under OP2)

Output Title	Improved understanding amongst Chinese officials and researchers of best practice in international health development cooperation (including bilateral and multilateral)
Output number per LF		Output 2	Output Score	A+
Impact weighting (%)?		25%	Impact weighting % revised since last AR?	No

Indicator(s)	Target	Achievement*
Output indicator 2.1: Number of policy or programmatic papers on development cooperation in health developed	15 policy papers	67
Output indicator 2.2: Policy- and programme- relevant research developed reflecting international practice in DCIH	20 relevant research projects	35
Output indicator 3: Core Chinese institutions developed with capacity as think tank and training provider in development cooperation in health	4 think tanks	4
Output indicator 2.4: Development of a cadre of Chinese consultants supported by the programme with capacity to support Development Cooperation in Health and actively engaged in support to Chinese government, global health institutions, LMIC governments and/or agencies	50 consultants	104

Financial data (GBP ‘000)

OUTPUT 2	PIA	Total Contract Value	Accumulated Spending by June 2019

GHSP-CS-OP2-01	School of Public Health, Peking University	449.86	412.13
GHSP-CS-OP2-02	China National Health and Development Research Centre	449.93	390.38
GHSP-CS-OP2-03	National Institute of Parasitic Disease, China CDC	449.39	412.46
Secondments	SHIYUHUA etc.	107.41	79.90

Supporting narrative

The numerical targets and milestones set in the logframe have been exceeded, and the quality of outputs (briefing papers and policy briefs) in the view of NHFPC officials and TAG member Xu Tongwu (who has actively supported the process of preparing policy briefs) has continued to improve.

Improved policy briefs: The policy briefs produced under GHSP have been reviewed by the Institution of Information Studies of the Chinese Academy of Social Sciences (at its own initiative). As a measure of influence, out of 30-plus briefs produced under GHSP, five were selected as being of potential interest to the highest level of government, and sent to the General Office of the central government. Of these, three were concerned with non-communicable diseases: one spelling out the magnitude of the threat; one specifically on tobacco; and a third recommending learning from the experience of Japan. The other two briefs were both concerned with health security: protecting China’s borders from incoming threats (particularly malaria), and focusing on health security in the context of BRI. This suggests that global health as an issue has greatest traction politically when shown to be of domestic as well as international concern.

Institutionalising global health: For some individuals involved in the project, GHSP has been of great value – not just in building awareness, but in potentially launching careers in global health. At an institutional level, there is evidence of a stronger link between the NHC and researchers. Conducting research funded by GHSP has led to an active search for other sources of funding, so that all institutions involved in GHSP now have a growing portfolio of global health-related research, albeit with small grants from diverse sources. Fudan GHI has been particularly active in this respect, securing funding for MCH projects in Africa from the South-South Fund. Similarly, NIPD has been successful in lobbying for funding from the Gates Foundation to continue aspects of the pilot work in Tanzania.

Approaches to capacity building: In the universities, the emphasis has been on building research capacity in the specific departments involved as PIAs. By contrast, the National Institute of Parasitic Diseases (and China CDC – see OP4) has been more concerned to develop – through training and overseas exposure – a cadre of officials at central and provincial level who can be called upon in future to provide international technical support.

Recommendations for future collaboration from OP1 and OP2

Note: It is not assumed that future collaboration would necessarily be structured in the same way as GHSP and thus the following points address the issue of capacity building more generally.

Changing the focus of capacity building: Building capacity is seen as a priority for future UK-China collaboration. While there is likely to be a demand for continued support to the PIAs involved in GHSP, the focus of support needs to change: a) to be more strategic and programmatic – focusing outward on China’s role in the world – not simply strengthening the traditional role of academic institutions; and b) to operate more as a genuine partnership with exchange of learning and experience between individuals and institutions in the UK and China.

Learning on the job: While China will forge its own path as a global health actor, there is a recognition of a need for greater learning, including learning by doing. The UK is still seen as an experienced partner that China can learn from.

Possible objectives for future work on capacity building (set out in more detail in a paper in January 2019: Developing China-UK collaboration on global health, Lewis Husain and Andrew Cassels) include:

Strengthening capacity of Chinese institutions (health and non-health) to provide better support to China’s overseas engagement and – in time – better outcomes as China’s health engagement increases.

Strengthening health agencies in their interactions with key parts of the emerging development architecture, including CIDCA and associated agencies, so as to promote better planning, spending, project oversight, etc, and sufficient inclusion of health concerns across the Chinese system.

Strengthening the capacity of non-health agencies (CIDCA and others) to work with and draw on health agencies in their planning, spending, project oversight, etc.

Chinese overseas investment programmes that are not directly health-focused explicitly consider health implications, to achieve positive health outcomes and avoid negative health impacts.

Strengthening the capacity of health agencies to engage with multilateral agencies in order to increase China’s contribution to global health and its ability to determine which multilaterals to work with and how.

Output Title	Enhanced ability of Chinese officials and researchers to contribute to global health policy and governance
Output number per LF		Output 3	Output Score	A
Impact weighting (%)?		25%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s)	Achievements
Output Indicator 3.1 / Establishment and strengthening of a China global health network supported by the GHSP, whose aim is to provide a forum for discussion, development and mutual learning among PIAs and other concerned institutions	China Global Health Network	China Global Health Network established, but not yet fully financially sustainable
Output Indicator 3.2 / Policy relevant research produced and proposals developed for a China national global health strategy	Policy relevant research contributes to China Global Health Strategy (10 papers + 1 proposal)	China Global Health Strategy developed as internal NHFPC policy paper (11 papers + 1 proposal)
Output Indicator 3.3 / Increased collaboration between China and UK through High Level Global Health Dialogue	Increased collaboration between China and UK through High Level Global Health Dialogue	China-UK global Health dialogue convened regularly. Alignment on key global health issues of mutual concern – AMR, health security, WHO reform. Joint visits to Sierra Leone and Addis Ababa (Africa CDC). Fifth meeting was in January 2019 prior to WHO Executive Board meeting.

Financial data (GBP ‘000)

OUTPUT 3	PIA	Total Contract Value	Accumulated Spending by June 2019
GHSP-CS-OP3-01	School of Public Health, Peking University	553.75	485.81
GHSP-CS-OP3-02	School of Public Health, Fudan University	505.98	386.25
China Global Health NetworkⅠ	School of Public Health, Peking University	42.36	37.55
China Global Health NetworkⅡ	CGHN Members	153.00	140.84
4th UK-China Global Health Dialogue	PMO	N/A	1.89
5th UK-China Global Health Dialogue	PMO	N/A	21.26

Note: OP3 is concerned with capacity building and thus points made above with regard to future collaboration under OP2 are equally relevant here. However, the focus of OP3 is more specific and primarily concerned with three institutional objectives: a) the development of a Chinese Global Health Strategy; b) the establishment of a China Global Health Network; and c) the convening of China-UK High Level Health Dialogues.

Global Health Strategy (GHS):

Earlier Annual Reviews saw the Global Health Strategy as being potentially one of the most influential products of GHSP. Early progress resulted both in the impact weighting for OP3 being increased and the overall Programme Performance score being increased to A+. However, the research coordinated and carried out by PKU has been used so far by the NHC only to develop an internal policy paper, without specific endorsement and follow-up actions from MOFA, MOFCOM or other ministries. There still appears to be support for the idea of a cross-government global health strategy, as evidenced by reference to the global health strategy in the Healthy China 2030 Strategy. However, there remains insufficient system-level coordination between health and other ministries/agencies with a link to China’s increasing overseas engagement, through BRI and other channels.

Lessons learned (GHS)

GHS – overtaken by events?: Reasons suggested for proceeding with a government-wide strategy include the fact that the process of cross-sectoral and cross-ministerial consultation and approval would have been lengthy. It is also the case that recommendations with regard to aid coordination contained in the PKU papers may well have been overtaken by events – notably the creation of CIDCA in 2018. Recent interviews suggest that interactions between NHC and MOFCOM have increased markedly over the last 18 months as demand for advice from MOFCOM has grown. Discussion has been conducted in the context of a sub-committee on health issues covering Chinese medical teams, China-Africa Friendship Hospitals and Africa CDC, and priorities for health aid.

China Global Health Network (CGHN):

The first International Symposium on Global Health Development was convened by the China Global Health Network in November 2016 and attracted over 300 participants. DfID Asia health advisers meeting in Beijing at the same time took part as active participants. As part of the no-cost extension of GHSP, the SOC agreed that support for the Network should be extended to mid-2018, and subsequently to March 2019. During this period the GHN has organized bids for, and awarded, 11 small policy-research grants using GHSP funds, to both university and non-university recipients, for work related to AMR and to health in the context of BRI. In December 2018 the CGHN organized a successful conference following on from the Project Completion Meeting. As it has developed, the NHC has played a role in steering the network and guiding its work. In other words, the CHGN is beginning to function as a useful platform for government (which was one of its intended functions). The move to CNHDR – a think tank allied to DHC (see below) reinforces this view.

Lessons learned (CGHN)

Advantages over other networks: The importance of GHN is that it has the potential to bring together a wide range of institutional stakeholders involved in global health, including private companies and the Chamber of Commerce specialising in pharmaceuticals and medical devices, the China Hospital Alliance, the China Poverty Alleviation Foundation, as well as research bodies such as CNHDRC (supporting the NHC). While the focus to date has been on health-related agencies it has the potential to attract agencies involved in other aspects of development such as the Shanghai Institute for Development Studies (which supports MOFA). In this regard it has a distinct advantage over other existing networks. For example, the China Society for Global Health (CSGH), chaired by TAG member Han Tieru, is an association of individual medical specialists operating under the aegis of the Chinese Society of Preventive Medicine. Similarly, membership of the Chinese Consortium of Universities in Global Health (CCUGH) is limited to universities and is primarily concerned with developing the academic discipline of global health (defining content, coordinating courses across universities etc.).

Sustainability: CGHN is clearly valued by NHC as well as by its institutional members beyond the university sector. The first secretariat (managed by PKU) had ambitious and imaginative plans for how the network could be used as a platform for synthesizing knowledge for government on China’s key relationships with multilateral and bilateral partners. Responsibility for the Secretariat has now passed to CNHDRC whose staff have welcomed the opportunity to take the network forward, but the capacity of CNHDRC in terms of staff numbers is limited. A more fundamental problem is institutional and financial sustainability. Because GHN is an informal network it does not fit comfortably into an institutional category (unlike CSGH) that would readily allow registration as a national body. Lack of formal registration, in turn, makes it difficult to secure government financial support.

Recommendation for future collaboration (CGHN)

It is likely that there will be a bridging period while a new phase of partnership is being developed. Continuing support for CGHN during this gap would represent one way of maintaining some momentum. Beyond that gap, funding in future could support small research projects linked explicitly to topics that are the focus of the next stage of the partnership. The function of such projects could be viewed as much as building capacity and institutional links as for the value of the outputs. This could be a relatively cost-effective way of continuing collaboration, and bringing in more peripheral Chinese global health agencies, but (on the experience of similar work done under the GHSP) may require substantial involvement from senior Chinese researchers in an oversight capacity. Any support must also recognize the limited capacity (principally staffing) of the CNHDRC.

China-UK Global Health Dialogue (GHD)

July 2017: After a gap of two years the China-UK dialogue was held in Beijing in July 2017 including visits to two PIAs (NIPD and Fudan) in Shanghai. Earlier annual reviews noted that while the dialogue addressed issues of concern to both governments, meetings were not followed up with joint activities. In this case, however, the meeting was followed up by joint visits to Sierra Leone and, more recently, to the Africa CDC in Addis Ababa. Senior officials discussed Chinese and UK support for Africa CDC and its relationship with the WHO Regional Office for Africa.

January 2019: The fifth UK-China GHD took place in London in January 2019 immediately prior to the World Health Organization Executive Board meeting in Geneva. Topics covered included the next phase of China-UK Global Health Collaboration; preparation for the WHO Executive Board; the upcoming UN High-Level Meeting on Universal Health Coverage; approaches to GFATM replenishment; support to the Ebola outbreak in the DRC, and collaboration on health security in Africa.

Lessons learned (GHD)

Dialogue is highly valued: Maintaining a dialogue with senior officials in the UK on issues of mutual interest in global health is always the first point to be mentioned in any discussion of future collaboration with China. Considerations for the future: a) improving preparation, relevance, linkages and follow-up - while maintaining the basic format of the current China-UK Global Health Dialogue; b) seeking opportunities for UK engagement in other high-level fora that address China’s role in health in the context of globalization (such as the proposed WHO-China High Level dialogue on Health and the Belt and Road); and c) extending dialogue to both involve multilateral institutions and engage with multilaterals in other fora.

Coordination across departments is an issue for both governments: It is evident that to be productive, dialogue (and indeed future programme development) needs to involve a range of departments and agencies that are involved in global health. On the UK side, following the intervention of senior DfID officials, the 5th GHD brought together different functional and geographical departments in DfID, representatives from Public Health England, the FCO and the Department of Health and Social Care in order to cover the different issues on the agenda. In China, responsibilities for global health issues are similarly spread across government, with relationships changing following the creation of CIDCA.

Recommendations for future collaboration

Measures to substantially improve the effectiveness and relevance of the China-UK Global Health Dialogue are set out in the first four recommendations in the December 2018 GHSP Summary Evaluation Findings. In brief it is recommended that: a) both countries need to recognize the challenges inherent in having dispersed responsibilities for global health; b) both countries need to identify a focal point in government overseeing UK-China collaboration in global health; c) participation in future dialogues should be expanded to include all relevant agencies; and d) as China’s landscape changes there will be a need for additional mechanisms for collaboration that include newly significant actors including CIDCA, its associated agencies, development banks with overseas financing responsibilities and other financing and regulatory institutions.

In order to enhance the ability of China to contribute to global health policy and governance, a further phase of GHSP should continue to support these networks but also move beyond these to engaging directly with the relevant global institutions. As the Final Evaluation recommended, the China and UK governments should establish a mechanism for collaboration in managing their relationships with the WHO and other multi-lateral organisations and global health initiatives. The Evaluation also report noted that funding sources to work bilaterally are diversifying. For instance, the Gates Foundation is providing funding to continue the pilot in Tanzania and is starting to support work on China’s health assistance to Africa. Therefore, while UK-China bilateral cooperation should continue to be a feature of any future phase, there are also other possibile sources for funding. Explicitly extending a future phase also into the multilateral sphere will consolidate the gains achieved through the dialogue mechanisms developed in this programme and will raise the programme to a more strategic level to feed into global health policies and governance.

Output Title	Pilot partnerships apply China experience and international best practice in development cooperation in Low Income Countries and cross border (probably to include in the first instance malaria, universal health coverage, maternal and child health, polio and human resources for health).
Output number per LF		Output 4	Output Score	A
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Achievement
Output indicator 4.1: Number of pilot partnerships implemented	4 / Myanmar, Tanzania, Ethiopia and Sierra Leone.
Output indicator 4.2: Pilots incorporate China experience and international practice in DCIH	International best practice in malaria (Tanzania) more evident than specific China experience.
Output indicator 4.3: Pilot partnerships lead to improved Chinese engagement in global health cooperation	Lessons learned from pilots recognized as being critical for future development cooperation by PIAs, NHFPC, but link with MOFCOM remains weak.

Financial data (GBP ‘000)

OUTPUT 4	PIA	Total Contract Value	Accumulated Spending by June 2019
GHSP-CS-OP4-V01	MCH Pilot	2,135.67	2,112.87
GHSP-CS-OP4-D02	Malaria Pilot	1,820.35	1,812.79
GHSP-CS-OP4-D03	China CDC	343.83	200.88
GHSP-CS-OP4-D04	China CDC	104.83	77.35

Supporting narrative

Achievements in pilot countries

Improving health: The original intent of GHSP was for the pilots to demonstrate that applying Chinese experience in low income countries would result in better health outcomes. In practice, progress has been slow and many difficulties have been encountered. Despite these problems some health improvements have been recorded.

Work in Ethiopia led by Fudan University and implemented by MSI finished prematurely in June 2017 following a series of logistical difficulties with the procurement of commodities. Nevertheless, following training and refurbishment of facilities, there was an increase in family planning uptake and in assisted deliveries and referrals.

The MCH project in Myanmar, led by Fudan, monitored and assessed by Kunming Medical University and implemented by Marie Stopes International, contributed to an increase in institutional deliveries and uptake of pre- and post-natal services. It focused on using financial incentives (a proportion of expenses related to deliveries was reimbursed) to promote institutional deliveries, particularly among young women and migrants.

In Tanzania, a complex multi-component malaria control pilot led to some improved health outcomes in the project area, with the pilot interventions resulting in a decline in prevalence greater than that attributable to bed-nets alone.

GHSP also supported an assessment exercise in Sierra Leone designed to inform MOFCOM support for the Tropical Disease Research Centre. This followed the establishment of a Level 3 public health laboratory during China’s support for the Ebola response.

Pilots served several other functions: The methodology adopted as part of the evaluation delineated four additional functions of the pilots in addition to improving health outcomes: a means of testing Chinese experience in non-Chinese settings; providing a platform for learning by PIAs; providing a structure for UK-LIC-China cooperation; providing an evidence base for changing policy or practice in the countries concerned. Findings in relation to these functions are summarised in the sections below.

Lessons learned
The independent evaluation found that, overall, the pilots have demonstrated an ability of Chinese agencies to support overseas programmes in collaboration with in-country partners, and to contribute (to varying degrees) to implementation, though with substantial transaction costs. The following points are taken in part from the Summary Evaluation Findings:
Learning platform: The pilots have provided an important platform for learning by the programme implementing agencies, and for the Chinese system more broadly, about the complexities of operating overseas and constraints to this. Several of the institutions involved have documented their experience and the difficulties they have faced, but it is as yet unclear as to whether these lessons have been made available beyond the PMO and NHC.

Managing change: The GHSP has shown that adapting ‘experience’ from one country to another is challenging; understanding some of the deeper lessons from China’s experience will likely mean looking more deeply at how China has managed change.

Chinese experience: Linked to the former point: one of the fundamental ideas that underpin GHSP is that the pilots offer an opportunity to apply Chinese experience, particularly in disease control and MCH. However, the strategies for MCH in Myanmar (removing economic barriers to institutional delivery, using volunteers to stimulate demand, and upgrading facilities and equipment) and for malaria control in Tanzania are not markedly different from international best practice or from what is being done elsewhere by other partners in the same countries. It could be that the distinguishing element of Chinese experience is thus seen less in technical approaches and more in terms of a governance and institutional environment that has made rapid progress possible. Understanding institutional, political and social contexts is key to successful implementation. A key learning point for all the teams is that they have had to adapt their approach in the face of weak systems and poor governance.

Management of pilots: The operation of the pilots, and the learning from them, is conditioned, at least in part, by the way they were managed. Difficulties might have been reduced (and the pilots might have been able to accomplish more) with a different management structure, or more support.

Recommendations for future collaboration
- Capacity to manage overseas assistance: China contributing technical assistance to overseas programmes will require greater, and more widespread, capacity to operate in non-Chinese contexts and make Chinese expertise available in ways that are informed by other country contexts.
- Involvement of UK and China government in country: The pilots did not substantially engage Chinese and UK agencies in the pilot countries, however, and engagement with pilot country governments was slow to come. This highlights the limited capacity of both the Chinese and UK systems to cooperate at a country level. Feasible ways to collaborate will require further exploration, and greater support from Beijing and London (Note: recent work in Sierra Leone may be an exception in this regard, in that the assessment exercise carried out by China CDC had at least some input from Public Health England (PHE). The extent to which this input was reflected in the report is not clear).

Working with multilateral institutions: Building on the previous point about UK-China cooperation, future work needs to consider the wider range of actors, especially multilateral agencies. This will be both at the country level related to specific activities, and at the international level in relation to broader policies and approaches to global health interventions.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

The theory of change (summarised above) has evolved over the lifetime of the project. The starting assumption was that synthesizing Chinese experience in health and creating greater awareness of best practice in development cooperation would create a demand for more support from university researchers and other institutions, and that the pilot projects would provide the evidence needed to demonstrate the potential value of applying Chinese experience in low income countries.

In practice, policy changes and a range of commitments made by the Chinese government in relation to global health early in the life of the project meant that demand for support already existed and that the task of the PIAs was less to stimulate demand than to make sure it could be adequately met. While the purpose of the pilot projects (see analysis of lessons under OP4) has not primarily been to demonstrate the application of Chinese experience in low income countries, their role in the theory of change has remained significant – in terms of helping to identify structural, systemic and logistic constraints that will need to be overcome if China is to change its model of development cooperation in health. Partly this is about how China engages bilaterally, and partly it is how China maximises the impact of its interventions by collaborating with other parts of the global health system. This should be reflected in the theory of change of any further phase of this project.

Impact: China-UK partnership that contributes to improved global health policy and outcomes

In terms of impact there is little doubt that commitments to global health made by the government of China have the potential to improve health outcomes in low income countries. In part this is a function of aid volumes in a global context where levels of development assistance for health have plateaued since 2010 and prospects for a decline from traditional donors are to be expected. In aid dependent countries, where each dollar of domestic spending is matched by $ 0.71 of aid spending (IHME estimates 2016), China’s financial contribution will make a significant difference. In addition, however, it is a reasonable expectation that China will play an increasingly important role in global health governance and diplomacy – boosting efforts to address key issues on the global agenda, including universal health coverage, AMR, non-communicable diseases, health security and access to medicines.

The contribution of GHSP is modest. Nevertheless, its contribution is regarded very positively by key stakeholders (“no other project has been given so much attention” said one interlocutor reporting on a conversation with a high-level official in MOFCOM). It has also had a positive impact in broadening understanding of global health issues and development cooperation and increasing the number of individuals and institutions available to support China’s foreign policy and development cooperation goals.

Outcome: UK partnership helps China improve its contribution to global health and achieve the potential of its health cooperation

The logframe has three outcome indicators, which do not capture very well the theory of change to achieve the outcome:

Indicator 1: China is an active participant in a range of global health fora. The targets/milestones set in the logframe are laid out in terms of numbers of Chinese officials appointed to global health organizations. A possibly more useful measure, as noted in recent Annual Reviews, is to qualitatively assess China’s influence on global health governance through its interactions with key global players such as WHO. (Note: evidence from the evaluation shows that the number of senior Chinese personnel working in WHO HQ and the Global Fund has not changed significantly). It will be important to get this right in any second phase of the programme that will be more focussed on strategic engagement with these key global players.

Indicator 2: Lessons from pilot projects. As noted above - important lessons have been learned, to achieve the outcome fully these structural, systemic and logistic lessons need to be fully documented and made available for discussion by both MOFCOM, NHFPC and any new agency responsible for China’s development cooperation. It will be important that evaluation findings are made available beyond the NHC.

Indicator 3: Global health networks support China’s development cooperation in health. The Global Health Network (GHN) is seen as a way of accessing advice from its members, more by NHC than MOFCOM. If plans suggested originally by PKU are realised – using members of the network to track relationships between government agencies and key international partners – the utility of GHN’s advice is likely to increase substantially. For this to be possible, and for the full potential of GHN to be realised, it is critical that issues of financial sustainability and institutionalisation be addressed.

Major changes to the logframe in the past year
None made.

## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case
Original assumptions remain valid: The value for money proposition made in the original business case is based on the assumption that the different capacity building components of the project will result in improving the efficiency and effectiveness of China’s health cooperation. While the costs are relatively small at GBP12 million, the potential gains, while difficult to monetise, were predicted to be significant. Unit costs were controlled through project monitoring and through careful negotiation of performance-based contracts between the PMO and PIAs. All these assumptions remain valid.

Value for money has increased over the lifetime of the project: Given major changes in the policy context, and the growing importance of global health as a foreign policy and development objective in China, the project arguably represents even greater value for money than was predicted in the business case. For the same financial outlay the potential for influence on the effectiveness and efficiency of a growing quantum of Chinese aid continues to increase. Moreover, the project logic no longer relies on building a case with government for changes in the form and content of Chinese aid; there is already a growing demand for advice, for example on how to programme health aid in Africa and as part of BRI. The likelihood of project partners being able to influence project outcomes has increased substantially. While GHSP is not the only initiative that seeks to influence Chinese health and development cooperation it is seen as one of the most important and is being copied in some measure by others such as the Bill and Melinda Gates Foundation, thus creating further spin-offs and a multiplier effect.

Project governance and management continues to focus on value for money and efficiency. The production of policy briefs on the Chinese experience in global health illustrates how the project is achieving value for money. The quality of the English language briefs is now roughly equivalent to those produced by a UK resource centre; the audience for such briefs is large in China; and there is an appetite for understanding the Chinese experience globally. Had the production of these briefs been led by UK institutions working with Chinese partners (rather than vice-versa) costs would have been substantially higher. In addition, because contracting of UK and other international partners was managed by the PIAs, unit costs for external inputs were, for the most part, much lower than UK market rates.

Project extensions

GHSP was scheduled to close in March 2018, with the expectation that a new phase of collaboration would ensue. Given delays in starting work on a new business case a no-cost extension was agreed, initially to September 2018, subsequently through to March 2019. The extension required no additional funds and allowed support for completion of work on pilots in Tanzania and Myanmar as well as continuing funding for the China Global Health Network.

A further phase of this programme would have the potential to achieve significant value for money, building on the achievements, the capacity built and the networks established under this project. It provides the potential to lift future engagement to a more strategic level with China as an informed and active participant in global health institutions and activities.

E: RISK

Overview of programme risk

Overall risk rating: minor

The PMO has maintained a Risk Management Register, identifying 15 risk factors. Severe risks include: political factors in pilot countries cause project termination; pilots are not completed; the innovative nature of pilot activities might not lead to expected objectives; the influence of changes in SOC membership; insufficient managerial experience on the part of PIAs leads to delays and mistakes; and foreign exchange fluctuations reduce project funding. The risk to the project as a whole is rated as minor throughout the life of the project and no actions beyond the recommendations in each annual report were indicated.

Of the risks listed, those concerning the pilot projects were realised. The risk of not achieving original outcomes was compensated by the fact that the pilots offered a learning platform for PIAs, the PMO and government agencies more generally.

Update on partnership principles
Summary of partnership performance included in Section A.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Financial data (GBP ‘000)

Financial Year 2017-19*	Output 1	Output 2	Output 3	Output 4	Management	Governance	M & E	TOTAL
Forecast	0	455	414	2,323.22	300	570.6	157.5	4,340.67
Actual spending by June 2019	0	381.45	314.85	1,791.84	304.19	176.14	191.91	3,160.38

*the original project end date was end September 2018 so the workplan and budget were approved in 2017 for this period

Quality of financial management

The most recent audit covering all activities in 2017 was submitted in July 2018 by the China National Audit Office. As in previous years, the auditor examined the financial statements as well as compliance with state laws and regulations and grant agreements with the relevant entities, its internal financial control, project management, and project performance during the project implementing process. The report contains no objections and attests that the financial management and approval process was “relatively perfect to ensure the safety of funds”.

Date of last narrative financial report	18 February 2019
Date of last audited annual statement	July 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring

Five independent annual reviews have taken place by the same consultant, the most recent in March 2018. These reviews included interviews with all current PIAs as well as government officials and other development partners active in supporting China in the area of global health (WHO, UNICEF, Gates Foundation, China Medical Board). The last two annual reviews were conducted jointly with a member of the Final Evaluation team in order to combine discussions on recent progress with longer-term policy perspectives. Recommendations and actions taken following the Annual Reviews are summarised below.

For the last two Annual reviews no interview could be scheduled with MOFCOM, but the team had useful interactions with a health adviser in CAITEC (a think tank supporting MOFCOM).

Interaction with the pilot projects was limited to telephone calls for the purposes of the Annual Reviews. This is not a satisfactory means of assessing progress. Monitoring work in the pilots has therefore relied on visits by members of the evaluation team and DfID staff.

This Project Completion Review was undertaken as a desk-based exercise drawing on past annual reviews, reports from the evaluation team, and presentations made at the 2018 Project Completion Meeting.

Evidence

The most significant evidence gathering has been undertaken as part of the independent evaluation and is contained in the annexes of the ePact Final Report. Evidence from Annual Reviews has been used to make recommendations after each visit (see below). Evidence from pilot projects collected as part of the evaluation has been used to show impact where it has been achieved and to substantiate the lessons learned and recommendations listed under OP4.

Learning

GHSP has been designed as a learning exercise. As noted by the evaluation team: “GHSP can be viewed as a probe, helping create understanding of the constraints and possibilities for China’s increased global health engagement and for new forms of China-UK collaboration. In this PCR, which is organized around outputs, key lessons have been summarised in each section and combined, where appropriate, with recommendations for future collaboration.

A synthesis and overview of what has been learnt through GHSP is contained in a 10-page summary of the evaluation findings. What has been learned through GHSP has also informed the Options and Analysis Paper submitted to DfID as an input to the design of the next phase of collaboration.

Recommendations from past Annual Reviews

Recommendations over the lifetime of the project follow a number of themes:

Published outputs: early annual reviews noted the bias of PIAs toward producing research for peer-reviewed journals and text books. The recommendation to focus more on policy briefs was acted on, as was the proposal to conduct training and to provide feedback to authors. The effect has been improved quality of outputs. Subsequent recommendations focused on the importance of improving dissemination, seeking audiences beyond the NHC.

Synthesizing lessons from research and analysis: It was recommended that it would be useful to create a repository and synthesis of research and analysis carried out under GHSP. The PMO have done an excellent job in tabulating in detail all the work that has been carried out. It remains a challenge, however, to get a concise overview of where the body of research leads in terms of understanding China’s experience in global health.

Pilot projects: It was evident soon after the inception phase that implementing the pilot projects was going to be challenging. It was also clear that their prime purpose was going to be more concerned with exposure of Chinese officials to working in new environments than in terms of health outcomes. This resulted in a change in the weighting score for this output, and, more fundamentally, a change in the way senior officials in the SOC understood the importance of the pilots.

Learning from the experience: It was recommended that the extension of the Tanzania pilot should allow time for an end-line survey to show potential changes in malaria incidence. This has happened. It was also recommended that the extension should be used to document experience of the pilot projects with a view to making a synthesis of information available to government. Individual partners have documented their experience, the PMO has produced a broad-brush analysis in the final project report, and the evaluation report contains an extensive body of detailed evidence. There remains a concern, however, that the lessons learned from GHSP still do not reach CICA or other bodies concerned with development policy.

China Global Health Network: Following the 2016 Symposium it was recommended that the CGHN should not just be concerned with running large meetings. This recommendation was taken up with enthusiasm by the Secretariat and led eventually to work on managing small research grants noted above. Recommendations (also noted above) about institutionalisation and financial sustainability remain outstanding.

MOFCOM: throughout the life of GHSP it has been evident that its main channel for engagement with government has been through the NHC/DIC. MOFCOM signed the original MOU and sits on the SOC, but the relationship is with MOFCOM/DITEA (Department of International Trade and Economic Affairs), which traditionally deals with incoming assistance to China and has little influence over aid policy and systems. It is noticeable that GHSP has made less progress in working with MOFCOM/DFA than, for instance, with some multilateral agencies (WHO, UNDP, UNHCR and WFP) and other partners (notably the Gates Foundation). Engaging with CIDCA is likely to be an important component of any future partnership between the UK and China.

UN agencies: The 2016/17 annual review noted a number of UN agencies that were working with MOFCOM, of relevance to GHSP (as noted above). This was reiterated in the subsequent annual review. While relations have been established with UN agencies, GHSP has not fully built upon the opportunities in order to achieve the level of collaboration and cooperation with these key multilateral agencies that will be critical to effectively tackling global health issues.