Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Rural and Agricultural Markets Development Programme for Northern Nigeria (Propcom Mai-karfi)
Programme Value: £27m		Review Date: March 2015
Programme Code: 202098	Start Date: March 2013	End Date: March 2018

Summary of Programme Performance
Year	2013	2014
Programme Score	A+	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review:
Propcom Maikarfi (PM) had a challenging year marked by significant internal transitions i.e. staffing and, more significantly, in the markets on which the programme is working. As a result of both market and staffing changes, 2015 feels like a new beginning for Propcom Mai-Karfi.

Inevitably this level of change has been disruptive and results have suffered. However, PM has a strong foundation on which to build from its predecessor and there are encouraging signs that the new markets will begin to bear significant fruit in 2015. Although it continues to achieve the milestones on a cumulative basis, most of these achievements came during the inception phase and mainly from agricultural inputs and particularly from the fertilizer market. Overall progress in the first year substantially slowed and has only started recovering in the second year.

Propcom Maikarfi identifies constraints and gaps in rural agricultural market systems and plays the role of a facilitator to bring systemic changes through its private sector business partners’ investment, once they see value in making those investments. The main achievements this year include the programme’s active engagement and scale up in seven markets, with twelve activities following the “making markets work for poor” (M4P) approach. PM has formed market driven partnerships with thirteen private sector businesses investing in agricultural value chains development in the seven focal markets. The programme was also successful in implementing the transition plan that was put in place due to the departure of the Team leader, the programme Director’s retirement, recruitment of twenty two new staff and the replacement of Technical Director.

Propcom Maikarfi is following a flexible approach of deepening its presence in agricultural markets with high potential for pro poor growth, adding new markets where such opportunities are identified and exiting from the markets where the opportunities for inclusive growth are diminished due to change in market conditions or because it offers low value for money. The programme has built strong relationships and reputation across a range of stakeholders in the private, public, farmers’ associations, financial institutions and agricultural research sectors. As the programme goes into its third full year of implementation, it is exceeding all its cumulative outputs and outcomes when compared to milestones at the end of its second year and has also exceeded in two of its four cumulative impact milestones at the end of second year. However the programme has not been able to fully achieve its target of reaching 50% women beneficiaries at the outcome and impact levels. The programme should explore the opportunities for gender inclusive growth by identifying markets with high rates of participation by women farmers and understanding better the gender constraints and opportunities in existing markets.

The programme is currently interacting with Nigeria Stability and Reconciliation Programme (NSRP), The Maximizing Agricultural Revenue and Key Enterprises in Targeted States (Markets ll by USAID) and Market development in Niger Delta (MADE) programmes. It should also explore the options for linking into and learning from the following programmes:

Educating Nigerian Girls in New Enterprises (ENGINE) – PM should explore various distribution models in partnership with ENGINE for commercial products that have social benefits for example Proctor and Gamble’s PUR brand water purifier.

Growth and Employment in States (GEMS 4) – PM’s proposed new intervention in fast-moving consumer goods would benefit from learning from the successes of the GEMS 4 ‘micro-distribution’ intervention in Kaduna State.

Summary of recommendations for the next year

Strengthen the theory of change to allow a deeper understanding of how the programme will produce long term sustainable impact. Revise and improve the log frame accordingly.

Continue to revisit intervention level theories of change to understand how change will be affected by each intervention and to strengthen measurement and value for money assessments of each intervention

DFID should consider how to challenge the programme going forward given the risk of results accrued during inception masking underperformance to ensure continued ambition and value for money are achieved.

Consider the balance of outcome and impact indicators to include a measure of intervention depth at outcome level and to refine the range of indicators into more meaningful measures.

Develop stronger measures to understand the true extent to which incomes are being affected, including developing a better understanding of programme beneficiaries and the benefits they accrue from the programme. This is needed to align results reporting and value for money assessments.

Invest time in developing a more in-depth understanding of the constraints and opportunities in both existing and new markets from a women’s economic empowerment perspective and include this analysis in the proposed review of the theory of change. The partnership with the gender consultants, WISE Development consultancy, is a step in the right direction.

Ensure a focus is maintained on strong programme leadership and management and continuity in staff deployment.

Seize opportunities and mitigate risks around the recent oil price shocks and increased militancy in the Northern states;

Ensure continued and strengthened collaboration with federal, state and local governments, especially after 2015 elections;

Encourage the crowding in of new private sector partners in the focal markets by designing new interventions and deepening existing ones;

Improve coordination and strengthen relationships with the programme’s independent evaluator in UK and also in Nigeria using periodic VC meetings.

Collaborate and cross-fertilise ideas with ENGINE, GEMS4 and other programmes.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202098/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202098/documents/

Programme and context:

One third of Nigerians live below the national poverty line. Approximately 60 million Nigerians live without sufficient income to provide 3000 calories per day, roughly equivalent to $1.40[1]. Another third of Nigerians live at a level of less than twice that national poverty line. More than half of Nigerians live in poverty as measured by the multi-dimensional poverty index. Poverty rates and trends are worse in the North. Income poverty rates in the North East and North West zones are nearly 50 percent, more than 10 percentage points higher than any other zone and double those in the South West. Poverty rates in the north are also declining more slowly[2]. Given that 77% of people in the North depend on agriculture for their income, poverty will not be reduced without a focus on agriculture and rural enterprise. Northern Nigeria is also vulnerable to severe climatic impacts and, increasingly, to conflict and insecurity.
[1] World Bank Nigeria Economic Report 2014 – financial conversion using purchasing power parity conversion factors.
[2] DFID Nigeria Policy Paper on Poverty, Inequality and Vulnerability (Resilience), March 2015

While Nigeria’s economic growth has averaged 8% in the period 1999-2010[3], agricultural growth has largely been driven by agricultural expansion. Agricultural productivity has remained consistently low, particularly in the North where it is characterised by low levels of investment, innovation and use of technology. International evidence suggests that increases in agricultural productivity are usually associated with poverty reduction[4].
[3] International Monetary Fund, 2011. Nigeria: 2010-Article IV Consultation. IMF Country Report No. 11/57
[4] Gutierrez, C., Orecchia, P. and Serneels, P. (2009) ‘Does Employment Generation Really Matter for Poverty Reduction’ in R. Kanbur and J. Svejnar (eds) Labour Markets and Economic Development. Abingdon: Routledge. Cited in ODI Background Note, May 2011 Jobs, Growth and Poverty: what do we know, what don’t we know, what should we do. C Meelamed, R Hartwig and U Grant.

Context for the 2014 Annual Review:
While the overall context for this review remains unchanged, important developments have occurred in 2014 that have direct implications for the programme. The first is impact of the sharp fall in oil prices, for an oil-dependent economy. The halving of world prices of Brent Crude in the second half of 2014, and the decision by OPEC not to reduce production to drive up prices, is already impacting heavily on Nigeria’s economy. Unofficial calculations suggest that at Nigeria’s current rate of production (c.1.8m barrels per day (bpd), per barrel prices need to exceed US$100 for the government to fully meet its spending plans. The second is Nigeria’s elections. Manoeuvring for the 2015 presidential, legislative and gubernatorial elections has dominated the political landscape in the past year, consuming political energies and shortening politicians’ time horizons, thereby reducing policy space for agricultural reforms, e.g. the Growth Enhancement Support Scheme (GESS) bill and seed law which are pending in the legislative process. In spite of delays in these important policy actions, Propcom Maikarfi has been working to strengthen private sector participation in Nigerian agricultural markets by creating new opportunities that also promote pro poor growth.

Whilst the oil price shock may well have negative repercussions due to possible cuts in Nigerian government’s spending in the agriculture sector, it also represents an opportunity for PropCom Maikarfi in terms of a gradual reduction of the agricultural inputs subsidy provided by the Federal Ministry of Agriculture and Rural Development (FMARD), allowing for the crowding in of private sector input suppliers in this market. The programme is already supporting rural retail and distribution systems from the supply side, and training farmers in the proper use and application of good quality inputs from the demand side.
B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment:

Outcome: Better performing poor farmers and small scale rural entrepreneurs in selected markets.
Indicator 1: Number of poor farmers and small scale rural entrepreneurs that record an increase in sales, productivity and/or quality, as a result of programme activities (number of whom are women in brackets). Cumulative.

- Milestone by end March 2015: 102,000 (50,000)
- Achievement by end 2014: 250,223 (37,212)
- Assessment: This indicator is ahead not only of the March 2015 cumulative milestone but also that for March 2016. However, the reported results were almost exclusively accrued during the inception phase of the programme and it is likely that a large portion of this success is attributable to the activities inherited from the predecessor programme. Results achieved during the first year of implementation are extremely low and reported results for 2014 are also well below those expected in year. It should however be noted that results for 2014 are incomplete as a result of the DFID reporting year not lining up with the date on which the annual report is based. It is likely that after full reporting they will be close to the end year target. It is also important to note that if inception stage results were discounted the programme would be below target. The target for women is still cumulatively underachieving.

Indicator 2: Number of poor farmers and small scale rural entrepreneurs that make changes in the way they run their business as a result of programme activities (number of whom are women in brackets).Cumulative

- Milestone by end March 2015: 117,300 (57,500)
- Achievement by end 2014: 250,005 (36,991)
- Assessment: As with indicator 1, this is ahead of 2015 and 2016 cumulative targets but showed significantly lower than expected results during 2014

At the end of December 2014, PropCom Maikarfi has exceeded both of its second year outcome milestones by a large margin; indeed it has already achieved those set for March 2015. However it was unable to achieve the milestone for reaching women farmers and entrepreneurs both in total number as well as in percentage terms. This reflects a narrow base and potentially fragile results achievement. There has been some progress on diversification but as it is highly dependent on this one market any adverse market conditions could result in quick reversal of success. The target for women is still cumulatively underachieving.

The 2013 annual review raised the same issues about the dependence on agriculture inputs, particularly fertilizer market and not reaching the target for women farmers and entrepreneurs. The programme has now taken positive steps to expand into new markets. Emerging results from agricultural mechanisation are encouraging, and other markets, including shea and electronic warehousing, show strong potential.

It is also worth noting that, unlike many DFID programmes, impact level data is available on a near annual basis and it is only from these indicators that the depth to which the programme is reaching beneficiaries can be judged. Two of the four impact level indicators involve percentage ranges which, without further details, are not helpful indicators. The indicator on aggregate income is currently below target, despite beneficiary numbers having been overachieved. The review team suggests that a depth indicator be considered at the outcome level, along similar lines to the impact measure, and that the range of indicators be revisited to provide a more meaningful measure.

Overall output score and description: The overall output score is A keeping in view the relatively low results achieved in the last year and not just cumulative performance. Cumulative results mask the real performance of the programme in this year.
Background to Markets:

Propcom Mai-karfi is expected to work in at least 8 different markets, or sectors, over its 4.5 year implementation period. An overview of the project’s current interventions is as follows:

Poultry Health:

Chickens are susceptible to many infectious diseases. One of the most important of these is the viral disease known as Newcastle disease (ND), which causes devastating losses in both commercial and village chickens. Reducing losses of large numbers of village chickens to virulent Newcastle disease is an essential first step to improving their productivity. Poultry nutrition and disease control are the primary factors affecting bird production at the small farm/household level. If the poultry is better fed and protected from disease, significant increase in profits can be achieved without added labour.

The I-2 Newcastle disease vaccine is more robust and known as a thermostable vaccine. Thermostable vaccines still require long-term storage in the refrigerator; however during transportation of the vaccine to the field, the vaccine will not deteriorate as quickly as the traditional vaccines. This makes it much more suitable for use in rural areas. During 2014, Propcom Mai-karfi used this approach to expand upon and create a platform for replication of the thermostable Newcastle vaccination method in addition to enhancing crowding in by other veterinary service companies.

Soap with Hand-washing:

The Soap and Hand Washing intervention has highlighted that inadequate sanitation and insufficient knowledge are not just public health issues but also very much an individual health concern. The intervention seeks to increase the knowledge of rural women in northern Nigeria on the importance of hand washing with soap to encourage health seeking behavioural change, leading to an increase in the demand for the sale of soap.

A partnership with PZ Cussons (PZC) was initiated with a pilot activity that concluded in 2013 which demonstrated what was possible and achievable. In early 2014, PZC launched a second phase of the pilot that tested what distribution strategy worked within the new test market area of twenty (20) Local Government Areas (LGA) in Kano State.

Agricultural Inputs:

Input suppliers are currently only serving a fraction of the demand generated by smallholder farmers seeking reliable access to high quality farming inputs. Nigeria’s agricultural inputs usage rates are among the lowest in the world. Currently the agricultural inputs market has been dominated by big buyers, commercial farmers and government. For the smallholder farmer, who usually requires smaller unit sizes of fertiliser and seed, traditionally there have not been appropriate products in the market. The programme has invested in companies that are breaking bulk (repackaging large units into smaller units) and are willing to sell inputs to smallholder farmers in packages that fit their needs and are affordable. These packages allow the farmer to buy what they can afford, and take into account the available money a farmer may have at a particular time.

Babban Gona Agricultural Franchise Service:

Babban Gona (BG), which means ‘great farm' in Hausa, has ambitious aims of raising the incomes of one million farmers in northern Nigeria by 2025. The real attraction of the BG partnership, is that it signals to the wider business and political community that agri-business with smallholders is possible in northern Nigeria. BG operates on a unique agricultural franchise model known as trust groups where farmers come together as a unit to help each other produce high quality grains with higher than average yields. An additional focus for BG is on youth unemployment in rural areas and promoting women to enter agricultural production.

Propcom Mai-karfi has continued a strong relationship with BG. In April of 2013, a development impact investment referred to as a “Raise out of Poverty (ROPO) Bond”, was made by PM in BG, worth ₦72million. In 2014, the programme continued to support BG through a combination of a new ₦40million ROPO bond investment and technical assistance. This additional investment has been used by BG to finance the 2014 target of a 10% increase in new members within the trust groups i.e. 200 new farmers, together with building and strengthening of members’ capacity. In 2014, BG put greater emphasis on reaching out to women farmers and involving them in the BG farming systems.

BG has been able to leverage the value of PM’s investment by nine times with funding from other sources, as a result of the confidence shown by PM regarding the ROPO bond and the subsequent results. BG has indicated its desire to increase the investment by PM through the bond mechanism in order to scale up efforts to attract more female farmers into the trust groups. BG farmers have reportedly realised income growth in 2014 of 30% above 2013 levels, and nearly 80% of these farmers have realised yield increases above 100%.

Agricultural Mechanisation:

Nigeria is in the early stages of agricultural mechanisation and small farmers remain hesitant to adapt to change for a number of reasons, such as insufficient training and knowledge. In nearly all instances farmers are too poor to purchase or hire mechanised equipment even with government subsidies. This low level of mechanisation limits the ability of farmers to meet deadlines, expand cultivated areas and achieve economies of scale. Women farmers continue to be at a disadvantage and face enormous challenges accessing and utilising mechanised services.

PM’s involvement in mechanisation continued in 2014 with expansion into another form of agricultural mechanisation, the power tiller. This multipurpose light weight hand tractor has strong for small scale agricultural producers, especially among women farmers.

Shea Market:

The objective of this intervention is to improve the quality of Shea kernels and to improve the supply chain efficiency in Niger State. Women groups, who typically pick Shea nuts from the wild and process into kernels, need to be trained in best practices that will yield high quality kernels. This intervention is piloting a model in which capacity building is provided throughout the value chain by the buyer as a way of reducing cost of procurement, while offering good financial returns to the suppliers, who are all women.

Technology Pilot for Growth Enhancement Support Scheme (GESS) and Federal Ministry of Agriculture (Known as GES ‘TAP’ pilot):

The Nigerian Federal Ministry of Agriculture and Rural Development (FMARD) operate the Growth Enhancement Support Scheme. The vision of GESS is to tackle rural poverty by helping farmers maximise their crop yield, and provide a source of income. A step in this process is to subsidise the purchase of farming inputs for farmers across rural Nigeria. However, the Federal Government had experienced acute challenges in implementing the scheme of distributing the inputs to deserving farmers, as it is prone to bureaucracy, rent seeking, and technology failure. This has resulted in farmers receiving inputs that were not appropriate to their circumstance, never receiving inputs or receiving inputs that were not needed or usable. FMARD decided to change the way subsidised inputs were accounted for and delivered to farmers. This led to an agreement between FMARD, IFDC and Consult Hyperion (CHyp) to develop an ICT based system, GES – Touch and Pay (GES-TAP) to tackle the challenges faced by GESS.

GES-TAP technology is a system designed to help with the identification and proper targeting of poor farmers. The aim is to utilise TAP technology, developed by CHyp, to overcome the constraints faced in the enumeration and redemption process experienced during the first two years of GESS.

Support to IFPRI (International Food Policy Research Institute):

The project has commissioned six rapid research studies on various issues of importance to agriculture in the north of Nigeria. Three draft reports on nutrition, youth unemployment in agriculture, and mechanisation have been submitted to FMARD for review and approval.

Electronic Warehouse Receipting System:

The majority of small farmers are dependent on prevailing market prices which tend to be lower at harvest time. In Nigeria, most farmers are smallholders who do not have suitable on farm storage to retain grain for extended periods, thus most of the grain is sold at the end of the growing season. This drives the price down, leaving most farmers with little return. Grain storage remains an ongoing problem for farmers. However, if suitable storage facilities are available this can give the farmer the option to retain his grain until prices increase.

PM together with African Exchange Holdings Ltd (AFEX) are co-investing in a pilot electronic warehouse receipting system (EWRS) to increase smallholder farmer’s participation. PM’s investment is to enable AFEX to promote EWRS among smallholder farmers and encourage farmers to use the systems as a strategy to manage price fluctuations. During the pilot, AFEX will initially aim to attract smallholder farmers to sell to the warehouse. Over time AFEX hopes to attract individual farmers and farmer groups to adopt the EWRS for storage management and as a source of finance.

Key lessons and actions:

A flexible programming approach and the ability to scale up or down interventions in different markets as required are key strengths of Propcom Maikarfi. This flexibility also helps the programme achieve better value for money by focusing on more cost efficient or high impact interventions. The programme avoids taking a directive approach and instead focuses on bringing private sector players together around specific market problems and supporting them to take the lead in how to address them. This approach is sustainable and addresses the long term systemic changes required in a market.

Greater investment in the programme’s capacity on gender has been late in coming, given the ambitious gender targets and a difficult context in which to work. However, some progress has clearly been made in this review period, such as piloting power tillers and developing a shea intervention.

The terms of reference for the gender consultants focuses on identifying new markets with potential for including and empowering women. The consultants need to assess efforts in existing markets to identify the challenges and opportunities and to come up with an action plan. While the team have explained that some partners are unwilling to invest more in adapting their strategies to include women, there are others who have a more positive attitude and would benefit from targeted expert advice/support and an informed ‘push’. The gender consultants should be invited to attend Programme Direction Team meetings. They should also conduct training for intervention leads and other key technical staff to embed gender within the PM team.

Recommendation: Revise the gender consultants’ Terms of Reference to reflect the above two aspects. This might mean allocating a few more person days for gender related activities.

Has the logframe been updated since the last review? No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Selected rural market systems work more effectively for poor farmers and small scale rural entrepreneurs
Output number per LF		1	Output Score	A++
Risk:		High	Impact weighting (%):	50%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	End March 2015 Milestones	Progress
1.1: Number of market player partners that invest in pro-poor innovations that the programme helps to pilot. (Cumulative)	8 private sector partners investing in pro poor market approaches	Achieved: / 13 private sector partners investing in pro poor market approaches in partnership with PMk
1.2: Number of poor farmers and small scale rural entrepreneurs who access new inputs, services, technology as a result of programme activities(number of whom are women in brackets) (Cumulative)	117,300 (57,500)	Achieved: / 422,319 poor farmers and small scale rural entrepreneurs including 77,554 women accessed new inputs, services and technology as a result of programme activities

Key points and highlights:

PropCom Maikarfi formed new partnerships with private sector investors during the year and diversified its portfolio of interventions. As a result there are 13 private sector partners currently investing in rural markets that are contributing to pro poor growth in Northern Nigerian focal states (Kano, Kaduna, Katsina, Zamfara and Jigawa). Last year there were 7 such investor partners. A wider base of private sector partners will create more competition in the focal markets (agricultural mechanisation; agricultural inputs; agribusiness franchise; poultry health; shea; electronic warehouse receipting, and soap and hand washing) and will result in wide spread gains in pro poor livelihoods and jobs creation. This increase in partnerships demonstrates an encouraging diversification and is promising for the future of the programme.

The programme needs to diversify its beneficiary base and generate results that are spread over all the markets instead of achieving results only from agricultural inputs and specially the fertilizer market. There is also a need to continue to strengthen results reporting so that results are available from all markets and interventions. Without this data it is not possible for the programme to judge whether market interventions have been successful.

The programme’s interventions resulted in improved access to new inputs, services and technology for 422,319 poor farmers and small rural entrepreneurs, including 77,554 women. This is a significant increase over previous year, when 315,030 total farmers and small entrepreneurs, including 66,419 women, benefitted.

This output is assessed as A++ on cumulative basis. (If the performance is to be assessed only for the current year than it should be assessed as A+).

Summary of responses to issues raised in previous annual reviews (where relevant):
The previous annual review recommended that Propcom Mai-karfi should continue to strengthen partnerships and crowd in other players in existing markets with the aim of achieving systemic change and reaching scale; and start activities in at least two new markets that can deliver wide outreach and significant results for women. It also recommended that Propcom Mai-karfi should continue to explore new environmental markets that can increase incomes and build longer term resilience, particularly those that will benefit the poorest and the most vulnerable in the far North. Lastly, it recommended updating the logframe with new output indicators covering the GESS – Token Administration Platform (GES-TAP) and International Food Policy Research Institute (IFRPRI) studies components as and when these are available.
During the past year, two new markets, shea and electronic warehouse receipting, were added to the programme portfolio, raising the total number of markets from 5 to 7. Despite investigating opportunities in the ‘environmental markets’ of water, cook stoves, fuel wood and bio gas in 2014 the programme has not identified any viable environmental markets to help build longer term resilience among vulnerable people in North and the log frame was also not updated with GES and IFPRI components as the outcome and impact assessment of GES-TAP is still going on. Three draft IFPRI study reports have been received but feedback from FMARD is still awaited.

Recommendations

- PropCom Maikarfi should explore and add at least two new markets in its intervention portfolio to seize emerging opportunities and to back ideas and activities which may not have been foreseen earlier. Special emphasis should be given to markets with high rates of women participation and having good potential of reaching the poorest income segments.
- The programme should make further assessments in markets that will help to build environmental resilience in vulnerable communities. The programme should keep investigating a wide variety of possibilities, particularly in the far north.
- After the GES-TAP outcome and impact assessment and IFPRI studies are finalized the log frame should be updated to include these two activities.
- The programme should consider how to capture benefits for medium and small enterprises in addition to those for farmers and entrepreneurs.
- The programme should place considerable emphasis on bringing a number of interventions to scale where they can begin to produce significant results.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Poor women and men engaged in selected rural markets are less vulnerable to shocks, trends and seasonality
Output number per LF		2	Output Score	A++
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	End March 2015 Milestones	Progress
2.1: Number of poor farmers and small scale rural entrepreneurs that as a result of programme activities, adopt a practice change, or are affected by a market system change that contributes to their improved resilience (number of whom are women in brackets). Cumulative	To improve the resilience (against shocks, trends and seasonality) of 46,920 poor farmers and small scale rural entrepreneurs (of which 23,000 will be women) through changes in practice or the impacts of market system changes attributed to Propcom Mai-karfi.	Achieved / Resilience to shocks, trends and seasonality of 250,960 poor farmers and small scale rural entrepreneurs improved including 37,151 women

Key points and highlights: To January 2015, 250,960 poor farmers and small scale rural entrepreneurs, of which 37,151 are women, have improved their resilience as a result of adopted practices, or impacts of market system changes. However the number of women has actually decreased from last year when it was 47,845. Though this remains above the milestone of 23,000 for the second year of the programme it remains a significant concern.

Non-seasonal income generating opportunities have been created for village based agents in many markets reached by Propcom Mai-karfi, including poultry health and soap with hand-washing. For example, whilst chickens need to be vaccinated approximately every three months to be fully protected against Newcastle Disease, deaths typically peak during the Harmattan season, when the vaccination season (October-February) also peaks. This does not coincide with the most intensive months of agricultural activity e.g. planting and harvesting, so it offers income generation opportunities both for distributors and vaccinators and to households who would otherwise have had fewer chickens to sell. In addition poultry often acts as a savings instrument (particularly for women) that can be liquidated in response to shocks.

The programme has taken a minimalist approach to the question of vulnerability to climate change and resilience. They have chosen to review and climate proof existing investments / intervention markets instead of exploring the potential for new environmental value chains. The one exception to this is shea. Mention has been made of cook-stoves, water and drought resistant / early maturing seeds. The potential needs to be explored in forest products, natural pesticides, and in capitalising on state-led initiatives such as the Jigawa State Environmental Policy.
There are indications that incidences of diarrhoea are reducing by about a half (from 24 per household per year to 12) where the programme has been able to sustain the practice of hand-washing and soap sales. Each incidence costs about N500 per child.

Poverty focus – the ‘P’ in M4P

West Africa Cotton (WACOT) is using and seeking-out smallholder farmers for seed multiplication (rice in Kebbi State, and sesame in Gombe State), a source of increased income for those involved. The aim is for 60% of 300,000 MT of sesame produced to be from smallholders by the end of 2016. In 2014, WACOT was able to initiate a certified seeds marketing campaign in Kebbi state that enabled the company to sell 60MT of certified rice seeds in just 2 months. WACOT managed to achieve revenues of N13 million from open market sales, something the company has never achieved before. Seed coordinators employed by WACOT earned N300,000 from commissions, and farmers reported over 90% germination rate and a 2 week reduction in germination time in the nurseries.

Springfield Agro and Syngenta are working successfully with smallholder farmers. PropCom Maikarfi’s work with these two partners revolves around developing a distribution network for seeds and crop protection products that effectively reaches the poorest farmers. This is done through rural based retailers and lead farmers. Other agriculture input companies are not involved in contracting smallholders hence Springfield Agro and Syngenta enjoy a much wider distribution reach.

The warehouse receipting concept is still in the early days of testing. Establishing a dense network of storage facilities, geographically close to the farmers, will be the key to enabling poor smallholders to participate and benefit – to overcome barriers of distance, transport cost, infrastructure deficits, and even trust. Similarly, a dense network of lending institutions will also be required. The programme will test the feasibility with Lapo Micro-finance bank, ultimately aiming to crowd-in of other micro finance institutions or even commercial banks.

This output is assessed as A++ on cumulative basis. (If the performance is to be assessed only for the current year than it should be assessed as B as the output moderately did not meet expectation)

Summary of responses to issues raised in previous annual reviews (where relevant): The 2013 annual review recommended providing more detail on the overall theory of change and testing the causal logic of interventions, particularly how it relates to outputs and outcomes in the logframe. A theory of change is in place for each intervention and is updated quarterly.

Recommendations
- Propcom Maikarfi should explore and analyse why the number of women improving resilience has slipped from last year and should take steps to reverse this trend.
- The independent evaluation of Propcom Maikarfi should look to validate the theory of change and the causal logic with the reported results.
- Continue the good practice of encouraging all partners to pursue pro-poor practices, creating employment and income for smallholder farmers.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Private investors, government, non-government organisations and development agencies make changes in their approach to northern Nigeria as a result of programme influence
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	End March 2015 Milestones	Progress
3.1: Number of businesses that buy more from, or invest more in selling to, poor women and men in northern Nigeria, due to a change in practice that they ascribe to the programme (cumulative)	2 businesses buying more from or investing more in selling to poor women and men in Northern Nigeria due to a change in practice attributable to the programme	Achieved / 5 businesses buying more from or investing more in selling to poor women and men in Northern Nigeria due to a change in practice attributable to the programme
3.2: Number of actions (regulatory changes, policy reforms, practice changes or releases of funds for investment) by state and federal government, influenced by the programme (cumulative)	0, no milestone is set for this indicator before year 3	Achieved / 3 actions (regulatory changes, policy reforms, practice changes or releases of funds for investment) taken by state and federal government, influenced by the programme
3.3: Number of interventions that development agencies and non-government organisations (NGOs) acknowledge have been influenced by the programme (cumulative)	0, no milestone is set for this indicator before year 3	Achieved / 1 intervention that development agencies and non-government organisations (NGOs) acknowledged has been influenced by the programme

Key points and highlights: In the agriculture inputs market Propcom Maikarfi has invested in companies that are reducing larger units into smaller units, especially the fertilizer distributors and resellers who reach small farmers with packages that are affordable to them and suit their needs. The programme continued to work with a veterinary services company to sell poultry vaccines directly to smallholder farmers using local distributors and vaccinators and also received the buy in by the Veterinary Council of Nigeria (VCN) and other governing agencies within the industry. The programme worked with a lightweight power tiller company to make agricultural mechanization more accessible to women farmers who otherwise are excluded from mechanized agriculture as large tractors are not well suited to their needs. Mechanized tillers are lightweight, can be easily operated by women in their small plots and do not require a driving licence.

This output is assessed as A+ on cumulative basis. (If the performance is to be assessed only for the current year then it should be assessed as A as the output meets expectation but does not exceed the expectation if last year’s results are not added to it)
Summary of responses to issues raised in previous annual reviews: Last year’s review recommended developing strategies for crowding in new investors in the intervention markets and also collaborating with other organisations to reduce market distortions. Policy influencing (including through DFID), particularly developing plans to be ready to pro-actively engage with the new government administration after the 2015 elections and setting milestones for output indicators 3.2 and 3.3.
The government’s GESS programme remains distortionary by crowding out private sector investment. The 2015 elections are yet to be held. No milestones were set for output indicators 3.2 and 3.3 as these were not anticipated until 2016/2017.

Recommendations
- The declining oil revenue and the pressure on the Nigerian government’s budget provides a unique window of opportunity for policy influencing, to gradually phase out the agricultural input subsidies and crowd in the private sector’s investment in this market. PropCom Maikarfi and DFID should engage jointly with the new administration after the 2015 election for this policy influencing work.
- Milestones should be set for output indicators 3.2 and 3.3.
- PropCom Maikarfi should step up its state level influencing by convincing policy makers to stop distorting the markets through hand outs to farmers. It should also increase interaction with other development agencies and NGOs implementing similar programmes. Both these activities should be linked to building the evidence that the M4P approach is working and is linked to improving the programme’s own generation of high quality monitoring and evaluation data, plus getting the independent evaluation off the ground.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance:

The key cost drivers are personnel fees and grants. This reflects the programme’s model of providing technical assistance to market players. 47% of spend reported was on personnel fees, which has decreased compared to 50% reported in 2013/14. 37% of the budget was spent on grants, 90% of which was for the GES-TAP pilot. The GES-TAP pilot intervention was taken on in early 2014 in response to requests from the Federal Ministry of Agriculture. Following a recommendation from the last review, the GES-TAP costs have been excluded from VFM calculations because the results of this pilot are still being assessed.

VfM performance compared to the original VfM proposition in the business case:

The business case proposed that overall VFM for the programme will be calculated at aggregate level using two measures:
- The net additional income change (NAIC) compared to the programme costs, estimated at 1.90 by 2019
- Total private sector investment leveraged estimated at £3.59m, £0.14 investment per pound invested by DFID

The programme has identified additional VFM indicators which they have been monitoring and reporting on. The 2014 Information, Training And Development Ltd (ITAD) report on ‘Monitoring VFM in DFID’s Economic Growth Portfolio’ put forward specific recommendations to improve Propcom’s VFM indicators. This included adding equity measures as well as making the indicators less ambiguous. The table below compares cumulative VFM values over time with the planned spend and Logframe targets. This creates indicative VfM milestones for March 2015 against which to compare the cumulative indicators.

VFM Dimension	VFM Indicator	2012	2013	2014	Milestone March2015*
Economy	Total operational costs/total costs	0.42	0.41	0.38	-
Efficiency	Private sector investment leveraged per £ spent.	£0.24	£0.14	£0.60	-
	Cost per farmer/small scale rural entrepreneur reached through inputs, services or technology	£9	£16	£20	£103
	Cost per female farmer/small scale rural entrepreneur reached through inputs, services or technology	£42	£78	£110	£210
Effectiveness	Cost per farmer/small scale rural entrepreneur recording an increase in sales, productivity and/or quality.	£12	£23	£34	£119
	Cost per female farmer/small scale rural entrepreneur recording an increase in sales, productivity and/or quality	£82	£149	£233	£242
Cost-effectiveness	Cost per farmer/small scale rural entrepreneur benefitted	£12	£23	£34	£119
	Cost per female farmer/small scale rural entrepreneur benefitted	£82	£149	£233	£242
	Beneficiary income gain per £ spent	£0.30	£0.20	£0.27	£0.25

On economy, the programme only reports the percentage of total operation costs; this has reduced to 38% from 41% [5] in 2013. Whilst there may have been some improvement, this is still relatively high compared to other programmes in the economic growth portfolio. For example the GEMS programme overheads costs ranged from 18-30%.[6] The ITAD report suggested additional economy indicators which the programme should explore.
[5] 36% was reported in the 2013 review which included costs for GES, these VFM calculations exclude GES costs
[6] GEMS 2014 Annual Review

The programme has currently exceeded its target on leveraging private sector investment, and there has particularly been an improvement in this year. The programme has leveraged £1.48 of private investment for every pound spent. The largest returns have been from the Babban Gona investment (£5.43) and the agri-inputs intervention (£1.09). Babban Gona represents particularly strong value for money due to the use of a returnable bond funding mechanism. The other efficiency measures appear to be doing well cumulatively when compared to the estimated BC targets; however there has been a negative trend in the VFM values. The cost per beneficiary reached, and cost per female beneficiary reached, have both increased by over 100% since 2012. This relates to results issues highlighted elsewhere regarding slow results during the past year of the programme.

Similarly effectiveness measures compare well cumulatively to the estimated business case targets but show a declining trend. In this case the cost per farmer beneficiary increased by almost 200%. The beneficiary income gain on the other hand shows an improvement from last year. Further investigation showed that income gain per £ spent in 2014 alone was £0.41. Reaching the ultimate effectiveness measure will require a significant increase in the level of income gained, with total cumulative value approximately doubling each year. This will require a combination of sustained income increases and outreach throughout the programme.

Recommendations

Continue to develop value for money indicators and approaches, in particular to develop gender measures which reflect the true cost of achieving results for women.

Ensure that value for money measures are used appropriately and effectively when assessing investments in different market sectors, including analysis behind simple ratio measures to understand how and why interventions are proving more or less cost effective and whether lessons can be learnt.

Assessment of whether the programme continues to represent value for money:

Currently Propcom MaiKarfi represents value for money. Cumulatively, indicators are around the level they would be expected to be at this stage in the programme. However the direction of travel is not positive in many cases and the programme will need to start making significant progress, particularly at the effectiveness level, in order to continue to drive value for money.

The programme should invest time and resources in understanding the full value of investing in women – see comments on qualitative learning techniques under the M&E section. Similarly, the programme could maximise value to the poorest in Nigeria by investigating more in environmental value chains and supporting greater resilience to desertification and climate change in the far north, where most of the poor live.

Quality of financial management:

The programme has good financial management systems and effectively monitors spend against the budget. A budget of £4.5m was agreed for the 2014/15 financial year, the programme had spent 69% as at December 2014 and it is forecasting to spend 99.6% of the agreed budget the end of the financial year.

Current approved budget 2014/15 FY	Spend as at Dec	%spend as at Dec	Forecast spend by March 2015	% variance from Budget
4,500,000	3,125,828	69%	4,477,618	0.4%

Whereas the overall aggregate budget spend is good, there have been considerable variances in monthly forecasting. Programme forecasting has mostly fallen outside of the 5% target, with variance as high as 64% in July. This issue was picked up in the last review. Whilst some variation is expected in programmes of this nature, consistently large variances show the need for improvement in the programme’s forecasting systems, particularly with more predictable items such as staff time and accommodation expenses.

Performance on monthly invoicing has seen a significant improvement over time in terms of invoice accuracy and response times. Narrative financial reports are sent as part of quarterly and annual reports. Financial performance is also reviewed quarterly as part of DFID’s Key Supplier Management review and feedback is given to service providers.

The last audit was carried out in August 2014 for the period covering December 2011 to July 2014. The audit report was unqualified. In the auditors’ opinion all materials, receipts and payments for the period under review were in accordance with the international standards and the agreed terms of contract. The next audit is scheduled to take place in June 2016.

Date of last narrative financial report	20th January 2015
Date of last audited annual statement	26th September 2014

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk:

Internal risk

Delivery of results (High) – If the programme continues to rely on agricultural inputs, and particularly the fertilizer market, for the achievement of its results then there is a high level of risk as the fertilizer market is open to distortion by the government’s GESS agricultural inputs subsidy programme. Whenever GESS scales up, it crowds out the private sector players. This happened last year when Notore ending up selling all of its output to GESS and discontinuing the production and sale of its small bags of fertilizers through private distributors.

To reduce the results delivery risk, the programme should diversify and deepen its presence in a range of markets. It should also aim for a larger increase in farmers’ income as the programme is currently improving the incomes on a small scale but for a large number of farmers.

Reputational risk (Low). The service provider’s accounting, monitoring and evaluation and overall management systems are good, and were strengthened after the recruitment of new staff and consolidation of its management team in 2014.

External risk

Political (Medium) – The current Minister of Agriculture, who has been driving market based agricultural transformation, may well not be in post after the elections. The programme should engage early on with the new administration to seek continuity for market based and pro private sector policies. The G8 New Alliance for Food Security and Nutrition and the Agricultural Donors Working Group should be used to mobilize support from other donors for the continuation of current policies and to reform the agriculture input subsidy policy.

Conflict and security (High) - The states of Borno, Yobe and Adamawa are no longer areas in which the programme can safely operate. Nigeria has suffered increasing militant activity that has spread from these three emergency states, to encompass most of the north and areas of the middle belt of Nigeria. The states of Bauchi and Gombe have suffered attacks from marauding elements of Boko Haram. Niger, Kaduna, Katsina and Zamfara have faced terror attacks in the form of suicide bombers, indiscriminate gunfire on crowds and car bombs. In the middle belt region, including the states of Plateau, Nassarawa and Benue, tribal and ethnic conflict continues. In the latter half of 2014, tensions increased the ferocity of the attacks as political contenders stirred sectarian sentiment.

PM has implemented a robust security structure to ensure the safety and security of personnel and programmes. The security structure includes an in-country security team consisting of a Security Manager based in Abuja, a Deputy Security Manager based in Kano, an Operations Manager and Security Focal Points embedded in each programme. Context specific Standard Operating Procedures are in place with all personnel trained on their roles and responsibilities. The Propcom Mai-karfi programme is also supported by an Operations Room based in Abuja that opened in late 2014. This provides an on call service which responds to emergencies and incidents on a round the clock basis.

Avian Flu (Low) – Nigeria experienced an outbreak of avian bird flu in early 2015. This affected 14 states including Jigawa, Kaduna and Gombe, where Propcom Maikarfi is working in the poultry health sector. An initial risk assessment has been completed and the risk to the programme is considered low to moderate, as Propcom Maikarfi and its poultry health intervention partner have proactively engaged in disseminating information on measures to prevent and curb the spread of the virus. More so, the Federal Government’s efforts to provide a referral system, decontaminate, and compensate farmers of infected birds provide an incentive for early detection and reporting as well as containing the spread. The programme is following these mitigation measures to minimize the risk on an ongoing basis by:

  - Working with partners to ensure surveillance in wetlands for migratory birds;
  - Sharing a checklist of precautionary measures and making the distinction between avian flu symptoms and Newcastle Disease (NCD) with new partners;
  - Continuing to work with existing partners to disseminate the right information on NCD and Avian flu to farmers and vaccinators;
  - Continuing to monitor field events and report appropriately.

Outstanding actions from risk assessment

The Business Case described in detail the significant risk of climate change and environmental degradation on Northern Nigeria, and those risks remain. Finding a partner to work on these issues has, however, proven to be difficult.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is on track to deliver against the planned timeframe. The implementation phase is for a 4.5 year period which will end on 31st December 2017

Performance of partnership(s)

GRM International has been managing the programme well. The programme is well aligned with DFID priorities. DFID constantly engages with the PM, including through the Advisory Committee, and provides strategic guidance on programme implementation. The programme was very flexible and responsive to issues regarding budget cuts at the beginning of the financial year. PM works effectively through a number of private sector partners on various market development projects.

Asset monitoring and control

The programme keeps an inventory of assets owned by DFID for items valued over £1000 or which have a useful life of more than one year. The assets register is updated as new assets are procured. It is reviewed monthly along with invoices to confirm that new purchases are recorded.  Following the end of the GES -TAP pilot, the programme drew up an asset disposal plan which proposes to transfer GESS assets to Sokoto state Ministry of Agriculture (one of the pilot States) and the International Fertilizer Development Corporation (IFDC). This arrangement is yet to be finalised with DFID.

Asset verification was carried out as part of the independent audit. It confirmed that the majority of assets were correctly represented on the register. A few unregistered items were identified and Propcom management has taken actions to review and update the register accordingly.
G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Partnership Principles were not assessed during business case design. The principles are however considered valid in reviewing Propcom Maikarfi’s approach and objectives. This project aims to support small farmers in Northern Nigeria by strengthening pro poor market systems at different stages of the selected value chains, and by working with private sector partners to increase their investment in rural commodity and services markets. The programme is implemented through a commercially contracted service provider and no funds are passed through government systems. This is in direct response to the high fiduciary risks associated with funding through the Nigerian government.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation:

The programme has made considerable progress in its approach to evidence gathering over the year. However, there are still significant gaps in the evidence required both for programme management and for the assessment of progress. Partly this is due to monitoring systems still being under development. Partly it is a result of an incomplete understanding of the way in which the programme is impacting on beneficiaries.

Propcom MaiKarfi needs to carefully consider the approach taken to measuring incomes and income increases. Whilst the methodology for considering income increases only in sectoral incomes is broadly sensible, there is a risk that the programme is applying sectoral boundaries too narrowly, resulting in inflated impact level income results. This has the potential to produce a disconnect between impact results and effectiveness measures of value for money – with impact results exceeding targets despite comparatively low value for money measures. Further research is required to better understand intervention beneficiaries – such as their income profile and the importance of PM’s intervention in relation to household income.

The design of the programme’s independent evaluation has been finalised. Cooperation between the programme and the independent evaluator has improved in terms of evidence sharing. Both sides are currently working together to finalise the evaluation methodology, timing and selection of markets to be evaluated.

Capturing the wider impacts for women, such as control over income, decision making power, decreased violence, asset accumulation, or less child labour, would bring a qualitative lens to the benefits of targeting women, and would also be helpful in understanding and communicating the challenges of reaching the target for women beneficiaries.

Monitoring progress throughout the review period

During 2014, Propcom MaiKarfi has made significant improvements to the programme’s monitoring systems. These provide much better data on interventions and programme results, which is critical to deciding the future of market interventions. The new programme monitoring system should provide a solid basis for results reporting. However, Propcom MaiKarfi needs to prioritise completing data across the interventions and to ensure that procedures for regular updating of the data are in place.

There is scope for Propcom MaiKarfi to research further into the way that interventions impact on beneficiaries and the extent to which they benefit. This research would provide evidence to underpin intervention level theories of change and data to understand the mechanisms by which interventions are or are not working. This research should complement efforts to fill gaps in intervention level results reporting.

Current results for 2014 are significantly below expectations, particularly at outcome level. It is understandable that in-depth studies will not be possible every year but it is hoped that once a full set of intervention studies and results are available it will be possible to monitor progress realistically and more regularly.

There is an issue with programme targets not being aligned with the reporting period, which makes an annual review of results against targets problematic. The logframe should be revised to reflect reporting periods.

Recommendations:

- Review the approach to impact level incomes calculation and consider these in relation to value for money metrics – this should include research into the background characteristics of beneficiaries, beneficiary households and, where relevant agricultural and subsistence practices.
- Make use of qualitative and participatory research techniques to listen to and learn from programme beneficiaries and other people in the programme’s target group.
- Methodologies for calculating beneficiary income gains should be assessed to ensure they are consistent with multiyear impact as well as one off gains from changes in practice.
- Align logframe targets to programme reporting years.
- Maintain a programme of research activities which prioritises the conduct of research and studies which will allow reporting at outcome level across the range of interventions.

Below are some examples of programmes’ stakeholders’ comments collated as part of the Propcom Maikarfi team’s annual review self-assessment:

“If you look at the initial cost of a tractor and the members benefitting from this programme, you cannot find two people who can afford to buy this tractor. This loan helps us to acquire new tractors and provide services to farmers who previously find it scarce to access tractors. It benefits the tractor owner and benefits the farmer.”
- Alhaji Danladi – Tractors operators and hiring facilities association in Nigeria (TOHFAN) Chairman

“Propcom Mai-karfi’s tractor intervention has been working for the market; strengthening hands of the rural farming community; strategizing partners and building relations for the society in need.”
- Manoj Ramakrishnan - Springfield Agro Limited.

“About 30% of my income which used to be lost as a result of insincerity of my operators is now being saved from the use of trackers on my tractors introduced by Propcom Mai-karfi for the purpose of monitoring the field operations of my tractors from the convenience of my office or home.”
- Alhaji Danladi Garba - National Chairman, TOHFAN

“From the improvement on my farm I am now also doing other businesses. I will keep building on my success and train all my children in both Arabic and Western education to give them a better standing in life.”
- Umar Farouk – Kaduna farmer / Notore fertiliser beneficiary

“With PM having faith in us by providing both technical and strategic advice, we were able to leverage their support to grow Babban Gona into the great farmer organisation it is today”
- Kola Masha, CEO, Babban Gona

“VCN adopts and supports the model based on the way Agriprojects has implemented it”
- Dr Avong – Veterinary Council of Nigeria Registrar

“This campaign is a platform to familiarize PZ Cussons brand in the North. The motivators identified and the hand washing messaging can be used for many years, while the product itself might change. As far as using hand washing with soap as the vehicle”
- Christos Giouras – PZ Sales Director

I will use the money that I am saving from getting inputs from GES TAP to buy more food from my family, and with continued support from the programme I hope to expand my farm business and better care for my family.
- Isah Ma’azu – GES TAP beneficiary in Sokoto state

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process