Project Completion Review – post April 2018

Title: Improving the Quality of General Education in Ethiopia (GEQIP II)
Final Programme Value £ (full life): £130 million	Review Date:	June 2019
Programme Code: 203396	Start Date: October 2013	Final End Date: March 31st, 2019 (extended by one year)

Summary of Programme Performance

Year	2014/15	2015/16	2016/17	2017/18	2018/19
Programme Score	A	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/

A. Summary and Overview

Description of programme and what it has achieved
GEQIP II is a package of reforms focused on improving the quality of education and raising learning outcomes in Ethiopia’s ‘general’ education sector (primary and secondary schools). These reforms, started under the first GEQIP project (2009-2013), are part of the Ethiopia’s fifth Education Sector Development Plan (ESDP V, 2015-2020), expenditure on which constitutes 24% of GDP.

GEQIP II is administered through a World Bank Multi-Donor Trust Fund (MTDF) and has been funded by eight donors (the World Bank, DFID, Finland, Norway, Italy, UNICEF, USAID and the Global Partnership for Education). The programme was designed to support a comprehensive set of inputs that would improve teaching and learning conditions in schools and thereby raise learning outcomes. The World Bank extended GEQIP II by 12 months (with a new end date of June 30th 2019[1]) with no additional financing primarily to accommodate delays in textbook and IT equipment procurement and distribution. It closed on DFID’s system in March 2019 and it has been agreed to use DFID funds to finance some of the costs associated with the delayed textbooks. The follow-on programme to GEQIP II – GEQIP-E – has already started implementation in July 2018.
[1] The Ministry is currently seeking a further six-month extension until December 31st 2019 to complete the remaining textbook distribution

Overall the programme is judged to have met expectations and to have scored an A. The majority of GEQIP’s outputs have either been met or exceeded and this is despite a very difficult operating context, including an increase in ethnic violence, two changes in Education Minister, and the election of a new Prime Minister. Although there have been some delays, 117 million textbooks have so far been distributed (at a cost of around 40 p per book); over 240,000 teachers and 8,000 school leaders have been trained; 40,000 schools were provided with annual school grants to enhance teaching and learning; Delivery Units were established in the Ministry and the regions.

The assessment of outcomes shows that GEQIP II has had a positive impact on schools and there has been increased community engagement and ownership. However, there has only been limited change in teacher effectiveness. More work needs to be done to ensure that training is continuous and targeted on practical applications, and that efforts are made to reduce teacher turnover.

At the impact level, there has been some progress on learning achievement in secondary schools. Data for primary schools will be available later this year. There has been better progress on students’ completion.
Box 1: Lessons learned[2]:
[2] The majority of these came from stakeholder interviews

Design education programmes to be flexible and resilient to conflict and natural disasters in order to keep children in school and learning.

Capacity constraints at all levels of the system have sometimes been a brake on the delivery of what was an ambitious programme with very stretching targets.

Data collection and dissemination was not always as accurate and timely as it should have been which limited the capacity of GEQIP II partners to respond and adapt when circumstances changed or results were not being achieved.

GEQIP II was a complex programme with several inter-linked components. More should have been done to ensure synergy between the inputs in schools and classrooms to maximise the impact on teacher performance.

There was over-reliance on the 4 year cycle of National Learning Assessments to monitor learning achievement which has meant that data on progress with respect to learning and changes at classroom level has not been routinely available.

Special needs education needs targeted support to make a difference.

In order to improve learning outcomes funding and accountability need to be decentralised to school level.

Recommendations for future programmes

For GEQIP II, DFID should support the World Bank to ensure that the remaining textbooks which have been held up by a legal dispute are distributed to schools by the end of 2019.

The impact of training and textbook provision on classroom practice and learning outcomes should be routinely monitored to focus on effective utilisation and gender-disaggregated findings reported back to the Ministry and stakeholders – the QESSP supported snapshot survey is a promising approach.

Ensure that financing is disbursed directly to schools and is focused on those areas and students most in need, including those displaced by conflict, those with disabilities, and girls at risk of drop out.

Support the government to improve data collection and dissemination, including considering how tablet or mobile phone-based technology can be used to collect real time data to inform policy and programme decisions.

Ensure the lessons from QESSP are fed into the new TA programme and keep the model of programme delivery under review, particularly the relative effectiveness and responsiveness of the funding delivered directly by DFID through its new more focused Technical Assistance programme as against that delivered through the World Bank-managed pooled fund.

DFID-E to quickly conduct a formal evaluation of the implementation of ICT and feed the lessons into the design of future ICT in education interventions.

Undertake analysis on factors behind the deteriorating gender parity in primary and secondary levels and plan informed interventions to improve the situation.

Ensure that GEQIP-E is properly and independently evaluated and includes a link to learning achievement.

Progress towards the Gender Equality Act

Gender parity in education has improved over the past decade. However, it has dropped slightly in recent years. The primary GPI ( Gender Parity Index) is 0.91 and has decreased compared to the ESDP V baseline which stood at 0.93. The lowest regional GPI is Ethiopia-Somali at 0.8. Gender parity in secondary school is 0.89 (down from 0.93 in 2015/16) and has not met the 2017/18 target of 0.96 at the national level. The emerging regions consistently have the worst secondary school GPIs with Gambella having the biggest difference in GPI between the two secondary cycles, dropping from 0.84 in the first cycle to 0.31 for second cycle. Girls with special needs are even more disadvantaged. The average gross enrolment rate (GER) in primary schools for girls with special needs is only 8.7% and drops as low as 0.2% in Afar region. In secondary schools the average GER for girls with special needs drops to 2.4% showing that very few girls with special needs are progressing from primary school. The situation is not much better for boys. In terms of learning achievement, boys consistently outperformed girls in all subjects in the 2017 grade 10 and 12 National Learning Assessment. The picture was similar in the 2018 Early Grade Reading Assessment results for grades 2 and 3 although interestingly girls outperformed boys at both grades on the Amharic language assessment.

In-depth analysis on the emerging factors contributing to the recent deterioration on gender parity in education is required. However, it is believed it may be the effect of the manmade and natural disasters prevailed in the country over the past years, in which girls and women are more vulnerable. Morever, only first cycle primary (grade 1-4) schools are extensive and accessible across the nation and girls dropping out is more acute in the higher grades. This can be partly explained by larger distances to second cycle primary (grade 5-8) and secondary (grade 9-12) schools and safety concerns are constraining access, and also gender norms mostly affecting girls reaching puberty, which is the same age as second cycle primary and above.

GEQIP E intervenes on enrolment and progression of girls at second cycle primary and secondary levels.

Feedback from the field visits conducted as part of the PCR shows that GEQIP II has had positive effects on girls and those with special needs. See box 1 below.

Box 2: Examples of how GEQIP II has promoted the learning of girls and those with special needs

In 2017, the Regional Education Bureau (REB) in Afar targeted support to the woredas with the
highest levels of need and then further targeted the type of support to meet the needs most prevalent
in the woredas.  In Ewa woreda, the REB invited a specialist audiologist from Hossana School in SNNPR.   The audiologist accurately assessed and prescribed the equipment needed for students with hearing difficulties.  For example, Fatimah*, a 15-year-old girl in Grade 4, who suffered from profound deafness since birth, was prescribed an appropriate hearing aid - hearing her father’s voice for the first time.  Her father ensured the battery was renewed when needed, supporting Fatimah to communicate more easily and continue her schooling. *Name changed for anonymity

In SNNPR Wolayita Zone, support from DFIDs Girls Education Challenge (GEC) is strengthening
the impact of GEQIP by providing holistic support to girls and the community.  One GEC initiative, led by Link Community Development, provides safe spaces to enable girls to better manage their menstrual cycles safely while at school.  In addition to a quiet space with facilities and resources, materials have also been translated in the local language to support with awareness and the school has a designated female teacher to support the girls. The school shares its best practice with schools in the vicinity as well as provides lessons learned to the wider zone and region. GECs support to girls’ safe access to school enhances their opportunity to benefit from the support provided to their school through GEQIP.

## B: DETAILED OUTPUT SCORING

Output Title	Improved curriculum, textbooks, supplementary materials and inspection
Output number per LF		1	Output Score	B
Impact weighting (%)?		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (2018)	Progress
Ratio of number of students to number of subject books distributed to students	1:1	Moderately did not meet expectations / While it has been achieved in some subjects, overall this is not achieved.
Number of textbooks and teacher’s guides (based on new curriculum) distributed to schools (cumulative)	138,011,817	Moderately did not meet expectations / 117 million have been distributed and 52 million are planned for distribution by the coming academic year (see below).
% of schools inspected and re-inspected each year	100% - level 1 schools and 50% level 2 schools re-inspected	Met expectations / 80% of Level 1 and 88% Level 2 schools reinspected

Provide supporting narrative for the score
Textbooks and teachers’ guides have been distributed nationwide. The printing and distribution of textbooks and teachers’ guides at scale and reduced cost has been a noted success of GEQIP II. Texbook:student ratios have improved significantly but are still falling short of 1:1 in some subjects and there is regional variation[3]. Although this indicator has not been met, the government should be commended for its efforts to print and distribute textbooks.
[3] PRIN Consultancy Services (June 2018) Status of student -textbook ratios by Regions, Grades and Subjects; and textbook utilisation in Ethiopia

Textbook procurement delays. GEQIP II was extended for 12 months by the World Bank at the request of the Ministry because of delays in textbook and IT equipment procurement. There was a legal dispute over the procurement of English textbooks brought by a losing supplier which has delayed the distribution of 52 million Grade 1 – 8 English textbooks. The court has found in favour of the Ministry and the books are now being distributed and should be in schools for the next academic year.

The school inspection system has been established. GEQIP II supported the inspection of 34,126 schools between 2013/14 and 2015/16 and over 80% of these have been re-inspected. The Ministry is considering making the inspection service independent to better hold the system to account.

Lessons identified this year linked to this output and recommendations for future programmes
The status of textbook utilisation report contains much useful learning which partners should take the time to review and digest. The finding that only 30% of students carry their books to school for use in class should be followed up on. Schools visited don’t always have a consistent system to manage the care, storage and distribution of learning materials. It is not clear what the mechanisms are for capturing feedback from teachers and schools on the current materials and the curriculum. These are issues that GEQIP-E will be working on.

Measures taken to improve inspection levels were mostly input oriented (input standards) and focus needs to be given to improve process and outcome aspects of inspection so this quality assurance measure can contribute to improved learning.

The recommendation is to support the World Bank and GEQIP partners to ensure that the remaining 52 million textbooks are distributed to schools by the coming academic year and are effectively utilised.

Output Title	Strengthened teacher training programme
Output number per LF		2	Output Score	A+
Impact weighting (%)?		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (2018)	Progress
Number of teachers who graduated from diploma & degree pre-service programmes, upgraded from certificate to diploma and from diploma to degree (cumulative) and teachers who graduated	Upgraded from certificate to diploma – 92,012 (cumulative) / Upgraded from Diploma to degree: 29,222 (cumulative) / Number of teachers who graduated from diploma and degree pre-service programmes: 26,000	Substantially exceeded expectations / 106,063 teachers (43,466 female) / 32,463 teachers (not disaggregated) / 83,309 from diploma programmes / 24,896 from degree programme / (not disaggregated)
No. of teachers licensed (cumulative)	5,500 primary teachers / 2,000 secondary teachers / 1,000 school leaders licensed	Moderately did not meet expectation / 7,370 teachers and leaders licensed

Provide supporting narrative for the score
Teacher training: A total of 83,309 primary teacher trainees and 24,896 secondary teacher trainees graduated from diploma and post-graduate diploma pre-service teaching programmes during the project period. 106,063 in-service primary teachers completed their upgrading programmes from certificate to diploma, and 32,463 secondary teachers from diploma to degree. In addition, 70,226 in-service English language teachers, and 27,811 mathematics and science teachers attended short-term training programmes as part of their continuous professional development. In all cases, achievements have exceeded the targets.

Licensing: the number of teachers who have been licensed is slightly below the target set while the number who have sat the examination far exceeds the targets set by the Ministry (333,341 have sat so far). The pass rate in the written examination is only 23% (76,837) and of the total who sat only 2% are licensed.

While the milestone on “Teacher Training” is rated as Substantially Exceeding Expectation (A++), the mile stone in “Licensing” is rated as Moderately Did Not Meet Expectation (B). Three relatively dense indicators are compressed in the former hence weights higher and influence the overall output scoring to A+.

Lessons identified this year linked to this output and recommendations for future programmes
The volume of teachers trained is impressive but less clear is how this training is impacting on classroom practice. The GEQIP Exit evaluation[4] found that teaching is still lecture-dominated, and that students and teachers spend close to 20% of the instructional time on writing and taking notes from a blackboard. GEQIP II’s own measure of teacher effectiveness – inspection reports – also showed little progress in teacher effectiveness between school inspection and re-inspection.
[4] BDS (Feburary 2019) GEQIP II Exit Evaluation

The licensing programme considers both examination and portfolio. Schools have not been able to timely and accurately support teachers to prepare their portfolio. There is also a mismatch between the licensing examination and the teacher training programme that is being addressed through a review of the teacher training curriculum. The Ministry needs to act quickly to solve these challenges as they are undermining the vfm of the licensing system. The TA in GEQIP-E could potentially be used to help to reform the licensing system.

It is recommended that going forward the impact of training and textbooks on classroom practice should be routinely monitored and findings reported back to the Ministry and stakeholders.

Output Title	Improved school improvement programme, including provision of school grant
Output number per LF		3	Output Score	A
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (2018)	Progress
% of schools receiving school grants in October every year	85%	Moderately did not meet expectations / 32.1 % (57% from Ministry’s own data)
% schools receiving training on the alignment of inspection results to School Improvement Planning (SIP)	Training of Trainers (ToT) Trainings cascaded to remaining 50% of schools	Moderately Exceeded Expectation / The ToT was achieved at the last Annual Review. Training was provided for all regions and cascaded to all schools by the REBs except Somali. The SIP guidelines have now been revised to align them with the inspection framework

Provide supporting narrative for the score
Timely disbursement of grants: An evaluation of the school improvement planning process and school grant flow and utilisation was conducted in 2018[5]. This found that while over 99% of schools had received the grant, only 32% received by October 31st which is the target set. The Ministry’s own figures from the September 2018 GEQIP report indicate that this figure was 57%. The main reason for the delay in schools receiving school grants is reported to be the flow of funds from the Ministry of Finance onward to woredas and down to schools. Field visits report that all schools had received the grants by November.
[5] BDS (June 2018) Evaluation of School Improvement Planning and flow and utilisation of school grants

Alignment of inspection and school planning: The 2017/2018 Annual Review reported that a ToT training on evidence-based planning and decision has been provided for all regions, but Somali. The alignment of the school improvement guidelines with the inspection standards has been delayed but the SIP guidelines have now been revised, including aligning them more closely with the inspection standards (there was a workshop in December 2017), and the revised guidelines are now approved and will be rolled out later this year. The exit evaluation found that inspection results are one of the sources of data used in preparing school improvement plans. This was confirmed in the field visits to schools.

Lessons identified this year linked to this output and recommendations for future programmes
The problem of delayed school grants has been addressed in GEQIP-E as the grants are now disbursed by the Ministry of Finance in July before the academic year starts rather than in September as was the case under GEQIP II. Results-based financing allows for this earlier disbursement.

The whole school improvement process including the grants has created strong ownership and local initiative in improving schools. Very strong ownership has been built at local level and the school grants have been described as the ‘backbone’ of the system. Government has inserted a budget line for school grants this year and there are signs that they are beginning to move away from a reliance on donor funding.

The school grants included incentives to enrol and retain students with special needs. The school grant survey found that there were no clear guidelines for disbursement and risks that these funds are not used for their intended purposes. The Ministry has now developed guidelines for GEQIP-E, enhanced the monitoring system, and increased the amount of the grant.

The main recommendation is to ensure that financing is disbursed directly to schools and is focused on those areas and students most in need, including those displaced by conflict, those with disabilities, and girls at risk of drop out.

Output Title	Strengthened Education Management and Administration
Output number per LF		4	Output Score	A
Impact weighting (%)?		13%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
No. of school leaders received school leadership and principalship training (cumulative)	3,293 (20% female)	Moderatly exceeded expectations / 8,421 school leaders have enrolled and 1600 have graduated so far. Gender disaggregated data is not available
Timely dissemination of Education Statistics Annual Abstract by early October following the school year	October	Moderately did not meet expectation December

Provide supporting narrative for the score

School leadership, especially for females, has been accorded a high priority under GEQIP II. An accelerated female leadership course has been established to provide short term leadership training for aspiring female heads. To date 1,080 female leaders have been trained and 75% of these have been assigned as school leaders. For some regions, such as Gambela and Afar, this was the first time that females had been assigned to school leadership roles.

The 2017/18 Education Statistics Abstract was published in December 2018 which is an improvement on the previous year when the 2016/17 Abstract had still not been published by the time of the Annual Review in March. The main reasons for the delays are related to the design of the questionnaire, the data collection process, and errors in data entry (forms are handwritten). A report has been produced by UNICEF (see below) which contains useful analysis and recommendations for EMIS going forward.

Lessons identified this year linked to this output and recommendations for future programmes

The 2017/18 Annual Review reports that there are concerns that much of this training has been academic rather than practical and has not always led to enhanced school management or community relationship skills. There is also a need for more focus on instructional leadership and follow up of professional development in school. GEQIP-E includes a strong focus on school leadership.

The special leadership programme for females demonstrates that it is possible to identify females who can take up leadership roles even in the emerging regions. In Afar 83 female teachers are trained and all have been appointed. In the REB, attitudes were reported to have changed on female leadership – one male informant said ‘women make the best leaders.’

The Education Management Information System generates important system-wide data, but the quality and timeliness of the data limits its usefulness for policy makers. A 2019 UNICEF EMIS report focused on Somali Region[6] contains some very practical suggestions for improving the system of data collection which are relevant to other regions as well and which the Ministry and partners should act on. GEQIP-E TA has EMIS as one of its focus areas.
[6] UNICEF 2019 EMIS Ethiopia Key Bottlenecks and Recommendations

The main recommendation is to support the government to improve data collection and dissemination, including considering how tablet or mobile phone-based technology can be used to collect real time data to inform policy and programme decisions.

Output Title	Maximising the impact of GEQIP II through strategic support from the Quality Education Strategic Support Programme (QESSP)
Output number per LF		5	Output Score	A+
Impact weighting (%)?		12%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of capacity building proposals supported by QESSP (cumulative)	18 capacity building projects	Moderately Exceeded expectations / 22
Number of research studies conducted/ innovative and relevant interventions identified, designed and implemented (cumulative)	12 research studies	Moderately Exceeded expectations / 15 studies completed
Introduce delivery programme within the Ethiopian Education system and support regions to design delivery plans to improve learning	11 functioning Delivery Units	Moderately Exceeded expectations / Three ministerial and 22 regional delivery units have been established and are functional. Also 36 University Delivery Units established

Provide supporting narrative for the score
QESSP has provided capacity building support across teacher education, school leadership, equitable and inclusive education, and systems strengthening. A total of 20,000 staff have been directly trained by QESSP and 7,800 days of technical assistance have been provided. The SNNPR REB Head was very positive about the QESSP intervention on school leadership which went to scale. GEQIP-E is picking up on these achievements.

QESSP has directly supported 15 major studies. The study of current teacher training practices in Ethiopia was widely used by the Ministry to make decisions such as establishing Centres of Excellence for Teacher Education and School Leadership and the Colleges of Teacher Education Accreditation.

QESSP supported the Ministry to introduce a delivery approach in general education, Technical Vocational Education, and Higher Education. While it is too early to witness concrete results, achievements are: i) agreed priority areas of focus; ii) establishment of 25 Delivery Units; iii) routines introduced to track and review progress; and iv) development of quality implementation plans. A system has been developed for assessing student learning outcomes on a snapshot basis.

Lessons identified this year linked to this output and recommendations for future programmes
The British Council, who implemented QESSP, have produced a lesson learned document in 2019. This covers lessons from design, implementation and sustainability. These lessons will be useful as DFID brings on board the Technical Assistance Facility that is being procured alongside GEQIP-E. DFID-E have built on learning from QESSP in their new TA programme which is more focused, and less demand driven as this is judged to have the potential to be more transformative with more measurable impact.

The biggest challenge for the delivery approach in the future will be to align it to GEQIP-E. There was no designated delivery team member in SNNPR and while the Afar REB is positive about delivery, it is not embedded in their programming yet. The term ‘deliverology’ can be problematic.

The main recommendation is to keep the model of GEQIP-E programme delivery under review, particularly the relative effectiveness and responsiveness of the funding delivered directly by DFID through its new Technical Assistance programme as against that delivered through the World Bank managed pooled fund.

Output Title	Improved use of ICT to enhance the quality of education
Output number per LF		6	Output Score	A
Impact weighting (%)?		5%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Conducting a survey of ICT in education knowledge and capacity for the participating (pilot) secondary schools and universities	Baseline survey carried out to provide essential information on knowledge, capacity and practices in ICT of participating schools and Universities	Met expectations / A survey was conducted in 2017

Provide supporting narrative for the score

A survey of technology for education capacity was completed in 2017, across 300 secondary schools and 10 universities as reported in the 2018 Annual Review. Since then, the Ministry’s ICT Centre reports that a site survey has been conducted on sample sites of selected 300 secondary schools from all regions to review availability of necessary infrastructure for the project. The finding of the survey has been disseminated through consultative meetings with school principals to act on findings that may be bottlenecks for the project implementation. Training was also organized for school technicians and IT teachers drawn from 300 schools on the utilization, operation and maintenance of the infrastructure.

This output has been affected by delays, but the procurement and installation of e-cloud infrastructure in 300 schools and universities has now been completed and the pilot schools are using the new ICT infrastructure to enhance teaching and learning. The cost of the ICT for the 300 schools was around £22million.

Although many of the schools are facing challenges with implementation, in a secondary school visited in Afar (which is very remote) the equipment has been installed and they have loaded plasma lessons and supplementary lessons, and these are being used to support teaching and learning.

Lessons identified this year linked to this output and any recommendations for future programmes

The QESSP project contributed greatly with a study of the effective utilisation of ICT in class in secondary schools. This provides lessons and information for the use of information communication technology in the classroom.

The recommendation from this output is for DFID-E to quickly conduct a formal evaluation of the implementation of the e-cloud system and feed the lessons into the design of future ICT in education interventions.

Output Title	Improved co-ordination, monitoring and evaluation
Output number per LF		7	Output Score	A
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
% implementing agencies (IAs) providing timely inputs to GEQIP annual planning exercise and GEQIP six-monthly reports with good quality	90% with good quality	Met expectations / Ministry reports that this has been achieved with all IAs submitting reports on time for the 2017/18 Annual Progress Report
Evidence base on impact of reforms aimed at improving the quality of education	Comprehensive exit evaluation and school grant evaluation carried out	Met Expectations / An exit evaluation and a school grant evaluation have both been undertaken

Provide supporting narrative for the score

The Ministry GEQIP reports are comprehensive and well structured. They include comprehensive information from the regions on progress. The 2017/18 Annual Report provides a good overview of GEQIP II performance over the life of the programme. The bi-annual World Bank GEQIP II missions have continued to be a useful mechanism for pulling together findings on progress.

The evidence base on impact has improved considerably since the last Annual Review. Three studies have been commissioned: a GEQIP Exit Evaluation[7], a School Grant Utilisation study[8], and textbook utilisation study[9].
[7] BDS (Feburary 2019) GEQIP II Exit Evaluation
[8] BDS (June 2018) Evaluation of School Improvement Planning and flow and utilisation of school grants
[9] PRIN Consultancy Services (June 2018) Status of student -textbook ratios by Regions, Grades and Subjects; and textbook utilisation in Ethiopia

Lessons identified this year linked to this output and recommendations for future programmes

There have been no regular quarterly GEQIP Coordination meetings over the past year or more which has limited the space for dialogue between GEQIP II partners and senior Ministry leadership on key issues. GEQIP-E should ensure that regular Steering Committee meetings are held.

Notwithstanding this, there were examples of events that had brought partners together such as the ESDP mid-term review meeting which was held in Mekele in March of this year. This was cited as an excellent opportunity for government and partners to discuss sector progress and challenges in the sector. Other meetings that have been helpful to bring partners together include GPE approval process, joint donor/MoE field trips, special meetings on issues such as procurement, and the monthly Education Technical Working Group.

DFID presence in the sector was mentioned as important by several stakeholders who we spoke to, including senior staff in the Ministry of Education. DFID colleagues are particularly valued for their technical expertise and their relationships with government.

Although a GEQIP II Exit evaluation has been commissioned, it lacks any baseline data, and it reports that it was unable to obtain data on learning achievement. This is a major drawback for a study which aims to assess the impact of GEQIP II over the life of the programme.

The main recommendation is for DFID to ensure that GEQIP-E is properly and independently evaluated and includes a link to learning achievement
## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and target impact(s) were achieved
GEQIP’s Theory of Change assumes that an evidence-based package of inputs can be delivered to schools that will in turn have an impact on the effectiveness of schools (improved learning conditions and institutional capacity for enhanced learning outcomes) which will then positively impact on learning outcomes (as measured by the National Learning Assessment). GEQIP II has been relatively successful at delivering a package of inputs to schools but to what extent has this impacted on school effectiveness? The outcomes of the programme are assessed below. The assessment indicates that although schools and communities have been energised by GEQIP support, the desired changes in teacher effectiveness are happening slowly. There are several possible reasons, including training that is too removed from the classroom, teacher turnover and poor teacher selection practices.

Table 2: Progress at outcome level
Indicators	Target	Achievement
Teaching effectiveness measured as index of average scores of school inspection standards on teachers' knowledge, lesson planning, teaching practices and assessment practices	50% for level 1 schools / 63% for level 2 schools	Moderately did not meet expectation / 46% / 59%
Percentage of schools using at least half of their school grants allocation for the SIP teaching and learning domain.	95%	Met expectation / The 2016 school grant survey reported this was met and field visits confirm this. The 2018 report 74% but the data is disputed
% of PTAs positively involved in the management of school grants	95%	Met expectation / All schools reported involving PTAs in planning
Procurement and delivery of E-cloud infrastructure (1 if it is delivered, 0 if not)	1	Met expectation / Delivered to schools

The impact of GEQIP II was expected to be an increase in the percentage of students achieving or above basic competency in English and Maths and increased completion rates. As can be seen from the table below the anticipated changes in learning achievement have not been realised except in grade 12 English. Completion rates at grade 5 for girls and boys are above the target, but the target for completion of girls at the end of grade 8 has not been met.

Table 3: Progress at impact level
Indicator	Target 2018	Achieved
Impact 1: Improved Learning Outcomes in Ethiopia	Gr 4 Reading - 50%; Maths - 50%; Gr 8 English - 50%; Maths - 50% / Gr 10 Maths -50%; English - 50%; Gr 12 Maths - 50%; English - 50%	Not met / Grade 4 and 8 NLA due later this year / Gr 10 Maths – 48%; English – 31% / Gr 12 Maths – 47%; English – 73%
Impact 2: Completion rates in grade 5 and 8	Gr 5 - F: 81%; M: 81%; T: 81% Gr 8 F: 60%; M: 60%; T: 60%	Partially met / Gr 5: F – 84%; M – 92%; T – 88% / Gr 8: F - 56%; M- 60%; T – 58%

Summarise the programme’s theory of change and major changes to it in the past year
There was no revision of Theory of change during programme implementation. However, the new education programme, GEQIP E follows a new Theory of Change.

Explain major changes to the logframe in the past year
No major changes have been made to the logframe for the extension and the targets remain the same as for those in 2018.
## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme
Key Cost Drivers
Key cost drivers of GEQIP II
The School grant took the highest share (around 60%) of the cost throughout the implementation period of the programme. This is followed by the cost of teaching and learning materials. The share in the cost of in–service training has shown a decline although it has been above the estimated cost in both years. GEQIP II had a one year no cost extension granted in June 2018.

GEQIP II has generally performed well on measures of economy over the life of the programme
- A significant amount of money (£20 million) has been saved from bulk procurement of text books and savings were used to provide additional supplementary readers. The average cost of a text book has been between £0.43 and £0.7 which is less than the £1 proposed in the Business Case.
- The cost of in-service training was reported to be only £120 in 2014/15 and although this increased to £221 in 2015/16 and to £205 in 2016/17, it is still well below the estimated cost in the Business Case (£475).
- Cost of installing ICT labs in 300 schools and 10 universities was £22 million.

The programme has also been generally efficient despite some delays
- Teacher training was carried out in an efficient way. The number of teachers trained has surpassed the target. For example, the number of teachers that graduated from diploma and degree pre-service programmes has surpassed the target of 26,000 and reached 108,205[10].
  [10] However, only 2% of teachers who sat for licensing exam could be qualified
- Number of text books and teachers guides procured and distributed has exceeded expectations. There would have been more efficiency gain if the procurement and thus the distribution of these remaining books had not been delayed.
- The timely distribution of school grants has not been met. Reasons included delays of up to two and three months were reported in previous years. Delayed approval of the GEQIP annual plan, delayed submission of the SIP, and lengthy time for the funds to reach Woreda Finance Offices were main contributory factors.
- The procurement of ICT equipment was delayed affecting the contribution of this output to the overall effectiveness of the programme.
- The cumulative utilization of funds out of the transfer to federal, regions and universities by the 3rd quarter of the period ended in April 2018 was 92% and it has reached 99.6% by the 2nd quarter of the period ended January 2019.

The programme has been less effective at contributing to education results
Teachers’ effectiveness as measured by an index of average scores of standards (teachers’ knowledge, lesson planning, teaching practices and assessment practices) only rose very slightly to 45.4% for level 1 schools and 59.3% for level 2 schools according to the 2013/14-2015/16 inspection data.
- The percentage of schools using at least 50% of their school grant allocation for the SIP teaching and learning domain was 95% in 2016 while it dropped to 75% in 2017/18 failing to meet the 95% target for the year.
- The textbook survey found that textbook utilisation is low with an average of only 30% of students bringing the subject textbooks to school on any given day.
- The ICT labs have now been delivered to schools but there are challenges with implementation.

The overall cost effectiveness of GEQIP II is also mixed
- The programme has contributed to improvements in completion rates in grades 5 and 8 for both girls and boys.
- However, it has had less impact on learning achievement scores with targets for English and Maths in grades 10 and 12 not being met, and progress from the baseline mixed.
- Cost per primary pupil has risen from £13.00 per pupil in 2013/14 to an estimated £30.00 per pupil in 2016/17. This still compares quite well to other African countries (Tanzania had a spend of £42.00 per primary student in 2012/13) but is still below the World Bank’s estimate of the spend needed to achieve education quality.

Equity:
- GEQIP II does not directly target girls but as far as possible data is disaggregated and tracked by gender. There have been improvements in girls’ completion rates over the baseline, but their learning achievement continues to lag behind that of boys. A female leadership programme has been successful in training females to take on school leadership roles.
- Participation of those with special needs in education is very low. GEQIP II has allocated 4% of school grants to special needs and some positive success was identified in the 2017 Annual Review. However, this review found that the amount was too small to make a significant difference in many schools. Braille book provision has been part of the learning materials aimed at addressing students with special needs.

Quality Education Strategic Support Programme (QESSP)
Economy: Total programme spend was £9.2 million. Savings made in earlier stages of the programme through several costs saving and cost contribution/ value added initiatives enabled a four-month extension of QESSP to March 2019 to complete some activities that were critical to the Ministry.

Efficiency Over the life of the programme, QESSP leveraged £1.5 million of partnership funds which made an important contribution to the achievement of its objectives. Programme savings through efficient management of professional fees amounted to £117,264. According to the Milestone payment statements, 100% of the milestones were achieved with the revised annual budget. For the 1st quarter of the first year, 78% of the milestones,were achieved, and for the 4th quarter of the 3rd and 4th year 88% of the milestones were achieved.

Effectiveness: This is difficult to measure in a Technical l Assistance programme. The British Council produced a report on key achievements[11] which indicates that QESSP has had impact on several policy areas over the past four years. Discussions with the Head of Planning in the Ministry suggested high levels of satisfaction with QESSP support. The Minister personally requested an extension to support some key activities.
[11] British Council (March 2019) Lessons from a Technical Assistance Programme

Equity: QESSP has supported two studies directly relevant to equity – one on pastoralist education and the other on girls’ education. It has also supported capacity building in special needs education. QESSP also supported the EMIS team to strengthen the gender analysis in the annual abstract.

Assessment of whether the programme has offered good vfm
The programme has been delivered economically – with unit costs kept very reasonable – and has also been relatively efficient although this has been undermined somewhat by procurement delays - some of which are still ongoing. The effectiveness proposition has been undermined by the lack of progress on learning outcomes although it is encouraging to see that completion rates, especially for girls at grade 5, are moving in the right direction. Overall we judge that the programme performed satisfactorily from a vfm perspective.

E: RISK

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

The overall risk for the programme remains moderate and in general risks were managed well throughout the programme. Two risk categories are worth noting in this project completion review.

Risk relating to conflict, social and political unrest and associated outcomes such as a large displacement of communities has continued to persist in the past one year. To mitigate the risk of the programme’s reduced effectiveness and disruption to education services, DFID has been liaising with GoE and the WB to undertake proactive and joint monitoring of changes in the political and security context. In addition, donors are conducting regular monitoring, annual reviews and audits on environmental and social impact of the programme. Sharing best practice on integrating emergency responses within sector programmes is also an established measure within DFID. The risk rating following mitigation actions remains moderate.

A major change to the overall risk environment is the risk related to procurement. The issues within this category of risk are two-fold. The first one is in relation to MoE’s procurement capacity and capability. The existence of high staff turnover within the MoE procurement department has put procurement capacity and capability within the Ministry at risk. The high turnover is due to inadequate salary payment cap set by the MoF. The second risk is related to the procurement of textbooks which has been delayed since procurement contracts were awarded in August 2018 due to a court case filed by the unsuccessful bidder. This has caused the suspension of disbursement to winning firms and a delay in the completion of contracts for printing and distribution of textbooks. The court case was only resolved in April 2019 with the court ruling in favour of MoE. As a result, there is a delay in the original programme completion date. The MoE has now asked for an extension until December 31st, 2019 which most donors, including DFID, agreed to. This time extension is to enable finalisation of printing and distribution of textbooks.

The lessons which GEQIP E identified to take forward is to implement further mitigating actions by the World Bank and GoE (including Ministry of Finance and Ministry of Education) to work together to strengthen MoE’s capacity with regards to procurement staff as well as procurement systems and include early planning and implementation.

Update on partnership principles
DFID Ethiopia uses the partnership principles to hold the government to account in relation to financial aid disbursements, and to provide a narrative for annual dialogue with government. The 2018 Partnership Principles Assessment noted the political change underway in Ethiopia and the increased recognition of the importance of civil and political rights. It highlighted the Government’s continued commitment to reducing poverty. It is therefore judged that it remains appropriate to use targeted financial aid to improve the life chances of poor people in Ethiopia. This is also the most effective way to provide value for money for the UK taxpayer.

The programmatic assessment of the partnership principles also carried out in October 2018 judged that the General Education Quality Improvement Programme for Equity (GEQIP E), which is the successor for GEQIP II, demonstrated strong commitment to poverty reduction and the SDGs, strengthening management of public finances, fighting corruption and strengthening domestic accountability. It also judged strong commitment to service delivery and economic and social rights but had concerns that limited commitment on aspects of civil and political rights may impact delivery in some geographical areas. Safeguards have been designed into the Programme Administrative Document (PAD) of the World Bank Managed Multi-Donor Trust Fund. The Memorandum of Understanding signed with the World Bank and Ministry of Finance articulates measures to mitigate the social and environmental risks of the financial aid and exclude funding of activities that could bring about sensitive, diverse and irreversible or unprecedented adverse impacts on the environment, and/or vulnerable people.
The programme undertook continuous monitoring through independent reviews, and the overall delivery of the GEQIP II programme focused on delivery of results aligning with the national priorities, improved aid coordination and harmonization in line with the Paris Declaration.

The analysis made concludes that at the education programme level, there remains evidence of a credible commitment of GoE across all the Partnershp Principles and that results-based, non-budget support financial aid to the Education sector remains appropriate to deliver results on Improving Equity and Learning Outcomes for the poorest in Ethiopia.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
DFID’s financial management of disbursements to the GEQIP II programme is based on its MoU agreement with the Government of Ethiopia (GoE) and the administrative agreement with the World Bank, for the WB managed Multi-Donor Trust Fund (MDTF). Payments to the contracted suppliers were based on signed contracts, with disbursements following timely submission of quality-approved milestone deliverables. The major Technical Assistance (TA) Service Provider was the British Council which provided capacity building support for the education sector in general during the programme implementation. There were other service providers that were recruited to provide audit and research related services. Table 1 below shows the programme’s performance on overall spending against budgets and for each active programme components for the period 2014- March 2019.

The WB has been managing the Multi-Donor Trust Fund and quarterly Interim Financial Reports (IFR) were prepared by the Ministry of Finance and Economic Cooperation (MoFEC) and distributed to the respective development/contributing partners through WB. Moreover, both financial and commercial aspects of the programme implementation were jointly reviewed whenever the Joint Implementation Review missions were undertaken bi-annually during the programme lifetime. These review missions were very important in pin-pointing the gaps observed in budget management in general and the low budget implementation status in some cases. Practical action points were drawn after each review missions which the World Bank accounted for to ensure they were followed up and acted on.

One of the major delays that is important to note was in the procurement of textbooks. There was a delay on the timely utilization of the budget after procurement contracts were awarded in August 2018 due to a court case filed by the unsuccessful bidder. This caused the suspension of disbursement to winning firms and a delay in the completion of contracts for printing and distribution of textbooks. The court case was only resolved in April 2019 with the court ruling in favour of MoE. This caused a delay in the original programme completion date and became the major reason for extending the programme to March 31st 2019. DFID, as part of the contributing partners to MDTF, has agreed to the time extension with the caveat that DFID can only be accountable for the accomplishment of the procurement contracts that were signed before the end of March 2019.

DFID, through the QESSP has provided support for strengthening the MoE’s procurement capacity and capability. However, the Ministry still needs to institutionalise the capacity that was built due to high staff turnover within certain departments.

Table 1: Spend by component
Component Code	Component Description	Total Programme Budget (£) / (A)	Total Spend against Budget to Date (£) / (B)	% Spend Against Total Budget (£) / (B/A)	Remaining budget/Budget not utilized as of March 2019 / (£) / (A-B=D)	Remark on the / Total Programme Performance
		2014 - 2019	March 2019	March / 2019	March 2019
203396 - 101	Procurement of services	130,172	130,140	100%	32	-
203396-102	Financial Aid- General Education Quality Improvement Programme (GEQIP) phase II	30,000,000	30,000,000	100%	-
203396 - 103	Strategic technical support to the Education Sector in Ethiopia (QESSP)	9,920,062	9,182,722	93%	737,340	The supplier couldn’t utilise the total contract amount -which was 9, 950,000 even with the time extension.12
203396 - 104	Programme Monitoring, Evaluation and Auditing	99,765	94,765	95%	5,000	This budget mainly came from the 103 component
203396 - 106	Financial Aid- Support to the GoE GEQIP II Programme	89,850,000	89,000,000	99%	850,000	This was allocated for the GEQIP- II Final Programme evaluation. DFID didn’t disburse as the WB was not ready to do the evaluation at the time of the last disbursement -December 2016
Total		130,000,000	128,407,627	99 %	1,592,373

 ____________________
12 The time extension for QESSP was granted to the supplier inorder to finalize few important activities specially the roadmap as it has political significance.

	Financial Aid	Technical Assistance
Date of last narrative financial report	18 June 2019	15 April 2019
Date of last audited annual statement	30 April 2019	10 December 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring
The main monitoring instruments for GEQIP II were the World Bank bi-annual missions (January / February and November/December each year) which organised, along with Ministry of Education, joint field visits with partners supporting the multi-donor trust fund to different regions, woredas, and schools. These were followed by wrap-up meetings in Addis with Federal Ministry of Education (FMoE), with specific directorates to discuss issues such as school grants, teacher licensing and EMIS, and a final meeting between GEQIP II funding partners and Ministry of Education to sum up the overall findings. The achievements, challenges ,recommendations and action plans were then captured in an Aide Memoire for each year of GEQIP II.

Apart from the missions, the Ministry of Education did not hold joint reviews regularly during the life of the programme nor were regular GEQIP II co-ordination meetings held. However, there were two major events initiated by FMoE in the transition from GEQIP II to GEQIP–E. This included a major conference on teachers and school principals in Mekelle in late 2018 at which it was announced that a Teacher’s Service Commission/Teacher Development Agency would be set up to standardise recruitment and management of teachers. The second major event was an Education Annual Review also in Mekelle, Tigray Region which in addition to presenting the latest version of the Education Roadmap, 2018-2025, also presented results of GEQIP II in terms of national assessment, enrolment, completion, teacher recruitment and licensing (all gender-disaggregated) and the distribution of school grants.

DFID Ethiopia Human Development team members participated in all bi-annual monitoring missions and reviews. In addition, they undertook up to 3 field visits per year to schools, woredas, and regions including in-depth field visits supported by external DFID colleagues to carry out the DFID annual reviews.

Evidence
Although the Ministry of Education supported by World Bank were not able to carry out an in-depth comprehensive evaluation, the GEQIP II exit evaluation contains very useful information on achievements although it lacks any baseline and there is no assessment of the contribution of the programme to learning achievement which is the biggest gap. The design of the new GEQIP-E programme was based on analysis of the strengths and weaknesses of GEQIP II, but a full formal evaluation would have provided even greater evidence for the new programme’s targets and objectives. However the new DFID technical assistance programme for GEQIP-E will ensure that such a comprehensive independent evaluation is included.

Nevertheless, the DFID-funded technical assistance programme QESSP covered many of the evidence gaps with some high-quality studies and analyses. Not only did their analysis of school leadership pilots in Amhara Region and SNNPR provide strong evidence for DFID’s new technical intervention areas in GEQIP-E, but studies on teachers’ supply and gap analysis, review of current teaching training practices and impact assessment of the effectiveness of upgraded primary school teachers have contributed to reforms in both selection/recruitment as well as training of teachers in Ethiopia. Their analysis and development of the pastoralist development strategy has also led to changes in the way education of these groups is being addressed. On improving learning achievement, QESSP has contributed two major analyses : A study on the factors that affect students’ academic achievement in English, mathematics, biology, chemistry & physics in the secondary schools in Addis Ababa and Harari REBs; and a collaboration with the National Education Assessment and Evaluation Agency on national learning assessment data of English, Maths and Mother Tongue in Grade 3 in 4,000 primary schools using tablets and real-time data. The latter was enthusiastically received by the Ministry and has resulted in a further analysis of the same schools being commissioned for end of school year 2019. Finally, QESSP has supported the analysis, development of and consultation on the Draft Ethiopia Education Roadmap which is now seen as a major policy document for future education development and reform with the backing of the Ethiopia Prime Minister.

Learning

The major lesson learnt from GEQIP Phases I and II is that any further investments by DFID and other partners in the education sector need to move away from inputs and enrolment to ensure effective utilization of the inputs and systems and radically address learning outcomes as well as increase transition to secondary schools, (especially of girls). It is also important to ensure investments in the education system equally benefit marginalised learners to lead to inclusive development. This is the only way to deliver the education outcomes needed for an industrialised lower middle-income economy.

Therefore, GEQIP-E’s adoption of a results-based approach, focusing on learning outcomes, efficiency (reduced dropout and repetition) and equity, and targeting emerging regions and vulnerable groups is a significant change from GEQIP I and II. DFID’s combination of Financial Aid and Technical Assistance will help to deliver improved learning outcomes for 1.035 million children, half of whom are girls.

Progress on recommendations from annual reviews for this programme

The recommendations of the 2017/18 review related to actions ahead of this PCR, actions for the PCR itself, and actions for the programme going forward. The table below summarises the status of these recommendations.

Table 2: Progress on recommendations from 2017/18 Annual Review
Actions	Progress
Actions ahead of the PCR	All key studies completed (textbook utilisation study, 2017 National Learning Assessment, 2017 school grant utilisation study, and GEQIP II evaluation. / Human Development pillar of country diagnostic was completed. / GEQIP partner review missions were aligned.
Actions for the PCR	Procurement status of textbooks and IT equipment noted. / GEQIP Exit Evaluation used to assess achievement of GEQIP II. / Achievements of QESSP noted. / Recommendation on QESSP lesson learning included.
Actions for GEQIP-E	Evaluation and learning have been embedded in GEQIP-E. / Closer alignment between GEQIP-E and ESDP underway.