PESP II Annual Review – 2018-19

Title: Punjab Education Sector Programme II (PESP II)
Programme Value £ (full life): £ 420.5 Million		Review Date: 2nd January 2019
Programme Code: / 202697	Start Date: 22/02/2013	End Date: 31/03/2020

Summary of Programme Performance
Year	2013-14	2014-15	2015-16	2016-17	2017-18	2018-19
Programme Score	A	A	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium	Moderate	Moderate

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/

A. Summary and Overview

Description of programme
PESP II supports the Government of Punjab (GoPb) to deliver more equitable access to better quality education across the whole province through a range of interventions designed to ensure more children are in school, stay longer and learn more. The programme combines a mix of delivery mechanisms including Sector Budget Support (SBS), financial aid, and technical assistance (TA) to the GoPb. In January 2013, DFID approved the Punjab Education Sector Programme II (PESP II) building on the UK’s previous support to the GoPb to reform and transform delivery of education in Punjab. PESP II complements the DFID supported Punjab Education Reform Roadmap. The UK aims to provide up to £420.5 million over six years between 2013 and 2019. PESP II is comprised of ten components:

Sector budget support to improve access to and quality of education in government schools through School Education Department (SED) and its entities including Quaid-e-Azam Academy for Educational Development (QAED), Punjab Curriculum and Text Book Board (PCTB), Punjab Examination Commission (PEC) and Programme Monitoring and Implementation Unit (PMIU).

School Construction and Rehabilitation Programme (SCRP) to build additional classrooms and toilets in existing government schools.

Financial aid to the Punjab Education Foundation (PEF) to improve access to and quality of Punjab’s low fee private school sector through an Education Voucher Scheme (EVS), New Schools Programme (NSP), and Foundation Assisted Schools (FAS) programme.

Targeted support to PEF to tackle social exclusion and inequality by identifying and enrolling out of school children in the 11 lowest-performing priority districts in Punjab.

Support to Special Education Department for an inclusive education programme to provide children with mild disabilities with formal schooling opportunities.

Support to the Punjab Education Endowment Fund (PEEF) to provide scholarships for talented female students from poor households in the 16 priority districts to study at intermediate level; and for male and female students to study at tertiary level.

Support to the Lahore University of Medical Sciences (LUMS) National Outreach Programme (NOP) for providing scholarships for talented male and female students from poor households and disadvantaged areas at the tertiary level.

A technical assistance component to deliver the programme and manage key components through a commercial supplier - comprising Cambridge Education (CE) and Delivery Associates (DA) - providing support to the GoPb, the Chief Minister’s Education Roadmap process and other partners in the PESP II programme and $1million through the World Bank to GoPb to support early implementation of the World Bank’s Third Punjab Education Sector Project.

Advancing Action for Adolescent Girls (A3G) for 24,000 out of school adolescent girls in three of the lowest performing districts of South Punjab implemented by Idara Taleem-o-Aagahi (ITA).

A programme performance evaluation component.

PESP II provides Technical Assistance to SED (and its affiliated agencies), SpED and PEF to support programme delivery, capacity building and institutional strengthening. The current PESP II TA contract is being managed by CE (up till 31st Mar 2020) after the previous contract managed by Adam Smith International (ASI) ended in March 2018.  PESP II also provided TA to support the Chief Minister’s Education Reform Roadmap though McKinsey and Company. The McKinsey contract ended in December 2018 and is now managed by DA, a sub-contractor for CE. PESP II also provided TA to SED through an Externally Financed Output (EFO) agreement with the World Bank (£808,092, Jan 2017 to Dec 2018). The EFO was designed to align technical assistance and to strengthen collaboration between PESP II and the World Bank’s Education Sector Project across areas that are not covered by other DFID or World Bank TA.

Summary supporting narrative for the overall score in this review

The programme scored an ‘A’ meaning outputs met expectations. The year was marked by general elections and subsequent changes with a new political party forming the Punjab Government. The change in Government was also preceded by two months of interim Government and this political scenario had some expected impact on the momentum of education reforms. However, with the new Government coming on board in August 2018, the top political and bureaucratic leadership have identified education as one of the priority sectors for reform and this was reflected in 100 days agenda of the Government as the ‘New Deal’ for education in Punjab.

There is strong political will and engagement, along with resource allocation, to improve education in Punjab. The reform agenda under the Education Roadmap, supported by PESP II, provides the high-level political engagement and accountability to drive progress through SED. The 2018 roadmap goals are:
- Enrolment and access: 95% minimum participation rate for 5 to 9 year olds;
- Teaching quality: 75% score on six-monthly assessments;
- Schools and teachers: 36,000 new classrooms, 46,000 new teachers, 100% functioning facilities in schools;
- Public private cooperation: 2.6 million students enrolled in PEF supported schools.

The results achieved against the roadmap targets included participation rate for 5-9 years old at 94.9%; six monthly assessment score at 77%, 99% functioning facilities with 87% primary schools having four teachers and 2.6 million children enrolled in low cost private schools through Public Private Partnerships (PPP). After the general elections the roadmap team’s continuous engagement with the new government helped in developing future strategy documents on quality, enrolment and delivery approach. The last education stock take led by the Chief Minister happened in March 2018 though there have been internal stocktakes led by Secretary Education during 2018. In view of the success of roadmap approach it would be advisable to advocate for the process to continue under the new Government.

The programme progressed satisfactorily during the last year. Some of the key achievements at the outcome level included 77% score on student learning objectives (SLO) and student attendance at 94%, much above envisaged targets. At the output level, the progress is as below:

Overall the programme outputs scored an A: Met expectations

Output	Score	Impact Weight	Summary
1. Stronger leadership and accountability	A	15%	Progress met expectations with the milestone on the district performance management system exceeding expectations.
2. Better teacher performance and better teaching	A	25%	Overall progress met expectations with PCTB on track for textbook printing and distribution. Progress / lagged on approval of PEC organisational plan however progress on teacher training met expectations. Lastly progress on teacher recruitment substantially exceeded expectations with 87% primary schools having more than four teachers.
3. High-quality infrastructure	C	15%	Progress substantially did not meet expectations, with progress on construction of additional classrooms and toilets and the quality of construction substantially below expectations.
4. Improved access to schools, especially in priority districts	A	25%	Progress met expectations across all areas and on the efforts made by PEF to enrol out of school children in priority districts as well as the enrolment of children with disabilities in PEF partner schools however ITA struggled to meet its enrolment targets. PEEF also on track to meet its targets to enrol 20,000 additional girls.
5. Top political leadership engaged on education reform agenda in the Punjab	A	10%	Progress has met expectations as despite some slowing down during political transition, overall stocktake routines continued. The Roadmap team also worked on capacity building of PMIU to take over the management of stocktake routines besides contributing to the education blue print.
6. High-quality technical assistance to government stakeholders that builds sustainable systems and processes	A	10%	Progress has met expectations against both milestones for this year. The TA contract with ASI ended with a successful handover to DFID, and the new supplier CE has successfully completed the inception phase, and has an agreed workplan with SED.

Overall the programme made some good progress over the period under review. The PMIU successfully led Monitoring and Evaluation Assistant (MEA) monthly school visits, covering over 90% of schools with third party audit showing a variation of less than 5% between MEA and TPV assessment. The schools were able to utilise 55% of Non-Salary budget (NSB) during the first 6 months of the financial year which is crucial to provide for the every-day needs of schools like utilities and stationery.

Quaid Academy for Education Development successfully completed Training of Trainers (ToT) and leadership training programmes. However, it could not implement its continuous professional development (CPD) plans in full due to limited resources. Last year, the teacher mentoring role was transferred to newly recruited Assistant Education Officers (AEO) who are also responsible for administrative work and monitoring of schools. AEOs report to SED in terms of their line management and QAED has limited influence over AEOs in terms of supervising them on mentoring responsibilities. This issue needs resolution so that mentoring for teachers can be carried out effectively.

Similarly, Punjab Examination Commission successfully conducted grade 5 and grade 8 exams but is still waiting for a permanent CEO as well as approval of its organisational plan. The School Education Department was able to provide for 99% functioning facilities in all 52,000 plus schools along with 87% of these schools having more than four teachers each.

Punjab Education Foundation, a major recipient of DFID’s financial aid, was able to enrol another 100,000 Out of School Children (OOSC) in priority low performing districts besides meeting the targets for special needs children mainstreaming in PEF schools. PEF also underwent a Third Party Validation (TPV) last year which gives DFID assurance about PEF systems in general. Currently PEF is facing a budget shortfall of PKR 5 billion in the current year and resultantly has frozen its enrolment targets. However, Government has indicated its commitment to resolve this resource constraint issue at the earliest.

The scholarships component also progressed well last year. Lahore University of Management Sciences (LUMS) programme concluded with 742 scholars benefitting from DFID’s support in the field of economics, law, engineering and computer studies with 25% of the scholars being women. There was substantial improvement in gender balance during the life of the programme though there is still a long way to go. Punjab Education Endowment Fund exceeded its original targets of benefitting 27,500 girls in higher education and were able to achieve a target of 34,000 girls benefitting from the programme due to efficient management. The programme received an extension to provide scholarships to another 15,000 girls to complete their higher secondary education during the current year and is on track to deliver the revised targets.

The programme also supported a new project Advancing Action for Adolescent Girls (A3G), being implemented through an NGO - ‘Idara Taleem-o-Aagahi (ITA) to enrol 24,000 out of school adolescent girls in schools of South Punjab as well as provide them with vocational education. The programme is in its initial phase and being monitored regularly by DFID. Another new initiative this year has been support to the government to scale up second shift schooling and provision of transport solutions for girls and boys to complete secondary education. This project - Sustainable Transition and Retention in Delivering Education (STRIDE) aims to enrol 20,000 students in 20 districts of Punjab.

The School Construction and Rehabilitation Programme (SCRP) implementation through IMC Worldwide (IMC) has a target to complete 6,941 classrooms by September 2019 and the progress to date has not crossed the half-way mark. DFID put IMC on a performance improvement plan (PIP) followed by a comprehensive review, which recommended to reduce the scope of work. DFID is reviewing alternate options to deliver the gap of 3,000 classrooms left by IMC in close consultation with SED. DFID has engaged TPV for closer monitoring of school construction and has recently increased the sample percentage to ensure quality. To bring SCRP on track, it is being actively monitored by DFID at three levels: by the team and senior management, as well as through the Strategic Relationship Management process.

The technical assistance management was successfully transferred to a new supplier Cambridge Education supported by Delivery Associates. The TA has since completed the inception phase, deployed the TA team and agreed workplan with the new Government.

The PESP II programme is also undergoing an independent evaluation aimed at understanding the performance of the education system in Punjab over the period of the PESP II programme, and the contribution of the PESP II project components (individually and collectively) to progress in the education sector. The first interim evaluation report provided in October 2018 focuses on providing an interim assessment of the contribution of DFID’s Sector Budget Support, Technical Assistance and support to the Education Roadmap and Stocktake process. The evaluation confirms that the period since 2013 has seen significant progress in education in Punjab with evidence of increased participation and of improvement in learning outcomes, and that the Roadmap and Stocktake process has provided the main instrument for driving and monitoring improvements in the education system. The evaluation also presents some useful reflections on the effectiveness of the SBS approach and finds that the way in which SBS was delivered has not provided direct incentives to the organisations responsible for achieving targets since they have not perceived a link between the achievement of targets and the funding they have received. While TA provided by DFID is assessed to have been largely effective, the evaluation stresses the need for better institutional assessment in designing TA support and a stronger feedback mechanism from beneficiaries so that emerging concerns about TA quality can be addressed in a timely way. Finally, while acknowledging that the programme has supported several targeted interventions that address gender and equity considerations, the evaluation recommends mainstreaming gender and equity across all the different components of the programme to strengthen the focus on equity and gender. The findings and recommendations of the evaluation shall be used to improve the design and effectiveness of any future assistance.

The programme is aligned with ‘The New Deal 2018-23’ [1]– the education reforms blueprint for school education in Punjab and is supportive of all three pillars of the initiative. This need for better alignment with Government priorities was also recommended by the PESP II evaluation[2]. PESP II supports the ‘Learning’ pillar through its work with QAED and PEC while it is supporting the ‘Access’ pillar through its roadmap and infrastructure components. The critical pillar of ‘Governance’ is being supported through support to SED and PMIU. The programme is also flexible and adaptive and can address the changing governance paradigm under the new local governments’ framework expected to be introduced soon. The programme continues to support District Education Authorities (DEAs) and strengthen public financial management through linkages with other DFID programmes like the Sub-National Governance programme.
[1] https://www.dawn.com/news/1445543
[2] First interim evaluation report PESPII 2018

Key recommendations for the year ahead

Governance/SBS:
- SED/PMIU should develop a better system for monitoring Non-Salary Budget (NSB) releases and utilisation and find ways of raising awareness and empowering school councils for efficient utilisation of NSB - July 2019.
- The TA should work closely with the SED for early establishment and resourcing of a Financial Management Cell (FMC) for better resource management - Immediate.
- SED to allocate funds to PEF and QAED to meet their delivery needs - Immediate.

Teaching and Learning:
TA to provide support to PEC for analysis, reporting and customised dissemination of exam results to different stakeholders such as SED, QAED and PEC. Capacity to be built on how results can be utilized to inform core work of the department, June 2019.

Infrastructure:
- DFID and PMIU/SED should expedite the agreed alternate delivery options (classroom construction through school councils) as the programme end date is March 2020 - Immediate.
- DFID should continue to closely monitor IMC’s performance and should seek to share risk more effectively with IMC through a revised payment by results mechanism as part of the contract amendment currently under negotiation - On going.

Equity and Inclusion:
DFID should closely monitor the progress of the adolescent girls’ education programme to ensure that agreed milestones are met. In addition, a sustainability plan for the programme should be explored with options to scale up under any possible future assistance. To provide credible evidence of what works, a rigorous evaluation of the programme is needed.

Roadmap:
DFID and TA to work with the new government to find ways of institutionalizing the delivery approach providing the necessary technical assistance to the government.

Technical Assistance:
- DFID to ensure that there are clearly defined reporting processes in place to ensure systematic and timely feedback on the TA’s performance from the SED - Immediate.
- TA team needs to move quickly to deliver their agreed workplan as the PESP II programme and TA contract will be ending in March 2020 - Immediate.

Programme Management:
- DFID to review SCRP/IMC budgets and forecasts for the final year of the programme to avoid high level of variations - April 2019.
- DFID to closely monitor flow of funds to PEEF to avoid delays in funds reaching the organisation - Immediate.
- TA needs to fully mobilise the result area leads and local partners. The position for the equity lead is currently filled on ad hoc basis so a full time expert needs to be hired - Immediate.
- The KPIs for the TA team (CE) need to be fully aligned with the government priorities. It is an evolving area which needs to be closely monitored.
- DFID to review and update the PESP II log frame to reflect new assumptions and revised targets for the final year - March 2019.
- DFID to commission a rigorous evaluation of the adolescent girls’ education programme to gather evidence and learning on what works

List of Acronyms
ASI / A3G / AEO / ASER	Adam Smith International / Advancing Action for Adolescent Girls / Assistant Education Officer / Annual Status of Education Report
BC / CE / CEO / CM	Business Case / Cambridge Education / Chief Executive Officer / Chief Minister (Punjab)
C&W / CPD / DA	Construction and Works Department / Continuous Professional Development / Delivery Associates

DEA / DEO	District Education Authority / District Education Officer
DFC	District Field Coordinator
DFID	Department for International Development (UK)
DLI / DRC	Disbursement Linked indicator / District Reforms Committee

EFO / EVS	Externally Financed Output / Education Voucher Scheme
FAS / FMC	Foundation Assisted Schools / Financial Management Cell
GBP / GoPb / IMC / ITA / KPI	Pound Sterling / Government of Punjab / IMC Worldwide / Idara I Taleem o Aagahi / Key Performance Indices
LND	Literacy and Numeracy Drive
LUMS	Lahore University of Management Sciences
MEA	Monitoring and Evaluation Assistant
MIS	Management Information System
NOP	National Outreach Programme
NSB	Non-Salary Budget
NSP / OOSC	New School Programme / Out of School Children
OPM / PCTB	Oxford Policy Management / Punjab Curriculum and Textbook Board
P&DD / PEC / PEEF	Planning and Development Department / Punjab Examination Commission / Punjab Education Endowment Fund
PEF	Punjab Education Foundation
PESP II	Punjab Education Sector Programme II

PKR / PMIU / PPA / PMS / PRAP	Pakistani Rupee / Programme Monitoring and Implementation Unit / Partnership Principles Assessment / Performance Management System / Portfolio Risk Assurance Programme
Pre-DRC / PPP / QAED	Pre-District Review Committee / Public Private Partnership / Quaid-e-Azam Academy for Education Development
QSC / RAF / SDGs / SBS / SCRP	Quarterly Steering Committee / Results and Activities Framework / Sustainable Development Goals / Sector Budget Support / School Construction and Rehabilitation Programme
SED / SEND / STRIDE	School Education Department / Special Education Needs and Disabilities / Sustainable Transition and Retention in Delivering Education
SLO	Student Learning Outcome
SpED	Special Education Department
SMU / TAMO	Special Monitoring Unit / Technical Assistance and Management Organization
TA / TPV / VFM	Technical Assistance / Third Party Validation / Value for Money

## B: DETAILED OUTPUT SCORING

Output Title	Strong leadership and accountability
Output number per LF		1	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) 2018-19	Progress
1.1: Number of districts with performance management system in place and in use	At least 8 DRC meetings held in every district in the last year	A+: Milestone moderately exceeded expectations / 35 districts held 10 meetings in the year while one district held 8 meetings in the year.
1.2: Frequency of MEA visits and reliability of data collected	90% MEA school visit rate (including Special Education schools) maintained in all districts (12-month average) / Maximum variation between audit data (from DFC spot checks or TPVs) and MEA data for the same schools should be within +/- 10 %	A: Milestone met expectation / Except for the months of February (PEC exams) and May (start of summer vacations), MEA visits were consistently above 90% annually, the only exception being District Rajanpur / Variance remained within +/- 5% / Student attendance: - 2 % variance / Teacher presence: - 4% variance / Functioning facilities: - 0.3% variance
1.3: Timely release and efficient utilization of school NSB	60% utilization at district level (releases to schools), of NSB released to districts from July - Dec 2018.	B: Milestone moderately did not meet expectations / NSB utilisation at school level for the first six months of the current fiscal year (July-Dec 2018) is 55%

Provide supporting narrative for the score
Output one tracks progress made by the programme on governance and district delivery. The last year was critical for the smooth transitioning of education reforms due to planned elections and their expected impact on reform momentum. The activities under this output are primarily supported through sector budget support and technical assistance to the Government of Punjab. Progress under this output during the last year has met expectations.

Output 1.1: A+: Milestone moderately exceeded expectations
This indicator measures the rhythm of district delivery routines i.e. monthly district review committee (DRC) meetings that drive performance against key education indicators at the district level. The PESP II evaluation also found these routines to be effective in maintaining district focus on performance management and progress[3]. Except for Rawalpindi, every district held regular DRC meetings for ten out of twelve months barring two months of summer vacation. This is particularly noteworthy as the last year saw several transitions in government, first to an interim caretaker government and then to a newly elected government. The fact that district delivery routines, which include a monthly school monitoring and reporting system, pre and post review meetings, in addition to the DRC meetings, continued throughout this period and have transitioned into the new government is a testament that these routines have become sustainable and are embedded within the system. Strengthening district education governance is also fundamental to the decentralisation agenda of the new Government and there is a new impetus and opportunity to strengthen District Education Authorities (DEA) in Punjab. However, the exact contours of the new local government framework are still unclear, and the programme should be flexible enough to adjust to emerging priorities.
[3] Recommendations to DFID, First interim evaluation report on PESP2 2018

Output 1.2: A: Milestone met expectations
The School Education Department has an elaborate school monitoring system in place where data on 14 key education related indicators is collected every month using tablets by some 900 Monitoring and Evaluation Assistants (MEAs) across all 36 Districts of Punjab. This data is then analysed and used to monitor progress. This indicator assesses both the frequency of visits by these monitors to look at overall coverage of the monitoring system, as well as the quality of this monitoring process through spot audits. In the last year the monitoring visits target of 90% plus was consistently met for all Districts except District Rajanpur where hard terrain and remoteness of areas always make measuring targets a challenge. More importantly there was minimal variation between the data recorded by monitors and data collected through independent third-party verification. One obvious fact is that though the variance is less than 5%, in all cases it’s the monitors’ data which shows better performance, and this is an area for further strengthening of monitors’ data collection processes.

Output 1.3: B: Milestone moderately did not meet expectations
Non-Salary Budget (NSB) which provides schools with the funds to cover school operating costs as well as missing facilities has been a significant intervention under the overall Punjab education reforms programme. This provision is unique in many respects to Punjab. Currently a total of Rs.14 billion is allocated to all 36 districts of Punjab according to an approved formula based on enrolment, school need etc. In the first six months of the current fiscal year, the government has already released Rs.6.1 billion (43% of the total Rs.14 Billion) to schools which is reflective of Government’s commitment to school improvement despite severe fiscal constraints. NSB utilisation data is maintained in school registers and monitored every month by MEAs who feed this information into the provincial school management information system. The utilisation rate for NSB according to MEA data is 55% for the first six months of the financial year. There is still considerable room for improvement in the capacity of school councils to utilise non-salary budgets efficiently and effectively. Improving the effectiveness of NSB spend is part of wider Public Financial Management reforms supported through PESP II. As part of this the programme has introduced regular budget monitoring in the education department and supported the establishment of a Financial Management Cell in the department. The FMC which had been mainly funded and staffed through the DFID programme, is still struggling to find the necessary funding from the Government and appropriate human resource to ensure that it becomes sustainable. The new government recognizes the need for strengthening financial management systems within the department and has provided assurance that these issues will be resolved soon.

Lessons identified this year:
The District Field Coordinators (DFC) provided through DFID TA had a crucial role in driving district delivery routines, providing both facilitation as well as independent oversight of the process. While these positions were temporarily accommodated by the government as part of PMIU staff, this could not be continued due to funding constraints.
- Non-salary budgets to schools remain a challenge in terms of both timely releases and utilisation.
- Roadmaps and stocktake processes are effective monitoring tools to measure progress but need top political and bureaucratic ownership to be successful and sustained beyond successive political cycles.
There is limited capacity at the district level to spearhead reforms in a decentralised set up.

Recommendations for next year and new business case:
- SED to ensure that the support provided through DFCs is transferred to district education officials (new hire/ current) for sustainability beyond the life of the programme - July 2019.
- SED/PMIU should develop a better system for monitoring NSB releases and utilisation and find ways of raising awareness and empowering school councils for efficient utilisation of NSB - July 2019.
- The two DFID programmes – PESP II and Sub-National Governance, should be supporting DEAs in areas of leadership, financial management and improved monitoring of schools - through the year

Output Title	Better teacher performance and better teaching
Output number per LF		2	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) 2018-19	Progress
2.1 Development, dissemination and use of new textbooks and teacher guides for primary grades	PCTB completes procurement of authors / publishers using the new scheme for the development of textbooks and supplementary reading materials	A: Milestone met expectations / Procurement of authors/publishers completed.
2.2 Improved reporting, analysis and dissemination of PEC exam results	PEC organizational development plan approved by PEC Board and implementation started	C: Milestone substantially did not meet expectations / Organizational development plan developed but still awaits approval. Implementation has not started.
2.3 Quality and delivery of teacher training and mentoring	QAED completes Training of Trainers for CPD and leadership development programme	A: Milestone met expectations / Training of Trainers was conducted for continuous professional development of teachers and leadership development of head teachers.
2.4 Quality, transparency and timeliness of teacher recruitment and deployment.	75% government primary schools have at least 4 teachers	A++: Milestone substantially exceeded expectations / 87% of government primary schools now have 4 teachers.

Provide supporting narrative for the score
This output tracks key components of improved teaching and learning in Government of Punjab’s schools through (i) the provision of improved curriculum materials, (ii) expanded and better use of learning assessments and examinations and (iii) the equitable deployment of more effective teachers. While limited progress has been made on strengthening the functions of the Punjab Examination Commission, other areas such as teacher training have received considerable attention. Therefore, overall this output has met expectations.

Output Indicator 2.1: A – Milestone met expectations

This indicator tracks the textbook development process by PCTB. DFID with its TA team has supported the government to rationalise the 2006 curriculum to focus on key learning outcomes in the core primary subjects of English, Urdu, Mathematics and Science. The TA team has supported the PCTB to improve its capability and capacity to apply textbook standards and review guidelines for the development of new textbooks and supplementary materials. The quality criteria in the standards and guidelines require that new textbooks are high quality, more inclusive, more gender sensitive and have a more positive view of minorities. It remains the responsibility of the PCTB to approve the final versions of new texts.

PCTB is now following a rigorous process for development, review and approval of science and technology textbooks. In the last year, textbook manuscripts were commissioned from shortlisted authors and publishers. The PCTB is now using a new scheme of studies and textbook standards and review guidelines developed through technical assistance to review the manuscripts. A team of independent experts have also been commissioned by the PCTB for this work and the final manuscripts will go to the board for approval. As the procurement of authors/publishers has been completed, this milestone has met expectations.

Output Indicator 2.2: C - Milestone substantially did not meet expectations
This indicator tracks the approval and implementation of the organizational strengthening plan for PEC. An organisational development plan was developed by PEC which was approved by the previous Board. The staffing plan, which is a key element of the organizational development plan, was also approved by the previous PEC Board and Chief Minister (CM).

With the change of government, the new PEC Board is being reconstituted and the staffing plan needs re-approval. The Chief Minister has directed that the staffing plan may be placed before the committee headed by Chief Secretary, Punjab. PEC is currently reviewing the staffing plan which will then be submitted to the Secretary SED for onward submission to the Chief Secretary, Punjab for approval. As the plan is still being finalized and implementation has not started, this milestone is off track and substantially did not meet expectations.

In addition to the organizational development plan, TA has supported PEC to develop an Assessment Policy Framework which was shared with a variety of different stakeholders including District Education Authorities (DEAs) for feedback. Certain key policy recommendations made therein have been adopted by the new government and DFID TA continues to support the education department in the implementation of these recommendations.

Output Indicator 2.3: A - Milestone met expectations
This indicator tracks the delivery of training to teachers and head teachers in schools in Punjab. The Quaid-e-Azam Academy for Education Development (QAED), the provincial institute for teacher professional development, completed a needs assessment and developed training material (Primary Teachers Guides, Elementary Teachers Guides, LitNum Lesson Plans and Professional Development Day modules), for continuous professional development (CPD) of teachers with support from DFID TA. A 12-month implementation plan and Academic Calendar was also developed. Thereafter, QAED selected and validated 432 District Subject Experts (DSEs) and conducted 4 days of professional development at provincial level. Also, 14,000 Cluster Subject Experts (CSEs) were selected and underwent 6 days of training. However, the annual regular budget allocation to QAED does not include expenditure heads on CPD of all teachers. To overcome this budget shortfall, QAED has submitted PC-1 to SED for 3-week CPD of teachers in 6 districts of Punjab.

For training of head teachers, QAED developed a module on School Leadership Development Programme with the assistance of the British Council. 50 Lead Trainers were trained and validated by the British Council who further trained 634 QAED Master Trainers. Of these, 500 trainers conducted a training of 8 days for 15,000 head teachers. As next steps, QAED is analysing the training evaluation forms received from participants.

In the upcoming months, it is expected that QAED might undergo restructuring and devolve their training to the district level. QAED is also working with SED to review the job descriptions of AEOs and introduce a classroom observation tool through which feedback from Assistant Education Officers (AEOs) or school supervisors can be used to inform teacher professional development.

Output Indicator 2.4: A++ - Milestone substantially exceeded expectations
This indicator tracks the percentage of schools with fewer than 4 teachers. In 2018, a major round of recruitment was conducted in which 24,635 teachers were recruited, trained and placed in schools. As a result of the deployment, the percentage of primary schools with four or more teachers has increased from 72% last year to 87% this year. Therefore, this milestone has substantially exceeded expectations. This will reduce the number of schools with multi-grade teaching and increase student attendance rates and student learning outcomes.

Lessons Learnt
- Transition of provincial/federal governments can lead to changes/delays in delivery of programmes as incoming office bearers might want to shift focus in a different direction or require time to get up to speed with previous workflow. This was one of the reasons for revising milestones for PCTB, PEC and QAED.
- Over the last year, while QAED has continued to introduce several reforms in the CPD structure, budget constraints remain to be one of the biggest challenges for the organization. The support provided by DFID is given directly to SED under SBS which is difficult for QAED to access.
- In the current structure of the district, the AEOs are managed by the SED which leads them to focus more on administration related issues during their school visits. If they had an institutionalized feedback mechanism for reporting back to QAED, then there is a possibility of AEOs providing substantial on-going support to teachers and head teachers to drive learning outcomes for students.

Recommendations
PEC and TA team to work together to expedite finalisation of staffing plan to be shared with Chief Secretary Punjab for approval so that vacancies in the department can be filled on a priority basis
- TA team to provide support to PEC for analysis, reporting and dissemination of exam results to different stakeholders such as SED, QAED and PEC. Capacity to be built on how results can be utilized to inform core work of the department.
- TA team and DFID to work with PCTB, PEC and QAED to develop long term institutional partnerships with local and international universities and educational institutes to strengthen these government institutions in a sustained manner.

Output Title	High quality school infrastructure
Output number per LF		3	Output Score	C
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) 2018-19	Progress
3.1 Improved availability and functioning of basic school facilities (toilets, boundary walls, drinking water, electricity) in all districts	Every district with functioning of facilities >95%	A++: Milestone substantially exceeded expectations / All districts have functioning facilities >95%. Overall 99% of the schools across the province have functioning facilities
3.2 Number of classrooms and toilet cubicles constructed under School Construction and Rehabilitation Programme	a. Additional classrooms: 2412 / b. Toilet cubicles: 1291 / c. All construction breaks ground	C: Milestone substantially did not meet expectations / a. 1702 (Girls 740, Boys 962) / b. 922 (Girls 334, Boys 588) / c. 248 schools did not start
3.3 Percentage decrease of failed construction inspections per quarter	0.8% decrease / Baseline (Sep 2017): 8.8%	C: Milestone substantially did not meet expectations / The percentage of failed inspections increased to 25.1%

Provide supporting narrative for the score
This output tracks the quantity and quality of existing and new school infrastructure in Punjab. It supports the provision of new classrooms and essential facilities. It also supports the systems to ensure essential school infrastructure (classrooms, toilets, boundary walls, electricity, and water) is available and functioning. There is good progress on the availability and functioning of basic school facilities in all districts. However, progress on the construction of additional classrooms and toilets remains substantially behind targets in the year under review. Overall, progress under this output this year substantially did not meet expectations.

Output Indicator 3.1: A++: Output substantially exceeded expectations
This indicator tracks the provision and functioning of basic school facilities in all districts of Punjab and is a measure of the government’s investment in school infrastructure. The percentage milestone and progress represent the number of functioning and available facilities as a percentage of total facilities. In Punjab as a whole, there has been a positive increase in functioning facilities in schools over last year from 98% to 99%. The milestone required functioning facilities at 95% or above in all districts and meeting this target in all districts is a significant achievement as at least a third of the districts in Punjab are under developed and marginalized. For next year, it is recommended that a revised indicator is selected capturing both the functioning school facilities as well as required facilities in these schools.

Output Indicator 3.2: C - Output substantially did not meet expectations
The indicator tracks the number of new classrooms and toilet cubicles constructed under the School Construction and Rehabilitation Programme (SCRP). SCRP is implemented by IMC Worldwide (IMC) which is responsible for both construction and technical assistance. This indicator assesses the performance for the construction works. 1702 additional classrooms were completed against a target of 2412; 922 toilet cubicles were completed against a target of 1291; and 248 schools could not break ground and thus remained behind schedule. This is substantially below expectations as milestones and targets were revised downwards along with a £21 million reduction in contract. All construction activities need to be complete by September 2019 and to date progress has not crossed the half-way mark. Therefore, the pace of construction needs to increase significantly to reach the target by September 2019. Cardno Emerging Market Ltd conducted third party monitoring of SCRP and has reported several critical observations. DFID has asked IMC to respond and action on all observations. IMC was put on a performance improvement plan (PIP) from February to April 2018. IMC partially met the targets in the PIP, following which DFID undertook a comprehensive review of SCRP. The review also recommended to reduce the scope of work and contract value.

Output Indicator 3.3: C - Outputs substantially did not meet expectations
The indicator tracks the percentage decrease of failed construction inspections undertaken by IMC on sub-contractors. IMC performs construction inspections; quality control; quality assurance; and capacity building for their staff, subcontractors and the community which aims to reduce failed inspections. The number of failed inspections increased to 25.1%, representing a 3.3% increase from last year, whereas the required target was a 3.2% decrease (over the four quarters). IMC has also moved far away from the baseline of 8.8%. This does not substantially meet expectation, especially as DFID approved an enhanced level of effort and greater number of international experts in July 2018 which should have improved this further.

Following the review, DFID has initiated a contract amendment to reduce the size of the contract, lock the list of schools to be delivered and to enhance payment by results. DFID has increased the third-party monitoring by Cardno. DFID continues enhanced monitoring of SCRP at programme level with IMC delivery team, monthly calls with IMC top management and using strategic relationship management. DFID is evaluating alternates to deliver additional classrooms and missing facilities.

Lessons learnt:

A key lesson for DFID is to ensure better understanding of the local markets in terms of capacity, political economy, legal structures etc before embarking on costly construction projects. This is even more important when we are envisioning a number of alternatives to deliver the results.

Recommendations
- As Indicator 3.1 has overall met its objectives, DFID should revise this indicator capturing both functioning as well as required facilities.
- DFID should expedite the alternate delivery options (classrooms construction through school councils) and take a decision as the programme end date is March 2020.
- DFID should continue to closely monitor IMC’s performance and should seek to secure better value for money through an enhanced payment by results mechanisms.
- DFID programme team should develop a note on lessons learnt and share with the Infrastructure Cadre.

Output Title	Improved access to schools, especially in priority districts.
Output number per LF		4	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) 2018-19	Progress
4.1 Number of OOSC enrolled in priority districts through PEF and CSOs.	100, 000 (cumulative) out of school children enrolled through FAS, EVS and NSP in new schools across 11 districts / 6,525 out of school adolescent girls are enrolled in and complete (graduate) ALP and TVET in three districts of South Punjab: / Accelerated Learning Programme (ALP): 5,400 / Technical and Vocational Education Training (TVET): 450 / Linkages: 675	A: Milestone met expectations / 100,000 OOSC enrolled in 11 priority districts. / 3357 out of school adolescent girls are enrolled. / Accelerated Learning Programme : 3025 / Technical and Vocational Education Training : 332 / Linkages: 82
4.2 Number of children in school supported through the Punjab Education Foundation (cumulative) / i) EVS ii) NSP iii) FAS	i) EVS ii) NSP iii) FAS / Total i) 515,357 ii) 237,516 iii) 1,872,126 / Boys i) 283,446 ii) 130,633 iii) 1,029,669 / Girls i) 231,911 ii) 106,883 iii) 842,457 / Total: 2,620,000 students	A: Milestone met expectations / Total i) 468,149 ii) 276,226 iii) 1,860,677 / Boys i) 254,513 ii) 149,181 iii) 1,009,730 / Girls i) 213,636 ii) 127,045 iii) 850,947 / Total: 2,605,052 students
4.3 Number of additional children with special educational needs and disabilities enrolled and supported.	2,000 additional children with SEND enrolled in special education institutions	A++: Milestone substantially exceeded expectations / 5018 additional children with SEND enrolled in special education institutions / 1761 additional children with SEND enrolled in Sped Government special schools. / 3257 enrolled in PEF schools through IVS.
4.4 Number of scholarships for poor and able students disaggregated by sex.	15,000 intermediate level scholarships provided to girls in 11 priority districts by PEEF	A: Milestone met expectations. / PEEF on track to enrol 20,000 girls by the end of February.

Provide supporting narrative for the score
Under this output, the programme improves access to quality education for children with disabilities and out of school children with a focus on girls. This is done by increasing enrolment through government collaboration with low fee private schools, scholarship programmes, and targeted programmes for children with disabilities and secondary school aged out of school girls. The programme focuses on districts that have high poverty and a high number of out of school children. This year saw an increased focus on girls’ education with the introduction of a new programme targeting out of school adolescent girls and the expansion of secondary school scholarships for girls. In addition, both PEF and the Special Education Department enrolled a high number of children with disabilities. Progress under this output has met expectations.

Indicator 4.1: A Milestone met expectations
This indicator tracks the enrolment of OOSC in Punjab’s lowest performing districts by the Punjab Education Foundation and the NGO Idara-e-Taleem-o-Aagahi (ITA). PEF manages public private partnerships with low fee private schools to provide free school places to children. PEF has enrolled 100,000 OOSC in the last year.

DFID has also partnered with a non-profit on a new project – Advancing Action for Adolescent Girls (A3G) to enroll out of school girls aged 9 to 19 years in accelerated learning, technical and vocational education programmes. This programme operates in three of the lowest performing districts of Punjab where access to education for girls is particularly challenging: Bahawalpur, Rahimyar Khan and, Muzaffargarh. ITA’s community mobilizers raise awareness about the programme in poor communities and select girls using poverty score card questionnaires. Given that a high number of girls drop out after primary school, this is an effective approach to increasing the access of women and girls to education. As of January 2019, the programme has enrolled 3,357 girls. While this fall short of the targeted enrollment in year one, the number of girls enrolled is still significant given the unavoidable delay in programme start up due to issues in securing the necessary permissions (NOCs) and finalizing MoUs with the government departments. The targets were revised in October 2018 to factor in these issues.

Indicator 4.2: A: Milestone met expectations
This indicator tracks progress in enrolment against PEF’s expansion plan enrolment targets through its Education Voucher Scheme, Foundation Assisted Schools, and the New School Programme (NSP). As the 2017 target was not completely met, the 2018 milestone was the same as the 2017 milestone. The target set is also consistent with PEF’s five-year expansion plan targets which were achieved in March 2018.

While there has been some increase in enrolment in PEF supported schools over the last year, from 2,589,000 students in 2017 to 2,605,052 in 2018, this is slightly below target (2,620,000). Due to the elections in 2018 which resulted in reshuffling of staff throughout the Punjab government, delay in approval of policies and re-allocation of budgets, PEF has not been able to undertake an enrolment drive in 2018.

Future goals for PEF are yet to be devised and will be in line with the new government’s policy on expansion of PPPs and the availability of public financing to support these initiatives.

Indicator 4.3: A++ : Milestone substantially exceeded expectations
This indicator tracks the enrolment of children with disabilities in both segregated special education schools and mainstream government and PEF schools. Under this component, the Special Education Department in Punjab set up new and upgraded existing special education institutions, carried out enrolment campaigns and provided free transportation to the existing special education centres. SpED was expected to partner with two or three private sector organisations to enrol and retain out-of-school children with disabilities in general and special schools. While a budget was allocated for PPPs from 2017 to 2019 and organisations were shortlisted, SpEd is still waiting for a policy decision from the newly elected government to proceed ahead with the PPPs. On the other hand, PEF was able to exceed the Special Education Needs and Disabilities (SEND) enrolment targets assigned to it substantially.

Indicator 4.4: A: Milestone met expectations
This indicator tracks increase in access to higher secondary and tertiary education for poor students. This component included two programmes. The support to LUMS National Outreach Programme (NOP) through ‘Empowerment through Education’ programme that provided tertiary level scholarships for merit based but needy students at the Lahore University of Management Sciences came to an end with its external review being completed this year. Through the NOP, 742 scholarships were awarded over five years (approx. 25% women). The summer coaching sessions helped to increase the percentage of female student inductees in LUMS, from 23% in 2013 to 38% in 2017. The job placement ratio for LUMS graduates is 91% with a 100% increase in family income for the scholars starting with their first job.

The second programme is an intermediate level scholarship programme for girls by the Punjab Education Endowment Fund in 11 priority districts in Punjab. In the first phase of the programme, PEEF showed good progress against its targets and was able to award more scholarships than projected due to lower than expected costs. This year DFID signed a new agreement with PEEF for two years to provide 15,000 additional scholarships to girls in secondary school. PEEF has completed the shortlisting of students and expects to disburse 20,000 scholarships to girls in 16 districts by the end of February 2019. The programme has a separate quota for children with disabilities and minorities. However, PEEF uses the government’s definition of disability which is limited to physical, vision and hearing disabilities. It excludes children with learning disability—a group that remains excluded in general in the country.

Lessons identified this year
The presence of cultural barriers and limited resources for children with disabilities affects their access to education. Within this group, children with learning disabilities are further marginalised as both public and private schools don’t have the capabilities to detect learning disabilities or to address the needs of such children. These children are also missed by the programmes under this output. While it is not possible to address this within the one year left in the programme, this should be taken up in any successor programme to PESP.

Recommendations for the year ahead linked to this output
- The A3G programme presents an alternative approach to targeting out of school adolescent girls, a group that is extremely marginalized and is not being catered to by the formal school system. DFID should closely monitor the programme’s progress to ensure that agreed milestones are met. In addition, a sustainability plan for the programme should be explored with options to scale up under any successor programme. To provide credible evidence of what works, a rigorous evaluation of the programme is needed.
- The School Education Department should consider introducing inclusive education programmes in mainstream public and private schools learning from the experience of the Punjab Inclusive Education Programme implemented by the Special Education Department. This should include the handover of the PEF Inclusive Voucher Scheme (IVS) from the Special Education Department to SED to support mainstreaming of children with mild disabilities in PEF and government schools.
As recommended by the PESP II evaluation, the design of any successor programme should ensure that inclusion is addressed across all programme components and not just through specific targeted interventions. The PESP II evaluation recommends clear and well-defined gender and equity targets under the education roadmap and sector budget support components[4].
[4] Lessons, First interim evaluation report on PESP2 2018

Output Title	Top political leadership engaged on education reform agenda in the Punjab
Output number per LF		5	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) 2018-19	Progress
5.1 Data analysis and performance management routines	i) Monthly data review meetings with the PMIU / ii) Monthly internal (SED) stocktakes / iii) Undertake the blueprint process with regular internal stakeholder meeting including SED, PMIU and other TA teams / iv) Presentation / stocktake of the education blueprint with senior stakeholders	B: Milestone moderately did not meet expectations / 6 data reviews meeting held with PMIU / 8 internal stocktake meetings held by the Secretary SED / 6 workshops were held with key stakeholders on the education blueprint / Roadmap team was part of the blue print/ new deal discussions however the roadmap TA contract ended before finalisation of education blue print/ new deal.
5.2 Roadmap transition planning and handover	i) Perspective on future priorities to be developed as part of Education Blueprint / ii) Handover of all roadmap activities and routines to the appropriate teams	A: Milestone met expectations / Roadmap team as part of the transition developed the future strategy documents on quality, enrolment and delivery approach and fed into the ‘New Deal’ for Education document. / Handover to CE and SMU[5] completed on time.
[5] Special Monitoring Unit (SMU) is a unit within the Chief Minister Punjab’s Secretariat and functions as a government-owned roadmap team to work on priority areas.

Provide supporting narrative for the score
This output tracks the effectiveness of DFID’s TA contribution in the education roadmap process and the transition and handover of delivery routines to the new government. The PESP II evaluation finds that the Roadmap and Stocktake process was largely an effective vehicle for creating momentum for education sector reform in Punjab and monitoring improvements in the education system, and that DFID support has played a central role in facilitating this process over a period of seven years (2011-2018). This is reflected in the achievement of targets set by the Roadmap. The final stocktake against the four high level goals agreed by the previous government was held in March 2018 under the leadership of the outgoing Chief Minister. This stocktake reviewed the performance of Punjab on education roadmap goals since start of the Roadmap in 2011. Except for school construction targets, all other roadmap goals have been met and, in some cases, even exceeded the target. Significant achievements include: increase in school participation rate of 5-9 year olds from 84.8% in November 2011 to 94.9% in 2018; enrolment of 1.6 million more children in public schools since 2012; 1.85 million additional children enrolled in low cost private schools through public private partnerships; the percentage of schools with four and more teachers increased to 87% in April 2018; and a dramatic improvement in early grade literacy and numeracy levels, with Grade 3 students in Punjab attaining an average score of 77% in March 2018 on independently administered six monthly assessment - an increase from 56% in March 2015. Overall, this output has met expectations.

Output Indicator 5.1: B – Milestone moderately did not meet expectations
This indicator tracks the effectiveness of the roadmap routines within the SED. The PD PMIU led 5 data review meetings and the Secretary SED held 6 internal stocktake meetings before the interim government came in. The delivery routines were off track during the period of political transition however re-started in November 2018 and data reviews and the Secretary’s internal stocktake meetings were held in November and December 2018. The Secretary SED and PD PMIU led these meetings to keep track and deliver progress on the SED roadmap targets. The last internal stocktake meeting was held in December 2018 and showed all the indicators on student attendance, teachers' presence, functioning of facilities, primary attendance and retention are on track. The data review meetings helped PMIU to effectively address the issues around the Student Information System, improved verification process of dangerous buildings in schools and strengthened the provincial monitoring framework.

Output Indicator 5.2: A – Milestone met expectations
This indicator tracks the roadmap team’s efforts to develop future priorities for the education sector in Punjab and handover of all the roadmap activities to the new TA team. As part of transition planning, the roadmap team developed three important strategy documents on quality, enrolment and future delivery approach. All these documents fed into the development of the ‘New Deal’ for Education in Punjab. The process involved reviewing the existing roadmap successes, gaps and evidence from local and international practices. The team also held 6 consultative workshops with all the key stakeholders to develop these strategy documents. The roadmap team presented these strategy documents to the SED. The GoPb launched the public version of the New Deal for Education in December 2018.

In response to last year’s annual review recommendations, the Roadmap TA team also completed a detailed training needs assessment of the PMIU and conducted trainings to build the capacity of the PMIU staff. These efforts have been acknowledged by PMIU. The roadmap team has also handed over all the roadmap routines to the new TA team (Cambridge Education) and the government (Special Monitoring Unit). The roadmap team had two months overlap with the CE team and held over 30 sessions (remotely and face-to-face) to handover all roadmap activities and data repository to CE and DA.

Lessons learnt
As this year was a period of transition in government, it was difficult to maintain the expected frequency of delivery routines in part due to a lack of focus on delivery by the government over the election period, a lack of clarity on reform goals and targets for the future, frequent changes in the government’s administrative set-up, and changes within the TA team.

Recommendations
- DFID and TA to work with the new government to find ways of institutionalizing the delivery approach providing the necessary TA to government
- DFID to ensure that there are clearly defined reporting processes in place to ensure systematic and timely feedback on TA’s performance from the SED. This needs to ensure that any problems or concerns with the quality or effectiveness of TA can be identified and addressed quickly and this information is available for the annual review assessment.
- The new TA team should proactively consult with DFID and the SED to agree expectations and a mechanism for handover of knowledge and skills to PMIU or Secretary’s Delivery Unit.

Output Title	High quality technical assistance to government stakeholders that builds sustainable systems and processes
Output number per LF		6	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) 2018-19	Progress
6.1 High quality TA to GoPb	Team mobilised, inception report submitted, and work plan agreed with DFID/GoPb for the implementation phase	A: Milestone met expectations / The inception phase has been completed and workplan agreed with the government
6.2 Capacity building and transfer of knowledge, skills and practices	All knowledge products, progress reports and proposed way forward handed over to DFID in March 2018 and handed over to the new supplier in September 2018.	A: Milestone met expectations / The handover was completed by ASI to DFID since the new supplier was not on board by the time ASI contract ended

Provide supporting narrative for the score
There were two milestones agreed against this output; the first measuring progress made by the new TA (CE) during inception, and the second assessing the quality of the handover of key information by the previous TA team (ASI) to DFID and the government. Progress against both these milestones, and the overall output has met expectations

Output Indicator 6.1: A - met expectations
Cambridge Education started work in September 2018 by mobilising the key team members and engagement with the new government. The key deliverable for the CE team during the two-month inception phase was to set up an office in Lahore, mobilise key members of the team including the leadership and programme management team followed by the result area leads, engagement with the government to agree workplan for the remaining 15 months of the implementation period of the contract. There have been some challenges in mobilising the team as the procurement process took longer and some of the proposed experts were no longer available. Other positions have now been filled but a full-time result area lead for equity is yet to be hired. Similarly, engagement with government counterparts was a challenge as new government took over in August 2018 which was followed by changes in leadership at the SED and other affiliated departments. Despite this challenging environment, the TA team has been able to engage effectively with these departments to align the TA workplan with government priorities. These departments (PEC, QAED, PEF, PCTB) during the meetings with the review team acknowledged the alignment with the TA team and the support provided in various areas.

The TA contract for the World Bank supported Third Punjab Education Sector Project has also been awarded to CE. The TA teams funded by World Bank and DFID are separate and have very clear roles and responsibilities. The focal point for all the TA support is the PMIU, however, the TA teams work directly with the departments.

To avoid any overlap, it is extremely important that the scope of work under the two TA contracts is clearly communicated to the government counterparts and that SED is proactively managing inputs from these TA teams.

Output Indicator 6.2: A - met expectations
The contract with the previous TA supplier (ASI) ended in March last year. A key milestone related to this contract was to compile the progress achieved through the TA support in the form of a final report, and handover of all knowledge products to the new supplier. However due to a prolonged procurement process, the new contract was signed in August 2018 and the new supplier, Cambridge Education could only commence work in September 2018. This resulted in a gap of five months between the two contracts. As a result, the knowledge products and the final progress report were handed over by ASI to DFID. The handover was smooth and timely. ASI submitted a detailed close out report as well as summary documents for all strands of work carried out over four years. The handover was satisfactory and met expectations. Once the new TA contract was signed in September with the Cambridge Education, all information and knowledge products were handed over by DFID to CE.

Lessons learnt
The delay in the procurement of new TA was caused mainly due to additional processes introduced by DFID at the time of procurement for the second round of TA. Since the new processes were just introduced after the supplier review, there was a lack of clarity in terms of timelines, which significantly delayed the outcome of procurement process. Learning from this, programme teams across office need to be fully aware of additional requirements like development of sourcing strategies and approval by the Cabinet Office.

Recommendations
- The TA team needs to move quickly for delivery of agreed workplan as the PESP II programme and the TA contract will be ending in March 2020. This needs to be closely monitored by DFID through joint progress review meetings with the GoPb and the TA team.
- A full time Result Area Lead for equity needs to be hired by CE at the earliest.
- CE should regularly update SED on the role and contribution of the two TA teams funded by DFID and the World Bank to avoid duplication and promote complementarity.
- SED should engage proactively with the TA teams, communicating expectations and managing, coordinating and owning input from TA.
- CE to ensure that their workplan continues to be closely aligned with the new governments’ priorities as outlined in the New Deal.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The programme has evolved as it progressed over years and added a few new activities and outputs focusing on the same outcomes as were planned under the original theory of change. In the last year, the PEEF scholarships component was expanded, a new programme for enrolling adolescent girls in South Punjab through ITA was initiated, and the LUMS scholarship component came to an end. The technical assistance by ASI (2013-18) ended and a new supplier CE started implementing TA from September 2018 up till March 2020. The TA contract with McKinsey to support the education roadmap also ended in December 2018. Some elements of this support will be carried forward through the new TA by Delivery Associates, a sub-contractor to CE. Theory of change remains valid as is evident in achievement of outcome indicators. The assumptions hold largely true and points to an effective programme design with no need for a major shift next year.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Impact indicators: As shown in the table below, the targets on literacy are still to be achieved though the trajectory is positive. The indicators on primary and secondary transition rates have been substantially surpassed and same is true of the GDP growth rate target.

Impact	Target	Achievement
Literacy Rate (Ages 10 and older) and / Adult Literacy Rate (Ages 15 and older)	63% / 60%	60% / 57%
Transition rate in: / a) Primary / b) Secondary	70% (boys) / 68% (girls)	84% (boys & girls) / 94% (boys) / 88% (girls)
Real GDP growth per capita	5%	5.3% (2018)

- 1.6 million more children in government schools since 2012
- Punjab Education Foundation supporting over 3 million children to attend low cost private schools
- Improved learning outcomes for students of Grade 3 from 54% to 90.7% in Urdu, from 55% to 85.1% in English, and from 63% to 92% in Mathematics between March 2015 and December 2018.
- Increased student attendance by more than 15% points from 79% in September 2011 to 94% in December 2018 and teacher attendance by 10% points from 85% to 95.1%.
- 34,014 scholarships awarded to girls from low income households across the 11 priority districts of Punjab for higher secondary and higher education.
- 1,614 classrooms and 903 toilets completed in 442 schools

Outcome indicators: The Punjab School Education Survey was not conducted last year as data on school participation rates is available through the Multiple Indicator Cluster Survey (MICS) conducted last year in Punjab. MICS measures primary participation rate at 94.9% against a target of 95% and secondary participation rate at 79.1% against a target of 84%. Grade 3 student learning outcomes in literacy and numeracy show an average score of 77% against a target of 75%. Student attendance remained above 90% throughout the year.

Outcome Indicator(s)	Target	Achievement
Participation rate for primary school aged population (ages 5-9) / Participation rate for primary school aged population (ages 5-9) in 11 priority districts	Punjab average: 95% / Priority districts: 85%	Punjab average: 94.9% / Priority districts: 82%
Participation rate for secondary school aged population (ages 10-16) / Participation rate for secondary school aged population (ages 10-16) in 11 priority districts	Punjab average: 84% / Priority districts: 74%	Punjab average: 79.1% / Priority districts: 70%
Student learning outcomes: / % students achieving specific Student Learning Objectives (SLOs)	Punjab average: 75%	Punjab average: 77%
Student attendance	92% attendance rate every month (92% boys 92% girls)	On or above 90% every month / 12 month rolling average: 94%

While overall the programme is delivering impact and most of the outcomes are on track, the outcomes pertaining to participation of primary school children in priority southern districts is off track. Similarly, the participation rates for secondary schools’ children also needs improvement. The programme is already addressing these challenges through the programmes for adolescent girls, STRIDE and PEEF scholarships, all focused primarily on south Punjab and shall further strengthen these components. Any future programming should also focus on gender, equity and south Punjab to improve these outcomes. The programme should also advocate for regular stock takes at Ministerial level or higher to ensure regular performance monitoring by political leadership.

Explain major changes to the log frame in the past year
There were no changes at the impact and outcome levels, however, milestones for certain outputs were revised taking into consideration the slow progress due to government transition and a shift in direction due to a change in the provincial government. The milestone for the Punjab Examination Commission was revised as progress slowed down due to a change of leadership during the transition from one government to the interim government, and then to the new government. PEC didn’t have a full time CEO and board of governors during this period. In addition, PEC couldn’t recruit the human resources agreed in the staffing plan to build the institutional capacity.

The milestone for QAED was also revised as the department could not go ahead with planned training of staff due to limited funds available. The milestone for PCTB was also revised as the department decided to continue with the existing textbooks this year. The milestones for PEF were kept as the same as last year as PEF had achieved its expansion plan targets and was unable to launch a fresh enrolment drive due to financial constraints. The milestones to improve equity in access were revised upward due to additional funds provided to PEEF to fund another 20,000 scholarships for girls in secondary schools, and to ITA to support education for 24,000 adolescent girls in three districts of South Punjab. The targets for the school construction component were revised downward based on the findings of the internal review of the programme.

Describe any planned changes to the log frame as a result of this review

Some of the suggested changes to the log frame are as follows:
- Output 1.1: Inclusion of approved job descriptions and key performance indicators for district education managers as next year’s targets.
- Output 1.3: NSB indicator to be revised to reflect’ 60% utilisation of released budget in first 6 months of financial year excluding opening balance’.
Output 3.1: Revision of ‘Functioning facilities’ indicator to capture both functioning as well as required facilities.
- Addition/ amendment of an output under the infrastructure component to reflect targets under any new delivery modality
- Output 4.1 should be segregated into two outputs separately for PEF and ITA.
- Revision of PEF/ITA targets to be ambitious but pragmatic
- Revision of sources of data for impact and outcome level targets so that data is easily available for the next review/PCR.

## D: VALUE FOR MONEY

Assess VFM compared to the proposition in the Business Case, based on the past year
PESP II is at a mature stage. The original VFM proposition in the business case (BC) was outlined in its quantitative cost-benefit analysis, which estimated a strong benefit cost ratio of 1:1.5 – every £1 invested would return £1.50 in benefits. PESP’s monetised benefit estimates were derived solely from increased future wage earnings of the additional graduates funded via PESP II intervention. The payment of higher wages to the graduate is assumed to represent greater productivity on the part of the graduate – so returns are not strictly private. PESP II would increase the number of students enrolled and improve the quality of the education they received in the public and publicly-funded system.

Student enrolment: Overall, VFM performance appears to be matching expectations with achievement of 3.3m additional enrolments against the target of 2.97m during the life of the programme. Targeted PEF funding for lower-performing districts improves the equity of increases in enrolment. The BC estimated that public/publicly-funded enrolment would increase by 2.97m over the project lifetime due to increased investment from DFID, Government of Punjab and other donors. The latest data reveals (TA provided from GoPb data) - for grades 1-10 - enrolment of 9.96m in public schools and 2.75m in (PEF) publicly-funded schools; up from pre-project baselines of 8.2m and 1.2m respectively. Together, this represents a 3.3m increase in enrolment (110% of cumulative target) across publicly-funded schools and means the key outcome - on which the VFM proposition rests - has been delivered.

Scholarships: This component has proved successful in cost-efficiency terms, with more scholarships being granted than estimated besides doubling in family incomes of the scholars immediately after graduation. The business case estimated annual unit costs of £370 for 27,000 PEEF students and £4,500 for 500 LUMS students, however this was revised downward during implementation. Expected wage earnings in Pakistan increase disproportionately for those with higher or tertiary education – this component was estimated to provide robust VFM based on these wage premiums. The LUMS component finished this year and the latest analysis (LUMS-DFID Final Report, Nov 2018) indicates that the 91% of beneficiaries have secured jobs after graduation, earning an average monthly salary of PKR 49,500 (These salaries are in the upper quintile for Pakistan and would be PKR 595,000 (£3700) annually). The latest annual unit cost estimates are £3,990 for LUMS students and these economy and efficiency savings were realized by changes to the funding mechanism and favorable movements in the GBP to PKR exchange rate over the last year. The unit costs for PEEF students are also less then estimated with over 34,000 scholarships awarded (124% of target). Private returns to the beneficiaries are not in doubt but there is a gap before we can assess any desired demonstration effect on families and communities of these beneficiaries. The scholarship component is currently undergoing an independent third-party evaluation and the findings shall inform any future programming.

Infrastructure: Classroom construction has been the weakest performing component of PESP II in VFM terms with the classrooms constructed by IMC at a considerable higher cost then initially estimated. The original VFM proposition for this component was that classrooms could be built of higher quality and at lower cost than classrooms contracted through the GoPb’s own Communication and Works Department. The BC estimated that 15,000 classrooms would be built, and missing facilities installed in thousands of schools with enrolment in those schools increasing by 7% due to increased and improved infrastructure. After several contract amendments, a Performance Improvement Plan and extra review, current estimates are that 4,391 classrooms (29% of original forecast) will be constructed (alongside 1,927 toilets). Currently, 1,702 classrooms and 922 toilets have been completed. Average enrolment increases per classroom constructed (seats 40) is 20, suggesting that half of the extra capacity is used to alleviate current overcrowding. The contract revisions have worsened the ratio of capital works (actual construction costs) over TA (and management fees) and highlights poor efficiency – quality inputs have not led to efficient delivery of construction. IMC argue that poor quality construction firms and lack of redress via the legal system has contributed largely to the inefficiency. Reliable data on GoPb construction costs remains unavailable, the only figures available suggesting PKR 1.8m construction costs per class room (derived from the Roadmap document). IMC’s latest figures on classrooms completed indicate unit costs of PKR 2.7m, which are several times costlier than estimated in the BC and 50% higher than the (unvalidated) GoPb costs.

SED and Budget support: The VFM of SBS depends on both quantitative as well as qualitative parameters like influencing merit-based recruitments or better financial management. Service delivery is implemented at the district level, with remuneration for the public system’s approximately 400,000 teachers constituting the biggest cost driver. DFID’s support to SED of £24.5m in FY17-18 means that DFID financed 1.53% of SED and allied departments current budget expenditure (The 2017-18 current budget expenditure (exclusive of the PKR 52.9bn development expenditure) was PKR 255.5bn. DFID funds calculated at PKR 160:1 GBP were PKR 3.9bn). This financing would support 152,900 students in grades 1-10, at an annual cost of £160 per Government school student. DFID’s support to PEF in FY17-18 represents 11% of the PEF budget, meaning that 284,500 students are being supported through a year of education. This represents an annual unit cost of £49 per PEF student. For reference, the latest data (IFS, 2017) of the cost of educating a UK child for a year (2016) in primary school is £4,900 – this means that 100 students are being educated in PEF schools at the same cost as one child in UK (Institute for Fiscal Studies, Long-run comparisons of spending per pupil across different stages of education, 2017).

Technical Assistance (TA): Value for Money has been attained this year despite the distraction of the election period. The value of PESP’s TA is the provision of high-quality assistance to support the GoPb in reforming the education system and implement its priorities. This last year has brought some disruption to these efforts as the election period, and thereafter the change in Government and the contracting of a new TA supplier have required a re-alignment of support and building of new relationships. The GoPb though there is some challenge in re-instituting the process at top political leadership level. The new TA supplier successfully completed its inception period and support to SED re-commenced in September after the new government was embedded. The TA workplan is now closely aligned with the new GoPb priority areas and has started providing support. VFM savings have been made last year including a contract change

Explain whether and why the programme should continue from a VFM perspective, based on its own merits and in the context of the wider portfolio
PESP II should continue as the programme has been very successful in meeting most of its key objectives and had made a demonstrable impact to the equitable access and quality of education in Pakistan. PESP II aligns with the DFID Pakistan business plan and works to build a more healthy, educated and prosperous Pakistan.

Sustained and improved enrolment within the public and public funded system over the last year are central to the VFM argument. Government schools increased enrolment by 9.2% and PEF schools by 10.3% - well above the (fast) national population growth rate of 2.4% - meaning the pool of children who are out of school decreased over the last year. Moreover, performance targets (Latest Roadmap stocktake data, late 2018) in public schools are being met (and exceeded) with students attending better schools (99.1% have fully functioning facilities) and taught by better teachers (attendance at 95% and 89.9% teaching quality scores). This in turn has contributed to improved student outcomes (94% attendance rate and 77% average marks). Key pre-programme inefficiencies are being overcome and replaced by cost-efficiency gains as teachers are more often in class and there are more students present for them to teach – fewer days are wasted. The increase in competency and outcomes for students indicate the increase in the quality of education for these 10m students; access and quality improving in tandem. These data reference points are only known because of the monitoring undertaken as part of the Roadmap process, which has been hugely successful in helping the Chief Minister and top education leadership drive this reform process.

Overall the success of PEF due to its ability to provide greater access and maintain quality in-line with the costlier public system means that student outcomes are improving at a faster pace than supporting the public system alone would allow. Unit costs for PEEF and LUMS students are less than estimated allowing for increased beneficiary numbers. On the negative side, extra classrooms are needed but the school infrastructure impact has been less than expected and costlier. Robust programme management has seen extra reviews and a performance improvement plan; and negotiated several contract amendments. However, alternative delivery mechanisms should be used to help deliver against the projected number of classrooms.

 Recommendations:

1. DFID to consider continued funding PEF if linked to further expansion plans (Future Programming).
2. Validated classroom cost estimates should be obtained from the Government of Punjab.
3. DFID to assess alternative means of classroom construction.

E: RISK

Overall risk rating: Moderate

Overview of programme risk
The overall level of risk remains moderate. The PESP II team reviews programme risks on a quarterly basis to identify the key risks in each quarter and agree mitigation measures. The current risks to the programme are: overall budget constraints in Punjab, failure to meet targets under SCRP, frequent transfers of government staff at senior level, programme delivery and fiduciary risks.

There is a risk around top political will and ownership of education reforms, particularly following the change of Government last year. However, the education department led by the Minister and new Secretary are leading the reforms with considerable momentum. DFID also continuously engages with the Minister and Secretary Education to keep the reforms momentum going besides advocating for a restart of stocktake process with the top political leadership.

The lack of funds for the departments within SED remains a major delivery challenge. PEF and QAED have not received required funds so far this year which has implications for the programme delivery. The programme team continues to engage with the SED to increase budgetary allocations to these departments.

Classroom construction through IMC continues to fall behind on construction targets. DFID conducted a detailed review of the component and as a result DFID decided to reduce the scope of IMC work through contract amendment. DFID is now considering working with the GoPb to construct additional classrooms.

Another delivery risk is delay in issuance of No Objection Certificates (NOCs) by the government authorities to carry out programme activities in the field. It has adversely affected the progress of ITA against agreed targets for the reporting year. The delay in issuance of NOC of ITA resulted in loss of three months of programme activities. Learning from this experience, the team is proactively supporting the OPM to secure timely NOC for their field work at the district level to complete the performance evaluation of the PESP II programme.

There is a risk associated with the human resourcing of key education departments. SED has had four different Secretaries since August 2018. The heads of PCTB, QAED and PMIU are in place for some time now, however the Director General of QAED has an additional charge for the PEC. The PEC institutional development plan, which includes the staffing plan was delayed during the political transition in 2018. The plan is still being discussed internally by the GoPb and DFID continues to push GoPb to finalise it at the earliest.

Punjab’s latest fiduciary risk assessment suggests that the risks around expenditure controls and independent scrutiny of Government expenditure remain substantial while risk around procurement remains high. There is a strong need to operationalise the Financial Management Cell (FMC) within SED to improve the budget planning and execution. The FMC was established with support from DFID in 2017 but could not sustain beyond DFID support. The government has funds allocated in the current budget to recruit the staff for FMC, however the recruitment could not go ahead due to an appointment ban during the transition government in 2018. The review team reiterated the need to speed up the process to establish the FMC in its meetings with Secretary SED.

On safeguarding, DFID sought assurances from all project partners that the systems are in place to protect staff and beneficiaries. The review team also witnessed that ITA, implementing the PESP II adolescent girls’ education project, displayed safeguarding awareness materials in the learning hubs for students. Earlier this year SED in collaboration with Punjab Information Technology Board launched a hotline for all public schools in Punjab and launched a booklet on child safety to be distributed among teachers and parents to raise awareness on child abuse issues.

Recommendations
- DFID should influence the School Education Department for early operationalisation of the Financial Management Cell.
- DFID should advocate for the allocation of funds by SED to PEF and QAED at the earliest to meet their delivery needs.
- DFID should follow up with SED to finalise the PEC institutional development plan and fill the vacant positions.
- DFID should proactively engage with SED for the timely issuance of NOCs to the programme delivery partners.

Update on partnership principles
The Partnership Principles Assessment (PPA) is regularly discussed with the Economic Affairs Division, Government of Pakistan at the federal level. The PPA was last discussed in March 2018 during our Bilateral Assistance Talks. The PPA sets out DFID’s assessment of the Government of Pakistan’s commitment to the four partnership principles, as demonstrated through its policies and action for reducing poverty and achieving the Sustainable Development Goals (SDGs). These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability.

DFID Pakistan’s overall assessment is that the government is demonstrating a credible commitment to the four principles. The Government of Punjab has increased budget allocation for education by 11.7 percent in FY 2018-19. In terms of sectoral prioritization, the Finance Minister’s budget speech categorically laid down education as the current government’s foremost priority. The GoPb is also demonstrating commitment towards more equitable distribution of resources with approximately 30% of the development budget allocation targeted towards the lowest performing and marginalized districts; providing scholarships for poor deserving children; stipends for girls in secondary school; and education for children working in brick kilns as bonded laborers. It is expected that the active involvement of top tier provincial leadership in SED may lead to other, equally important outcomes, such as improved budget execution rates, timely release by the Finance Department of funds earmarked for the School Education Department and faster implementation of approved projects. DFID can therefore continue to plan and deliver sizeable programming on-budget. Progress towards the SDGs and poverty reduction is proceeding, albeit slowly, given the challenges. Progress on human rights is mixed. The GoPb has taken some steps to remove bias and discriminatory content from textbooks although this remains work in progress. On public financial management and anti-corruption, the direction of travel is broadly neutral, with some improvements in the areas of transparency on budgets, progress on audit and procurement, more openness on corruption and an appetite to tackle this at the highest levels. Finally, the GoPb has demonstrated strong commitment to improving oversight and accountability through the Punjab Education Reform Roadmap and the routine stocktakes where progress across a broad range of issues was being monitored at different levels.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
The support to Chief Minister’s education roadmap was provided by the McKinsey team through a £5 m TA contract from Jan 2016 to Dec 2018. The TA provided through this contract supported analysis and reporting of data collected from field level through the SED, support to the quarterly stocktakes led by the Chief Minister, and the capacity building of the PMIU to continue the monitoring and reporting beyond the life of TA contract. During the reporting period, the delivery routines varied significantly due to changing political situation and national elections. During the first quarter of 2018, the team followed agreed routines including a quarterly stocktake meeting chaired by the former CM, and a six-monthly assessment. During the second quarter, the interim government had taken over the charge, and the focus of the government was mostly on the preparations for the general elections. The only major engagement during the interim government was the quarterly stocktake meeting led by the Chief Secretary in June 2018. During the third quarter, the roadmap team was requested to coordinate the process of drafting an education blue print for Punjab for the next five years, an initiative led by the Education Minister, as well as supporting the education roadmap routines including handover of this work to the Chief Minister’s Special Monitoring Unit and they have already started leading on the data collection and analysis. There were several changes in the roadmap team during the year which led to lack of continuity. The contract has now ended with some handover activities planned to be completed in the first quarter of 2019.

The TA contract with ASI worth £17.9 million ended in March 2018. The contract ended before the end of the overall PESP II programme and a new contract through a fresh procurement process was awarded to a consortium led by Cambridge Education in September 2018 for the final two years of the programme. The overall value of the contract is £6.6 million. This annual review assessed the performance of the supplier during the inception period. The main deliverables during the inception phase were mobilisation of the team and agreeing the workplan with the government. The team has achieved both agreed milestones of the inception period. The contract is now going through a no-cost amendment to incorporate required adjustments identified during the inception period including strengthening district level support through increased number of District Field Coordinators (DFCs). CE had originally proposed 5 DFCs however based on experience from the previous contract, DFID recommended to increase the number of DFCs to 12. The increase in number of DFCs will ensure adequate support to all 36 districts of Punjab. CE has already mobilised their main consortium partner, Delivery Associates and is in the process of mobilising other partners.

Idara-e-Taleem o Aagahi (ITA) was awarded an accountable grant worth £2.5 million to support the education of up to 24,000 adolescent girls in the three underperforming districts of South Punjab including Muzaffargarh, Bahawalpur and Rahimyar Khan. The same accountable grant also covers ITA’s work to compile the Annual Status of Education (ASER) report. There have been delays in starting work due to delay in receiving No Objection Certificates (NOCs) from the GoPb to ITA. The learning hubs have now been established in all three districts and girls are being enrolled through these hubs. The review shows that ITA has good financial management systems both at the head office and field offices. Necessary processes for procurement are in place and followed by the field teams. All major procurement is carried out by the central office in Lahore, while only consumables are purchased locally. Two of the three learning hubs (Muzaffargarh and Bahawalpur) were visited by the review team. The review of progress against the agreed milestones shows that ITA has not been able to meet the agreed targets due to delay in the grant of NOCs by provincial authorities. The enrolment targets were revised down in October considering these delays. However, ITA was not able to achieve the revised targets as well. The team plans to review the progress in March and agree realistic targets with ITA for the final year of the programme. The review also shows that the staff at the field level needs to be better informed about the procedures laid out by DFID to report any fraud and corruption. In addition, an asset spot check of ITA was also conducted in October which shows that the assets procured through this initiative are being used and managed in line with DFID guidance.

Punjab Education Foundation implements the second largest component under PESP II after Sector Budget Support. In total, PEF has an allocation of £78.6 million under PESP II which includes £68 million to support the enrolment under expansion plan targets and another £10 million to enrol 150,000 children in the 11 low performing districts of Punjab. PEF has achieved the expansion plan targets. DFID has disbursed its full financial commitment of £68.6 million under this component. Under the priority districts component, DFID has disbursed £8 million out of a total of £10 million and the remaining £2 million will be disbursed in 2019 against achievement of agreed enrolment targets in the priority districts. However, PEF is facing severe financial constraints as its anticipated budget allocation from GoPb has not been released. PEF has halted new enrolments and will only be able to support the children already enrolled until March 2019 unless additional funds are secured. DFID senior leadership is actively engaging with GoPb to advocate for adequate budget allocation and release.

Punjab Education Endowment Fund has already achieved the target of providing scholarships to girls at the intermediate level. Against an agreed target of 27,500, PEEF awarded over 34,000 scholarships within agreed budget using savings within existing budget. Considering the successful delivery model and availability of funds within PESP II, DFID approved to add £4.49 million to fund another 19,000 scholarships for girls to continue education at the intermediate level this year. The additional scholarships will follow the same standards agreed with PEEF to support the education of girls in 16 districts of Punjab based on merit and need. Previously there have been delays in receiving DFID funds by PEEF due to bureaucratic processes involved. However, PEEF informed the review team that they are expecting quicker disbursement this year.

Oxford Policy Management (OPM) is contracted to conduct the evaluation of PESP II programme. The overall value of the contract is £1.49 m and is a milestone-based contract. OPM has performed well thus far against the agreed milestones. DFID and OPM jointly reviewed and updated some proposed milestones to maximise the impact of the programme as per the findings in the inception report. The number of milestones were increased from 12 to 19 for a better breakdown of activities and deliverables within the same budget.

School construction though IMC Worldwide (IMC) continues to be a challenging component of the programme. During the reporting year a contract amendment (number 8) was processed to reflect the need to bring international monitors to keep track of the construction progress. A detailed internal review of the programme was carried out at the start of the reporting year to evaluate the performance of IMC and recommend a way forward. Based on the findings of the review, in June 2018 DFID decided to reduce the scope of IMC’s contract to include schools that have been already awarded to contractors and ‘low risk’ awards where there is a high degree of confidence that construction can be completed within the next 12 months. This contract amendment is currently under negotiation.

There are significant challenges related to managing forecasts for the IMC contract, with forecasts revised downwards throughout the reporting year as a result of construction delays. It is anticipated that by the end of the current financial year IMC will have spent only £14m out of a forecast budget of £34.5m at the start of the financial year.

Status of financial statements and audit reports:

	PEEF	PEF	ITA	CE	OPM	SED
Date of last narrative/ financial report(s)	Jan 2019	Jun 2018	Nov 2018	Nov 2018	Oct 2018	Apr 2018
Date of last audited annual statement (s)	Jan 2018	Apr 2018

The above-mentioned narrative and financial reports received from partners were in line with agreed programme management routines. Regular feedback has been provided by DFID programme team on the reports submitted and the feedback has been incorporated by partners. The audited reports for the period 2017-18 have been received from PEEF and PEF and do not raise any concerns. The audited reports from ITA, CE, and OPM are expected to be received in the first quarter of 2019. The team plans to follow up to ensure timely receipt of the audited reports. The audited report from SED expected to be received by Dec 2018 is now overdue, and the programme team is following up to ensure that the report is submitted. To note, the initial financial reports from SED have been received, however, the audit report is still with the Auditor General of Pakistan (AGP) for follow up discussions with SED. The audited report will be submitted once approved by AGP and SED.

Recommendations:
- The SCRP/IMC budgets and forecasts for the final year of the programme need to be thoroughly reviewed and agreed with IMC to avoid the high level of variations.
- The flow of funds to PEEF needs to be closely monitored to avoid delays in funds reaching PEEF.
- PEF faces a shortfall of PKR 5 billion to fully support children already enrolled. DFID should carefully monitor and advocate where possible to ensure PEF receives adequate allocation from SED / Finance Department to support the children already enrolled.
- ITA is falling short of achieving the targets revised down in October 2018. These targets were revised considering delay in the start of project activities. DFID should discuss with ITA to adjust the targets to realistic levels considering the remaining duration of programme. The budget needs to be adjusted accordingly.
- CE needs to fully mobilise result area leads and local partners. The position for the equity lead is currently filled on ad hoc basis so a full time expert needs to be hired.
- The KPIs for the TA team (CE) need to be fully aligned with the government priorities. It is an evolving area which needs to be closely monitored.

G: MONITORING, EVIDENCE & LEARNING

Monitoring
The DFID PESP II team (SRO/senior education adviser and programme officers) conducts regular monitoring with all the partners, quarterly monitoring of the risk matrix and VFM framework with the support of a governance adviser and economist.

DFID conducts regular monthly and fortnightly progress review meetings with the technical assistance partners. In the last year the ASI led TA contract came to an end and the new TA was contracted to Cambridge Education in September. There was a gap between the transition from TAMO to the new TA which was partially filled by the Roadmap team. The DFID PESP II Team engaged regularly with the new TA partner CE during their inception phase to bring them up to speed with the new government in place especially developing linkages with the SED. CE has successfully completed its inception phase. DFID continues to engage with them in the implementation phase and monitors progress updates through workplan reviews and progress reports during fortnightly meetings. The CE contract is based on hybrid model that is 65% of inputs and 35% of outputs. This model effectively helps to monitor the inputs utilised in the TA and provides good VFM.

To monitor the progress on Sector Budget Support, DFID conducts Quarterly Steering Committee (QSC) meetings with the SED to assess and review progress with GoPb. This also provides a platform to discuss the Results and Activities Framework (RAF), a framework of disbursement linked indicators agreed between SED and DFID. In the last year, three QSC meetings were conducted. DFID’s SBS support ends in the current year, however, £4.8 million of the SBS funds were reallocated after discussion with SED to support the STRIDE initiative.

DFID conducts regular fortnightly check in meetings with the Roadmap team and receives quarterly progress reports on the workplan. The team was able to support the Chief Minister’s stocktake in March 2018 and later stocktakes led by the Chief Secretary and the Secretary Education. The team also supported the new government in the development of the ‘New Deal’ for school education in Punjab. The Roadmap TA contract has now ended and the final handover/transition to CE has also been completed.

Punjab Education Foundation’s regular monitoring is ensured through DFID’s TA arrangements which worked closely on the Portfolio Risk Assurance Programme (PRAP)[6] action plan. During the phase in the year where TA was not available, DFID team took over the process and closely monitored the progress on PRAP action plan through quarterly progress meetings. DFID also put in place last year a TPV to monitor financial controls and any implementation issues in PEF. The TPV points to gaps in the staffing of PEF, a need for better registration controls of PEF partner schools and better mechanism to deliver textbooks in time. DFID is also providing support to PEF for a strategy refresh and communication and outreach, through the World Bank EFO in the current year.
[6] The PRAP process helps to monitor DFID’s critical programmes on management, risks and quality assures their systems and processes.

PEEF and LUMS are also monitored regularly through quarterly progress reports and regular progress reviews by the programme team. The LUMS grant agreement ended this year and the final report generated shows significant benefits and impact through DFID funding.

The new initiative under Idara-e-Taleem o Aagahi (ITA) started in 2018. The progress on this component has been slow and there are significant delays in the delivery of the project. This component is monitored closely through weekly and monthly progress update meetings besides regular field visits in the districts of Bahawalpur and Muzaffargarh. There is a permanent advisory for DFID to avoid going to Rahimyar Khan district due to security reasons, therefore DFID cannot monitor the progress in this district. DFID will continue to monitor this component closely to assess implementation challenges and delays.

This Annual Review was conducted by DFID Pakistan’s education team through:
1. Desk review of key background documents on the PESP II programme (November 2018). Review of log frame progress with all partners.
2. Visit to Lahore, Multan, Bahawalpur, Muzaffargarh 17-21 December 2018 and 2-4 January 2019. The objective of this visit was to analyse progress made under the different components of PESP II and assess key successes and challenges. The review team met with the senior leadership within the GoPb (Secretary SED, Special Secretary SED, Secretary SpED, Directors of PCTB, QAED, PEC), as well as PEF, PEEF, LUMS, IMC, OPM, Cambridge Education and McKinsey. The review team also visited government primary, middle schools, a PEF school and LUMS.

Evidence
The previous review’s recommendations have been incorporated in the log frame. This has improved the ability to track milestones for outcomes and outputs. [7]
[7] PMIU monthly monitoring data on enrolment, literacy and numeracy, teacher and student attendance, functioning facilities PEF TPV report PESP II First Interim Evaluation Report Pakistan Social and Living Standards Measurement (PSLM) Data Pakistan Economic Survey Punjab School Education Survey (PSES) (formerly known as Nielsen Household Survey) TA quarterly reports Roadmap reports SCRP reports LUMS final report PEEF quarterly reports

Third party validation: Last year DFID has contracted a TPV to monitor PEF. The TPV measured the quality of service delivery in PEF’s Foundation Assisted Schools (FAS), New School Program (NSP), Public School Support Program (PSSP) and Education Voucher Scheme (EVS) programmes. The TPV main findings were that overall the PEF programmes and processes are relevant, efficient, and effective and financial fund flow mechanisms are efficient and traceable. There are some delays in textbooks delivery and a review of criteria for partner school selection is needed. PEF’s enrolment has significantly increased in the last two years, but the recent financial constraint may affect the retention percentage. The TPV also highlighted PEF being significantly understaffed in the M&E and Continuous Professional Development Programme (CPDP) departments.

Evaluation: DFID has contracted OPM to conduct a performance evaluation of PESP II. The evaluation aims to assess the performance of the education system in Punjab over the period of the PESP II programme, and the contribution of the PESP II project components (individually and collectively) to progress in the education sector. The first interim evaluation report provided in October 2018 focuses on providing an interim assessment of the contribution of DFID’s Sector Budget Support, Technical Assistance and support to the Education Roadmap and Stocktake process. This report was rated ‘Green’ by EQUALS[8] which shows good quality of evidence and evaluation resources being utilised.
[8] Evaluation Quality Assurance and Learning Service (EQUALS)

The evaluation confirms that the period since 2013 has seen significant progress in education in Punjab with evidence of increased participation and of improvement in learning outcomes, and that the Roadmap and Stocktake process has provided the main instrument for driving and monitoring improvements in the education system. The main challenge however remains in institutionalisation and sustainability of this process with the new government. The evaluation also presents some useful reflections on the effectiveness of the SBS approach and finds that the way in which SBS was delivered has not provided direct incentives to the organisations responsible for achieving targets since they have not perceived a link between the achievement of targets and the funding they have received. The evaluation report highlights that DFID’s SBS contribution (£70m) may have contributed in higher spending in education sector but it has not helped to increase the overall education budget. Strengthening public financial management has been identified as an area that needs enhanced support. Initiatives based on TA provided do not appear to have been sustained, though some capacity has been built in the system. While TA provided by DFID is assessed to have been largely effective, the evaluation stresses the need for better institutional assessment in designing TA support and a stronger feedback mechanism from beneficiaries so that emerging concerns about TA quality can be addressed timely. Finally, while acknowledging that the programme has supported several targeted interventions that address gender and equity considerations, the evaluation recommends mainstreaming gender and equity across all the different components of the programme to strengthen the focus on equity and gender.

OPM will be conducting its first primary data collection in the next phase of the evaluation in three districts (Rawalpindi, Bhakkar and Rahimyar Khan) with district authorities, and at school and community level. OPM’s second interim evaluation report will be focused on PESP II’s scholarship and PEF components which is now in process.

Learning

Evidence Generated:
A range of processes have been used in PESP II to capture learning and new evidence. At the government level, the stocktake meetings held by the Chief Minister in March 2018 and the Interim Chief Secretary in July 2018 have served as a platform to collate and analyse results from Punjab’s education department. In addition, Quarterly Steering Committee meetings chaired by Secretary SED were used for reviewing of RAF activities as well as to share learning related to technical assistance being provided to different departments of SED.

Evidence is being generated by partners like LUMS, PEF and PEEF monthly through reports, which are shared with DFID. TA has also produced quarterly progress reports to update on TA activities undertaken with DFID support. Progress listed in these reports is discussed by DFID with partners in meetings.

As the evaluation partner, OPM has shared a performance evaluation report of PESP II with DFID and has also held two dissemination workshops with key stakeholders from government and development partners to discuss findings and next steps. As part of this work, OPM has also generated learning by authoring eight background studies:
1. Education Policy and Reform Review;
2. Review of Education Sector Performance;
3. Public Finance for Education Review;
4. Review of Technical Assistance Management Arrangements;
5. TAMO Documentation Review;
6. Case Study of Curriculum;
7. Case Study of Teacher Training;
8. Case Study of Punjab Examination Commission.

The programme has generated wider learning for DFID and development partners on the effectiveness of large sector budget support programmes to deliver outcomes in areas such as student learning, transition, enrolment and attendance rates. For special education departments in Pakistan, this programme has paved the way for enrolment of children with mild special educational needs and disability (SEND) into mainstream schools.

Key Lessons for Programme/DFID and development work:
- The programme was able to ensure regularity and quality of monthly District Review Committee meetings primarily due to the support provided by DFCs as part of PESP II’s technical assistance.
- Non-salary budgets to schools remain a challenge in terms of both timely releases and utilisation.
- Roadmaps and stocktake processes are effective monitoring tools to measure progress but need top political and bureaucratic ownership to be successful and sustained through successive political cycles.
- There is limited capacity at the district level to spearhead reforms in a decentralised set up.
- Transition of government leads to delays in progress on outputs as incoming office bearers require time to get up to speed with previous workflow.
- In the current structure of the district, the AEOs are managed by the SED which leads them to focus more on administration related issues during their school visits. If they were managed by QAED, then there is a possibility of them providing on-going support to teachers and head teachers to drive learning outcomes for students.
- The presence of cultural barriers and limited infrastructure and resources for children with disabilities limits their access to education. Within this group, children with learning disabilities are further marginalised as both public and private schools don’t have the capabilities to detect learning disabilities or to address the needs of children who have learning disabilities. These children are also missed by the programmes under this output. While it is not possible to address this within the one year left in the programme, this should be taken up in any successor programme.
- The first interim report of PESP II evaluation suggests that DFID’s support on roadmap approach and performance-based accountability has been the main tool to deliver and monitor improvements in the education sector in Punjab. The main challenge is for the institutionalisation and sustainability of the performance-based accountability process that continues regardless of political governments.

Learning for upcoming year:
The transition in the Government of Punjab is now complete and with the ministerial priorities becoming clear through the ‘New Deal’, DFID and CE should be exploring new delivery routines with the government.

In the upcoming year, Idara-e-Taleem o Aagahi (ITA) will be providing education to out-of-school adolescent girls in three underperforming districts of Punjab. As this is the first time that such an initiative is part of PESP II, the learning generated around challenges and successes will be useful for DFID and other development partners.

Recommendations:
- DFID to ensure that all programme components have clear approaches to address equity and gender in all aspects, bringing in more focus on these areas. This should be more evident in the evidence gathering.
- DFID to review and update the PESP II log frame to reflect new assumptions and revised targets for the final year.
- DFID to conduct a TPV on Idara Taleem-o-Aagahi component to understand challenges, constraints in the delivery.

Progress on recommendations from previous reviews:
There was mixed progress on recommendations from the previous annual reviews. Under Output One, the recommendation to modify MEA target to make it more realistic was implemented. However, the exit strategy for DFCs still needs to be developed. Similarly, NSB reporting mechanism has improved during the last year but needs further strengthening. Under Output Two, an organisational / staffing plan was developed for Punjab Examination Commission but awaits approval by the competent authority. QAED conducted training evaluations and assessments to better inform its future plans. As per recommendation to strengthen head teachers, QAED trained over 15,000 head teachers during last year.

Under Output Three, the log frame was revised, and IMC was made to update workplans regularly. Additionally, the innovations introduced during construction were reviewed and modified. Under Output Four, PEF strengthened its efforts to enrol out of school children with a 100,000 enrolment target for the year. However, SED, SpED and PEF still need to strengthen their support for children with SEND. Under Output Five, the progress on recommendations for Roadmap remained mixed. The McKinsey roadmap TA team handed over information to the new TA team under CE but transfer of knowledge to Government/ PMIU remained a challenge. Under Output Six, the recommendation regarding smooth handover from ASI to Cambridge Education was reasonably successful.

Under the Monitoring and Evaluation component, the programme revised the log frame in November 2018 as per recommendations. However, there is a need for improvement in gender and equity data collection by partners. The VFM framework was last revised in April 2018 but should be revised more regularly to reflect evolving priorities of the programme.