ANNEX B: SWARIP LOGFRAME (Revise May and June 2014)

PROJECT NAME	Support for West African Regional Integration
IMPACT	Impact Indicator 1		Baseline	Milestone 1	Milestone 2	Target (date)
Reduced costs of doing business in West Africa through better regional integration	GDP growth Rate per annum (%)	Planned	West African average growth rate per annum – 2.5% (2010)	2.5%pa / (2013)	2.5%pa / (2014)	2.5% (2015)	Assumes stable growth rate per annum
		Achieved
			Source World Bank Africa Development Indicators
	Impact Indicator 2		Baseline	Milestone 1	Milestone 2	Target (date)
	Ease of doing Business	ECOWAS countries rankings at 2012	3 WA countries improve rankings (2013)	5 WA countries improve rankings / (2013)	8 WA countries improve rankings (2014)	8 countries improve rankings (2015)	Cumulative total
			Source World Bank’s Doing Business Survey
	Impact Indicator 3		Baseline	Milestone 1	Milestone 2	Target (date)
	ECOWAS average costs of trading across borders (import/export cost per container)	Planned	ECOWAS countries rankings at 2012	3 countries improve rankings (2013)	5 countries improve rankings / (2014)	8 countries improve rankings (2015)	Cumulative total
		Achieved
			Source World Bank’s Doing Business Trading Across Borders Survey (6 indicators in total/2 selected as proxy measures)
OUTCOME	Outcome Indicator 1		Baseline	Milestone 1	Milestone 2	Target (date)	Assumptions
By 2015 (post MDGs), the foundation is in place to help bring West Africa into the CFTA	Implementation status of the West African Free Trade Area and the Continental Free Trade Initiative Road Map	Planned	0 West Africa Member states ready to negotiate CFTA	Nigeria to commit to a roadmapon regional integration / (March 2013)	Nigeria agree roadmap in consultation with up to 5 other West African states / (Sept 2013)	ECOWAS agree to develop a roadmap to join the Continental Free Trade Area, through specific and public commitments to regional integration / (March 2014)	Nigeria accepts lead role in regional and pan-African trade / AU and ECOWAS resolve issues relating to the Sahel
		Achieved
			Source: Annual Report from World Bank on ‘SWARIP’ window of the Trade and Development Multi-Donor Trust Fund; ECOWAS updates on FTA
	Impact Indicator 2		Baseline	Milestone 1	Milestone 2	Target (date)
	Number of ECOWAS countries implementing the ELTS		8 countries (with gap analyses) not fully implementing ECOWAS Trade Liberalisation Scheme (ELTS)	Review process agreed for gap analyses to be reviewed (2013)	1 country makes tangible improvement to achieving implementation of ELTS which are verifiable / (2014)	2 countries (2015) make tangible improvement to achieving implementation of ELTS which are independently verifiable
			Source: West African Trade Hub and ECOWAS Gap Analyses[1]
INPUTS (HR)	DFID (FTEs)
	2 (A2 and B1)
[1] ECOWAS Gap Analyses have been completed for the six BIC border countries—Ghana, Cote d’Ivoire, Burkina Faso, Nigeria, Benin and Togo. The original analyses identified gaps in the implementation of the ECOWAS Trade Liberalization Scheme

OUTPUT 1	Output Indicator 1.1		Baseline	Milestone 1	Milestone 2	Target (date)	Assumptions
Expanded knowledge and policy dialogue on regional integration	West African developing countries applying trade related diagnostic tools (Transport and Trade Facilitation audits, Competitiveness Diagnostics, etc) as developed through the MDTF.	Planned	0 / (Sept 2012)	1 / (March 2013)	3	3 (March 2015)	World Bank deliver research in time for countries to put research into use
		Achieved
	Output Indicator 1.2		Baseline	Milestone 1	Milestone 2	Target (date)
Competitiveness Diagnostics, etc) as developed through the MDTF.	Number of research reports on trade that fill key information and knowledge gaps that are put into use in region		0	0 (2013)	5 (December 2014)	10	Cumulative

		Source:World Bank MDTF Trade and Development Annual report and SWARIP Annual Review; World Bank reports of decision making within country					RISK RATING – High
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£2.5m					100
INPUTS (HR)	DFID (FTEs)
	0.6 (0.3 A2 and 0.3 B1)

OUTPUT 2	Output Indicator 2.1		Baseline	Milestone 1	Milestone 2	Target (date)	Assumptions
Increased private sector and civil society advocacy for regional integration and trade	Output Indicator 2.2		Baseline	Milestone 1	Milestone 2	Target (date)
	Number of West African Governments, PSOs and CSOs receiving support from the Regional Policy Fund	Planned	0 (2012)	0 (2013)	5 (2014)	15 (2015)
		Achieved
IMPACT WEIGHTING (%) / 40%		Source: Regional Policy Fund reports

	Output Indicator 2.3		Baseline	Milestone 1	Milestone 2	Target (date)
	Number of representative bodies for women traders accessing the Regional Policy Fund		0	0	2	5
		Achieved
		Source: Regional Policy Fund Reports					RISK RATING: HIGH
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£650k					100%
INPUTS (HR)	DFID (FTEs)
	0.8 (0.4 A2/0.4 B1)

OUTPUT 3	Output Indicator 3.1		Baseline	Milestone 1	Milestone 2	Target (date)	Assumptions
Effective support in place for regional transport infrastructure and trade facilitation programmes.	Identification of large scale trade facilitation projects through a gap analysis which DFID can support (e.g. the West African Regional Transport Observatory)	Planned	0 projects identified	1 projects identified (2014)	2 projects identified / (2015)	Programme of interventions identified and arrangements in places to support those projects (2015)	DFID has sufficient resources to commit to in the future to projects which will have an impact / Cumulative milestone
		Achieved
		Source: DFID Gap analysis; EU donor support matrix on interventions; ECOWAS strategy documents and reports
							RISK RATING: High
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£80k					100%
INPUTS (HR)	DFID (FTEs)
	0.4 (0.2 A2/0.2 B1)

OUTPUT 4	Output Indicator 1.1		Baseline	Milestone 1	Milestone 2	Target (date)	Assumption
Assessment of effectiveness of the ECOWAS commission in delivering its mandate for regional integration	Effective monitoring of the Pool Fund disbursements made up to end of 2011 in support of ECOWAS’s capacity building needs	Planned	Lack of timely financial reporting and forecasting	Recommendations on whether to resume support to ECOWAS / (October 2012)	Final reports for funding until end 2012	Satisfactory reports and resumption of funding through ECOWAS	ECOWAS maintains commitment to capacity building and conclude their root and branch review by December 2012) / ECOWAS provide accurate information to the Pool Fund Partners which satisfies to point of committing further funding
		Achieved
		Source	ECOWAS quarterly reports and external audits; Assurance report September (2012)

INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	0					100%
INPUTS (HR)	DFID (FTEs)
	0.2 (0.1 A2/0.1 B1)