Annual Review

Title: Neglected Tropical Diseases Implementation Research Programme (NIRP) – COUNTDOWN
Programme Value £ (full life): £8,114,049		Review Date: June 2019
Programme Code: 203089	Start Date: / 1 November 2014	End Date: 31 October 2019

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019
Programme Score	A	A	A	A+	A+	A+
Risk Rating	Minor	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents

A. Summary and Overview (1-2 pages)

Description of programme

COUNTDOWN is a 5 year programme of implementation research (a 2 year extension through to 2021 is close to being finalised) that is led by Liverpool School of Tropical Medicine (LSTM). The programme is focussed on delivering high quality evidence on cost effective, scalable and sustainable solutions necessary to control and eliminate 7 Neglected Tropical Diseases (NTDs) (trachoma, schistosomiasis, elephantiasis, river blindness and three soil transmitted helminths) that together are responsible for 90% of the total global burden of NTDs. COUNTDOWN is currently operating in 4 countries in Sub Saharan Africa (Ghana, Liberia, Nigeria and Cameroon) that have a high prevalence of NTDs. The main pillar of Integrated NTD Control Initiatives is delivery of Mass Drug Administration (MDA) to simultaneously treat and control disease.

COUNTDOWN brings together researchers from a range of backgrounds and disciplines, health care providers, policy makers, laboratory scientists, research uptake specialists, Ministries of Health and Non-Government Development Organisations (NGDOs) and presents an opportunity to bridge the knowledge to implementation gap for shared health impact. COUNTDOWN’s investment in proactive research uptake and co-ordinated communications allows reporting of events often in near real-time. It also consolidates the narrative of research to policy change in an accessible manner, supporting evidence informed policy at district (state), national and international levels. The programme’s efforts to increase the reach and scale up of NTD treatments is important in helping to accelerate progress towards meeting the targets set out in the London Declaration on NTDs.

Summary supporting narrative for the overall score in this review

COUNTDOWN has continued to perform very well this year, scoring A+ on 2 of it’s 3 outputs. Research continues to be of high quality and engagement with key stakeholders in country is aiding the relevance and dissemination of the consortium’s work. As the initial programme period draws to a close, investment in the early part of the programme is beginning to reap dividends as research evidence impacts on policy and practice in partner countries. The extent to which social science and, in particular, a focus on gender and equity, is embedded in the programme is particularly noteworthy. Plans are well underway for a planned extension phase.

Recommendations for the year ahead

- To update/finalise the logframe for the planned extension phase – by 31 August 2019
- That COUNTDOWN increase its focus on cross-country and multidisciplinary products – by 31 May 2020
- To better capture how COUNTDOWN has been effective at building capacity at an institutional level and to disseminate that learning amongst relevant stakeholders - by 31 May 2020
- To advise DFID to any changes in budget forecasts as soon as these become known - ongoing
- To confirm whether pre-paid funds held at LSTM represents only expenditure incurred and/or planned – by 31 July 2017

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)
Output Title	COUNTDOWN generates research evidence to respond to priority information needs of NTD policy makers and programme managers
Output number per LF		1	Output Score	A+
Impact weighting (%):		60	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 NTD implementation research gaps identified	Implementation research conducted to address 5 knowledge gaps for NTD policy makers and programmes.	Met expectations: 6 knowledge gaps addressed
1.2 Number of approved research projects	i) Design: 0 / ii) Implementation: 3 / iii) Analysis/Dissemination: 8 / iv) Completed: 4 Total: 15	Met expectations: 15 approved research projects
1.3 Open access knowledge products	22 peer reviewed articles(cumulative)	Moderately exceeded expectations: 25 open access peer reviewed articles published.
1.4 Open access knowledge products (presentations, blogs, briefs) produced and disseminated	200 knowledge products, including 10 policy briefs, developed and geographic dissemination mapped, including through website download and page views	Moderately exceeded expectations: 248 knowledge products, including 15 policy briefs.

Provide supporting narrative for the score
Output moderately exceeded expectations for. The team have worked on 6 knowledge gaps, to provide evidence to influence the work of NTD policy makers and programmes. These are 1) the extent to which involving state/local government implementers in participatory action research can help identify implementation challenges and so improve planning and promote equity; 2) the extent to which visual images can be used to validate research findings amongst communities with low literacy levels/traditional beliefs and so help shape demand for and acceptance of MDA; 3) the need for an alternative approach to Community Drug Distributors (CDDs) for the Mass Administration of Medicines (MAM) in urban centres where CDDs were perceived to lack sufficient training and skills to dispense; 4) the need for a variety of drug distribution methods (house to house as well as fixed points in communities/schools) to maximise inclusion/control NTDs among at risk populations; 5) the need for a locally owned drug management system to enable people who miss MDA campaigns to access medicines after formal distribution; and 6) the extent to which out of pocket expenditure can impact on the retention of CDDs and teachers within the MAM programme.

Four out of 15 of COUNTDOWN’s research projects are complete. There is some risk to the end survey for the onchocerciases control project, Cameroon, due the security situation although the project has already yielded valuable policy related findings. There have been 8 open access peer reviewed papers over the review period, a further 6 are in draft. COUNTDOWN have exceeded expectations for open access publications overall with a wide variety of publications, policy briefs, presentations, posters and blogs, see https://countdown.lstmed.ac.uk/publications-resources .

Lessons identified this year, and recommendations for the year ahead linked to this output
- Investing time/resources in writing workshops/mentoring for academic/other publications led to a positive shift towards a broader range of lead authors (beyond seniors) across disciplines.
- Open access knowledge products have been effective in disseminating summaries and impact of research findings more timeously.
- Recommendation: COUNTDOWN, as planned, should increase its focus on cross-country and multidisciplinary products.
Output Title	COUNTDOWN supports incorporation of evidence to improve policies and operational plans and practices for scale-up of NTD control
Output number per LF		2	Output Score	A+
Impact weighting (%):		25	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Involvement of key stakeholders at national, state and district level in developing linkages, partnerships, across disciplines, sectors and countries to enhance evidence-based NTD policymaking/programming	COUNTDOWN expands stakeholder network into 4 COUNTDOWN countries and at international level that advocate and manage multi-disciplinary research	Met expectations: engagement with policymakers and practitioners across all 4 COUNTDOWN countries and with the international community
2.2 COUNTDOWN undertakes research uptake and dissemination activities effectively	5 effective activities which led to research uptake/dissemination	Moderately exceeded expectations - 6 effective activities

Briefly describe the output and provide supporting narrative for the score:
Output moderately exceeded expectations. A particular focus has been on synthesising, assessing and updating the often-fragmented literature on NTDs to provide coherent reviews, policy briefs etc to support policymakers’ decision-making. The programme has worked proactively and collaboratively on an ongoing basis with NTD policymakers and programme implementers in partner countries to help maximise the impact of COUNTDOWN generated evidence. In Nigeria, COUNTDOWN is represented on the Federal MoH NTD Programme research sub-committee and has involved NTD actors at Federal, State and Local Government in the design/delivery of research; in Liberia, participatory research design and dissemination at national and county level led to the collaborative development of a national NTD communications strategy. Following publication of a study in Ghana on female genital schistosomiasis (FGS) that identified key gaps in knowledge and understanding of FGS within local communities, COUNTDOWN has facilitated the application of new evidence to programming, developing proposals to update the curriculum for health staff; and also working to launch a national FGS sensitisation campaign on a national TV programme that tackles topical issues affecting communities. COUNTDOWN continues to engage at the international level e.g. by contributing research evidence and case studies to the NGDO Onchocerciasis Elimination blueprint advocacy document; and by contributing to the development and multi-country partner roll out of WHO’s Gender, Equity and Rights Toolkit.

COUNTDOWN has undertaken a wide range of research dissemination activities at national and international level over the year to influence relevant stakeholders/support the uptake of research evidence. These include: in Liberia, dissemination of Countdown’s research findings, at community, county and national level, participation in the national NTD’s review meeting to plan the allocation of programme resources, and the launch, attended by key MoH stakeholders, of the COUNTDOWN-informed NTD Communication Strategy; presentation of COUNTDOWN evidence at a meeting of the UK APPG on malaria and NTDs; attendance at a multi-stakeholder hearing in advance of the UN General Assembly high-level meeting on Universal Health Coverage (UHC); active participation via numerous sessions/posters at the Health Systems Global conference attended by 2400 delegates (52% from LMICs); and active engagement on schistosomiasis control via the Coalition for Operational Research on NTDs ( COR-NTD) conference and meetings with the American Society of Tropical Medicine and Hygiene and the WHO technical working group

Lessons identified this year, and recommendations for the year ahead linked to this output
- A combination of factors - programme length, inclusion of research and research uptake activities, partner composition, and research partners being embedded in local systems – has helped support policy discussion and influence, and is beginning to deliver impact through changes in policy and practice.
- The frequency/extent to which sustained policy engagement/influence can be affected, both positively and negatively, by changes in partner researchers (reliant on grant income) and by political changes.
Output Title	COUNTDOWN strengthens capacity for evidence-based decision making and planning through learning by doing amongst its staff, associated partners and country-based research communities
Output number per LF		3	Output Score	A
Impact weighting (%):		15	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 COUNTDOWN stakeholders engaged in implementation research training	Institutions in at least 4 COUNTDOWN countries demonstrate the impact of improved research capacity through new knowledge, skills, networks, collaborations, funding	Met expectations – completed in all 4 COUNTDOWN countries

Provide supporting narrative for the score

Output expectations, with capacity building activities having taken place across all 4 partner countries.

At an individual level, the focus has been on strengthening partner capacity to conduct, manage, lead, communicate and use research, enhancing skills for developing research ideas, writing, networking, leadership as well as the specifics of health systems and NTD research methodology and analytical approaches. Activities have been focussed around: co-designing projects, jointly analysing findings and co-creating outputs; integrating training, such as paper writing, into COUNTDOWN partner meetings; and organised webinars e.g. on research uptake/the use of social media. Representatives from all partners have attended international conferences and presented COUNTDOWN’s work. The social scientist in Liberia, successfully competed to participate in the prestigious Emerging Voices for Global Health programme that prepares future health leaders from around the world. COUNTDOWN has supported 3 PhD and 4 Masters students and there has been substantial mentorship of younger COUNTDOWN researchers over the last year. As part of their capacity development and to aid their critical thinking skills, 4 junior researchers from Cameroon, Nigeria and Ghana participated in the COUNTDOWN Annual Partners Meeting this year. COUNTDOWN’s capacity building efforts have been received positively by individuals involved.

Organisational and institutional capacity building efforts have been focussed around developing strong independent research groups, able to conduct high quality research and inform policy development. COUNTDOWN partners have successfully leveraged additional funding from various sources including UNDP and the Tropical Diseases Research (TDR) special programme, based at WHO. Improved capacity has been evident at the country level e.g. by the Cameroon team writing and mapping key reference national policy documents such as The Atlas of Schistosomiasis Transmission; and by the Nigerian team who, following training, piloted household surveys in the community to capture some of the impact of the first action research cycle to strengthen the NTD programme.

Lessons identified this year, and recommendations for the year ahead linked to this output
- The extent to which it takes time to build capacity, systems and structures to support and sustain research and dialogue on NTDs and health systems.
- Recommendation: To better capture how COUNTDOWN has been effective at building capacity at an institutional level and to disseminate that learning amongst relevant stakeholders

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year

Countdown’s Theory of Change(ToC) has been slightly amended this year (as underlined in the heavy border box) to capture evolving priorities in preparation for the planned extension. The extension phase will build on COUNTDOWN’s work to date to strengthen, solidify and extend its impact. In particular, there will be a more explicit focus on different contexts/settings, including urban areas, nomadic groups, peri-urban/commuter belt, state border areas and how these contexts impact differently on programme implementation. There will also be a greater focus on multi-sectoral collaboration and public health solutions that span multiple diseases/ health programmes.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The programme is on track to meet its outcomes. Most of the research is now complete in Ghana and Cameroon bringing the initial 5 year plans to a conclusion and extension planning is currently underway with partners in Nigeria and Liberia. Overall, inputs, outputs and outcomes have been largely achieved as planned and, in some cases, exceeded. The extent to which stakeholder engagement has been achieved - from the community to international arena – is particularly noteworthy. In line with the ToC, participation at all phases in the research process has stimulated demand for and interest in research results by programme partners. Less positively, the political context in some countries has led to difficulties in conducting research (most recently in Cameroon with the onchocerciasis control project) and delays in dissemination events. And, it has been difficult to recruit to replace health economists, in part, because there is a shortage of qualified health economists across COUNTDOWN settings but also because of uncertainty over approval of the extension phase (in-house LSTM economists are covering in the interim).

To illustrate progress towards outcomes in the ToC:
COUNTDOWN’s social science research portfolio continues to provide evidence on obstacles impeding access to NTD services and the populations most affected by inequitable coverage. A key learning point has been around the extent to which NTDs that are disfiguring can lead to those affected being excluded from or being unable to fully participate in community and economic activities and the severe impact of these on mental and physical. https://countdown.lstmed.ac.uk/sites/default/files/centre/CS.%201.%20NTD%20related%20stigma%20and%20mental%20health.pdf
https://opendocs.ids.ac.uk/opendocs/handle/123456789/14549
This will be given increased focus during the planned extension phase with the aim of generating evidence that supports inclusion via policy guidelines to ensure that those affected get treatment and can fully participate in day to day life.
COUNTDOWN continues to test innovations designed to achieve greater impact than traditional NTD treatments e.g. to improve onchocerciasis control through complementary ground larviciding (to reduce blackfly biting rate) with doxycycline (rather than the traditional ivermectin) treatment to clear the infection in those affected. The programme has identified factors that would improve the effective delivery of NTD interventions - CDD training, supervision and incentives; drug management; and the development of context appropriate gender equitable information, education, and communication strategies and materials https://countdown.lstmed.ac.uk/sites/default/files/centre/CS.%202.%20Implementing%20Alternative%20Strategies%20for%20Oncho%20Control.pdf
From a cost perspective, COUNTDOWN is assessing the economic burden that NTDs place on households as well as assessing the costs of both MDA and other control/treatment interventions. Combined findings from these studies will enable COUNTDOWN to model the cost-effectiveness of new NTD interventions.
COUNTDOWN continues to make progress in identifying how to improve the acceptability of NTD interventions and thus improve service use, effectiveness and equity. For example, research has revealed that young women seeking care for female genital schistosomiasis have been reprimanded for having a sexually transmitted infection, paving the way for recommendations to improve service quality with a stronger client focus
https://journals.plos.org/plosntds/article?id=10.1371/journal.pntd.0007207

Explain major changes to the logframe in the past year

There have been no changes to the logframe in the past year.

Describe any planned changes to the logframe as a result of this review

There are no planned changes to the logframe as a result of this review; milestone indicators for the planned extension phase have yet to be finalised.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year

COUNTDOWN continues to represent good value for money, consistent with the original business case and the ambition of the 2012 London Declaration on NTDs. The programme has developed expertise in building evidence to help improve NTD control programmes through effective interventions. It remains focussed on identifying the most successful strategies for scale up, including amongst the hardest to reach populations and on identifying factors that influence acceptance, accessibility and affordability. COUNTDOWN has been involved in high level international consultations relating to SDGs and UHC and has responded to technical assistance requests from UNDP and WHO. The programme has helped support the effective capacity building of junior researchers, enabling them, for example, to have presentations accepted and to deliver these at international conferences e.g. hosted by COR-NTD. The key cost drivers are personnel and programme costs.

In terms of DFID’s value for money framework:

Economy: COUNTDOWN works to secure cost-savings for travel and the procurement of consumables to conduct and support research. Cost sharing has been secured for multiple conferences and capacity building opportunities. Robust programme management and procurement procedures are adopted when assessing the purpose/need for expenditure and spend is closely monitored against budget allocations. Sourcing is done cost-effectively and involves reviewing supplier suitability and stringently evaluating quotations to secure value for money. Travel is avoided whenever alternative arrangements using technological solutions are available and feasible.

Efficiency: Through effective planning COUNTDOWN has sought to secure more outputs for less cost, sharing resources in the production of outputs. For example, consortium partners in Ghana are spread across three separate institutions and share support staff, vehicles and other common resources. Meetings are hosted in the most cost-effective venues, often making use of LSTM facilities which are free. Travel costs are minimised by scheduling business to coincide with other meetings/events whenever possible e.g. routine training sessions are often scheduled to coincide with other consortium meetings and dissemination events have been scheduled to coincide with policy makers attending annual meetings or contributing to panel discussions. The leveraging of additional funds from other donors for complementary activities, such as the interrogation of “big data” to develop user-friendly analysis framework for gender equity in MDA further enhances the efficiency of the programme.

Effectiveness: COUNTDOWN has capitalised on the expertise and experience of consortium members and their existing relationship with policy makers to underpin research uptake and ensure the effects of DFID funding is wider-reaching. COUNTDOWN has stimulated debate and thinking among policy makers, practitioners, funders and the communities affected by NTDs, with active consultation with many key stakeholders guided by the programme’s research uptake strategy. In-country partners have provided evidence to health authorities and government, that have led to changes in policy and practice (e.g. to combat the stigma of perceived promiscuity amongst health workers who are treating patients with female genital schistosomiasis in Ghana); and findings from COUNTDOWN have been presented back to communities in innovative ways e.g. through images, so as to enable increased acceptability of NTD programmes and medicines.

Cost Effectiveness: COUNTDOWN continues to be cost-effective and is making good progress towards delivering outcomes. The programme is examining NTD intervention effectiveness from a cost perspective in various settings. Household surveys have assessed the economic burden of NTDs and other investigations, including looking at the cost of both MDA and the alternative strategies COUNTDOWN are exploring. Combined findings from these studies will enable COUNTDOWN to model the cost-effectiveness of new NTD interventions.

Equity: The programme is working to identify and deliver alternative strategies to improve equity of NTD programmes and help ensure universal access to NTD treatment and care, with a priority given to those previously ignored or left behind. For example, in Liberia, communication was identified as a major gap in NTD programming in communities with low education and literacy rates and so multiple methods (including interpersonal communication, large-scale community meetings, the use of town criers and engagement of chiefs and elders) were used to combat limited awareness of NTDs and the drug distribution programme. COUNTDOWN continues to explore how social determinants of health such as age, gender, sexuality and wealth is central to NTD health service delivery and how collaboration and participation can improve outcomes of accessibility to treatment and social wellbeing. This will continue to be a key area of focus during the planned extension phase.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The programme is delivering high quality research and demonstrating impact in NTDs and equity, high priority areas for DFID. The planned 2 year extension will further embed implementation of research results into revised policies and practices, scale up COUNTDOWN’s work on equity and further develop an understanding of NTD control strategies from a cost-effectiveness perspective.

The inclusion of Key Performance Indicators (KPIs) in the contract documents will further enhance value for money in the planned extension phase.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The overall programme risk was recently reviewed and assessed as “Major”.

Context (Major): The main contextual risks relate to: civil unrest and security issues in S.W. Cameroon and parts of Nigeria where ongoing conflict has made research data collection challenging; and a change of Government/leadership. In Cameroon some activities have been delayed whilst in Nigeria an alternative local government area (LGA) to Kaduna was selected to avoid potential unrest. Consortium partners in both countries remain vigilant and are in regular contact with the COUNTDOWN Secretariat to keep them abreast of the security situation. Elections in Liberia and Nigeria in the last year passed relatively smoothly although there have been some changes in key personnel in the MoH in both countries. The new NTD Programme Manager in Nigeria has been briefed on COUNTDOWN and his team continue to provide support and participate in programme activities.

Delivery (Severe): Risks to effective and timely programme delivery over the year have included: DFID delays in finalising the planned contract extension which has resulted in uncertainty for programme partners and, has impacted, for example, on COUNTDOWN’s ability to replace health economists who have moved to other posts; time delays in the publication of peer reviewed articles as journals struggled to source reviewers; and challenges in planning and costing activities associated with MDA which, for a variety of reasons, can be subject to frequent postponements - insufficient drugs available to complete MDA, delays in the receipt of donor funds etc.

Safeguarding (Moderate): All consortium partners have agreed to adhere to safeguarding policies and guidelines. COUNTDOWN is currently working to strengthen country specific documents that outline safeguarding legislation. As part of the COUNTDOWN contract extension process, DFID’s Procurement and Commercial staff have undertaken due diligence on safeguarding issues.

Fiduciary (Moderate): COUNTDOWN use LSTM systems which are considered robust and provide satisfactory assurance that DFID funds are managed appropriately.

Reputational (Moderate): The main risk to DFID’s reputation relates to the lengthy delay in finalising the planned contract extension (under consideration since 2017).

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues

COUNTDOWN has continued to demonstrate good financial acumen. Invoices are received from LSTM within an acceptable timeframe and are always supported by a succinct narrative report which provides DFID with an overview of how the funds have been spent/allocated during the quarter. At the beginning of the 2018/19 financial year COUNTDOWN had been allocated a budget of £2,176,343 which was reduced to £1,869,391 following a re-forecast from COUNTDOWN in September 2018. At the end of the financial year the actual spend was £1,815,615 which equates to an underspend of 3% against the revised forecast or 17% against the original allocation. Recent underspends relate to: unavoidable delays in activities in Cameroon as a result of the security situation there; and delays in bringing to account work that has taken place in Nigeria during 18/19 but not yet reimbursed. The latter will be addressed during the planned extension phase by LSTM insisting on more frequent (monthly rather than quarterly) financial reporting from their Nigerian partner.

To avoid cash-flow issues on the programme, DFID agreed to pre-payments to support activities being undertaken by named southern based downstream partners. It has however been noted that during the 2018/19 fiscal year COUNTDOWN have been reporting a pre-payment figure in the region of £130k. It is not clear whether the amount being held represents only expenditure yet to be incurred or if it also includes an element of expenditure that was incurred during the period of the invoice and has not yet been accounted for by the southern partner. This requires further clarification and, if appropriate, a revision to the value of pre-paid funds held by LSTM.

Over the past year, COUNTDOWN has sought to improve partner programme management, including by tightening management systems and control procedures to more closely monitor outputs in relation to cost. Activity-based budgeting, linked to specific deliverables, is now outlined in contractual workplans. This has been challenging to implement and has required additional capacity strengthening of partner teams to ensure that they can plan, monitor and adapt to changes (implementation research is always moving). A further consideration has been the time required to implement the strengthened procedures, especially for research staff who play multiple roles.

COUNTDOWN continues to respond quickly to ad hoc requests from DFID for information and the data returns provided meets our needs.

It is expected that the planned contract extension will be formalised shortly, however, DFID is conscious of the difficulties that have arisen within COUNTDOWN due to the length of time taken to conclude this extension. In particular, the loss of certain staff and COUNTDOWN’s inability to confidently advertise vacant positions until the extension paperwork is complete.

Part way through the year, COUNTDOWN sought approval for a switch in roles between the named Programme Director and the Programme Coordinator. Following consideration and discussion with COUNTDOWN, DFID agreed to the change, recognising that this would ensure the continued smooth running of the programme and presented the best use of DFID funds. The transition has been seamless.

The most recent Annual Audited Statement (AAS) was unqualified and provided DFID with adequate assurance that funds are being managed appropriately.

All equipment and other programme assets are recorded centrally at LSTM and the asset register is routinely shared with DFID. The asset list is maintained on a quarterly basis drawing on returns from programme partners. The COUNTDOWN programme management team audit these returns, notably during visits to partner institutions.

COUNTDOWN acknowledge their strong links with staff in DFID’s Research and Evidence Division (RED). The programme team has had some engagement with DFID health advisers this year (notably through a “lunch and learn” and meetings with the health adviser in DFID Ghana and the DFID representative in Liberia) but would welcome further opportunities to discuss extension plans, particularly with DFID staff with a knowledge of Nigeria and/or Liberia health systems. RED staff will continue to support and broker such engagement as opportunities arise.

Date of last narrative financial report(s)	30 Apr 2019
Date of last audited annual statement (s)	8 Nov 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring
The annual review was carried out by members of the Health Research Team in RED. Members of the review team had ongoing dialogue and e-mail exchanges with the COUNTDOWN team throughout the year on issues related to invoicing and forecasting, reporting, the contract extension, Health Systems Global conference attendance, the APPG meeting etc. DFID programme staff met in person with COUNTDOWN staff in June 2018 in the margins of a DFID seminar and by telephone in September 2018 and May 2019, to review progress against the workplan, discuss emerging issues, the importance of capturing programme impact etc. DFID advisory staff met in person with COUNTDOWN personnel at the Health Systems Global event in Liverpool in October 2018.

Evidence
COUNTDOWN has continued to generate high quality evidence with potential for impact over the review period. The programme’s work in Cameroon has demonstrated the importance of precision mapping of schistosomiasis in moving away from disease control towards interruption of transmission of the disease in sub-Saharan Africa. Identifying and targeting interventions on disease “hot spots” allows for better and more rational use of preventative chemotherapy drugs and shows promise in shrinking the map and accelerating the elimination of schistosomiasis. In Nigeria, the Participatory Action Research process led to an increase in the number of female CDDs trained and is estimated to have improved therapeutic coverage by 10% due to: increased access to households, improved structures of training processes and timing which aided increased knowledge and understanding, and awareness and acceptability of the programme. Female CDDs were able to gain access to households where men could not. More women were sensitised and, in turn, mobilised other households in the community.

COUNTDOWN recognises how gender shapes equity, poverty and disease experience in multiple ways and, at a basic level. COUNTDOWN disaggregates data and analysis by age and gender. To support more complete gender analysis, COUNTDOWN conducts multi-disciplinary investigations exploring how disease risk, health seeking behaviour, and suitability of services are all influenced by gender role and relations and other axes on inequity.

No evaluation is planned for the programme.

Learning
COUNTDOWN has captured learning across the consortium in various ways over the year, including through: regular management meetings, the annual consortium meeting, dialogue within and across project teams, published products, training events and joint working with partners and stakeholders. A key learning point was around the value and knowledge gained from working closely with communities across all 4 countries – for example, COUNTDOWN used an image of a person with a black bar across their eyes to represent the anonymity of research, but the picture was perceived by the community as representing fear of blindness and death. Further consortium learning has been around: the non-linear nature of research uptake, the multiple leverage points to support that, and the associated timelines; and the huge investment of time and effort needed to develop relationships (multidisciplinary, cross country and cross sector), build capacity and maintain networks for effective research implementation and uptake.

Progress on recommendations from previous reviews

COUNTDOWN provided DFID with detail on programme sites with security issues to aid monitoring.

COUNTDOWN completed a case study on the integration of mental health and healthcare for NTDs.

COUNTDOWN expanded the geographic coverage of their policy briefs this year (i.e. beyond Nigeria) with 3 each from Liberia and Cameroon, 1 from Ghana and 1 cross-country.