Annex 1: Aligned DfiD logframe with JPP M&E Matrix (2011-2014)

Jan 17, 2014
PROJECT TITLE			DFID support to UN Joint Programme on Population, Uganda
GOAL	Indicator 1	Reporting Level		Baseline / (UDHS 2006)		Milestone 2011	Milestone 2012			Milestone 2013			Target 2014
To accelerate the onset of a beneficial demographic transition	Total fertility rate	National	Planned			NA	NA			NA			6.0
			Achieved	6.7		6.2	6.2			6.2
			Source	UDHS and NDP
	Indicator 2	Reporting Level		Baseline (2010)	Milestone 2011		Milestone 2012			Milestone 2013			Target 2014
	Young age dependency ratio (% of working age population)	National	Planned		NA		TBD			TBD			96
			Achieved	99	98		99.5
			Source	World Development Indicators and projections from NDP
	Indicator 3	Reporting Level		Baseline (2010)	Milestone 2011		Milestone 2012			Milestone 2013			Target 2014
	Human development index	National	Planned		0.531		0.541			0.543			0.572
			Achieved	0.422	0.446		0.456
			Source	UNDP Human Development Report and NDP
PURPOSE	Indicator 4	Reporting Level		Baseline / (UDHS 2006)	Milestone 2011		Milestone 2012			Milestone 2013			Target 2014		Assumptions
National, community, cultural and issue-based leadership are managing the acceleration of a downward trend in population growth	Contraceptive prevalence rate (modern methods, reproductive age women)	National	Planned		NA		28.5%			31.0%			33.5%		National economic growth is sustained, including equitable job
			Achieved	18%	26%		26%			26%
			Source	UDHS and Annual Panel Survey
	Indicator 5	Reporting Level		Baseline / (UDHS 2006)	Milestone 2011		Milestone 2012			Milestone 2013		Target 2014
	Teenage pregnancy rate	National	Planned		NA		TBD			TBD		20%
			Achieved	25%	24%		24%			24%
			Source	UDHS
INPUTS (£)[1]	DFID (£)			Govt (£)		Other (£)	Total (£)			DFID SHARE (%)
	30,000,000					58,000,000	88,000,000			34
INPUTS (HR)[2]	DFID (FTEs) / 0.3 x B1D Programme Manager / 0.1 x A2L Programme Manager / 0.1 x A1 Results Adviser / Occasional inputs: / A1 Regional Maternal Health Adviser / A2 Social Development Adviser
OUTPUT 1	Indicator 1.1	Reporting level		Baseline		Milestone 2011		Milestone 2012	Milestone 2013		Target 2014			Assumptions
Fertility reduced in line with the choices of individuals and couples, especially of young people	Proportion of young people (10-24 years) with accurate information on family planning in target districts	15 JPP districts	Planned	N/A		N/A		5%	10%		15%			Broader health sector issues addressed especially around absenteeism. / Funding for contraceptives sustained from other donors and increased by GoU / National Medical Stores improves supply chain processes including to private sector
			Achieved			No data		1.3%	6.1%		N/A
			Source	JPP survey
	Indicator 1.2	Reporting level		Baseline (2010)		Milestone 2011		Milestone 2012	Milestone 2013		Target 2014
	Number of HCIII and HCIV providing youth-friendly services in target districts	15 JPP districts	Planned	5 (HCIV) / 0 (HCIII)		4 (HCIV) / 4 (HCIII)		8 (HCIV) / 35 (HCIII)	10 (HCIV) / 60 (HCIII)		15 (HCIV) / 80 (HCIII)
			Achieved			4 (HCIV) / 5 (HCIII)		6 (HCIV) / 37 (HCIII)	20 (HCIV) / 60 (HCIII)		N/A
			Source	JPP Survey
[1] Financial inputs are calculated here on the basis of UN secured funding already in place for joint programme activities, plus DFID contributions. We assume a UNFPA contribution of USD10m to contraceptive supplies over this period.
[2] HR inputs below Programme Manager level are not output-specific and have not been further broken down by output.

IMPACT WEIGHTING		Indicator 1.3		Reporting level					Baseline			Milestone 2011			Milestone 2012		Milestone 2013			Target 2014
50%		Proportion of health facilities in target districts without stock-outs of 3 most commonly used contraceptive methods (pills, make condoms & de-provera)		15 JPP districts		Planned			N/A			60%			65%		70%			75%
						Achieved						No data			59.5%		74.5%			N/A	RISK RATING
						Source			JPP Survey												Medium
INPUTS (£)		DFID (£)				Govt (£)			Other (£)					Total (£)				DFID SHARE (%)
		18,000,000							13,000,000					31,000,000				58
INPUTS (HR)		DFID (FTEs)
		0.1 x B1D Programme Manager

OUTPUT 2		Indicator 2.1			Reporting level					Baseline (2010)	Milestone 2011				Milestone 2012		Milestone 2013			Target 2014	Assumptions
Prepared, protected and healthy mothers, children and youth		Number of girls retained in school through secondary bursary programme			15 JPP districts		Planned			0	500				1000		1000			1000	Broader health sector issues addressed, including availability of medicines
							Achieved				839				1000		1000			1000
							Source			JPP programme reports
IMPACT WEIGHTING		Indicator 2.2			Reporting level					Baseline (2010)			Milestone 2011			Milestone 2012	Milestone 2013			Target 2014
20%		Percentage deliveries occurring in health facilities in the target districts			15 JPP districts		Planned			NA			34%			39%	46%			50%
							Achieved			NA			37.5%			36.4%	37.9%			49%	RISK RATING
							Source			HMIS and Calculations based on annual expected deliveries											Medium
INPUTS (£)		DFID (£)					Govt (£)			Other (£)				Total (£)					DFID SHARE (%)
		5,500,000								29,000,000				34,000,000					16
INPUTS (HR)		DFID (FTEs)
		0.05 x B1D Programme Manager

OUTPUT 3	Indicator 3.1	Reporting Level			Baseline		Milestone 2011		Milestone 2012			Milestone / 2013		Target / 2014	Assumptions
An improved policy context for youth employment and opportunities	Number of key policy documents developed on youth employment	National	Planned		0		NA		NA			4		4	Sustained economic growth and equitable job creation / Sustained GoU commitment to youth employment promotion
			Achieved				NA		NA			4		4
			Source		JPP Reports
	An institutional mechanism of collection, analysis and exchange of Labour Market Information in place	National	Planned		0	NA				NA		0		1
			Achieved			NA				NA		0		In progress
			Source		JPP Reports
IMPACT WEIGHTING
10%
															RISK RATING
															Low
INPUTS (£)	DFID (£)			Govt (£)				Other (£)			Total (£)		DFID SHARE (%)
	2,000,000							9,000,000			11,000,000		18
INPUTS (HR)	DFID (FTEs)
	0.05 x B1D Programme Manager

OUTPUT 4	Indicator 4.1	Reporting Level		Baseline	Milestone 2011	Milestone 2012	Milestone / 2013	Target / 2014	Assumptions
An adequately resourced, coordinated and managed national population programme	Proportion of target districts allocating and disbursing funds to population issues	15 JPP districts	Planned	N/A	25%	60%	80%	100%	UN agencies dedicate sufficient human resource to joint programme management / GoU commitment to NPP sustained (including implementation of Action Plan)
			Achieved		No data	40%	NA (could not be assessed based on DDP as DDP is a 3-5 year plan. It will be assessed based on District Annual Performance Reports	N/A
			Source	District Annual Performance Reports and data from Ministry of Finance, Planning and Economic Development
IMPACT WEIGHTING	Indicator 4.2	Reporting Level		Baseline	Milestone 2011	Milestone 2012	Milestone / 2013	Target / 2014
20%	Proportion of district development plans (DDPs) developed based on socio-economic, demographic and other data sources	15 JPP districts	Planned	N/A	N/A	60%	95%	100%
			Achieved		No data	87%	87% (figure will remain the same until the DDPs have been revised)	N/A	RISK RATING
			Source	JPP survey					Low
INPUTS (£)	DFID (£)		Govt (£)	Other (£)		Total (£)		DFID SHARE (%)
	4,000,000			7,000,000		11,000,000		36
INPUTS (HR)	DFID (FTEs)
	0.1 x B1D Programme Manager