BLISS LOGICAL FRAMEWORK (Mar 2015)

GOAL	Indicator	Baseline / March 2014	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
A coherent, high quality and sustainable model for English teacher development at secondary level in Bihar which will improve the quality of instruction and ultimately raise the level of English proficiency among both teachers and learners in the state	Classroom practice improves; language confidence and competence increases among Teacher Educators and teachers; state demonstrates capacity to plan, administer and evaluate impact of in-service training programme	198 Teacher Educators (TEs) from all 38 districts selected and 163 complete 24 days initial training to required standard. / 50 TEs train 498 teachers in 3 day pilot training programmes / 38 local officials orientated to programme. / BLISS specific teacher development films completed / first Block of five day teacher training materials piloted in 3 districts.	160 TEs complete 7 day trainer training and CPD orientation programme. / 80 TEs train 1000 teachers in five day programme in 15 districts / 150 local officials orientated to programme / teacher development films edited and workbook completed, with DVD/workbook launch for all TEs. A / All three blocks of five day training complete, with block 1 rolled out across 15 districts.	160 TEs complete second 7 day trainer training and CPD orientation programme. / 120 TEs train in all 30 districts. 2000 teachers will complete Block 1, 1500 Block 2 / 150 local officials 2nd phase of orientation/ professional development input / teacher development films rolled out to 1500 teachers alongside block 2 training / Blocks 1 and 2 five day training materials rolled out in 30 districts	160 TEs complete third 7 day trainer training and CPD orientation programme. / 160 TEs train in all 38 districts. 2000 teachers to have complete Blocks 1 & 2 training / 35 mentors selected and initial 5 day training programme / teacher development films rolled out to 2000 teachers alongside block 2 training. Films and workbooks available for download from British Council and Bihar government websites / Blocks 1, 2 & 3 five day training materials rolled out in all 38 districts. Materials made publically available on British Council and Bihar government websites	160 TEs will have trained 3,200 teachers in every district in the state in 3 phases of 5 day training programme. / Training for phases including 1,200 teachers organised independently of British Council support by state and TEs / 35 mentors complete second phase of 5 day training and shadowing programme. Mentors observe/report on final phases of training / teacher development films available as mobile app / state government agree three year English teacher development plan for teachers across state, utilising resources developed and trained TEs and mentors.
		Source
		Project reports / Independent evaluation

PURPOSE	Indicator	Baseline / March 2014	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017	Assumptions and Risks
English language teachers and teacher educators will have the necessary language and practical teaching skills to achieve the NCF (2005) and BCF (2008) goals, working within a supportive and systemised professional development framework.	% of Teacher Educators language, teaching and training skills to agreed standards	Baseline study complete, data under review and to be updated end March 2015.	50% of TEs meet agreed teaching standards.[1] / 40% of TEs[2] meet agreed standards conducting training. / 70% of TEs show demonstrable improvement in language test with 50% moving one level higher on CEFR scale[3]	60% of TEs meet agreed standards conducting training / (teaching and language not observed / tested in this period)	70% of TEs meet agreed teaching standards. / 70% of TEs meet agreed standards conducting training / 80% of TEs show demonstrable improvement in language test with 70% moving one level higher on CEFR scale	80% of TEs teaching to agreed standards. / 80% of TEs meet agreed standards conducting training / (language not tested in this period)	Security situation in Bihar is stable and does not limit the reach of project activities. / Political change and transfer of key officials does not disrupt implementation due to strong local level relationships and joint planning / Local stakeholder commitment and buy-in, as well as strong communications, leads to positive implementation on the ground / Outside influences (e.g., media, opinion leaders, role models) support implementation. / Stakeholders see the value in monitoring and evaluation and create time for it, and for the discussions around the learning and feedback. / Impact is sustained beyond the lifetime of the project on withdrawl of British Council and DFID direct support.
		Source
		Aptis test scores / Classroom/ training room observation reports / Independent evaluation
	Indicator	Baseline / March 2014	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
	% of teachers language and teaching skills to agreed standards	Baseline study complete, data under review and to be updated March 2015	Nil (classroom observations of teachers not conducted in this period)	25% of teachers meet agreed teaching standards after one phase of training input.	40% of teachers meet agreed teaching standards after two phases of training input.	60% of teachers meet agreed teaching standards after three phases of training input. / 40% teachers tested show demonstrable improvement in language test.
		Source
		Aptis (link) test scores / Classroom/ training room observation reports / Independent evaluation
[1] Summary of agreed teaching standards: 1. Teacher has a lesson plan which enables learners to practice language skills (Reading, writing, speaking and listening) 2. Teacher uses English in their lesson at least 50% of the time 3. Teacher creates a positive learning environment, encouraging interactive and communicative learning 4. Learners are encouraged to interact and are involved in learner centered activities 5. Lesson includes a mix of activities and practices language skills 6. Teacher is able to reflect on their lesson, identifying strengths and areas for development.
[2] Summary of agreed training standards: 1. Trainer plans courses and sessions in advance to ensure preparedness for meeting participants’ needs 2. Trainer uses interactive training methodology in their sessions, encouraging participation and teacher reflection 3. Trainer creates opportunities for participants to interact with each other and encourages the use English throughout the session 4. Teachers are encouraged to interact and are involved in learner centered activities 5. Trainer gives generally appropriate feedback as well as appropriate encouragement and praise (verbal and/or through gestures) to participants 6. Trainer is able to reflect on their training session, identifying strengths and areas for development.
[3] Common European Framework of Reference (CEFR) Proficient User	C2	Can understand with ease virtually everything heard or read. Can summarise information from different spoken and written sources, reconstructing arguments and accounts in a coherent presentation. Can express him/herself spontaneously, very fluently and precisely, differentiating finer shades of meaning even in more complex situations. C1	Can understand a wide range of demanding, longer texts, and recognise implicit meaning. Can express him/herself fluently and spontaneously without much obvious searching for expressions. Can use language flexibly and effectively for social, academic and professional purposes. Can produce clear, well-structured, detailed text on complex subjects, showing controlled use of organisational patterns, connectors and cohesive devices. Independent User	B2	Can understand the main ideas of complex text on both concrete and abstract topics, including technical discussions in his/her field of specialisation. Can interact with a degree of fluency and spontaneity that makes regular interaction with native speakers quite possible without strain for either party. Can produce clear, detailed text on a wide range of subjects and explain a viewpoint on a topical issue giving the advantages and disadvantages of various options. B1	Can understand the main points of clear standard input on familiar matters regularly encountered in work, school, leisure, etc. Can deal with most situations likely to arise whilst travelling in an area where the language is spoken. Can produce simple connected text on topics which are familiar or of personal interest. Can describe experiences and events, dreams, hopes & ambitions and briefly give reasons and explanations for opinions and plans. Basic User	A2	Can understand sentences and frequently used expressions related to areas of most immediate relevance (e.g. very basic personal and family information, shopping, local geography, employment). Can communicate in simple and routine tasks requiring a simple and direct exchange of information on familiar and routine matters. Can describe in simple terms aspects of his/her background, immediate environment and matters in areas of immediate need. A1	Can understand and use familiar everyday expressions and very basic phrases aimed at the satisfaction of needs of a concrete type. Can introduce him/herself and others and can ask and answer questions about personal details such as where he/she lives, people he/she knows and things he/she has. Can interact in a simple way provided the other person talks slowly and clearly and is prepared to help.

OUTPUT 1	Indicator 1.1	Baseline / March 2014	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017	Assumptions and Risks
Development of a cadre of trained English language teachers, teacher educators, mentors & head teachers in secondary schools	Number of teacher educators and mentors selected and trained to agreed standards	198 TEs selected from 38 districts. 163 TEs complete initial 24 training course focussed on learning centred methodologies and language proficiency.	160 TEs complete Block 1 trainer training and 80 delivery of course to teachers in their districts. 40% of TEs meet agreed standards conducting training.	160 TEs complete trainer training and 120 delivery of blocks 1-2 course. 60% of TEs meet agreed standards conducting training	160 TEs complete third 7 day trainer training programme and 70% of TEs meet agreed standards conducting training / 35 mentors selected and complete initial 5 day training programme	160 TEs complete and delivery of blocks 1-2 course. 80% of TEs meet agreed standards conducting training. / Mentors complete second phase of 5 day training. 80% of mentors certified.	TEs and headteachers/officials understand the need to change teaching practice and believe that methodologies recommended will lead to learner gains. / Head Teachers, TEs and teachers grasp the concept of self-directed CPD, and are ultimately able to self-assess, plan and track their own progress. / Head teachers and local officials value the approach and encourage TEs to use the methodology and framework developed by the project. / TEs understand and are able to implement child-centred approaches. / English competence of educators is sufficient to maximise learning from training courses and use of support materials. / Training capacity and skills and materials meet quality standards in order to achieve the aims of the project. / TEs and teachers are motivated to improve their language ability and change classroom practice.
		Source
		Project monitoring and evaluation reports / Attendance records
	Indicator 1.2	Baseline / March 2014	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
	Number/duration of teacher educator and mentor development courses completed to agreed standards[4].	163 TEs x 7.5 days foundation training developing pedagogical skills, subject knowledge & language development	160 TEs complete 7 day trainer training and CPD orientation programme.	160 TEs complete (additional?)7 days trainer training and CPD orientation programme.	160 TEs complete 7 days (additional?)trainer training and CPD orientation programme. 35 mentors selected and complete 5 day mentor training	35 mentors selected and complete 5 day mentor training including shadowing of British Council trainers/ evaluators and 80% certified as Mentors
		Source
		Project monitoring and evaluation reports / Attendance records / Independent evaluation
	Indicator 1.3	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
	Number of officials (DPOs/ DEOs/ ARP[5]), Head Teachers participating in development programmes and manage training programmes	66 officials (DEOs and DPOs) participate in one day orientation to BLISS programme	200 officials (DEO, DPO, ARP) and head teachers[6] participate in one day orientation to district level training in five divisions[7]; joint planning and analysis of their needs	200 officials (DEO, DPO, ARP) and head teachers participate in half day joint planning and analysis for Block 2 training	200 officials (DEO, DPO, ARP) and head teachers participate in two day ‘managing change’ programme focussed on needs identified in earlier workshops	200 officials (DEO, DPO, ARP) and head teachers participate in 2 day joint planning programme for three year state wide in-service training programme; demonstrate capacity to plan and organise INSET training programmes for new teachers as well as facilitation of CPD initiatives for all teachers
IMPACT WEIGHTING		Source
40%		Project monitoring and evaluation reports / Attendance records / Independent evaluation
[4] Course completion requirements - Teacher Educator and mentor training programmes require 90% attendance (residential) - Satisfactory reports from British Council Training Consultants including learning assignments and peer teaching/training reports - Teacher training courses require 80% attendance (non-residential)
[5] DEO = District Education Officer DPO = District Project Officer ARP = Area Resource Person
[6] Head teachers will be those working in schools in which Teacher Educators currently teach
[7] ‘Divisions’ an organisational unit agreed with state government grouping several (5-7) districts together for orientation purposes

OUTPUT 2	Indicator 2.1	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017	Assumptions and Risks
English teachers (Standards IX-XII) will use English in their lessons and provide opportunities for their students to use English in a variety of interactive and meaningful ways that are relevant to their needs and context	Number of districts where teacher training is held and number of teachers attending training courses delivered by BLISS teacher educators.[8]	Baseline study complete (classroom observation and language tests), data under review and to be updated March 2015 / 496 teachers attended three days of pilot training in six districts	1,250 teachers in 25 districts complete 1 phase of training (Block 1) totalling 5 days. Teachers attend minimum 80% of course.	750 teachers in 13 (additional?)districts complete 1 phase of training (Block 1) totalling 5 days. Teachers attend minimum 80% of course.	2000 teachers in 38 districts complete 2nd phase of training (Block 2) and CPD orientation totalling 6 days. Teachers attend minimum 80% of course.	2000 teachers in 38 districts complete 3nd phase of training (Block 3) and CPD orientation totalling 6 days. / 1200 teachers complete Blocks 1-3 training and CPD totalling 17 days. Teachers attend min. 80% of course.	Head teachers value the approach and encourage teachers to use the methodology and framework developed by the project. / Teachers understand the need to change their teaching practice and believe that methodologies recommended will lead to learner gains. / Teachers understand and are able to implement child-centred approaches. / English competence of teachers is sufficient to maximise learning from training courses and use of support materials.
		Source
		Project monitoring and evaluation reports / State attendance records
	Indicator 2.2	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
	% of observed classes shown to be using specified methodology to agreed standards (e.g. use of English, use of group and pair work, activity-based learning)	Baseline study complete, data under review and to be updated March 2015	Nil	25% of teachers meet agreed teaching standards after one phase of training input.	40% of teachers meet agreed teaching standards after two phases of training input.	60% of teachers meet agreed teaching standards after three phases of training input. / 40% teachers tested show demonstrable improvement in language test.
		Source
		Project monitoring and evaluation reports / Attendance records / Independent evaluation
IMPACT WEIGHTING
30%
[8] Teacher training at district level will be rolled out in phases: - Year 1: 1250 teachers in 25 districts will have completed Block 1 training - Year 2: 2000 teachers in 38 teachers will have completed Block 1 & 2 training - Year 3: 3200 teachers will have completed Block 1-3 training

OUTPUT 3	Indicator 3.1	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017	Assumptions and Risks
Accessible bank of high quality resources available to develop professional practice of teacher educators and teachers	15 day (3 blocks of 5 days) BLISS specific teacher development course developed: % recommendation, quality, and relevance to context ratings in questionnaires	Block 1 piloted in 3 districts with 496 teachers	Block 1 & 2 completed. TEs orientated to Block 1 and rolled out across 25 districts to 1000 teachers. 80% favourability across all ratings.	Block 3 completed. Block 1 rolled out in 13 districts to 750 teachers; TEs orientated to Block 2. / 80% favourability across all ratings	Block 2 and rolled out across 38 districts to 2000 teachers. TEs orientated to Block 3. 80% favourability across all ratings.	Blocks 1, 2, 3 completed in all 38 districts with 3,200 teachers; 80% favourability across all ratings; All three blocks available on-line as OERs.	BLISS project products and resources are produced according to the agreed timeline. / The digital infrastructure and distribution mechanisms required for self-access learning, both institutionally and on an individual level, is in place so activities can take place as envisaged, with planning taking into account any limitations in such access. / Teacher Educators, teachers and learners see the value in self-access learning materials.
		Source
		Project monitoring and evaluation reports / Independent evaluation of materials
	Indicator 3.2	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
	BLISS specific teacher development (TD) films with supporting notes available in multiple formats (DVD, on-line and mobile): % recommendation, quality, and relevance to context ratings in questionnaires	2 preparation workshops completed for 8 teacher educators and filming completed in 6 districts.	TD films in DVD format and accompanying workbook complete	160 TEs and 200 official orientated to TD films	2,000 teachers orientated to TD films as part of CPD programme; Downloadable web version on-line (BC and Bihar websites). 75% favourability across all ratings.	3,200 teachers orientated to TD films; App version of TD films launched; 5,000 teachers access films via app and/or download; 75% favourability across all ratings
		Source
		Project monitoring and evaluation reports / Independent web monitoring
	Indicator 3.3	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
	Mentor programme, including increased institutional capacity for delivering & monitoring English language teaching and training: % recommendation, quality, and relevance to context ratings	Nil	Nil	Phase 1 5 day programme mentor programme complete	Phase 2 5 day mentoring programme complete. Phase 1 rolled out with selected 40 mentors. / 80% favourability across all ratings.	Phase 2 rolled out with selected 35 mentors. 80% favourability across all ratings. 80% of those selected certified as mentors.
		Source
		Project monitoring and evaluation reports
	Indicator 3.4	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
	Resources for teachers and learners made available in variety of formats: number of teachers and students reached; % recommendation, quality, and relevance to context ratings[9]	160 TEs have access to teachingenglish (TE) print resources	40 teachers and TEs orientated to TE audio resources on DVD with accompanying workbook (pilot); LearnEnglish Schools DVD self-access materials piloted in 10 schools in 2 districts.	(further rollouts not conducted in this period)	160 TEs teachers orientated to TE audio resources on DVD with accompanying workbook; LearnEnglish Schools DVD materials in 50 schools in 8 districts; 75% favourability across all ratings	3,200 teachers have access to teachingenglish print and audio resources; LearnEnglish Schools DVD materials in 300 schools in 12 districts; 75% favourability across all ratings
IMPACT WEIGHTING		Source
15%		Project monitoring and evaluation reports / State records
[9] Teachingenglish (TE) print and audio resources as well as LearnEnglish (LE) Schools have been developed by the British Council India and not specifically as part of BLISS programme.

OUTPUT 4	Indicator 4.1	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017	Assumptions and Risks
An advocacy campaign raises awareness of the importance of English to young people and parents as well as promoting the work and profile of the project. The Bihar state government are committed to a sustained and long-term in-service English teacher development programme and have the capacity to plan and implement the same.	BLISS public events, advocacy materials on the web, television and other media	BLISS stalls at public events (Bihar Diwas and Patna Book Fair, 35,000 visitors); BLISS short (8 min, English version) advocacy film created (7,500 viewers on YouTube).	BLISS stall at Bihar Diwas; BLISS advocacy film (long – 25 mins Hindi version) shown on local terrestrial TV. Convocation event for 50 BLISS TEs.	BLISS advocacy film repeated.	BLISS stall at Bihar Diwas / BLISS advocacy materials for parents and learners distributed at all (3,200) schools.	Parents and learners at secondary level in the state are aware of the BLISS project and its aims. Awareness is raised of the role of English as a skill for employability	Strategy reflects the needs and interests of key stakeholders to gain traction and positively influence education stakeholders and take-up of the project’s approaches and materials. / There is political will to foster greater demand from beneficiaries and to hear and respond to the voice of communities.
		Source
		Project monitoring and evaluation reports
	Indicator 4.2	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
	BLISS research and awareness raising activity for key local stakeholders as well as potential partners locally and internationally for the development of the BLISS programme	1 event held with local officials, NGOs, donor organisations invited to mark one year of BLISS. BLISS presentations at 4 local and international conferences[10] . 100 BLISS TEs / officials attend conferences (TEC – Teacher Educators Conference Hyderabad; IATEFL)	1 event held with local officials, NGOs, donor organisations invited to mark second year of BLISS. 50 BLISS TEs delegates at Teacher Educators Conference (TEC) Hyderabad and presentation on BLISS materials.	Launch event for BLISS teacher development films and training materials with local officials, NGOs, donor organisations invited. Research conducted on ‘Parental Attitudes to English in Education in Bihar’	Launch event launching ‘Parental Attitudes’ research findings.	Project closure event with local officials, NGOs, donor organisations invited.
		Source
		Project monitoring and evaluation reports / Independent media monitoring data; press reports
IMPACT WEIGHTING	Indicator 4.3	Baseline	Milestone 1 / March 2015	Milestone 2 / Sept 2015	Milestone 3 / March 2016	Target / March 2017
15%	Governance structure for BLISS project is established and a sustainable plan for the BLISS project beyond the lifetime of the existing project is agreed and funded.	BLISS steering committee and implementation group established	One formal meeting of BLISS steering committee and 5 meetings of implementation group	One formal meeting of BLISS steering committee and 3 meetings of implementation group; One ‘Partnership Conclave’ held to discuss BLISS impact and potential collaboration	One formal meeting of BLISS steering committee and 3 meetings of implementation group; Second ‘Partnership Conclave’ held developing sustainability plan for BLISS	Two formal meeting of BLISS steering committee sign off three year BLISS English teacher development programme. One funding partner and one delivery partner commit to support BLISS expansion and sustainability.
		Source
		Project monitoring and evaluation reports
[10] BLISS presentations at international and local conferences including: IATEFL Conference, Liverpool (International Association of Teachers of English as a Foreign Language); Asia TESOL Conference, Delhi (Teachers of English to Speakers of Other Languages); ABCI conference, Sao Paulo (Associacao Brasileira de Culturas Inglesas); UK-India English Partnerships Event, British Council London

Additional Notes