Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Lebanon Municipal Service Programme
Programme Value: £5.2 million		Review Date:
Programme Code: 204397	Start Date: March 2014	End Date: March 2015

Summary of Programme Performance
Year	2014	2015
Programme Score	N/A	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

The Lebanon Municipal Service Programme is supporting host communities to contain the consequences and manage the risks associated with regional overspill of Syrian refugees. The UK provided £5 million to UNDP to support municipalities in the most vulnerable areas in Lebanon to provide basic services to communities hosting Syrian refugees. £0.2 million was allocated to support monitoring and improve learning and impact of the programme.

As a result of DFID funding to The Lebanon Municipal Service Programme, the 20 municipalities most affected by the influx of Syrian refugees are now able to provide additional municipal services (such as waste collection, sewerage networks, street lighting, and water, playgrounds and public spaces) to both Lebanese and Syrians. The programme is therefore helping build Lebanese’ confidence in their government’s ability to deliver services and ultimately help reduce community tensions between Lebanese and Syrians. All Lebanese and Syrians in these 20 municipalities (over 500,000) are beneficiaries of the programme.

A DFID / UNDP / MOSA mission in December 2014 reviewed progress in detail and were very satisfied. The December quarterly UNDP report showed strong progress, 6 municipal service projects are fully completed and 3 livelihood (infrastructure) projects are also fully completed, UNDP are forecasting to complete most of the projects by March 2015. 100% of the allocated budget is committed for the coming period.

In January 2015 the UNDP / MOSA / DFID mission agreed changes for any follow on programme based on a review of 2014 performance including a) stronger MRR b) more involvement by MOSA at subnational level c) strengthening conflict mitigation processes.

The programme outputs were designed to be delivered over DFID’s financial year.

On Output 1: (Target municipalities undertake effective community planning) By September 2014 all community planning meetings were held to discuss municipal improvement related to the project. 20 MRR methodology planning prcersses were finalized in the 20 communities and action plans were prepared accordingly. Around 20% of the attendees at the community planning meetings were women.; 100% of the allocated budget was committed to projects in the 20 municipalities.

On Output 2 (Improved and/or expanded municipal services and livelihood initiatives are delivered in target municipalities based on community-driven needs assessments). By September 2014, UNDP were able to commit 100% of the allocated budget. By March 2015 most of the projects are delivered with a remaining of 300,000$ allocated.

A baseline assessment of the project across the 20 municipalities supported by LHSP was comlpeted in 2014 by a UNDP contracted NGO. Additionally, DFID contracted separate monitoring using ‘sense maker’ from an International independent consultancy (Aktis strategy) for the programme The “early findings” of Aktis show that there is some impact on ‘stability / easing of tensions’. Final reports from both will be available in late march 2015..

The Programme Governance by MOSA via the technical committee has been very effective, allowing cross government oversight and effectively steering the project as well as central government oversight os all prjects funded.

Summary of recommendations for the next year

The pilot one year programme with UNDP is a success. MOSA and UNDP have delivered effectively and well.   Therefore the programme should be extended for a further year and additional resources are allocated

A joint Government of Lebanon, UNDP and Donor (including the WB and EU) annual review is commissioned by the MOSA Steering Committee to take place in Lebanon at the end of September / October 2015. The purpose of the review is to reflect on project progress and recommend policy and management actions for the future. DFID will use this as the key evidence base for a potential design of a medium term programme from 2016.

UNDP to explore how to better advise MOSA on the establishment of coordination structures which bring together key Municipal donors under the auspices of the national plans and donor programmes.

DFID to support MOSA and UNDP in think through how to address the monitoring of social stability, as et out in the LCRP, and the contribution being made by this programme to the GoL objectives

DFID to launch the planned ‘action research’ programme to ensure lessons are learnt by all stakeholders from the experiences of this programme.

DFID to work closely with UNDP/GoL/ and the British Embassy Beirut communications team to develop and deliver a full visibility plan.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	4884790
DevTracker Link to Log frame:	4884804

Outline of the programme

The UK provided £5.2 million to UNDP to support municipalities in the poorer areas of Lebanon to provide basic services to communities hosting Syrian refugees. £0.2m of this funding is used for research and monitoring on the impacts of the programme on municipal capacity.

UNHCR estimates that approximately 1.2 million Syrians have sought refuge in Lebanon (March 2015), equal to an approximate increase in the national population of more than 25%. The vast majority of Syrian refugees are staying in urban centres where they share space, resources and services with their Lebanese hosts. The refugee population is dispersed – while there are still no large formal camps, there are estimated to be around 2000 informal settlements across the country. Some municipalities, such as those around Wadi Khalid, have seen their populations double since the start of the conflict in 2011; new neighborhoods of refugees are appearing with little or no municipal planning or services provided. While statistics in Lebanon are difficult to verify, a recent assessment by the World Bank, the UN and the Lebanese government has estimated that the cost over 2012-14 to respond to the surge in demand for public services is $1.1 billion, while the additional cost of restoring services to pre-2010 levels of quality has been estimated at a further $2.5 billion[1].
[1] World Bank, Economic and Social Impact Assessment of the Syrian Crisis, September 2013

The programme addressed the need for increased delivery of municipal services in selected poorer areas of Lebanon which have received significant refugee influxes from Syria: UNDP facilitated community-led planning activities to identify needs, and delivered service improvements according to these priorities. If needs are not addressed, tensions between host and refugee communities are expected to continue to increase, possibly leading to violence and increased instability. This programme built community confidence in government’s ability to work with them to deliver services, and reduced community tensions.

Through this programme we provided finance (managed by UNDP) to selected municipalities in poorer areas of Lebanon hosting large concentrations of Syrians. The funds allowed municipalities, supported by UNDP, to finance additional public services and programmes to help improve living conditions. DFID’s funding was allocated across three areas of Lebanon, comprising 20 of the most vulnerable municipalities. Communities identified priority areas for improvement through a participatory process facilitated by UNDP; UNDP then delivered, in collaboration with municipalities, the required service improvements. Eligible municipal expenditures included activities such as construction and extension of waste water and drainage systems, rehabilitation of school infrastructure, and rehabilitation/maintenance of roads and sidewalks, as well as basic equipment provision.

The programme assisted municipal governments and communities to better manage social tensions though consultations that support planning, implementation and management of activities funded by the programme. Project management support from UNDP helped the Ministry of Social Affairs (MOSA) and other relevant central government agencies and ministries to coordinate project implementation, including participation in national and local coordination mechanisms.

The programme targeted communities most in need. To identify these communities, an indexing methodology was used which combined pre-existing poverty profiles (from a 2008 UNDP-supported national poverty study) with current UNHCR data on refugee concentrations. The overall group includes about 600,000 Lebanese living in 220 municipalities/host communities, and accounts for 85% of refugees and 67% of the poorest Lebanese.

Programme implementation, including financial management, was undertaken by UNDP in collaboration with municipalities, with oversight by the Ministry of Social Affairs (MoSA), which is responsible for managing the national response to the influx of Syrian refugees.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

By September 2014 the implementation of the MRR (the community / municipal planning process) in the 20 municipalities of Bekaa, South and North Lebanon and development of a multi-sectorial municipal action plans for each municipality targeting the identified weaknesses were finalized. According to the action plans, a total of forty eight (48) local development initiatives have been identified to be funded by DFID: 20 projects in Bekaa region, 15 projects in North Lebanon and 13 projects in South Lebanon.

After the identification of the projects based on the pre-defined criteria set in full collaboration with MOSA, project proposals have been formulated targeting different sectors: Livelihood and Basic Services (WASH, Social, Infrastructure, Education, Health and Solid Waste Management).

All project proposals were submitted to the Technical Group of MOSA for approval. All the projects were discussed, approved (some reject for re formulation), delivered and allocated on time.

Overall output score and description

A - Outputs met expectation

Key lessons

Due to their presence in Lebanon since 2006 and their well-established area offices UNDP were able to deliver the projects efficiently on time.

With our support and guidance UNDP managed to work well with the Government of Lebanon at the Beirut level and they were able to work extremely well with the municipalities at the different stages of the projects.

The effective management and support of the MOSA led technical Group has been key to the effective working of the Programme.

Key actions

A joint Government of Lebanon, UNDP and Donor (including the WB and EU) annual review is commissioned by the MOSA Steering Committee to take place in Lebanon at the end of September 2015. The purpose of the review is to reflect on project progress and recommend policy and management actions for the future. DFID will use this as the key evidence base for a potential design of a medium term programme from 2016.

Has the logframe been updated since the last review?

No – a new logframe will be comlpeted for the next year – if extension funding approved.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Target municipalities undertake effective community planning
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of community planning meetings held to discuss municipal improvements related to this project.	19	The MRR was implemented in the 20 municipalities of Bekaa, South and North Lebanon
Percentage attendees at community planning meetings (related to this project) who are women/refugees.	At least 20%	20% of women representing Women groups/NGOs, activists and women stakeholders took part in the planning meetings.
Number of municipalities with local development plans (related to this project) updated/completed in participatory manner.	19	All 20 municipalities completed in a participatory manner action plans and a total of forty eight (48) local development initiatives have been identified
Percentage of residents (who took part in the planning process) are "satisfied or very satisfied" with the process for planning the improvements (related to this project) in their municipality.	50	The data collected by Aktis indicates that the sense of cooperation increased, in the thematic areas of project implementation in all three locations. There was a marked increase (from 10% to 29% of all respondents) in people who expressed a strong sense of cooperation.
Percentage of budget allocated to planned activity spent or committed.	100	100% of the allocated budget has been committed

Key Points

The implementation of the MRR in the 20 municipalities of Bekaa, South and North Lebanon and development of a multi-sectorial municipal action plans for each region targeting the identified vulnerable municipalities were finalized. According to the action plans, a total of forty eight (48) local development initiatives have been identified to be funded by DFID: 20 projects in Bekaa region, 15 projects in North Lebanon and 13 projects in South Lebanon. 20% of the attendees at the community planning meetings were women. 20 municipalities have their local development plans ready for implementation. 100% of the allocated budget has been committed.

We were able to see from reporting, monitoring, our field visits, feedback from the Ministry of Social Affairs and the independent research done by Aktis that the residents who took part in the planning process are satisfied with the process and the improvements in their municipality. In their report on page 12 and 13 Aktis clearly says: ‘In the case of water and sewerage, in the baseline most of the stories were negative, where in the impact assessment the remaining stories were much more positive in nature. In other words, it seems that far fewer people are likely to complain about shortages in these services when they are improved - but instead of relating a positive improvement, they switch their focus to the ‘next most pressing problem’, and relate another negative story. This does not mean that they are not happy to have received the additional service, or do not feel the benefit – simply that they have other problems which continue to negatively affect their lives.’

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

For 2015/2016 we decided to strengthen the MRR process by extending the workshops to 4 days instead of 2 and ensuring close coordination and involvement from the MOSA Regional Offices.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved and/or expanded municipal services and livelihoods initiatives are delivered in target municipalities based on community-driven needs assessments
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	80%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Proportion of municipal service projects identified in community plans which are fully completed	100	100% the municipal service projects has been delivered/committed
Number of direct beneficiaries of completed municipal service projects	Was not agreed	The Number of benefeciaries is over 500 000 which is considered a good VFM
Proportion of livelihoods projects identified in community plans which are fully completed	100	100% of the livelihoods service projects has been delivered/committed
Number of direct beneficiaries of completed livelihoods projects	27 000	Over 40 000 beneficiaries benefited from the livelihoods projects
Percentage of budget allocated to projects spent or committed	100	100% of the budget was spent and committed

Key Points

After the identification of the projects based on the pre-defined criteria set in full collaboration with MoSA, project proposals have been formulated targeting different sectors: Livelihood and Basic Services (WASH, Social, Infrastructure, Education, Health and Solid Waste Management).

The Technical Group of MoSA approved. Among these over the last quarter of 2014, four projects were discussed and approved on the 30th of October 2014 and the remaining two were discussed and approved on the 7th of November 2014 during a second Technical Group meeting.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

We should keep our regular field visits to monitor the progress, the quality and the impact of the projects implemented.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The number of Syrian refugees in the municiplaities the programme is targettting is most of the time substantive compared to the Lebanese population (sometime more than double), and is increasing. As a result there is less funding per capita. Otherwise there have not been other changes to the specific costs and cost drivers identified in the Business Case at programme approval.

VfM performance compared to the original VfM proposition in the business case

No changes.

Assessment of whether the programme continues to represent value for money

Yes - The programme has delivered better than expected.

Quality of financial management

Financial management from UNDP seem very organized and of good quality. UNDP used their international procurement processes which is good and transparent.

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Medium

Medium. UNDP were able to work with GoL, municipalities and deliver ahead of time.

The mitigation strategies of working closely with MOSA and other involved Ministeries has supported programme delivery. As has the Lebanese national policy of creating incentievs to support Municiplaties that are hosting refugees.

Overview of programme risk

The overview programme risk remains medium mainly because of the security situation in Lebanon

Outstanding actions from risk assessment

None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Delivered on time.

Performance of partnership (s)

The partnership with UNDP and the GoL on this programme was fairly smooth enough to deliver in a constructive, effective and on time. We will continure to work with UNDP and the GoL next year almost in the same way.

Asset monitoring and control

N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Independent consultancy (Aktis strategy) primary results show a positive change in reducing tension between the Lebanese host community and the Syrian refugees. Final report expected at the end of March 2015.

Monitoring progress throughout the review period

DFID has done several field visits to monitor the progress of the work. Results were satisfying at all times. We are aiming to increase these visits next year.