END OF TERM EVALUATION FOR STRENGTHENING POLITICAL PARTIES PROJECT IN MALAWI

PROJECT ID: 00071927

DRAFT REPORT

Submitted by

Cliff Bernard Nuwakora (International Consultant)
C/o
CASE International Consultants Ltd
P.O Box 6916
Mukwasi hse, 1st floor, suite W1.5,
Lumumba av, Nakasero
Tel. +256 772 525 661, Kampala Uganda
Email: cliff.nuwakora@gmail.com, cliff@caseconsultug.com
Website: www.caseconsultug.com

November, 2016

ACRONYMS AND ACRONYMS

AWP	Annual Work Plan
CMD	Centre for Multiparty Democracy
CSO	Civil Society Organizations
DFID	United Kingdom Department for International Development
DSA	Daily Subsistence Allowance
FACE	Funding Authorization and certificate of expenditures
GoM	Government of Malawi
HACT	Harmonized Approach to Cash Transfers
ISS	Implementation Support Services
MALGA	Malawi Local Government Association
MEC	Malawi Electoral Commission
MESN	Malawi Electoral Support Network
MGDS	Malawi Government Development Strategy
MHRC	Malawi Human Rights Commission
MoGCSW	Ministry of Gender, Children and Social Welfare
MoJA	Ministry of Justice and Constitutional Affairs
MoLGRD	Ministry of Local Government and Rural Development
NAO	National Audit Office
NDI	National Democratic Institute
NICE	National Initiative for Civic Education
NMID	Netherlands Institute for Multiparty Democracy
PAC	Public Affairs Committee
PEW	Political Empowerment of Women
PPRRA	Political Parties Regulations and Regulations Act
PSC	Project Steering Committee
QPPR	Quarterly Project Progress Reports
RRF	Results and Resources Framework
UNDP	United Nations Development Program
# EXECUTIVE SUMMARY

This Report presents the findings of the terminal evaluation of “Strengthening Political Parties Project- ID: 00071927” that has been implemented by CMD with financial and technical support from UNDP and DFID. This independent assessment was undertaken by Cliff Bernard Nuwakora of CASE International Consultants Ltd between October and December, 2016.
Introduction: The design and implementation of the project was informed by a number of studies that consistently revealed dire gaps in the mult-party political dispensation in Malawi due to economic meltdown evidenced by fuel shortages, rising unemployment, budgetary and foreign exchange constraints as well as failing social services. Therefore, the project was conceived to promote democratic governance by strengthening political parties and creating an enabling legal and regulatory environment for effective operation of political parties in the country. The project was intended to contribute to the realization of UNDAF output 4.1.4 “The national electoral processes and capacities in Malawi Electoral Commission, Civil Society and different arms of government strengthened to ensure peaceful, free and credible national and by-elections” hence contributing to the achievement of UNDAF outcome 4.1 “National institutions foster democratic governance and human rights to promote transparency, accountability, participation and access to justice for all especially women and youth by 2016”.

More specifically, the project focused on achieving five key outputs which were intended to support the realization of the UNDAF output and outcome indicated above. Implemented over a four year period, the project is set to close in 2016 and hence the need for a terminal evaluation to ascertain the project performance in the light of the set outputs and outcomes.

Methodology: The evaluation adopted a mixed methods approach though with a more qualitative leaning in order to facilitate learning. The evaluation utilized data from both primary and secondary sources in order to enhance the validity of the findings. A number of key informant interviews and focus group discussions as well as application of a self-assessment tool were utilized to elicit primary and secondary data. For case studies, the evaluator also visited some two districts of Thylo and Nsanje where he interacted and solicited views from both MPLCs and District Local government authorities. This was in addition to intensive desk review that the evaluator conducted. OECD/DAC evaluation criteria with emphasis on relevance, effectiveness, efficiency, impact and sustainability formed the overall evaluation framework on which the derived conclusions, lessons learnt and recommendations hinge.

Findings
The findings have been presented according to the standard OECD-DAC evaluation criteria so as to respond to the evaluation objectives as specified in the terms of reference for the project evaluation
The evaluation was able to note the following after assessing the design of the project:
- The evaluation noted that the project was largely relevant with a sound intervention logic (see theory of change). The enhanced project relevance was largely achieved by the fact that the project was well informed by empirical studies namely; 1) benchmarking core CMD capacity assessment study and 2) searching for the Holy Grail: exploring the feasibility of political party ideologies in Malawi. These studies coupled with the vast track record of UNDP in promoting good governance globally were key in ensuring relevant project design and implementation.
- The alignment of the project with the national development framework particularly the Malawi Growth and Development Strategy II (2012-2016) and the overall UNDAF programme also ensured enhanced relevance of the project to the development priorities of Malawi.
- However, critical scrutiny of the outcome and outputs in verifiable terms with SMART indicators revealed that that given the nature of the design all output indicators could not fully conform to SMART criteria. This is explained by the fact that where some indicators had quantities as unit of measure, the qualitative elements were not measurable yet were critical to achieving the overall result.
- During the assessment of intervention logic, the evaluation noted that according to the project design, the project documents reviewed illustrate the sequencing logic but the implementation did not follow the sequencing for conclusive results.
- Documents reviewed and respondents interviewed demonstrated anecdotal evidence of high relevancy of the project to the development of intra-party and multiparty democracy because it provided key building blocks of political parties that included among others-capacity building for political parties in dialogue and policy based issue campaigns. The capacity has enabled them function as effective agents for fundamental and sustainable democratic transformation in Malawi. Furthermore, intervention was informed by the existing political dispensation of multiparty and attendant challenges that stifled political parties to deliver on their mandates. For example political parties have been able to marshal support and membership beyond the founding personality’s region, ethnicity and tribal lines unlike the case before the intervention.
- Timelines were operationalized as detailed Annual Work Plans drawn and agreed upon by both the executing agency (UNDP) and implementing partner (CMD). However, evidence from the document review and interviews conducted with stakeholders reveals that some activities were not executed as scheduled and there were also overlaps of the activities in successive work plans. The delays were solely beyond the means of the implementing partner and the executing agency.
- There was significant change in the environment during the project implementation exhibited by change of government in Malawi after the April 2014 elections that saw new leadership taking over office. Change in government not only meant change of leadership but also change in policy direction that affected the progress of project activities -the PPRRA bill that is not yet enacted.
- The evaluation noted that there was adequate monitoring and backstopping of the project by Government and UNDP which played a crucial role in its streamlined implementation. Few hitches noted include: some development partners and UNDP were not constantly on board during implementation as they would surface towards end of the year to monitor and supervise. Reporting mechanism was also destabilized due to delayed releases of funds due to approval procedures whereby even after submission of Quarterly reports in some instances CMD would have to in between prepare again progress report to trigger release of funds.
- UNDP country Office played a crucial role in supporting and management of the project through mobilizing resources and financing as well as risk mitigation. This was done through assessments of the progress of project activities and the financial accountability, scrutinizing the Annual Work Plans and approving processing of the payment and technical support including the recruitment process of the technical personnel
The evaluation of the effectiveness of the project revealed the following:
- The evaluation noted that the project outputs were largely achieved apart from only one; Revised Political Parties Registration and Regulations Act enacted by the National Assembly by December 2014. Effective stakeholder engagement and involvement has been a key factor that has supported enhanced output level achievement. This has in turn facilitated project ownership and acceptability hence favouring activity implementation.
- There has in fact been significant improvement in the way political parties campaigned with focus on articulating issues focused on policies intended to improve the wellbeing of the citizens unlike in the past when it was not the case; and capacity building initiatives conducted in the area of building governance structures were undertaken as prescribed in the work plans among others.
- A lot has changed in terms of the way the political parties relate with each other and the tendency to network and collaborate especially during the collection of views for the PPRRA bill demonstrates high potential for impact of the project.
- Significant initiatives of capacity building seem to have taken root within the political parties themselves and other stake holders; an opportunity of strengthening operations of political parties as well as targeting the special interest groups like women and youth. Most of the political parties that benefited from the initiatives have taken them as part of their modus operandi in their political parties.
The observations and assessment of the Implementation/Efficiency phase of the project revealed the following:
- That there were clear management arrangements to oversee the coordination, financing and actual implementation of the project. UNDP /DFID were able to deliver on their mandate of mobilizing required resources and financing (how much was raised and sources, its adequacy) of the project activities.
- However, the evaluation noted that some activities did not commence on schedule, but there was a quick viable solution devised. This was done by compressing many activities within a short period of time to ensure all the planned activities were accomplished in line with the initial timeline.
- Much as there has been delayed inaction of the review of the PPRRA due to the Ministry of Justice slow pace, CMD embarked on the concerted efforts to lobbying and sought to identify other voices who can urge Government of Malawi to pass the bill. There is fact good progress towards realization of the respective output under this engagement.
Efficiency of the project is demonstrated by the evidence here below:
- There was positive variance between the budgeted funding and expenditure incurred in the four out of five outputs, an indicator of prudence in financial management
- Effective use of resources to produce results and value for money observed in effective use of the resources to ensure that the resources at the project disposal yielded most outputs. For instance, the radio program offered wide coverage as the radio station selected had wide spectrum coverage and the interactive nature of program evoked discussions, attracted wide audience because its scheduled broadcast was prime time
- Value-for-Money was ensured by prudent financial management and auditing practices undertaken by the implementing agency with guidance of UNDP the funding agency. As result, only minor queries were raised in the Audit Report of 2015
- Suitability of selected technologies- the radio was very suitable as it attracted wide, interactive audience that could not be as tenable if the alternative methods like workshops were adopted
- The resource mobilization strategy by UNDP was appropriate. The bringing on board of DFID was indication of the power of UNDP to marshal effective resource mobilization for the project activities.
 Sustainability of the project activities is anchored on the following:
Future CMD programming as provided for in its Strategic Plan 2016-2020 which focuses on more less similar activities as those of the project, is an ideal opportunity for project sustainability. This is further reinforced by the CMD demonstrated technical capacity exemplified in its well qualified staff, and permanent governance structure, focus on niche area which all embrace the sustainability of the project activities. Finally, the CMD 2016-2020 strategy clearly spells out that the principle focus of the five year plan is to ensure that it makes critical inroads in areas of research, institutional capacity development, financial sustainability and strengthening partnerships all geared towards strengthen multiparty democracy in Malawi, which itself is an opportunity for sustainability.

Capacity building initiatives conducted by the project have multiplier effect for the project activities as political parties demonstrated willingness to practice what they had learnt during the capacity building activities especially on advocacy and inter party dialoguing
Women and Youth issues:
A multi-pronged strategies and approaches by the project implementing agency (CMD) to mainstream gender equality targets. Networks initiated have paid off contributing to the project efforts to addressing issue of inclusion of women in politics.
The project also initiated capacity building initiatives for the women and youth leagues of political parties and there are to work with key stakeholders to strengthen legislation and policy on political party registration and electoral processes and mainstreaming issues to do with youth participation in politics.
Lessons learned- the critical lessons learnt are presented here below:
1. Evidence based planning is key in ensuring enhance project relevancy in terms of design and implementation arrangements
2. A project of this stature requires ample time to manage expectations
3. Tailor made designs to address certain aspects is critical for success
4. Mainstreaming results based management is key
5. Dialogue and trust building are key ingradients in promoting democratic governance
6. Documentation of events and activities very key to monitoring and evaluation of project activities
7. Joint monitoring by project stakeholders is a timely measure for corrective action measures and facilitates project success
8. Media is critical and most efficient tool for social transformation whose effects transcends geographical boundaries.
9. Constant consultations with relevant stakeholders during project implementation creates synergy that re-energizes critical project activities
10. Guidance of project steering committee was handy and critical toward end of project life.
11. Pro-active engagement with stakeholders so that they appreciate political environment is important for enlisting critical support.

The evaluation concludes that the project has done the following:
- Made significant in loads towards the realization of the outcome despite the challenging environment in which it was implemented.
- The project addressed the problem for which it was designed. It was able to build the capacity of political parties to meaningfully participate in the democratic processes of the country through interparty dialogue platforms and issues based campaigns as well as the trainings and awareness raising.
- The intended objectives and outputs of the strengthening the political project as outlined in the project document were achieved, both by way of meeting targets and intended results/effects with an exception of the PPRRA act
- The project was in line with defined needs of the political parties and other stakeholders. It can thus be said that it was justified and relevant in both the country context as well as the context of the executing agency (UNDP), implementing partner (CMD) and political parties.
- The implementation of the project generated good lessons that not only inform improvement of the project in the remaining period but also for future programming to support politically sensitive projects of this stature.
Key sustainable aspects of the project are capacity built for political parties and its membership especially the women, youth; CMD itself as the implementing agency through competent staff recruitment as well as knowledge gained by the target beneficiaries.

The evaluation therefore recommends thus:
Future project designs should tailor indicators to verifiable SMART indicators for better measurement of project outcomes
During design of future projects, effort should be made to come out with indicators that are refined in both qualitative and quantitative measurements that corresponds well with SMART indicators for ease of monitoring and evaluation of the results. This experience is drawn from the way some indicators of the project were designed that rendered them fall short of being verified using SMART. For example although quantitative measurements of indicators were critical aspects that could be easily measured they were not robust to bring out the qualitative change which is action oriented in SMART terms.

There should be strict enforcement of selection criteria for targeted beneficiaries of capacity building initiatives to ensure such initiatives yield maximum results
Selection of the targeted beneficiaries of capacity building initiatives should be strictly enforced against set criteria to ensure credible and transparent processes for better results of the initiatives. This recommendation draws from the experience where some people selected to benefit from trainings in election monitoring were illiterate while others lacked interest yet were selected by political parties to represent them. This flaw watered down the otherwise good intentions and ultimately affects delivery on results.
There should be continuous mentoring of political parties by supporting them to practice what they have been trained to do.
Capacity building initiatives focused on in-house management of political parties should be emphasized and continuously supported through mentoring to improve on functioning of political parties. This is because parties that received training have started managing well their in house business like keeping books of accounts and semblance of putting other systems in place. These developments form important building blocks for in house transparency and intraparty democracy.
Future initiatives should exploit and utilize capacity already built by the project to improve on their deliverables
The initiatives Already put in place should not be put to waste but used to enhance further the activities aimed at achieving the project impact. The attempt to link MPLCs with the security committees is positives step that could actually be exploited so that skills and experience of personnel from MPLCs could reinforce the operations of the security committees at first instance. This could go a long way in not only enhancing project activities but also strengthening such budding institutions thereby aiding them to perform their functions better in the forthcoming general elections.
There is need for adequate funding for CMD strategy 2016-2020 to carry on the project related activities in future
The other way to convert the potential into success is to secure and provide adequate funding to the CMD strategic plan 2016-2020. The evaluation noted that the strategy has in place mechanisms and tailored programming to carry the mantle of the project to its success.
There is need to encourage and support the interface between political parties and parliament since they do complementary work
There is need encourage the interface between parties and Parliament since the work performed by these two institutions is complementary. This is the case because political parties provide the vehicle through which candidates get elected to Parliament while the work of Parliament is central to the realization of party policies and party electoral promises.
 There should be institutionalization of political parties as way of promoting good governance within political parties themselves as a way for achieving qualitative change

Promote the establishment of a multi-party system which encourages the emergence, development and institutionalization of democratic, transparent and accountable political parties. The success of the policy function of political parties require the existence of political parties that are properly structured, administered and run with proper structures, processes and systems for critical decision making exercises.
Political parties should undertake in-house research and documentation as a step towards acquiring capacity to meaningfully engage with external stakeholders and ensure informed decision making.
Encourage political parties to establish and deepen their research capacity. While political parties can draw from existing research institutions, think tanks, NGOs and CSOs, they need to have credible in house research capacity which is instrumental in facilitating meaningful engagement with external stakeholders and making critical policy decisions and choices.
There is need to lobby for public funding mechanism to political parties that prove their worth
There is urgent need to lobby for the creation of a public funding mechanism for political parties represented in Parliament for purposes of harnessing their expertise, skills and knowledge in policy development. Parties require access to resources in order to constantly develop a critical mass well versed with matters of public policy inspired by their respective ideological inclinations and perspectives.

There is need to promote engagement between political parties, Parliament and development agencies as way of making the priorities of parties known to potential funders

Promote tripartite engagement between political parties, Parliament and development agencies so that parties get an appreciation of the perspectives of donors on policy issues. This interface would enable development agencies to get a feel of the development priorities that parties feel inclined to act on especially since it is the parties themselves that are critical players in the legislatures.
Future trainings in capacity building should have properly sequenced themes, timely and have wide covering so as have meaningful impact
- The training programs for election monitors should cover all the constituencies and districts and carried out well in advance to avoid rush that is usually not beneficial to both the targeted trainees and the project itself. The calls for better organization and management by polling adequate resources and selecting the right caliber people to undertake the trainings. Wide coverage of any training has an effect on effectiveness of the program ultimately yielding better results
- Background knowledge on the subject matter of any capacity building initiatives should be allotted own module to set the context and tone that enables participants appreciate and follow on matters related to policy formulation, campaigning and advocacy.
- The training programmes should be implemented timely in order to allow for the participants’ undivided attention so as to achieve the desired maximum strategic impact. Integration of the training programme into the electoral cycle is critical if premised on the understanding that elections are not a one off event but rather a process.
- For the sake of sustainability of the programme, it would be imperative to consider funding the development of manuals for each of these modules which the parties may use for reference in their day-to-day engagement as well as use for in house training targeting party cadres that would not directly benefit from CMD’s facilitated training opportunities.
There should be promotion of radio debates to help parties show case their policy positions to a wider audience
Radio debates among parties should be considered as one of the key elements of the programme which would help the parties to showcase their policy positions on various issues to a wider voting public. Radio debates are considered imperative in disseminating party positions on issues widely for two main reasons. Some parties, especially smaller ones, may not have the financial means to disseminate their policy positions widely. The dominance of the oral culture in the country implies that access to the materials would only be restricted to a very small proportion of Malawians who are able to read and write.

Political parties should properly facilitate their agents during election time to ensure they live up to the task at hand
During election time, the political parties should ensure that are represented by the election monitors who are well facilitated in all the polling stations. Good facilitation for agents enables them do a better job of election monitoring.
- For the Bill to be popularised once its passed there is need for Development partners to integrate such post PPs project into their newly planned governance and democratic program interventions especially CMD monitoring the PP in compliance with the Act while NICE can popularise to the masses through National Civic Education framework.
- Need for development of costed multi-media communication strategy for popularising the PPRRA Act hand in hand with the Gender Equality 2015 Act
- Funding release and accountability in future upon UNDP/DFID etc approving the progress reports and QWPs/AWPs funds should be directly disbursed to CMD
- CMD and Political party institutional systems and capacities especially their respective Secretariats still need to be supported due to enormous work ahead especially as the Bill is passed to be able to ensure and monitor PPs compliance etc Other areas for strengthening and support are the IT systems and databases of PPs
- Youth and women wing specific and targeted programs should be designed and developed for strengthening PPs as there was no footprint noticed for roles of important organisations like Young Politicians Union (YPU)
# 1.0 INTRODUCTION AND BACKGROUND
This Report is the final deliverable on the Terms of Reference (TOR) and service contract for the terminal evaluation of “Strengthening Political Parties Project- ID: 00071927” implemented by CMD and supported by UNDP and DFID for a period of 4 years. The report is presented in four chapters, namely; Chapter one presents the introduction and background; Chapter two, the Evaluation Approach covers the evaluation methodology applied, Chapter three, presents the findings of the evaluation, lessons learnt and challenges documented and Chapter four, outlines Conclusions and Recommendations.
## 1.1. National Development Context
Malawi has been practicing multiparty politics since 1993 and the country has made significant strides in consolidating the gains in democracy and development. The government and other stakeholders(Development partners and Civil society) have taken steps to support development of democratic governance through multiparty democratic elections which have been held since 1994. In recent years Malawi has experienced deteriorating social economic conditions, budgetary and foreign exchange constraints, fuel shortages, unemployment and cost of living as well as failing social services. All these threaten to derail the achievements that had earlier on been gained in democratic governance[1].
[1] Project document

The current population of Malawi is estimated to be 18.5 m with 20.5 % youth aged 15-24 years and rest is adult population aged 24 years and above. The population growth rate is 3.3 %. Of the total population, 16.3% live in the urban centers while the majority 83.7% living in rural areas. Literacy rates above age 15 years stand at 65.8 percent, with women lowest at 58.6 percent and male at 73 percent(2015 estimates), maternal mortality rate at very high at 634 deaths /100,000 live births)[2].Poverty headcount and extreme poverty levels have declined significantly since 2005. The country has also experienced improved economic growth averaging 7.5 percent per year. This growth was attributed to a number of initiatives that were implemented aimed at fighting poverty which resulted in the decline of poverty incidence from 50 percent in 2005 to 39 percent in 2009[3].
[2] Malawi Demographics Profile 2016 accessed on 17th November 2016 on www.indexmundi.com/malawi
[3] MDGS II

In regard to gender, Malawi boys and girls, men and women assume culturally different identities and traits. The status is worse among females as compared to their male counterparts. For instance, a female headed household has 14 percent less consumption per capita than a male headed household mainly due to gender based differences in access and control over resources (UN Malawi, 2010). In addition, girls and boys experience some form of GBV during their life time. For example, Burton (2005) showed that 65 percent of girls and 35 percent of boys were subjected to GBV. The experience of violence increases the risk of HIV and other sexually transmitted diseases. In Malawi, HIV prevalence is extremely high at 12.9% among women and girls compared to the national average of 10.6 percent. HIV prevalence among their male counterparts is just at 8.1 percent[4].
[4] DHS 2010

Democratic governance has improved in Malawi and a result the country has experienced positive developments that included successful presidential and parliamentary elections, growing civil society and non-governmental organizations, and deepening constitutionalism. The Malawi Government recognizes the importance of free and fair elections to allow the people to freely choose public office holders. In the recent past, Malawi has progressed in ensuring free and fair elections, especially for the president and parliamentarians. However, inadequate public awareness of the electoral processes and logistical problems remain some of the main challenges[5]. As a consequence, Malawi Development Strategy II takes cognizance of the fact and outlines key strategies to be taken to enhance democratic governance that include: improving governance in political parties; enhancing implementation of law reforms to facilitate free and fair elections at national and local levels; and fostering informed and active participation in local governance among others[6].
[5] MDGS II
[6] MDGS II

Since the introduction of multiparty dispensation in 1994, several political parties were formed and have been participating in national elections independently as well as through some form of electoral alliances. Political parties are regarded as the major instruments for the mobilization of the citizenry in the country and therefore central to the effective functioning of a multiparty democracy. A lot has been happening on the political scene, including lack of intra-party democracy, founder syndrome trends within political parties, lack of interparty democracy, voter apathy, and squabbles over electoral results, violence perpetuated by leaders of political parties, floor-crossing and proliferation of independent candidates during elections. Other occurrences include unstable party alliances, party splits, leadership squabbles, and imposed candidates during primary elections, allegation of rigging, among others[7].
[7] CMD Benchmarking Study July 2011
It was against the above context that UNDP /DFID funded the project that was a brain child of the Centre for Multiparty Democracy (CMD) which later become the implementing agency. United Nations Development Programme (UNDP) country office has the executing agency. The project was initiated to build on existing initiatives as stipulated in the United nations Assistance framework and Malawi Development Strategy II to improve the internal democracy within the parties and interparty dialogue as well foster inclusion of women and youth. It was envisaged that through capacity building activities, the outcome of the project will be realized.
## 1.2. UNDP /DFID
1.2.1 UNDP
The United Nations Development Programme (UNDP) is the United Nations’ global development network, advocating for change and connecting countries to knowledge, expertise, and resources to help people build a better life. The Programme works in 166 countries to generate solutions to national and global development challenges. The organization’s main goal is to help developing countries build their own national capacities to achieve sustainable human development, using its global network to help the UN system and its partners raise awareness on and track development.
For over 50 years, UNDP has made tremendous contributions by providing support to Malawi in programmes These include; governance, gender equality and women empowerment, climate change, disaster risk management, environment and natural resources management, HIV prevention, public sector reform, social cohesion, economic competitiveness and private sector development. Specifically, between 1993 ‐ 2016, the Governance Programme focused interventions Malawi’s transition to multiparty dispensation and support to free and fair elections since 1993 to date.
1.2.2. DFID
Department for International Development (DFID) is the British government department charged with promoting development overseas. It is one of the largest donors in Malawi and has an influential role on development policy and analytical issues. DFID has supported and contributed to the development of Malawi Development Strategy II, building on improving the lives of Malawian citizens especially girls and women, by supporting programs on Health, HIV, Justice and Agriculture. DFID governance work in Malawi has been aimed to promote accountability, responsiveness and capability in the Malawian government while underpinning the plan to ensuring Malawi’s limited resources are used to maximum effect. The activities include empowering local citizens, increasing accountability and space for debate, protecting rights of the vulnerable groups, access to justice, including violence against girls and women and major contribution to the fight against corruption. DFID supported new efforts of the new government to improve governance context and preparing programs of support to 2014 elections and strengthening democratic institutions. DFID three priority areas of work are: addressing poverty and inequality facing large parts of the population; supporting economic growth and wealth creation to turn the economy around and sustainably help the people out of poverty; and promoting good governance in Malawi[8].
[8] DFID Malawi operational plan 2011-2015
1.2.3. CMD
Centre for Multiparty Democracy (CMD) is a civil society organization in Malawi formed in 2003 and registered as Trust in 2005 to act as forum for political dialogue in the country. CMD was established to strengthen and consolidate multiparty democracy that witnessed increased political turmoil emanating from the fact that political parties operated as single and intolerant entities. Evidence were the several incidences of political violence witnessed 1999 and 2004 general elections. As response to t founding a solution to the problem, an ad-hoc multiparty committee was formed which later metamorphosed into CMD. CMD therefore was formed to assist in addressing such issues. The precursor to CMD, the multiparty adhoc committee consisted of active political parties during that time, and these were UDF, MCP, AFORD, MAFUNDE and MDP.
Centre for Multiparty Democracy is mandated to do the following to foster democratic governance in Malawi:
- To be a platform for political dialogue and building of consensus on topical issues amongst political parties;
- To strengthen the capacity of political parties to deepening and consolidating democratic governance in Malawi;
- To engage in advocacy and civic education in order to level playing field for all political parties;
- To foster national unity , peace and reconciliation by mapping out common goals
- To promote gender equality, and effective participation and representation of vulnerable groups; and
- To facilitate in mediation of inter and intraparty conflicts.
## 1.3. Project Background
The Strengthening Political Parties Project was a 4-year project whose goal was to strengthen political parties to effectively participate in Malawi’s multiparty democracy, integrating women and youth groups in political parties’ structures and dialogue. The project had three objectives:
- To revise the Political Parties Registration and Regulations Act (PPRRA);
- To assist political parties to develop issue-based platforms for the 2014 elections; and
- To strengthen inter-party dialogue among political parties.

The project commenced in 2013 and is expected to close in December 2016 with a total estimated cost of USD 2,800,000.00 and out of this USD 1,600,000 was committed. Funding is provided by United Nations Development Program (UNDP) and the Department for International Development (DFID). The project is implemented by the CMD, an inter-party dialogue platform established in 2005.

1.3.1 Problems that the project sought to address
The project was designed to address problems in democratic governance during the multiparty democratic dispensation in Malawi. Specifically various studies (issues study) and previous interventions have identified that political parties in Malawi as weak and more often than not suffered significant gaps in three broad but closely interlinked areas of legal, organizational and administrative management. The challenges in these areas contributed to weak ownership and identification with political parties, deficits in transparency and accountability, lack of interparty dialogue, and intraparty democracy among others and continue to hamper the evolution of political parties into key political actors, impeding progress in the country ‘s burgeoning democracy[9]. The project theory of change in figure 1.1 below gives a summary of the situation analysis prior to the project and how it informed the project design and implementation.
[9] Project document

- Intuitionally weak political parties
- Lack of opportunities for political consultation
- Poor country performance in governance
- Weak ownership & identification with political
- Parties
- Deficits in transparency & accountability

- Large number of ineffective political parties
- Weak legal & regulatory framework of platform
- Lack of political will to implement section 65
- Weak capacity in policy analysis & formulation
- Low women & youth involvement in political processes
Members of political parties & CMD staff
Political party structures & members of national Assembly
Members of political parties
Project management team and entire stakeholder group.
Members of political parties
Targeted Project Beneficiaries
Capacity strengthening for CMD staff & Political Party members .
Improving capacity of political parties in policy development
Review & revision of key building blocks of political parties including constitutions and even the ACT.
Conducting political debates & strengthening inter-party dialogue
Project oversight & management.
Platform for inter-party dialogue strengthened to promote transparency & accountability as well as enhance credibility and legitimacy of political parties at all levels;

Effective and Efficient Management, partnership formation and M&E of the project
Governance structure for political parties developed to foster transparency and accountability by December 2015;

Political Parties' Issue Based platforms for 2014 Elections developed and disseminated;

Revised Political Parties Registration and Regulations Act enacted by the National Assembly by December 2014
Democratic Governance Sector Strategy Operationalized.
National institutions foster democratic governance for all, especially women and children by 2016.
UNDAF Outcome
UNDAF Output
Project Out puts
Project interventions/ activities & strategies
Focal problems the project sought to address
1.3.2. Immediate and development objectives of the project

The immediate objective project was to build the capacity of the political parties in Malawi so as to enable them participate in the multiparty dispensation by engaging in issues based campaigns and inclusiveness of women , youth and other marginalized groups. The project aimed to achieve the following:
- Strengthen political parties project to effectively participate in Malawi’s multiparty democracy,
- integrating women and youth groups in political parties project’ structures and dialogue
- Revise the political parties project registration and regulations Act and to assist political parties
- project to develop issue based platforms for 2014 elections,
- Strengthen inter-party dialogue among political parties project.
The development objective of the project were to support the overall development of Malawi by to contributing to the improvement of governance by removing barriers that constrained the participation of women and youth in social, economic and political programs as enshrined in the MGDS II. These barriers include among others addressing the gender gaps so as to improve the representation of women in decision-making processes through affirmative action policy measures, improve women‘s limited access to credit, reform land policy, address gender based violence and widespread retrogressive cultural practices such as female genital mutilation, and reduce maternal mortality. For the youth, the project was envisaged to contribute to amelioration of limiting factors experienced by the youth to exploit their development potential. These include: high illiteracy and innumeracy levels; inadequate technical, vocational and entrepreneurial skills; limited access to credit facilities; high unemployment rate; poor access to guidance and counselling services; poverty and deprivation; marginalization in decision making processes; early marriages and teenage pregnancies. High prevalence of HIV and AIDS and limited access to SRH services further compounds the ability of the youth to meaningfully contribute to socio-economic development of the country[10].
[10] Malawi Development Strategy II

1.3.3. Main stakeholders
 The key stakeholders of the project were the Centre for Multiparty Democracy(CMD)- the implementing agency; United Nations Development Program(UNDP) and Department for International Development(DFID)- the funding agencies; Political Parties- primary targeted beneficiaries; Malawi Electoral Commission(MEC), Ministry of Justice and constitutional affairs(MoJCA), Parliament, Law Reform Commission, Registrar of political parties as key partners[11].
[11] Project document 2012-2016

Partners during the implementation of the project were: the Government of Malawi and its ministries and departments that include: The Ministry of Gender, Children and Social Welfare (MoGCSW), the Legal Affairs Committee of Parliament, the National Democratic Institute (NDI), Malawi Electoral Support Network (MESN), Public Affairs Committee (PAC), National Initiative for Civic Education (NICE), the Malawi Local Government Association (MALGA), the Ministry of Justice and Constitutional Affairs and the Ministry of Local Government and Rural Development (MoLGRD).and UN Women.
## 1.4. Purpose and Objectives the evaluation
CMD, UNDP & DFID monitoring and evaluation policies for this kind of project require that a final evaluation be performed upon completion of the project implementation. The end of project cycle evaluation is needed to assess the project design and its performance. It may also contribute to CMD evaluation data bases for reporting effectiveness of CMD operations in achieving its goals and on quality of monitoring and evaluation across CMD system.
### 1.4.1 The purpose of the end of term evaluation was to:
1. Determine the extent to which the outcome and outputs of the project have been achieved;
2. Assess UNDP’s and DFID’s contribution to the project outcome;
3. Document the achievements and lessons learnt during the course of implementation to inform future decisions in design, implementation and management of similar interventions.
4. Assess the effectiveness and efficiency of the delivery channel and determine whether the delivery channel was fit for purpose.
5. Determine the extent to which value for money was achieved throughout project implementation
### 1.4.2. Objectives of the evaluation
The objectives of the evaluation are to:
(i)Assess and analyse the progress made by the project to date towards achieving the project outcome, goal and outputs and the extent to which these results will be sustained after project closure.
(ii)Examine and analyse factors which have positively and negatively impacted on achievement of project outputs and outcome;
(iii)Assess the relevance of the outputs to the effective achievement of the outcome and goal;
(iv)Assess the relevance and adequacy of the project outcomes and goal to address political challenges in the democratic governance sector.
(v)Assess the adequacy of the scope of the project interventions relative to the objectives of the project;
(vi)Assess the extent to which Centre for Multiparty Democracy support Multi-party Liaison Committees in promoting interparty dialogue and reduce political conflicts in relation to Malawi Electoral Commission (MEC).
(vii)Assess the effectiveness of institutional arrangements, sustainability arrangements and partnership strategies;
(viii)Assess extent to which the existing financial, political and regulatory frameworks support the operation of political parties represented in the National Assembly;
(ix)Provide recommendations and document lessons on the design of the project, implementation, sustainability or exit strategies and partnership arrangements to inform future programming;
## 1.5. Key issues addressed
As stated in the Terms of Reference(Annex 6 ), the purpose of the end of term evaluation was to provide the project partners i.e. UNDP, DFID,CMD and Malawi Government with an independent assessment on key achievements of the project as laid out in the project document for the 4 years implementation period. Assess the extent to which expected results were achieved, the contribution UNDP and DFID to the project outcome, document the achievements and lessons learnt through measurements of the changes in the set indicators, summarize experiences gained and recommend future decisions in design, implementation and management of remaining part of the project.
# 2.0 EVALUATION APPROACH AND METHODOLOGY
## 2.1. Technical Approach
The approach to the assignment was participatory in nature involving consultations with key stakeholders at all stages. This involved engaging the stakeholders through interactive meetings to articulate the key evaluation issues. This includes the review of the tools after submission of the inception report; presentation of the preliminary findings to key stakeholders through the emerging issues paper and the draft report for comments that informed the review and preparation of the final evaluation report. Feedback sought from key stakeholders at every stage of the assignment was very informative in refining the tools used in data collection as well as final report. The interview methods especially the Key Informant Interviews and Focus Group Discussions were interactive and facilitated a learning process through dialogue. Document review during the process was key in the tool design and provided vital data on qualitative data as well as triangulation of information and was a key source of quantitative data. Key among these documents were the annual work plans, quarterly review progress reports and both country and CMD strategy documents.
The overall evaluation approach was premised on what the consultant has termed as the triple results focus model which sought to answer the three fundamental universal evaluation questions namely; 1) Did the project do the right things? 2) Did the project do things right? and 3) what can be learnt from the project implementation experience?. This guided the analysis of whether the project achieved the set targets as well as the whether the adopted strategies have been sound enough to support the realization of the intended results at output and outcome levels as illustrated in figure 2.1 below.
# Fig 2.1: Triple Results Focus Model

A focus on results shall form a key dimension in answering the above questions basing on the empirical evidence that will be captured throughout the evaluation exercise. The first question shall be answered through analysis of both intended and un-intended results that have been achieved as guided by the project results matrix. This will support the analysis of both facilitating and inhibiting factors for enhanced results. Therefore, the analysis will take into account the project design and implementation arrangements with an intention of ascertaining how they have facilitated and/or inhibited the achievement of the desired results. Through this analysis, project relevance, efficiency and sustainability will be assessed in addition to the contribution of various actors particularly UNDP and DFID in the observed results. Best practices and key lessons shall be derived basing on the strategies that have consistently yielded superior or inferior results
## 2.2. Scope
The project implementation covered the covered all the political parties registered and with membership with CMD. The project coverage was the entire Republic of Malawi for all its regions and districts. However, the geographical scope of the evaluation covered the project districts of ….The selection of the…political parties and districts was purposive based on the following criteria; in and out of parliament political parties, gender and youth inclusiveness, level of political party experiencing internal disputes and founder syndrome and the membership numbers.

## 2.3. Study Population
Study population consisted of beneficiaries of the project who included women and youth members of party youth wings that participated in capacity building trainings implemented by the project. The evaluation further interfaced with staff of CMD based at the Lilongwe Offices as well as Political party leaders in the regions visited. For divergence of views, respondents also included Civil society leaders; media practitioners, select MPLCs leaders, Local women and Youth Council leaders, and Local Government officials responsible for Women and Youth programme and were associated with the project were interviewed. The evaluation also reached out to women and youth leadership at national level and some development partners who are supporting women and youth interventions in the country. UNDP staffs were purposively sampled based on their knowledge and participation in the project. List of respondents interviewed is attached.
## 2.4. Document Review
The evaluation reviewed project documents that include among others- the project document, MDGS II strategy, recent studies relevant to the project, UNDAF,PPRRA draft bill, Audit Report 2015, Quarterly Progress Reports 2013-2016, Annual work plans and CDM strategies 2012-2016 and 2017-2020 and other critical grey literature documents in possession of the implementing partners and the stakeholders. The purpose of document review in the initial stages of the assignment was to inform inception report, design of the tools. At a later stage the document review helped the evaluation to piece up to together concrete evidence on project design, implementation and achievements of the project.
## 2.5. Field collection Methods and tools
The evaluation used mixed methods that include both qualitative and quantitative approaches. Appropriate tools and instruments were designed to enlist and capture the required data (see Annex … tools).
In qualitative approaches, the consultant designed Key Informant Interview and Focus Group discussion guides, and self-assessment tool and case studies to assist in gathering the required data to enable him answer the evaluation questions. As detailed in the Annex …tools, the evaluator adopted and adapted the evaluation questions to guides used for Key Informant Interviews and Focus group discussions in order to ably meet the evaluation objectives.
The Key Informant Interviews were conducted with the Key stakeholders notably the project managers at the UNDP Country Office, DFID Malawi Country Office, Executive Director of the Centre for Multiparty Democracy(CMD), Key personnel for In parliament and out of parliament Political parties, Electoral Commission, Speaker of Malawi Parliament, the Ministry of Gender, Children and Social Welfare (MoGCSW), UN Women, UNDP, the Legal Affairs Committee of Parliament, Malawi Electoral Commission (MEC), Malawi Electoral Support Network (MESN), Public Affairs Committee (PAC), National Initiative for Civic Education (NICE), the Malawi Local Government Association (MALGA), the Ministry of Justice and the Ministry of Local Government and Rural Development (MoLGRD), MPLCs.
Focus group discussions were conducted with select groups of the members of the Project Steering and technical Committees, Multiparty Liaison Committees; Public Affairs Committee (PAC); members of women and youth leagues of the registered political parties. During focus group discussions, stakeholder mapping tool was deployed to identify who the stakeholders are, their interests and involvement in the project. During the process of using the tool, there was stakeholder analysis to clarify and categorize the various stakeholders by drawing a picture of what the stakeholder groups were , the interests they represented, the amount of power they possessed, whether they presented inhibiting or supporting factors for the project to realize its objectives, or methods in which they were dealt with.
A self-assessment tool was designed to help the evaluator enlist views of the stakeholders who may not be physically meet due to limited time. The self-assessment tool was an all exhaustive instrument deliberately designed for detail and ease of administration yet generate required data within available means of the project stakeholder
For quantitative approach, the consultant relied on secondary data sources to collect data on the statistics available from the political parties secretariats on their membership records(representation of men and women and youth), Malawi Electoral Commission records, Centre for Multiparty Democracy records and any official statistics from the Bureau of Statistics or Government of Malawi; and other quantitative studies relevant to the project. The inclusion of the quantitative methods was to capture statistical data on trends for women and youth representation in the political parties’ structures, elective positions in districts, regions and national level and to ascertain miles stones reached in terms of numbers on reforms and performances of political parties on inclusion of the women, youth and marginalized groups. The extent of women and youth representation in terms of numbers was crucial for understanding how well the political space had been accommodative of women and youth as well as gain insights whether their inclusion was taking a positive trend or not. However, it was very difficult to obtain statistics at all the mentioned levels hence this study did not rely on quantitative data.
## 2.3. Data Analysis:
The data analysis varied for each of the methods deployed. For qualitative methods, thematic analysis was used for data generated from Key Informant Interviews and Focus Group Discussions. Note that some analysis was ongoing during some data collection methods especially during deployment of stakeholder analysis and other focus group discussion activities and content analysis was used for document review.
Triangulation of the results was done at two levels. One level was where the consultant was cross checking for validity of data from similar variables from different data sources; second level was at report drafting while merging the quantitative with qualitative information. During the second level, the consultant compared information to offer explanations of a given finding to reinforce an argument. This happened in the use of quotes from KII and FGD scripts to explain numerical trends. Similarly, the statistical information was used to justify a qualitative perception on why an issue is explained in a given way. As explained above, triangulation focused on comparing information from different sources such as documentation and interviews, or interviews on the same subject from different stakeholders and to corroborate or check reliability of the evidence.
## 2.4. Ethical Consideration
The evaluation consultant adhered to ethical guidelines in the execution of the evaluation. Verbal informed consent was sought from the respondents before the interview. Explanations were provided to respondents regarding likely benefits, rights, obligations and confidentiality of data collected.

## 2.5. Pre-Evaluation Consultations
Pre‐evaluation meetings were held with the UNDP and DFID staff and the CMD Project staff. The meetings focused the Inception Report and served as a means for strengthening ownership of the evaluation process and outputs by the stakeholders.

## 2.6 Limitations to Evaluation Findings
- Obtaining quantitative data in form of statistics was very difficult and not available hence the study relied more on qualitative primary and secondary data
- During data collection, it turned out we could not get enough respondents that participated in all activities due to limited time allocated to the study.
- Lack of National Counterpart consultant also paused some challenge to the international consultant especially during field work due to language barrier. The National consultant would also have assisted in following up rigorously with government and other stakeholders to obtain statistics as well as provide local knowledge to the study
- It was difficult in getting appointments with representatives to some of the selected Key Informants at the national level allegedly due to having hectic schedules. A few responded by telephone, while some number did not respond even after sending constant reminders. This is also due to the busy schedule of the ongoing Parliament Sessions.
# 3.0 EVALUATION FINDINGS
## 3.1. Introduction
The findings have been presented according to the standard evaluation criteria so as to respond to the evaluation objectives as specified in the terms of reference for the project evaluation. The evaluation addresses questions in relation to design and relevance, implementation/ efficiency, effectiveness, efficiency, sustainability, cross cutting issues and lessons learnt. The answers provided to the evaluation questions are discussed under each element of the terms of reference.
## 3.2. Project Design and Relevance
### 3.2.1. Clarity of the problem and soundness of the approach
According to the documents reviewed and evidence there in, the problem the project intended to address was clear outright and informed by evidence. The design of the project was informed by basically two studies 1) Benchmarking Core CMD capacity assessment study 2) Searching for the Holy Grail: Exploring the feasibility of political party ideologies in Malawi. The Design of the project was therefore evidence based that sought to bottlenecks by a addressing critical areas such as the Legal Framework of Political Parties under which they operated among others. Furthermore, the substantial changes in political landscape of Malawi with various interventions since as CMD they also wanted to create avenues for engaging PP in constructive and progressive dialogue and of course Design was also build up on previous UNDP support to CMD which later brought in DFID[12]. The problem of poor governance under multiparty dispensation in Malawi has been largely attributed to lack of inter party dialogue and intraparty democracy and exclusion of the majority of population- women and youth in party activities[13]. The documentary evidence availed to the evaluator indicates that indeed political parties were very weak in terms of internal democracy and inclusiveness of the majority of the population- the women and youth.
[12] Interview with the Executive Director Centre for multiparty democracy
[13] Project document 2013-2016
 The evaluation noted that the approach used was very sound as the project intended to address the problem from a holistic angle by seeking to address the legal, organizational and administrative weaknesses inherent in political parties of Malawi under the multiparty dispensation[14] Thus, the intention of the project approach was to build the capacity of the political parties to enable them ably tackle issues of internal democracy as well as interparty dialogue to serve as pre-cursor to promotion of democratic governance. The project also sought to phase the activities in sequential manner following an election cycle in order to empirically test the contribution of its interventions. Thus the project looked at tackling the problem in an approach that was all round yet consistent to ensure that targeted outputs are met and the ultimate outcome realized.
[14] See issues paper, project doc and PPRRA bill
 The project was also designed to geographically cover the entire country by establishing offices in all the districts with CMD presence. This scope was however watered down by the limited financial resources and human resources low capacity to do so. To cover up for this resource challenge, CMD adopted an outreach activity approach.
Beyond structural reengineering of the political parties, it the design also sought to bring out put 2 basically to build robust parties by focus that made political parties focus on issues and policy agenda than reliance on individuals and personalities
### 3.2.2. Clarity in identification of the targeted beneficiaries
 Clear identification of the targeted beneficiaries is one of the key pillars for any project to accurately measure its success and ultimately the impact of its intervention. The evaluation noted that targeted beneficiaries clearly identified first of all using research based approach –CITE issues study conducted by CMD in 2011, and reference to relevant national and multinational interventions. The project relied on first of all key lessons learnt during the design of MGDS II and UNDAF/UNDP programming as well as World Bank Support program. All these interventions point out that lack of intraparty democracy and interparty dialogue are responsible for poor governance under the multiparty dispensation in Malawi. Indeed, they issues had contributed to weak political parties that lacked the clout to have a popular appeal as well deliver on their mandate to the population. The MGDSII whose goal the project intends to contribute to cites improving good governance and inclusion of women and youth as key development pillars to realizing of the strategy and overall development of Malawi.
### 3.2.3. Measuring the outcome and outputs in verifiable terms with SMART indicators
In any project intervention, the ability of the design to accurately forecast its results in terms of their specificity, quantification and qualification; how they can be realized and action oriented, their direct relationship with project contribution and whether they could be achievable within the time of the project life; are key indicators of how robust the project design was. This is in short what is referred to as SMART indicators that can be used to measure in verifiable terms outcome and outputs of the intervention to assess whether the intervention logic was clearly thought out at design level.

The evaluation analyzed key documents reviewed as well as primary data collected through interviews with stakeholders and beneficiates to discern how the outcome and outputs were in conformity with SMART indicators. Here below are the analysis findings:

1. Outcome-Political parties with clear ideologies and functioning internal democracy
Outcome indicator-the public holds duty bearers accountable

In assessing the indicators of the outcome using the verifiable SMART indicators, the evaluation noted that whereas the outcome is specific on its focus and on what it sets out to achieve, it appears hard to measure in both qualitative and quantitative terms given the volatility and instability of political parties in Malawi. This situation applies to both political parties in and out of parliament. Although the outcome is attainable, this is a long term aspect that cannot be accurately forecast to have been achieved with the four years of the project life. This is further compounded by deteriorating social, economic and political environment obtaining in Malawi. On whether it was time bound; it is difficult for the evaluation to claim that the outcome indicator can be tagged to a specific time frame when it can be achieved thus it cannot be verifiable in terms of time given the short term span of the project. This is because most the outcome indicators are driven by attitude changes which cannot be tagged on specific time frame but rather a long and complex process influenced by a myriad of factors. For example the male domination and exclusion of youth are rather underlying structural issues whose change is gradual with no specific time that can be forecast. The evaluation is of the view that a rather long term programming that is multisector and holistic in approach can drive the process towards that attainment of the outcome. The attainment of the outcome could also be based on assumption that there are improvements in social, and economic political conditions which are difficult to forecast as of now.

Measuring outputs indicators verifiable using SMART indicators

The project was set to achieve the following outputs:-

Output 1-Revised political parties registration and regulations act is enacted by the national assembly

Indicators
Enacted political parties act that insulates the registrar of political parties from political manipulation among others
The indicator is specific in its reference of what is to be achieved i.e. Revised Political Parties Act. However, it’s very hard to measure insulation of registrar from political manipulation even if the law came into place. Please note opposition party members crossing to the ruling party on the floor of parliament yet the law prohibits that under the multiparty dispensation(cite progress reports of project and project document). The indicator is attainable and realizable but not time bound due to stakeholder contestations and limited powers of CMD the implementing agency to have the law enacted well in time.
Member political parties constitutions aligned with the revised political parties act
The indicator is specific on its result, and can be measurable in terms of aligning constitutions to the revised political parties act but it cannot be time bound. Note interview with CMD pointed out due to delay the act, they had decided to realign party constitutions prior to enactment of the law. One wonders whether if done towards the end of the project life, one is likely to measure the accuracy of the indicator incase further changes occur in the bill and post 2014 general elections that are long past yet were supposed to taste the efficacy of political parties constitutions

Output 2-Political parties issues based platforms for 2014 elections are developed and disseminated
Indicators
No of political parties formulating policy documents with involvement of party membership
The indicator is not specific on what kind of policy documents are to be formulated because they are diverse; it’s also not easy to measure the level of involvement of party membership as involvement may a be process issue and level of input in terms of time, gender influence etc.; its attainable as the policy documents can be made, it’s realistic but may not be time bound because capacity is built overtime and influenced by factors such as quality membership and leadership that cannot be tagged to the project life.

No of political party debates conducted
The indicator is not specific on number of political party debates to be conducted and therefore measuring this indicator in verifiable terms is hard. One wonders whether the attainability of the number of debates is itself enough to catalyze issues based platform. There is also influential element of spatial and time distribution, inclusiveness of a critical mass of the women, youth that may not be feasible within the project life given the social-economic and political environment obtaining in Malawi.

No of political parties members trained in policy formulation
The indicator is not specific on the number and type of members that constitute the critical mass of the party membership that will demonstrate the capacity built, the numbers are measurable but critical numbers of membership are not easily discernible due to high party membership turn over and therefore no accurate statistics on what actual membership of a given party is. Again the critical mass of the numbers for membership of any given political is not easily attainable for lack of accurate statistics. To attain a critical mass of number of trained party membership in policy formulation is not attainable in the project life but rather a long time engagement that caters for attrition and desertions characteristic features of the political parties in Malawi.

Percentage of women and youth wings trained in policy formulation
Specificity in terms of percentages does not reflect accurate capacity built due to diverse intellectual abilities of women and youth wings of different political parties; whereas the percentage can be measured in terms of numbers, it may not necessarily reflect capacity built over time and in different parties among the women and youth wings. The numbers may be attainable but not the competency actions to undertake the policy formulation. Therefore, the indicator may not be time bound given the short project life of four years but rather should be a continuous process.

Output 3- governance structures for political parties developed to foster transparency and accountability
Number of political parties trained on election monitoring
Whereas the indicator talks of the numbers, they do not reflect the actual measure of capacity of political parties to monitor elections. Similarly, attaining capacity to monitor elections can be verifiable by the efficiency and effectiveness of participation of the political party in election monitoring. This evidence can be adduced from what a given political party can do in terms of geographical coverage during general elections and quality of the monitors in areas of reporting and analysis abilities. Due to high levels of attrition in party membership and crossings, it’s hard to measure that this indicator could be time bound within the limited project life but rather in the long-term.

Number of political parties with revised constitutions with clear statements on the inclusion of women and youth and marginalized groups
Whereas the indicator is specific and verifiable in terms of the targeted output, it’s no guarantee that number of political parties inclusion of women and youth and other marginalized in their records translates into verifiable tangible participation. The numbers may be attainable but the critical mass of the women, youth and marginalized groups may be hard to measure as to what constitutes qualitative and quantitative numbers due to unstable political party membership. Also as cited in issues paper, the level of attrition in membership of political parties and founder syndrome may render it hard to achieve this result in the project life of only four years.
Number of political parties with functioning administrative structures
Functionality of administrative structures of an given political party is multifaceted and includes among other things the ability of the party to hold regular party conferences, recruitment and updates of the membership, ability to handle intra party disputes and wrangles etc. Thus when one rates them to SMART indicators, functionality of administrative structures falls short of being verified due to diverse attributes driven by change of attitudes action oriented that can be attainable in the long-term for structures to perform according to the expected functions not in the project life.

### 3.2.4 Logic and relevance of relationship between outcome, outputs, activities and inputs of the project tackling the problem identified

According to the project design, the project documents reviewed illustrate the sequencing logic but the implementation did not follow the sequencing of the results. This implied that tackling the problem identified was haphazard characterized by oversight in following the logic earlier on envisaged during the design. This in a way jeopardized the relevance of relationships between outcome, outputs, activities and inputs.

### 3.2.5 Relevance of the project to the development of intra-party and multiparty democracy
Relevancy to the intraparty democracy
According to the design, the project was aimed at promoting intra-party democracy by supporting the review and revision of key building blocks of political parties including parties’ constitutions to integrate women, youth, and other marginalized groups in party structures, as well as provide training for relevant party members/ staff(second quarter progress report 2013).The Strengthening Political Parties project was designed to support the attainment of “Political parties with clear ideologies and functioning internal democracy”. Thus the capacity to be built was to enable them function as effective agents for fundamental and sustainable democratic transformation in Malawi[15]. The intraparty weak capacity was demonstrated in rising trend of independent MPs since June 1999. Statistics showed that independent MPs rose 9 times from 4 in 1994 to 32 in the 2009-2014 parliaments[16].
[15] CMD bench marking study 2011

 Relevancy to Multiparty democracy
The documents reviewed and interviews conducted during this evaluation, showed that indeed this project intervention design was informed by the existing political dispensation of multiparty and attendant challenges that stifled political parties to deliver on their mandates. Hence its design relevance was the focus on addressing the underlying multiparty democracy challenges in Malawi. During the conception of the project, multiparty democracy in Malawi was in state of malaise evidenced by weak political parties suffering from the crisis of legitimacy, ethnic divisions and regionalism since May 1994 elections as most of the parties had not prepared themselves for a life beyond transitional period. For example, there was lack of capacity by political parties to marshal support and membership beyond the founding personality’s region, ethnicity and tribal lines. This evidence was adduced from performance of major three political parties, namely: AFORD, MCP and UDF were dominant in the north, center and south respectively. As a consequence, political culture favorable to the democratic brand of politics was at stake[17].
[17] CMD Bench Marking Study July 2011

### 3.2.6. Effectiveness of the project’s capacity building interventions
 In order to ensure the effectiveness of the capacity building initiatives, the design did envisage an all-out spatial and temporal coverage of the targeted beneficiaries. Care was not taken to provide adequate resources and ample time to respond to the needs and challenges anticipated for the project to be effective in its capacity building initiatives. Evidence gathered from interviews conducted and documents reviewed demonstrate glaring omissions when it came to the design in which outputs would be delivered. A number of limitations stand out that rendered the design of project not very effective in its capacity building interventions.
First, the project was aimed at strengthening the capacities of Political Parties, but CMD the implementing agency only provided software without direct support to Political Party respective secretariats which also needed capacity in terms of logistics, systems, programing, etc. This therefore meant that capacity building initiatives didn’t happen at the Political Party individual secretariats[18].
[18] Interview with ED-CMD
Second, there was the issue of the failure for the project to cover all the districts due to resource and capacity limitations.
Third, whereas CMD adopted within its implementation approach to working with Multiparty Party Liaison Committees (MPLCs) which were initially Malawi Electoral Commission structures, there were misconception that CMD should change the way MPLCs work yet they were not within the mandates of CMD but MECs.
Four, misconception by the population that MPLCs are structures of CMD rendered the operationalize of the structures due to monetary expectations of the targeted membership .
Fifth, in terms of Output identification especially Output 2 on issue Based platform focused more on the supply side and less on the demand side which would have empowered people and masses to demand issue based policies and programs for Political Party interventions.

Six, the design did not provide for midterm review to assess the project progress. Midterm reviews in addition to the monitoring activities are key to assessing the progress of project implementation midway and usually serve as catalyst to reactivate slowed activities critical to delivery of the project outputs and outcome. The evaluation observed that lack of the midterm review in a way was a weaknesses that possibly lead to failure to appreciate and address the risks that were foreseen during design stage yet could not be addressed along the way; something likely to affect the realization of project outcome as envisioned in the design[19].
[19] Interview with the Executive Director-CMD November 2016
Seven, our document review also revealed that within the project document, there were no clearly identified and articulated strategies to guide the implementation of the project.

Further, the 2 year delay in constitution of the Project Steering Committee also affected the policy and strategic implementation of the project as much was initially left to the Technical committee.

In addition, the implementation period also left much to be desired, the 4 years of the project was a short period to change peoples and PP culture and mind-set of the targeted beneficiaries – the political parties, women, youth and government ministries and departments.

Lastly, the Project Document doesn’t provide for anticipated exit strategy of the project to pave way for how otherwise the delayed activities especially the enactment of the PPRRA bill could be brought to conclusion.

## 3.3. Implementation/Efficiency
### 3.3.1. Appropriateness of the management arrangements-coordination, financing and actual implementation

In the overall observation, the evaluation noted that there were clear management arrangements to oversee the coordination, financing and actual implementation of the project. The executing agency of the project was UNDP and DFID while the implementing agency was the Centre for Multiparty Democracy. As an executing agency UNDP and DFID were responsible for overall management, financing, technical guidance to the implementing agency monitoring and evaluation of the project. According to this evaluation UNDP /DFID were able to deliver on their mandate of mobilizing the required resources and financing (how much was raised and sources, its adequacy) of the project activities. However, UNDP/DFID are reported not have provided adequate technical guidance expected of them during the project implementation. While CMD as the implementing partner performed all actual implementation activities that it could given the time and resources at its disposal and circumstances.CMD was in fact engaged in day today implementation of activities and used its clout to design strategies that could ensure the continuity of the project activities beyond the project life. The design of the2017-2020 strategies was actually in line with ensuring the sustainability of the project.

### 3.3.2. Major factors that influenced project delivery and solutions devised
Number factors influenced the project delivery. Some activities did not commencing on schedule, the solution to compress many activities within a short period of time and all the planned activities were accomplished in line with the initial timeline.

The tight schedules of political players towards the 2014 elections - key stakeholders in the activities of CMD, their involvement is always of critical importance. Progress on some activities were either delayed or postponed, for example, the conclusion of the review of party manifestos. Closely related to this was the active involvement of CMD in organizing presidential debates. This took a lot of time and human resources that delayed reporting in the first quarter of the 2014[20].
[20] Project progress Report, January –March 2014

The major challenge being experienced was the reduced funding. This has affected the reach of the project. For instance, resources had not been allocated to MPLC meetings. The solutions sought was to rethink about MPLC’s whose mandate could probably be inbuilt within district peace committees being established under the national peace architecture to ensure the continuity of their valuable activities.

The delayed inaction of the review the PPRRA due to the Ministry of Justice slow pace yet CMD found hard to influence the ministry fast track the process. However, CMD embarked on the concerted efforts to lobbying and sought to identify other voices who can urge Government of Malawi to pass the bill[21].
[21] Project progress Report 2016,January –March 2016

Interruption of funding from other partners was also a factor to reckon with during the implementation. Since the expiry of funding from the Netherlands Institute for Multiparty Democracy, CMD did not have any other secure funding for party bilateral programs, where it would have direct intervention initiatives with political parties, including tailor made capacity development plans. Recent trends have indicated that political parties are suffering from intra party democracy issues, but CMD has no resources to adequately intervene. This has a potential of affecting the cross party program[22].
[22] Project progress Report 2016,January –March 2016
### 3.3.3. Efficiency in delivery of results-timing
The time stipulated in the delivery of results was guided by the project documents on the scheduling of the activities and respective timelines to deliver on the anticipated results. Timelines were operationalized in the detailed annual work plans drawn and agreed upon by both the executing agency(UNDP) and implementing partner (CMD).As to whether there was time efficiency in delivery of the results as stipulated in the work plans and related schedules, the document review and interviews conducted with stakeholders reveal that some activities were not executed as scheduled and there were also overlaps of the activities in successive work plans. The evaluation observed that some of the delays were solely beyond the means of the implementing partner and the executing agency. For instance, the delay to enact the PPRRA bill as explained above in section 3.3.3 above point to inefficiencies that impacted heavily on the timely delivery of the results.

3.3.4. Fulfillment of the success criteria –as per outlined in the project
Output	Rating	Comments
1. National Assembly enacts revised Political Parties Registration and Regulation Act (PPRRA).	5	Project championed the review of the Act; produced a bill and got consensus from all parties in CMD; convinced government to adopt the bill as a government bill and agreed on the text with the minister of justice, way up to the cabinet committee.
2. Political Parties’ issue-based Platforms for 2014 elections developed and disseminated	4	Project was able to have parties produce manifestoes, inserts and newspaper pullout and brochures; political parties were able to participate in public debates starting from spokespersons to vice presidential candidates to presidential candidates. The downside is that this has been restricted to the elections period. Not much issue based engagement after elections.
3. Organizational structure for political parties developed to foster transparency and accountability	3	A start intervention under this was the training of Elections Monitors for political parties. The other interventions were reconfiguring taking into account that they were dependent on the passing of the revised political party bill.
4. Platform for inter-party dialogue strengthened to promote transparency and accountability as well as enhance credibility and legitimacy of political parties at all levels	5	This output is an actualization of CMD as a platform for dialogue for political parties. CMD mobilized MPLCs in 12 districts. The MPLC were a great success in averting conflict in hot spot areas (Mulanje,Thyolo, Mangochi, Ntcheu and Mchiinji but also Rumphi); Facilitation of interparty dialogue platform – there was trust building between the EBM and the political parties. Both ruling and opposition political parties kept together and continued to dialogue and engage under the CMD umbrella. Further the relationship with the EC held even at moments of high tension… in which cases MEC would not make a decision without involving CMD. A notable trust from the EC to CMD is when they delegated the responsibility of distributing nomination papers to political parties to CMD.
5. Effective and efficient management, partnership development and monitoring and evaluation of the project.	5	The implementing agency worked closely with the funding partners to build synergies in partnerships. / There was observance of reporting on activities through quarterly reports and financial reports and expenditure guidelines strictly followed.

### 3.3.5. Responsiveness of the project management to significant changes in the environment
The significant change in the environment during the project implementation was the change of government in Malawi after the April 2014 elections that saw new leadership taking over office. Change in government not only meant change of leadership but also change in policy direction that affected the progress of at which the MDC - the implementing agency was making towards realizing most critical result of the project the PPRRA bill that was not yet enacted. The implication was that CMD had to devise new lobbying strategies to engage the new government on the matters of the reviewing the PPRRA bill that it had to start all over again. This not only disrupted the tempo of the project but also the delivery of results in a timely manner[23].
[23] Progress report May to September 2014
### 3.3.6. Monitoring and backstopping of Government and UNDP
The evaluation observed that Government and UNDP were better placed to play a crucial role in the monitoring and backstopping given their positioning on the board and as a greed in the project document.

One of the challenges cited was that some development partners and UNDP were not constantly on board during implementation as they would surface towards end of the year to monitor and supervise. Secondly, reporting mechanism were destabilized due to delayed releases of funds due to approval procedures whereby even after submission of Quarterly reports in some instances CMD would have to in between prepare again progress report to trigger release of funds[24]
[24] Interview with the Executive Director- Centre for Multiparty Democracy

Another challenge is in regard to joint monitoring and evaluation, where different partners were involved, it was difficult for monitoring exercise to be planned properly when the actual activities are taking place. At times monitoring was done outside the moment of implementation (ex post evaluation) when it was convenient to the partners. This has provided challenges especially because of the nature of activities that CMD does. CMD works through people spread in the districts. For one to engage these people, there are considerable expenses that have to be incurred especially in terms of transport and accommodation. These expenses were not factored in the budgets. Thus the best way to carry out monitoring in this case would be for the partners to be present during activity implementation. Alternatively, resources have to be made available for stand-alone M&E[25].
[25] Progress report May to September 2014
### 3.3.7. Project collaboration with public and private sector; and CSOs and faith groups
Since the commencement of the project in 2013,CMD initiated collaborations that took root and yielded partnership that ultimately engendered the sustainability of the project activities as well as built synergies with similar interventions. The number of themes and activities such as gender and women participation in politics, review of the electoral laws and the review of the political parties’ registration act are some of the highlights of the project partnerships[26]
[26] January- March progress Report 2016

With government, CMD initiated partnerships with the Ministry of Gender, Children and Social Welfare (MoGCSW), the Legal Affairs Committee of Parliament, Malawi Electoral Commission (MEC), the National Democratic Institute (NDI), Public Affairs Committee (PAC) the Ministry of Local Government and Rural Development (MoLGRD), the Malawi Broadcasting Cooperation (MBC), Partnership with government departments were key in lobbying for the successful review of the PPRRA bill.

CMD also initiated partnerships with development partners to a level beyond that of the project scope. Key among others were the UNWomen and UNDP. These partnerships were enlargement on scale that fostered initiatives aimed at promoted women and youth participation in the governance programs in Malawi.

Partnership with civil society was also initiated and the evaluation notes that this led to the building of synergies that enhanced the project implementation through sharing experience and skills critical for the success of the project interventions. Among the civil society the key partners were the Catholic Commission for Justice and Peace CCCJP), National Initiative for Civic Education (NICE) and the National Democratic Institute (NDI) [27], the Times TV; Malawi Electoral Services Network (MESN), and the Mtendere Electoral Services Network (MESN)
[27] Quarterly progress reports 2013,2014,2015 and 2016

On the international scene, CMD is partnering with the Socialist Party and the Liberal party of Denmark on the youth project. It is also partnering with the Danish Institute for Parties and Democracy (DIPD) on the women empowerment project.

The evaluation noted that the partnerships positioned CMD as critical partner for both government, development partners and civil society in Malawi. This not only credited the implementing partner but also built confidence and trust for partnerships are likely to yield dividends that will greatly contribute the realizing the outcome of the project. One report notes that: “There is a growing appreciation among Government and civil society organizations, including donor partners, of the unique role that CMD plays in Malawi not only with regard to democracy consolidation, but also in matters of policy lobbying and advocacy. It is increasingly becoming more evident that political parties are not only the building blocks of democratic governance but also sustainable socio-economic development. They are strategic in matters of national policy and as such cannot be ignored.”[28]
[28] Quarterly Progress Report 2013

### 3.3.8. The role of UNDP country Office and its Impact
As the executing agency, UNDP Country Office carried out enormous tasks of mobilizing resources required for the success of the project activities. The bringing on board of other development partners like DFID and supporting the activities for the formulation the CMD strategic plan 2017-2020.Note that the latter strategy is largely focused towards carrying on the activities beyond the project life a step towards the project sustainability.
UNDP Country Office is also credited for having supported the project in building linkages and synergies with the UN system like UNWomen, a key ally in promotion of the emancipation of women; key catalyst in the inclusion and active participation of women in political party activities in Malawi.
The positive impact seems to be high according to the evaluation observations. This impact was evident in the synergies built between the implementing partner and different stakeholders which are key sustainability avenues for the project activities. In short, UNDP has set in motion the activities that served as agenda of capacity building of political parties on to which other development partners can come in to support similar or related activities as a way of promoting democratic governance in Malawi.
However, we noted that on the negative side, UNDP office impact is likely to bring undesired effects. This was attributed to UNDP and DFID reluctance to committee more funding beyond the project life and the CMD reported such stance will likely have grave consequences regarding programing and positioning of CMD for 2019 elections the preparedness. There is also a likelihood of key personnel critical for the agenda of political party capacity building[29].
[29] April-June 2016 Progress Report
### 3.3.9. Management contribution by the UNDP country office
The role of the UNDP country office in the project management was immense according to the evidence available during the review. As provided for in the project document, UNDP country office provided adequate support in financial management and risk mitigation. The implementation of audit to assess the progress of project activities and the financial accountability, scrutinizing the Annual Work Plans and approving processing of the payment and technical support including the recruitment process of the technical personnel for the project were critical roles the UNDP country office provided. Monitoring activities and scrutinizing the Annual Work Plans enabled the implementing agency CMD to undertake flexible programming to conduct activities that had been skipped in 2015 due to technical hitches beyond their control. This was intended to cater for situations where some planned activities could not start before certain processes were completed. This development was mostly brought about by the added dimension of the unpredictability of the project deliverables which the project never had control over. Also the Country Office had to take care of the crucial role of working around politically sensitivity deliverables that were beyond the control of project management team[30].
[30] Audit Report 2015

## 3.4. Effectiveness
## 3.4.1. Major achievements of the project towards realization of results
This section assesses the progress made towards set targets in terms of outputs and activities prescribed in the project document, annual work plans and what was actually achieved given the circumstance , time and resources for the project implementation.
The project documents spells out the four outputs that were to be achieved. The evaluation reviewed the annual work plans and activity reports to ascertain the major achievements realized towards attainment of the results. Here below are our findings:
The project was able to engage all stakeholders in both government and political parties to generate contents of the bill in consultative manner giving a lee way for ownership that will eventually lead to acceptability among all the concerned parties and thereby an easy law to operationalize. The process serves as a way for the best practice in enactment of other laws in the future. Evidenced is adduced from the way CMD under took the initiative bringing everyone on board and open discussions were generated that informed the objective nature of the contributions. As it was put”…it managed to rally and bring together political parties in both in power and opposition to constructively dialogue and come to a consensus.[31]”
[31] Interview with Executive Director of CMD
The evaluation was able to note the improvement in the way political parties campaigned with focus on articulating issues focused on policies intended to improve the wellbeing of the citizens unlike in the past when it was not the case. This achievement sets a good precedent in promoting good governance and is likely to lead to violence free elections. It should be noted most of the violence is borne out of failure of the candidates to focus in issues but personal attacks.
Capacity building initiatives conducted in the area of building governance structures were undertaken as prescribed in the work plans. Notable is the trainings done for Training of Trainers 5-10 in the 192 constituencies that were supposed to undertake to train others. The evaluation notes that limited resources seem to have constrained the process but not evidence is yet to come to the fore on what ToT has so far achieved.
There was mitigation of conflicts in 12 hot spot districts as result of the reactivation of Multiparty liaison committees(MPLCs). This had a positive effect in the 2014 generation elections in Malawi. Thus the reactivation of the committees set a good precedent to the way conflict was managed during an election time proving that actually there can be violence free elections if all stakeholders were brought on board early enough to deal with such kind of problem. The MPLCs have played significant roles as further explained in the following case study
CASE STUDIES: Case study of Thylo and Nsanje Districts – MPLCs

“Taking a leading role we the MPLC in Nsanje are doing a lot of work beyond elections which include monitoring of government development projects such as Local Development Fund (LDF), Malawi Social Action Fund (MASAF) hence the government and development partners should support us” Quote by AFORD Governor from Nsanje MPLC

Thylo MPLC meeting was a surprising one to the evaluator as members of the various political parties represented in Parliament namely DPP, AFORD, MCP and PP all turned up in party colors for MPLC evaluation meeting. The way the members contributed and the way they were organized and consulting each other during my meeting with them was a great testimony on how successful MPLCs have been. A case study of the MPLCs revealed how the district was being considered as the “Bedroom of the incumbent President” hence no other part was allowed to mobilize or carry out political activities within the district. This generated a lot of tension and eventually degenerated into violence and conflicts especially during the run up to the 2014 tripartite elections.

This was to some extent dating back to the historical trends of one party state which rendered people intolerant to each other in politics. “Here in Thylo there was no way people could co-exist as there were tensions and inter-party conflicts that even led to loss of lives….a case in point being in Thylo East Constituency where no other party was allowed to campaign against the DPP party. A police officer and a Peoples party member were killed as a result of these extreme conflicts…. But thanks to CMD and MPLCs who came in and resolved the violence and conflicts” Political Party Governor and member of Thylo MPLC

Other vivid examples where MPLCs went and resolved the conflicts was when they conducted meetings at the Traditional authority place at Bvumbwe with the chiefs and population and many conflicts among members and supporters from various Political parties arrived at compromise and started working together and respecting each other. In Thylo West at Thomas traditional authority Headquarters the role of MPLCs as supported by CMD was also climaxed with the signing of the Code of Conduct between Political parties and members of the MPLCs in which major milestones were stipulated and implemented satisfactorily in Thylo District. The MPLCs were also commended in Thylo for uniting the people from different shades and political parties whereby this also gave the district authorities mileage in effecting their work as well as NICE as a member of the MPLC in Thylo was able to smoothly conduct civic education.

The Nsanje MPLC was also undertaking the same activities and organised well though it had also started monitoring government development programs under Local Development Fund and Malawi Social Action Funds. For example at Nkapako Primary School the contractor was doing shoddy work and MPLC utilised its members who were conversant with technical engineering skills and had sit down with project committee that eventually forced the contractor to redo the work.

Both Thylo and Nsanje district MPLCs attributed their success to the role and support played by the CMD and were all playing that CMD should be further supported beyond elections since their work together with MPLCs transcends elections. Whereas MPLCs work was hailed, members also proposed that apart from district and constituency based MPLCs, there should be institution of a Regional and National MPLCs so that the structures are able to coordinate effectively and ensure that descions from the grassroots are properly channelled and owned by all political players and actors especially the parties

The role of MPLCs were thus summarised as having done the following in Thylo and Nsanje districts

- Participated in civic and voter education which resulted in improvement in voter registration process and turn up
- In Nsanje district specifically MPLC is monitoring government development programs such the Local development Fund under Hospital advisory committee etc
- Dialoguing among political parties to iron out tensions within parties
- Promoted the issue based campaigns as opposed to castigation and personal attacks along sectarian lines like tribe, religion etc
- Prevailed on supporters and voters to refrain from defacing and pulling down posters
- Undertook meetings within communities with various stakeholders to guide on the management of society
- For Nsanje MPLCs they have gone beyond elections and started monitoring development projects
MPLCs however are also faced with a lot of challenges during their execution of their work which include the following
- Lack of adequate resources and funding in form of facilitation and logistics since they have to attend meetings as well as travel all over the districts to monitor political and development work
- Lack of identification and uniforms in order to be visible within the areas where they operate
- Transport challenges were also reported as major challenge
- Seasonal funding which only comes during the elections yet their work stretches beyond and in between elections as well as monitoring government development programs
- Limited or even lack of exchange visits and tours to share experiences and learn from other MPLCs

The capacity of Political Parties in areas of the policy development and articulation as well in the resource mobilisation through membership are taking root with evidence adduced from the way political parties of DPP, MCP, UDF and AFORD were conducting business.
In areas of promoting gender and youth, notable achievements include:
- The project has involved women especially during outreach activities by ensuring that a ratio of 50:50 men and women is emphasised and also in most case Secretary Generals and Directors of women affairs in PP are engaged in all PP activities
- Issue based policy development platforms also specifically targeted women and youth in separate trainings
- Study tours in Ghana and Uganda also took care of gender aspects by picking some women and youth
- The project structures are also useful interventions points for Women and Youth specific projects funded by Danish, DFID and Danish socialist party
The implementing partners CMD has also gained a lot through implementing the project activities. This has enabled CMD to improve on its internal management through building its capacity in results based management that have greatly contributed to Monitoring and Evaluation processes. In the same vein, CMD has also gone ahead to develop knowledge based products such as booklets, studies, baselines, training manuals, brochures, policy platform briefs that were not being done before it engaged in the project work. This achievement in away is a good practice that will enable the implementing partner sustaining some of the project results that are focused on advocacy.
## 3.4.2. Evidence of contribution of UNDP and DFID to achieving the project outcome
Evidence is exemplified in form of financial co-ordination and resource mobilization as well as supporting the CMD which has brought the political parties on the same table to plan and dialogue. The chair rotates in between the member political parties, a sign of parties managing themselves.

UNDP and DFID have own country program strategic partnerships with government of Malawi that are funded separately on jointly aimed at promoting good governance particularly interventions aimed at strengthening political parties and the participation in the multiparty dispensation in the country. Key evidence is found in the United Nations Assistance framework and DFID . Both documents spell out support mechanisms including funding that is aimed at contributing towards realization of the outcome.
Furthermore, DFID has pledged to continue supporting the implementing agency with financial support to carry on with some of the activities after the end of the project.
## 3.4.3. Potential areas for project success-impact, sustainability of results and capacity building
 Despite the challenges and a few hitches suffered, the evaluation notes key areas that demonstrate that in fact there is high potential for the project to realize success.
Impact- a lot has changed in terms of the way the political parties relate with each other and the tendency to network and collaborate especially during the collection of views for the PPRRA bill demonstrates high potential for impact of the project.

On sustainability of results, we noted that there has been growing interest in the development partners to fund CMD strategic programing as clearly set in the 2017-2020 CMD strategic plan. Also the aligning MPLCs to security committees is a step towards the sustainability of the results in the long run.

Significant initiatives of capacity building seem to have taken root within the political parties themselves and other stake holders, an opportunity of strengthening operations of political parties as well as targeting the special interest groups like women. Notable triggers in that direction were the training of trainers for monitoring elections, research and issues based advocacy within political parties and implementing agencies. Most of the political parties that benefited from the initiatives have taken them as part of their modus operandi in their political parties. This response from the project initiatives is symbolizes positive aspects that are likely to yielded maximum benefits of well promoted and supported.

## 3.4.4. Factors beyond control that affected the outcome
It’s important to first point out the outcome of the project to be realized is a protracted struggle whose achievement is highly influenced by the a myriad of social-cultural, economic and political environment that is highly unpredictable. The evaluation noted that change of government affected the fast tracking of the enactment of the key legislation as the implementing partner had to begin by redoing the lobbying all over again. The delayed enactment of the PPRRA bill remains a thorn in the realization of the outcome in the foreseeable future.

Another factor, is that the CMD itself admitted having no muscle to push the enactment of the bill beyond the lobbying initiatives that could not help much.
## 3.5 Efficiency
Efficiency measures the extent to which inputs contributed cost-effectively to the realization of outputs. The ToR required the evaluation to measure the efficiency of this project in terms of adequacy of the resources in quantity and quality; effective use of resources to produce results and value for money; cost effectiveness of the project; suitability of selected technologies; evidence of observing accountability measures prescribed by UNDP; delivery of government counterpart inputs; cost drivers and solutions suggested and appropriateness of UNDP resource mobilization strategy.
### 3.5.1. Adequacy of resources in quantity and quality
The evaluation assessed the expenditures against the initial budget for the delivery of each of the outputs and activities planned to ascertain whether the financial resources allocated were quantitatively adequate. On the whole, the evaluation noted that there was a positive variance between the budgeted funding and actual expenditure on all the five outputs as illustrated in fig 3.1 below.
# Fig 3.1: Level of project budget and expenditure variations

Source: Project financial reports 2013-2016
As indicated in the figure above, there was small positive variation between the total budget and expenditure signifying the adequacy of resources throughout the project implementation period. Throughout the project years, the total expenditure has slightly been lower than the budget implying that adherence to the budget lines has been satisfactory. However, further analysis of the variances on specific activity budgets and expenditures revealed wide variations as illustrated in figure 3.2 below.
# Fig 3.2: level of variation between activity budgets and actual expenditures

Source: Project financial reports (2013-2016)
Activity implementation in the second and third years had negative variations from the planned budget; a sign of poor financial forecasts although on the other hand reflects flexibility in the budget implementation. The variation levels were significant to have adversely affected activity implementation should there have been inflexible budgets. Analysis of the project’s financial performance further revealed that the highest proportion (46.6%) of the project budget was spent on project management. Project management costs exponentially increased even when costs on the other core project activities were decreasing as shown in figures 3.3 and 3.4 below.
# Figs 3.3 & 3.4: Expenditure patterns on the project activities

Source: Project financial reports (2013-16)
While it is a requirement for some donors that project management cost should not go beyond a certain threshold, the annual increase of the project management costs while other activity costs were reducing does not urge well for value for money. Much of the project expenditure should have been tagged to core project activities other than management such that management costs resonate well with the level of activity implementation. It is in the evaluator’s view that this project fell short on value for money and instituting standard criteria to guide budget allocation to various project activities. This shortcoming notwithstanding, the evaluation noted that both the implementing agencies (UNDP and DFID) and partner (CMD) subscribe to sound financial management principles and practices and have put in place financial systems to facilitate financial prudence with satisfactory emphasis on effective use of resources as further explained in the next sub section.
### 3.5.2. Effective use of resources to produce results and value for money
Observations made in the reviewed documents and interviews demonstrate effective use of the resources to deliver on the mandate of the project. The target of the effective resource use was to ensure the resources at the project disposal yielded most. The evaluated noted very good approaches and initiatives notable ones being the radio programs and the social media. For instance, the use of radio programming to run a call in talk shows- Chipani Changa was effective compared to other alternative means like TV shows. The radio program offered wide coverage as the radio station selected had wide spectrum coverage and the interactive nature of program evoked discussions, attracted wide audience because its scheduled broadcast was prime time-; a clear demonstration the most effective resource use strategy of the project.
The evaluation noted that a number of measures were instituted and followed to realise Value-for-Money. The Annual reports submitted were accompanied by the financial reports. Budgeting and financial disbursements were closely monitored and reported between the executing agency-UNDP and the implementing agency CMD. We noted that prudent financial management and auditing practices were undertaken. The recommendations of the audit were quickly responded to by the implementing agency (CMD) and the funding agency (UNDP).Infact due to strict observance of the value for money it was only minor queries that were raised according to the Audit Report of 2015 and other financial records that the evaluation came across.
### 3.5.3. Cost effectiveness of the project
Cost effectiveness of the project entails the choice of taking up best least cost alternatives to deliver on the results anticipated of the project. The evaluation noted that due to political sensitivity of the project, there seemed to be no alternative least cost ways the project could have been implemented. It’s important to note that bringing together the political parties and supporting them under CMD was the only viable alternative than carrying out a none targeted stakeholder approach to deliver on the results the way it was implemented by the project.
### 3.5.4. Suitability of selected technologies
Evidence available in the documents and interviews show that during the course of project implementation, various technologies were deployed with varying degrees of frequency to undertake project activities The technologies deployed include electronic media - Radio, ICT and social media. These technologies proved to have worked effectively and were therefore choices that best suited the project media given the targeting of the activities and beneficiaries. As noted above, the radio was very suitable as it attracted wide, interactive audience that could not be as tenable if the alternatives like workshops were adopted. This has been particularly so in advancing the agenda on the issues advocacy and civic education. The social media also because it appealed to the youth, was quite handy and proved to be the most suitable tool for targeting the youth in programming. The evaluation concludes that there could not have been any better suitable technologies to support the project activities other than those deployed given the efficiency and effectiveness they delivered on the results.

### 3.5.5. Evidence of observing accountability measures prescribed by UNDP
The evidence found available were the annual workplans,financial and audit reports that conformed to the requirements in terms of standards and regularity as required by the UNDP. The evaluation is therefore happy to report no major deviations in terms of observing the accountability measures as per UNDP guidelines. This clearly demonstrates as discussed above why the cost effectiveness and value for money were met by the CMD the project implementation agency.
### 3.5.6. Delivery of government counterpart inputs
Documents reviewed showed that CMD had sought the interventions and support of the government funding to the project related activities as way to argument project resources. There was a promise made by the head of state but could not materialize basically because CMD was not a statutory government entity and could not be entitled to subventions from the national treasury on such grounds. Up to now, the board of the CMD is still exploring avenues on how best it can lobby government to finance CMD activities[32].
[32] Minutes Board Meeting November 6th 2015
### 3.5.7. Cost drivers and solutions suggested
As indicated in the table I above, the activity that overshot its budget was the Issues based political parties platform. The activity overshot its budget by 23,750 US$ and this attributed to more unanticipated activities intended to realize the critical output before the elections could be held. To deal with the rising costs, some financing parties had to devise extra resources to bridge the gap.
### 3.5.8. Appropriateness of UNDP resource mobilization strategy
The mobilization strategy by UNDP was appropriate in the sense that efforts were made to bring on board other development partners to support the project initiatives. The bringing on board of DFID was indication of the power of UNDP to marshal effective resource mobilization for the project activities. The only loopholes that of course were not foreseen before was the delayed disbursements of resources from the DFID through UNDP to the implementing agency-CMD that in some instances delayed implementation of the some project activities.
## 3.6. Sustainability
Sustainability measures whether there was a sustainability framework, including an exit strategy, in place for the project. It assesses the measures the project has taken to prepare stakeholders and beneficiaries for continued operations in the event of cessation of funding. It also examines the measures the political parties have undertaken to prepare for changes in funding.
### 3.6.1. Assessment of the project’s sustainability
The evaluation assessed whether there have been any measures put in place to ensure project sustainability once the project has come to an end.
Our findings demonstrate that there was no specific exist strategy in place that could guarantee the continuity of the project activities. However, scrutiny of data available in the course of the interviews and documents reviewed point to some outcrops on to which the project can anchor its activities for sustainability. The evaluation noted that the existence of the CMD itself provides continuity in many respects. For instance some of the project activities were aligned in the CMD Strategic Plan 2017-2020 providing an ideal framework and continuity. Further, the CMD itself has established networks with stakeholders in government departments as well a civil society and international links in search for funding and networking. There are also projects that CMD is implementing that actually could be a continuity in line with project activities. These include the Cross Party Local Government Initiative funded by Tilitonse and enhancing Women Participation in Politics through Mentoring, funded by The Danish Institute for Parties and Democracy[33]. The implementing agency CMD also initiated fundraising networks with NIMD which are opportunities related sustainability.
[33] Minutes CMD Board Meeting held 8th May 2015
The evaluation noted the project implementing agency has demonstrated technical capacity exemplified in its well qualified staff, and permanent governance structure, focus on niche area an embrace of the sustainability of the project activities.
Respondents and documents reviewed also attest to a number of more other sustainability avenues for the project activities. Here below is what was identified:

Capacity acquired by the political parties in dialoguing, campaign on issue based using the policy based approaches was reported as having set root within political parties likely to be maintained as attested to by political party activists.

 As pointed out by some respondents, the project has influenced Participatory and consensus building in gathering views for advocacy as well as informing debates on the laws in the making. This has become an attitude changer with a cultivated culture that will go on within the political parties and government even when the project comes to an end hence contributing to sustainability of project activities.

Use the ICT particularly radio and Social media in activities of the project has served an important eye open to other stakeholders interested in promoting governance processes including the radio station itself. A number of respondents including the implementing agency promised to use the very avenue of mass media in their governance programming hence continuity that will guarantee sustainability of project activities.
### 3.6.2. Actions to strengthen project outcomes
 A number of key strategies and interventions have already been designed to enable the continuation of the project activities aimed towards realizing the project outcomes. Key among these is the CMD 2016-2020 strategy. The strategy clearly points out targeting stakeholders in the political and electoral processes in the country as one of the areas of principle focus. The strategy also clearly spells out that the principle focus of the five years plan is to ensure it makes critical inroads in areas of research, institutional capacity development financial sustainability and strengthening partnerships all geared towards multiparty democracy in Malawi the outcome of the project.

## 3.7. Cross Cutting Issues
### 3.7.1. Gender Equality targets
 During the document review and interviews, evidence adduced points to multi-pronged strategies and approaches by the project implementing agency(CMD) to mainstream gender equality targets. These approaches and strategies are derived from other projects under the CMD. Networks initiated in that regard have paid off contributing to the project efforts to addressing issue of inclusion of women in politics. Indeed, the efforts seemed to be paying off with evidenced from the increase in number of women that participated in the 2014 elections as demonstrated below quote: Overall, the total number of women candidates for Parliamentary seats in the country is 269. Out of this number 149 women candidates are contesting on party tickets. This means that 112 women candidates are contesting as independent candidates. The total number of women candidates for Local Government seats is 417. Out of this number 198 women candidates are contesting on party tickets, with 219 women candidates contesting as independent candidates[34].
[34] First quarter January-March 2014

The 50:50 campaign for women and coordinated efforts where CMD is a member of the Technical Working Group on the two projects/programmes being implemented by the Ministry of Gender in partnership with UNDP- the Political Empowerment of Women (PEW). CMD is also a member of the project on Women's Active Participation in Politics and Decision-Making with support from the Danish Institute for Parties and Democracy (DIPD). Such positioning of the project implementing agency is critical gender parity and continues to form an important link pin in the promoting the agenda of women inclusion thus contributing to project outcomes[35].
[35] Quarterly progress report Jan- March 2016
As the evaluation leant while interacting with respondents, there have been tailored programming initiated during the project to specifically support women participation in political parties. This initiative by CMD has encouraged the inclusion of women in political parties for example the inclusion of women in Board meetings and the rule of that for each party representation with CMD one of the three members had to be a woman[36]. This fostered women inclusion but it’s too early for the evaluation to judge that there has been increased women participation.
[36] Quarterly progress April-June 2016
Women aspirants to political office in Malawi face several constraints and challenges from within their parties and the electorate at large. According to some women Political activists interviewed despite the existence of women’s wings, women appear largely to be marginalized from the mainstream political leadership indicated that Parties are dominated by Men and patriarchy mindset hence rendering women to mere ceremonial figures who end up composing music and dancing for men during political activities.

While there are no formal barriers to women participating in politics, there are considerable informal barriers, nonetheless, that prevent women from playing their due role those that go through the race encounter a lot of challenges. Most women who have chosen to run for office have been the victims of vicious attacks on their moral character. All parties cited cultural and financial barriers as the main obstacles to women’s participation in politics as equals. These barriers are also reflected in the male-dominated party structures where many men continue to see women as a threat, rather than an equal partner and valuable resource in building support for the party. On the positive side, some parties were found to be electing women in important decision positions as well as attending trainings and exchange visits.

While the barriers to women’s political participation are deeply rooted in society overall, more could be done within the parties themselves to promote women to leadership positions. Political parties play decisive roles, especially in multi-party systems and in the transition to democracy, and reforms by the leading political parties would send strong signals to the electorate and help transform their attitudes towards women candidates who would in turn feel more committed to the party.

The Gender equality Act 2015, includes clauses to increase the role of women in political parties that will provide strong incentives for change such as Clause which stipulates ratio of 60:40: The proposed legislation can be a strong basis for advocates to promote policy changes in the parties.

The women’s organizers indicated a strong interest in having their women’s wings acquire the organizational and advocacy skills necessary to formulate policies to increase women’s participation and to initiate a sustained campaign to promote them. Based on the assessment, it seems there are men in the party who would support their efforts.

3.7.2. Women and Youth empowerment targets
CMD Strategic Plan 2016-2020 plans to chart a path for promoting women and youth in politics, as well as addressing inequalities, in general, on the political front. CMD hoped to also continue its work with key stakeholders to strengthen legislation and policy on political party registration and electoral processes[37] and mainstreaming issues to do with youth participation in politics. A new project had also been with the Liberal and Socialist parties of Denmark. An exchange visit to Denmark was organized for representatives of youth wings in Malawi, and it’s expected that the project will take shape to champion issues of youth representation[38].
[38] Quarterly progress July -Sept-2016
## 3.8. Lessons learnt
Critical lessons have been learnt that could inform future programming and lesson have been categorised into the design and implementation phases as listed here below:

Design phase

Evidence based planning
One major lesson during the design is the evidence based planning. The project was inspired and informed by the benchmarking study. Since the design followed an identified need, implementation was a response to that need. Thus project implementation is enhanced if the designed was informed by evidence of the problem and need. The benchmarking study in this case provided the analysis of the problem.

Ample time required to manage expectations
For projects that relate to politics and Political parties there is need to spend ample time in carefully designing the project in order to manage and minimize over expectations on the outcomes etc. of the project. More often than not targeted beneficiaries view such interventions as opportunities for raising funds. When their expectations are not met, their attitude towards the project is negative which affects the ability of the project to realise set out targets.
Tailor made designs to address certain aspects critical
Issue based platforms should have been designed differently stretching beyond actual elections in order to have more impact during and in between elections. This is because capacity for issues based platform provided an important avenues for political parties to develop competences nurture their will to persue objective approaches in delivering on their political agenda.

Lessons during the implementation phase
Mainstreaming results based management is key

Results based project management has to be mainstreamed at both the IP level but also the funding partners. There have been moments where attention has been focused on why a certain activity hasn’t been done instead of looking at a higher level outcome. E.g. output 2 activity result 2 action 1 (training in Communication) was never done because dissemination of issue based platforms was achieved satisfactorily under debates and the dissemination of inserts and brochures. This training would not add value to the outcome but despite not doing that, the expected result was achieved.

Dialogue and trust building were key to project success
Dialogue and trust building are key for the success of the project especially one being implemented in volatile social economic and political arena. In this regard, CMD dialogues were instrumental in bringing together the otherwise political parties that could not see eye to eye. This was attributed to the importance of having a neutral and professional secretariat in CMD that served as a neutral broker and facilitator of the dialogues initiative.
Documentation of events and activities very key to monitoring and evaluation of project activities
Documentation is critical for keeping track of developments in the environment such as major socio-political developments that occur to enable a project implementing agency navigate any challenges that may occur along the way but were not earlier on anticipated. Also documenting preliminary indicators along the way during monitoring activities makes reporting easier at a later date especially end of term evaluations.

Joint monitoring by project stakeholder timely measure for corrective measures
The need for active joint monitoring of the implementation of the planned activities by the partners is critical. For example the joint monitoring between UNDP and CMD has ensured that the project is on track and where possible it guarantees timely corrective measures. Additional monitoring visits by DFID and UNDP leadership gave a boost to project implementers at the local level to work harder.

Media critical tool to success of key project activities
The media is a critical tool and ally in the field of advocacy and public relations and exploration of innovative ways to exploit that potential is critical to achieving a lot by the implementing agency. Media especially the radio where reading culture is low has a multiplier effect in terms of mileage it can crate in activities related to advocacy and civic education campaigns.

Constant consultations with relevant stakeholders during project implementation creates synergy that re-energizes critical project activities
Constant consultations with relevant stakeholders during implementation of some activities evokes critical synergies that propel project implementation greater heights. The wide consultations in reviewing the Political Party (registration and regulation) Act, assisted in that the process of developing the draft bill took into account the expectations of relevant stakeholders with similar interests.

Guidance of project steering committee was handy at critical toward end of project life.
The Project Steering Committee is a very useful element of project implementation. The Committee guided the approach and strategic orientation of the program, particularly bearing in mind that this is the final year of the project. Guidance in most cases focused on covering up for activities missed in the preceding annual work plans and in most cases helped to realise the results of the project.

Pro-active engagement with stakeholders so that they appreciate political environment is important for enlisting critical support.

There is need to proactively engage Development Partners in order to understand the political environment since some political dynamic processes were taken for granted during the project design. Proactive engagement with partners has the beauty of being demand driven and can support derived therefrom can be better tailored to the needs of the recipient with high possibilities of creating more impact for the project in the long run.

# 4.0 CONCLUSIONS AND RECOMMENDATIONS
This section presents the conclusions and recommendations derived during this end of term evaluation.
## 4.1. Conclusion

At glance, the project made significant in loads towards the realization of the outcome despite the challenging environment in which it was implemented. Notable challenging aspects of the environment were the way it touched on the sensitive nerve centres like the pursuit to enact the PPRRA bill and there is glowing hope that soon or later the bill will enacted into law in the near future.

The project addressed the problem for which it was designed. It was able to build the capacity of political parties to participate in the democratic process of the country through interparty dialogues platforms and issues based campaigns as well as the trainings and awareness created by the project. The executing modalities of the project as laid down by UNDP as an executing agency and MDC as the implementing partner was strategic but it can still be improved as indicated in the recommendations.

The intended objectives and outputs of the strengthening the political project as outlined in the project document were achieved, both by way of implementation targets and intended results/effects with an exception of the PPRRA act but whose foundation has been well laid down by the MDC the implementing agency in conjunction with government and relevant departments. The project activities as set were adequate to realize the outputs and they contributed to the measure of effectiveness of the project.

The project was in line with defined needs of the political parties and other stakeholders. It can thus be said that it was justified and relevant in both the Country context as well as the context of the executing agency UNDP’s and the implementing partner MDC. The project contributed to the governance programme objectives of the UNDP Country programme and MGDS II. It was also relevant and in line with the strategic objectives of MDC as a national CSO champion the promotion of good governance and thus rightly placed the Political Party needs on the national agenda towards better multiparty governance.

The implementation of the project generated good lessons that not only inform improvement of the project in the remaining period but also for future programming to support politically sensitive projects in the future

Key sustainable aspects of the project are capacity built for political parties and its membership especially the women, youth; CMD itself as the implementing agency through competent staff recruitment as well as knowledge gained by the target beneficiaries. Although continuation of activities will not be possible without additional funding, skills and knowledge gained will be sustainable benefit to political parties and key government agencies like the Malawi Electoral Commission with of course a multiplier effect that cannot be under estimated.

## 4.2. Recommendations
The evaluation thus recommends the following:
Future project designs should tailor indicators to verifiable SMART indicators for better measurement of project outcomes
During design of future projects, effort should be made to come out with indicators that are refined in both qualitative and quantitative measurements that corresponds well with SMART indicators for ease of monitoring and evaluation of the results. This experience is drawn from the way some indicators of the project were designed that rendered them fall short of being verified using SMART. For example although quantitative measurements of indicators were critical aspects that could be easily measured they were not robust to bring out the qualitative change which is action oriented in SMART terms.
There should be strict enforcement of selection criteria for targeted beneficiaries of capacity building initiatives to ensure such initiatives yield maximum results
Selection of the targeted beneficiaries of capacity building initiatives should be strictly enforced against set criteria to ensure credible and transparent processes for better results of the initiatives. This recommendation draws from the experience where some people selected to benefit from trainings in election monitoring were illiterate while others lacked interest yet were selected by political parties to represent them. This flaw watered down the otherwise good intentions and ultimately affects delivery on results.
There should be continuous mentoring of political parties by supporting them to practice what they have been trained to do.
Capacity building initiatives focused on in-house management of political parties should be emphasized and continuously supported through mentoring to improve on functioning of political parties. This is because parties that received training have started managing well their in house business like keeping books of accounts and semblance of putting other systems in place. These developments form important building blocks for in house transparency and intraparty democracy.
Future initiatives should exploit and utilize capacity already built by the project to improve on their deliverables
The initiatives Already put in place should not be put to waste but used to enhance further the activities aimed at achieving the project impact. The attempt to link MPLCs with the security committees is positives step that could actually be exploited so that skills and experience of personnel from MPLCs could reinforce the operations of the security committees at first instance. This could go a long way in not only enhancing project activities but also strengthening such budding institutions thereby aiding them to perform their functions better in the forth coming general elections.
There is need for adequate funding for CMD strategy 2016-2020 to carry on the project related activities in future
The other way to convert the potential into success is to secure and provide adequate funding to the CMD strategic plan 2016-2020. The evaluation noted that the strategy has in place mechanisms and tailored programming to carry the mantle of the project to its success.
There is need to encourage and support the interface between political parties and parliament since they do complementary work
There is need encourage the interface between parties and Parliament since the work performed by these two institutions is complementary. This is the case because political parties provide the vehicle through which candidates get elected to Parliament while the work of Parliament is central to the realization of party policies and party electoral promises.

There should be institutionalization of political parties as way of promoting good governance within political parties themselves as a way for qualitative change

Promote the establishment of a multi-party system which encourages the emergence, development and institutionalization of democratic, transparent and accountable political parties. The success of the policy function of political parties require the existence of political parties that are properly structured, administered and run with proper structures, processes and systems for critical decision making exercises.

Political parties should undertake in-house research and documentation as a step towards acquiring capacity to meaning fully engage with external stakeholders and informed decision making.
Encourage political parties to establish and deepen their research capacity. While political parties can draw from existing research institutions, think tanks, NGOs and CSOs, they need to have credible in house research capacity which is instrumental in facilitating meaningful engagement with external stakeholders and making critical policy decisions and choices.
There is need to lobby for public funding mechanism to political parties that prove their worth
There is urgent need to lobby for the creation of a public funding mechanism for political parties represented in Parliament for purposes of harnessing their expertise, skills and knowledge in policy development. Parties require access to resources in order to constantly develop a critical mass well versed with matters of public policy inspired by their respective ideological inclinations and perspectives.

 There is need to promote engagement between political parties, Parliament and development agencies as way of parties making their priorities known to potential funders

Promote tripartite engagement between political parties, Parliament and development agencies so that parties get an appreciation of the perspectives of donors on policy issues. This interface would enable development agencies to get a feel of the development priorities that parties feel inclined to act on especially since it is the parties themselves that are critical players in the legislatures.

Future trainings in capacity building should have properly sequenced themes, timely and have wide covering so as have meaningful impact
- The training programs for election monitors should cover all the constituencies and districts and carried out well in advance to avoid rush that is usually not beneficial to both the targeted trainees and the project itself. The calls for better organization and management by polling adequate resources and selecting the right caliber people to undertake the trainings. Wide coverage of any training has an effect on effectiveness of the program ultimately yielding better results
- Background knowledge on the subject matter of any capacity building initiatives should be allotted own module to set the context and tone that enables participants appreciate and follow on matters related to policy formulation, campaigning and advocacy.
- The training programmes should be implemented timely in order to allow for the participants’ undivided attention so as to achieve the desired maximum strategic impact. Integration of the training programme into the electoral cycle is critical if premised on the understanding that elections are not a one off event but rather a process.
- For the sake of sustainability of the programme, it would be imperative to consider funding the development of manuals for each of these modules which the parties may use for reference in their day-to-day engagement as well as use for in house training targeting party cadres that would not directly benefit from CMD’s facilitated training opportunities.
There should be promotion of radio debates to help parties show case their policy positions to a wider audience
Radio debates among parties should be considered as one of the key elements of the programme which would help the parties to showcase their policy positions on various issues to a wider voting public. Radio debates are considered imperative in disseminating party positions on issues widely for two main reasons. Some parties, especially smaller ones, may not have the financial means to disseminate their policy positions widely. The dominance of the oral culture in the country implies that access to the materials would only be restricted to a very small proportion of Malawians who are able to read and write.

Political parties should properly facilitate their agents during election time to ensure they live up to the task at hand
During election time, the political parties should ensure that are represented by the election monitors who are well facilitated in all the polling stations. Good facilitation for agents enables them do a better For the Bill to be popularized once its passed there is need for Development partners to integrate such post PPs project into their newly planned governance and democratic program interventions especially CMD monitoring the PP in compliance with the Act while NICE can popularize to the masses through National Civic Education framework.
Other critical general recommendations
- Need for development of costed multi-media communication strategy for popularizing the PPRRA Act hand in hand with the Gender Equality 2015 Act
- Funding release and accountability in future upon UNDP/DFID etc approving the progress reports and QWPs/AWPs funds should be directly disbursed to CMD
- CMD and Political party institutional systems and capacities especially their respective Secretariats still need to be supported due to enormous work ahead especially as the Bill is passed to be able to ensure and monitor PPs compliance etc Other areas for strengthening and support are the IT systems and databases of PPs
- Youth and women wing specific and targeted programs should be designed and developed for strengthening PPs as there was no footprint noticed for roles of important organizations like Young Politicians Union (YPU)
# 5.0 ANNEXES
Annex i-List of the Persons Interviewed

Annex ii-List of Documents Reviewed
1. Audit Report for the year ending 2015-project- Strengthening Political Parties Project –UNDP and MDC 1st January 2015-31st December 205
2. Blessings Chinsinga-Benchmarking core capacities and capacities of political parties in Malawi, July 2011 prepared for CMD
3. Centre for Multiparty Democracy – Malawi Collaboration on the Reactivation of MPLCs Selection Criteria
4. Centre for Multiparty Democracy Strengthening Political Parties Project Third Quarterly Report July to September, 2016
5. CMD Annual Work Plan 2015
6. CMD Strategic Plan (2012-2016)
7. CMD Strategic plan 2012-2015, Second Draft
8. CMD-In between the ballot-Multiparty Liason Committees-activities to realize Output 4: Platform for Interparty Dialogue Strengthened to promote transparency & accountability and enhance credibility and legitimacy of political parties
9. CMD-Multiparty Liaison Committees active ratings- Output 4: Platform for inter-party dialogue strengthened to promote transparency & accountability and enhance credibility & legitimacy of political parties Indicator 1: Number of districts where Multiparty Liaison Committees (MPLCs) are reactivated-n the run-up to the May 2014
10. First Quarter Report January to March, 2016- Strengthening Political Parties Project 00071927
11. Malawi: 2014 general elections Key issues from political party manifestoes
12. Ministry of Justice Draft: Political Parties Bill, 2016
13. Minutes for MPLC meeting for Nsanje District on 1st October, 2015
14. Minutes of the second CMD-Malawi Board Meeting-held at Sun N Sund Holiday Resort, Mangochi-on 8th May, 2015
15. Minutes of the third CMD - Malawi Board Meeting held at Sun N Sund Holiday Resort, Mangochi- on 6th November, 2015
16. Nsanje MPLC 2nd October, 2013- Review of registration exercise
17. Quarter Report-April to June, 2016- Strengthening Political Parties Project 00071927
18. Strengthening Political Parties Project Annual Work Plan 2016
19. Strengthening Political Parties Project Malawi 2013-2016- Project Support Document January 2013
20. Terms of Reference End of Term Evaluation-Strengthening Political Parties Project- Project ID: 00071927
21. Catholic Commission for Justice and Peace; a Nation in Search of Redemption A Media and Advocacy Statement from the Catholic Commission for Justice and Peace 11th November, 2016
22. January to July 2015 Progress Report
23. Second Quarter Report for September, 2013
24. Strengthening Political Parties Project Report October, 2014

- Summary of the Field Visits
- ToR
- Tools Used- Self Assessment, Key Informant and Focus Group Discussion Guides