Type of Review: Annual Review

Project Title: Institutional Support to the Electoral Process in Malawi (ISEP)
 (2013-2017)

Aries Code: 203567

Date started: 15th February, 2013	Date review undertaken: January, 2014

Summary of results
Output/outcome	Scale	description
Outcome: 2014 Elections are credible and free with public debate informing voter choices and electoral cycle support sustaining capacity in electoral process	A	Outcome met expectation
Output 1: Capacity of MEC to deliver elections and advocate for electoral reform increased	A+	Output moderately exceeded expectation
Output 2: Capacity of Political Parties to develop issues-based electoral platforms, increase party democracy and promote reforms of the party system increased	A+	Output moderately exceeded expectation
Output 3: CSOs better able to deliver issue-based civic and voter education programmes and stimulate public debate	A	Output met expectation
Output 4: Civil society better able to monitor 2014 elections and speak out against cases of electoral malpractice	B	Output moderately did not meet expectation
Overall ISEP Annual Review rating	A	Met expectation

## Introduction and Context

What support is the UK providing?
The UK will provide up to £6.3 million between February 2013 and March 2017 to support long-term institutional strengthening of the electoral process in Malawi as outlined in the DFID Malawi Operational Plan. £6.1 million of this will be focussed on supporting the lead-up to the 2014 Presidential, Parliamentary and Local Government Elections, the actual elections and their immediate aftermath. Post-election support (2015/16 onwards) will be subject to the results of a post-election strategic review in DFID Malawi and the new UK HMG spending round. / The UK will deliver this support through: / Electoral-cycle support to the Malawi Electoral Commission (MEC) (£3.1 million) / This support is delivered via a multi-donor Basket fund managed by UNDP to achieve the following: / procuring technical support for the MEC (such as training for MEC staff and commissioners, short and medium-term technical and strategic inputs such as for ICT, budgeting, procurement and capacity development through on-the-job learning); / procuring material support for the MEC (such as ballot boxes, computers and ballot papers etc); / procuring human resource support for the MEC (costs associated with elections day temporary staff). / Issue-based Civic and Voter Education project (£2.4 million) / This support is through an Accountable Grant to NDI to support issue-based Civic and Voter Education (CVE) focused on two activities: / The development of coordinated issue-based platforms and materials by Malawi civil society partners that engage citizens around the electoral process and lay a foundation to strengthen the relationship between citizens and government; / Promoting confidence in election result through statistically sound domestic election observation. / Electoral-cycle support for Political Parties (£600,000) / This support is provided through DFID-UNDP joint funding to the Centre for Multiparty Democracy (CMD), an organisation run by the Political Parties to provide a forum for discussion and conflict resolution as well as a channel to provide multi-party support to strengthen Political Parties and the Political Party system. The support to CMD will help all major Political Parties get ready for the 2014 elections by: / developing policy platforms and preparing issue-based manifestos and campaign messaging; / providing a forum for where disputes can be prevented and resolved at the centre; / supporting local Multi-Party Liaison Committees to strengthen local dialogue and conflict resolution; / training political party monitors to help ensure the credibility of the electoral process. / Rapid Response fund to support unforeseen needs (£200,000) / The Rapid Response fund will be used to meet important and critical needs as they arise in the electoral process up to 2014. These needs are not defined but could include material, technical or financial needs of the various actors within the election process. Opportunities might arise where relatively small sums of money could make a difference to the credibility and freeness of the 2014 elections. The Rapid Response fund will be managed by a HMG Elections Committee combining staff from DFID and FCO. Decisions will be made by consensus on spending and implemented by DFID as part of this programme.

What are the expected results?
The expected impact of the programme is a strengthened ability of Malawi to deliver elections that are free, credible and with electoral outcomes informed by public debate. / The major outcome of the programme will be 2014 Elections are credible and free with public debate informing voter choices and electoral cycle support sustaining capacity in electoral process. / Specific results: Up to the elections, the following outputs are expected to be achieved: / Capacity of the MEC to deliver elections and advocate for electoral reform increased / Capacity of Political Parties to develop issues-based electoral platforms, party democracy and promote reforms of the party system increased / CSOs better able to deliver issue-based civic and voter education programmes and stimulate public debate / Civil society better able to monitor 2014 elections and speak out against cases of electoral malpractice

What is the context in which UK support is provided?
A successful electoral process requires that a number of organisations and agents central to the process have the necessary financial and technical capacity to fulfil their responsibilities. At the current time there are major capacity gaps within some of the key players, including the MEC, the Political Parties and Civil Society[1] that need to be addressed. / The MEC has rarely had adequate technical capacity to undertake its duties and has relied heavily on external support. In terms of electoral administration, the quality of elections in Malawi did not greatly improve between 1994 and 2004[2]. In terms of process and administration the 2009 election appears to have been an improvement from previous polls but was still flawed. The European Union Observer Mission in 2009 said “the elections fell short of fully meeting Malawi’s commitments to international and regional standards for elections as a number of key problem areas exposed structural and regulatory weaknesses…..these included limited capacity of the Electoral Commission”[3]. / At the current time the MEC is suffering from a number of key gaps in capacity that include: / the absence of key staff in the MEC, especially within the Finance Unit where 10 staff were suspended, preventing the recruitment of new staff; / a new set of Electoral Commissioners including the new Chairperson (who are barely 18 months into office) with low levels of experience of the Electoral process; and / the questionable legitimacy of the MEC resulting from its closure during late 2010/early 2011 for financial mismanagement. / On top of these gaps is a history within the MEC of poor management that in 2009 led to the Commissioners taking over the executive functions of the MEC’s work against the rules laid down in the legal framework[4]. / In terms of political parties, a study on Political Party Capabilities by CMD found parties lacking in almost all major capacity areas, buffeted by external factors and a failure to embed a democratic political culture in Malawi post-1994[5]. An increasing lack of internal democracy, a focus on a small elite cabal of leaders and a focus on internal party politics rather than developing positive political strategies for the mass electorate has led to a general disengagement of Malawians from active party politics. This trend is reflected in a recent Afrobarometer survey which showed the number of Malawians saying they felt “close” to a Political Party falling from 72% in 1999 to 60% in 2012[6]. The increasing number of independent MPs (currently 32[7]) is also symptomatic of these developments. / A 2010 situation analysis of civil society uncovered many of the problems that still lie beneath the surface of CSOs today[8]. It identified a weak institutional capacity, technical skills and human resources; an unpredictable financial base; and a lack of legitimacy. Where democracy and elections are concerned, civil society have tried to play two main roles: as domestic monitors of the electoral process and as implementers of civic and voter education (CVE) programmes. The capacity issues faced by CSOs have an impact on their ability to undertake either of these activities with success. / With regard to domestic monitoring of elections, the situation in Malawi has been characterised by a lack of coordination of domestic monitors (69 different groups were accredited for the 2009 elections) and a resulting failure of civil society to speak with one voice on critical issues. If coordination cannot be improved the 107 CSOs accredited for the tripartite elections will face similar challenges. Many of the monitoring groups also lack the capacity and funding to deploy observers to the field, and in the case of 2009 elections when they managed to deploy observers, their reports were often “very limited and shallow”[9] or took so long to produce they were not deemed credible. / In terms of civic and voter education, the penetration of civic education is seemingly quite low due to lack of capacity and financial resources for those CSOs and community groups implementing CVE. / Financial capacity is also lacking. The Malawian economy is facing difficult times and has slowed down since the highs of 2004-2009. It is faced with increasing inflationary pressure, and an increase in the price of imports due to devaluation and now the Cash-gate corruption cases leading to the loss of billions of public funds. This is already making it harder for the government to fully fund the increase from 193 electoral races at parliamentary and presidential levels, to the 655 required for the tripartite elections. Development Partners will provide up to 40% of the 44 million dollars elections budget with Malawi government supporting at least 60%. / The above text shows how capacity gaps can impact negatively on Malawi’s ability to deliver free and fair elections. However, increasing financial resources and technical capacity alone has rarely been enough to achieve free and credible elections[10]. This is because the electoral process, like any political institution, is deeply influenced by the struggle between competing groups for access to power, and especially by the different ways in which they seek to advance their claims. / Formal rules do exist which govern the actions and duties of actors and organisations in the electoral process. For example, the independence of the MEC, a free media and and a sound electoral environment where people are free from any form of coercion and intimidation. However, Malawi’s history suggests that the implementation of these formal rules by those in power has been lacking. The MEC was closed by Government in 2011 for almost 6 months; Government withdrew advertising from critical media and banned some papers from Government buildings; and the local elections have been “postponed” since they were last due in 2005. In Malawi this has progressively led to the de-legitimisation of the electoral process and the results it produces. For example, 35% of the population see the MEC as a partial body and 60% of people think their MPs never listen. 40% of people see Malawi as either not a democracy, or a democracy with major problems.[11] / A political-economic reading of the Malawi context suggests that political elites prefer to use traditional, informal, patrimonial systems to gain votes rather than subject themselves to open political competition regulated by strong, formal organisations and institutions, and so have a vested interest in ensuring these organisations have weak capacity and formal rules are not implemented[12]. / Therefore, strengthening the Malawian electoral process will be necessary if democracy and good governance are to be entrenched in Malawi. This requires not just a major investment in sustained technical capacity building of electoral organisations and actors but also support for institutional change in the Malawian political system to move incentives for elites away from power being won and shared through informal patronage-based electoral platforms. / Has the context changed since we approved our support? / The trajectory is more positive with a MEC which has the marks of being professional, open and engaging and less influenced by the political elites. Tensions between government and civil actors have died down and the environment is more conducive for the running of elections. However, in terms of delivering a credible election, concerns remain as the Malawi government still lacks the necessary capacity to deliver a tripartite election and political parties are still struggling with internal democratic values and a continuously weakened civil society. / The recent revelation of gross mismanagement of the public funds by some government officials is a major setback to the confidence of the international community and general public in the Malawi government. The effect of this on the electoral process is huge. Although there is assurance from the donors that the elections budget will be sustained, there is uncertainty about whether the government can actually manage to support its 60% share of the elections budget given donors’ decision to freeze budget support which is making it challenging for the government to run public services. Patronage tendencies and a culture of hand outs still exist and this needs concerted efforts to counter.
[1] For example, see European Union Election Observer Mission (2009), “Malawi Presidential and Parliamentary Elections May 2009” and ed. Martin Ott and Fidelis Edge Kanyongolo (2009) “Democracy in Progress: Malawi’s 2009 Presidential and Parliamentary Elections”
[2] Rakner and Svasan (2005), “Maybe free, but not fair: Electoral Administration in Malawi 1994-2004”,
[3] European Union Election Observer Mission (2009), “Malawi Presidential and Parliamentary Elections May 2009”
[4] UNDP Brief Assessment of the Elections, January 2012 plus information provided at the meetings of the Electoral Task Force (see minutes of meetings in 2012)
[5] Centre or Multi-Party Democracy (2012), “Benchmarking of core capacities of political parties in Malawi”
[6] 2012 Afrobarometer data (unreleased)
[7] Ibid
[8] Robert White (2010), “State of Civil Society in Malawi”
[9] Ott, M “The role of international and domestic observers in” ed. Martin Ott and Fidelis Edge Kanyongolo (2009) “Democracy in Progress: Malawi’s 2009 Presidential and Parliamentary Elections”.
[10] Pycroft and Butterworth (2005) “Where Capacity is not the only problem”, World Bank Information Briefing
[11] 2012 Afrobarometer data (unpublished)
[12] Chiweza, Foot and Waldock (2011), “Development and Change in Malawi” (unpublished)

## Section A: Detailed Output Scoring
Output 1: Capacity of MEC to deliver elections and advocate for electoral reform increased
Output 1 score and performance description: Output 1 final score: A+ / This output is measured by the following indicators; i) Percentage of milestones of the electoral calendar achieved on schedule, ii) Progress in the MEC using formalised/codified inter-institutional arrangements, and III) Percentage of Null and Void votes (this will be measured after the elections). Based on achievement of milestones for 2013, the rating for this output is A+ (Outputs moderately exceeded expectation). / Evidence / Output indicator 1.1: Percentage of milestones of the electoral calendar achieved on schedule: The milestone for 2013 was 60%. MEC has posted 68% of the key activities on the electoral calendar achieved on schedule. The key activities include: demarcation of ward boundaries, development of the electoral budget, harmonisation of the electoral laws, accreditation of CVE service providers, registration of voters and distribution of nomination forms. / Demarcation of wards: Demarcation of wards was done on time and the process resulted in the establishment of 462 wards which parliament approved as the legal units for the conduct of the 2014 tripartite elections. In the 2000 local government elections, there were 440 wards. / Electoral budget: The MEC delivered the budget within its planned time frame of February to April, 2013 and the budget was approved during the Annual Budget sitting of parliament in June, 2013. The MK18 billion budget is being followed by both donors and government with government shouldering 60% and donors 40%. / Electoral laws: The MEC reviewed electoral laws and compiled a list of proposals for amendments in parliament. These included the MEC’s lack of jurisdiction over local government elections, which was not addressed by the subsequent constitutional amendment of section 147; wider publication of MEC notices than through the Gazette; candidate and voter registration eligibility criteria and timelines; determination of the candidacy deposit amount; removing withdrawn candidacies from the ballot; District Commissioner discretion to prohibit campaign rallies; liberalisation of campaign regulation; reinforcement of public media regulation; effective remedies for party agents; more flexibility to adjust polling equipment; shortening of voting hours, while allowing the MEC to exceptionally extend polling; ballot invalidation criteria; ballot chain-of-custody; complaints, appeals, swearing in timeline; and the rights of national as compared to international observers. All these were approved in parliament apart from the shortening of voting hours. / Accreditation of CVE service providers: 107 CVE service providers were accredited to provide CVE Education. MEC coordinated several meetings of the CVE service providers leading to the establishment of a CVE Implementation Coordination Working Group chaired by the MEC which now meets monthly to review and coordinate CVE activities with support from UNDP and UN Women. Owing to this arrangement, there is sharing of information amongst donors who are providing bilateral support to CVE service providers to ensure that there is no duplication of funding and ground level coverage. / Registration of voters: The MEC completed the registration of voters by December before reaching the expected last phase 10 which was planned for January, 2014. During the exercise, the Commission registered a total 7,537,548 voters nationwide. This represents 94.10 percent of the projected total for the exercise which was 8,009,734 registrants. The total registered is also 16 percent above the 6,500,759 voters in 2010. Of the total registered voters, 3,481,365 are men representing 46.19 percent while 4,056,183 are women representing 53.81 percent. / Nomination papers: Distribution of nomination papers has been timely and the process has been made much easier and orderly for Political Parties. The MEC has distributed nomination papers through CMD where all political parties will collect nomination papers for their candidates and in all district assemblies where independent candidates will collect their nomination papers. Nomination fees were announced six months in advance, enabling aspirants to get prepared for the nomination exercise. / Achievement of the milestone for output indicator 1.1 is therefore rated as A++ (substantially exceeded expectation) / Output indicator 1.2: Progress in the MEC using formalised/codified inter-institutional arrangements. This indicator measures MEC capacity to coordinate the participation and use of various state and non-state institutions through formal agreements to support the electoral process. The Milestone for 2013 was “Election observers and CSOs are accredited for 2014 elections & sign revised code of conduct”. / The MEC accredited 107 CVE service providers and provided orientation for the proper delivery of CVE services. The expected number of CVE service providers was 60. The MEC issued formal invitation letters to both local and international observers to participate in observer missions for the registration and the actual voting process. The Elections Basket Fund Project has also assisted the MEC with the development of codes of conduct, including CSOs engaged in Civic and Voter Education (CVE), the Media and Political Parties. The MEC is further pursuing the Political Party Code of Conduct to be promulgated as a regulation through the Minister of Justice. The Project has facilitated the engagement of UN Women through the UNDP Political Empowerment of Women (PEW) project as well as the UN Peace and Development Advisor to ensure that gender and conflict sensitivity have been mainstreamed as cross-cutting concerns. Each Code has been concluded through consultative public processes with the respective key stakeholders to ensure transparency, consensus and ownership in the outcome. In this period, the MEC’s engagement with other institutions has principally been through established multi-agency task forces, such as the Transportation Task Force, to coordinate governmental resources in support of the process. / Achievement of indicator 1.2 is therefore rated as A+ (moderately exceeded expectation) / Output 1 indicators Baseline Milestone 2013 Achievement of milestone / 1.1. Percentage of milestones of the electoral calendar achieved on schedule / Indicator Rating / A++ Not yet started 60% 90% of the activities of the Electoral calendar have been achieved on schedule. / 1.2 Progress in the MEC using formalised/codified inter-institutional arrangements. / Indicator Rating / A+ No codified inter-institutional arrangements in place Election observers and CSOs are accredited for 2014 elections & sign revised codes of conduct 107 CVE service providers were accredited. The target was 60. International and local observers were officially invited to participate in the observation of the electoral process. This was done well in advance of the expected timeline. / Of the 4 codes of conduct expected to be signed between the MEC and electoral stakeholders during the electoral process, 3 were already signed in 2013 and these were the Political Parties Code of Conduct (which is usually signed at nomination and campaign time but was signed months in advance), the Media Code of Conduct and the CVE Service Providers Code of Conduct. / Recommendations: MEC should re-submit the proposed legal amendment on shortening of voting hours.
Impact Weighting :50% / Revised since last Annual Review? Not revised / Risk: Low/Medium/High: Medium / Revised since last Annual Review? Revised (The original rating was high but due to MEC, Donor and government collaboration, MEC and stakeholder performance seems to be on track)

Output 2: Capacity of Political Parties to develop issues-based electoral platforms, increase party democracy and promote reforms of the party system increased
Output 2 score and performance description: Output 2 final score: A+ / This output is being measured by the following indicators: i) Member Political Parties’ constitutions aligned with the revised political parties act, ii) Number of districts where Multiparty Liaison Committees are reactivated, and iii) Number of member Political Parties signing up the National Code of Conduct for Political Parties. Based on achievement of milestones for 2013, the rating for this output is A+ (Output moderately exceeded expectation). / Evidence / Output indicator 2.1: Member Political Parties constitutions aligned with the revised political parties act. The milestone for 2013 was 40%. The new Political Parties bill has been drafted and a Reference Group comprising the Law Commission, Solicitor General, Malawi Law Society and the Registrar of Political Parties has been constituted to further work on the Draft Bill. Critical areas of the bill include: raising the minimum number of people who can register a political party, extending the scope of entitlement to state funding, enhancing the independence of the Registrar of Political Parties, establishing accountability for state funding, enhancing transparency on assets held by Political Parties, improving access to party information by members, and encouraging intra-party democracy e.g. holding of conventions. Consultation meetings have been held with Political Parties and the general public throughout the country and the Legal Affairs Committee has been engaged to provide direction. The Minister of Justice has been referred and there is increasing pressure from Political Parties themselves to have the bill put before parliament in the coming sessions. / A lead facilitator has been engaged to conduct a review of the selected Political Parties’ constitutions. In total, eleven constitutions have been collected and are under review to establish the extent to which they entrench the provisions for intra-party democracy. Assessment criteria have also been discussed and agreed with CMD. Of the eleven, eight are members of CMD, and these are: Alliance for Multiparty Democracy (Aford); Democratic Progressive Party (DPP); Mafunde; Malawi Congress Party (MCP); People’s Party (PP); People’s Progressive Movement (PPM); People’s Transformation Party (Petra); and United Democratic Front (UDF). However, much attention is being focused on those parties with representation in Parliament, and these are: the Democratic Progressive Party (DPP), the Malawi Congress Party (MCP), the People’s Party (PP), the Alliance for Democracy (Aford), and the United Democratic Front (UDF). / Internationally, three constitutions have been collected from the African National Congress (ANC) of South Africa, Chama Cha Mapinduzi (CCM) of Tanzania, and the National Democratic Congress NDC) of Ghana. A preliminary presentation was to be made to the CMD Board during the December quarter Board sitting. Based on this progress, the achievement of milestone for output indicator 2.1 is rated as A+ (moderately exceeded expectation) / Output indicator 2.2: Number of districts where Multiparty Liaison Committees (MPLCs) are reactivated. The milestone for 2013 is 12 districts. CMD has selected and facilitated the reactivation of MPLCS in the following districts: Rumphi, Mzimba, Nkhatabay, Lilongwe, Mchinji, Dowa; Dedza, Mangochi; Mulanje, Thyolo, Blantyre, and Nsanje. The reactivation process started with preliminary consultative meetings with the 12 District Commissioners who all eagerly welcomed CMD’s initiative. MPLC activities have since been taking place in several districts to defuse tension among political parties. Issues discussed in these meetings concern factors that ignite conflict and violence in the districts such as provocative campaign speeches, disruption of campaign rallies and destruction of campaign materials, the partisan position of some chiefs and civil servants, and monopoly over venues for rallies. In the course of discussions, participants have also been able to explore and agree on how to peacefully resolve conflicts and ensure co-existence between and among political parties as well as other key stakeholders. Based on this progress, the achievement of milestone for output indictor 2.2 is rated as A (met expectation). / Output indicator 2.3: Number of member political parties signing up the national Code of Conduct for Political Parties. The milestone for 2013 is 6. All Political Parties represented in Parliament and 2 non-Parliamentary parties, i.e. PPM and Petra signed the National Code of Conduct. In its contribution to this process, CMD provided technical input that shaped the review of the Code of Conduct, facilitated dialogue between Political Parties and the Malawi Electoral Commission, as well as mobilised and lobbied political parties to reach consensus on the contents of the Code of Conduct. The code of conduct was signed in June, 2013 and although legal enforcement can only start during the official campaign period, the parties agreed to abide by the code of conduct from the signing date to the end of the electoral process. The Code of Conduct is being monitored by both CMD and the MEC. Based on the progress the achievement of milestone for output indicator 2.3 is rated as A+ (moderately exceeded expectation).
Progress against expected results: / Output indicators 2 Baseline Milestone 2013 Achievement of milestone / 2.1 Member political parties’ constitutions aligned with the revised political parties act / Indicator Rating / A+ 0 40% Eleven constitutions of Political Parties (representing 137.5%) were collected and reviewed to establish the extent to which they entrench the provisions for intra-party democracy. Assessment criteria had also been discussed and agreed with CMD. Of the eleven, eight are from the members of the Centre for Multiparty Democracy (CMD). The report was due to be presented to CMD Board in the December Board siting. / 2.2 Number of districts where Multiparty Liaison Committees are reactivated / Indicator Rating / A 0 12 Consultative meetings were held with the District Commissioners in all the 12 districts. Earnest meetings started in 11 districts with Lilongwe starting late in December. / 2.3 Number of member political parties signing up the national Code of Conduct for Political Parties / Indicator Rating / A+ 0 6 All 6 Political Parties represented in Parliament and 2 non-Parliamentary parties, i.e. PPM and Petra have signed the National Code of Conduct. / Recommendations: / The cash-gate scandal has contributed to creating a growing interest in the Draft Bill because it is seen as essential in the fight against abuse of public resources by a party in government. To build on this momentum, CMD should ensure it enacted as soon as possible. / CMD should take steps to increase its coordination with the other organisations that are working with MPLCs namely CMD, NICE and GIZ in order to harmonise certain inputs like training and conflict management approaches. / Impact Weighting: 10% / Revised since last Annual Review? No / Risk: Low/Medium/High Medium / Revised since last Annual Review? Yes (The original rating was high due to the sensitivity of political party support. However after CMD carefully developed criteria for which parties should benefit from the programme, there has not been any tension or resentment. The risk was therefore scaled down to medium)

Output 3: CSOs better able to deliver issue-based civic and voter education programmes and stimulate public debate
Output 3 score and performance description: Output 3 final score: A / This output is being measured by the following indicators: i) Number of voter education kits produced, ii) Number of townhall/issue-based public information campaigns completed by civil society partners, iii) Number of candidates debates conducted. The achievement of this output is rated s A (output met expectation) / Evidence / Output indicator 3.1: Number of CSOs participating in the programme: The milestone was 31. The programme planned to support 19 CBOs and 12 NGOs through small grants and sub-grants to participate in Issue-Based CVE. The total number of grants given is 31 which means a 100% achievement of the set milestone. The achievement of the milestone for output indicator 3.1 is therefore rated as A (met expectation) / Output indicator 3.2: Number of townhall/issue-based public information campaigns completed by civil society partners. The milestone for 2013 was 40. Forty-seven (47) issue identification and outreach activities have been conducted by CVE partners, including meetings with district executive committees, issues identification exercises, printing and distribution of education materials and community/townhall meetings. Partners have undertaken activities in 20 districts, including Chiradzulu, Thyolo (including Luncheza), Zomba, Mangochi, Phalombe, Chikhwawa, Mneno, Mulanje, Kasungu, Dowa, Mchinji, Lilongwe, Dedza, Ntchisi, Nkhotakota (including Luncheza), Chitipa, Mzimba, Rumphi, Nkhatabay and Karonga. According to partner reports and estimations of attendance at such events, activities have reached more than 13,500 people in these districts. Based on this progress, the achievement of milestone for output indicator 3.2 is rated as A+ (moderately exceeded expectation) / Output indicator 3.3: Number of candidates’ debates conducted. The milestone for 2013 as revised in the logframe is 0. However, preparatory work has already started. In August, NDI coordinated with Malawian civil society organisations (CSOs) to create a task force on presidential debates. The task force, with financial support from MEC and technical assistance from NDI, has met three times to discuss and plan the organisation of presidential debates for the upcoming elections. Members of the task force are drawn from civil society and media organisations each charged with the responsibility to look into all modalities of hosting the debates. Once the nomination of candidates has been completed in February, 2014, debates will start in wards, constituencies and at national level. Although actual debates did not happen on account that there were no official candidates before the nomination period, achievement of milestone for output indicator 3.3 is rated as A (met expectation). This rating is justified as all the critical preparatory work has been done apart from the actual debates which could not be done because there were no official candidates.
Progress against expected results: / Output indicators Baseline Milestone 2013 Achievement of milestone / Number of CBOs participating in the programme / Indicator Rating / A 0 31 19 Community Based Organisations and 12 NGOs have been awarded grants and are implementing CVE activities in 20 districts. The total number is 31 and this represents 100% achievement of the set milestone. / Number of townhall /issue-based public information campaigns completed by civil society partners. / Indicator Rating / A+ 7 40 Forty-seven (47) issue identification and outreach activities conducted by CVE partners, including meetings with district executive committees, issues identification exercises, printing and distribution of education materials and community/townhall meetings. / Number of candidates’ debates conducted / Indicator Rating / A 0 10 Through the MEC, a taskforce is in place which has been holding meetings to prepare for the debates. The debates will be held once nominations have been made. / Recommendations: / Impact Weighting : 20% / Revised since last Annual Review? Not revised / Risk: Low/Medium/High Medium / Revised since last Annual Review? Not Revised

Output 4: Civil society better able to monitor 2014 elections and speak out against cases of electoral malpractice
Output 4 score and performance description: Output 4 final score is B / This output is being measured by the following indicators: i) Number of citizen observers trained on how to conduct a Parallel Voter Tabulation (PVT - disaggregated by sex and age), ii) Percentage of observers that transmit data to a central information centre, including the vote count from randomly sampled polling stations on election day, iii) Number of public statements that civil society partners issue using PVT analysis. Apart from indicator number 1, the rest will be measured in 2014. The achievement of this output is rated as A (output met expectation) / Evidence / Indicator 4.1: Number of citizen observers trained on how to conduct a PVT (disaggregated by sex and age). The milestone for 2013 was 813. Due to electoral timeline and logistical necessities, observers will be trained in 2014 and will be deployed to centres immediately after training. However, all the preparations for the training and deployment are on track: MESN has been given a grant to manage the PVT and they have taken steps to prepare for the observer role using the PVT. Three (3) regional workshops on electoral observation were held in Blantyre, Lilongwe and Mzuzu in late June 2013. Sixty-three (63) participants (including 12 women) from 50 organisations participated in the workshops. A report from the workshops helped inform strategic planning sessions, as well as the electoral observation and information, communication and technology (ICT) assessment. MESN has fully established the secretariat to run the PVT with full time staff. Discussions and consultations with political parties, the MEC and all stakeholders are underway. The MEC has issued official statements in several media outlets and forums to endorse the PVT. Therefore since observers were not trained in 2013, the achievement of milestone for output indicator 4.1 is rated as B (moderately did not meet expectation)
Progress against expected results: / Output indicators 4 Baseline Milestone 2013-2014 Achievement of milestone / 4.1 Number of citizen observers trained on how to conduct a PVT (disaggregated by sex and age). / Indicator Rating / B 0 813 Three (3) regional workshops on electoral observation were held in Blantyre, Lilongwe and Mzuzu in late June 2013. Sixty-three (63) participants (including 12 women) from 50 organisations participated in the workshops. A report from the workshops helped inform strategic planning sessions, as well as the electoral observation and information, communication and technology (ICT) assessment. MESN will recruit and train observers in 2014 with a view to deploying them immediately after training to observe elections / Official statements from MEC to endorsing the PVT have been made and political party support for a PVT has been obtained. / Recommendations: / Impact Weighting:20% / Revised since last Annual Review? Not Revised / Risk: Low/Medium/High : High / Revised since last Annual Review? Not Revised

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the log-frame been updated since last review? Yes, some milestones in the main log-frame have been revised together with the log-frames of the various ISEP components. When the ISEP Business Case was submitted, it was made clear that there would be an update of the log-frame based on the log-frames of its three main components. The first major revision of the ISEP Log-frame was done in July, 2013. Because of developments in the electoral process, the ISEP main components were revised towards the end of the year and this has led to further changes in the ISEP Log-frame. For example the Political Parties project was originally designed on the basis of a $2,800 million budget. However UNDP did not manage to engage other donors to raise all the resources planned for and the project was launched with a budget of $1,600 million (£1,200 million). As a result, it will not be able to deliver results at the scale first envisaged. The log-frame has been revised so that milestones and targets are in line with the results that can realistically be achieved with the final budget. For instance, while the original project planned to work with 12 parties, the project is now only targeting half of these. This is now reflected in the ISEP main log-frame. Risk matrices and implementation plans have also been revised for both the ISEP main programme and its components. / This Annual Review is based on the Logframe which has just been updated (January, 2014). A revised Logframe is submitted together with the Annual Review for approval by DFID Malawi’s Head of Office. / 1.2 Overall Output Score and Description: / The aggregate score for ISEP in the first year of its implementation is rated as A (Outputs met expectations). There has been good progress towards achievement of its 4 key outputs with output 1 which relates to increased capacity of Malawi Electoral Commission to manage the tripartite electoral process attaining a rating of A+, output 2 which relates to the capacity of Political Parties to prepare policy platforms and embrace democratic values attaining the rating of A, output 3 which relates to civil society coordinating issue-based platforms and engage citizens around issue based campaigning attaining the rating of A, and the domestic observation to bring confidence in the electoral process attaining the rating of B. / 1.3 Direct feedback from beneficiaries / ISEP beneficiaries are diverse ranging from the MEC, Political Parties, CSOs and citizens. During the process of this Annual Review, a cross section of stakeholders and beneficiaries were interviewed and the general impression is that the programme has played a vital role in supporting the implementation of the electoral process. / Feedback from beneficiaries in the Political parties project: / Data collection from UNDP monitoring visits shows that political parties appreciate the interventions. For instance the training sessions conducted through the project have brought confidence in the youth to take leading positions in the party hierarchies. Feedback from beneficiaries has also been obtained directly by DFID through field visits to monitor selected project interventions. Monitoring of the CMD workshop with political parties to develop their policy platforms was conducted in Mangochi. The DFID team also carried out monitoring of a Multiparty Liaison Committee Meeting in Nsanje. / A UDF representative attending the workshop to develop policy was highly positive about the process: “This is the first time us politicians have been involved in formulating our policies. In the past the task was given to technocrats. There were brilliant ideas and it has been very participatory. It is a very positive development.” / Feedback from beneficiaries in the in the Issue-Based CVE Project / DFID and NDI held a joint Annual Review meeting in the rural area of Mhuju in Rumphi district where the National Women’s Lobby Rights Group is implementing the Issue-Based CVE project. Various remarks made indicated that the project has changed the whole electoral campaign discourse as communities and voters have been empowered to engage electoral contestants and political parties on issues and policies which parties will implement once they are voted into power. In his remarks, TA Mhuju said… “in all the elections since multiparty democracy, we were told to vote for leaders without understanding what policies they have and what promises they will deliver to our communities. In these elections, we have been trained and we have gone out fully fledged to engage our communities to identify issues which should be the centre of focus when those who want to contest for ward councillor and MP positions in this area come to meet us and conduct their campaigns. We will challenge those who come to castigate others and give us money and goods for our votes. This election will not be for such people…” / . / TA Mhuju: In grey suit and black hat
1.4 Summary of overall progress / There has been good progress generally and the electoral process has not been dogged by challenges to the degree it was predicted when the programme was being designed. The support to the MEC through the UNDP Elections Basket Fund has made a significant contribution to the way elections are being coordinated. Hitherto, there have not been any major challenges to the delivery of the key milestones on the electoral calendar. The Issue Based CVE is now in full operation and once the nomination of candidates is complete in February 2014, the activities will gain pace to ensure that communities engage their candidates on policies and issues of concern. Political Parties have intensified their policy and manifesto preparations. With CMD support all key parties have finalised their party policies and manifesto bulletins which are now ready to be mass produced and disseminated throughout the country. Preparations for political debates are at advanced stage, with the first debates ever to happen at presidential level in the election history of Malawi.
1.5 Key challenges / UNDP Elections Basket Fund component / Unusually competitive elections for Malawi creating an atmosphere of heightened political distrust between parties and government actors. This affects the role of the MEC as some stakeholders feel the elections could be in danger of manipulation. / Executive decision making of the electoral commission is hampered by the part-time status of Commissioners which means that is challenging for them to meet regularly, given their operational commitments. / Economic environment and public sector finances creating currency fluctuation. / Financial systems and capacity of government to support elections in light of Cash Gate scandal. Government has introduced monthly regional ceilings and MEC is affected considering that it incurs huge payments to run elections and celling are reached for the region before MEC can make all its payments to its service providers. / Issue- Based CVE Education project component / Lower levels of capacity than expected in overall project management among the selected sub-grantee partners led to a brief delay in the start-up of some partner activities. In order to address this and ensure partners were prepared to manage their activities under this programme, NDI spent a significant amount of time during the start-up of the programme to help partners develop risk management and monitoring and evaluation plans prior to the implementation of project activities. The Institute continues to work with the local partner organisations to revise their work plans to reflect new implementation timelines and strengthen their organisational capacities. / As highlighted in NDI’s election and ICT observation assessment, for the most part new MESN board members lack experience and knowledge of conducting PVTs. The board was recently elected and many of its members did not participate in the 2009 elections. Through a training workshop, NDI introduced board members to the PVT methodology and facilitated a discussion about how the proposed PVT and systematic long-term election observation would be implemented within Malawi’s current political context. In addition, NDI plans to provide training to MESN to help the organisation integrate technology approaches based on best practices learned from PVTs that the Institute has supported in Zimbabwe, Kenya and Ghana. / Political parties project component / The major challenge has been the 3 months delay in starting the project because of delays with formalising the project document and funding agreement. Although the project tried to fast track implementation of activities, it is clear that tight schedules especially for political parties are causing delays to some of the activities.
1.6 Annual Outcome Assessment. / Outcome Annual score is A (Outcome met expectation) / The outcome statement is “2014 Elections are credible and free with public debate informing voter choices and electoral cycle support sustaining capacity in electoral process”. The outcome is measured by the following indicators: i) People who Trust the Malawi Electoral Commission, ii) Majority verdict on the freeness and credibility of Malawi 2014 Elections, iii) Percentage of agreed Strategic Plan activities achieved on schedule. The measurement of Milestone 1 is based on Afrobarometer survey results which are due to be released in 2014. However, performance of the MEC will still be determined by the actual progress seen on the ground and reported in UNDP Basket Fund reports. The freeness and credibility of the polls will only be assessed after the actual voting. Evidence from reports of the UNDP Basket fund show that MEC achievement of activities in its Strategic Plan is high and the overall progress is impressive. Therefore the achievement of milestones for outcome indicators is rated as A ( Met expectation) / Evidence / Having delivered the registration of voters on time with a 94.10% of all eligible voters, the public confidence in the MEC has improved significantly. Key political parties express confidence in the independence of the MEC. The manner in which the MEC has organised the nomination process has further increased stakeholders trust in the MEC’s performance. The MEC has implemented several of the guiding principles and actions that were elaborated in the Strategic Plan such as for example: / releasing the 2010 Audit Report / establishing an Audit Committee / recruiting internal auditors / re-establishing the National Electoral Consultative Forum (NECOF) as a regular national level meeting for political parties and other stakeholders to complement district level Multi-Party Liaison Committees (MPLCs), as part of its planned activities to enhance transparency and consultation / The MEC has translated most of the key activities of its Strategic plan into the Electoral Calendar and the assessment shows that MEC has achieved 68% of its planned activities on the electoral calendar. The general environment for a free and credible election is promising. The MEC has been able to publicise all its key activities and decisions through the media, stakeholders forums and meetings, and has also shown itself to be responsive to the concerns of stakeholders. / Outcome Indicators Baseline Milestone 2013 Progress on Milestone / People who Trust the Malawi Electoral Commission / Indicator Rating / A 41% 45% Afrobarometer results will come out in 2014. However, indications are that public opinion about the performance and trust in MEC is gradually being restored due to its open and transparent electoral processes and especially as a result of the way it delivered the registration process which achieved a 94.10% registration of all expected voters. / Percentage of agreed Strategic Plan activities achieved on schedule. / Indicator Rating / A 0 30% The MEC has implemented several of the guiding principles and actions that were elaborated in the Strategic Plan. Most these were included in the electoral calendar and MEC has delivered all its activities for the period January, 2013 to February, 2014. Based on activities of the electoral calendar, 68% has been achieved.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Overall, the project has been on track against its financial forecast. There have been some adjustments to individual budget lines which have balanced each other out. For instance, the support to the UNDP Elections Basket fund had to support MEC to do an unplanned emergency purchase of additional scanners for use in the compilation of the voters’ roll since the other scanners broke down. The savings achieved by the MEC by allowing some registration materials to be bought using government money instead of donor money will help to cushion the gap. / 2.2 Key cost drivers / The main programme cost drivers are as follows: / MEC capability: Interventions have been justified based on supporting the expansion of capability (e.g. procuring extra voter registration kits) to enable larger numbers of teams to operate simultaneously, thereby reducing the period of field work and the risk of higher costs being incurred during wet weather conditions. Interventions via operational, contingency and risk planning have been made to assist in streamlining activities, thereby reducing shorter timeframes and higher costs for downstream activities. / Travel costs: The CVE and Political Parties components have a significant proportion of interventions at this early stage which involve people travelling for meetings and workshops. As a result travelling costs and accommodation have been the main cost drivers so far. / 2.3 Is the project on-track against original timescale: / Generally, all the three main components of the programme are on track in terms of implementation plans and achievement of Milestones. The only area of concern has been the Political Parties Bill which has not yet gone to Parliament due to lengthy consultations with stakeholders. The Bill is now in its final stages and awaiting submission to the Minister of Justice.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The ISEP main log-frame was revised in July 2013. There has been another revision following the observations during the Annual Review. Some milestones and targets have changed. / 3.2 Where an evaluation is planned what progress has been made? / There is no external evaluation for this programme.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Overall output risk is rated as medium / 4.2 Assessment of the risk level / The overall risk level remains as it was at the time of designing the programme and drafting of the log-frame. However, risks related to output 1 and 2 have been reviewed. Output 1 risks have been scaled down from high to medium. At the design and approval stage, MEC delivery capacity was considered high risk due to uncertainty about the funding. Since both donors and government agreed on cost sharing the elections budget this risk was scaled down to medium. Output 2 risks were also scaled down from high to medium. The initial assessment was that working with political parties is very unpredictable with serious concerns around political party participation and conflicts amongst political parties. However after the CMD Board agreed to participate in the project and agreed on how and which parties to benefit in the project, the risk was reduced from high to medium.

Risk of funds not being used as intended / There has been no observable risk of funds not being used as intended. There is close monitoring of the partners to ensure that no funds are diverted to non-project areas. For example, the UNDP Elections Basket fund supported the emergency procurement of scanners. As this was unplanned, it was discussed and approved at both the Technical Committee and Steering Committee levels. / Climate and Environment Risk / A lot of materials will be used in the elections such as printing of Civic and Voter Education messages and voting materials. Use of vehicles will also be high and the risk to environment will be significant. To mitigate these risks, political parties will be encouraged to adopt climate change and environmental friendly policies and commit to taking special measures to support climate and environment related initiatives. Our project partners will be encouraged to send reports via emails and not hard copies and printing of elections messages will only be done for areas where electronic messages cannot be accessed.

5. Value for Money
5.1 Performance on VfM measures / The programme tracks efficiency savings by establishing cash flow forecasts, detailed work plans and monitoring plans with each of our partners. Partner outputs are reviewed carefully through financial and narrative reports submitted on a monthly and quarterly basis. NDI also makes field visits to partners to observe activities and provide additional assistance in programme and financial management as needed. / Advance operational and contingency planning is informing procurement, especially for the direct delivery of elections, allowing for early development of specifications and tendering. Risks are being monitored and reviewed monthly and mitigating measures identified. / In an effort to encourage a transparent and competitive selection process for components where downstream sub-granting is required, an open call is issued for statements of interest from potential partners. This allows the programme to move beyond working with the “usual suspects” to a competitive process where those who can deliver value for money are preferred. / 5.2 Commercial Improvement and Value for Money / The UNDP Elections Basket fund component involves large procurements. From the outset it was made a condition the Basket Fund cannot be used to reimburse expenditures made by the client institution or government. This has limited the possibility of unexpected costs. In the case of the UNDP Elections Basket Fund, procurement reports are submitted to the Technical and Steering committees as part of the financial management and tracking process. / 5.3 Role of project partners / There are three key project partners in the Elections programme. UNDP is coordinating the implementation of the Elections Basket Fund to which DFID contributes £3.1million. UNDP manages the Basket Fund with oversight of the Technical and the Steering Committees. All the Programme delivery is monitored by UNDP. The Civic and Voter Education component is being delivered by NDI who have put mechanisms in place to ensure that downstream partners have the right capacity to deliver. The Political Parties component is being coordinated by CMD who works with member political parties to strengthen their capacities and improve democratic values and political environment. DFID holds regular management meetings with these partners to ensure that they play their role effectively and contribute to the successful delivery of the programme. / 5.4 Does the project still represent Value for Money : Yes / . / 5.5 If not, what action will you take? / NA

6. Conditionality
Generally, there are no conditions. However, the support to UNDP Elections Basket Fund is contingent on UNDP putting strict financial management measures to avoid loopholes in MEC financial controls as experienced in the 2009 general elections. This being the case, UNDP will not be allowed to fund MEC directly. All funding will be managed by UNDP and payments will be to suppliers of services.

7. Conclusions and actions
The 2013 Annual Review is the first for ISEP. The progress of the programme is good as reflected by the overall A-rating for the achievements of millstones for the outputs. The outcome rating is also A. However, the 4th output got a rating of B and this will have to be closely monitored in 2014 to ensure that milestones are fully achieved. The log-frame was reviewed in July, 2013 and has been reviewed again this January, 2014 based on the rapid changes in the electoral process and environment.

8. Review Process
This Annual review has been done with the close involvement of all the three key implementing partners; the UNDP Elections Basket Fund team, the Political Parties project team which involves UNDP and CMD, and NDI who are implementing the Issue-Based CVE. Each partner carried out their own reviews and provided initial data which has fed into the final review. Field visits were done with the participation of DFID and the implementing partners for each component. Various efforts were made to triangulate the data and ensure its validity and reliability. The Democratic Governance cluster of the Governance and Security team which comprises Lone Sorensen, Chris Phiri and Adamson Mkandawire have put this report together. / The Annual Review will be peer-reviewed by the DFID Malawi Programme Board and submitted for approval by DFID Malawi’s Head of Office.