ADDENDUM TO BUSINESS CASE FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Institutional Strengthening of the Electoral Process (ISEP)
Country or region targeted	Malawi
Type of cost extension	Cost extension up to a maximum of £5 million
Original project budget	£6, 300,000
Original project start and end dates	26 July, 2012 – 30 June, 2017
Cost extension value	£1,481,474 (One Million Four Hundred and Eighty One Thousand Four Hundred Seventy Four Pounds Sterling
New project end date	30 June, 2017
Business Case Quest Document No.	3767145

INFORMATION
What is the project’s purpose?
To support long-term institutional strengthening of the electoral process in Malawi, as outlined in the DFID Malawi Operational Plan. £6.1 million of this will be focussed on supporting the lead up to, the event and immediate aftermath of the 2014 Presidential, Parliamentary and Local Elections.
What is the objective of the cost extension?
The cost extension will support; i) electoral reforms up to February, 2016 with clear outcomes in terms of legislative amendments to electoral process and the electoral system in Malawi; ii) Community engagement and trainings in all wards and district councils in 12 districts which will entrench Issue-Based politics and ensure that elected officials account for their promises and improve delivery of services.
What is the additional and total support the UK will provide?
The UK will provide additional support of £1,481,474 which will bring the total support DFID provides to ISEP to £7,781,474.
What are the expected results?
The additional support to ISEP will enable the programme to provide more support to its Issue-Based Civic and Voter Education component which is being implemented through an Accountable Grant to NDI. This additional support will increase the ability of civil society organizations, local officials and councils to work on community issues and improve local service delivery and enhance effectiveness of the multi-stakeholder process for electoral laws and system reforms. The proposed additional support to NDI will have two objectives as follows: / Objective 1: Civic groups and local government officials in targeted districts work collaboratively to address community concerns and improve local service delivery. / Specific interventions under this objective will be as follows: / Train communities and local councilors on their roles and development issues; / Selected districts to educate on local government structures, functions and processes such as participatory budgeting[1] ; / Collective action through the creation of “accountability clubs.” These clubs would include a partnership with reform-minded members of the ADCs or VDCs to coordinate and organize monthly meetings with ward councilors, MPs and district secretariat staff; / Facilitate the participation of accountability club representatives to also observe council and/or committee meetings in the district councils to learn first-hand about developments in local government or to provide insight to the district councils about specific concerns; / Collaborate and coordinate with radio partners; / Engage with NGO experts in various development sectors to better understand what solutions to service delivery blockages are most technically viable in the targeted districts. / Objective 2: The multi-stakeholder process effectively contributes to electoral laws and system reforms to avert the challenges that affected the 2014 tripartite elections. Specific interventions will include: / Facilitating engagement of national and local political party leaders in the ongoing electoral reform processes; / Supporting the consolidation of the overall National Taskforce on Electoral Reform position paper that takes into account the views of all stakeholders, including political parties; / Contributing to the advocacy efforts for electoral reform recommendations that result from the process. Through NDI’s support, the multi-stakeholder process would be better able to contribute to the adoption of electoral reforms. / Organize regional conferences with civil society and local political party leaders on the electoral reform position paper and strengthen MESN’s organizational capacities for the longer term; / Train and popularize new electoral laws throughout the country / The successful implementation of this additional support will result in a more active civil society advocacy for accountable and responsive local government and improved service delivery; and a more informed multi-stakeholder electoral reform process that gains the confidence of all stakeholders and enhances national stability. / Compliance with the Gender Equality Act / We have considered the likely impact of the programme on gender equality. The ISEP programme’s focus on communities holding elected and government officials to account on campaign promises to improve service delivery for poor considers inclusion of traditionally marginalised groups, specifically persons with disabilities, women and or girls. The programme is continuing to systematically track results delivered for this group by disaggregating data by sex in all instances where this is relevant.
What is the approach to implementation?
This project component will be implemented by NDI. In turn, NDI will build productive relationships with civil society partners through a combination of technical and financial assistance. The financial assistance will be in form of sub-grants to 18 organisations working in 12 districts in all the three regions of Malawi. When providing technical assistance, NDI has maintained an approach of guided practice and participatory learning through which the Institute accompanies organizations in their work through long-term partnerships, consultations and regular feedback. The Institute draws on relevant successful experiences in other countries and helps partners develop relationships with peers in those countries to build support networks. This allows NDI to transfer knowledge and address problems on a daily basis, and increases their ability to immediately apply new skills. This approach helps partners improve their ability to plan and undertake political actions, manage and account for resources, communicate successes and challenges, and build greater levels of capacity for sustained organizing and activism. As a complement, financial assistance through sub-grants helps partners to develop democratic organizational cultures built around fundamental principles of ethics, accountability and social responsibility. As a result, local partners increase their credibility and establish stronger connections to their respective communities.
Describe any key changes to the original business case?
The original Business Case continues to be successfully implemented and its three key components continue to achieve results. However, there is general loss of steam after the May 2014 elections, and the window for electoral legal and policy reforms is at risk of closing fast. Specific challenges relate to lack of inclusion in the electoral reforms. While there are several stakeholders who participate in the electoral reforms, most political parties feel they are not included and this is a real risk to the success of these reforms. As one of the key elements will be to engage political party structures at various levels to contribute to the reforms dialogue, this is where the additional activities implemented by ISEP will add significant value. Another challenge is with regard to the political parties’ registration amendment bill. It is moving slowly and there is risk it may fall off the radar as attention is turned to electoral reforms. The programme is working on how to deal with these challenges to ensure that its success is maintained.
[1] From July 2015 to November 2015, district councils must carry out a process of participatory budgeting this is a key mandate of the ADCs and VDCs.