Business Case

Summary Sheet

Title: Improving Security & Access to Justice in the Occupied Palestinian Territories

Programme Value: £10.8 million		Country/ Region: OPTs

Project Code: 204797	Start Date: 01.04.2015	End Date: 31.03.2018
Quest Number:

Intervention Summary

What support will the UK provide?

The UK will provide £10.8 million over three financial years (2015/16, 2016/17, and 2017/18) to support the development of capable, accountable and responsive security and justice services for citizens in the Occupied Palestinian Territories (OPTs). The primary focus of the programme will be the West Bank with some support in East Jerusalem and Gaza.

What are the main programme activities?

This intervention will target both the ‘supply’ and ‘demand’ sides of security and justice services. Citizens will be empowered to access services and to hold authorities to account while the capability, accountability and responsiveness of the two key ministries (Ministry of Interior and Justice) will be strengthened to enable them to deliver more effective and efficient services.

The intervention has two components:

£5m contribution to a multi-donor programme implemented by the UN Development Programme (UNDP) and UN Women. This will focus on improving service delivery and capacity building of key justice and security institutions, including the Ministry of Justice (MOJ), the High Judicial Council (HJC), Attorney General’s Office (AGO), the Palestinian Civil Police (PCP) and a number of civil society organisations (CSOs), with a strong focus on improving women’s security and access to justice.

£5.8m for UNOPS to deliver technical assistance to the Ministry of Interior (MOI) to improve its capability to provide oversight and management of the security services.

What are the expected results?

The intended impact of this intervention is to contribute towards a viable and sovereign Palestinian state living alongside Israel in peace and security.

The intended outcome of this programme is: The PA providing more capable, accountable and responsive security and justice services to the Palestinian people, especially for women and girls.

The link between outcome and impact will occur as people’s awareness of and access to quality security and justice services develops. Improved public services which meet people’s expectations will help strengthen state-society relations. This will in turn help raise public confidence in, and strengthen the viability and legitimacy of the Palestinian Authority (PA), both in the eyes of the Palestinian people but also as a credible partner for peace for Israel and the international community.

Expected outputs include:
The Ministry of Interior has the institutional and organisational structures, processes and capabilities to exert clear civilian oversight of state security and intelligence agencies;
Accountable justice and security services to prevent, protect and respond to violence against women and girls.

Why is UK support required?

This intervention is part of the UK Government’s ongoing investment in Palestinian state building, helping to contribute to the prospects for a negotiated two state solution to the Israeli-Palestinian conflict. This supports a key strategic priority of the UK National Security Council.

It builds on DFID’s strong partnership with the PA and its experience in the justice and security sector, where DFID has been a lead donor. DFID is the co-chair of the Security Sector Working Group and has supported the establishment of a number of Family Protection Units as part of its efforts to prevent and reduce violence against women. In addition, following several years of dialogue between DFID and the Ministry of Interior, the latter has now requested DFID’s support to help reform the institution and strengthen civilian oversight.

The Interim Technocratic Government also presents a unique opportunity for donors to lend their support to reforms across the OPTs, including supporting steps for the PA to return to Gaza. There are significant political challenges to the reconciliation process but if reintegration moves forward, the intervention will seek to capitalise on opportunities while still rigorously monitoring risks.

DFID’s Secretary of State has identified eliminating Violence Against Women and Girls and promoting gender equality as one of her priorities. This programme will directly support this aim.

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

The UK’s vision for the Occupied Palestinian Territories (OPTs) is a negotiated two state solution leading to a safe and secure Israel living alongside a viable and sovereign Palestinian state; based on 1967 borders with agreed land swaps, Jerusalem as the shared capital of both states, and a just, fair and agreed settlement for refugees.

In line with this, the DFID Palestinian Operational Plan outlines its main policy objectives as the following:

1. political stabilisation through an investment in the PA and its institutions;
2. long-term development by mitigating the worst effects of the occupation, providing basic services and upholding Palestinians’ right to live and move freely;
3. economic stabilisation and development so that a future Palestinian state will be stable, prosperous, well-run, and an effective partner for peace with Israel.
Particular mention is made in the Operational Plan on the need to improve services for women victims of violence.
This intervention sits within the Governance and Security Pillar as part of the statebuilding work under the first policy objective.

What are the key risks to the success of the programme?

This is a complex intervention in a fragile and highly politicised environment which therefore carries a number of risks. These include:

- Political or fiscal difficulties lead to the collapse of the PA;
- Changes in Palestinian leadership affect the PA’s commitment to reform and demand for this intervention;
- Suspension of security cooperation between the Government of Israel and the PA;
- The creation of gender-sensitive security forces and justice institutions is undermined by broader social attitudes to women and girls.

DFID has developed a thorough risk matrix which will be reviewed and updated on a quarterly basis.

Table of contents

Abbreviations	p. 5
Strategic case	p. 6
The context: Conflict & Fragility	p. 6
Palestinian national institutional capacity	p. 7
Security & Justice in the OPTs	p. 8
DFID Engagement	p. 10
Expected Impact and Outcome	p. 11
Safeguards	p. 12
Justification for programming beyond the Spending Review	p. 12
Appraisal case	p. 13
Option A: Do nothing	p. 13
Option B: Improving security and access to justice for women and girls	p. 14
Option C: A comprehensive approach to security and justice sectors reform, with an integrated gender approach focused on improving access to security and justice services for women	p. 17
Theory of Change for preferred option (Option C)	p.19
Commercial case	p. 23
Implementing partners’ capability to deliver	p. 23
Value for money	p. 24
Financial Case	p. 26
Overview of costs	p. 26
Reporting requirements	p. 27
Additional financial management requirements	p. 28
Management Case	p. 29
DFID staffing & management	p. 29
Monitoring & Evaluation	p. 29
Governance Arrangements	p. 30
Risk Matrix	p. 30
Annexes
Annex 1. Theory of Change diagram	p.33
Annex 2. Logical Framework	(separate doc)
Annex 3. Governance Arrangements of MOI Component	p.34
Annex 4. Governance Arrangements of Joint UNDP/UN Women Component	p.35
Annex 5: Methodologies considered for economic appraisal	p.36

Abbreviations

AGO	Attorney General’s Office
AHLC	Ad Hoc Liaison Committee
CSOs	Civil Society Organisations
CSSF	Conflict, Stability and Security Fund
CT	Counter-Terrorism
DDA	Due Diligence Assessment
EUPOLCOPPS	EU Co-ordinating Office for Palestinian Police Support
GoI	Government of Israel
HJC	High Judicial Council
ISF	Israeli Security Forces
MEPP	Middle-East Peace Process
MOI	Ministry of Interior
MOJ	Ministry of Justice
NSC	National Security Council
OPTs	Occupied Palestinian Territories
OSJA	Overseas Security & Justice Assessment
PA	Palestinian Authority
PASF	Palestinian Authority Security Forces
PCBS	Palestinian Central Bureau of Statistics
PCP	Palestinian Civil Police
PLO	Palestine Liberation Organisation
SRO	Senior Responsible Owner
SSR	Security Sector Reform
SSWG	Security Sector Working Group
UNDP	United National Development Programme
UNOPS	United Nations Office for Project Services
UN Women	United Nations Entity for Gender Equality and the Empowerment of Women
USSC	United States Security Coordinator
VAWG	Violence Against Women and Girls

Strategic Case

The UK continues to support a negotiated two-state solution leading to a safe and secure Israel living alongside a viable and sovereign Palestinian state; based on 1967 borders with agreed land swaps, Jerusalem as the shared capital of both states, and a just, fair and agreed settlement for refugees. A key part of this is building a strong and accountable PA, capable of ensuring stability and security across the OPTs and being a credible partner for peace.

The PA was established under the 1993 Oslo Accords to give Palestinians a measure of administrative and security responsibility for the Occupied Palestinian Territories (OPTs) whilst a permanent peace deal was negotiated.

Under the Accords, the PA assumed powers and responsibilities for internal security and public order in Area A (18% of the land and 55% of the population). The Israeli government retained security control in Area B (21% of the land and 41% of the population) while the PA took administrative control. The Israelis retained full security and administrative control in Area C (61% of the land). The PA has no administrative or security control over East Jerusalem which was excluded from the Accords and is illegally occupied by Israel under international law.

More than twenty years on, peace talks have not yet resulted in an agreement. The PA’s ability to exercise full authority and provide services remains curtailed by the Occupation. There has been encouraging progress in building the capacity of Palestinian institutions and security forces, thanks partly to substantial investment by the UK and other donors in state-building. At the United Nations Security Council in February 2011, the UK, with France and Germany, asserted that the PA has the institutional capacity of a state.[1] The UK has also invested significant support to civil society to help strengthen the accountability of the PA.
[1] In the Chair’s summary of the the Ad Hoc Liaison Committee (AHLC) meeting in April 2011, the AHLC welcomed ‘the assessment of the World Bank, the IMF, and the UN that the PA is above the threshold for a functioning state in the key sectors they studied, and that Palestinian institutions compare favourably with those in established states’. AHLC April, 2011 Accessed Online at: http://www.europarl.europa.eu/meetdocs/2009_2014/documents/wgme/dv/201/201106/20110608_6_meetingahlc_en.pdf

The context: conflict and fragility

The development context in the OPTs is characterised by long-running conflict and fragility. Public trust in institutions and in the Palestinian political establishment risks being eroded by the ongoing Occupation and the lack of progress on the Middle East Peace Process (MEPP): the latest round of MEPP talks, led by US Secretary of State John Kerry broke down in April 2014. In the absence of meaningful political progress, Palestinians face the possibility of further fragmentation of territory, politics, power, government structures, business, economy, civil society and communities.

Conflict exists on a number of levels, including:

Government of Israel (GoI) and Hamas

Israel withdrew from the Gaza Strip in 2005 but continues to control its land borders and access to the sea. Hamas and other groups have regularly launched rocket attacks from Gaza since 2005. There have been three conflicts between GoI and Hamas since 2005: 2008-9 (Operation Cast Lead), 2012 (Operation Pillar of Defence) and 2014 (Operation Protective Edge). Operation Protective Edge resulted in the deaths of 2,254 Palestinians (including 538 children) as well as 71 Israelis.[2]  Over 100,000 people were made homeless and 450,000 had no access to water. In January 2015, just under 12,000 IDPs are still sheltering in UNRWA Collective Centres. While a ceasefire was agreed in August 2014, this has not been formalised and it is possible that Hamas and the GoI could return to violent conflict.
[2] FCO, 2014 Human Rights Report, 2015.

The Occupation of the West Bank & East Jerusalem

A period of relative calm since the end of the 2014 conflict in Gaza did not result in progress on negotiations. Settlements have expanded, restrictions remain in place and tensions are rising. The last few months of 2014 saw a serious deterioration in security and a number of high profile attacks against both Israeli and Palestinians.

c) Fatah and Hamas

In 2007, Hamas took de facto control of Gaza following victory in the 2006 elections. Since then, the PA has had no control in Gaza. This has resulted in further political and legal fragmentation between Gaza and the West Bank, re-enforced by Israel’s movement and access restrictions. In April 2014, surprise reconciliation talks between Fatah and Hamas, following the breakdown of the latest round of the MEPP negotiations, resulted in an Interim Technocratic Government (ITG). It consists of secular, independent Ministers, including four from Gaza. The ITG was initially supposed to manage Palestinian affairs for an interim six-month period followed by elections. However, no elections have been held and the reconciliation agreement remains fragile with little progress on the ground.

All this is happening within a wider context of regional upheaval and shifts in alliances, including the rise of the Islamic State of Iraq and the Levant and the fall of the Muslim Brotherhood, which traditionally has close links to Hamas.

Palestinian national institutional capacity

Despite significant progress, a number of challenges remain:

Accountability

As a result of the Hamas-Fatah rift, the Palestinian legislature has not functioned since 2007, undermining parliamentary oversight and accountability of PA institutions and their legitimacy. While the reconciliation agreement included a pledge to hold elections within six months, these have continued to be postponed. Laws can only be passed by presidential decree. Despite an active Palestinian civil society, they still play a limited role in policy and decision-making processes, in particular in the justice and security sector.

Fiscal difficulties and reliance on donors

The PA is highly dependent on international aid with donors providing an estimated $1 billion a year in budget support. Despite this assistance, the PA’s fiscal situation remains precarious, with a budget deficit in 2014 estimated at around $1.7 billion[3] – around $400 million more than budgeted. The cost of Gaza reconstruction is likely to send this higher. GoI restrictions on movement and access across the OPTs also cost the PA at least £2bn a year.[4] In addition, the ability of the GoI to freeze the transfer of tax revenues collected on behalf of the PA prevents the payment of the salaries of Palestinian public sector workers and places the PA in a precarious financial situation.
[3] PA Ministry of Finance, Macro Fiscal Unit, Q3 report Nov 5th, 2014
[4] The total potential value added (direct and indirect) as a result of the alleviation of current restrictions on access to, and activity and production in Area C is about $3.4 billion (or 35 percent of Palestinian GDP in 2011). This estimation refers to Area C only so if we included the potential for Gaza and other parts of the West Bank, the figure would obviously be much larger . Source: World Bank, 2013, Area C and the Future of the Palestinian Economy.

The possibility of reconciliation between Fatah and Hamas could result in the addition of 40,000[5] Gaza-based workers onto the already stretched public sector payroll. Any future integration of security related personnel poses particular challenges, in a context where the PA does not have complete control over its resources, and where movement and access restrictions remain in place.
[5] According to estimations by the Swiss Representative office in Ramallah

Security and Justice in the OPTs

The PA has made encouraging progress on improving the effectiveness of security and justice in recent years. According to a UNDP survey of the Palestinian justice and security sector, 5% more Palestinian men and women accessed these services between 2011-2012. In addition, the number of Palestinian households that regard Palestinian security and justice institutions as legitimate, independent and effective has increased. There was also a 26.7 percent increase in the number of women accessing the justice system in 2012 compared to 2011.[6]
[6] Statistics taken from the forthcoming UNDP Public Perceptions of Palestinian Justice and Security Institutions. 85 percent of households indicated that ‘courts are the only legitimate institutions through which to resolve disputes’, a 19.6 percent increase on 2011. There were also significant increases in the number of respondents who believe that the law is clear and fair (155.6 percent); that using the courts leads to justice (120.1 percent) and prevents violence (159.7 percent).

However, the survey also highlighted weaknesses in the system. These include gaps in police oversight and accountability; a lack of mainstreamed policy frameworks and coherent, specialised services for women and children across the justice chain; gaps in support to anti-corruption efforts by both institutions and civil society; and an overall lack of capacity to generate reliable data and use it to inform policy development.

The framework for reform: The PA’s Security and Justice Sector Strategies under the Interim Technocratic Government

The PA’s Justice Sector Strategy for 2014-16 identifies two key priorities: (1) enhancing the quality of justice service delivery and (2) empowering justice sector institutions to effectively play their assigned roles. It refers to the Palestinian reconciliation effort and the need for institutional re-unification and integration of the justice sector through transitional justice measures.

The Security Sector Strategy for 2014-2016 outlines the main challenges facing the security sector, with a stronger focus on governance and accountability than the previous 2011-2013 strategy. Efforts are now underway in the MOI to develop and oversee an implementation plan and identify and prioritize relevant interventions and donor support. In the meantime, some restructuring and reform of the security sector have occurred. However, this has been ad hoc and is incomplete, resulting in mixed progress in terms of civilian control over the security forces, overlapping mandates and significant organisational inefficiencies and ineffectiveness. Furthermore, integration of the various security services under the full control of MOI has not occurred and is not highlighted as a priority under the current strategy.

Finally, in the final phase of the MEPP negotiations in April 2014, the PLO signed up to 16 International Conventions and Treaties, and in December 2014, it presented documents for accession to an additional 20 conventions and treaties. This includes the Convention for the Elimination of Violence Against Women and various other human rights instruments. Signing up to the Conventions formally commits the PA to improving human rights standards and to report progress to the relevant UN bodies. Notably, the National Development Plan 2014-2016 was based on human rights principles for the first time, providing an additional tool for ensuring better compliance with international standards.

Key challenges in the PA’s Security and Justice Sector:

The Occupation and the resulting fragmentation of the justice and security systems

As outlined above, the PA exercises different degrees of authority in different areas of the OPTs. The Security and Justice sectors are perhaps most affected by the continuing and growing impact of the Occupation. This has created rule of law vacuums, especially in Area C where the GoI exercises full control but also in Area B where 41% of Palestinians live. Different issues face Palestinians living in annexed East Jerusalem where they are subject to discriminatory Israeli laws such as the Absentee Property Law and the Citizenship and Entry into Israel Law. In these areas outside of the PA’s jurisdiction, alternative service delivery mechanisms are needed to help Palestinians navigate the justice system, such as legal assistance through civil society organisations.

Institutional weaknesses of security and justice actors

The lack of clarity over roles and responsibilities in the justice and security sectors is a major obstacle to progress. Despite some efforts to rationalise the legal framework of the PA Security Forces, it remains incomplete and inconsistent.

Similarly, the lack of formal links between the security and justice institutions remains a key obstacle which prevents these sectors from working effectively. This includes inadequate coordination among justice and security sector institutions, the absence of specialised courts and prosecution capacities as well as poor judgment enforcement.

In this context, interventions can instead focus on strengthening the policy-making process; both at the policy as well as operational level, and help develop guidelines and standard operating procedures for the relevant services.

What this means for Palestinians, especially for women and girls

Perceptions of justice and security: Palestinians rate some aspects of the justice and security sectors highly. For instance, they have in the past shown a high degree of confidence in the PCP. However, new surveys indicate this support is waning, suggesting there is an urgent need to improve the delivery of these services and make them more responsive to the daily needs of Palestinians.[7] Palestinians have few channels for voicing dissatisfaction, expressing their needs and holding the PA to account. In particular, although the Palestinian Basic Law demonstrates an important commitment by the PA to guarantee rights for women and girls on the basis of equality and non-discrimination, they continue to struggle to access justice and security services that respond to their needs.
[7] P110, UNDP/UNW, Strengthening the Rule of Law in the OPTs: Justice and Security for the Palestinian People (2014-2017). UNDP compared the 2012/2013 UNDP Public Perception Surveys and concluded a drop in overall satisfaction rating from 2.71 to 2.61. It is however important to bear in mind the limitations of public surveys on PA actors, in particular the Civil Police. These can be skewed by the Occupation and perceptions of them being complicit with it. For example, PCP cooperation with Israel when three Israeli youth were abducted in the West Bank in May 2014 has lowered the levels of confidence in the PCP and the PA more generally. The forthcoming 2014 survey will indicate if this is a growing trend or a blip.

Violence Against Women and Girls (VAWG): Women in both the West Bank and Gaza have unequal rights. Palestinians inherited legal systems from previous occupying powers. For instance, Hamas use Egyptian Personal Status Law and the PA uses the Jordanian Personal Status law, both of which discriminate against women.

The most recent National Violence Survey (2011) conducted by the Palestinian Central Bureau of Statistics (PCBS) revealed high levels of domestic violence. Nearly 50 percent (West Bank) and more than 75 percent (Gaza) of married women are psychologically abused; 17 percent of women (West Bank) and nearly 35 percent (Gaza) are physically abused; and nearly 12 percent of married women across the OPTs are sexually abused by their husbands.[8]
[8] http://www.pcbs.gov.ps/Portals/_PCBS/Downloads/book1864.pdf

In the West Bank, the draft law on family violence has not yet been passed. The prosecution and legal services lack capacity to develop and implement gender-responsive processes; nor are there specialised courts or a legal framework to ensure women and girls have robust and effective access to justice and security services. There are also weak referral mechanisms between the various security and justice institutions.[9] Under the Hamas leadership in Gaza, Shari’a (Islamic) law has also played an increasingly significant role there which allowed for the death penalty being applied, and an increase in the use of corporal punishments such as lashings.
[9] P9, UNDP/UNW, Strengthening the Rule of Law in the OPT: Justice and Security for the Palestinian People (2014-2017).

DFID engagement

UK strategic priorities

Resolution of the Israeli-Palestinian conflict is high priority for the UK Government. DFID supports the UK Government objectives for a successful MEPP by helping build Palestinian institutions and promoting economic growth, so that any future state will meet the aspirations of the Israeli and Palestinian people,and will be stable, prosperous, well-run, and an effective partner for peace with Israel.

These objectives are reflected in the UK’s strategic bid for the Conflict, Stability and Security Fund (CSSF) in the OPTs, which prioritises Security and Justice interventions for programmatic support.

In addition, eliminating Violence Against Women and Girls and promoting gender equality is a DFID Ministerial priority and there is a strong need for interventions in this area in the OPTs.

Finally, the UK has humanitarian, strategic and national security interests in seeing a political resolution to the conflict which has been a source of regional instability and radicalisation both internationally and in the UK.

This programme has the potential to contribute to peace and stability through developing state security and justice institutions. DFID promotes stability as a key part of the UK’s overall strategic and policy framework set out in the National Security Strategy (2010); Strategic Defence and Security Review (2010); and the Building Stability Overseas Strategy (2011). The programme is also consistent with the approach in DFID’s Building Peaceful States and Societies practice paper (2010) which identifies the importance of making long-term investments in building capacities in key state security and justice actors.

UK track record on Security and Justice in the OPTs

HMG has been supporting a range of security and justice-related developments in the West Bank for a number of years. DFID is the co-chair of the Security Sector Working Group (SSWG), convening and providing strategic leadership across the international community on key security sector reform issues. We have funded interventions to support women’s access to security and justice in the OPTs since 2011, which has resulted in the successful establishment of a number of Family Protection Units across the West Bank and the creation of an observatory on women’s access to justice. HMG also contributes to the PA Security Forces’ training and development through the British Support Team in support of the US Security Coordinator (USSC), and provides funding to EUPOLCOPPS. In addition, HMG, through the conflict pool, has been supporting institutional capacity development work in the Palestinian MOJ since 2012.

As the SSWG co-chair, DFID has developed an important partnership with the Palestinian Ministry of Interior which has directly requested support from DFID on institutional reform. A previous proposed programme which focused on institutional reform could not begin because political commitment at senior levels of the ministry was lacking at the time. This has been overcome through regular dialogue with the MOI and close engagement with other partners in the sector. In October 2014, a Memorandum of Understanding on MOI reform was signed between DFID’s Minister of State and the Palestinian Prime Minister, who is also the Minister of Interior. A strong working relationship has also been established with the Netherlands who co-chair the Justice Sector Working Group and are the lead donor in the Justice Sector.

DFID is therefore now well placed to support further reform of the Palestinian justice and security sectors, in particular at the institutional level. To date this has been largely overlooked despite being a critical component of an accountable, capable and responsive state security and justice sector. Donors have in the past tended to support direct capacity-building of the security forces (training, infrastructure & equipment) with a view to progressing Palestinian-Israeli security cooperation and enabling a viable two-state solution.

This programme will build on HMG’s existing work and we will work closely with other relevant FCO and MOD colleagues to enhance complementarity and coordination.

Expected Impact and Outcome

Impact: To contribute towards a viable and sovereign Palestinian state living alongside Israel in peace and security.

This impact is achievable if the following assumptions are met:

- Progress on the MEPP towards a two-state solution;
- Tensions and instances of sporadic violence resulting from the continued occupation of the Palestinian Territories does not lead to significant instability and insecurity, thereby threatening the viability of a future Palestinian State;
- Continued PA commitment to principles of good governance, including to international human rights standards.
- Continued security cooperation between the PA and the Government of Israel.

Outcome: The PA providing more capable, accountable and responsive security and justice services to the Palestinian people, especially for women and girls

Safeguards

Partnership Principles

A country level assessment of the Partnership Principles is carried out every quarter with each disbursement of DFID’s Statebuilding and Service Delivery Grant to the PA. In general, it is found that the PA is delivering on the partnership principles under difficult circumstances. Of particular importance to this programme is the second commitment on ‘Respecting human rights and other international obligations’, which will be monitored closely throughout the delivery of this programme.

Conflict-sensitivity

Given the operating context, any intervention will need to pay particular attention to how it will affect the existing power dynamics and ensure it does not increase the potential for violent conflict. Where possible, it should help facilitate an environment which is conducive to a political settlement. In addition, any activities taking place at the community level will need to be particularly mindful of potential horizontal inequalities, and make sure they do not place communities and/or individuals at risk of harm. This will be done by ongoing analysis of the contextual dynamics, using our partners’ extensive local knowledge.

Impact on gender equality

The intervention will build on the commitments set out in the DFID OPT Business Plan to contribute to significant improvements and sustainable transformations in girls’ and women’s lives in the domestic and public spheres. This is through addressing the barriers which prevent women from accessing formal justice and security services as well as strengthening those services’ capacity to deal effectively with violence against women and other gender-related issues. Strengthening the effectiveness of interventions in the security and justice sector in cases of violence against women and other gendered issues is also a pre-requisite for enabling greater women and girls’ participation in the OPTs’ social, political and economic development.

Justification for programming beyond current Spending Review

Funding for this intervention is expected to be split between DFID’s bilateral allocation and the CSSF.

There are two main reasons for taking a multi-year approach. One is that institutional reform is a long-term process which requires an investment of time and resources over a number of years.
A one year programme would also not represent value for money in terms of DFID staff resources to get the programme up and running. Results are expected to be proportionally lower in the first year, with a gradual increase over the following years as strong working relationships are established and trust is built.

## Appraisal Case

Summary: Three options are being assessed. Option 1 is the ‘do nothing’ counterfactual. Options 2 and 3 both offer good value for money. Option 3 is the preferred option as it incorporates the intervention outlined in Option 2 but includes an additional element of institutional strengthening in the MOI, MOJ and related institutions. This will result in a more sustainable provision of services in these sectors.

Note: Options 2 and 3 outline different scale and focus for possible interventions in the Security and Justice Sector. They do not outline different delivery modalities. UN Women, UNDP and UNOPS have a strong track-record in the Justice and Security Sector and have established trust and successful partnerships with PA institutions, implementing partners and beneficiaries. Initiating new interventions in the Security and Justice Sector with new implementing partners would require significant investment in building relationships with partners and beneficiaries and would therefore delay the achievement of the programme’s objectives. Consequently, other delivery options have not been appraised.

Option A: Do nothing

The counterfactual is for DFID to stop investing in the security and justice sector when the current project with UN Women finishes in March 2015[10]. Headline results expected from the latter include the establishment of Family Protection Units, with standard operating procedures; gender-sensitisation of justice and security professionals; and systematic data collection on VAWG and women’s access to justice.
[10] Project memorandum (which contains full details of this programme) is saved under quest number 306997.
Impact of doing nothing

Gains made from current investment undermined. The economic rationale for the current intervention is twofold: (i) government failure to address VAWG, and (ii) lack of government accountability for the delivery of security services. The do nothing option runs the risk of gains made to date not being sustained in the future. The current proposal is for the UK, Sweden and the Netherlands to equally share the financial burden of a continued programme of support along the lines outlined above. The UK withdrawing would leave a shortfall in the budget equivalent to one third and significantly limit efforts to support reform in the sector.

The UK’s reputation as an influential donor in the security and justice sectors at risk. The UK is the co-chair of the Security Sector Working Group and an active member of the Justice Sector Working Group. DFID provides leadership, strategic direction and coordination of the international community to support the implementation of the PA’s National Security and Justice Sector Strategies. In the past, the sectors have suffered from a lack of coordination. This resulted in some reform areas (namely institutional strengthening) being neglected, and others being over-emphasised (e.g. front-line delivery of services). It also resulted in duplication and overlapping of efforts. Doing nothing would significantly affect our ability to leverage other donors’ financial and political support to achieve strategic reform in the justice and security sector.

The UK would miss an opportunity to deliver NSC strategic objectives and to honour its ministerial commitment to women and girls. Building capable, accountable institutions and professional security forces which operate within the rule of law is a key priority of the NSC strategy for the OPTs. Without investment in the institutions which oversee the security forces, this objective will only be partially achieved. In addition, DFID has been a key donor in improving access to security and justice for women victims of violence. Ending our support would result in a missed opportunity to support the Secretary of State’s commitment to addressing VAWG.

An important political moment would be missed. The current reconciliation agreement between political parties Fatah and Hamas increases the urgency to take action in the security and justice sectors. If reunification of Gaza and the West Bank (requiring reintegration of institutions) moves ahead, they will face institutional, legal and capability challenges on an unprecedented scale. The Cairo conference in October 2014 elicited strong donor support for the reconstruction of Gaza. This support needs to materialise on the ground, not least to provide the opportunity to support the PA’s return to Gaza and help address the chronic needs of the population.

Option B: Improving security and access to justice for women and girls

Intervention and delivery mechanism

This option builds on results achieved to date and lessons learned through UK support to UN Women (£2m since 2011).

The intervention would deliver services to improve the PA’s accountability and responsiveness in the security and justice sectors, with a special focus on women and girls. This would entail:

- Making justice and security systems responsive to women by changing the mandates, procedures and organizational cultures of the police, the courts and other service providers.
- Making women aware of their rights and giving them the knowledge to navigate the justice system, as well as be part of front line justice delivery.[11]
  [11] In pursuit of Justice, UN Women, 2011-2012, p.46-64.
- In areas which are not under the PA’s full administrative control, work with CSOs to enhance quality legal aid service provision, strengthen community legal literacy, provide advocacy on rule of law and human rights issues, and provide monitoring and oversight of justice and security institutions with a particular focus on women beneficiaries.
- Create greater linkages between the security and justice sectors, for example through strengthening capacities of the Family and Juvenile Protection Units.

The delivery mechanism is a continuation of the ongoing UN Women programme (Support to Accountable and Responsive Security & Justice in the OPTs) which DFID has been funding since 2011. We will continue to support, and expand, current activities in this next phase, including Family and Juvenile Protection units, the International Commission for Human Rights Observatory, and the training of prosecutors and defence lawyers.

Evidence

Women living in the OPTs suffer from violence on two levels; one that is related to the Palestinian patriarchal system, and one that is linked to the Israeli occupation (Israeli policies, the military and settler violence). The Israeli military occupation includes home demolitions, closures, mobility restrictions that affect access to health centres, work places, schools, universities, in addition to other forms of social support. On the Palestinian side, a Palestinian Central Bureau Statistics survey in 2011 revealed that among 5,811 Palestinian families in both the West Bank and Gaza, 29.9% of married women in the West Bank have experienced violence (physical, psychological and sexual) by their husbands compared to 51.1% in Gaza. Cases of Femicide (honour related killings) increased from 11 in 2009, to 28 in 2013.

UNDP perception data[12] finds that women are on average 11% less satisfied with the performance of institutions and personnel than men. This gender justice gap would be a good indicator to track progress of the proposed intervention on an annual basis. The same survey also recommends that efforts to strengthen legal literacy, availability of legal assistance and gender-sensitive case management (all aspects of service provision) will not achieve their purpose unless accompanied by efforts at removing discriminatory legislation and other institutional barriers.
[12] UNDP, March 2012, Public Perceptions of Palestinian Justice and Security Institutions.

The 2014 Annual Review[13] of the original UN Women programme found that it had met its objectives, and exceeded them with regards to the establishment of Family Protection Units and the development of standard operating procedures. Although coordination and cooperation among justice and security actors had improved through the creation of multi-sectoral mechanisms such as the Prison Coordination Group and the Serious Case Review, further support would be required to fully institutionalise these and clarify the roles and responsibilities of all stakeholders. The review also stated that “despite early and ongoing challenges, the programme is contributing to more strategic and longer term impact than was originally envisaged.”[14] A full evaluation of the programme is underway (expected to be completed in March 2015), which will focus on lessons learned to inform any future programming.
[13] DFID Annual Review of UN Women programme: Support to Accountable and Responsive Security & Justice in the OPTs, October 2014.
[14] http://www.unwomen.org/~/media/58ED9AE6A3B544149C9DEFA302CC9884.ashx

Cost and benefits

The additional costs as a result of the intervention are of three main kinds:

- DFID project costs: £2m over three years 2015-18, split evenly.
- DFID staff time: 20% of a conflict adviser and 15% of a project officer each year 2015-18.
- Total discounted costs £2.3m.

There is a serious dearth of evidence on the costs and cost-effectiveness of VAWG interventions.[15] Likewise, there is no global estimation of Disability Adjusted Life Years that would be averted from a year free of violence. The section below contains data from other countries.
[15] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/337939/approaches-to-scaling-up-prog-intervention-vfm-J.pdf

The incremental benefits of addressing VAWG includes:

- Improved health status: VAWG impacts heavily on the health of survivors in terms of reproductive health (unwanted pregnancies, other gynaecological problems), physical well-being (injuries and deaths), and mental health (depression, post-traumatic stress disorder, alcohol and drug abuse). According to World Bank estimates, gender-based violence accounts for one out of every five healthy days of life lost to women of reproductive age. [16] The health burden created by this type of violence is comparable to that from other conditions already high on the world agenda, such as HIV, TB and cancer.
  [16] Calculated in terms of Disability-Affected Life Years (DALYS) in the World Bank’s World Development Report 1993: Investing in health.
- Increased output and income: injuries can force women to take time off from paid as well as unpaid work and/or may result in lower productivity. For instance, in India, women lose an average of seven working days after an incidence of violence. Recent evidence suggests that globally, domestic VAWG imposes a social cost of $8 trillion each year[17]. Older evidence estimates the cost to the economy of domestic violence as 2% of 1996 GDP in Chile and 1.6% of GDP in Nicaragua[18].
  [17] http://www.project-syndicate.org/commentary/bj-rn-lomborg-shows-that--in-terms-of-global-welfare-costs--wars-are-the-least-of-our-problem
  [18] Morrison and Orlando, 1999.
- Health service provision to survivors: in addition to the immediate cost of medical visits, hospital costs and medicines, women who have been physically or sexually assaulted tend to be intensive long-term users of health services. The only developing country for which this seems to have been estimated is Bangladesh, which amounted to $1m a year.

We have chosen to use ‘lost GDP’ as a proxy for the cost of VAWG in the OPTs. Conversely, the benefit of improving access to justice for women and girls is a reduction in the incidence of VAWG.

Assumptions
- VAWG costs the economy 1.8% of GDP. This is the midway point between the 2% GDP estimate for Chile and the 1.6% GDP estimate for Nicaragua.
- The contribution of the proposed intervention by the UK to the outcome of saving the economy from VAWG is 1%.
- The benefits of the access to justice programme accrue over a five year period.
With the above assumptions, total benefits = £7m.

The Benefit-Cost ratio is 3.26. This is a very conservative estimate.

Challenges, risk and likelihood of success

Challenges:
- Entrenched legal and social discrimination against women and girls;
- Lack of capacity in some parts of the security and justice sectors and understanding of gender-specific issues; and
- Underlying barriers to success relating to the occupation of the Palestinian territory (in particular in Area C and East Jerusalem where the PA does not have control).

Risks:
- Service delivery improved, but in an institutional vacuum; and
- Lack of commitment to gender mainstreaming.

Likelihood of success:
In the short run, service delivery improvements are likely to be tangible and visible. In the long run, the sustainability of these services is questionable due to an absence of institutional backing (e.g. making sure that budgets are gender-responsive; instituting ongoing training programmes for security and justice staff on gender issues).

Option C: A comprehensive approach to security and justice sectors reform, with an integrated gender approach focused on improving access to security and justice services for women

Intervention and delivery mechanism

This option proposes the coupling of service delivery (as outlined in Option 2) with institutional reform of the MOI, MOJ, and related institutions (HJC and AGO). The institutional reform would focus on strengthening the MOI’s capability to provide oversight and management of the security sector, for example by institutionalising standard operating procedures, improving human resource management and strengthening budgetary processes and expenditure controls. It would also seek to strengthen the capacity of the justice sector institutions in key legal and administrative skills. It would build on progress made to date through our support to UN Women, by institutionalising the work of the Family Protection Units, by providing direct training as well as advice on integrating gender across the justice institution’s processes. In the security sector, international donor assistance to date has primarily focused on the capacity-building of the PA security forces. Less attention has been paid to issues of civilian oversight, accountability and strategic management.

The delivery mechanism is technical assistance by UNOPS to the MOI and by UNDP/UN Women to a number of institutions and partners in the Justice and Security Sector, including the MOJ, HJC, PCP and a number of CSOs.

All three organisations have a strong track record of successful engagement with the relevant institutions. In addition, the Joint UNDP/UNWomen component is a multi-donor programme currently funded by the Netherlands and Sweden. EUREP are exploring the possibility of joining the consortium.

Evidence

The 2011 World Development Report notes that strengthening institutional legitimacy and investing in citizen security, justice and economic empowerment are essential to reducing violence and maximising development prospects.[19] As underlined in DFID’s Rule of Law policy approach paper (2013), a flexible and integrated framework will help build a system of results delivery that can build on diagnosis of specific problems, adapt to the changes in context and counterparts, and take opportunities for progress as they arise.
[19] 2011 World Development Report: Conflict, Security & Development.

In addition, the evaluation [20] of UNDP’s previous Rule of Law and Access to Justice Programme concluded that the Programme achieved a high level of impact and outcome-level change within the context of extremely challenging political and security realities and according to its funding and resource base. Especially critical were UNDP’s support to women and children via grassroots legal aid initiatives in both the West Bank and Gaza, as well as its support to the PA justice institutions, lawyers and the Palestinian Bar Association. As detailed in the evaluation report, the capabilities of the key justice institutions (including legislative capabilities) have been greatly expanded through UNDP-supported training and education programmes, as well as by embedded experts and improved legal infrastructure funded by the programme. The provision of legal aid and coordination between legal aid providers and the state have been significantly improved, and efforts have been made to inform the public of their rights and their ability to protect them through formal justice mechanisms. A comprehensive study of women’s rights in relation to existing legislation has been carried out with UNDP support, and ground-breaking programmes have been instituted to increase the capacity of security and justice institutions to address the needs and rights of women and juveniles.
[20] Independent Outcome Evaluation, UNDP Rule of Law & Access to Justice Programme in the OPTs , September 2013, Richard Langan.

While the evidence base for the impact of supporting MOI development is relatively weak, there are lessons that suggest that a strong and accountable interior ministry is vital to ensure oversight of the security sector and to improve police performance and accountability over time: ‘Police reform without concurrent MOI reform can yield short-term security gains, but jeopardises long-term police performance, accountability and legitimacy.[21]
[21] DFID, Lessons learnt from international Assistance to Reform of Ministries of Interior, February 2011.

Cost and benefits

The additional costs as a result of the intervention are of three main kinds:

- DFID project costs: £10.8m over three years 2015-18;[22]
  [22] We are expecting this intervention to be funded out of the CSSF. Although we are able to undertake multi-year interventions, allocations are confirmed on an annual basis. There might therefore be fluctuations in the planned annual breakdown.
- DFID staff time: 40% of an adviser and 20% of a project officer each year 2015-18;
- Total discounted costs are £10.79m.

The benefits of strengthening the MOI can be quantified by estimating ‘efficiency savings’ as a proportion of the MOI budgets. This was the approach taken by the DFID Afghanistan programme “Strategic Support to the Ministry of Interior”. It is a simple method, but has been selected to capture the savings that will be reaped by improving strategic planning and management, functional and organisational processes (human resources, procurement etc) as well as its accountability.

The overall budget of the Palestinian MOI in 2014 is $995 million[23] (£622m). An annual 0.3% ‘efficiency saving’[24] over a ten year period would result in the PA saving £18m. This compares to a project cost of £10.8m[25]. In other words, the benefit cost ratio is 1.7 . For a similar institutional strengthening programme in Afghanistan, it was estimated to be 1.1.
[23] Taken from Ministry of Finance budget tables. Include MOI Central and MOI and National Security. The latter accounts for $977m.
[24] This was the efficiency saving needed in the Afghanistan business case to ‘break even’ over a ten year period.
Assumptions to calculate break even over a ten year period:
  1. The budget for the MOI goes up by 3% per year in nominal terms each year;[26]
    [26] This would be in line with the MOI allocations for the last five years in which the average year-on-year budgetary increase is 3%.
  2. That the benefits of the project accrue over 10 years;
  3. The discount rate for costs and benefits is the HM Treasury Green Book discount rate of 3.5%[27].
    [27] The UK is currently the sole donor but the MOI is open to other donors joining the programme. However, this would not alter the cost-benefit figures.

Sensitivity analysis: If the efficiency saving is reduced to 0.1%, and the assumptions above hold, the project continues to break even.

Challenges, risk and likelihood of success

Challenges:

Effective institutional and service delivery reform takes years and requires gradual, sustained and measured engagement;

Risks:
Progress is expected to be incremental as trust and relationships are built. This could put donor support and vital political buy-in from the PA actors at risk. It is therefore important for DFID and other stakeholders to be realistic about the pace of delivery and manage expectations;

Likelihood of success:
The expected results are considered achievable but are contingent on continued political buy-in and PA leadership.

Theory of Change for preferred option (Option C)

Problem statement

Flaws in the PA justice and security institutions (which include lack of civilian oversight), combined with a lack of accountability, mean that the services they provide do not meet the needs and expectations of Palestinians. Women and girls are particularly vulnerable due to the prevalence of violence against women and a security and justice sector which is not equipped to deal with these issues.

Theory of change

The diagram in Annex 1 shows the theory of change from inputs to impact. In summary, the impact is to contribute towards a viable and sovereign Palestinian state living alongside Israel in peace and security. The expected outcome is that the PA provides more capable, accountable and responsive security and justice services to its people, especially to women and girls.

Outputs include strengthening the MOI institutional and organisational structures, processes and capabilities to enable them to exert clear civilian oversight of state security and intelligence agencies, and ensuring women and girls’ access to justice is improved by providing accountable and responsive services.

The link between outcome and impact will occur as people’s awareness of and access to quality security and justice services, in line with the rule of law, develops. Improved public services which meet people’s expectations will help strengthen state-society relations. This will in turn help raise public confidence in, and strengthen the viability and legitimacy of the PA, both in the eyes of the Palestinian people but also as a credible partner for peace for Israel and the international community.

Success assumes continued commitment by the PA to good governance, the rule of law, and more specifically institutional and operational reform in the justice and security sector, all within the framework of a negotiated two-state solution. However, continued incursions of the Israeli security forces in Area A, absence of PA and responsibility in Area C, and a perceived lack of accountability of the Israeli Security Forces in the OPTs undermine the PA’s Security and Justice apparatus and its capacity to provide for its people. The link between outcome and impact is therefore also contingent on the political horizon provided by the MEPP.

The intervention in the security and justice sector will target both the ‘supply’ and ‘demand’ sides. It will support national institutions as well as civil society actors to improve service delivery. Citizens will be empowered to access services and to hold authorities to account while the capacity, accountability and responsiveness of the two key ministries (Ministries of Interior and Justice) and other relevant bodies will be strengthened to enable them to deliver more effective and efficient services.

This Capability-Accountability-Responsiveness framework is particularly relevant to the challenges facing the security and justice sector in the OPTs. DFID’s support to the Family Protection Units (Police units dealing with cases of violence against women) in the OPTs has shown the need for close coordination and cooperation between justice and security actors to address the specific needs of women victims of violence.[28]
[28] DFID Annual Review of Support to Accountable and Responsive Security & Justice in the OPTs, October 2014.

The Capabilty-Accountability-Responsiveness Framework

State Capability
= the ability and authority of leaders, governments and public organisations to get things done

Responsiveness
= how leaders and public organisations actually behave in responding to the needs and rights of citizens

Accountability
= the ability of citizens to hold leaders and public organisations to account
Good Governance

There are a number of interventions underway in the security and justice sector. Although the theory of change for this intervention focuses on a holistic approach of the sector using the capability-accountability-responsiveness framework (see annex 1), the intervention is not expected to cover all aspects of it. Instead, it will focus on where the UK can add value, where there is demand and traction for reform, and where it will complement other UK or international interventions in the sector.

Capability

The intervention will focus on strengthening the skills of key staff in the targeted institutions (MOI, MOJ, HJC, AGO) through practical training in core administrative (e.g. management, budgeting) and specialist skills (e.g. legal and gender awareness). Underpinning this, technical assistance will be provided to help counterparts in those institutions put in place efficient and sustainable organisational processes as well as the necessary legal and policy frameworks.

The balance of effort will vary according to the institutional needs. A stronger emphasis on specialist processes is appropriate in the justice institutions who have previously benefited from wider technical assistance, whereas the focus for the MOI will be primarily on core public service skills and processes (e.g. effective human resources management; procurement in line with international best practice).

In the longer-term, strengthening the capability of these institutions is expected to help them be more responsive to the needs of the Palestinians. For example, putting in place measures for transparent, collaborative and evidence-based strategic planning will help ensure that future policies and interventions from the MOI will meet the security needs of Palestinians.

Accountability

The accountability of the security and justice sector is weak. With the backdrop of the occupation, and without elections and a functioning Palestinian parliament, there are limited options for engagement at scale. A delicate interaction is required between donors, the PA and Israel to gradually effect change. The intervention will therefore focus on discrete entry-points (e.g. standard operating procedures for a MOI complaints mechanism) to cement the building blocks for future robust accountability processes and will coordinate with existing interventions in this sector.

In relation to horizontal accountability[29], the programme will support the development and the implementation of the National Anti-Corruption Strategy which has a key role to play in improving the transparency and accountability of the justice and security sector. Where possible, the programme will also build on the PA’s obligations under international human rights law to bring its practice in line with international standards, including through the reporting processes.
[29] Horizontal accountability consists of formal relationships within the state itself, whereby one state actor has the formal authority to demand explanations or impose penalties on another. Its focus is on internal checks and oversight processes. For example, executive agencies must explain their decisions to legislatures, and can in some cases be overruled or sanctioned for procedural violations. Vertical forms of accountability are those in which citizens and their associations play direct roles in holding the powerful to account. Elections are the formal institutional channel of vertical accountability. But there are also informal processes through which citizens organize themselves into associations capable of lobbying governments and private service providers, demanding explanations and threatening less formal sanctions like negative publicity.. Definitions from The Transparency and Accountability Iniatiative: Definitions taken from http://www.transparency-initiative.org/about/definitions, December, 2014.

In relation to vertical accountability, targeted support will be provided to civil society organisations to help provide services as well as monitor and challenge PA service delivery through dialogue and advocacy processes, such as facilitating CSO participation in sector strategy development. In close collaboration with other donors in the security sector, the intervention will explore the possibility of providing training and development of standard operating procedures for an MOI complaints mechanism. Separately, DFID is planning an evaluation of its current civil society accountability programme (Tajaawob) and will explore the possibility of extending the remit to security and justice issues as part of a costed extension in 15/16.

Responsiveness

The responsiveness component of the intervention will focus primarily on women and girls’ access to security and justice. For example, helping the MOJ and HJC adopt gender-strategies and action plans should in turn result in more gender-responsive budgeting[30] which will help meet the specific requirements for the delivery of PA security services and access to justice for women and girls.
[30] “Gender-responsive budgeting is government planning, programming and budgeting that contributes to the advancement of gender equality and the fulfillment of women's rights. It entails identifying and reflecting needed interventions to address gender gaps in sector and local government policies, plans and budgets. It also aims to analyze the gender-differentiated impact of revenue-raising policies and the allocation of domestic resources and Official Development Assistance”, UN Women, http://www.gender-budgets.org/, February 2015.

In addition, the intervention will build on progress made to date through DFID’s support to UN Women. This will include continued work to strengthen the capacity of the Civil Police’s Family and Juvenile Protection Units and of the Independent Commission for Human Rights’ role in monitoring and collecting data on violence against women and women’s access to justice, providing the basis for more responsive PA strategies and policies in the sector.

There are limitations to this theory of change in the areas where the PA does not have direct responsibility and control: Area C, East Jerusalem and Gaza. In these instances, the intervention will support civil society organisations as an interim measure to improve Palestinian’s access to justice and strengthen the rule of law under Israeli jurisdiction. In Gaza for instance, this includes campaigns on particular issues concerning criminal justice and women’s rights and advocating on rule of law principles or raising human rights concerns. The intervention will also work with the Observatory of the Independent Commission for Human Rights to monitor the impact on women’s access to justice across all relevant parts of the justice chain in the West Bank and Gaza. It will also support legal assistance, including in both ‘formal’ courts and also informal justice processes.

Commercial Case

Delivery mechanism through UN agencies, with two components: i) Joint multi-donor UNDP/UN Women ii) UNOPS.

DFID funds will be disbursed to the UNDP Multi-Partner Trust Fund (MPTF), which will act as the Administrative Agent for funding allocated for the multi-donor Joint Programme. Both UNDP and UN Women are the recipient organisations of the DFID funds according to an agreed division of resources between the agencies with 80% to UNDP and 20% to UN Women.
DFID funds will also be disbursed directly to UNOPS under a Memorandum of Understanding.[31]
[31] Given the CSSF annual allocation process, the MOU would be an annual one, renewed on a yearly basis.

DFID will review programme performance on a quarterly basis, monitoring progress against outputs. DFID will also have a seat on the management board of the projects. This is detailed in the management case.

Implementing partners’ capability and capacity to deliver

a) Core competences of organisation to deliver in-country

Over the past four years, both UNDP and UN Women have already achieved key results in the Palestinian rule of law sector, which is strong evidence of their ability to deliver results in the OPTs. A Central Assurance Assessment of UNDP has been carried out by DFID’s UN Department and is in the process of being finalised.[32] Nevertheless as per DFID requirements, a Due Diligence Assessment (DDA) of UNDP and UN Women will take place before funding occurs to ensure that these organisations have the core competencies and processes to manage DFID funds effectively and deliver in country. Findings from the Multilateral Aid Review and Central Assurance Assessment will be used for the UNDP DDA, and recent internal audit assessments of those country offices will be built upon to inform the UN Women DDA.
[32] Draft Central Assurance Assessment of UNDP, DFID UNCD, November 2014.

In country, DFID recently undertook a due diligence assessment of UNOPS, based on a rigorous EU assessment. Recommendations included:

- UNOPS should provide DFID with a full detailed organogram for the proposed project with percentages each UNOPS employee will dedicate to the project.
- DFID should make certain that milestones and targets are clear with UNOPS for monitoring and reporting purposes.
- DFID should check with UNOPS how fewer projects will affect its operations over the next few years.

DFID has also been funding another UNOPS project (UN Access Coordination Unit) which has been found to be well managed and has performed strongly.[33]
[33] Quest number: 4620039

b) Technical capability and sources of expertise

UNDP and UN Women have significant experience in implementing Rule of Law programmes at the global level, and in the OPTs. They are important players in the justice and security sector, with ability to deliver at scale. The UNDP programme also brings experience of working with a donor consortium. From 2009 to 2013, it implemented a large scale programme to strengthen the PA justice system, attracting funding in excess of USD 20 million for rule of law programming, including support from the governments of Canada, Sweden and the Netherlands.

UNDP and UN Women already have mature relationships with the various stakeholders in the sector and embedded staff members working within several PA institutions.

UNOPS has delivered a total value of projects in the OPTs in excess of USD 120m and has been heavily engaged in the security sector since 2007. As a result, MOI and UNOPS have developed a strong working relationship which is paramount to facilitating change.

Procurement capability

While UNDP had sound procurement policies, the Multilateral Aid Review (MAR) in 2011 found that little evidence was available on the extent to which they were being used to drive the achievement of value for money. However, in the MAR update of 2013, feedback from DFID’s MAR Country Office Monitoring (of 7 countries) corroborates UNDP’s own reporting of improvements in procurement , particularly reductions in operating costs, renegotiations of costs and shorter procurement lead times with lower staff workloads. The in-country Due Diligence Assessment of UNDP will take place in January/February 2015, and will include reviewing their procurement policies and processes to ensure value for money.

UN Women, like UNDP, underwent a MAR in 2011. The 2011 found that their policies largely followed UNDPs procurement and financial control systems. In the 2013 MAR review, feedback from DFID country offices suggested that procurement was executed efficiently and UN Women appeared to have achieved value in their delivery and contracts. This will also be looked at during the Due Diligence Assessment of UN Women.

The 2014 due diligence assessment of UNOPS found that their procurement principles and policies include clear value for money considerations. There, VfM is outlined in regulation 18.02 of Article 18 of UNOPS’ financial regulations and rules that were issued in 13 February 2012. The DDA on UNOPS found that their procedures were satisfactory.

Risk management capability

UNDP/UN Women and UNOPS have mapped multiple foreseeable risks on all levels, ranging from the activity level to the macro-political level. These matrices include impact and probability levels, and mitigating actions.

Throughout the intervention, DFID will remain closely involved in order to explore and negotiate greater efficiency from the organizations. For instance, DFID will meet with partners on a quarterly basis to review the risk matrix. UNOPS will develop a risk management strategy, a shared risk register, and the programme manager will monitor risks monthly. We will address risk with the other implementing partners and donors within the regular Project Steering Committee meetings.

Value for Money

In the 2011 MAR, UNDP was assessed to represent good Value for Money (VfM) for UK Aid. The 2013 MAR review found that UNDP still represents good VfM, however, there was only slight progress on this since the previous MAR. This will be looked at closely in the DDA.

The assessment of UN Women in the 2011 MAR found that it represented poor VFM for UK Aid. However, the 2013 MAR found that UN Women had a number of good practice systems and policies in place to allow management to pay attention to value for money and cost control. In short, the most recent MAR found that there was reasonable progress overall. This will be looked at closely in the DDA.

DFID has conducted a robust assessment of UNOPS (Jerusalem) against DFID’s Due Diligence criteria, testing issues including financial stability, value for money, internal controls and risk management. DFID’s due diligence assessment was built on a previous assessment conducted by the EU on UNOPS, and both found that UNOPS, at country level, has good systems in place.

Tracking VFM

VfM of the intervention will be assessed in due course (e.g. Annual Reviews) by tracking key unit costs. These are likely to include the following (to be confirmed when logframe is finalised):

Economy Indicators:
- Overhead costs payable to UNDP as the implementing agency;
- Overhead costs payable to UNOPS as the implementing agency;
- Consultant salary and benefits for institutional strengthening activities.

Efficiency Indicators
- Cost per MOJ personnel trained in key legal and administrative skills;
- Cost per MOI personnel trained in key programme;
- Cost per legal assistance case provided.

The approach which will be taken to maximise VfM will include the following:
1. a robust methodology for assessing appropriate action over time in order to vary the investment of funds across approaches as more information becomes available;
2. implementers will be expected to systematically check quality of delivery and value for money; and
3. an effective system of Monitoring and Evaluation.

VfM will be judged through a multi-criteria analysis to assess (i) the right balance of investments across the Security and Justice system and identify the break-even point for each, and (ii) the economy, efficiency and effectiveness to ensure VfM.[34] The break even analysis considers the benefits, notably the comparative advantage or ‘unique selling point’ of that particular option, and costs, including administrative, political etc., of the individual delivery options.
[34] Economy – “a measure of what goes into providing a service”, Efficiency – “a measure of productivity, in other words how much you get out in relation to what is put in” and Effectiveness – a programme “is effective in achieving its intended objectives”

By combining these approaches, options will be ranked for their importance in delivering on the programme outcome and outputs, while considering the validity, strength and appropriateness of each option.[35] This analytical method can be built on as more information and data becomes available, therefore allowing the potential for future changes to the design and delivery of the programme. In addition this methodology will act as a starting point for the monitoring and evaluation of the programme.
[35] here may be circumstances where a high score is achieved as part of the multi-criteria analysis, but the break-even analysis is poor (or visa-versa). This may suggest that to begin with this option receives a small amount of funding until more information is available to make a stronger assessment.

Financial Case

Overview of Costs

DFID will be signing up to a Multi-Donor Trust Fund to fund UNDP/UNWomen, and an MoU to fund UNOPS. As per UN rules and regulations, the overhead percentage for the funding dedicated to UNDP and UN Women is 8% of which 1% goes to the UNDP MPTF Office to perform its role as Administering Agency. UNOPS will impose a similar rate of 8%.

    1. Flow of funds

Payments will be made in advance of need due to the UN’s financial and accounting processes. However, following the initial payment, all subsequent payments will be disbursed on the basis of need. Implementing partners will also be required to submit financial statements demonstrating that the previous funds disbursed have been spent, thereby reducing the risk of implementing partners having to return unspent funds.
Subject to negotiations with the implementing partners, DFID will make disbursements in advance:
- on a six-monthly basis for the UNDP/UN Women programme[36];
  [36] The Standard Administrative Arrangement for multi-donor programmes with more than one UN agency provides for annual disbursements (a new one is currently being negotiated, although we do not expect it to be finalised in time for the start of this intervention). The recently agreed DFID-UN Framework Agreement makes provisions for six-monthly reporting as a minimum. We will therefore seek to negotiate with UNDP/UNWomen and other donors the possibility of including additional clauses as an annex to the SAA, using the Framework Agreement as a basis for negotiation.
- on a six-monthly basis for the UNOPS programme, with the exception of programme salary costs, which might need to be disbursed annually.[37]
  [37] UNOPS needs to be able to offer consultants at minimum contracts for a 1 year period to ensure consistency and quality in staff, as well as to avoid high fees related to short-term contracts. UNOPS financial rules and regulations as approved by the Executive Board requires a project to have the cash on hand equal to or exceeding commitments made in human resourcing contracts. Hence if tranches were to be disbursed on a quarterly basis, the project would be limited to offering only 3 month contracts to consultants, significantly increasing the risk of high turnover of programme staff and affecting the delivery of the programme.

    1. Costs to be incurred directly by DFID

The cost estimates for implementation of MOI components by UNOPS is £5.8m (rounded up), while the cost estimates for UNDP UNWomen Joint Programme is £5m.

    1. Costs to be incurred by third party organisations

For the Joint UNDP/UNWomen Programme, partners will enter into agreements with Palestinian and Israeli civil society organisations. These CSOs have been assessed by partners against a range of criteria, including financial management capacity, and will be subject to UN procedures for monitoring and financial controls. The cost estimate for transfer of funds to civil society organisations amounts to approximately £1.3m. As per the formal agreement between UNDP/UNWomen and other partners, transfer of funds to these institutions will be contingent upon an assessment of the institution’s capacity to manage the funding by partners. Based on these quality checks, and partners’ prior experience with many of these third parties, the estimated financial risk is considered to be low. Furthermore, financial risks are mitigated through partners’ method of disbursements to counterparts, which is done against the receipt of liquidation and progress reports, and evaluations from the project team. DFID will have full access to financial information requested by UNDP to the third party.

    1. Financial aid to government

There will be no financial aid to the government as such. Funds will be directed to specific programme purposes under the UNDP/UN Women and the UNOPS components.

    1. Affordability

This intervention will be jointly funded from DFID’s bilateral allocation as well as from the CSSF.

The £5m component for the Joint UNDP/UN Women programme has been factored in to DFID’s bilateral allocation for its Palestinian Programme (£2.4m for 2015/16, and £2.6m for 2016/17).
The £5.8m component for UNOPS will be dependent upon the annual CSSF allocation, and there might therefore be fluctuations in the annual breakdown. For 2015/16, the agreed CSSF allocation for this programme is £1.8m.

    1. Cost profiling and forecasting

Monthly and quarterly cost estimates are done based on the Annual Work Plan forecasts. We expect UNOPS to revise their forecast estimates on a quarterly basis which will be included in their quarterly reports to DFID. We will seek to negotiate six-monthly forecasts with UNDP and UN Women.

Reporting Requirements
UNDP/UNWomen will provide DFID with quarterly updates through joint donor meetings and annual narrative progress reports.

UNOPS will provide DFID with quarterly and annual narrative reports.

DFID will reserve the right to request short ad hoc reports if and when it foresees a tolerance being exceeded. These would highlight the issue, possible solutions and recommended actions for the programme board.

Financial statements
DFID will receive financial statements on activities prior to disbursements to the UNDP/UNWomen and UNOPS.

UNDP/UNWomen will provide DFID with certified annual financial statements including reports based on expenditures incurred per financial year. Financial reports will include a breakdown of fund expenditures per donor contributions, allowing for monitoring of DFID fund utilisation. UNDP/UNWomen will carry out a financial audit prior to the completion of the programme.

UNOPS will provide quarterly financial progress reports and detailed uncertified interim financial reports as well as certified annual financial statements audited by third party external auditors engaged by UNOPS.

Additional financial management requirements

Transparency & accessibility of information

In line with UK policy on transparency and access to information, DFID will make the Business Case and any related DFID programme documents available on DFID’s website and Development Tracker. Documents include DFID’s Business Case, Annual Reviews, expenditures, and Logframes.

Asset Management

No major assets are expected to be procured under this intervention. However, UNDP, UN Women and UNOPS have internal processes to register, monitor and account for assets procured during the programme. Annual reports submitted to DFID will include an Assets register for each component, and at the end of the project, DFID will decide on transfer of ownership of assets to agencies if necessary, and DFID will make clear within its agreements on procured assets with partners.

Fraud Risk

UNDP has an established policy to prevent fraud which includes internal financial control procedures and external auditing. We will look into the details and specific examples on the financial control and procedures for UNDP and UNWomen during the Due Diligence Assessment. We expect it to be completed by February 2015.

UNOPS will exercise the same care in the discharge of its functions under this arrangement as it exercises with respect to the administration and management of its own resources and affairs. UNOPS has a zero tolerance approach towards fraud and fraudulent behaviour that may lead to the misuse of funds and agree in principle to recover such funds. UNOPS will ensure that all goods and services financed from this business case will be used for the purpose set out within this arrangement. As evidenced by the recent DDA, we are confident with the systems in place by UNOPS from previous experience in another project, and consider the level of fraud risk to be low.

Return of Funds

Any unspent funds remaining at the scheduled end of a project, will be returned to DFID unless specifically decided between DFID and UNDP and DFID and UNOPS, in writing. The SRO will ensure that these are transferred to DFID’s central contingency fund.

Management Case

The Management Case sets out arrangements necessary for the successful delivery or implementation of the intervention, including procedures for monitoring and evaluation. It makes the link to the key milestones that will be delivered through the delivery plan.

DFID staffing and management

Within DFID the programme will be managed by the Palestinian Programme in the MENA Department. The Security and Governance Programme Officer (20%) will provide day to day management of the finances and wider programme management support under the direction of the SRO.

At key decision-points in DFID’s involvement in the programme, the SRO will call upon strategic expertise and oversight of the Statebuilding Team Leader and other key advisers (Governance and Economic Advisers) as well as financial and commercial expertise from the finance officer. As this programme is a key component of the Statebuilding Pillar’s portfolio, the SRO will report to the Statebuilding Team Leader in the first instance and then to the DFID Head of Office. The same reporting line will be followed for escalating risks.

Monitoring and Evaluation

A draft logframe (see annex 2) and theory of change have been developed. Both will be reviewed during the first quarter of the 2015/16 financial year following the completion of the MOI functional review and the evaluation of DFID’s current funding to UN Women.

DFID monitoring

DFID officials will monitor progress against the logframe through informal monthly meetings with programme implementers.

Formal programme update and review meetings will take place on a quarterly basis with programme implementers (UNOPS, UNDP/UNWomen), to identify progress against the logframe (and any need for revision) and review the risk matrix. In the case of the Joint UNDP/UN Women programme, the quarterly meetings will be undertaken jointly with other donors (Sweden and the Netherlands). These quarterly reviews will help inform annual and project completion reviews.

External monitoring & review

To strengthen independent monitoring of the programme, the UK’s Stabilisation Unit will be called upon to provide technical inputs to the programme at key stages of the implementation (e.g. in carrying out annual or mid-term/project completion reviews).

Independent evaluations

Both components of the programme have factored in to their planning an independent impact evaluation.

Exit strategy

All the activities under this programme are being developed with a view to ensuring sustainability once the programme terminates. Palestinian ownership of the programme is a critical factor in this. A detailed exit plan for all work streams will be developed following the last annual review.

In addition, through annual reviews, DFID will continue to monitor the value for money of the programme and its various components. If the performance of the programme is poor in a particular area of work and cannot be rectified, we will seek to redeploy the resources of the programme towards better performing areas. If this is not possible, we will reduce the scope of the programme to focus solely on work streams which are performing well.

Governance Arrangements

Senior-level Steering Committees

Formal engagement with PA partners and programme beneficiaries will take place through the Steering Committees. These are expected to take place on a six-monthly basis, and will include PA and beneficiaries’ representatives. These meetings will be responsible for endorsing the strategic direction of the programme as well as resolving any issues that arise during the implementation.

In addition to this process, informal meetings with PA stakeholders will take place on a regular basis to identify any risks or opportunities for the programme in the context of overall security and justice reform. As part of this, DFID, in its capacity of co-chair of the Security Sector Working Group, will engage with the MOI and relevant Security Services, whilst the Netherlands will lead engagement with the MOJ and other justice institutions.

[See annex 3 and 4 for management arrangements of each component]

Risk management

Overall, we assess the residual risk as medium/high. The net risk at the programme level (in terms of activities and delivery mechanisms) is assessed as medium. The most significant and highest risks relate to the political context in which the intervention will operate.

Any heightened risk will be escalated through the management chain.

Contextual Risks	Probability	Impact	Mitigation Measure	Residual Risk
Political or fiscal difficulties lead to a collapse of the PA	Medium	High	DFID-wide continued engagement with the PA, political representations and donors and support to the PA	Medium
Dissolution of/Changes in Palestinian leadership affect the PA’s commitment to reform and human rights and/or donors’ ability to engage with the PA	Medium	High	Political alignment with FCO and where possible other donors as part of ongoing dialogue with the PLO and PA / Building strong relationships with partners active in the sector, including civil society organisations. / Ongoing dialogue with the PA on our Partnership Principles	Medium
Non-functioning of the Palestinian Legislative Council hampers legal reform of the PA	High	Medium	Focus on accountability through supporting civil society organisations to encourage the PA to ensure a more inclusive and participatory law and policy-making process	Medium
GoI-PA Security cooperation is halted or suspended	Medium	High	Political alignment/lobbying with FCO and where possible other political missions	High
Programme-level risk	Probability	Impact	Mitigation Measure	Residual Risk
Resistance to change amongst PA counterparts	Medium	High	Careful planning and full counterpart buy-in to ensure ownership of reform efforts and minimise resistance to the introduction of new ways of working	Medium
Limited PA absorption capacity (e.g. due to staffing constraints)	Medium	High	Functional review and ongoing training needs assessments will determine exact needs and areas for engagement. / Careful planning and engagement with PA counterparts will ensure that programme interventions match PA staffing and resourcing.	Medium
Lack of commitment to gender mainstreaming	Medium	High	Adopt incremental approach through intense engagement focusing on concrete work and activities	Medium
The intervention is unable to deliver results quickly as governance reform takes years and requires gradual, sustained and measured engagement, putting DFID support and vital political buy-in from the PA actors at risk.	Medium	Medium	Set clear expectations at the outset and manage them closely through ongoing dialogue across all stakeholders. / Build trust and strong working relationships with implementing partners as well as between DFID and beneficiaries.	Medium
Entrenched legal and social discrimination against women hinders programme outcome	High	High	Adopt two-pronged approach focused on reforming the institutions as well as strengthening civil society/community-based approaches focused on women’s rights	Medium / High
Management of Joint programme may encounter problems due to internal struggles which could result in poor reporting, execution and/or delays.	Medium	High	Close coordination with other donors of the joint programme, and meetings every quarter with programme board to ensue smoothness of operations	Low
Lack of reliable data to make informed decisions about programme interventions	Medium	High	Ensure meaningful baselines are created, filling data gaps where possible. Close cooperation with other interventions (incl. UNDP) which seek to develop regular perception surveys and data reports.	Medium
Programme staff turnover affects the relationship and trust with PA counterparts, impeding delivery of results	Medium	High	Close monitoring of implementing partners’ staffing arrangements. Close relationship with beneficiaries throughout the implementation to ensure smoothness of staffing transitions	Medium
Funding for the programme will depend on annual CSSF allocations and may therefore affect distribution and amount of funds across activities	Medium	Medium	Ensuring on-time and effective bidding for annual allocation of funds through collaboration with HMG in Jerusalem and in the UK. Build in flexibility into the intervention to adjust effectively.	Low
Poor coordination among Development Partners leads to duplication and wasted resources from our intervention	Medium	High	As co-chair of Security Sector Working Group, DFID will coordinate closely with other donors (including through the Justice Sector Working Group) and security agencies in order to ensure proper coordination across the sector.	Medium
Intervention might directly or significantly contribute to violations of Human Rights	Low	High	Monitor the Human Rights situation and update the OSJA when there is a significant political or security change to identify any risk & mitigate against it / Ensure partners are aware of the OSJA rating and flag any potential risk when identifying new activities	Low
Deterioration of the security situation in the Gaza affects safety and freedom of movement of staff and partners and impedes our capacity to M&E	High	Medium	Ensure flexibility of programme in Gaza to adapt to needs, in addition to ensuring scalability of activities in West Bank.	Medium
Deterioration of the security situation in the West Bank affects safety and freedom of movement of staff and partners and impedes our capacity to M&E	Low	High	Close monitoring of political & security situation. Regularly review programme exit points. If the probability increases to medium, initiate contingency planning.	Low

Annex 1: Theory of Change for Improving Security & Access to Justice in the Occupied Palestinian Territories
Approach: A comprehensive approach to improving Palestinians’ Security & Access to Justice by strengthening institutional and organisational capability of the PA’s Justice and Security Sector as well as making it more accountable and responsive to the needs of its population, in particular women and girls. In Areas which are not under the PA’s administrative control (Area C, East Jerusalem and Gaza), efforts will focus on supporting civil society organisations to support Palestinian’s access to justice.
PROBLEM
OUTCOME
OUTPUTS
ACTIVITIES
Flaws in the PA justice and security institutions (incl. lack of civilian oversight) mean that the services they provide are not responsive to the needs of Palestinians who are not able to hold them to account. Women and girls are particularly vulnerable due to the prevalence of violence against women and a security & justice sector which is not equipped to deal with these issues.
The PA provides more capable, accountable and responsive security and justice services to its people, especially to women and girls
The MOI has the institutional and organisational structures, processes and capabilities to exert clear civilian oversight of state security and intelligence agencies
 Institutional and technical capacity of the MoJ, HJC, AGO and Anti-Corruption Commission strengthened, in particular with regards to legal and gender issues
Women and girls' access to justice and security improved by ensuring accountable service provision to prevent, protect and respond to violence
Civil society contribution to rule of law and community access to justice enhanced
INDIRECT IMPACT: To enable a viable and sovereign Palestinian State living alongside Israel in peace and security
Enhancing the skills of key staff across the security & justice institutions
Technical assistance on the development and implementation of key sector strategies and action plans, including Ministry-wide and gender-specific action plans and standard operating procedures
Targeted training to enhance gender awareness in key institutions and services
Data collection & monitoring of violence against women & women’s access to justice
Support to civil society to provide legal assistance areas which are not under PA control

Programme Governance & Management
WS
Governance
WS
Design & Management
1. Civil society
2. Private Enterprise
3. Frontline Agencies
4. Central Agencies
5. Political System
6. Monitor’g orgs
DIFD Conflict Advisor
Programme Steering Group
MOI Programme Manager
MOI WS #1
Progress legal and institutionalization of MOI and sector
MOI WS #2
Improved planning and strategy execution
MOI WS #3
More efficient and effective support services
MOI WS #4
Improved MOI community engagement and public perception
Panel of Experts
Prog. governance spt team (internal)
Chief Technical Advisor
MOI/UNOPS Programme Support Office
Change
Delivery
Civilian Review Board
Annex 3:
Governance Arragements for MOI Component (UNOPS)
Annex 4 – Management arrangements for the Joint UNDP/ UN Women programme

Annex 5 : Methodologies considered for economic appraisal

Assumed benefit from investing in MoI	Transmission mechanism	Method of estimation	Inclusion in this economic appraisal	Rationale for inclusion or not
Better human resource management systems and stronger expenditure controls in MoI
Lower vacancy rates.	MoI gets faster at filling vacant posts	Efficiency savings as a proportion of MoI budget. This acts as a proxy for institutional strengthening
Improved budget credibility.	MoI strengthens budget process and improving allocations.
Reduced leakages from budget.	MoI institutional reform reduces leakages through payroll, procurement.
Stronger public confidence in security and justice
More accountable, capable and responsive S&J services, especially for women and girls		UNDP Public perception survey	No	Not possible to quantify, but this should certainly be included in the logframe as there is a baseline and it is monitorable.
Better services to handle Violence Against Women cases
Improved service delivery outcomes.	Rule of Law programme enables greater spending on shelters, family protection centres and legal aid clinics, generating returns from each.	Cost to the economy of domestic violence, estimated as 1.8% of GDP (based on an average of Morrison and Orlando study of Chile 2% of 1996 GDP and Nicaragua 1.6% of GDP).	Yes for Option 2, justice sector component	Yes