Project Completion Review – post April 2018

Title: Ghana Health Sector Support Programme (2013-2019)
Final Programme Value £ (full life): £59 million	Review Date:	June 2019
Programme Code: 203536	Start Date: 3 July 2013	Final End Date: 31 March 2019[1]
[1] Output 1 & 2 ended July 2018. Output 3 & 5 (TA Fund, NHIA, FDA) closed Dec 2017, Output 4 ended March 2019.

Summary of Programme Performance

Year	2014	2015	2016	2017	2018	2019
Programme Score	B	A	A	A	A	A
Risk Rating	Medium	High	Major	Moderate	Moderate	Low

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203536/
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203536/

A. Summary and Overview (1-2 pages)

Description of programme and what it has achieved

The Health Sector Support Programme (HSSP) was a £59 million programme which aimed to contribute to a more sustainable and equitable health system in Ghana. It supported Government efforts to strengthen the health system, with a focus on health financing and public financial management (efficient and effective use of resources) and equity (community health care and mental health). The programme had five outputs, delivered by a lead agency of the Government of Ghana (GoG), NGOs with additional support from DFID.
1. Advancement towards UHC (national level): sustainable financing and sector performance: Ministry of Health (MoH)
2. Advancement towards UHC (regional level): scale up community health services: Ghana Health Services (GHS)
3. Strengthen sector management and quality assurance, stimulate more efficient use of resources in health (MoH, GHS, National Health Insurance Agency (NHIA)
4. Improve access to and delivery of mental health services and policy (Mental Health Authority (MHA) Basic Needs Ghana (BNGh), Christian Health Association of Ghana (CHAG)
5. Improve medicines safety and quality and stimulate local manufacturing capacity: Food and Drugs Authority (FDA)

Expected results outlined in the business case included:
- Increase coverage of health services: Percentage of births attended by skilled professional increases from 68% to 75%
- Improve quality: Increase proportion of facilities achieving higher accreditation scores; reduce substandard drugs from 20% to <3%
- Equity: gap between number of nurses in the worst and best scoring regions reduces from 1:1.75 to 1:1.5; increase number of functional community health services; increase number of health workers able to provide mental health care from 769 to 2500
- Sustainability: Increased sustainability of the NHIS and per capita spending on health

Change from original 2014 approved business case:
HSSP was designed to provide up to £67 million, which included £40m of sector budget support (SBS); earmarked financial aid and technical assistance to three Agencies - the Mental Health Authority (MHA), National Health Insurance Agency (NHIA) and Food and Drugs Authority (FDA). DFID also signed grant agreements with two NGOs, Christian Health Association of Ghana (CHAG) and Basic Needs Ghana (BNGh) to improve mental health. There were two main changes from the original business case.
- November 2015 Business Case Addendum: the SBS component was re-programmed after the first year’s tranche (£14m) to earmarked financial aid to CHPS and results-based aid linked to health financing reforms, adding output 2. The decision to re-programme was based on (i) stagnant sector performance, fiduciary risk and concerns that funds were not being channeled through system[2] and (ii) to ensure the programme delivered on its planned equity focus. It responded to a GoG request and Presidential commitment to CHPS, and a World Bank partnership offer to jointly fund CHPS scale up before handing over to GoG. HSSP maintained its other outputs on more efficient and effective use of resources, stewardship of the MoH, quality of medicines and mental health.
  [2] Ghana Health Sector Support Programme: scenario planning and risk management, draft report October 2014,: Jeremy Clarke and Stewart Tyson.
- 2017 Assessment: DFID withdrew support for the construction of CHPS facilities due to procurement delays and reduced the budget to other slower spending areas. Mental health received a boost of £3m on the basis of good results and demonstration of additional need. Overall, the programme was reduced by £8 million. In June 2018, DFID again extended support to mental health, with £450,000 to BNGh with a particular focus on safeguarding.

Throughout these changes, HSSP maintained its focus on supporting Ghana to achieve Universal Health Coverage (UHC) through Ghana’s ‘twin track’ approach of health financing (efficient and effective use of resources) and equity (community level service delivery). It was flexible and responsive to GoG priorities, including around Ebola preparedness in 2014/15, CHPS and mental health, where programme successes and GoG priorities were boosted with additional funding and technical support.

At output level, HSSP progress has been mixed, with three of five outputs as measured by the indicators in the logframe achieved. HSSP directly supported a scale up of community level services in four of Ghana’s ten regions, the establishment of a community mental health system and improvements toward medicines quality. HSSP did not meet two objectives related to health financing and sector management within the programme timeframe (both outcome level results).

Output	Instrument	Main partner	Performance
			2014	2015	2016	2017	2018	2019	Overall
Advancement to Universal Health Coverage- national: 25%	SBS then RBA / Policy support/influencing	MOH	B	A	A	A	B	B	B
Advancement to Universal Health Coverage- CHPS :25%	Earmarked FA for CHPs for service use, GHS planning DFID procurement of equipment	MOH / GHS	N/A	N/A	B	A	A	A	A
Strengthened sector management, financial & quality assurance 25%	TA Fund (GoG managed), FA & TA to NHIA, TA Policy support/influencing	MOH	B	B	A	B	B	N/A	B
Improved mental health:20%	FA to MHA / AG: with (i) CHAG (ii) Basic Needs	MHA / CHAG / BNs	B	A	A	A+	A	A	A
Improved medicine safety Weight:5%	FA - Food and Drug Agency	FDA	A	A	A	A	A	N/A	A

The three outputs achieved, on mental health, CHPs and medicine safety are all areas where it is easier for donor funding to have direct impact.
- HSSP has supported GoG to provide services at scale to four of Ghana’s ten regions, nearly doubling Community Health Planning and Services (CHPS) zones from 1,248 in 2014 to 2,320 in 2018 and acting as a platform for maternal and child health services such as malaria and immunisation closer to communities. These provide services to an estimated 1.3 million women and children, reducing the burden on higher level facilities. CHPS is likely to have contributed to impact indicators on child health.
- The programme supported the establishment of the MHA in line with the 2012 Act. HSSP worked with the public sector, faith-based providers and NGOs to build a community mental health system, with every district now providing some mental health (MH) services compared to 32 at the start of the programme. Ghana now has more than 5000 mental health nurses/officers, including >2000 based at community level (CMHO/CMHN)[3]. In 2018, for the first time the number of people accessing outpatient and community MH services exceeded 100,000 per year. 75% of patients are registered on NHIS to access general health services free of charge, although MH treatment continues to be hampered by the shortage and costs of medicines, limited psychosocial therapy options and continued stigma. Community self-help groups reached 32,827 people, civil society alliances have been built and partners are leading a wave of gradual erosion of social stigma.
  [3] Community Mental Health Officer/Nurse
- HSSP supported a reduction in the percentage of drugs tested as sub-standard from 16% in 2011 to <2.5% in 2017, an increase in local manufacturing capacity and increase capacity to detect drug quality and report adverse drug effects. A continuing partnership was built between the FDA and the UK’s Medicines and Healthcare Regulatory Authority.

HSSP did not meet two outputs related to health financing and sector management during the programme period. These are areas where donors can influence, accelerate action and build capacity, but were reliant on political and financial priorities which shifted over time. During the HSSP period the health sector was impacted by: the threat of Ebola in 2014; revelations of fraud in the central medical store in 2015[4]; changing GoG priorities around the 2016 elections as well as lower than expected levels of economic growth and stagnant funding for health. These factors, combined with ongoing weaknesses in governance and public financial management, contributed to delays and reduced the effectiveness of HSSP outcomes, and in the case of sector management, output level too. Progress included:
[4] The MOH has been working on a Supply Chain Master Plan to guide the procurement, warehousing, distribution, staffing and financing medical supplies. However, commodity security was severely disrupted when on 13 January 2015 Ghana lost drugs and medical supplies estimated to cost GHC263 million, following the fire at the Tema Central Medical Stores. But Government is yet to prosecute the 12 persons found culpable in spite of calls by donors, the media and parliament.
- The MoH-led Technical Assistance (TA) Fund delivered some pieces of transformative work with potentially large savings that could be reinvested into the sector. The support to NHIA on automation of software was important. However, the TA Fund did not meet its targets or deliver consistently as envisaged.
- Key reforms envisaged in the Health Financing Strategy and Implementation Plan (HFS-IP), notably health provider payment mechanisms and primary health care (PHC) had not been delivered by July 2018, despite steps forward in the early years resulting in the disbursement of DFID’s results-based aid (RBA). At outcome level, there has been no change on per capita government spending on health. At $30 pp in 2018 this represents a decline in real terms. NHIS is not delivering on its potential, coverage (not measured by the programme) declined from 40% to 36%. However, NHIS reforms were, after the period under review, moving forward as part of the ‘Universal Health Coverage Roadmap’.

Recommendations for DFID’s future programme portfolio in Ghana. Additional recommendations for the sector and for DFID, are included in each of the output sections below.

Recommendations for the DFID’s approach to transition in Ghana: As development is not linear, and transition is highly context sensitive DFID will need to maintain a flexible approach, regularly assessing Ghana’s progress against key health indicators and adjusting the UK offer accordingly, pulling in resources as needed. Based on Ghana’s current trajectory - established levels of growth at 8% in 2019; Government’s push for self-reliance (‘Ghana Beyond Aid’); only “moderate”[5] progress in the health sector; alongside DFID’s approach to transition[6], and lessons from HSSP on the need for a graduated approach, DFID Ghana will remain engaged in the sector but with a different offer. DFID will shift from directly funding health services to supporting more efficient and effective use of Government’s own resources for health. This will align with GoG’s priorities, supporting their reform objectives while focusing on four priority areas below, which draw from DFID’s (draft) Health Strategy to 2030 and assessment of the current gaps in the sector including support from other partners.
[5] See Ministry of Health’s Holistic Assessment 2018
[6] Aid transition refers to a relationship where country-level bilateral aid will change, but the development relationship continues. Transition countries are defined as “a set of middle-income countries and their features where the longer-term prospects of the poor are overall good, but not necessarily secure or sustainable, and at risk of development reversals

Continue to support Ghana to progress towards UHC through Health System Strengthening (HSS). The bilateral Partnership Beyond Aid (PBA) programme will focus on institutions, systems and sustainability, financial management and financing (equity and efficiency), quality of care. PBA’s support to governance of the sector will depend on entry points and where it can have impact. Lessons from HSSP that have informed the design of PBA include:
- Health systems and financing reforms are difficult, essentially political and take time – no country’s journey to UHC is quick. But that does not mean the UK should not continue to engage in this area as it underpins the transition to self-reliance. GoG has refocused on financing through the ‘UHC Roadmap’, linked to the attainment of SDG 3. The President’s “Ghana Beyond Aid” plan has energised debate around self-financing. Reductions in future donor financial assistance, which represents 9% of the health budget, means there is a heightened imperative to address financing the sector and advance financial protection. DFID Ghana should continue to engage with and influence policies on PHC and health promotion, and NHIS/financing reform.
- There is still work to be done on quality of care, particularly for the most neglected groups, as quality is a greater impact on lives lost than access to care. While this needs a systems wide approach, and so should be a key part of PBA (HR management, monitoring/supervision, regulatory systems), other programmes can contribute to aspects such as clinical care e.g. through Women’s Integrated Sexual Health programme (WISH), or mental health (Quality & Rights focus).
- There is a continued need to build citizen demand for and political will to prioritise health and to deliver quality services for all. PBA should consider a focus on building social accountability mechanisms to demand effective, equitable quality services and carefully consider GoG responsiveness.

(2) Continue the effort to tackle causes of early death and disability for the poorest and most excluded including diseases of poverty and addressing premature mortality and morbidity of maternal mortality and early child death. Through multilaterals and central programmes including the World Bank, The Global Fund to Fight Aids, TB and Malaria, Gavi, the Vaccine Alliance, the Global Financing Facility, UNFPA, and ASCEND[7] for Neglected Tropical Diseases (NTDs). Progress in Ghana on maternal and newborn health continues to be slow and lags behind countries of similar income levels, related in part to issues of quality of care (above). There are DFID multilateral partners working in these areas, and Ghana is a new GFF focus country. DFID will need to remain engaged, working with partners to think about HSS, increasingly through integration of disease programmes into the essential health service package, sequenced transition and planning by GoG to ensure gains are sustained as there is a decline in support as the economy grows.
[7] DFID regional programme: Accelerating the Sustainable Control and Elimination of Neglected Tropical Diseases (ASCEND)

 (3) Tackle the risk factors for mental and physical ill health, to reduce current mortality and morbidity; and to avoid/mitigate some of the ill-health trajectories which will pose a significant burden in future. The bilateral Leave no One Behind (LNOB) programme will focus on mental health and disability. This will be based on HSSP programme learning and emerging international evidence on de-institutionalisation, community-based rehabilitation, rights-based approaches and early intervention and prevention. We will prioritise implementation of robust safeguarding mechanisms both to improve the quality of services delivered and to mitigate associated risk to DFID. We will continue to influence GoG to prioritise the procurement of psychotropic medicines and support CSOs to address stigma and build the demand for quality MH services – both barriers to access. Further recommendations are in output 4.
DFID G will also maintain an advisory role on UK ODA on anti-microbial resistance (AMR) through the Fleming Fund and related initiatives.

 (4) Advance comprehensive Sexual and Reproductive Health Rights, and the rights of people to inclusive, high quality health services. DFID will continue to build GoG and the private sector capacity to deliver high quality family planning services and ensure their sustainability in the national package of services, through the CMP Women’s Integrated Sexual Health (WISH) as well as through UNFPA supplies and policy engagement with post FP 2020 activities.

DFID’s support should be delivered through a variety of instruments available: policy discussions, partnerships, technical assistance, bilateral, centrally managed programmes (CMPs), multilaterals, and through greater donor co-ordination. Transparency with government and partners in-country is key: DFID must ensure clear communications on the changing offer on health through bilateral and central programmes, and global funds as part of communications for next Business Plan. The DFID-MoH exchange of letters is a helpful mechanism for this and should continue.
A number of lessons relate to programme delivery model and aid instruments and the following recommendations are being applied in DFID Ghana’s new portfolio.

Results based aid (RBA) supports change but not necessarily incentivises it. HSSP used a combination of results-based aid, earmarked financial aid (FA) and TA. RBA worked where aligned with GoG reform priorities and to other development partners efforts. It was however, subject to changing political priorities and delays following the 2016 elections, as the new government determined new focus areas. RBA can enable reforms for which there is already political commitment to take place, and needs to be thought of as one, but not the only tool to support change. If combined with TA, more likely to have impact. This is being applied in DFID Ghana’s new Leave No One Behind (LNOB) programme.

Technical Assistance (TA) is most effective when demand driven, responsive, agile, builds and not substitutes capacity or is highly specialised[8]. Importantly, it should scale up and scale down in response to the political economy. PBA should consider options for embedded TA with GoG, combining government and external national and international experts, de-linked from financial management of the TA Fund, that can scale up/down as needed. Clearly defining measurements for the effectiveness of TA is also needed.
[8] Refer to DFID How to Note on How to Build Capacity.

UK - GoG relationship should be given space to focus on the high-level reform issues, not detailed financial management ones. HSSP’s approach to managing FA to different agencies has been resource intensive and has arguably distracted both from having strategic policy level discussions. On MH, catalysing coordinated working between GoG agencies and partners was a challenge. This points to the need for a programme management unit or fund manager to manage financial support, rather than DFID directly, to free up time to focus on strategic conversations. This is being applied to LNOB programme through a considering a mix of a fund manager and RBA.

Linked to the above, the redesign from SBS brought in more DFID management requirements and complexity of delivery chains, with an increase in the number of partners interactions at different levels of government and significant delays in the flows of funds through the system outside of DFID control. Added to which, the original BC underestimated the degree of DFID engagement in some components (such as the TA Fund and the MH component) and increased needs for monitoring and risk management. So, whilst programmes such as HSSP are designed to be flexible and adaptive, the management cost to DFID (i.e. staff engaged in a programme) must adequately respond to this.

Follow up actions required following approval of this report

- Finalise review of CHPS close out audit from PWC and refund of balance: ~600,000 GHC
- Handover of assets for remaining partners: GHS, MHA, NHIS
- Presentation of CHPS lessons learnt with GHS to partners
- Presentation of PCR findings and UK support to health 1993-2018 within DFID and with partners

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Advancement to Universal Health Coverage - National
Output number per LF		1	Output Score	B
Impact weighting (%)?		25%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Note on indicators and data: Indicators are outcome level, reflecting the SBS/RBA aid instruments. Given the time lag in data (available in April of the following year) the ‘2019’ score reflects progress in 2018.

Indicator(s)	Milestones (2018)	Progress (2019, based on 2018 data)
1.1 Improved overall performance of the health sector- proxy Holistic Assessment score	Improve on previous year	2018: 3.6 Achieved / 2017: 3.4 Achieved / 2016: 2.8 Not achieved / 2015: 3.2 Achieved / 2014: 3 Achieved
1.2 Budget execution on goods and services	Targets initially set at 90% then dropped to as more realistic >65%	2018: 82% Achieved / 2017: 55.1% Not achieved / 2016: 46% Not achieved / 2015: 53% Not achieved / 2014: 61% Not achieved / 2013: 55% Not achieved
1.3 % of health financing strategy annual implementation plan being delivered	By 2018, 80% of planned stages delivered. (50% in 2016, 80% in 2017)	Not achieved / 2018: Not achieved 30% plans delivered) / 2017: Achieved (progress against phase 1) / 2016: Achieved (implementation stalled, but / 2015: Achieved (implementation started) / 2014: Achieved (complete HFS-IP) / 2013: Achieved (draft HFS-IP)
1.4 Sustainability of National Health Insurance Scheme (NHIS) funding	New NHIS in operation (new package and eligibility defined, capitation rolled out)	Not achieved / No significant reforms during HSSP project period. Capitation started, suspended. Actuarial study not yet published after >3 years. PHC package (funded by TA Fund) not yet taken forward yet.

Narrative for the score
Indicator 1.1 Sector performance is measured by an annual Holistic Assessment, a process that culminates in a ‘composite score’ which includes indicators related to service coverage and equity, health outcomes, health sector governance and management, prevention and promotion. 2018 was the first year for the implementation of the Health Sector Medium Term Development Plan (HSMTDP 2018-2023), with a new methodology. On a scale from 0-5 on the holistic assessment, the sector’s performance score was 3.6 or moderately performing. This composite measure does mask progress in some areas or declines in others – indicators are drawn out in other outputs and section C of this report. Throughout HSSP, the health sector has judged itself to have stagnating or moderate performance.

Indicator 1.2: Budget execution rate is the proportion of approved budgets released by the Ministry of Finance (MoF) to the MoH. The 20-18 milestone for budget execution (82%) exceeded the target and all years prior to this – where this had hovered around 50% reflecting continued issues around PFM. It is of note that the new Minister and Chief Director for MoH Health appointed in 2017 and 2018 come with a finance background and are committed to move forward with PFM and rolling out the Government Financial Management and Information System (GFMIS) in the health sector. A DFID CMP is also providing TA through WHO to MoH to improve programme-based budgeting.

Indicator 1.3 & 1.4 The MoH developed a Health Financing Strategy & Implementation Plan (HFS-IP 2014-2026)[9] to guide Ghana’s approach to health financing, drive reforms in NHIS to ensure sustainable financing and financial risk protection for the poor and increase financing for primary health care (PHC - linked to HSSP output 2. This was a broad reform strategy covering areas such as PFM, revenue raising and provider payment mechanisms, increasing enrolment in NHIS among the poor, health worker redistribution and capital investment plans. These were key areas which HSSP sought to drive forward progress on through results-based aid agreements and TA. Steps forward in 2016, 2017 and 2018 – highlighted below - resulted in the partial disbursement of DFID RBA. Further details of milestones are included as Annex A, and support provided below by the TA Fund in output 3.
[9] Developed by a MoH chaired Technical Working Group, comprising the representatives from the Ministry of Finance, Accountant-General’s Department, the MOH/Agencies, NGOs and development partners.

Ghana’s flagship National Health Insurance Scheme (NHIS) has been an example in region and globally of progress towards UHC, but for the HSSP period was under significant pressure, and not delivering on its potential, with population coverage falling from 40 to 36%. A Presidential review at the end of 2016 made recommendations on sustainability, efficiency, including the need to focus more on primary care. Low levels of spending in 2016 and 2017 contributed to NHIA indebtedness to service providers (up to 16 months arrears in 2016/17), forcing providers to exit the scheme and/or introduce co-payments. This increased financial barriers to access, especially among the poor. The informal cost sharing policy appears to continue despite recent progress in clearing debts (in 2018 reduced to <9 months delay) and improving membership through mobile renewals, moving to e-claims. An actuarial analysis of the package of benefits, supported by DFID, was completed in 2019, although no changes have yet been made.

Implementation of the HFS-IP including public financial management & public sector procurement
Progress towards capitation in three regions: 80% of enrolled population registered with a preferred primary healthcare provider, a necessary pre-condition for capitation: achieved
- Completion of PHC strategy with a defined list of services to be covered capitation: achieved
- In year 3, following the change of political party, a statement of intent on the 2016 NHIS Presidential Review including planned implementation of policy reforms (above) and revitalisation of the health financing working group: partly achieved
- National health accounts completed and analysed: achieved
- Dissemination of the public expenditure and implementation review achieved
- Revised procurement manuals and updated procurement plan in place and % executed: achieved
- Increased % of audit queries resolved, and leaders trained on the new PFM: achieved
- New efficient models in medicines procurement through framework agreements in place for agreed medicines: achieved
From year 3, milestones were added related to warehousing and supply chain distribution, following the 2015 Central Medical Stores Fire in which DFID, government and partners lost commodities (2016 AR)
- Three regional medical stores upgraded based on the warehousing optimisation study: achieved
- 80% of all health facilities in four regions at sub-district level including CHPS receive health products on a regular basis based last mile distribution plan: achieved

By 2018 the HFS-IP document was no longer in use, and just 30% of the strategies contained within the document were completed. NHIS reforms have not yet taken place, although the actuarial analysis of the NHIS package was completed in 2019, and reforms to increase coverage are proposed under a new overarching framework - the UHC roadmap. However there has been continued progress in procurement and last mile distribution (recent Gavi audit) and the introduction of framework contract in 2017 between the MOH and the pharmaceutical companies could reduce the price of medicines on the NHIS by 30%

Lessons identified this year linked to this output and recommendations for future programmes

1. Donor transition: MoH know they have a looming financing gap. DFID could support them think through what “beyond aid” looks like including a range of financing options. HSSP has shown that there are limitations in providing technical support to what is a political decision, and it is ultimately MoF and GoG to determine the appropriate budget allocation to health.
2. PFM issues continue to be a significant barrier to achieving Universal Health Coverage (UHC). Developing more functional systems and processes both within MoH; and between MoH and Ministry of Finance (MoF) could help alleviate this. DFID is looking to support this under PBA.
3. Results Based Aid worked where aligned with GoG reform priorities, and supported by other partners (e.g. framework contracting, warehousing reform). It was however subject to changing political priorities (and delays following an election). However, this continues to be a useful aid instrument for financial aid in Ghana, subject to partnership principles and fiduciary risk assessments and particularly where used as one tool in a package of support. This lesson is being taken on in the new LNOB programme in its support to mental health.

Output Title	Advancement to Universal Health Coverage through improved PHC -
Output number per LF		2	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N
Risk:		Moderate	Risk revised since last AR?	N

Note this section is based on an external review carried out in June 2019[10], which also reviewed and cleaned up data, some of the results are different to previously reported results but scored are not affected.
[10] DFID Ghana support to Community Health Planning and Services (CHPS) 2016-2018, Achievements, Challenges and Lessons Learned. Kathy Attawell and Ayaga Bawah, Oxford Policy Management.

Indicators	2015	2016	2017	2018 targets	Progress 2019 (2018 data)
2.1 No. of functional CHPS zones in the 4 regions	BAR: 495 / ER: 383 / CR: 220 / WR: 388 / Baseline	BAR: 558 / ER: 547 / CR: 255 / WR: 410 / Achieved	BAR: 713 / ER: 716 / CR: 262 / WR: 586 / Achieved	BAR: 580 / ER: 700 / CR: 309 / WR: 500	BAR: 742 / ER: 640 / CR: 389 / WR: 567 / Achieved
2.2 No. of beneficiaries (ANC registrants and U5 weighed)	BAR: 89,217 / ER: 88,318 / CR: 89,815 / WR: 100,251 / Baseline ‘	BAR: 269,372 / ER: 329,158 / CR: 252,148 / WR: 365,763 / New indicator	BAR: 327,364 / ER: 347,204 / CR: 272,172 / WR: 320,291 / New indicator	BAR: 270,000 / ER: 330,000 / R: 253,000 / WR: 366,000	BAR: 342,959 / ER: 365,564 / CR: 278,759 / WR: 319,331 / Achieved
2.3 % pregnant women ANC 4+	BAR: 64.5% / ER: 50% / CR: 63.6% / WR: 64.2% / Baseline	BAR: 89.7% / ER: 70.5% / CR: 68.85 / WR: 68% / Achieved	BAR: 81.1% / ER: 67.5% / CR: 69.1% / WR: 66.4% / Not achieved	BAR: 80% / ER: 70% / CR: 70% / WR: 70%	BAR: 84.1% / ER: 66.4% / CR: 77.1% / WR: 68.9% / Not Achieved
2.4 Family planning acceptor rate[11]	BAR: 32.9% / ER: 26.2% / CR: 21.9% / WR: 20% / Baseline	BAR: 52.3% / ER: 27.8% / CR: 29.8% / WR: 23.6% / Not Achieved	BAR: 58.2% / ER: 28.2% / CR: 30.5% / WR: 26.2% / Not Achieved	BAR: 50% / ER: 30% / CR: 32% / WR: 27%	BAR: 55.8% / ER: 28.4% / CR: 32.6% / WR: 29.1% / Achieved
2.5 U5s treatment (total # of diarrhoea cases seen at OPD/# children U5)	BAR: 18% / ER: 17.6% / CR: 14.7% / WR: 19.4%	BAR: 18% / ER: 15.5% / CR: 16% / WR: 21%		BAR: 30% / ER: 20% / CR: 30% / WR: 30%	BAR: 18.9% / ER: 10.5% / CR: 9.4% / WR: 15.1% / Not achieved

DFID supported Ghana Health Service’s Maternal and Child Health and Nutrition Improvement Project (MCHNP) from November 2015 to June 2018, which was also funded by the World Bank (till 2020). This – the driver towards enhanced PHC – was in response to the President’s commitment to resurrect the policy and uplift the scale and quality for the national CHPS programme which has existed for 20 years. DFID funding supported four regions – Brong Ahafo, Central, Eastern and Western – with the World Bank funding the other six. MCHNP specifically targets women of reproductive age, pregnant women and children aged under 2 and supports community delivery of a package of health and nutrition interventions, improve community health knowledge and practices, create demand and strengthen accountability.

CHPS is a national strategy that aims, together with the NHIS, to achieve Universal Health Coverage. It is intended to make services available close to the client and to reduce geographical and wealth inequities in access to health care. CHPS involves a zone, a compound (comprised of a facility and accommodation for staff), Community Health Officers (CHOs) who live and work in the community, Community Health Volunteers (CHVs), and Community Health Management Committees (CHMCs). A CHPS zone is defined as functional when 12 key milestones are completed, and a CHO resides in the community and provides a basic package of services to the catchment population. DFID provided financial aid to GHS aligned with the World Bank programme to support operational cost and community outreach activities. DFID also directly procured equipment. There had been plans to support CHPS construction, but the programme was slow in spending and identifying a suitable procurement route, and DFID withdrew support in this area, which was also supported by USAID, JICA and KOICA.

Narrative for score
Indicator 2.1: The number of functional CHPS zones increased in all four DFID-supported regions from 1,248 in 2014 to 2,320 in 2018, exceeding three of the four targets for the year. Based on the estimated population covered by CHPS in each region, these were providing services to more than 8.5 million people in 2018. The number of functional CHPS zones declined in Eastern Region between 2017 and 2018, although it is still higher than 2015. The reasons for this are unclear; it may be due to more accurate reporting or a real decline. Data for this indicator is based on self-reporting by districts, which does not match the 2018 GHS 2018 CHPS verification survey. This was based on a more comprehensive review of ‘12 milestones’ met and found that a low proportion (13%) could be defined as fully functional.

Indicator 2.2: The total number of direct beneficiaries reached by CHPS[12] (women attending antenatal care – ANC clinics and children under 5) in the four regions increased from 367,601 in 2015 before DFID support started to 1,306,613 in 2018. This represents a more than a threefold increase from 367,601 in 2015. Targets were met in three of the four regions; Western Region did not achieve its target. Children under five reached through child welfare clinics account for most of these beneficiaries. As Table 1 shows, the number of pregnant women registering for ANC increased in all four regions and by around 25% overall.
[12] Total number of direct beneficiaries based on number of pregnant women registering for ANC and number of children under five registered for weighing.

Table 1: Number of pregnant women registered for ANC at CHPS level

Region	2016	2017	2018
Brong Ahafo	5,608	6,382	7,175
Central	10,282	11,866	13,232
Eastern	17,671	19,072	19,651
Western	15,046	18,020	21,169
Total	48,607	55,340	61,227

Indicator 2.3: At outcome level, the proportion of women attending 4+ ANC has increased in all four regions, particularly in the Brong Ahafo and Central Regions, which exceeded their 2018 targets. Eastern and Western Regions did not quite meet their 2018 targets.

Indicator 2.4: The family planning (FP) acceptor rate increased in all four regions, with all regions except Eastern meeting 2018 targets. This reflects increased access to FP services and commodities through CHPS, and national trends. The contraceptive prevalence rate has also increased from 22% in 2014 to 26% in 2018, after many years of stagnation, with significant increase in % share to long lasting methods. CHPS have provided a platform for this.

DFID supported GHS in their national task shifting policy, training of Community Health Nurses to provide contraceptive implants as well as injectables (2,861 in total, 1207 using HSSP funds). This is also likely to have influenced uptake of family planning across all four regions. Feedback during field visits indicated that many women choose method that are less visible to partners; this suggests that there is more to be done to sensitise men on family planning to ensure their support and that women can choose from a range of methods. Data on the extent to which acceptance translates into sustained use of family planning would be useful to assess the effectiveness of family planning counselling and services.

DFID supported a separate reproductive health programme in Brong Ahafo (2013- 2017, Ghana Adolescent Reproductive Health Programme – GARH) and this is likely to have contributed to the better results achieved in this region. NHIS plans to operationalise Ghana’s commitment to include long lasting, reversible contraceptives (implants and injectables) in the benefits package, based on a pilot supported through another DFID project (Preventing Maternal Deaths & Access Health Markets for Equity), which should contribute to reduced financial barriers to accessing FP services and sustainability for Ghana.

Indicator 2.5: Data on U5s treatment (total number of diarrhoea cases in U5s seen at out patient level over total number of children U5) showed no change in Brong Ahafo and a decrease in the other three regions. (Data for 2017 is not included as it is significantly different from other years.) Targets were not met in any of the four regions, but it is difficult to interpret the data. Fewer treatments at OPD could mean that CHPS are treating more diarrhoea cases at community level or that the number of cases has decreased.

An external review of CHPS completed in June 2019 provides information on achievements beyond the logframe, lessons learnt and sustainability. This concluded that support for CHPS through HSSP has contributed to increasing service delivery, and community and national health system strengthening, which should contribute to future improvements in outcome indicators, even if not yet evidenced. Key findings:

Increasing service delivery and uptake – in addition to those areas outlined above
- More than 500,000 children immunised. The number of children immunised at CHPS level increased in all four regions and by around 30% overall between 2016 and 2018, from 188,726 to 243,527. National sector-wide indicators show that the proportion of children fully immunised (using Penta 3 coverage as a proxy) increased from 90% in 2014 to 97.8% in 2017. While funding is provided by Gavi and delivered by the Expanded Programme for Immunisation, the scale up of CHPs has provided a platform for this.
- Vitamin A supplementation. The number of doses of Vitamin A provided by CHPS increased in all four regions and by around 50% overall between 2016 and 2018, from 723,759 to 1,109,282.
- Increased prevention, detection and early treatment of malaria at CHPS level. The number of insecticide-treated nets distributed at CHPS level increased in all four regions and by around 100% overall between 2016 and 2018, from 101,547 to 213,039. This should result in significant health benefits, since feedback from CHPS staff and communities visited for this review suggests that malaria is the main cause of illness and reason for seeking health care from CHPS facilities.

CHPS contribution to Health system strengthening and health policy
- Strengthened planning and budgeting. DFID funding has enabled the GHS to revise resource allocation criteria, provide support to the regions for preparation of 2017, 2018 and 2019 plans and budgets, develop a detailed costing of services to inform negotiation with MoH, MoF, NHIS, World Bank around budget allocation and conduct a review of health workforce staffing norms (described in output 3).
- Increased financial management capacity targeted training for 1,510 finance staff in the four regions in financial management and Accounting Treasury Financing reporting.
- Increased health worker capacity. DFID has supported advanced training in Public Health Nursing and training for 228 nurses through the GHS midwifery task sharing initiative, which aims to address the shortage of midwives at health centres. Supported implant task-shifting by training 1207 HW.
National dissemination of policy and guidelines. printing and national distribution of the updated 2016 CHPS national policy (this was revised through the DELIVER programme at the Office of the President) and CHPS implementation guidelines.
Essential equipment and transport procurement of basic MCH equipment, vehicles, motorbikes and laptop computers, has also been critical, to enable CHPS health workers to deliver services to the community and to support monitoring and supportive supervision. DFID has also supported national monitoring by GHS, including a verification survey to assess CHPS functionality across the country.

Lessons identified this year linked to this output and recommendations for future programmes

The external review made recommendations to GHS to improve future CHPS approach and DFID in future programming.

1. Measurement: When designing a new programme, take the necessary time to establish baseline, agree milestones and approaches to M & E. Output 2, and its five related indicators were added to the logframe to reflect the addition of the CHPS component to the HSSP. The output title (advancement to UHC) is misleading as the output does not address the financial protection aspect of UHC. In practice some CHPS facilities are supporting the community to enrol in the NHIS; an indicator and target for this could have been included. Other issues in the logframe included different definitions of ‘functionality’, the absence of appropriate national data indicators on quality of care at CHPS level. There are no indicators in the logframe, at output or outcome level, to monitor the effectiveness of CHPS nutrition activities e.g. vitamin A supplementation and exclusive breastfeeding.
2. Build community demand: The extent to which CHMCs are representative and active, and communities are engaged in monitoring CHPS services, varies. Limited community demand may be linked with rising expectations on secondary and tertiary care and future programmes could look at building demand for quality PHC services close to home and consider different approaches for community education beyond community health clinics and durbars to ensure barriers on demand side addressed. PBA will include an element of social accountability.

Focus on quality of care and ‘missing middle’. DFID funding supported national HSS activities, community activities and some regional, district and sub district activities. Reviews and monitoring visits have identified weak management and supportive supervision at sub-district, combined with a lack of understanding of CHPS guidelines at that level. The extent to which CHPS staff receive supervision varies and depends on effectiveness of the sub-district health team and the nearest health centre. GHS and partners working in this area should consider the quality of training provided, integrated supportive supervision, referral mechanisms or identify others working on this (e.g. USAID supported Preferred Primary Care provider - PPP networks).

Sustainable funding for CHPS/PHC continues to be a challenge as this is political, but TA for PHC financing should remain a priority for UK support. DFID closely linked incentives for results-based aid (output 1) and 3 (TA) to CHPS output 2, to ensure that the investment in front line services would be sustainable. However, several assumptions related to government priority and reforms, did not hold true. DFID and World Bank funding was explicitly stated as a short-term injection of support to get the President’s Policy off the ground. Despite some steps forward, operational costs of CHPS are still donor dependent, and the national debate on financing preventive care at CHPS level (not currently covered by NHIS or GoG funds) continues. However, DFID and the World Bank have played an important role in showing how it could be done. PBA should continue to provide technical input on sustainable financing for PHC and support the nationally defined package of cost effective PHC interventions.

Output Title	Strengthened sector-wide internal management and quality assurance
Output number per LF		3	Output Score	B
Impact weighting (%)?		25%	Impact weighting % revised since last AR?	N (if Yes, indicate if ↑or ↓)

Note: this output ended in December 2017 and has been reported on in previous ARs. Given the indicators are annual not cumulative, scores for 3.1 to 3.3 reflects the average over the period and not the final year. This section draws from the July 2018 study ‘Review of TA Fund Achievements and Lessons Learnt’

Indicator(s)	Milestones	Progress
3.1% of all commitments made in the strategic Aide Memoire from the health summit delivered	% of all commitments delivered (new indicator from 2015)	Overall – Not achieved / 2018: Achieved 92% / 2017: Not achieved 70% / 2016: Not achieved 65% / 2015: Not achieved 60%
3.2 % of DFID Funded and MOH managed Technical Assistance Plan delivered	% of the agreed TA Plan delivered with demonstrable change on policy and programme – at least two strategic pieces of work delivered with DFID support per year	Overall – not achieved / 2018: Not achieved 43% / 2017: Not achieved 65% / 2016: Achieved 90% ‘commenced’ / 2015: Partially achieved / 2014: Not achieved
3.3 Use of new models in planning’ (in relation to human resource planning, other evidence in use (BoD) etc.	Evidence of new models being used in annual planning (e.g. informing the medium-term strategic plan),	Overall – Not achieved / 2018: Not achieved / 2017: Partly achieved / 2016: Achieved / 2015: Achieved / 2014: Not achieved
3.4 % of National Health Insurance Authority (NHIA) Regional and District offices have automated financial accounting system	By 2018, 100% of offices use automated system	Overall - Achieved / 2018: Achieved / 2017: Achieved / 2016: Not achieved

Narrative for score
Performance on this output was mixed. There were significant steps forward, but this output is marked ‘not achieved’ based on agreed milestones. Indicator 3.3 was met eventually, outside of the programme timeframe.

Indicator 3.1: The aide memoire from each Annual Health Summit is agreed by GoG and development partners and guides strategic direction for the forthcoming year. In the final year under review 11 out of 12 of the commitments in the 2017 aide memoire were achieved, but in all previous years the target was not met. Sector achievements in 2017 included: the development of the Health Sector Medium Term Development Plan (2018-23); the establishment of a Health Promotion Unit to give policy direction to behaviour change communication interventions (albeit with questions about duplication with GHS), the National Quality Strategy and the Quality Management Unit; the reactivation of the Internally Generated Funds (IGF) committee; the regular activities of the One Health Committee on AMR; National Action Plan on Health Security, National Pricing Committee, and the new National Health Policy.

These are laudable commitments to policy and structures to develop, however, as this PCR illustrates, there are challenges to the implementation, as the underlying institutional tensions remain and increased funding for the sector is not assured. Throughout the programme the Health Summit, Holistic Assessment (and joint monitoring visits that precede this) and Aide Memoire have provided a useful way to jointly assess the performance of the sector. DFID funded this for much of HSSP and they are engrained as a way of working in the Sector Common Management Arrangements.

Indicator 3.2: The TA Fund supported research and policy analysis to inform national planning. DFID and GoG jointly agreed annual plans, aligned to five areas: stewardship; health financing and public financial management; human resources for health; procurement and supply chain; and clinical issues. Activities were linked to other HSSP focus areas to increase achievement and sustainability of these outputs.
In 2017, 12 out of the approved 28 activities under tranches 3 and 4 were completed. This indicator also includes a subjective element as to whether a project was ‘strategic’ with a demonstrable impact on policy and programming. A number of pieces of work, which have impacted policies and strategies were finalised, with MoH full oversight and ownership. According to Dr Emmanuel Odame, Director of PPME, MOH, “The TA Fund was crucial in enabling the MOH move forward on many reforms in the HSMTDP, because it came at a time when the country and for that matter the MOH was facing a severe financial crunch’. Areas where the TA Fund delivered:

Developing the Sustainable Development Goals (SDG) policy and indicator matrices, and enabled Ghana to take a lead role in SDG negotiations.
- The Draft National Health Policy - Ensuring the Right to Health through Universal Health Coverage, developed to replace the decade-old policy. This commenced in in May 2017. This policy is informing the ‘UHC Roadmap’ for Ghana which is currently under development. The focus is looking at health from a social determinants of health perspective
- Burden of Disease (BoD) Study: quantifies the physical and psychological impact of diseases, conditions and risk factors. This enabled the MOH to contextualise the SDGs, informed the HSMTDP and guided WHO Country Cooperation Mechanism.
- Anti-Microbial Resistance Policy and Action Plan: launched by the President in April 2018, this aims to increase public awareness about drug resistance, reduce treatment failures, support research into new medicines, strengthen surveillance, promote rational use of medicines and reduce health care costs. Ghana has now a well-established AMR Platform using the One Health approach and has been able to leverage support for the Action Plan, including from the Fleming Fund.

Advancing Health Financing reform and PFM.
- A Roadmap for Sustainability and Transition from External Finance (July 2018)
- Health Financing Strategy and Implementation Plan (HFS-IP see output 1).
- Other documents or sub-strategies contained within the HFS-IP:
  - PHC Care package of care, assisting the NHIA to define the benefit package, informed the actuarial analysis and UHC Roadmap. This is expected to prevent overuse of secondary and tertiary service through the gatekeeper system and reduce the escalating cost of medicines
  - Public expenditure and implementation review, identifying key PFM blocks
  - The National Hospital Strategy (2016) guiding the development of hospital infrastructure
  - The Capital Investment Plan (2017).
- Revisions to the internal audit manual, procurement procedure manual following the passage of the Amended Public Procurement Act 2016 (Act 914) and accounting, treasury and financial management manuals. The TA Fund also supported training on these manuals and dissemination of the New Public Financial Management Act, Act 92

Advancing quality of care
- the development of the (i) Maternal and Child Health Standard Operating Procedure, the (ii) Standard Treatment Guidelines and (iii) the revision of the Essential Medicines List – all of which have a demonstrable impact on programming. These are all widely disseminated and in use.
- Innovative partnership with Korle Bu Hospital to develop and institutionalise a quality improvement and patient safety programme (develop metrics, regular assessment and monitor). Partnerships have been formed with the UK’s Queen Mary’s Community Hospital, Care Quality Commission and the Imperial College Healthcare NHS Trust
- Development and passage of legal instruments to regulate professionals, reduce the incidence of sub-standard medicines, train specialists and improve the quality of care
- Agency performance contracts: designed and institutionalised performance-based system where all agencies are assessed annually as part of the public sector reform to improve accountability.

The TA Fund also supported MoH’s stewardship function, and build processes for sector coordination policy dialogue, strategic direction. DFID supported three annual Health Summits, monthly Health Sector Technical Working Group Meetings, Interagency Leadership Committee and biannual Business Meetings. Annual holistic assessment and joint monitoring visits to regions enabled MOH and development partners to understand performance at lower levels of the health system. The TA Fund was intended to provide support to agencies beyond the MoH, but except for a few activities such as the Korle Bu quality project, over 95% of the activities supported the ministry’s activities.

The TA funds were managed by the Policy Planning, Monitoring and Evaluation Unit (PPME) of the MOH, who contracted consultants directly or through DFID’s framework agreement (Oxford Policy Management). A UK Department of Health official was seconded to the MOH for 2 years ending in April 2016, managed by the National School of Government International. The objectives of the adviser changed from providing strategic governance advice to MOH to a range of more technical inputs to policies. In years 3 and 4, a part-time national adviser was seconded to MoH, who worked closely with DFID. The TA played a dual role of advice to MoH and reporting to DFID – this model could have been more effective if the technical advice and project and financial management functions had been split.

Indicator 3.3: The target for the MoH and GHS to adopt one new model each year to strengthen the annual plan was not achieved in the 2018 review, however was completed outside of the review period.
- In 2018, a workforce planning model was completed in partnership with WHO, using the workload indicators of staffing need (WISN) tool. It was used to compare allocations across regions, provided the basis for a national human resource forum and is now influencing staffing decisions. GHS estimates savings of 27% through redistribution could be channelled back into budget. It was however completed outside of the programme period.
- In 2017, MoH PPME completed a cost-effectiveness analysis of the NHI package, guiding the development of the five-year Health Sector Medium Term Development Plan (2018-2022). This wasn’t used by NHIS during the HSSP period but has been included in the UHC Roadmap work.
- The MOH has also made use of DFID TA support and partnerships such as through the centrally managed programme International Decision Support Initiative (IDSI) to use new models in planning, including Health Technology Assessment (HTA). The approach for hypertension has informed Ghana’s National Medicine Policy (2016-2020) and will be rolled out for other conditions.
- The Burden of Disease study (BoD) was finalised in 2016, comprising estimates of diseases causing Years of Life Lost, Years Lived with Disability and Disability Adjusted Life Years (DALYs) as well as risk factors contributing to the DALYs. (see 3.2)
Indicator 3.4: This project was concluded in 2017. All NHIA’s 10 regional and 165 district offices now use the automated financial accounting system. DFID funding for this financial system (£1.83 million) was used to procure computers and software; and build capacity of staff to use the system. The software is a centralised web-based system that generates real time financial reports, eases analysis, tracks expenditure, monitors fixed assets and facilitates decision making. The NHIA plans to link this with the claims processing software to create a unified system that tracks all inflows and outflows. Anecdotal feedback on the software from the beneficiaries has been positive but NHIA have not done any comprehensive assessment of usage making it difficult to assess if this was VfM.

Lessons identified this year linked to this output and recommendations for future programmes: Achievements and lessons are in the 2018 report ‘Review of TA Fund Achievements and Lessons Learnt’.

Models to deliver and measure effective TA. HSSP has learnt that TA is most effective when demand driven, responsive, agile, builds and not substitutes capacity or is highly specialised[13]. Importantly, it should scale up and scale down in response to the political economy. A number of policies were developed, and the TA Fund was valued by GoG, but the programme did not include clear indicators to measure the effectiveness of the TA Fund and contribution of DFID to building capacity in the sector. Logframe indicator wording such as ‘strategic’ and ‘new models’ were subjective. PBA is defining indicators for TA contribution, as well considering options for embedded TA with GoG, combining government and external national and international experts, de-linked from financial management of the TA Fund, that can scale up/down as needed.
[13] See also: DFID How To Note on How to Build Capacity.

Focus on implementation as well as design of reforms: In later years (possibly as the new government looked to determine new priorities) the TA Fund lacked coherence and strategic direction, with a number of policies developed in isolation of implementing agency or not finalised, limiting its effectiveness and VfM. At times this funded routine activities, although these have become engrained in how the MoH does business. A few areas have clearly been catalytic for the sector. The key question going forward will be implementation and rollout out of reform. Future programmes - notably PBA should focus on fewer priorities but follow these through from policy to implementation, while also balancing the need for some ‘quick wins.

Output Title	Improved mental health care delivery
Output number per LF		4	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Data is a challenge on mental health and baseline data was weak. This section draws on a 2018 assessment ‘Measuring Results in Mental Health, Kailash Balendran, Oxford Policy Management’ – but figures on treatment should be read with caution and instead, general trends observed.

Indicator(s)	Milestone Dec 2018	Progress
4.1 Number of district physicians, medical assistants and community health service providers trained in mental health service and delivering mental health services (annual)	2019:1400 (carried forward from 2018)	Overall: Achieved / 2019: Achieved. 1,889 (incl. QR) / 2018: Not achieved: 335 / 2017: Achieved 1842 / 2016: Achieved 1827 / 2015: Not achieved 1053 / 2014: Not achieved 646
4.2 Number of persons treated in mental health outpatient and community settings (annual)	Total: 75,000 / Female: 40,000	Overall: Achieved / 2019 (2018 data): 110,216 (including 35,466 at CHAG) / 2018: Achieved 80,955 (f: 40,778) / 2017: Not achieved 69,378 (f 38,673) / 2016: Achieved 65,438 / 2015: Achieved 55,250 (f: 30,120) / 2014: Not achieved 32,400 (f: 9720)
4.3 Number of district health facilities providing outpatient mental health care	By 2019: 216	2019: 257 districts 5,723 facilities / Achieved 216
4.4 % of mental unwell persons overall health care provision improves (people on treatment/enrolment onto NHIS)	Baseline 5%, target by end of project 80%	2019 (2018 data) Achieved: 82.3% / 2018: Not achieved 73% / 2017: Achieved 55.6% / 2016: Achieved 10% / 2015: Achieved 8%

Indicator 4.1 In 2018, 1679 community mental health workers (nurses and health officers, CMHN/CMHO/CPN) were trained by the MHA including 1334 in promoting MH, and 345 non-specialists in WHO Mental Health Gap Action Programme (mhGAP - mental, neurological and substance use disorders for non-specialist health settings). The extension to BNGh included funding for WHO’s Quality Rights training model and evaluated effective approach to build capacity and change attitudes and practices, promote recovery and respect for human rights for people with mental health conditions, psychosocial and intellectual disabilities. 2106 people were trained through Quality Rights face to face and e-training, with HSSP funding 10% of the programme.

This indicator measures training by all three of the MH implementation partners (MHA, BNGh, CHAG), but does not measure if the health professionals used their training. However, the 2018 results study found that the training has created the necessary capacity to provide MH services. This was articulated in relation to identifying MH conditions and accurately diagnosing those conditions. 'I am able to diagnose better. For example, I can now diagnose the psychosomatic symptoms of depression (pins and needles, burning sensations) – previously (as a physician’s assistant) I would have diagnosed as a more physical condition, I would be wasting time doing labs to test for diabetes.' CP_1, male, CPO, Northern Region

WHO’s Quality Rights has been valued by some health staff as an ‘eye opener’ One interviewer share how training had changed his practice ‘I didn’t realise that people with mental health conditions have freedom of speech, now I listen to patients and don’t let their relatives speak for them, I have realised that carers sometimes hide things and it’s important to speak to the patient’ District MH coordinator Upper East.

HSSP partners have increased the number of health workers trained and providing services in the formal sector and at community level. In Ghana numbers have grown rapidly.
- CHAG: 280 physicians trained in MHGAP; 26 health workers sponsored for two-year specialisation training for Community Psychiatric Officer positions; 52 health workers sponsored for one-year specialisation training for CMHO positions; 2 psychiatrists and one clinical psychologist
- MHA trained more than 2000 newly posted psychiatric nurses across the country.
- BNGh: 3667 community health workers trained in essential medical skills, 605 traditional healers, 524 teachers trained on common mental health disorders and support and referral

Indicator 4.2: This indicator is measured by compiling the total number of MH “registrants” in all out-patient units of psychiatric hospitals, regional hospitals, GHS CMHUs and CHAG facilities. It also includes outreach services by GoG psychiatrists to underserved areas, supported by Basic Needs (making up around 15-20,000 of the numbers each year). Good progress continues to be made to expand community mental and outpatient services. In 2018, nearly 80,000 more people (360% increase) were treated on OPD basis and community settings than in 2014. This includes 35,466 at CHAG facilities, who did not receive any DFID funding this year – demonstrating sustainability of the integrated approach.

This is likely due to investments in staff training, expansion of community-based services and public education. The use of behaviour change communication tools and social media has also increased public awareness about mental health. The 2018 MH review study found that the increase in availability of services has supported patient access by reducing the ‘difficulties’ (time, travel and associated costs) with having to access MH services outside of their own districts – i.e. in the urban centres. This is relevant to clients with mental or neurological conditions that require frequent follow-up visits.

Indicator 4.3: All 216 districts[14] in Ghana provide mental health services. Psychotropic medicines have been included in MoH’s essential medicines list meaning they are now provided free of charge at the point of delivery (in 2018 government approved GHC3million for the procurement of psychotropic drugs). However, stock outs continue to be a problem, poor supply systems and lack of financing continue to prevent access to drugs. This is turn continues to be a barrier to the provider of quality services and could continue to act as a deterrent from seeking care.
[14] In 2017, Ghana increased the number districts by 38, bring the total to 254. However, because the project data was based on 216 districts this has been maintained in the logframe.

Indicator 4.4: On mental health, the indicator refers to the % of individuals with mental ill-health who had an NHIA card at the time of visiting a health facility for MH services. 82 % of mental health patients registered on the NHIA, exceeding the target and previous year’s milestone by 30% and demonstrates government’s commitment to the financial risk protection of mental health patients (although falls short of guaranteeing access to treatment given stock outs of drugs).

The logframe indicators do not capture some of the major achievements in mental health, captured in the 2018 ‘Results’ study. Key highlights include:

Policy and System Strengthening:
- MHA has established itself as a fully functional agency leading the delivery of MH services.
- In 2017, MHA completed a 10-year Mental Health Policy and drafted a Strategic Plan. The policy aims to integrate and expand access to quality services focusing on community level services and support; and ensure sustainable financing and financial risk protection for people with MH conditions. The policy is yet to be approved by Cabinet but provides an important document to focus efforts and future support.
- Guidelines and protocols developed including Hospital Peer Review Guidelines, for Traditional and Faith Based Healers, Regional and District Mental Health Coordinators, and Visiting Committees when formed. Guidelines on Integration of Mental Health into general health and a communication strategy for Stigma Reduction.
- Regional MH coordinators appointed to all 10 regions
- Successful integration of MH indicators in the national DHMIS system. This will make data more available for planning and service delivery.

Scale up Access to Services: In 2018 all public hospitals offered mental health services compared to 2% in 2014.
- Integration of MH services within the CHAG network of facilities - 95% of which now offer MH services). 106 CPUs/MHUs refurbished, 7 districts supported with psychosocial recreation centres
- BNGh has supported GHS in the decentralisation of MH services establishing 159 CMHUs to provide community outpatient services and providing community psychiatric outreach services. These are included in regional outreach plans but may be the first to be cut if budgets are tight.
- GHS piloted an approach to integrating MH into CHPS.
- Diagnostic and therapeutic equipment for the three psychiatric hospitals to improve the quality of care; and the rehabilitation of a ward in each of the hospitals.
141 districts with a self-help group, reaching approximately 32,827 beneficiaries (clients + families); 14,601 people with MNS conditions supported to engage in livelihoods activities and 17,349 primary carers, with livelihood

Stigma and discrimination, empowerment and self-representation
- CHAG and Basic Needs have taken part in over 400 radio and TV shows, >60 newspaper articles, sent bulk SMSs, and held community durbars on reducing the stigma around.
- MHA, as part of mental health promotional activities organised community durbars at regional, district, sub-district and community levels.
- BNGh and its sub-grantees – MEHSOG, CPRI, CEDEP, GKS, MIHOSO, also contributed to building a ‘movement’ on Mental Health, convening Annual General Meetings of the Mental Health Society of Ghana, establishing an NGO coalition with 12 partners (Mental Health Alliance), and increasing representation in forums such as Launch of Quality Rights, Annual Performance Reviews, in line with the commitment to inclusion - ‘Nothing about us without us’.
These have contributed (in part) to creating demand for and use of MH services, as demonstrated by 2018 case studies. While a limited sample, interviews with patients, families and health workers identified positive changes in relation to stigma and discrimination including access to services and service quality.

Lessons identified this year linked to this output and recommendations for future programmes
Significant learning through the programme, combined with new evidence available globally, will inform both the work of HSSP partners and the future Leave no One Behind programme.

Learnings on methodology and theory of change: Despite the successes above over six years at national scale, the treatment gap is still high, an estimated 280,000 people suffer from severe MH conditions and more than two million from mild/moderate[15]. Stigma and discrimination towards people with MH conditions continues, and lack of access to medicines or psychosocial therapies and financing also remain as barriers. HSSP provides lessons on four areas – policy/systems; scale up of services – medical, psychosocial; community-based rehabilitation/recovery; and data – have informed the design of LNOB.
[15] The planned 2019 AIMS Study will provide clearer data on prevalence.

Extreme vulnerability and deep-rooted stigma mean approaches to behaviour and norm changing need to be tailored to the intended population. Both WHO’s Quality Rights and the FCO/DHSC ‘Time to Change’ campaign have very promising, evidence-based methodologies on stigma reduction, with evaluations due out soon. Quality Rights has been well received and should underpin any future work to improve quality of care, address human rights and minimise safeguarding risks. LNOB should build on the work of BNGh and partners at community level – formalising SHGs and peer support, working with traditional and religious leaders, and build networks and alliance of CSOs.

LNOB needs to carefully consider government change in a constrained fiscal climate and competing priorities. There is a risk that approaches won’t be effective or sustainable if government doesn’t step up as many of the systems blocks remain (medicines, governance, financing) and a new approach is needed to move out of status quo. LNOB will consider a focus on HSS, supported by specialist level TA and advocacy to tackle underlying obstacles. Financial aid should be results based - quality improvements in hospitals and access to medicines.

In determining approaches to scale up services, in partnership with GoG, LNOB should take a more comprehensive perspective with a focus on rights based and recovery-oriented approaches, community health services and psychosocial therapy. A focus on early interventions and prevention while not neglecting services for those with severe MH disorders (e.g. consider the role of psychiatric outreach services, balancing cost/sustainability with access in disserved areas. Any approaches (outreach, integration into PHC, peer support) should have operations research built in and can adapt if these aren’t working.

Is there a risk of setting up a parallel system? The separation of MH from GHS to MHA in 2012 has certainly raised profile and the increased numbers of MH workers is welcome given shortages in social welfare officers, but there are risks of it becoming a parallel system leading to inequities, missed opportunities to integrate care and lack of oversight/inspection functions. In line with Ghana’s MH policy, GHS and HSSP partner efforts in this area, a continued focus on integration will be key. One option to build national ownership and quality of care will be to work with hospitals as centres of excellence to train/support rest of the health system while maintaining programmatic focus on de-institutionalising and community care.

Data & evidence: No data to ascertain prevalence of mental health illnesses – and hard to judge the impact of DFID funded work. Much greater emphasis needed on M&E in order to better assess the programme’s success. A strong M&E and operational research element needs to be built in to the LNOB programme to establish a baseline (AIMS study planned[16]) and allow measurement of success. Following from this, outputs need to be achievable (unlike 4.2 and 4.3 in the current programme which are not directly accountable to the programme) but not too low level (unlike 4.1 which measures an activity rather than an output).
[16] The World Health Organization Assessment Instrument for Mental Health Systems (WHO-AIMS) is a new WHO tool for collecting essential information on the mental health system of a country or region

Learning on partners and delivery routes: LNOB programme will need to consider appropriate partners while ensuring GoG remains in driving seat to ensure comprehensive, effective and sustainable approaches. There are very few partners working in mental health given it is a specialist area touching on wide range of technical and development issues (health, rights and empowerment, livelihoods). A combination or consortium of national and international partners with technical expertise across a range of areas is therefore recommended (e.g. WHO + fund manager + govt + private sector + NGO movement, research experts). DFID also has a role to play in building core capacity of local partners to deliver development programmes (reporting, financial and risk management, safeguarding) as well as globally to boost the number of NGOs and suppliers that bring together medical and rights-based perspectives to deliver a holistic and sustainable MH service.

Output Title	Improved safety of medicines
Output number per LF		5	Output Score	A
Impact weighting (%):		5%	Impact weighting % revised since last AR?	N
Risk:		Moderate	Risk revised since last AR?	N

Indicator(s)	Target 2018	Progress
5.1 Number of drug quality tests completed	By 2018, 2700 p.a	2018: Achieved 2665 / 2017: Not achieved 2220 / 2016: Achieved 1235 / 2015: Not achieved 353
5.2 Number of reports submitted by health staff on drug adverse effects	By 2018, 1200 p.a	2018: Achieved 2496 / 2017: Achieved 1122 / 2016: Achieved 697 / 2015: Achieved 436 / 2014: Achieved 365
5.3 Number of local manufacturers with quality management standards in place	By 2018, 6	2018: Achieved 6 / 2017: Achieved 5 / 2016: Not achieved 0 / 2015: Not achieved 0 / 2015: Not achieved 0
5.4 % of drugs tested by the FDA that are substandard	By 2018, <2.5%	2018: Achieved 2.1% / 2017: Achieved 2.5% / 2016: Achieved 3 / 2015: Achieved 3.5%

This output ended in 2017 and was measured last year. FDA received less funding than planned given that in November 2016, DFID did not transfer the final tranche of £1million to the FDA due to non-compliance with some provisions in the MoU. In 2017, however, FDA embarked on institutional reform, including the appointment of a new Chief Executive Officer and a Coordinator for the DFID programme, and DFID approved the disbursement of £200,000 from the TA Fund to FDA.

Indicator 5.1: The number of drug quality tests grew each year and in 2018 fell just below the target but exceeded the previous year’s performance by 20%. The tests were done using the four Truscan RM analysers, procured by DFID. FDA trained twenty staff from the regions and the headquarters on the Analyser to improve the quality of testing. Because of its international managerial and technical competence, FDA has been accredited to conduct 40 tests - the highest in Africa. Fewer tests were done in four regions (Upper East, Upper West, Central and Western Regions) because of the small market size.

Indicator 5.2: FDA’s continued investments in consumer education and provider training on pharmacoviligence (PV)[17] has paid off. The adverse reports increased to 2,496, doubling the target of 1,200.
[17] The detection, assessment and prevention of adverse effects with pharmaceutical products –

Indicator 5.3: By 2018, one more local manufacturing company achieved the FDA’s minimum acceptable manufacturing standard[18], bringing the total to six. Building the capacity of local companies is part of efforts to increase access to quality, affordable medicines in Ghana.
[18] According to the FDA the minimum acceptable score is 5 out of 10 or Class C.

Indicator 5.4: Continued investment in staff training, chemicals and drug testing equipment has reduced the proportion of substandard medicines to 2.1%, falling far below the 16% reported at baseline in 2011.

Lessons learnt and recommendations:
1. FDA was a more mature agency, which generates its own income which means a partnership of a different level. FDA continues to maintain strong links with UK institutions. It continued its partnership with the UK Medicines and Healthcare Products Regulatory Agency (MHRA) to train FDA staff on the development of Risk Management Plans and Good Pharmacovigilance Practice and QPPVs[19] of 39 manufacturing companies in the safety monitoring of medicines.
[19] Qualified Person Responsible For Pharmacovigilance (QPPV) is an individual, usually an employee of a pharmaceutical company, who is personally responsible for the safety of the human pharmaceutical products.

2. Strong leadership is a critical success factor towards achieving programme deliverables. Following the change in leadership FDA has produced quality plans, strengthened monitoring, improved financial management and demonstrated positive results.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Impact Indicators	Baseline (2011)	2013	2014	2015	2016	2017	Target 2018	Actual 2018 / (latest survey)
Under Five mortality and neonatal mortality (Total; female; poorest quintile)	Total: 82 / Female: 75 / Poorest quintile: 106	-	U5: 60 / Poorest 92 / F 62 / NMR: 29 Poorest 32 / F 27)	No survey data	No survey data	No survey	U5M: 57, f 50 / Poorest quintile 79 / NMR: 19	U5 52 / NMR 25
Outpatient attendance per capita (National; Northern region)	National: 1.05 NR: 0.74	National: 1.15 NR: 0.78	National: 1.15 NR: 0.31	National: 1.08 NR: 0.72	National: 1.06 NR: 0.67	National 0.98 / NR: 0.62	National: 1.27 / NR: 1	National: 1.05 / NR 0.62
Health expenditure per capita $ (public)	35	32.8	-	37.6	24.8	33	45	30
Outcome Indicators
1.Percentage of births delivered by a skilled professional (total: poorest quintile) Proxy for utilisation	Routine: 56% Survey: 68.4% Poorest quintile: 38.6%	R: 57% (2014 HA) S: 74% Poorest quintile: 47%	R:57.4% / BA: 63% ER: 53.5% CR: 60% WR: 58%	R: 55.1% / BA: 60.8% ER: 51% CR: 55.7% WR: 54.2% (All R)	R: 55.5% / BA: 61.7% ER: 50.4% CR: 61.3% WR: 53.8 %	R BA:61.5%; ER,49%; CR, 61.7; WR,53.2%	R: 63% / BA: 62% / ER: 60% / CR: 65% / WR: 60%	S: 79% R: 58% / BA: 63.6% ER 51.5%; CR 58.6%; WR 62%
2.Proportion of facilities achieving accreditation scores A+, A or B: (proxy for quality of care)	22%	26%	34%	56%	67%	60.3%	70%	N/A
3.Nurse population ratio and ratio between best and worst performing (proxy for equity)	Nurse to patient: 1:1,750 / No equity ratio in 2011, 2014 data: 1.8	B: 1: 669 W: 1: 1,255 Ratio: 1.88		Ratio, 1:739 Equity B:1: 449 W: 1: 946 Ratio: 2.11	Ratio: 1:834 Equity: B, 1:500 W, 1:1033 Equity ratio: 2.1	Ratio: 1:799 / Equity ratio 2.1	Ratio: <1.8	1:839 / Equity B 1:495 W 1:1015 ratio: 2:06
4. % of mentally unwell patients overall health care provision improves	5% (2015)			7.9%	10.1%	55.6%	73.3%	80%

Impact and outcome indicators are largely not met. (one out of three impact indicators achieved, and one out of four outcome indicators achieved). Data at impact level (mortality rates) is provided in the 2014 DHS and the 2017 Maternal Health Survey, there is no updated survey for 2018 and the next DHS has been delayed to 2019.

Impact indicators
- Under five mortality from 82 in 2011 (baseline) fell to 52 in 2017 meeting the HSSP target.
- There has been a much slower reduction in neonatal mortality from 56/1000 to 25/1000 in the 2017 survey. 2018 target unlikely to have been met. Institutional Neonatal mortality rate is increasing (and has almost doubled since 2014)
- The fall in under five mortality is likely to have been driven by high and equitable immunisation coverage (above 95% for Penta3) and focused action on malaria. New-born mortality changes are harder to achieve requiring greater health sector investments – Ghana’s NMR is higher than countries of similar income levels.
- The latest MICS survey for Ghana shows that inequities have grown - the under-five mortality rate is twice as high for the poorest children as the richest.
- Outpatient attendance was, in 2018, the same as 2011 levels. It is possible that utilisation remains low as private facilities are not reporting onto DHIMS, but more likely to reflect continued barriers to accessing healthcare – geographic and financial. Inequities in OPD attendance have also grown
- The health budget has declined, at $30 per capita this is the same in 2018 as the 2011 baseline and significantly less if the effect of inflation is considered. Health expenditure per capita did increased after 2011 to $43 in 2017 then fell again and did not meet the project target of $45. Expenditure on health in 2018 as a share of the budget was 6.5%, compared to 10.6% in 2014.

At outcome level, the percentage of births delivered by a skilled professional (a proxy for access) as measured by the routine data system has not significantly changed since 2011 despite an increase in the number of midwives from 4,185 in 2013 to 9,557 in 2017. This may be due to under-reporting by private health facilities and maternity homes as survey data shows an increase from 68% in 2011 to 79% in 2017. This year saw an increase in the ratio of doctors, nurses and midwives to the population. There are continued issues around the equitable distribution with the equity ratio for geography at 2:1 since 2015. The proportion of facilities achieving accreditation scores A+, A or B: (proxy for quality of care) has steadily increased. However, without commensurate increases in OPD or changes to health outcomes it is hard to establish whether this is a true measure of quality of care.

Summarise the programme’s theory of change and major changes to it in the past year (1/2 page)

HSSP’s ToC was designed to address underlying weaknesses in the health system. The ToC stated that in order to achieve sustained health delivery and health outcomes, the health system would need to be strengthened and this would require improvements in: financing and financial management; strengthened leadership, management and capacity for human resources, policy, procurement and data; and inputs to address specific service delivery gaps particularly around quality and equity of health care provision. Inputs would be financial, material, technical assistance and policy dialogue.

Inputs
Impact
Outcome
Outputs

Financial
Material
Technical
Sustained health delivery and health outcomes
Improved health system delivers for the poor
Improved equity and quality

Increased funding strengthened
Financial management
policy, planning & budgeting
Management & capacity

The Theory of Change was revised in 2015 to reflect the addition of support for CHPS, and to closely link the HSSP to the ‘twin track’ approach to UHC – scale up CHPS and reform of the NHIS. This closely linked the new inputs – results-based aid, earmarked FA for CHPS and TA – to these two areas. It envisaged that ‘the early stages of the HFS-IP would drive reform of the NHIS by bringing preventive services into the package of services covered by insurance which previously included only curative care. NHIS in turn is critical to delivering a self-sustaining health system in Ghana that better meets the needs of the poor. CHPS is widely recognised as a key instrument for delivering PHC to a wider group of the population especially poorest.’ This relied on a series of stages and assumptions, underpinned by a continued role of Office of the Presidency, that the MoH would implement certain reforms (in their entirety, not piecemeal) related to PHC and NHIS reforms and take on the costs once proven through HSSP to be effective. It also envisaged a role for STAR Ghana boost community demand and public engagement on health

The ToC remains relevant. However, achievement of the outputs did not lead to achievement of the outcomes and impact. This is largely due to the outcome/impact indicators being outside of HSSP’s ability to deliver on directly (contribution not attribution at this level), given they relate to the political and financial climate. A number of the assumptions did not hold true and many of the system blocks were outside of DFID’s control. HSSP could have perhaps more impact if there had been larger scale social accountability initiatives to promote demand for quality health services – combined with greater responsiveness from GoG to these. STAR Ghana did work on this in the early years but not at scale and consistently.

It is also partly due to the logframe design. A clearer link showing how outputs would lead to outcomes (or induced outputs – changes in policy or capacity built) would have allowed DFID to better measure its contribution to outcomes and impacts. For example, it is difficult to demonstrate the contribution of Output 2 (CHPS) to the overall performance of the health sector as measured by come indicators on human resources and quality of care. It could contribute to Skilled Birth Attendance, given it contributed to the provision of delivery care at CHPS facilities, referral for delivery care at higher level facilities, and community planning for emergency transport, but it will take time to see the effects of this, health worker numbers which was not something HSSP contributed to beyond work on staffing norms. At impact level, Output 2 may have contributed to two of the three indicators (U5 mortality and outpatient attendance (OPD). Available data suggests that CHPS contribution to total OPD is increasing but total OPD is not increasing. Child mortality has reduced but it is too early to say this is CHPS – likely to be a combination of malaria and EPI which CHPS have provided a platform for.

 As noted in the previous annual reviews, the underlying weaknesses in the health system stems from issues around financing and governance, with indicators not reflecting a country of Ghana’s level of economic development. Underlying causes include:
- Salaries not services: In 2019, 98% of the GoG budgetary allocation for health was on salaries leaving very little for goods and services.
- Limited efficiency/equity in workforce planning: Increased recruitment of staff but unevenly distributed with shortages in specialist skills, affecting the quality of services provided.
- Duplication of roles: Distinction between the roles of MoH and its agencies has become blurred with MoH implementing directly and agencies also regulating
- Poor M&E: There is limited capacity in key competencies such as monitoring, regulation and inspection which impacts directly on quality; and poor use of data.
- Lack of financing: Health financing has steadily reduced as a share of the budget with health expenditure dropping from 11% in 2011 to 8% in 2019. Compounded by weaknesses in NHIS funding where increased membership was not accompanied by a widened payment net creating persistent annual deficits and a decline in NHIS membership. Declining donor funds have not been replaced by GoG.
- Weak PFM: weaknesses in budgeting, expenditure control, accounting, reporting and audit. Financial management information system in place (GIFMIS) but not fully utilised, particularly at sub-national level. Exacerbated by unreliable disbursements by the Ministry of Finance (MoF).[20] Delayed and irregular payments lead to poor/non-implementation of services; and increased cost.
  [20] Capital and goods and services budget execution in health has, for the past 3 years, been approximately 50% of the allocation.

That HSSP was unable to shift these barriers does not signal ineffectiveness as clear improvement were made in services reaching those most in need (through CHPS and mental health work). It does however point to the need for realism in what a donor programme can achieve, and with other fiscal pressures mounting (particularly from 2015), the lack of prioritisation Government gave to financing health. This is particularly clear in the case CHPS where sustained financing for it is not yet clear.

PBA has taken on these lessons and so will be:

1. Flexible and able to scale up/down depending on MoH demand for technical assistance
2. Include working with Ministry of Finance and social sector Ministries to strengthen the link between them.
3. Include a social accountability element to support more consistent political commitment to health services; as well as ensure the services being delivered meet needs.
4. Closely monitored through a series of logframes with support from a TA team.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme (1 page)

The VfM (Value for Money) proposition in the business case estimated the investments in the programme to generate direct benefits to the population of Ghana that outweigh costs by a net present value of an estimated £70.7 million. The Benefit-Cost Ratio is estimated as 2.28. For this PCR, a VfM study of CHPS provides value judgment of the CHPS component (21% of the budget) in terms of overall VfM performance (BCR achieved). Qualitative VfM – economy, efficiency and effectiveness - is provided for CHPS and other programme components.

Overall, the programme’s performance on VfM has been varied. In some areas, it has represented good VfM, improving financial management, efficiency and accountability in the health sector and positively impacting on service delivery and coverage. The support to CHPS, family planning and mental health has been particularly productive given how complex making progress in these areas can be - addressing stigma, changing behaviour and addressing equity. Support to FDA and NHIS has also represented high VfM. The TA Fund has struggled to represent VfM throughout the period, culminating in its early closure, but there are potential savings, which is implemented could yield long term VfM.

Economy: There were low management costs across the different components by delivering through government and national NGOs, as compared to the management costs of a supplier. The programme engaged an international and then a national technical advisor to provide strategic support to the three agencies – MHA, NHIA and FDA – and to the MOH. This support strengthened the capacity of the partners to deliver on the objectives of the programme. DFID also contracted a financial management consultant which has led to improved financial management at a low input cost. (This does not compare effectiveness/sustainability of both approaches, so despite being low cost, is not necessarily VfM).

CHPS accounted for 21% of the programme spend (taking services, equipment and training together), with the main driver being the equipment. The procurement process for the equipment was undertaken through DFID procurement agent, AECOM. This pre-tendered framework provided for speedy and direct access to a capable supply base, and to benchmarked competitive management fees and commodity prices from manufactures. As a result, the procurement timelines were met within the budget limits, representing good VfM. Activities were delivered according to agreed workplans and implementation guidelines, although there were instances where expenditures fell outside agreed plans (see Section F)[21].
[21] PWC Audit Report, May 2019.

Efficiency The results achieved in output 2, 4 & 5 imply that the mix of inputs to the programme was efficient enough to yield the desired outputs. There are also key efficiency results to note across all outputs, and HSSP had milestones that rewarded efficiency:
- Greater allocative efficiency achieved by re-focusing programme spend on CHPS from SBS
- Increased financial management capacity has improved financial management and this has improved accountability and effectiveness, not just for donor resources but also overall. However, a few issues remain, e.g. misuse, ineligible expenditure, and poor accountability, as reported in the financial audit conducted at the end of the programme.
- The staffing norms study showed that improved human resources planning and management, specifically redistribution, could yield a net 27% savings.
- The implant training to CHO and nurses has made long term contraception more accessible and represents strong VfM. It has contributed to the increase in the family planning acceptor rate across all 4 regions and freed up doctor’s time to deliver more high-skilled services.
- the introduction of the framework agreement between the MoH and the pharmaceutical companies reduced the price of medicines on the NHIS by 30%
- If implemented, the review of the NHIS to focus on cost effective PHC interventions and revised provider payment mechanisms will yield substantial benefits that can be re-invested in the system.
- Interventions in mental health have resulted into over 100,000 persons receiving treatment in outpatient and community settings. In the short term this may increase costs for the sector, as more people come forward for treatment, but ultimately community-based services will provide a more cost-effective service. There is evidence is that treating MH on OPD basis, focusing on interventions that are scalable such as peer support and psychosocial are cost-effective.
Effectiveness The achievement of outcomes as a result of DFID’s investment cannot be fully realised in the short term (for example CHPS - 3 years of implementation). However, the results of some outputs increase the likelihood that such outcomes could be achieved in the future – for CHPS this includes improved access to skilled deliveries, increased OPD use at primary level, increased ANC visits (averaging 74.1%), increased numbers of new contraceptive acceptors, and availability of long-lasting insecticide treated mosquito nets. These have potential future impact:
- Reduced maternal mortality from ANC screening and skilled deliveries.
- Reduced costs of referrals to higher levels of care as a result of increased OPD care at lower levels.
- Increased likelihood of achieving the 1st and 2nd demographic dividend for Ghana resulting from increased contraceptive prevalence rate.
- Reduced malaria-related mortality for children under 5 and pregnant women.
- Crowding in additional funding for mental health – greater allocative efficiency from GoG

Findings of CHPS VfM study: DFID’s total investment of £12.6m in CHPS targeted 28% of the population of Ghana, and accounts for a conservative 7% of the Total Health Expenditure (THE)[22] in the four regions. Using available evidence, conservative immediate direct benefits[23] attributed to DFID were estimated to be approximately £16m. This results in a conservative BCR of 1.25 and provides evidence that every £1 spent on CHPS unlocked an additional £0.25 benefit (at the very least) thus making funding for CHPS a worthwhile investment. The BCR would be otherwise higher than what is estimated, had additional evidence on increased skilled health personnel delivery and increased ANC visits been included. However, these were excluded because of data limitations. Other benefits not included in the 1.25 BC ratio include:
[22] THE for the regions is estimated using $30.41 per capita referenced in the Holistic Assessment, 2017
[23] Direct benefits were estimated from LLINs distributed, CYPs from family planning, U5 mortality averted from OPD management of diarrhea and impact of increased ANC visits.
- Capacity built amongst health personnel to deliver CHPS.
- Spill-over effects of improved financial management systems, mainly at regional level.
- Developed and improved functionality of CHPS zones in the four regions.
- Enhanced support, supervision and oversight mechanisms which have spill-over effects to other programmes outside of CHPS.

The second area of significant results is in mental health. Quantitative VfM evaluation of MH is a challenge due to the lack of cost-effectiveness data on MH in LMICs (a handful of studies exist). Assuming an additional % of GoG staff time dedicated to mental health and crowding in GoG funding (the 2018 budget included funds for psychotropic medicines) provides an estimated benefit of £30.5m following an investment of £10 million, but this is a rough estimate and not fully quantified due to data limitations.

Equity: HSSP has achieved excellent results on two output areas directly related to equity: CHPS and MH.
- By design, DFID’s support to the CHPS programme targets the primary service level of delivery, meeting the needs of women and children in rural areas living more than 8km from a health facility, a situation compounded by poor roads and transport networks. This has contributed to the expansion of access and utilisation of health care for most hard to reach and under-served populations. This has improved the utilisation rates of community-based health and nutrition services by women of reproductive age, pregnant women, and children under five.
- Mental health has also been directly focused on increasing equitable access to health services – both general and specialist for the most vulnerable people in Ghana. Through support from CHAG and Basic Needs, the programme is addressing stigma and discrimination which hinders patients/recovering patients from re-integrating into society and engaging in profitable ventures.
- NHIS support has not led to greater financial protection thus equity not achieved there.
- HR staffing norms work has not yet resulted in re-distribution of health workers but has the potential to do so.

Formal extensions or amendments to the programme
- Business Case Addendum of November 2015, resulting in revised MOU with MoH
- A time (but not cost) extension to the MHA to December 2018 and a revised Accountable Grant with Basic Needs to March 2019 (time and cost extension, adding £450,000 including to roll out Quality Rights).
E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

Overall risk rating: Moderate. The overall risk for the programme was medium in the Business Case and rose to major in 2015 and 2016. The risk framework was updated in May 2017 to moderate. The new risk rating was due to the reduction in fiduciary risk due to changes to the programme design, moving away from SBS to earmarked financial aid, and safeguards and financial controls put in place, including quarterly expenditure verification of earmarked financial aid. The closure of the CHPS construction component and use of DFID’s procurement service provider, AECOM, for all procurement reduced any risk associated with procurement using Government systems. Fiduciary risk was reduced in the final year due to having just two open components – earmarked FA to CHPS with tight scrutiny through PWC verification, and Basic Needs. Given continued safeguarding risk on mental health it remained moderate.

There are four main areas of risk on this programme:

Context: macro-economic situation and fiscal pressures leading to the reduction of the government budget for health sector, particularly for goods and services. This in turn reduces the ability of the sector to deliver to meet the health needs of the population as can be seen in the non-achievement of the outcome and impact level indicators. This risk has remained major despite the mitigation strategy in place (supporting domestic resource mobilisation through other programmes and using HSSP to incentivise health financing reform allocations). Lack of political will also demonstrated in not implementing the sustainable health financing strategy. Govt not planning for the reality of the reduction in financial aid from donors and transitioning from all aid – GF and GAVI

Safeguarding risks Mental health work with vulnerable populations means there is a heightened risk of abuse, violence, harm. DFID does not directly deliver services (we do not pay salaries, medicines or fund hospital running costs) but there is an associated risk (by being the only donor to support MH in Ghana) of non-adherence to national quality and patient standards/protocols and breach of human rights, related to the lack of independent inspection/quality commission covering the MH institutions. To manage this risk DFID Ghana:
- carried out an enhanced Due Diligence on BNGh, providing training on safeguarding to their teams
- Support BNGh’s work with prayer camps and traditional healers emphasising the need to uphold human rights standards;
- supporting the development of national protocols and guidelines, peer review processes, with a view to independent inspection in future to increase adherence with human rights standards in government facilities; and
- supported the WHO-led Quality Rights Project to improve both quality of MH treatment and human rights. This also includes elements of hospital reviews and improvement plans.

Delivery risk has included the internal capacity to oversee implementation of the programme, including through a period of staff change and resource constraints. HSSP is complex and requires intense staff time both in terms of programme management and technical expertise. It includes a range of funding modalities (MoUs with NGOs; financial aid to government; direct procurement by DFID; results-based disbursements) and technical area (health financing, mental health, family planning) which require a wide range of specialists’ skills. The approach will require a rethink for any new programme given any increase in DFID staff to oversee this type of programme is unlikely.

Fiduciary Risk has been moderate. A health sector Fiduciary Risk Assessment (FRA) was completed in March 2014, April 2017 (delayed from late 2016 due to the election) and the Annual Statement of Progress (ASP) in 2015 and 2018. In 2018, of the eight Good Practice Principles, five were assessed as posing ‘moderate’ risk and three as ‘substantial’: expenditure/budget correspondence, expenditure control, procurement. The 2016 FRA considered that there is a partially credible programme of PFM reform in the health sector, with a positive trajectory, and that the overall risk level was moderate. In 2018, there is no evidence of risks reducing (other than in government procurement); and some evidence of risks increasing (in expenditure control and in external audit as a result of proposed changes). Government audit information is not up to date, which in itself adds to the risk levels.

As a result, project funding flows were assessed to be vulnerable through the delivery chain, so DFID put in place additional safeguards to monitor funds at all levels of the system using: (i) PWC to complete expenditure verifications for CHPS and, from mid-2017, on all the partners (ii) spot checks by the technical adviser for the TA fund and agencies (iii) requirement for MoH to furnish drill down audits for the three agencies that received FA (iv)improved internal control systems to manage fiduciary risks associated with grant-making to CHAG and Basic Needs (included the review of due diligence assessments for CHAG and the identification of mitigation strategies to improve financial management and internal controls of Basic Needs, as well as measures to manage partners’ disbursements and spend); and v) ultimately holding back tranches of payments or refunding ineligible for some activities.

Update on partnership principles (1/2 page)

All Financial Aid to Government which DFID provides is subject to the Partnership Principles, which set out DFID’s expectations of Governments in relation to four partnership principles.[24]
[24] Commitment to poverty reduction; Commitment to human rights and other international obligations: Strengthening financial management and accountability and reducing the risks of funds being misused through weak administration or corruption; Commitment to strengthening domestic accountability.

The latest assessment of the partnership principles in October 2018 suggests commitment to the partnership principles was fulfilled. Ghana has maintained its democratic credentials by delivering peaceful and credible elections in December 2016. The government has implemented some of the manifesto commitments related to human development such as the Free SHS. It has stabilised the macro-economic situation and reduced the fiscal deficit although the public debt burden remains high. It remains committed on its international obligations and human rights. However critical weaknesses remain. The government needs to demonstrate stronger commitment to leave no one behind, especially when it is taking forward its Ghana beyond Aid agenda. This will also entail increasing the share of resources allocated to the social sectors, including health. To tackle the continuing macro-fiscal stress, the government needs to strengthen revenue mobilisation while improving debt management and reducing debt accumulation. It also needs to match the rhetoric of fighting corruption with positive actions including making the Office of the Special Prosecutor functional and strengthening accountability and transparency

In the health sector, DFID has concerns about the lack of progress in some health indicators. Government per capita spending on health has declined to pre-2011 levels and coverage of NHIS has fallen, suggesting people may face high out of pocket costs. The continued commitment to CHPS, which disproportionally benefit the poor, is welcome, as is the focus on accountability and quality of care in health. There is continued government commitment to tackling mental health, including through integrated services, and openness to external scrutiny such as WHO’s assessment of hospitals.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues

The original budget of the programme was £67,109,305. The total value of the programme was revised to £59,289,305. At the end of the programme in March 2019, a total amount of £59,062,046.78 was spent representing 99.6% of the approved revised budget. Some of the funds are being used for close out activities including, expenditure and assets verification exercises and project review of Community Health Planning and Services (CHPS). ‘Table A’ below shows the costs drivers after the programme re-design.

Table A – Below showing summary of budget vrs spend from 2014 – 2019.
Components	Component Description	Actual Spend	% of Spend
203536-101	Sector Budget Support for Ghana Health Sector 2013 - 2017 (closed)	14,000,000.00	24%
203536-102	Design Budget SBS Health Sector 2012 - 2016	93,885.61	0%
203536-103	Monitoring for Health Sector Support in Ghana	421,372.72	1%
203536-104	Support to Christian Health Association of Ghana to improve mental health	3,448,089.61	6%
203536-105	Support to BasicNeeds Ghana to improve mental health delivery	4,452,737.95	8%
203536-106	Non-Budgetary Financial Aid to 3 Agencies for Health Sector Support	6,649,242.00	11%
203536-107	Procurement of Materials supplies for Health Sector Support	94.86	0%
203536-108	Non-Budget Support Financial Aid - Technical Assistance to Ministry of Health	3,618,160.95	6%
203536-109	Support to the Government of Ghana’s response to the ongoing cholera outbreak and mitigate the threat of Ebola in the region.	2,357,185.09	4%
203536-110	Community Health Planning Services (CHPs)	10,625,710.43	18%
203536-111	Community Health Planning Services - Equipment	2,002,455.19	3%
203536-113	Results Based Aid: health financing and systems (formerly PBSBS)	9,395,319.00	16%
203536-114	Community Health Planning Services - Management Costs	157,813.37	0%
203536-115	Ghana Health Service Implant Trainings	1,446,250.00	2%
203536-116	Implementation of Electronic Accounting Systems in the Ghana Health Services	393,730.00	1%
Total		59,062,046.78	100%

The main cost driver has been the support to CHPS for both service delivery (21%) of total spend including procurement of equipment. Results-based aid follows with 16%. Other drivers were 6% and 8% on Mental Health work through CHAG and Basic Needs Ghana respectively; support to MoH TA Fund 6% and three agencies (MHA, FDA and NHIA) had 11% for institutional capacity building; Ebola responsiveness was 4%; 2% on consultancy work through contract with DFID call-down consultancy to train health workers on family planning methodology; total of £977,393 on various M & E work across various components. After the first SBS disbursement of £14 million the project was redesigned, and the remaining budget was reallocated to other specific priority areas (shown above). This action helped to mitigate existing fiduciary risks within the health sector. DFID continued to track these risks through a series of FRAs and ASPs and additional safeguards were implemented, described below and in the ‘risk’ section E.

Quality and timeliness of narrative reporting and audited financial statements
Funds were allocated by DFID to seven implementing partners based on annual workplans agreed with DFID. Funds were disbursed based on receipt of satisfactory narrative and financial reports and other supporting documents, where necessary. MoH and the 4 agencies including GHS reported every six months while CHAG and BNGh reported quarterly (see HSSP report tracker for details).

The quality and timeliness of partner reports over the five-year period has progressively improved. However, some partner reports did not meet expected standards and required extensive effort and support from DFID to review and finalise, delaying fund disbursement. In some cases, these reports neither adequately captured the progress of projects nor provided information on key areas such as risks, VfM, delivery chain. In August 2016, DFID engaged a Technical Adviser to provide support to the MoH and to play a quality assurance function on all deliverables and reports. Some partners have consistently produced reports of good quality over time, duly considering feedback for improvement.

Audited financial statements for all government partners (MoH, GHS, NHIA, FDA) have delayed as a result of the challenges with national level audits conducted by the Auditor-General’s Department. The 2017 and 2018 audited financial statements remain outstanding for MoH and the three agencies. In the absence of the audited financial statements, DFID conducted a series of extensive expenditure verifications on GHS and its agencies through an independent Financial Management Consultant. PwC was contracted to conduct expenditure verifications on CHPS, to give the added assurance on the use of funds through the system, identify high risk areas and improvements for GHS. Recommendations on internal control weaknesses were discussed and tracked. Funds identified under ineligible expenditure were retrieved.

Audits of the NGO partners are up to date as independent external auditors conducted them. Internal control issues identified in the 2017 audit for Basic Needs Ghana have now been resolved through a systematic process agreed with DFID to strengthen their systems and build capacity. The final close out audit for BasicNeeds Ghana is expected in June 2019.

Quality of financial management
Financial reports were submitted along with narrative reports and have followed varying formats across partners. These and Expenditure Verifications (EV) have served the basis for key decisions around disbursements as they are more regular than the audits and provide specific, and detailed information on use of DFID funds. Key programme risks and emerging ones are discussed during reports review meetings with partners and their risks matrix/register updated accordingly. Expenditure on the programme was closely monitored.

The quality of financial management varied by partner – as detailed in Annex B below. There were challenges with partners maintaining high balances (notably CHPS and MHA) which made disbursements according to agreed schedules sometimes difficult as there was the need to avoid payment in advance of need. This was, at time, the result of delays in transferring funds from MoF to MoH to the relevant agency, delaying implementing and spending. Reports from the final expenditure verification from the CHPS programme under the MoH/GHS also noted the continued existence of some internal control weaknesses. DFID has been in discussions with MoH/GHS on the findings and expects MoH/GHS to develop an action plan to address all recommendations and these will be resolved ahead of programme archiving.

The health team had to put in place extensive measures to ensure improvements across the board. The 5 EVs conducted by PWC on CHPS was recognised by GHS was helping also to them in shaping the financial management of the CHPS programme and streamlined the processes of fund distribution and proper usage/retirement.

Asset management
During implementation of the programme, various assets were procured for and by partners in agreement with DFID. High value assets such as for CHPS equipment was procured through DFID’s procurement agent AECOM. Comprehensive asset registers were kept for all partners and checked periodically to ensure efficient use and monitor conditions of assets. DFID commissioned an extensive asset verification exercise on CHPS. To date, asset transfers have been completed for CHAG, FDA and the rest are currently been considered. The transfer of the assets in each case was done in line with SMART rules and in a way that provides the best value for money to DFID. Allowing the partners to keep their assets ensured that they could continue to use them to deliver results intended by their respective projects while safeguarding DFID investments.

Date of last narrative financial report	Community Health Programme Services (CHPS) - July 2018 / Mental Health Authority – January 2019 / BasicNeeds Ghana - 29th April 2019
Date of last audited annual statement	Community Health Programme Services (CHPS) - 30th May 2019 / Mental Health Authority-Corporate audit expected in September 2019 / Basic Needs Ghana – 8th November 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

DFID received regular reports from all HSSP partners throughout the project – these are captured in the HSSP delivery plan and report tracker. Sector wide performance was monitored in 2018, as in previous years through: annual sector-wide review and holistic assessment regional Performance Reviews, Agency Performance reviews culminating in April Health Summit. The Health Adviser, Technical Adviser and/ or Team Leader attended monthly Health Sector working group meetings.

Logframe data for government partners was reported through the District Health Management Information system (DHMIS) which is reliable, transparent and available to DPs on request. Separate logframes and results matrices were maintained by Basic Needs Ghana and the MHA. Monitoring related to open components included:

CHPS

- Comprehensive survey conducted by GHS in 2018 to verify the functionality of CHPS zones.
- Field visit and review of external consultants to CHPS in two regions (June 2019). DFID had in previous years conducted joint monitoring visits with GHS (for CHPS to Eastern and Central Regions in 2016, Western and Brong Ahafo Region in 2017, Upper East in 2018)
- DFID Programme Manager conducted spot checks of CHPS equipment in Western and Central Regions in February 2018 and a full asset verification of equipment was completed in May 2019
- DFID contracted PWC to conduct six-monthly funds flow and expenditure verifications.
- Participation in GHS Senior Managers Meeting in late 2018.

Mental Health

DFID Health Adviser and Mental Health Policy lead conducted a monitoring visit to Basic Needs and MHA projects in Accra and Upper East in January and February 2019. The Health Adviser also visited GAR projects in June 2019.
Programme Manager and Finance Manager Visit to Basic Needs in August 2018 on enhanced due diligence and capacity building on safeguarding.
- Participation in the 2018 Annual Performance Review of Mental Health (May 2019)
- Regular meetings with the MHA, Basic Needs and periodic site visits to the Psychiatric hospitals by DFID Programme team and Technical Adviser

The Health Adviser completed this PCR with the Programme Officer. The PCR of the CHPS component of the HSSP was conducted by external international health and VfM consultants and an external national health consultant, with inputs from DFID Ghana. The Annual Review was quality assured by a Senior Health Adviser and Team Leader. The draft report was shared with partners for comments.

Evidence (1/2 page)
Evidence generated by the programme in 2018 includes publications on HRH staffing norms and mental health. These include
- Stakeholders perceptions about the impact of training and sensitisation of traditional and spiritual healers of mental illness: an impact evaluation (2019, as yet unpublished)
- Indicators of Staffing Need (WISN): Selected Country Implementation Experiences, WHO, Human Resources for Health Observer Series No. 15, 2018

Three areas of significant new global evidence available this year have influence DFID’s reflections and learning as reflected in this PCR.
- The Lancet Commission on Mental Health and studies on prevention 2019 provided significant new evidence in 2018 that has informed the new programmes and provided useful reflection on the impact learnings from this programme. There is a limit of relevant literature on MH in LMICS and this will be an important future contribution. Ghana partners attended the Summit where this was launched.
- The Lancet Commission on Quality of Care suggests that Ghana’s approach to enhancing the quality of care may benefit from the report’s recommendations.
- DFID’s systematic review of evidence on HSS provides analysis with which to reflect on the programme and includes a case study on Ghana’s national CHPS programme.

Learning (1/2 page)

Each output captures the related learning over the lifetime of HSSP. Further, the summary presents strategic learning points. This section presents a record of the reviews commissioned by DFID since the last AR. The impact of the policy and health systems work funded by HSSP will not become evident for some time, perhaps years. Although lessons have been learned, a more systematic approach to capturing and sharing learning would have been useful. There is also the obvious difficulty of trying to capture in one logframe and one report such an expansive package of support to the health sector covering a wide range of issues.

June 2018: ‘Measuring Results in Mental Health’, Kailash Balendran, Oxford Policy Management, commissioned by DFID through HEART framework. Used to improve partners logframes, monitor progress and to inform the design of the new programme and wider DFID work. This was shared with partners and built on the earlier June 2016 review of Mental Health carried out by DFID, MHA and partners.
- August 2018, ‘TA Fund to MoH Achievements Challenges and Lessons Learnt’. Dr Kobina Bainson, Technical Adviser to the MoH 2016-2018, with inputs from DFID. This provided a review of all work and lessons on areas of focus and delivery mechanisms.
- January 2019, the Policy Adviser with lead responsibility for Mental Health spent two months with DFID Ghana, reviewing the current programme and assisting to design the new one. Significant peer learning took place across DFID in 2018/2019, with ‘Learning Journeys’ (a package of resources and training sessions). DFID partners participated in tailored learning events, such as a session on PRIME – a DFID research programme on the integration of mental health into PHC in five countries.
- June 2019: ‘DFID Ghana support to Community Health Planning and Services (CHPS) 2016-2018, Achievements, Challenges and Lessons Learned. Kathy Attawell and Ayaga Bawah, Oxford Policy Management. This is currently being finalised
- June 2019 DFID Ghana commissioned study on the history and changing nature of DFID support to health sector development in Ghana 1993-2018 and the role of the UK’s Department for International Development by Erasmus Agongo, Susan Clapham, Catriona Waddington

Progress on recommendations from annual reviews for this programme (1/2 page)

See Annex C

Annex A – RBA Milestones Summary

Overview of RBA triggers under HSSP

Year 1 RBA signed in late 2015: focused on PFM and health financing, including financing for primary health care, drawing from the 2015 Health Financing Strategy – IP (HFS-IP). £3.776m paid based on attainment of the following milestones.

1. Publication and dissemination of health sector Public Expenditure and Implementation Review (PEIR). Achieved.
2. 80% of enrolled population registered with a PPPN in 3 regions - a key condition for the roll out of capitation, whereby active members of the scheme select a health facility as their “Preferred Primary Healthcare Provider” – (PPP). Achieved: Volta Region enrolled 93% of NHIS members to PPP, Upper East enrolled 88% and Upper West enrolled 85%. The further roll out of capitation was ended in 2017.
3. Completion of Primary Care Strategy with defined PHC services - MoH to define a comprehensive list of diseases and conditions to be covered under the capitation scheme.  Achieved. Used in actuarial analysis
4. Revision and dissemination of procurement manual. Achieved Gavi’s recent audit has found significant improvements in procurement than in 2016

Year 2 RBA: These should have been signed in late 2016, these were not signed until late April 2017 due to the delays between the election and appointment of new Minister (October 2016 – April 2017). Focus on Health Financing, PFM, public sector procurement. £3.776m paid based on attainment of the following milestones.

1. Strengthen procurement and supply chain at all levels (measured by availability of updated procurement plan, including execution, supported by TA Fund training for at least 100 procurement officers at Headquarters, region and selected districts: Achieved
2. Improve on Public Financial Management (PFM) in line with the new PFM law. Measured by: At least 80% of 2015 audit queries resolved and 80% of Senior Manager of MOH, Agencies, RHMTs and DHMTs trained on new PFM Act. TA fund supported training of at least 100 Internal Auditors at Headquarters, region and selected districts. Dissemination of the new PFM Act 2016 (Act 921) to at least 300 senior managers from MOH and Agencies (heads, finance, procurement and internal audit officers) Achieved
3. Implementation of Health Financing Strategy: Statement of intent on NHIS Review Committee Recommendations including plans for implementation of policy reforms. Revitalization of the health financing working group. Achieved but later, no progress forward on implementation.

Year 3: RBA: Signed in mid-2017, originally £4.3m linked to losses recovered in CMS Fire Agreement. Due to delays in agreeing triggers, MoH missed one payment of £2.15 m. The focus was on health financing and supply chain reform £2.15 m allocated, part of milestone 4 missed, MoH and DFID agreed payment would be on pro-rata basis and reduced to £2 m

- Achieving value for money: medicines. Frameworks agreements in place, no procurement for the agreed medicines under the FAs will be outside of the FAs. (Applies to RMS and teaching hospitals): verified by a Global Fund verification exercise. Trigger: Signature of framework agreement, and evidence of use of FAs by all regions. Achieved and estimated 30% savings (to be quantified in VfM analysis)
- Warehousing and distribution three regional medical stores upgraded based on the warehousing optimization study Achieved.
- Supply chain: Last mile distribution 80% of all health facilities in 4 supported regions at sub district level including CHPS receive health products on a regular basis based on milestones and last mile implementation plan.  Achieved
- Health Financing. National Health Accounts completed, analysed and disseminated’. 2. Health Finance working group revived and active Partly Achieved. HF working group did not meet and reforms supported in previous years not taken forward. A pro rata amount was then paid
ANNEX B PARTNERS FINANCIAL MANAGEMENT

MoH: DFID funds MoH through signed MoUs, in quarterly disbursements. These disbursements are made in advance, upon submission of reports (narrative and financial) of the preceding quarter and detailed budget/forecast for the subsequent quarter. Funds are disbursed after review of these documents when DFID is satisfied that the reporting requirements have been met. Implementation of agreed activities/reporting have delayed on many occasions. In 2015, a review was conducted, this exposed governance related concerns. In August 2016, a consultant (Technical Adviser) was engaged by DFID to provide strategic governance support to the MoH to resolve concerns identified during the review. The Technical Adviser also closely monitored the TA fund and the 3 Agencies (NHIA, FDA and MHA) and reported accordingly.

Financial management remained a concern despite a noticeable improvement over the life of the TA fund. The Fund continued to maintain high balances on the 4 disbursed tranches during project implementation. A final expenditure verification was conducted to end of period June 2018. It found ineligible expenditure largely on payment of honoraria and DSAs outside agreed conditions with DFID. Total refund (including ineligible expenditure and unspent funds) at the end of the project for the TA Fund was GHS 330,215. Fund balance and ineligible expenditure related to MoH’s 5% deductions from CHPS transfers was GHS 753,575. Total refund to DFID therefore came to GHS 1,083,790 i.e. £172,306. This was then deducted from the final RBA payment due MoH. Note: the original RBA allocation for 2017/18 was £2.15million but with some milestones missed, MoH and DFID agreed payment would be on pro-rata basis and therefore be reduced to £2,015,625. Taking out ineligible expenditure and unspent funds, final RBA payment to MoH therefore came to £1,843,319 (£2,015,625 less £172,306).

GHS: The fund transfer channel for the CHPS component (Bank of Ghana to the MoH to GHS for onward transfer to the regions and districts, then CHPS zones) posed challenges to the smooth flow of activities in line with workplans, delayed activities starting. With the associated high risk of implementing the CHPS model down to the sub districts/zonal levels, PwC’s work in reviewing expenditure/retirements and making recommendations has been critical. GHS has also intensified its own periodic expenditure verifications at the regional, district and municipal offices. These have been found to be reasonably robust albeit with room for continuous improvement. Clearly from the PwC reports, general financial management of CHPS has improved over time. Spend has been within agreed budget and funds have been used for agreed activities. The 2018 expenditure verification conducted by PwC identified some unsupported /ineligible expenditure, in addition to weak financial controls (disbursement of funds to districts via cheques instead of bank transfers, monitoring reports not prepared with sufficient detail and inadequate bookkeeping in some regions). This identified a total refund of approx. GHS600,000 (pending final draft of audit) which is expected to be refunded to DFID in 2019.

MHA: MHA’s financial management and understanding of DFID systems has largely improved with financial reporting providing adequate information required for analysis and decision making. At the end of 2017, MHA was holding a high balance (£900,000) due to delayed implementation of activities. MHA were granted no cost extension to December 2018 to enable them to complete all the remaining activities. Forecasting improved over the years. The expenditure verification conducted during the period noted some irregularities around unsupported spending and reallocation of funds to different budget lines without prior approval from DFID. Recommendations have been addressed and all issues resolved.

FDA: The standard of FDA’s financial management has been acceptable over the span of the programme. Their forecasting has improved over the years with support from DFID. Based on large balances and slow spending in 2016, DFID withdrew the final tranche of £1m. The 2017 expenditure verification identified concerns around unsupported expenditure, these were addressed as confirmed from a follow up visit by the FMC. Following this process, DFID approved additional funding (£200,000) of the TA fund tranche 5 to be used for FDA agreed activities. Reports together with all supporting documents were scrutinised to provide the necessary assurance that funds were used as agreed. An audit reports is expected.

NHIA: NHIA’s financial reports have been consistently accurate and timely. The final one highlighted a deficit of GHS 652,541 (circa £93,000) at the end of June 2018 even after DFID, through tranche 5 of the TA fund provided £100,000 to address the funding shortfall as a result of exchange rate fluctuations accruing from a period when the project was temporarily on hold to allow for some internal investigations (no fraud identified, and investigation closed in 2015). DFID made it clear that despite the deficit identified, no further disbursements could be made to them and that they needed to source funds elsewhere to clear the said deficit. Audit reports covering 2014/15 was unqualified and expenditure verification also covering November 2013- June 2017 did not identify any major issues. All assets have been verified to be in good condition and those wrongly classified in the register has now been rectified.

CHAG: CHAG’s financial management has been generally strong with largely clean audit reports and no major issues noted during expenditure verification. A review of CHAG was conducted by a Senior Fiduciary Risk Adviser in March 2017 considered CHAG operations to be in order, financial and narrative reporting timely. An updated due diligence did not flag any significant concerns but recommended that CHAG puts in place strategies to raise funds after DFID supports has ended. There were concerns around underspend, forecasting, slow in reporting. These concerns were resolved, and forecasting improved significantly over the years with support from DFID. A revised accountable grant letter was issued with additional requirements. All audited reports received were considered unqualified. Their final financial reconciliation noted no unspent funds and confirmed that funds had been used for intended activities. The £3.4 million grant was fully disbursed by March 2018 with financial and audit reports up to date. CHAG maintained a comprehensive asset register, annual assets verification was conducted and at the end of the project it was agreed they retain the project assets to ensure continuity of their programmes.

Basic Needs Ghana: During the review period, the overall budget allocated to BasicNeeds Ghana was £4.5 million and all has been disbursed. They have spent against their proposed objectives and provided explanation to recorded variances. Their reporting has also improved based on a new agreed financial template. Annual audit report continued to be unqualified. However, in December 2016, an audit on a UKAid direct grant to Basic Needs Ghana and expenditure verification commissioned through PWC identified significant internal control weaknesses. DFID Ghana conducted its own investigation in March 2017 as well as a due diligence. Finding included: unsupported expenditure, unreconcilable fund balance, outdated risk management framework, non-existence of a fraud register, inadequate staffing. DFID and Basic Needs Ghana agreed an action plan to improve these areas. Basic Needs paused activities for a period of 6 months while improvements were taken, and a new accountant recruited. All actions have now been completed and as a result, the accounting systems are in a better place. There were concern about Basic Needs Ghana dependency on DFID funding and this recommendation remains for concerted effort by Basic Needs to diversify funding sources. Basic Needs Ghana maintained an asset register, all were verified and their requested to retain the assets is currently been reviewed. The final project review report has submitted, and final audit report is expected by the close of June 2019.

ANNEX C PROGRESS ON AR RECOMMENDATIONS