Annual Review - Summary Sheet
Title: Health Pooled Fund (HPF) South Sudan
Programme Value: £56 million from DFID, £51 million from partners / Total: £107 million available at Nov 2014 (Project approval is up to £122 million)			Review Date: / 3rd – 14th November 2014
Programme Code: 203109	Start Date: October 2012	End Date: April 2016

Summary of Programme Performance
Year	2013	2014
Programme Score	A	A
Risk Rating	Medium	High

Summary of progress and lessons learnt since last review
Despite sudden internal armed conflict taking place during the year, HPF performed very well in its core objective of increasing the provision of health services in South Sudan. The conflict continued to disrupt project activities throughout the year in one target State, Unity, although the situation in the remaining five project States eased enough to allow a return to more normal project activities. In response to the security situation, HPF both strengthened its own security precautions and supported its Implementing Partners (IPs) to strengthen theirs where necessary.
Plans derived from the Health Systems Strengthening (HSS) situation analysis undertaken in 2013 have been prepared to carry forward the HSS component. Work was carried out over the year to support the development of the County Model through support to planning, human resources management, drug supply management and public sector financial management, both at state and county levels. Given that one aim of HPF is to support the development of a government-led health system, and while taking into account the difficult operational context, the implementation of the important leadership and governance component of HSS has lagged behind. The Technical Assistance (TA) provided by HPF was of satisfactory quality.
The community strategy and plan to guide HPF work on community engagement has made only limited progress within HPF, although work on community engagement has been carried out by the IPs without central guidance, and facility health committees are in place in most facilities with about 30% female participation. The platform for dialogue between communities, health facilities, IPs and County Health Departments (CHDs) has not yet been fully established.
Concerns about the management arrangements of HPF during the year resulted in the preparation of a Programme Management Update/Performance Improvement Plan which was agreed by DFID in September 2014. It is too early to say whether this will have had the desired effect. ( See CA Management Note at end of AR) This annual review noted a number of problems with project management both between the project office in Juba and the Principal Administrator headquarters in United Kingdom and within the Juba project office including communications, timely management of contracts, slow disbursement of funds..
The HPF responded well to the increased humanitarian needs resulting from the armed conflict, allowing flexibility for the IPs to respond to the humanitarian needs that arose in their areas of operation and assisting the IPs to continue support health services delivery for both the indigenous populations and for internally displaced persons in camps in the affected Counties.
Summary of recommendations for the next year:
HPF should:
- Support systems for improvement in quality of care by the Ministry of Health (MOH).particularly operations of county and state hospitals
- Develop further the oversight function, accountability and roles and responsibilities, at CHD level, including encouraging the universal introduction of Memoranda of Understanding (MOU) between the State MOH, CHDs, hospitals and the relevant IPs.
- Encourage mechanisms for disseminating best practice and innovative approaches through exchanges of IPs/CHDs between counties.
- Monitor National drug availability and liaise with IPs to enable them to procure supplies if it seems likely that gaps will emerge when the Emergency Medicines Fund (EMF) finishes in mid-2015.
- Finalise arrangements for managerial and technical back-up for the long term HPF technical experts under recruitment for State and National levels.
- Prepare, through the incoming Technical Assistance (TA), a community strategy and realistic operational plan and, subject to approval by the Steering Committee, implement it.
- Revise some of the logframe indicators and add indicators related to the quality of community engagement and quality of care.
- Continue efforts to build CHD capacity to analyse and utilise the HMIS data.
- Develop and provide formal guidance to IPs on a variety of both technical and administrative matters.

DFID should closely monitor project performance management performance against the Programme Management Update agreed between DFID and Crown Agents.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	BC Quest file 3867841
DevTracker Link to Log frame:	Logframe Quest File 4695715

Outline of the programme
With four other donors (Australia, Canada, the European Union and Sweden) the UK, through the Health Pooled Fund (HPF), is providing £107 million to support the delivery of the Health Sector Development Plan 2012-16 (HSDP) of the Government of the Republic of South Sudan (GRSS), in six of the country’s ten States (Eastern Equatoria, Unity, Western Bahr el Ghazal, Northern Bahr el Ghazal, Lakes and Warrap) to assist the transition from a Non-Governmental Organisation (NGO) led health service to one that is led by government.
Before the start of HPF, multiple NGOs supported service delivery in the six States through an individual health facility based model, with funding from at least five major humanitarian funds/projects. This funding came to an end in December 2012 and the HPF was designed to replace this with comprehensive support for primary health care delivery using a county based model of support. (Health services in the other four States are funded, separately, by USAID and World Bank, using a similar county based model - there is strong liaison among the three programmes to ensure consistency).including regular monthly meetings In this model, County Health Departments (CHDs) lead and manage the delivery of health services, supported by the National and State Ministries of Health (MOH).
The first task of HPF was to issue standardised service delivery bridging contracts to the existing NGOs to prevent any interruption in service delivery. The bridging contracts were completed within the first six months of the Inception Phase.This was followed by long-term contracts awarded, through competitive tender, to NGOs to support health service delivery and systems strengthening using a county based, rather than individual facility based, model. The contracts were awarded across 39 counties in two phases. The first phase completed by June and the second pahse contarted he NGOs in September 2013.
The HPF funds the delivery of a basic package of health services in the six states with support going to all levels of care (in 2015) in the near future, State hospitals. A central fund manager sub contracts Implementing Partners (IPs) at county and hospital levels in the six states. The fund manager of HPF is a consortium of agencies led by Crown Agents with a mandate to deliver the programme including both fund management and technical support.The programme also provides TA to CHDs as well as capacity development support to the central and state level MOH to enable them to lead and manage the health systems and service delivery effectively. HPF is a government-led programme overseen by a steering committee chaired by the MOH, co-chaired by DFID, with representation from other government ministries, the Health NGO Forum and donors. State and County Oversight Committees provide project oversight at the lower levels.
The programme began in October 2012 with an inception period extending until June 2013. In December 2012, bridging contracts were issued to 16 NGOs to continue health services delivery in 281 facilities in the six states. Long term contracts, based on the County Health model have now replaced the bridging contracts for the 39 Counties in the 6 target States. Eight County hospitals and seven Faith Based Hospitals are now being supported through a similar model with support to State Hospitals to be introduced in the near future.
The project had an initial focus from the programme start in October to June 2012 on sustaining essential health services, by means of the bridging contracts, in the absence of adequate government resources. Once this support was in place the focus was to shift to health system strengthening activities including strengthening public financial management for the transfer of health worker salaries from NGO to government payrolls and also supporting work to establish structures at the community level to increase the local accountability of health services.
The impact of this programme is intended to be Government led health systems that save lives. The overall outcome will be increased access to quality health services, in particular by children, pregnant women and other vulnerable groups. The outputs this programme will deliver to achieve the outcome are:
1. Strengthened delivery of health services, particularly responsive to the needs of women and children,
2. Increased ownership, governance and demand of communities for health service,
3. Strengthened health systems at State and County level.
Armed conflict erupted in South Sudan in mid-December 2013 necessitating the evacuation of HPF team members and IP staff for around six weeks. Subsequently the operating environment was extremely difficult and programme interventions were disrupted. While the acute conflict situation eased from March to November 2014, no peace agreement has yet been reached and localised conflict continues. Due to a fluid, uncertain and politically sensitive environment during the conflict, all DFID funded programmes were advised to limit engagement with government in the first few months of 2014.This particularly affected activities at central level. The programme responded by developing and implementing a six-month interim strategy and a strategy specific to Unity State (the most directly affected amongst the six HPF supported States) to adjust the programme delivery in response to the new realities. If widespread conflict recurs, project implementation is likely to become more difficult for both security reasons and the likely detrimental effect on government expenditure for health.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Impact Indicatorsa	Baseline (2010)		Target (2016)
1. Under 5 years mortality rate (per 1,000 live births)	106/1,000		95/1,000
2. Maternal Mortality Ratio (per 1,000 live births)	2,054/100,000		1,643/100,000
Outcome Indicatorsb	Baseline (2010)	Milestone (Dec 2014)	Progress / (Sept. 2014)
1. % of 1 year olds vaccinated with a third dose of DPT vaccine.	27,899 (11%)	75,000 (30%)	27.3%(29.3%)c
2. Proportion of children under 5 with fever in the last two weeks who were taken to a health facility.d	15.3%	None set	Not measured
3. Contraceptive Prevalence Rate.d	6.5%	None set	Not measured
4. % of births attended by skilled health personnel	7,311 (2.8%)	19,250 (7%)	6.4% (6.8%)

Notes:
1. National surveys required to measure Impact Indicators. None carried out recently due to the on going conflict and accessability. .
2. Source for Outcome Indicators HPF Quarterly Report July – September 2014.
3. In response to the continued insecurity in one HPF supported State (Unity), HPF is reporting performance in all six States as well as, in parentheses, performance in five states excluding Unity.
4. Source of data is a Household Survey scheduled for 2015 – milestones can be set once this is published based on latest data.
The impact indicators used in the project are national targets and not specific to HPF and will be measured through future national surveys.
Outcome indicators 1 and 4 reflect progress up to the end of September 2014[1]. The targets for both the proportion of children fully vaccinated with DPT and the proportion of births attended by a skilled health worker were close to being achieved in the nine months, suggesting that the 2014 Milestone will be achieved. These targets include the results for Unity State where implementation activities have been significantly disrupted by the armed conflict.
[1] Progress in outcome and outputs may not be attributable to HPF alone, as other programs contribute to the results, e.g. Drugs supply centrally from MOH/EMF, immunization supported by UNICEF and WHO, etc.
Outcome indicators 2 and 3 are to be measured through a household survey scheduled for 2015.
Overall output score and description - A
The HPF has been successful in increasing access to health care in all six supported States, including Unity. However, as support is limited to existing health facilities, many families still have no easy access to health care provision. Despite the engagement of significant numbers of qualified health workers through the HPF, the quality of care remains a significant cause for concern with shortages of qualified health workers, inadequate facilities, poor drug management, limited guidelines and protocols and inadequate supervision (particularly clinical) of peripheral health workers.
With the aim of developing a government-led health system, considerable further work is required in health systems strengthening, particularly in supporting efficient and effective leadership and governance at, and between, county and state levels, including evidence–based planning, budgeting and reviewing, and operational guidance for supportive supervision focussed on clinical care. Two out of the six proposed interventions in this area were implemented during the review period. Synergy between HSS and Service Delivery HPF work streams requires continuous and careful coordination
Work on community involvement with the health services has been carried out through the individual IPs in different counties but without any central MOH/HPF direction with the potential for considerable variation in the focus of this work stream in different counties.
Key lessons
The posting of qualified health workers along with a more regular drug supply, basic equipment and facility refurbishment has increased utilisation of health facilities. The introduction of a harmonised salary scale amongst all IPs has reduced competition for workers. However, the number of health workers, either in South Sudan or in neighbouring countries, available and willing to work in more remote facilities is limited, reducing the possibility of all primary care facilities having the full complement of staff as required by the Basic Package of Health Services (BPHS).
Security was and remains a significant concern, limiting activities in a number of states, most notably Unity.
Key actions
The baseline figure for Outcome indicator 1 needs correcting in the logframe and other logframe indicators / milestones (Output 1.5 milestone, 3.4 definition) would benefit from amendment.
It would be appropriate to try to introduce some indicators that address the quality of care provided. These could relate, for example, to knowledge and skills of health workers: percentage of staff knowing how to diagnose and treat common childhood diseases (e.g. malaria and diarrhoea), or staff providing IMCI in accordance with guidelines; with information to measure these obtained from the health worker observation element of the supervisory visits.

Has the logframe been updated since the last review? Yes
The first Annual Review (AR) recommended a revision of the logframe. A revised logframe was agreed in September 2014 that contained the revision of some output indicators, baseline figures, milestones and targets, as well as impact weighting and risk ratings of outputs.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened delivery of health services, particularly responsive to the needs of women and children
Output number per LF		1	Output Score	A+
Risk:		High	Impact weighting (%):	50%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones (Dec 2014)		Progress (September 2014)
1.1 Total <5 yrs. OPD consultations & <5 yrs. OPD consultations disaggregated by gender and preventive/promotive.	Male curative	450,000	Male curative	492,759
	Female curative	450,000	Female curative	503,517
	Preventive M&F	400,000	Preventive M&F	543,471
	TOTAL	1,300,000	TOTAL	1,539,747
			Milestone moderately exceeded
1.2 Number (%) of children < 5years with diarrhoea who receive ORT	750,000 (80%)		77.7% (78.9% excluding Unity) Milestone likely to be achieved by year end
1.3 Percentage of women who attended at least 4 times for antenatal care during pregnancy.	20% (57,000)		21.4% (22.4% excluding Unity) Milestone moderately exceeded
1.4 Number of acceptors new to modern contraceptives.	7,000		5,419 Milestone likely to be achieved by year end
1.5 No. of facilities with capacity to offer Emergency Obstetric care (disaggregated BEmONC and CEmONC)	All HPF supported hospitals provide CEmONC[2].		9 of the 15 HPF supported hospitals provide CEmONC. It is anticipated that a further 6 County and Faith based hospitals will be providing CEmONC by the end of the year. / Milestone will have been achieved
	25% of all 39 counties have at least one PHCC with BEmONC		49% (19) of HPF supported counties have at least one PHCC with BEmONC capacity. Milestone substantially exceeded
[2] CEmONC/BEmONC = Comprehensive/Basic Obstetric and Neonatal Care.

Key Points
The reported increased availability of basic health care services, in particular for women and children, is likely to be due to increased numbers of operational health facilities. These doubled from support to 281 primary care facilities and 3 hospitals through the original bridging contracts to support for 562 primary health care (PHC) facilities (135 PHC Centres (PHCC), 427 PHC Units (PHCU) and 15 hospitals by September 2014 . HPF enabled additional health staff, medical equipment, drug supplies, rehabilitation of facilities and stores to improve the functioning of facilities.
Uptake of MCH and other essential services; e.g. skilled birth attendance and vaccinations, are likely to meet their 2014 milestones. On average, family planning services are only provided in one third of the PHC facilities. Other reproductive health interventions complement HPF interventions in some counties. Referral systems have been strengthened with the procurement of ambulances and support for their maintenance. CEmONC2 services in selected faith-based and public hospitals were increasingly provided. The proportion of PHCC that provide BEmONC substantially exceeded expectations.
Insecurity following the 2013 conflict made access to some counties, especially in Unity, impossible. Health facilities were destroyed and vehicles looted. Access was regularised by April 2014 (except Unity) with increased costs and requiring additional humanitarian HPF assistance. HPF responded adequately and flexibly to the crisis.
Quality of services has been addressed by focusing on human resource capacity, the distribution of drugs and medical supplies and treatment guidelines, and joint supervisory visits. Despite these actions quality of care is low. In the absence of a Quality Assurance (QA) policy, strategy and management guidelines at SMOH and CHD levels, and easily readable/visual tools at facility level, the health system is in need of developing and using results-based management protocols/standard operational procedures that ensure adherence to quality of service standards throughout the system.
Summary of responses to issues raised in previous annual reviews (where relevant)
The project logframe, with milestones and impact weightings, was revised in March 2014 with further revisions in September 2014 agreed with DFID.
A health facility assessment was recently completed by MOH. National standards for delivery of a Basic Package of Health Services (BPHS) were established. HPF was involved in testing, introducing and encouraging County level quarterly supportive supervision as a step towards monitoring care standards.
Recommendations
HPF should:
- Prepare Information, Education and Communication (IEC) materials (simple, easily readable and visually attractive, based on the existing treatment guidelines) for health facilities, which focus on diagnosis and treatment of most common diseases (malaria, pneumonia and diarrhoea).
- Support MOH in the development of a QA policy and procedures for the CHD through:
- Facilitating MOH approval of existing draft QA materials.
- Supporting development of a QA policy, strategy and standard operational procedures using results-based management protocols/standard operational procedures.
- Preparing clinical information materials for health facilities that focus on diagnosis and treatment of a selection of the most common diseases.

Output Title	Communities have increased ownership, governance and demand for health services
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Note: a: HPF Survey 2014 that assessed 82% (444 facilities) of HPF supported facilities.
Indicators	Milestones (Dec 2014)	Progress (Sept 2014)a
2.1 No. of health facilities with a health committee in place for communities to give feedback regarding health services.	80% of all HPF supported facilities have a functioning health committee.	80% of facilities have a committee / Outputs meet expectations
2.2 Number of documented joint meetings between the CHD/IP and the health committee and facility staff.	At least 2 joint meetings per year held & documented in all PHCC and in 50% of PHC Units (PHCU).	50% of health facilities have held joint meetings involving IP/CHD/ Health Committee/Health facility. / Outputs significantly did not meet expectations
2.3 Number & percentage of health committee representatives that are women	At least 20% of committee members are women	32% of health committee members female. Outputs substantially exceeded expectations

Survey did not disaggregate findings by PHCC/PHCU
Key Points
The Community Strategy and Operational plan prepared for the project in July 2014 has not been finalised, although it did prompt the reconstitution of an MOH Technical Working Group (TWG) on community based healthcare. There was a lack of capacity both within MOH and HPF to take this work forward within the MOH.
Separately, IP’s are required to facilitate facility engagement with their communities, and have provided considerable training to community members and committees. However this was carried out with no direction from a national plan, resulting in the potential for widely diverging approaches being taken in different counties.
Many IPs inherited existing health facility community structures and both the number of facilities with committees and the female representation on the committees are reasonable. Less success has been seen in enabling the four party meetings (IP/CHD/health facility/Committee) that is seen as the mechanism for increasing accountability of service providers to their communities.
The IPs contracted by the HPF are mobilising communities for such activities as (i) supporting facility outreach activities such as vaccination programmes; (ii) validating the local staff being recruited; (iii) monitoring attendance of health workers at health facilities; (iv) resolving community disputes; (v) community needs assessments; (vi) facility supervision; (vii) health education and promotion; (viii) disease surveillance; and, (ix) reporting the status of health facilities. These activities are performed differently by different IPs in the counties’ project areas as there is no central guidance.
All the indicators used in this output demonstrate the quantity of community activities (number of committees, meetings, female committee members) with no consideration for the quality of these activities.
Summary of responses to issues raised in previous annual reviews (where relevant)
A short term TA was contracted to prepare a Community Strategy and Operational plan to guide HPF work on this Output. This was developed in July 2014, but not accepted by HPF.
All IPs have been requested to budget for a County Community Mobilisation Officer to act as focal point for community elements of the BPHS.
The indicator relating to Community Health Mobilisers was removed from the revised logframe.
Recommendations
A community strategy and realistic operational plan should be prepared by the incoming TA in this area, and, subject to approval by the Steering Committee and TWG, implemented.
The existing draft guidelines for community level bodies should be finalised as part of the overall plan and then used as a common framework for all IP community engagement activities.
While recognising the difficulty of defining and measuring the quality of community engagement, HPF should seek to define such an indicator that can be used in future. These could relate to a chosen focus of community activities such as the number of community referrals of pregnant women for antenatal care or health facility delivery or the number of children referred for immunisation services.

Output Title	Strengthened health systems at State and County levels with detailed focusing on Policy, Human resources for Health, Health Financing, Health Information and Leadership and Governance
Output number per LF		3	Output Score	B
Risk:		High	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones (Dec 2014)	Progress (Sept 2014)
3.1 Number of HPF Steering Committee meetings chaired by the GRSS and number of State Oversight Committee meetings held.	(a) 10 (cumulative) HPF Steering Committee meetings chaired by GRSS / (b) At least 2 State Oversight Committee (SOC) meetings held in each state except Unity	(a) 9 HPF Steering Committee meetings held between December 2012 and October 2014. A 10th is scheduled for December 2014. / Outputs expectations likely to be met / (b) In 3 states 2 SOC were held; / In 2 states 1 SOC was held; / In Unity no SOC was held. / Further meetings scheduled for final quarter of 2014. / Output likely to be met.
3.2 Number of facilities with quarterly integrated supervision conducted by county health department using QSC tool.	50% of HPF supported health facilities	33% (36% excluding Unity) / Outputs substantially did not meet expectations
3.3 No. of health facilities submitting HMIS reports through the DHIS (according to the data policy flow)	70%	78% (81% excluding Unity) / Outputs moderately exceeded expectations
3. 4 Proportion of counties with one joint plan, and one review system for all government and NGO health services	Proportion of counties with one joint plan = 50% Proportion of counties with one review system =20% Proportion of counties with one joint plan and one review system = 20%	Proportion of counties with one joint plan = 100%. Reviews anticipated to be held in January 2015. / Outputs moderately did not meet expectations
3.5 Number of counties submitting South Sudan Electronic Payroll System (SSEPS) forms, disaggregated by government and implementing partner (number of SSEPS forms completed and sent to HPF)	75% of counties use SSEPS for salaries paid through HPF	87% (34/39) of counties use SSEPS for IP paid salaries. / Target moderately exceeded expectations.

Governance, leadership and management:
A draft implementation plan for leadership and management development guided HPF TA inputs during the year. It was only partly implemented due to the conflict as well as due to inadequate budgeting in year 2.
The County Model has been applied in all 6 states. County health plans were developed for year 2. IPs and CHDs are co-located in nearly all counties and CHD human resource capacity has increased, but is still weak in some counties. In some counties IP performance is lower than expected. Transparency has improved and there are signs of trust being built between partners, thus increasing synergy. SMOH supportive supervision was funded, work plans initiated, and first visits made. A gaps analysis on supervisory visits was conducted in Warrap State.
Human resource management and development:
Through the IPs and SMOH, health workers have been recruited for health facilities and the CHD offices. A harmonised salary scale for all IPs is in operation, balancing the advantage of reduced competition, between IPs, for health workers with the disadvantage of reduced flexibility to encourage the deployment of skilled health staff in remote areas.
HPF has significantly contributed to the Human Resources Information System (HRIS), developed in collaboration with MOH and other government bodies. HRIS enables HR management by MOH and HFP and is seen as having critical financial as well as managerial benefits. It is strongly supported by central government, and is an example of the government-led nature of HPF. The HRIS is expected to identify discrepancies on the payroll. The system has been designed with HPF support and has been piloted in two counties. It is expected to be rolled out early in 2015 and will pave the way for another high Value-for-Money intervention, the Attendance Monitoring System (AMS). This will enable CHDs and State Ministries of Health to gauge the level of absenteeism and respond.
HPF supported an assessment of Health Training Institutes. Plans for support to an operational action plan to increase the number of skilled birth attendants were stopped as a debate is ongoing at MOH whether traditional births attendants should be capacitated or removed as cadre.
Pharmaceutical supply chain management (PSM): HPF has established an effective mechanism that allowed Emergency Medical Fund supplies to be supplemented by HPF procured supplies where needed.
HPF supported MOH in capacity building and quality improvement in PSM, facilitating the removal of expired drugs and reorganising drugs storage space. A pull system and a stock monitoring system were set up for a more rational distribution of drugs. The pull system should minimise expired drugs and optimize drug use according to the needs. At state level, HPF supported the process with Training of Trainers (TOT) on PSM in, so far, 4 states. PSM experts are being recruited for full time positions at each SMOH.
Public Finance Management Strengthening: Public Finance Management (PFM) strengthening activities are broadly interpreted in HPF. In addition to support for the financial transfer systems and financial management proper, it includes salary harmonization, the adoption of the GRSS payroll system, the South Sudan Electronic Payroll system (SSEPS), the introduction of HRIS and the development of an AMS. The focus has been on salary harmonization amongst NGOs which has been successfully carried out with limited exceptions. SSEPs has been introduced in 34 of 39 Counties, and this will in due course aid the smooth transfer of NGO staff to government. A major investment of PFM strengthening has been to develop a set of PFM benchmarks required before HPF funds can be paid directly to GRSS. These benchmarks remain desirable in themselves, however it is unlikely that DFID will use GRSS financial systems within the current project phase. A PFM baseline being developed in relation to these benchmarks since mid-2013 remains incomplete, and needs a renewed focus.
The PFM strengthening stream has made steady progress. It has been limited in its achievements because only 0.75 of a full time equivalent (FTE) person was allocated to this work. HPF has now recognized the need for much greater inputs and, along with a TA to be embedded in the MOH, 12 PFM staff are being recruited to work at State level to ensure better financial flows (from GRSS) and better financial management. Six of these new staff members have already been recruited. They will need to be intensively managed.
The PFM strengthening stream has been able to strengthen its rapport with MOH further by arranging for HPF to employ an already embedded and trusted PFM expert based in the MOH. This will deepen the HPF/MOH relationship, and support the joint action in this area.
Health information: Considerable effort has been placed, by HPF and consultants, on supporting the implementation of the MOH Health Management Information System (HMIS) through preparation of guidelines and manuals. Training was provided for IP, SMOH and CHD in the skills required for HMIS data capture and cleaning. HPF provides frequent ad hoc support to State and County through email, telephone and field visits. HMIS performance is improving but considerable weaknesses remain. HPF also uses the HMIS for monitoring some project outcomes. Performance monitoring of IPs has been well designed and results have been triangulated and proved valid.
Summary of responses to issues raised in previous annual reviews (where relevant)
The HPF Health Services Strengthening team is operating from an office within the MOH. More staff will be embedded within the MOH in late 2014/early 2015 through the HSS component of the project.
Other than for the strategic leadership component, no strategy to guide activities for improving the quality of service delivery was developed.
Recommendations
HPF should:
- Prepare a strategy and plan for Health System Strengthening activities, including quality of services delivery.
- Use the important role of the leadership and governance component of HSS to guide – at state and county levels – Government, HPF and other programme responses to the humanitarian crisis in conflict and adjacent area’s through supporting the joint steering, planning and review mechanisms.
- Encourage the further development of the MOH (all levels) oversight function, accountability (horizontal and vertical) and roles and responsibilities at CHD level to maintain progress.
- Encourage the universal introduction of MOUs between the SMOH, CHD, hospitals and the relevant IPs.
- Encourage mechanisms for best practice dissemination (e.g. information analysis and feedback to facilities, incentive scheme for facility deliveries, etc.) and innovative approaches through exchanges, between counties, of IPs/CHDs.
- Monitor national drug availability and liaise with IPs for them to procure supplies if it seems likely that gaps will emerge when the Emergency Medicines Fund finishes in mid-2015.
- Encourage the national MOH to determine what population data to use for the indicators and to set national targets for all PHC indicators.
- Further automate, through suitable IT solutions, the information regularly collected from IPs and others in this large program in order to manage knowledge in a timely and efficient manner.
- Undertake intensive and proactive management of all the TA under recruitment, to include strong monitorable job descriptions, targets, rigorous monitoring and clear guidance and technical back up.
- Ensure the early completion of PFM Baseline.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
Key cost drivers and performance
The major cost driver identified in the Business Case (BC) was the number, type and location of project supported health facilities. Other cost drivers identified were salaries of health workers and pharmaceuticals. There have been no changes in key cost drivers except that pharmaceuticals have proved less significantThe business case said: A further key cost driver during the first 1-2 years is drugs. Whilst the HPF should not be the primary provider of pharmaceuticals, around 50% of the pharmaceutical needs have been budgeted into the model. In practice, pharmaceuticals have not proved to be a great cost driver, representing only 3% of IP expenditure to date. This is likely to be because the Emergency Medicines Fund, a donor funded initiative to provide drugs and medical supplies to most of South Sudan's peripheral health facilities became operational in August 2012 and was providing a good proportion of overall requirements by mid-2013 and consequently there was no need for IPs to purchase significant quantities of drugs etc.
.
Some work streams are proceeding more slowly than planned while others are ahead. This divergence from plan is not expected to affect the overall project cost.
The financial statements from inception to June 30, 2014 indicate that £18.4m (79%) of a total spend of £23.3 million was spent on IP contracts. The balance was mostly management fees in accordance with contract. An analysis of this IP spending indicates that, in accordance with BC expectations, the largest spending category was salaries of health workers, 39% of the total. Other support to the CHDs represented 11% of the total, and support to the IPs themselves (South Sudan programme management costs) amounted to a further 39%. These three represent 89% of the total spending of IPs and 70% of total HPF spending. Contrary to BC expectations, pharmaceuticals are not a major cost driver, at only 3% of the total IP spend.
In addition to focusing on the performance in comparison to the BC, it is pertinent to enquire about the economy, efficiency, and effectiveness of these areas of spending. One of the challenges of South Sudan is that skilled human resources are scarce, and IPs struggle to secure good personnel to work in the counties. However, efforts made to train and supervise staff are being formalised and extended (discussed above). A Health Facility Survey carried out at the end of 2013 showed only a marginal change in the numbers of key cadres of PHCC staff compared with the 2011 survey, indicating that overall HR numbers did not increase up until the end of 2013.
It is not possible to speak of VfM in “Support to CHDs” since they are an assortment of things, but HPF reviewed the procurement policies of all IPs which should support economic procurement. The types of support provided by IPs to CHDs varies considerably across the 39 counties thus it is very difficult to compare the inputs between counties, for VfM purposes, as the support needs are so different. The HPF, as part of its due diligence assessment of the IPs during contracting had assessed and approved the procurement policies of each IP and thus was assured that procurements undertaken by the IPs would provide VfM.

“Service Provider Support” plus IP overhead was expected to be contained under 30% and the very high rate of 39% has arisen because of the very low spending on direct costs. As noted elsewhere, reported spending by IPs has been low (Half way through the project, RFP1 spend is only £5.7m from £31m; RFP 2 is £2.6m from £26m). Overhead management costs claimed by the IPs are relatively fixed and consequently represent a higher proportion of overall spend than they would have done had IP spending on service delivery been higher.
The low overall IP spend may be a result of a number of factors:
1. Expenditure is recorded on the basis of actual expenditures rather than expenditures plus commitments (accruals) thus probably underestimates the true financial picture.
2. IPs have been required to advance the funds for initial spending themselves, for subsequent reimbursement by HPF. This may have caused some cash flow issues for some IPs which should ease as the financial flows are established.
3. Less than anticipated expenditure on drugs has been required, as explained above.
VfM performance compared to the original VfM proposition in the business case
The BC VfM section focusses primarily on the core area of the programme – health service delivery. It identifies seven key areas of intervention and using the World Health Organisation’s CHOICE methodology calculates that the HPF intervention will produce 305,277 Disability Adjusted Life Years (DALY) averted. It calculates that the cost per DALY averted as $255, rising as high as possibly $325 if conflict is seriously intensified. It assesses this to be very cost effective in comparison with Gross National Income per capita.
Unfortunately, the BC does not disclose the full underlying DALY calculations, and the annual review could not generate DALY data for comparison, but considers that the strong progress on key indicators outlined under Output 1 demonstrate that the value expected in health service delivery is likely to have been achieved and exceeded.The Mid-Term Review – to be completed in January 2015 – will address these calculations and come up with a report on progresson them .

It is more difficult to demonstrate VfM in Outputs 2 and 3 because measurable indicators cover only process (for instance numbers of meetings in community mobilisation) rather than outcomes, or because the outputs are themselves intermediate, such as the roll out of SSEPS. Nonetheless, HPF have produced a VfM strategy as required by their Terms of Reference (TOR).
Assessment of whether the programme continues to represent value for money
It is clear from indicator movements in Output 1 that the project, together with other initiatives has added significant value. It is more difficult to demonstrate value in the areas of Outputs 2 and 3 - community mobilisation and HSS. However, the consideration of VfM in the BC alone understates the value of this project. Areas in which hard-to-measure value has been added include:
- HPF IPs have provided support to CHDs in the implementation of modern health delivery methods but which may not impact indicators immediately;
- HPF IPs have contributed to the training of health cadres;
- There is a significant increase in services utilisation; the size of increase suggests that health outcomes are likely to have improved, although there is, as yet, no data to support this.
- There are good signs that in addition to saving lives, a government-led health service is being built – a key objective. Evidence includes: (1) MOH indicate that HPF is responsive to government needs, (2) HPF has close links to MOH, (3) some particular initiatives (harmonisation and HRIS) have been carried out in close concert with MOH and (4) the Steering Committee is active, attended by high level MOH staff and there is evidence that it introduces new initiatives and takes an active role in key decisions, occasionally exercising a right of veto.
- Although as yet incomplete, progress in the related SSEPS roll out, HRIS and AMS promises to support significant VfM in the health sector as a whole, ensuring that health sector funds are spent more efficiently and that health workers are more productive.
- HPF has together with sister projects in USAID and World Bank, pioneered the county model.
However, VfM is threatened by the shortcomings in financial management and fiduciary risk indicated elsewhere in this AR. It is also undermined by the high levels of overhead associated with the county model, especially where direct spending is low.
The points made in the BC still hold: in the absence of HPF six of the ten states in South Sudan with a population of approximately 5 million, would have significantly reduced health services.
Quality of financial management
These comments are for the most part restricted to systems operating in South Sudan. In South Sudan financial forecasts are only for the coming three months. The latest estimate of future costs for the project as a whole was carried out by DFID in June 2014 and indicates a full spend of the currently committed £107.2 million. However, to June 30, 2014 only £23.3 million had been spent from a budget of £106.9 million, representing only 21.8% after 21 months (the programme’s half way point). Slow spending on county contracts (RFP1 spend is only £5.7m from £31m; RFP 2 is £2.6m from £26m) and County Hospital contracts only now starting suggest that further reallocations may be necessary as a result of underspending. Reasons for underspending include the difficulties IPs have in recruiting staff (a major cost-driver); understatement of spending because of the cash basis accounting; project disruption particularly for RFP2 counties which started just as conflict was breaking out; and the late start of hospital contracts. Underspending may also be aggravated by the requirement for IPs to pre-finance all costs. It is likely that spending will improve with additional contracts now let, and in fact September financial statements only just released indicate that spending has reached £30.0 million after a strong spending quarter.
Financial reporting from IPs to the Juba HPF office is done in Excel, based upon Excel submissions (invoices) from IPs. No accounting software is used. Planned review of underlying documentation (held at IP HQs, mostly in Juba) is not currently undertaken. Staff report that the Risk Based Assessments (RBAs), to be carried out quarterly, have not been done because staff capacity has not been adequate.
Excel summaries are forwarded to Crown Agents in UK where payments are made. Financial statements to June 30 have been prepared but are not accrual based and do not include a Balance Sheet.
There has been no financial audit since project inception in October 2012 despite this being a requirement of Programme TOR. It is understood that DFID will now arrange this directly.
The version of the financial statements to June 30th, 2014 includes unresolved discrepancies between the overall expenditure summary and subsidiary analyses.
Individual IPs are required to submit their audited financial statement to HPF, but as yet this has been partial with only 6 Annual Audit Reports having been received to date under RFPs I and II.
A systems audit of the HPF was carried out in October, the report of which was not yet finalised at the time of this review.
Concerns over HPF management capacity and levels of authority within the project have been addressed by a Performance Improvement Plan - the Programme Management Update - agreed between DFID and Crown Agents in September 2014. It is too early to know whether this has had the desired effect. ( See Management Note Note at end of AR )

Date of last narrative financial report	November 2014
Date of last audited annual statement	None

E: RISK (½ page)
Overall risk rating: High
Overview of programme risk
The following table presents the programme business case risk matrix with comments following the AR.
Risks	Probability / 3 high, / 1 low	Impact / 3 high, / 1 low	Comments
Budget: Decrease in projected government health budget over the next three years due to decreasing revenue, continued diversion of resources into defence and security making it difficult for GRSS to support procurement of drugs, expansion of HRH, and payment of salaries.	3	2	The MOH is planning for an increase in salaries for primary health care workers as well as earmarked grants to CHDs thus seems optimistic about at least maintaining funds for the health sector. In the event of a significant decrease, the HPF will enable a continuation of primary services in the six States. However other streams of work may be adversely affected by any significant decrease in government health spending.
Donor commitments and government expectations from donors result in decreased GRSS investment in health.	2	2	Donor funding for essential drugs is coming to an end mid-2015, MOH has committed to procure a further supply. There is an urgent need for DFID and HPF to engage with GRSS on this matter.
Security and conflict: Increasing insecurity resulting from conflict in South Sudan prevents access to programme areas / Programme is insensitive to conflict	3	2	The conflict that started in December 2013 has not been resolved and still has the potential to flare up significantly again. Localised conflict, separate from the main conflict continues sporadically. In all States, other than Unity, HPF activities have resumed as before with a greater emphasis on security. HPF has enhanced its security procedures and checked those of IPs increasing budget flexibility to enable IPs to enhance their security where lacking. / HPF also has a Revised Risk Strategy ( October 2014) including risks relating to conflict with input from DFID SS Conflict and Governance advisers. HPF support to badly affected areas (as in Unity at present) is dependent on the assistance of the major relief agencies to deliver medical supplies and other support to health workers.
Political risk: Lack of cooperation / opposition from Government. This may primarily be because we are unable to allow GRSS to hold the contracts for the Fund Manager for governance and fiduciary reasons.	1	2	A demand by the GRSS for the departure of all foreigners in 2014 was quickly rescinded. The HPF is collaborating well with MOH where the modalities of the fund seem to be well recognised and accepted.
Political risk: Government may not support the HPF and make it difficult for external partners to operate in South Sudan	1	3	The HPF is collaborating well with MOH where the modalities of the fund seem to be well recognised and accepted.
Partner risk: Donors may not be keen for funds to be put through the Local Services Support Aid Instrument (LSSAI) system despite benchmarking. This would place more risk on to DFID.	3	1	There is no immediate prospect for funds to be put through the LSSAI system.
Social risk: Health services are not provided in remoter more rural and poorer areas of South Sudan leading to exclusion from the benefits of development and deteriorating state citizen relations	3	2	HPF is supporting most primary care facilities in the six States, following the existing pattern of health care provision. Large sections of the population live too far from the supported facilities to enable access.Discussions are taking place with IMA ( World Bank) and USAID on improving access for communities in Greater Upper Nile region. HPF has a special strategy for Unity State.
Fiduciary risk of supporting salaries through conditional transfer system (i.e. government system) – funds do not reach the SMOH or are not used appropriately by the SMOH.	3	2	There is no immediate prospect for funds to be put through the LSSAI system.
Breakdown in services: Interruption to service delivery during the transition from the BSF to HPF.	1	1	Transition from BSF to HPF happened without disruption to services and is considered to be a significant success of HPF.
Insufficient interest from NGOs to expand coverage to county level.	1	1	NGO’s showed interest in HPF to enable competition to provide county services to take place.
Adverse impact on operations due to inflation/ currency management issues and its impact on NGO operating costs etc. fuel.	2	2	There has been inflation, particularly affecting the price of fuel in the conflict affected States as well as a depreciation of the currency which has reduced the attractiveness of South Sudan for Ugandan health workers. The drop in oil prices and reduced production is likely to further impact negatively on the economy and engagement of expatriate regional workers.
Fragmentation in service delivery across the country due to the three different funding mechanisms using different modes of service delivery	2	2	There is collaboration across the three programmes between HPF, and WB and USAID programmes. Although there is the same county model approach in the states of Jongeli and Unity, there is also humanitarian support to particularly with MSF hospitals. The county model does vary from one county to another therefore it is difficult to confirm equity across the entire 10 states.
Interruption of services due to unrest when salaries are changed from NGO rates to government pay scales	2	2	The MOH anticipates increasing the salaries of its qualified primary care staff through a new Infection Allowance. This will bring GRSS salaries close the NGO harmonised salary scales and, if implemented, will minimise the possibility of unrest.
Insufficient human resources for health: Insufficient number of suitable qualified staff to deliver services and manage implementation of HSDP/ HPF	3	2	The IPs are experiencing a shortage of qualified health workers particularly in the more remote locations where the harmonised salary scale does not allow for incentives to attract such workers. Some staff have left for better less constrained salary scales with humanitarian organisations. This is likely to impact on equitable delivery of services also.
Low financial, procurement and distribution capacity contributes to unreliable and interrupted supplies of commodities such as drugs that are essential for service delivery	3	2	The Emergency Drug Fund will provide core primary care drugs until mid-2015. The GRSS has indicated that it will procure drugs from then, although the quantity and requirement are not clear. There is the potential for drug shortages in late 2015. The HPF supports the procurement of drugs to cover temporary shortages.
Business continuity: NGOs are unable to hand over operational responsibility for clinics to the MOH at the end of the fund.	2	3	The HPF is strengthening CHDs and various health systems including payroll. Progress will need to be assessed towards the end of the project.
Inability to tailor funding to the needs in each state due to political rejection of the Census result	1	1	There has been no evidence of significant disagreement with the funding envelopes provided for each county/state.
Inter-sectoral synergies (with WASH and education) are lost as the new fund is not cross-sectoral (unlike BSF)	2	1	There are humanitarian linkages e.g. in IDP areas, HPF NGOs link with Humanitarian workers who can provide services for the increased population and liaise with HPF NGOs on community needs. We saw evidence of weekly meetings between HPF NGOs and the Humanitarian IDP hospitals during last field trip.
Disaster risk reduction: Flooding or other environmental hazards disrupt service delivery	2	2	Floods are a normal feature of many States. The selected IPs are experienced in the conditions pertaining to their counties and plan for them.
Weak monitoring and evaluation and use of information for evidence based decision making at lower levels of the health system	2	1	The HMIS is being used to report on County level activities and while there are still weaknesses in the use of the HMIS, HPF/IP support is resulting in improvements. HPF/IP is also encouraging the use of such data through annual performance reviews.
Aid Impact and Effectiveness: Donors fail to align and harmonise activities across the country	2	1	South Sudan has many health donors and harmonisation is difficult, resulting in a risk of inequity in delivery of services The project has supported the development of a harmonised salary scale for NGO health workers, a uniform County Health model for health care delivery and of a basic package of health services and the continued strengthening the MOH to undertake a coordinating role will improve this.

The programme has developed a Risk Management Strategy (RMS) in accordance with the ToR and it incorporates a substantive section on fiduciary risk. The RMS was updated in July 2014. The fiduciary risk strategy depends primarily on a very thorough due diligence process on IPs, which incorporates an initial assessment reviewing technical capacity, financial standing and ethical policies; a procurement assessment; and a Financial Management Assessment (FMA) which reviews the financial arrangements of the applicant for management of HPF funds. The RMS does not incorporate a Fiduciary Risk Management Action Plan (as envisaged in the TOR) which could be monitorable under the Annual Statement of Progress, and one could usefully be developed. The RMS makes the valid point that payment of IPs in arrears, reduces fiduciary risk in the programme.
Outstanding actions from risk assessment
The RMS does not consider fully the ongoing risks of the programme itself where routine tasks are not carried out in a timely manner. In this, fiduciary risk is undermined through many of the concerns indicated under quality of financial management above. This additional risk is proposed to be added.
Risks	Probability / 3 high, / 1 low	Impact / 3 high, / 1 low	Mitigation
Fiduciary risk inherent in the programme at both programme management and IP level and the additional fiduciary risk that may arise from non-compliance with good practice and/or guidelines issued	1	2	Annual financial audits of both the HPF and the Implementing Partners.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
Despite the delay caused by the security situation that enforced a delay in project activity for some months and a continuing lower level of security issues subsequently, the contract is largely on track against timescales detailed in the HPF contract. There were delays in issuing contracts for two of the IP contracts, due to the need to retender, and also the contract for a family planning IP has been delayed as the preferred bidder was not able to resolve some outstanding issues with the MOH.
A number of health systems strengthening activities designed to enhance engagement in this area are being implemented, albeit delayed by the conflict etc. These should continue.

Performance of partnership (s)
The project has partnerships at a number of levels:
Funding partners (Australia, Canada, European Union, Sweden and UK): the partners are grateful to DFID for managing the HPF as they would not have the capacity in the country to do so, however there is some dissatisfaction amongst partners about a lack of consultation over some project deliverables, e.g. not having a chance to review the annual report before it was finalised.
HPF and MOH: the Project Steering Committee, chaired jointly by MOH and DFID, has met frequently and provides a forum for project decision making. MOH has been involved in important decisions over contract TOR and selecting contractors through an agreed and transparent process. At State level the State Oversight Committees have also met in all States except Unity.
Contractual partnerships between HPF and the IPs have largely worked well with most contracts performing adequately or well and only two contracts performing poorly. The annual review meeting between HFP/MOH/IPs raised numerous issues where greater contact with, and leadership by, HPF would benefit IP performance.
Consortium Partners: there is some dissatisfaction amongst most of the non-leading consortium partners about the slow rate of implementation of the project.
Asset monitoring and control
The armed conflict that commenced in late 2013 resulted in damage and looting of HPF supported health facilities, particularly in Unity State where assets purchased by HPF, valued at £206,351, were looted and clinics damaged or destroyed.
There is no section on asset management in the HPF Procedures Manual and it was not addressed by the recent systems audit. Contracts with IPs contain some provisions on asset management but a clear policy statement is needed.
Asset registers for both Juba HPF HQ and for assets purchased by IPs are maintained by HPF. The latter was not complete. Each quarter NGOs are required to provide a list of assets acquired, but no guidance on this was seen.
The procurement of vehicles by IPs requires preauthorisation, and contracts with IPs state that assets are the property of the project until the project ends with all vehicles required to have an NGO number plate. Some IPs report vehicles are registered in their names, others report that vehicles are registered in the name of their partner CHD. Explicit guidelines should be issued by HPF to clarify asset management procedures for IPs and CHDs.
Insurance: a hospital contract reviewed by the team explicitly asks that project assets should not be insured, and informs the IP that DFID will self-insure. This is incorrect and insurance requirements should be clarified between DFID, HPF and the IPs.
An HPF branding policy is in force and is evident at Juba HQ. IPs have been told to do the same at county level and have been provided with the necessary budgets to do this.

G: CONDITIONALITY (½ page)
Update on partnership principles (if relevant)
Not applicable as this is not financial aid directly given to a partner government.

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
The Business Case Theory of Change remains valid with project inputs resulting in increased health facility utilisation. There is no evidence yet to demonstrate that this is resulting in an improvement in health status.
Increased health facility utilisation has been equally shared by boys and girls while the strengthening of maternity services has benefitted women and their babies.
While originally anticipated, no evaluation is currently planned.

Monitoring progress throughout the review period
Stakeholders – MOH at National, State and County levels – IPs, community health committee members and other partners were very supportive of the HPF and also voiced constructive criticisms about aspects of its implementation. No ultimate beneficiaries, patients, were consulted during the review.
The review was conducted through analysis of secondary data provided by HPF as well as GRSS and others. This was supplemented by key informant interviews amongst stakeholders at all levels and focus group discussions with health committee members and IP field workers. Field trips were undertaken to visit 4 counties in project States visiting CHDs, hospitals and primary care facilities.
The review was conducted by Garth Singleton (Team Leader), Peter Haycombe (HMIS & Community), Ronald Horstman (Health) and Tim Cammack (Finance) in Juba over the period 3rd – 14th November 2014, with distant support from Mike Esau (VfM).

Footnote on Crown Agents Management:

The audit of HPF has taken place and will be finalised by 3rd December 2014 . This audit was a requirement under the Crown Agents (CA) contract and was initiated after one year of Implementation. DFID selected the auditor independently of Crown Agents. The audit was solely to look at controls within CA management function. The finding of the audit will be reported in more depth within the Mid Term Review report.which will be  ready by 12th January 2015. The Management audit has returned a score of “Amber Red” and has been QA’d by the Head of IAD. Measures are being taken to hold discussions with CA, PCD and DFID SS to ensure due diligence is maintained and there will be no negative impact on the programme in terms of financial management and programme delivery.
Together with this Annual review, the DFID concerns on the Management pillar of HPF are likely to  be major.
Concerns were first (officially) raised with CA about late responses, errors of judgement in procurement processes, poor communication with the Juba team and concerns on the capability/capacity of the CA Project Director in September 2013. There was little improvement and a performance improvement plan (PIP) was placed with CA in June 2014. This was done in consultation with the DFID SS Commercial Adviser. It involves a Contract Performance Review and PCD communication with CA through the KSM Programme.  The project Director was removed as HPF programme leadership by CA and replaced. The PIP was originally for 3 months but it was felt there was not sufficient time to assess any improvement and in September 2014, the PIP was extended by a further 3 months.
The final actions to be taken will be decided when the Mid Term Review (MTR)  is completed in January 2015. Together with the management audit the AR and the MTR, a consultation will take place involving PCD (the HoD has been informed), DFID Senior management, the Commercial Adviser and the DFID SS Programme team. One possible action could be that the CA contract will be terminated. Should that be the preferred course of action, the other donors will need to be consulted on that proposal.