Mid-Term Review
Final Report
Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa (ICOSA)
-

29 October 2013

Cheri Grace
Richard Johnson

###### Acknowledgments

The authors would like to thank DFID, the ICOSA team - SCI, CNTD and Crown Agents - as well as the NTD teams supported by ICOSA for valuable discussions and guidance in support of this study.

We are also grateful to the key informants named in Appendix 2, who also gave their time and have provided invaluable data and insights into the review.

Table of Contents

Acronyms
API	Active Pharmaceutical Ingredient
BCC	Behaviour change communication
CA	Crown Agents
CdI	Cote d’Ivoire
CBD	Community based distribution (or distributors)
CIFF	Children's Investment Fund Foundation
CIP	Carriage and Insurance Paid
CNTD	Centre for Neglected Tropical Diseases
DAP	Delivery at Place
DFID	Department for International Development
DOTs	Directly Observed Therapy short-course
EU	European Union
ERP	Expert Review Panel
FHI	Family Health International
GBP	pound sterling
ICOSA	Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa
KAPs	Knowledge Attitudes and Practices
LATH	Liverpool Associates of Tropical Health
LF	Lymphatic Filiariasis
NSP	National Strategic Plan
NTD	Neglected Tropical Disease
Oncho	Onchocerciasis
PM	NTD Programme Manager in country (Ministry Official)
MDA	Mass drug administration
MTR	Mid term review
mn	million
MoE	Ministry of Education
MoH	Ministry of Health
MoU	Memorandum of Understanding
PZQ	Praziquantel
PCT	Preventative Chemotherapy
PMB	Programme Management Board
RTI	Research Triangle Institute
SAC	school age children
SCH	schistosomiasis
SCI	Schistosomiasis Control Initiative
SCORE	Schistosomiasis Consortium for Operational Research and Evaluation
SEC	Senior Executive Committee
STH	soil-transmitted helminths
TAC	Technical Advisory Committee
USAID	United States Agency for International Development
VfM	Value for Money
WATSAN	Water and Sanitation
WHO	World Health Organisation

Executive Summary

Progress against Objectives
By the end of 2012, the Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa (ICOSA) programme reported that it had delivered 6.3 million treatments, less than half of the 14.25 required for its Outcome target. The ICOSA Progress Report October 2012 to March 2013 reported delivery of 12.2 million treatments to March 2013. In March 2013, ICOSA was thus still 2 million short of its 2012 December target.

Despite falling short of its Outcome level targets, progress according to output indicators appeared to be progressing nearly on target. The ICOSA Inception Report and detailed implementation plans were completed by January 2011, while iterations to the log frame have continued as part of the business case process for the planned programme expansion. It was expected that formal project agreements with all 8 countries would be signed by December 2012, however Tanzania was not signed until May 2013 and there were also delays in the Zambian contract, signed in December 2012 (whereas the intent had been to sign January 2012). Mapping progress moderately exceeded expectations and the development of National Strategic Plans (NSPs) proceeded ahead of target due to the World Health Organisation (WHO) taking the lead.

Annual praziquantel (PZQ) tablets delivered to countries in 2012 totalled 54 million tablets, which exceeded the Output target of 36 million. There is now a greater need to expand the base of commercial suppliers. ICOSA should continue to inform discussions between WHO and Merck Serono regarding the implications of restrictions on their donated supply. The number of countries where implementation of mass drug administration (MDA) is taking place met the indicator expectation, but the target (the addition of 1 country by 2012) was insufficiently stretching. MDA treatment distribution has been far more concentrated than expected, with 80% of supply going to 3 countries.

Five countries are achieving 75% coverage in target areas, according to reported coverage (only Malawi has conducted a validated coverage survey), which exceeds the expectation of three countries achieving 75% coverage. Seven countries were expected to produce data using standardised protocols to measure health impact indicators. Zambia and Cote d’Ivoire are not doing this, which means the indicator was not met. Two countries were expected to start producing data using standardised protocols to measure cost-effectiveness and efficiency of programmes and this expectation was met. Work is in progress on the other indicators added to the 2013 log frame. However, the vacant health economist post will delay progress according to the timetable.

There are two likely reasons why Outcome slippage went under the radar: i) Output 5, which focused on number of countries ready for MDA, was a key one in terms of overall programme progress; however, it was insufficiently stretching and, since it did not require reporting for each country, it failed to flag up countries where progress was lagging behind. ii) The programme’s previous annual and mid-year reports to DFID did not clearly state what the target was by a certain date, what had been achieved by the target date, and a quantification of the shortfall on an output where it is “ongoing” rather than achieved. Given these two problems, the result was that the log frame and report to DFID were not operating sufficiently as performance and risk management tools, highlighting where shortcomings were occurring.

Many different secondary reasons have been offered for not meeting some targets, but at the core of the challenges were issues with staff continuity, systems/process for planning and reporting and, related to these, underspend at the country level in the first two years of the programme. The time taken to qualify PZQ suppliers, which meant supplies did not become available until January 2012, has contributed as well.

ICOSA’s contribution relative to country needs
ICOSA’s assistance in-country was variable and overall lower than expected. However, this is not necessarily a negative, as the level of assistance a country requires differs according to capacity and maturity of the programme, for instance, and how well other sources, including WHO and implementation partners, are meeting the country’s technical needs. However, the scope and scale of ICOSA’s involvement in supporting countries is markedly different than the level of support implied in the bid and in the inception report; this in turn has implications for the staffing needs. Based on these findings as well as country visits, the mid-term review (MTR) team recommends that the scope and scale of technical assistance offered by ICOSA will need to change to better meet country needs.

There were some common concerns across countries about ICOSA support: short contracts with uncertain budget ceilings; frequent requests to cut budgets but not treatment coverage, which has resulted usually in cuts to community sensitisation budgets; and needs for managerial and systems/processes support especially where programmes are new or there is a new variant to an established programme.

ICOSA staff rightly stress the importance of national leadership. However, this is not always balanced by recognition of the need for pro-active support in order to achieve a satisfactory programme growth. Country PMs may be more open to ICOSA technical support as well as influence if time is taken to build relationships and address practical needs such as clear budgets and funding; this involves committing the time and being customer-focused. Also, there needs to be a more strategic approach to capacity building, linked with change management objectives.

Value for Money and Sustainability
The £25 million GBP under Phase 1 is divided into £10.5 million to the Schistosomiasis Control Initiative (SCI) for programmatic implementation and £14.5 million to Crown Agents (CA) for procurement of vehicles, computers, other equipment and PZQ. The £10.5 million for programming is broken down into £4 million central management costs and overhead and £6.5 million goes towards costs associated with MDA delivery in countries.

There has been considerable scrutiny around the £6.5 million, but it remains unclear how the research will inform policy and practice. Central level expenditure needs to be similarly analysed. Staff time at SCI and CNTD has not been allocated on a bottom-up basis to specific ICOSA tasks and deliverables versus other wider SCI and CNTD tasks. There needs to be a system established for doing this, in order to guide ICOSA management decisions about how to allocate resources for maximum return.

Effectiveness of the programme is about its health impact. Country visits revealed a concern that the cost focus and constant budget trimming may have had repercussions on quality of MDA delivery. Effective targeting – the right countries, the right regions within countries and the right individuals – is also key to health impact. ICOSA’s choice of countries has appropriately balanced a number of factors, not only unmet disease burden, but also the entire budget envelope relative to size of need, country commitment, and the balance between a sustainability emphasis on Group III countries focus or an impact focus on Group I countries. However, the actual vs. projected allocation of MDA treatments has been rather more concentrated than expected and this raises some questions about whether actual practice is following strategic choice and intent with regard to allocations for maximum health impact

Within countries, ICOSA has funded mapping work in all but two countries (which already had mapping data) and this has been a major focus of the past two years of the programme. Guidance for mapping and how to translate mapping results into MDA implementation at country level is provided by the WHO Strategic Plan for schistosomiasis (SCH); this advises on which operational choices are appropriate in different country contexts with different neglected tropical disease (NTD) goals, most appropriate target populations and distribution channels, treatment intervals, and complementary water and sanitation interventions. ICOSA was unsuccessful in influencing the Tanzanian government to target all the areas with highest SCH disease burden. There have also been issues related to selection for mapping and sentinel sites, and whether to randomise blindly or try to account for the focal nature of the disease.

Effectiveness of health impact also depends on central government commitment to control SCH and soil transmitted helminths (STH) as evidenced by the country having included SCH and STH control objectives in their National Strategic Plan (NSP) for NTDs. All ICOSA countries now have NTD NSPs, however, the quality of plan implementation is variable, as is the resource the government provides to NTD strategic and planning capacity at Ministry level.

Health impact is crucially dependent on whether the preventative chemotherapy (PCT) distributed is actually taken up by the target individuals. Stakeholders acknowledge that global understanding of compliance and knowledge attitudes and practices (KAPs) is sub-optimal and ICOSA could make a greater contribution to the knowledge base.

A key issue in terms of equity is how the project is reaching children not in school and other high risk groups. Many country programme managers feel especially insecure in this area, acknowledging the heightened risks and costs of extending beyond the relatively more controlled school-based MDA programmes. Coverage validation surveys allow SCI to estimate the proportion of all school age children treated, as well as the gender-specific coverage and KAPs. This has so far only been implemented in Malawi; it is planned for Cote D’Ivoire, Tanzania, Uganda and Zanzibar during FY4 however the health economist lead on this work stream has recently left the programme so there may be delays.

Programmatic sustainability is a function of value for money (including health impact over time as the effectiveness variable, country ownership, capacity building, and contribution to global public goods (knowledge) with which all programmes can be improved.

Stakeholders widely acknowledge that the evidence base behind many WHO guidelines is sub-optimal. Even where there is more solid evidence behind the guidance, country PMs sometimes find it difficult to translate the guidance into the local situation, where financing or programming can be a limiting factor. This is where ICOSA staff should be able to add significant value, but in some of the countries surveyed, ICOSA advice is not being fully leveraged and/or it seems to conflict with WHO guidance (as in the sampling issue with regard to mapping and sentinel sites). There was also some contention about the balance between academic publication versus making available (what is perceived to be inappropriately guarded) data SCI has already, more speedily for the benefit of public health policy and programmatic improvement.

As for VfM and sustainability of Crown Agents, their work has been very positively reviewed by partners and there have been several examples whereby cost savings were achieved. Approximately 80% of the £14.5 million GBP channelled through CA is used to purchase PZQ, so PZQ price is a major cost driver of the programme. ICOSA purchases through CA are subject to European Union (EU) procurement regulations and PZQ suppliers must be approved by a WHO Expert Review Panel (ERP). The PZQ paid by Crown Agents rose by 25% between Years 1 and 3 of the existing ICOSA programme. Even though there will be an increase in donated PZQ, it is possible that supply security and pricing may become an issue as the programme increases in scale. The MTR team recommends that CA be incentivised through the project log frame to make the supply base more diverse. They can work with new suppliers to help them understand how to gain technical acceptance by WHO and encourage suppliers by sharing information on the expanding size of the market. A new framework contract will need to be issued during 2014.

Partner Linkages
The rationale and opportunities for further integration are country-specific and progress is likely to be driven by i) whether there is a process for partners to identify opportunities for cost-sharing and joint working ii) the existence of relationships between individuals who have the interest and potential to work more closely together and iii) the commitment of government, donors and other stakeholders to the concept of integration. ICOSA can be credited with making some attempts in this area, but has been held back in other areas partly due to factors outside its influence. Several options for tracking progress in this area are presented in the report. Communication between CA and ICOSA programming staff, as well as other partners, has been working effectively.

Alignment of Management and Processes with Programme Needs
The latest annual and mid-year reports to DFID do not focus clearly on the achievement of objectives on time. These reports lack a section that clearly addresses the outcome (formerly purpose) achieved compared with target; nor do they clearly quantify the size of the shortfall in an output, where it is “on-going” rather than achieved. We found little evidence that managers are focused on achievement of the outcome. We did not find regular feedback either within SCI or CNTD showing performance against targets. There neither appears to be periodic reporting, nor reporting at the end of a major activity, nor exceptional reporting of delays or problems. Trip reports by managers were either perfunctory, providing no indication of national programme status, or simply unavailable. Nor was it clear who was responsible for achieving a target, or to whom they were accountable. In both SCI and CNTD, the lack of accountability for performance supported by clear performance targets is a major concern.

ICOSA’s reports attribute delays to local factors, implying a very high degree of external risk outside ICOSA’s control. Delivering the outputs and outcomes of the programme requires ICOSA to reduce or mitigate the external risks to the programme and to provide a high standard of disciplined management to ensure that its own services reliably meet the requirement of national programmes. Interviewees were consistent in their recommendations to reduce uncertainty and delay: they stressed the importance of stronger in-country presence by ICOSA to advocate the ICOSA programme, to negotiate and to build partnerships with both statutory and other partners in NTD control, and to plan interventions; national staff also focused on the practical requirement for an agreed multi-year framework for planning ICOSA’s engagement, reliable information on future availability of funds, including budget ceilings and parameters, prompt contracting and release of funds. In some cases, these practical contributions were more important than technical contributions to SCH control, which in some countries are largely provided by in-country expertise and WHO guidance.

Successful delivery of MDA requires the management of complex and interdependent tasks, from advocacy and contracting to reporting and evaluation. Both CNTD and SCI use some project management tools to assist this. However, these tools do not appear to be used to track and correct performance in practice. ICOSA’s planning does not reflect the full scope and interdependency of plans. Plans currently focus only on Outputs, not on the key critical activities required to deliver them, such as agreement on regions, signature of contracts, and release of budgets. SCI and CNTD country workplans do not include the many tasks that have to be undertaken before implementation can take place. There need to be milestones for these stages, such as engagement with stakeholders, formation of a task team, a memorandum of understanding, coordination of mapping or sentinel sites with other agencies, an outline multi-year plan and budget and contract signature.

Financial management needs to be closely aligned to other reporting, so that budget and work plan form an integrated whole. In practice it was not easy to find adequate linkages between work plans and budgets, to evaluate what resource is required to do a job, and hence what budget is required. At the central level, it is important for the staff and travel resource allocated for ICOSA employees to be derived from the activities stated in the workplan. Similarly, at country level budgets need to be built up from, and scrutinised against, the work plan and relevant cost benchmarks. Currently, country budget scrutiny is limited to peer review, and on requiring national programme managers to cut budgets to fit budget ceilings. While both of these can be useful, country budgets also need primarily to be scrutinised against the resources required to deliver the activities specified in the work plan.

Financial controls and audit standards of funds held overseas are incomplete and below standards described in the proposed business case. There is considerable variation in accounting practice between locations, and between SCI and CNTD. SCI’s contract specifies accounting and audit requirements, and provides an accounting template. SCI has an accounting manual, and is currently updating this. It is also developing a template to facilitate cost analysis. CNTD’s contract does not mention accounting requirements beyond the requirement to submit a “narrative and financial report in CNTD financial template”. Contact between ICOSA and local accounting staff is limited. Although both SCI and CNTD accounting staff have made visits to a few overseas locations, there is no regular process of supervision or internal audit. CNTD ran a training workshop for finance staff in 2012. Similarly, local reporting routines vary, according to the requirements of SCI and ICOSA, and according to the practice of the local office.

ICOSA primarily operates as a professional grouping of highly qualified specialists under the supervision of a highly experienced director who is also a professor. Productivity of these high value professionals could be improved by complementing them with people who have other, often less specialised and sometimes less costly, skills. There are notable skill gaps in management and finance.

Systems need to be put in place to clarify what skill sets and what number of days are required to meet the activities required by work plans, countries, or project outputs. There has been a great fluctuation in availability of staff due to maternity leave and other causes, and there is concern that some staff could be overloaded, with responsibilities within ICOSA for country programmes, as well as other responsibilities across ICOSA, or outside ICOSA. These issues cannot be resolved and/or appropriate cover provided until annual staffing requirements have been clarified, based on the work plans of each country and ICOSA as a whole.

Key Risks and Mitigation Strategies

Phase 2 programme risks were identified in the May 2013 business case; those same risks apply to the Phase 1 programme. The MTR team’s view on those risks, given findings of the September 2013 MTR, are presented in Section 7.

Given the limited supply base for WHO pre-qualified PZQ, risks to supply security and pricing of PZQ have risen. To mitigate, CA needs to be incentivised through the log frame to expand the supply base and a new framework contract process needs to be initiated.

The probability of PCT compliance issues is expected to be higher for low-endemicity settings and mitigation includes increased community sensitisation, research into KAPs. The MDA delivery channel also has potential to influence compliance as community based distributors (CBDs) do not always use directly observed therapy (DOTs), and side effects (which can affect compliance) can be more common where people take PCT on an empty stomach. Mitigation: linking up with feeding programmes, increased investment in behaviour change communication (BCC) and health education, enrolling support of health workers for credibility and side effect management.

Shortfalls in numbers treated to date may be regarded as moderate. However, the pace of delivery will need to increase very rapidly in order to deliver the further 72 million treatments targeted by the end of 2014 (part Phase 1 and part Phase 2). This is no small operational challenge. Given findings of the MTR, we would raise the probability scores on the risks related to country capacity and contractor capacity to scale up. Having a large portfolio of countries and ability to move funding around to countries based on progress will help mitigate this risk, and ICOSA needs to better tailor its support to the bottlenecks experienced by countries so that it is not so dependent on 3 countries to take up 80% of treatments.

Subsequent to MTR country visits and interviews, exclusion of hard to reach is now viewed as more probable due to increased risks and costs as well as managerial challenges of reaching high risk adults and children out of school. Yet, in some settings, health gains are likely to be greater in these groups. There are opportunities to work with and learn from other programmes that use community based distribution e.g. onchocerciasis.

The risk of funds not being used for their intended purpose has been rated as medium risk; a timetable has been proposed for a programme of improvements to systems and audit of finance in 2013 and 2014.

Section 8 of the report presents a summary of recommendations and time-tabled actions agreed between ICOSA management and DFID at a final meeting.

Introduction

## 1.1 Background
A mid-term review was conducted of the Integrated Control of Schistosomiasis and Intestinal Helminths in sub-Saharan Africa (ICOSA) programme, focused on reducing morbidity and mortality by delivering 75 million treatments for schistosomiasis and intestinal helminths in 8 African countries. The programme provides chemotherapy through Mass Drug Administration (MDA) to school-aged children and high risk adults. The eight countries have classified into three groups according to current progress towards schistosomiasis and soil-transmitted helminth (STH) control, and are as follows:

- Group 1 (No active control programme): Malawi, Cote d’Ivoire, Liberia
- Group 2 (effective NTD treatment delivered to some degree): Tanzania, Mozambique, Zambia
- Group 3 (established integrated NTD programme): Niger, Uganda

This is DFID’s first programme of support for schistosomiasis; this support has been provided through the Schistosomiasis Control Initiative (SCI) based at Imperial College. SCI have sub-contracted, the Centre for Neglected Tropical Diseases (CNTD), Liverpool School of Tropical Medicine and the Liverpool Associates in Tropical Health (LATH). SCI and CNTD provide technical assistance and other support to governments in the design, implementation and monitoring of programmes. LATH provides support and manages project funds for CNTD.

Schistosomiasis is a debilitating parasitic disease. It is a chronic illness that damages internal organs, affecting 200 million people in developing countries. According to the World Health Organization (WHO), Africa accounts for nearly 90% of the global burden of disease. Soil transmitted Helminths (STH), commonly known as intestinal worms, affect a large number of people, perhaps over 2 billion worldwide, and have an insidious effect on health and nutritional status.

Schistosomiasis (SCH) along with other neglected tropical diseases (NTDs) disproportionately affects the poorest people living in rural areas, and perpetuates their poverty through the disability they cause. The control and elimination of SCH in the long term requires an improvement in environmental conditions especially water and sanitation. However, in the short to medium term, WHO recommends chemotherapy as the most cost-effective means of control. A child can be given praziquantel, a safe and effective drug, at a very low cost. Ideally treatments should be given annually in high risk areas but less often in lower risk areas. Because STH commonly occur alongside SCH, it is more efficient to treat both together. STH are normally treated annually with albendazole, which is donated.

Crown Agents has been contracted to supply goods worth £14.5 million while implementation costs channelled through SCI total £10.5 million. SCI retains overall responsibility for delivering results; it leads on 5 countries and CNTD leads on 3. Governance of the programme is via a Programme Management Board (PMB) which meets once per quarter and is specific to ICOSA. SCI’s Technical Advisory Board governs the work of SCI overall and meets once per year. CNTD also has separate systems for approving work plans and budgets, including those related to ICOSA – Technical Advisory Committee (TAC) and also now (a recent initiative) the Senior Executive Committee (SEC).

The project began in October 2010 and is currently in its 35th month (out of a total 60 months). The inception period was between October 2010 to May 2011 and the implementation phase began May 2011. Thus the programme has been fully operational for 28 months, although PZQ only became available in January 2012 due to the time taken for supplier qualification for procurement.
## 1.2 Terms of Reference
The objectives of the MTR were as follows:
- Evaluate and score the overall progress of the programme against the objectives set out in the log frame for Phase 1. Where possible also comment on progress against the additional indicators in the new log frame.
- Review how well the project meets the technical or management needs of countries given the different contexts?
- Assess the efficiency and effectiveness of the programme, its sustainability and its value for money.
- Consider how well the project links up work of other partners, for example:
- With other NTD control efforts, the integration of delivery or the sharing of resources where needed
- Links with water and sanitation
- Communication and co-ordination with other funders, purchasers and quality regulators of PZQ
Is there more that can or should be done on this area?

- Identify any key risks, opportunities or threats to the programme’s expected impact caused by changes in global context and assess mitigation strategies.
- Assess whether the project has the most appropriate skill mix
- Analyse the robustness of the planning and reporting processes
- Analyse the robustness of the financial management and reporting processes

## 1.3 Methodology
Methods included document review, focused interviews of the ICOSA team, interviews with NTD programme managers in ICOSA-supported countries, and other relevant stakeholders including other donors, followed by final analysis and feedback. Appendix 1 provides details on the timing of the work and the approach.

The MTR team spent half a day with SCI and CNTD in London reviewing their summary of progress against objectives. The team member with responsibility for management and finance spent further time with staff at CNTD and SCI. Twenty-six stakeholders were interviewed by phone. Based on these early meetings and iteratively through the work, the team developed notes on what theories and issues needed to be further tested and validated, including with stakeholders at country level. An interview guide for country based informants was developed – Appendix 3, and was tailored to the role of the specific informant.

The team visited Zambia, Tanzania and Zanzibar where they spoke with NTD Programme Managers (PMs), other stakeholders, observed a snail control programme in Zanzibar, participated in a pilot MDA in Zambia and interviewed technicians involved in mapping in Zambia. The rationale for country selection was that these countries had not yet been visited during previous annual reviews, and represented one CNTD- supported as well as one SCI-supported country. Zanzibar was added due to convenience of location and because it added an element of diversity in SCH disease burden and approach. PMs in Liberia, Malawi and Uganda were also interviewed by phone. PMs in all except Mozambique and Cote d’Ivoire completed a survey quantifying the scope and scale of support received by ICOSA.

In order to bolster the validity and credibility of findings, the MTR team used i) mixed methods, combining methods to collect qualitative and secondary quantitative data; ii) triangulated observations, relying on two or more data sources to study the same question or outcome; and iii) validation – checking back with key informants on the accuracy of data and reasonableness of interpretations, especially where contentious issues arose; and iv) ‘counterfactual thinking’ – exploring whether alternative explanations could have caused or contributed to observed relationships or outcomes.

Independence of informant interviews was bolstered through i) MTR team driving the selection of country-based informants ii) leaving some time for confidential discussion, without presence of the ICOSA team at the end of each interview and iii) supplementing the stakeholder list provided by ICOSA with independently identified additional stakeholders to interview.

During the country visits the MTR team tried to balance developmental issues – bringing stakeholders along through a process of enquiry, furthering programme objectives – whilst accomplishing an objective evaluation. Thus, ICOSA staff usually stayed with the MTR team during part of the meeting and then left the review team to interview privately during a portion of the meeting.

To evaluate the portion of the programme channelled through Crown Agents, interviews were held with CA’s two suppliers with active framework agreements, as well as IDA and RTI who conduct similar functions to CA albeit with USAID funds, and a half day meeting was held with the CA team (see Appendix 4 for the agenda from that meeting).

Two final meetings were held to agree and timetable specific actions in Section 8; one meeting was held with ICOSA management, DFID and the MTR review team and a second meeting included the Crown Agents team, DFID, the MTR review team and the SCI Director.

2. Progress Against Objectives

The MTR team was asked to evaluate and score the overall progress of the programme against the objectives set out in the log frame for Phase 1 (presented below), and where possible also comment on progress against the additional indicators in the new log frame from May 2013 (See Appendix 10).

## Purpose (now Outcome) Level

At the purpose (now Outcome) level, the project is expected to “Contribute to the global strategic plan for SCH (2012-2020) by controlling morbidity due to SCH by 2020 and eliminating SCH as a public health problem by 2025”. The indicator is “Number of treatments delivered, in millions (cumulative)” with a milestone of 14.25 by December 2012.

By the end of 2012, ICOSA reported that it had delivered 6.3 million treatments, less than half of the 14.25 expected. The ICOSA Progress Report October 2012 to March 2013 reported delivery of 12.2 million cumulative treatments to March 2013. In March 2013, ICOSA was thus still 2 million short of its 2012 December target in the log frame.

Despite falling short of its Outcome level targets, progress according to output indicators appeared to be progressing nearly on target. There are two likely reasons why Outcome slippage went under the radar: i) Output 5 focused on countries ready for MDA delivery, was a key one in terms of overall programme progress and it was insufficiently stretching and specific in that it did not have targets for each country. ii) The programme’s previous annual and mid-year reports to DFID did not clearly state what the target was by a certain date, what had been achieved by the target date, and a quantification of the shortfall on an output where it is “ongoing” rather than achieved. Given these two problems, the result was that the log frame and report to DFID were not operating sufficiently as performance and risk management tools, highlighting where shortcomings were occurring.

Many different secondary reasons have been offered for not meeting some targets, but at the core of the challenges were issues with staff continuity and systems/process for planning and reporting and, related to that, under spend at the country level in the first two years of the programme. The time taken to qualify PZQ suppliers, which meant supplies did not become available until January 2012, has contributed as well.

## Output 1 Countries selected and project implementation plan finalised
Impact Weighting: 10%
SCORE: B

Output Indicator	Milestone 2012	Status
1.1 Inception Report and detailed implementation plan completed	Implementation plan and detailed log frame accepted	Inception Report and detailed implementation plans were completed by Jan 2011. Iterations to the log frame have continued, partly as a result of the business case for Phase 2.
1.2 Formal project agreements signed	3 agreements existed at baseline and 8 agreements were expected by 2012.	The target required that formal project agreements with all 8 countries would be signed by Dec 2012. However, Tanzania was not signed until May 2013, although SCI had transferred 75% of funds for MDA activities in February 2012.There were also delays in the Zambian contract, signed in December 2012, despite the intent to sign by January 2012, when the first payment was made.

Reasons given for delays in signing the Tanzania contract were related to i) Intellectual Property – the head of NEMRI was not happy with the ownership of data and asked for the contract wording to be amended recognising the government rather than SCI as the ultimate data owner[1] and ii) some contract rigidities and misaligned timescales between country and ICOSA related as well to change in senior MoH staff. To overcome these challenges, informants at the country level said “closer follow up from SCI would have helped”. The SCI programme manager was on maternity leave for a year and insufficient cover was provided in her absence.
[1] Imperial report that they could not sign a contract to allow ownership of the data by the country. In order for Imperial to fulfil the terms of their contract with DFID, Imperial was required to have ownership of the data. This was negotiated with Tazania and co-ownership was agreed.

Signing of the Zambia contract was delayed due to a combination of delays on the CNTD side and delays on the Zambia side. During the first half of 2012, contracts were the responsibility of a CNTD Centre Manager dealing with finance and contracts at LSTM level and CNTD personnel dealing with Finance and contracts at country level. When the Centre Manager left in June 2012, a new CNTD country manager began to work with the contract office and by the 3rd of July 2012 the contract was sent to Zambia, though it was not until 17th December that it was signed.

Recommendation:
There should be adequate coverage for absent staff and tighter allocation of responsibility and reporting. Managers need to be responsible for achieving outcomes and objectives, within a supportive management framework. There should be monthly feedback within SCI and CNTD showing performance against targets. There should be quarterly formal reporting against targets, reporting at the end of a major activity, exceptional reporting of delays or problems. There should be pre-trip reports outlining the purpose of the trip (including any influencing agenda) as well as post-trip reports detailing national programme status against objectives. When it appears that programme progress is becoming challenged in a country, there should be a process to problem solve and work through options such as strengthening relationships and/or tailoring/adapting support services.

## Output 2 Priority areas selected by mapping of infected populations
Impact Weighting: 10%
Score: A+

Output Indicator	Milestone by 2012	Status
2.1 Number of countries with specific mapping protocols available	In the log frame agreed at inception, it was stated that 3 country protocols existed at baseline and 8 country protocols would be developed by 2012. In the May 2013 log frame, this was revised to 2 existing at baseline, 6 to be available at 2012 and 8 to be available by 2014.	The prediction of 8 countries requiring protocols has been reduced to 4 after assessment of available data. Target achieved.
2.2 Number of project countries who have conducted mapping surveys.	The target was for 6 out of 8 countries to have undertaken mapping surveys by end of 2012. After assessment, only 4 countries (Cote D’Ivoire, Liberia, Zambia and Malawi) required mapping surveys to be conducted, with 2 requiring re-assessment (Niger and Uganda) and 2 countries (Tanzania and Mozambique) where no mapping or re-assessment is required.	Target has been met.
2.3 Target areas mapped for disease by country (cumulative)	May ’13 log frame states that 100% at risk areas had been mapped in Mozambique and Tanzania at baseline and by 2012 the following at risk areas would be mapped: 100% Malawi, 30% Liberia, 20% Cote d’Ivoire and 40% Zambia.	Progress has moderately exceeded expectation in that more of the country has been mapped than was anticipated: 100% Malawi / 60% Liberia / 46% Cote d’Ivoire / 70% Zambia

The distribution of schistosomiasis is very focal, having a varied distribution within a small radius. Disease mapping is therefore required for better targeting and a more rational approach to MDA, conserving resources for the highest need areas and informing treatment schedules. By revealing the disease burden, it also provides the evidence for advocacy. Prevalence is determined by assessing infection status in children from randomly sampled schools.

Mapping activities, including assessment of existing data, protocol development and data collection surveys, have started in all countries where required. Some countries have recently been mapped and therefore no further mapping is needed. The mapping data collected as part of ICOSA contributes to the information that countries submit to WHO as part of their application for drug donations.

Mapping protocols for Group 1 and 2 countries have been designed in order to categorise each implementation unit (the lowest administrative unit at which treatment decisions are taken) to determine whether they need treatment and the frequency of this (annual, biennial or every three years). There have been issues with regard to site selection methods for both mapping and M&E, in the absence of clear guidance from WHO. The debate centres on appropriate sample size and whether to randomise site selection vs. target suspected focal areas. ICOSA has used a standardised mapping protocol to date in all Group 1&2 countries (Malawi, Zambia, Liberia, Cote d’Ivoire – Mozambique and Tanzania had historical mapping data available). This protocol is not consistent with WHO guidance as it prioritises randomised site selection and requires a larger (than 5 schools) sample size. In practice (as identified during the MTR) some ICOSA funded countries have not followed SCI guidance precisely and have altered the list of randomly selected schools to account for local knowledge of SCH focal areas. Similar debates also apply to sentinel site selection. ICOSA is in discussion with WHO at present to try and come to an agreement on a consistent view that balances what is achievable for countries with often limited resources and the ideal methodology to guide where treatment truly is required. A significant amount of resource has been devoted to mapping during the first half of the project and it has been a source of delays, so it is important to get issues resolved.

The Group 3 countries, Uganda and Niger, rather than re-mapping are undergoing a reassessment exercise to evaluate the impact of historical treatment to inform decisions on the treatment frequency. The evidence base for the most appropriate timing of reassessment is not well established.

In Zambia, the entire country was mapped in one year between March 2012 and March 2013, which is record-breaking speed. This was achieved despite a number of constraints which are not under the control of the project – maternity leave, Ministerial realignment.

Recommendations:
- Resolve outstanding issues on mapping protocols with WHO
- Complete data collection in 2013 in those countries which have only been partially mapped.
- Continue to develop coordinated mapping and sharing of data with partners to ensure no duplication of resources.

## Output 3 National Strategy plans developed in selected countries
Impact Weighting: 10%
Score: A

Output Indicator	Milestone by 2012	Status
3.1 Group 1 countries National Strategic Plans (NSPs) - reviewed and approved	Baseline was existing NSP in 1 country. The target was for NSPs to be developed in 3 countries by 2012, with approval by 2014.	Target has been met.
3.2 Group 2 & 3 countries National Strategy Plans (NSPs) - reviewed and approved	The target was NSPs approved in 5 countries in 2012.	This has been met.

The development of a National Strategic Plan (NSP), to outline the policies and plans for implementation of NTD control, indicates government commitment to NTD control and facilitates country-led priority setting. Quality NSPs should demonstrate appropriate resource targeting for maximum health impact as well as managerial structures and plans.

Prior to the start of ICOSA, draft NSPs existed for Uganda, Niger, Tanzania, Malawi, Mozambique and Zambia. Since 2010, WHO/AFRO have convened training workshops for national NTD programme managers to elaborate their country NSPs. As a result, all ICOSA supported countries have produced NSPs for the control of NTDs for the period 2012-2016, identifying the strategic priorities. Although the NSP process limited participation of external partners to encourage country-led approaches, ICOSA has worked with countries, to varying degrees, ensure the annual plans address the most urgent needs. However, the MDA scale-up plans for Tanzania did not prioritise the regions with the highest SCH burden and ICOSA was unable to influence this. Countries visited during the MTR expressed the need for stronger support on technical and managerial challenges affecting plans.

This indicator was dropped from the May 2013 log frame as there was a view that WHO AFRO had taken the lead and with diminished need for ICOSA role. However, countries (especially those with less mature programmes) require greater technical as well as managerial support from ICOSA. Developing detailed work plans and corresponding budgets is a particularly weak area. Even countries with established programmes are experiencing technical challenges such as method of site selection for mapping and sentinel sites; schedule of monitoring with regard to programme issues and affordability; minimising risks of treating non-enrolled and at risk adults through community distribution; and for Niger and Uganda, understanding where, when and how to interrupt transmission in line with the revised WHO recommendations
Recommendation:
ICOSA should help identify and respond to needs for greater technical as well as managerial support where this is required, including work plans and budgets, mapping, MDA, M&E and interruption of transmission.
## Output 4 Drugs procured and delivered to countries
Impact Weighting: 20%
Score: A+

Output Indicator	Milestone by 2012	Status
4.1 No of tablets delivered to countries annually	35.6 million tablets (40 million in the Inception log frame) were to be delivered by 2012	Exceeded target – 54 million delivered between Dec 2011 and Dec 2012.

In 2011, a Pre-Qualification Questionnaire was issued to all of the potential PZQ suppliers and 14 responses were received, 13 of which were invited to submit tenders. Nine companies submitted bids. All bids were subject to a Preliminary, Technical and Commercial evaluations and the product samples were forwarded to the WHO to enable the Expert Review Panel (ERP) to carry out the technical evaluation. The longest delay in the procurement process was due to the time taken by the suppliers to submit data required by the ERP.

Microlabs Ltd and Cipla Ltd were the only two sources of supply which were technically acceptable to the ERP. Inspections of the manufacturing plants of Cipla and Microlabs were carried out to ensure that they were suitable to supply PZQ to the project. Framework contracts were placed with Microlabs Ltd, Cipla Ltd and IDA Foundation (who are supplying product manufactured by Cipla Ltd) for the continuous call-down requirements for PZQ over the life of the project.

The global supply of quality PZQ is limited and ICOSA relies on a limited supply base. There is now a greater need to expand the supply base due to scale up with Phase 2 and limited qualified supply. Merck Serono is scaling up donations but this presents opportunities as well as risks to security of supply to the programme. The donation also carries certain restrictions (school age children only, single source within a country) and rigidities in terms of supply request timing (requests must be made each August for the subsequent year). This highlights the importance of maintaining supplies from commercial manufacturers alongside donations. WHO is currently in discussions with Merck Serono about the requirement for their donations to be sole source to beneficiary countries.
The target for 2012 was to have delivered 40 million tablets. This indicator was met and the number of tablets procured and delivered between end of Dec 2011 and end of December 2012 was 54,375,500 tablets (108,751 packs).

Recommendations:
- Crown Agents should intensify discussion with suppliers on WHO qualification process, convey new (expanded) market size projections, and issue a new call for proposals for framework agreements. Crown Agents should be evaluated on expanding number of WHO approved suppliers having an active framework agreement for supplying ICOSA.
- ICOSA should contribute programmatic knowledge to current WHO and Merck Serono discussions with regard to feasibility and appropriateness of Merck Serono restrictions on their donated supply. The risks and disadvantages of excluding at risk adults and requiring single source should be made transparent to all parties.

## Output 5 Project countries implement MDA for schistosomiasis and soil-transmitted helminths (STH)
Impact Weighting: 30%
Score: A

Output Indicator	Milestone by 2012	Status
5.1 No of countries ready for MDA campaign in selected areas	At baseline, capacity for conducting MDA existed in 4 countries and it was expected that those same 4 countries would be ready for MDA implementation in 2012	Target met.
5.2 No of countries implementing MDA according to their Strategic Plans	2 countries were already implementing MDA according to NSPs at baseline and the target was 3 countries by 2012	Achieved but target was insufficiently stretching.

Preparing countries for MDA delivery involves a complex set of interdependent steps and processes and the potential scope and scale ICOSA has been funded to offer countries is vast: support to policy and strategy development (NTD integration, advocacy with stakeholders or policy-makers, strategies for reaching specific target groups); support to mapping (protocol development, data collection and analysis); managerial support (MDA work planning, logistics, budgeting, development of training materials); support to communications and community sensitisation; support to M&E (health impact monitoring, cost analysis). ICOSA was significantly under spent in country support during the first two years of the programme[2] and according to country surveys conducted as part of the MTR, it still is not providing the sort of scale and scope of support as was envisaged at the outset of the programme.
[2] During 6 months of FY 1 (October 2010 to March 2012) there was an under spend of £67 K. During FY 2 (April 2011 to March 2012) there was an under spend of £380 K, most of which came from under spend on programming at country level (£905 K was spent instead of the £1.6 million budgeted). There was insecurity during this timeframe about whether the programme would be subject to VAT, however the VAT issue alone would not account for spending only 56% of the intended budget at country level. During FY3, to March 2013, there has been a £432 K over spend, comprised of: i) £1.4 million instead of £1.1 million spent on country programming and ii) slight overspend on technical staff.

Although Output 5 targets were met, this output was insufficiently stretching and a focus on only three countries fails to draw attention to: i) the large number of countries ICOSA is funded to support and the scale and scope of funds it was given to support them ii) the countries where ICOSA has been unsuccessful in influencing quality and speed of targeting and implementation. For example MDA delivery in Tanzania was delayed by 1 year; insufficient cover for maternity leave was a key reason for ICOSA’s lack of influence in this case. Zambia has also been proceeding behind schedule, albeit with a different set of circumstances and despite considerable effort on behalf of the Zambian country PM and the CNTD manager. By contrast, ICOSA provided considerable support to Malawi to prepare for MDA and progress has been strong, fuelling 30% of the update of ICOSA funded treatments to date. Mozambique is the source of another 30% of ICOSA funded demand for treatments, but the large and mature programme (reportedly, as the country PM did not respond to survey requests) has required little ICOSA involvement to accompany financial support. Zanzibar delivers 20% of ICOSA funded treatments and also has a well-established programme and strong support from a range of partners.

The table and figure below shows the difference between MDA treatments ICOSA expected to deliver[3] between June 2012 and March 2013 as compared with what was actually delivered.[4]
[3] ICOSA Second Annual Report January 2013
[4] ICOSA Mid-Year Progress Report October 2012 - March 2013

Table and Figure 1: June 2012 to March 2013 Planned vs. Actual SCH Treatments delivered
Country Planned % of total Actual % of total Difference / Cote d'Ivoire 3,026,719 17% 295,943 5% 2,730,776 / Liberia 440,719 2% 0 0% 440,719 / Malawi 5,600,000 31% 2,037,487 37% 3,562,513 / Mozambique 3,664,345 21% 1,819,000 33% 1,845,345 / Niger 0 0% 272,994 5% -272,994 / Tanzania 2,276,453 13% 0 0% 2,276,453 / Uganda 457,814 3% 0 0% 457,814 / Zambia 1,295,882 7% 0 0% 1,295,882 / Zanzibar 1,037,672 6% 1,059,318 19% -21,646 / 17,799,604 100% 5,484,742 100% 12,314,862

Actual MDA uptake was very concentrated - 80% to three countries (counting Zanzibar as a country). This level of concentration was clearly not the intent and it is worrying that the other 6 countries are well behind target. ICOSA is funded to work in 9 different settings, so the log frame should require more ambitious progress in all countries.

Recommendations:
- The ICOSA service offering needs to contract in some cases (where countries have existing capacity, programmes are mature and/or others are meeting their needs) and expand in other cases (e.g. to include managerial disciplines and standardised tools where programmes are new and/or capacity weak). A more customised approach needs to be taken to scale and scope of ICOSA support to countries relative to diverse needs. See also the recommendations under Outputs 1 and 3.
- ICOSA should provide projections of expected treatment delivery per year per country and it should report on actual treatments delivered per year per country. While recognising that the absorption capacity can shift as new data becomes available on treatment needs and/or country level delivery capacity, it is still useful to report on actual versus expected MDA in order to inform a discussion and draw attention to the factors making some programmes absorb more or less MDA than anticipated.
## Output 6 National programmes refined through M&E Results
Impact Weighting: 20%
Score: B

Output Indicator	Milestone by 2012	Status
6.1 No of countries achieving 75% coverage in target areas	3 countries	Achieved in 5 countries, according to reported coverage. Only Malawi has done validated coverage.
6.2 No of countries producing data using standardised protocols to measure health impact indicators	7 countries	Not achieved in Zambia and Cote d’Ivoire, and (due to paradigm shift to elimination) Group 3 countries also need to be revisited
6.3 No of countries producing data using standardised protocols to measure cost-effectiveness and efficiency of programme	2 countries	Achieved. Liberia and Cote d’Ivoire. Mozambique previously had data.

Indicator 1:
Reported coverage is a performance indicator. The WHO objective for control of morbidity is to reach 75% coverage of the eligible population in the targeted geographical area.

Milestone for 2012 is three countries reaching 75% coverage. This has been achieved in 5 countries, according to reported coverage. The intent was for coverage validation surveys to be conducted in selected countries within 3 months of MDA which will compare data reported by the health system with that reported by a sample of people. Only Malawi has so far conducted coverage surveys, although they were envisaged for Cote d’Ivoire and Liberia for early 2013.

During FY4 (2013-14), SCI plans to conduct coverage surveys in Cote D’Ivoire, Tanzania, Uganda and Zanzibar (funds for this have been included in country budgets). CNTD-supported countries are not yet planning to implement coverage validation surveys; they do not have the budget for it and this work was supposed to have been supported by SCI’s health economist. That post has been vacant for some time, so coverage validation progress has been delayed.

Indicator 2:
For health impact monitoring in Group 1 and 2 countries, standard protocols were developed, albeit with unresolved issues with WHO as described under Output 2. Sentinel sites have been randomly selected across intervention areas by the ICOSA team working with national governments. Schistosoma haematobium, S mansoni and STH prevalence and intensity are measured. Morbidity indicators include blood in urine and anaemia. Heights and weights are measured as an indicator of malnutrition and stunting. Baseline health impact data is collected prior to treatment and impact surveys are conducted immediately prior to the first and subsequent MDA rounds. When measuring health impact there will inevitably be confounding by a number of other interventions. The variety of different diseases being treated will all impact on height, weight and anaemia. However reduction of prevalence and intensity of SCH can be attributed to MDA.

Data collection is progressing at different stages in each country:

Group 1 and 2:
Cote d’Ivoire - Baseline data had not been collected according to milestone target
Zambia - Baseline data had not been collected according to milestone target
ICOSA supported baseline data collection in Malawi, Liberia and Mozambique. (NB: There were reported to be problems in the methodology used in Mozambique)
Tanzania and Zanzibar already had good historical baseline data available.

Group 3:
Niger and Uganda: M and E activities that were started 6 years ago have already shown the impact of long term control. In light of the new WHO elimination targets ICOSA is working with countries to revise the M&E protocols.

The target was baseline data to be available in 7 out of the 8 countries by 2012 and this target was not met, not only due to the change in programme objectives for Group 3 countries but also due to slippages in Zambia and Cote d’Ivoire.

Indicator 3:
The objective of collecting data on the cost element of the project is to provide management information at district level and to assist the development of sustainable programme implementation. ICOSA aimed to support countries to collect data to allow the estimation of: Cost per treatment, Cost of treatment by district and at programme level, Financial data by activity for manpower, transport, fuel and materials, Financial cost /person trained for different activities.

A data collection model was developed and tested in Niger and Uganda before ICOSA. It was expected that other countries would make their financial reports available within 3 months of MDA. Reports have been produced for Cote d’Ivoire, Liberia and Mozambique (with earlier data). The target was 2 countries by 2012 and this has been met by Liberia and Cote d’Ivoire, but the approach is still not finalised.

The approach taken has been to adopt an intensive research approach, rather than to use less labour-intensive and more sustainable accounting and financial management procedures. This work stream has been affected by planning and management issues. The approach needs to be better informed by programme managers, national managers, and advice on accounting methods, so that the availability of this data results in better budgeting, better management decision making, and therefore better value for money. Recommendations for this are considered in Section 6.

Recommendations:
- Coverage validation surveys should be carried out by people independent of the SCH health team and done promptly after MDA. CNTD countries need to be supported equally to SCI supported countries with regard to coverage validation surveys.
- SCI’s differences with WHO with regard to methodology for site selection for health impact monitoring need to be resolved.

The progress on additional indicators in the log frame update from May 2013 has been provided in Annex 10

3. ICOSA’s Contribution to Country Needs

The MTR team was asked to review how well the project is meeting the technical or management needs of countries given the different contexts. In this section, we will discuss the way ICOSA had envisaged supporting countries, as described in the bid and Inception report and as compared with country perceptions of support. We also discuss key issues that were flagged during country visits and interviews - capacity building, support to planning and budgeting, advocacy and influence, and community sensitisation.

## 3.1 The vision and the reality compared
In the ICOSA bid, the proponent states the intention to:
- Support countries with technical input into NSPs
- Help countries make linkages with WATSAN
- Engage in advocacy and sensitisation
- Help devise M&E plans
- Engage in operational research to guide the strategic direction of the programme
- Provide input to mapping, including use of parasitological methods and STH linked to geostatistical modelling
- Develop risk maps to determine prevalence at the smallest geographical implementation unit
- Support development of a country work plan
- Bringing national programmes together in regional groupings to share best practice and lessons
- Define the roles of each key player - district level officials, CHWs, CBDs, teachers – and design training agendas work with social marketing NGOs to develop IEC materials
- Ensure that messages which educate...on SCH...are developed (p. 15)
- Engage independent consultants for external assessment of quality and impact of IEC materials
- Conduct surveys after MDA to validate reported coverage rates (p.17)
- We will identify quantitative performance indicators to use at different organisational levels. This will support the annual review process and assist targeting of capacity building and TA
- Conduct studies on QALYs and DALYs
- We will use epicollect for our M&E questionnaires
- We will conduct resistance monitoring via the Schistosomiasis Consortium for Operational Research and Evaluation (SCORE) and Joanne Webster

The inception report carries along in the same vein. The language used suggests a rather active “hands on” role for ICOSA.

During MTR visits in 2 out of 3 countries (counting Zanzibar as a separate “country”), through telephone interviewers and through a standardised survey completed by 7 of 9 programme managers, the view of reality was rather different. In Tanzania, ICOSA has funded MDA delivery in two urban areas, full stop. In Zanzibar, ICOSA did slightly more, not only funding MDA delivery but also helping programme managers write their bid for the SCORE research grant but otherwise this established programme is operating fairly self-sufficiently in terms of technical resource. ICOSA took a more hands on role in Zambia, along the lines suggested in the bid and inception report, though in this relatively immature programme, the Zambian country PM would have appreciated even more support.

Seven out of nine[5] countries responded to a standardised survey instrument designed to gauge levels of support provided to various activities associated with NTD control. (See Appendix 5 for the survey instrument and the aggregated responses.) The two countries that did not respond to the survey were Mozambique and Cote d’Ivoire. Countries were asked to rate the degree of support provided to different activities falling under 5 categories: policy and strategy development, support to mapping, managerial support, communications and sensitisation support, support to M&E. The following scales were used:
[5] Zanzibar has been counted as separate country, given it is administratively separate to the mainland and the epidemiological profile and control strategy is quite different as well.

0 = No ICOSA support at all for this activity (neither funding nor technical support)
1 = ICOSA (SCI or CNTD) provided funding only to this activity. We had the technical expertise in house and/or relied on WHO or other partners and did not require assistance (other than funding) for this particular activity
2 = ICOSA staff (SCI or CNTD) provided some limited technical assistance or advice, e.g. brief discussion every few months
3 = ICOSA staff (SCI or CNTD) provided more substantial technical inputs into this activity, e.g. monthly communication and responsive support to deal with challenges we encountered
4 = ICOSA (SCI or CNTD) provided essential technical support, without which the activity would not have moved forward as well or as quickly. We were in communication almost every week and ICOSA helped us with the detail of implementing the activity (possibly also through funding local TA)

Table and Figure 2: Country perspectives on support offered by ICOSA: aggregated results (see Appendix 5 for detailed scoring by activity)
Strength of contribution 0 1 2 3 4 / Policy and Strategy Development 4 11 7 18 2 / Support to mapping 6 6 7 7 9 / Managerial support 2 4 9 12 8 / Communications and sensitisation support 1 5 2 12 1 / Support to M&E 2 4 3 7 5 / 15 30 28 56 25

Each country (7 respondents) was asked to provide a score for each sub-category under the 5 programme areas. There were 22 sub-categories in total, so each country had a total of 22 responses to place in contribution category 0 through 4. Thus, there were 154 total responses and the table and figure above shows how these were distributed. The respondents were told that their responses would be shared with ICOSA only in aggregated format. Approximately half of the responses were in category 2 or lower, meaning that ICOSA staff did not support that activity, funded the activity with no technical input, or provided some limited technical assistance or advice, e.g. brief discussion every few months. Had Mozambique and Cote d’Ivoire responded to the survey, their responses would have likely skewed the results even further towards the lower ICOSA contribution figures, as these countries reportedly do not accept much support from ICOSA.

Low levels of ICOSA contribution are not necessarily a negative, as the level of assistance a country requires will differ according to capacity and maturity of the programme, for instance, and how well other groups are meeting the country’s technical needs. WHO has been gearing up the past several years to produce technical guidance and WHO AFRO has become more hands on with support, for example, helping countries pull together their strategic plans, budgets, procurement estimates. Some countries explicitly state that WHO is the group to whom they refer, and to whom they should refer, for technical guidance. There is also quite a lot of support provided in countries where USAID is active, for example in Tanzania, where USAID funds three FTEs to help the integrated NTD programme.

However, low levels of ICOSA contribution are a negative if some countries actually would benefit from further support and are not receiving it. Three observations are noteworthy here: i) ICOSA has ended up being heavily reliant on 3 countries to take up 80% of treatments – Mozambique (30%) and Zanzibar (20%) have not had very intensive support from ICOSA, while Malawi (30%) has. Could more intensive support to address bottlenecks in other countries have allowed increased distribution of treatments in the remaining 6 countries only taking up 20%? MTR country visits suggest the answer is yes. ii) Three countries took the time to offer qualitative feedback on whether the support provided was adequate, insufficient or excessive. All three countries noted that technical support had been insufficient in some areas, implying that needs were not being met. iii) If plans are to continue the current scale and scope of support, then – given that ICOSA’s involvement in supporting countries is markedly different than the level of support implied in the bid and in the inception report – this in turn has implications for the staffing needs, as will be discussed in Section 6 and value for money Section 4.

Based on these findings as well as country visits, the MTR team advises that the scope and scale of technical assistance offered by ICOSA will need to shift in light of varied country needs and considering the shift in what others are providing. For example, the Zambian NTD PM did have some technical needs with regard to conducting coverage surveys, but the programme’s immediate needs were rather more managerial and related to systems/processes and tools, for example:
- The country PM would have benefitted from more support to the budgeting process
- The supervisory model for the MDA delivery had not yet been worked out at the time of the MTR visit, whereas this should have been worked out at the budgeting stage. Neither the PM nor the TA were able to explain why 5 trainers from central level would be required nor how the number of training supervisory days (the key cost driver) could be justified.
- Support to the development of a GANTT chart and timescales: The review team visited in early September and the MDA delivery was due to take place end of September, yet the cascade training had not yet started. Presumably two day training needs to be timetabled into people’s diaries at least a month in advance.
- Supporting training of the government accountant in ICOSA reporting systems: The previous accountant had received 1 week of training from CNTD but he was replaced and CNTD was not aware of this. The former trained accountant did not pass knowledge onto the new government accountant. During the MTR visit, several accounting discrepancies were identified. CNTD cannot release further funds if the accountant does not follow procedure for accounting for previous spending, so this can have programmatic effects. Page 8 of March ‘13 progress report “The project will retrain both managers and their accounting staff at all levels in a practical manner to facilitate account and activity reconciliation.” So the need is recognised but the implementation has yet to happen.
- Support to logistics: It was only during the review team’s visit that the PM met with the head of medical stories and began to appreciate constraints in the medical stores with regard to stock turnover and allowing delivery to districts and what this in turn would mean for the drug ordering schedule and timetable for calculating procurement needs and ordering.
- It was also clear that this relatively new programme would have benefitted from franchise-like standardised management models to draw on, so that quality of communications is maintained throughout the training cascade and quality does not get diluted as one gets further from the centre. For example:
  - a map showing “stations” and process of a standard MDA delivery campaign
  - a standard training module to train people at district level, teachers and health workers on all aspects of the MDA (logistics management, financial management and reporting, M&E framework, BCC messages with enrolled and non enrolled SAC). NB: IMA (USAID funded via RTI) reported that they have such a training module in use in Tanzania and perhaps in other countries as well.
  - a teaching package aimed for use with SAC by teachers and health workers with visual materials and (adaptable by age) and standard teaching messages.
- Some of these materials may be already developed by WHO or USAID contractors, in which case ICOSA would not need to reinvent the wheel but could facilitate their dissemination and adaptation in the field.

## 3.2 Capacity building
The 2011 and 2012 ICOSA Annual Reports offer little information about ICOSA’s capacity building strategy and activities/support provided to counties. SCI’s capacity building emphasis historically has been on the dichotomous choice about whether to have expatriate presence in country vs. UK based staff who visit countries on a needs basis. This appears to be overly supply side focused, i.e. where do we best situate our people? The MTR team recommends that a more strategic demand-led approach should be taken, including a participatory process to identify capacity needs and the best ways to meet them, followed by skills training (technical and managerial skills as well as process development); action learning/practical skills application with coaching, and change management (implementation/use of new skills and capacities).

With regard to a specific issue - data analysis - which was identified in the March ’13 progress update as a major bottleneck to timescales - the new strategy is discussed of “moving to generate more capacity in programme staff and increase sustainability of country programmes by moving data analysis within country instead of outsourcing it.” In the MTR team’s view, the argument that doing manual data entry builds country capacity is not very convincing, unless there is some strategic iteration between the data entry and data quality checks or validation, which would be missed if the data processing were outsourced. The consequence of the move to have the data entered locally has been increased costs and delays. It is suggested that this strategy be revisited as there needs to be a balance between getting the programme moving in an efficient manner versus apparent capacity building efforts.

## 3.3 Support to planning and budgeting
Rationale planning and implementation would be improved if countries could secure 3 year MoUs with ICOSA, with an agreed budget linked to a plan. Just as the ICOSA country managers need to be empowered to do their jobs unencumbered by unnecessary contract approval processes, the country PM also need to be empowered to do theirs. They need to know multi-year budget ceilings, so they can plan ahead – how many provinces, what cost per head? Effective planning will allow them to optimise their budget and to have a vision to integrate NTD control efforts with each other and into the health system, where it is justified. The development of a Memorandum of Understanding is proposed below.

## 3.4 Advocacy and Influence
ICOSA staff do not uniformly see themselves in an influencing/managing change role, but it is argued that this is an area where the UK based technical team could be adding further value – as change agents themselves (having an influencing role) as well as supporting others within country in terms of their influencing agendas - at individual, organisational and systems levels.

The CNTD country manager for Zambia does seek to influence change; in Zambia meetings, it was clear that she had planned her agenda and what she wanted to influence before the meeting. For example, in a meeting with the Ministry of Education, she assertively conveyed the need for, and benefit of, having NTD related health, education and sanitation messages integrated into the curriculum. She had also clearly developed solid relationships with in-country programme staff, based on frequent visits and empathy with local staff needs and capacity. Given the role of the political economy in NTD and health programmes in general, having relationships with country based change agents is key.

By contrast, during the visit to Tanzania, the SCI country manager acknowledged directly to the Tanzanian PM that she had not been able to visit often enough and it was clear that relationships were not strong overall between SCI and the NTD programme. In response to reviewers’ observations about the hands off approach taken in Tanzania, the SCI country manager opined that this was appropriate given the strong local ownership of the programme and complications brought by programme’s integration strategy. But what became clear during the visit was that there were missed opportunities for making the programme more responsive to health need (e.g. targeting the northern lakes regions where SCH prevalence is highest), and missed opportunities for supporting the country’s technical needs and issues. Some examples of challenges the country PM acknowledged as technical needs SCI might be able to help her with included:
- appropriateness of sentinel site sampling procedure
- schedule of monitoring with regard to programme issues and affordability
- need to share experiences with Niger, Burkino Faso and Uganda with regard to reaching adults at risk
- whether 30 or 50% prevalence should be the trigger for adult treatment
- feasibility of mapping for LF before treating for LF, as was done in Mwanza with CNTD support, but in contrast with WHO guidelines).

The Tanzanian PM presented these technical needs at a meeting held during the MTR and it was clear that the SCI team had previously been unaware of these needs. Similarly, it was clear that the in-country technical assistance, housed in the school health programme and funded by ICOSA, had been side-lined from the NTD programme. The reviewers think this is likely due to a variety of reasons, not only her recent ill-health. Her presence at local NGDO meetings was described as “infrequent” and her role “opaque” and during conversations with the MTR team she seemed fixated on problems created by the new institutional structure implemented as part of the integrated NTD approach and on how institutions should ideally be organised – not a battle she will likely win.

Country PMs may be more open to ICOSA technical support as well as influence if time is taken to build relationships and understand needs; this involves committing the time and being customer-focused. ICOSA is already supporting change and capacity strengthening through training and the offer of technical assistance. It could further support change through coaching (e.g. sitting down to work on a GANTT chart collaboratively with the in country team, helping discuss through the steps of what needs to happen by when) and through provision of management tools that will support country work (examples are offered under 3.1 comments on Zambia visit). The MTR team witnessed one successful influencing event in Tanzania when the SCI country manager started to think aloud (in front of the NTD team) about the critical path leading to the first SCH MDA in the priority Lake regions. By thinking aloud through the steps, the SCI country manager exposed lack of congruency in the NTD team’s plans, indirectly showing them that what they planned would not be likely to be achieved unless they made changes to their plan. These are the kinds of “coaching” conversations that need to happen more often.
### Recommendations
- Before country visits, ICOSA should draw up TOR, setting out the objectives and activities, including the influencing and advocacy agenda.
- ICOSA should work with national NTD programmes from an early stage to define mutual expectations and requirements, and develop multi-year work plans and budgets. This should all be reflected in the agreement of a Memorandum of Understanding spanning the life of the ICOSA programme.
- ICOSA should be accountable to national programmes for punctual delivery of resources agreed in accordance with these plans, whether these are technical assistance, materials, or finance.

4. Value for Money and Sustainability

Reviewers were asked to assess the efficiency and effectiveness of the programme, its sustainability and its value for money. Standard value for money dimensions include economy, efficiency, effectiveness and equity.[6] The value for money dimensions are interdependent, for example, evaluating costs in relation to treatment numbers can produce incentives to boost the denominator, at the expense of appropriate targeting for maximum health impact. Similarly, cost cutting to achieve economies can have inverse effects on community sensitisation spending, which otherwise improves PCT uptake and health impact.
[6] www.nao.org.uk/sectors/third_sector/successful_commissioning/successful_commissioning/general_principles/value_for_money/assessing_value_for_money.aspx
## 4.1 Programmatic Value for money
Economy and Efficiency: The £25 million GBP under Phase 1 is divided into £10.5 million to SCI for programmatic implementation and £14.5 million to Crown Agents for procurement of vehicles, computers, other equipment and PZQ. Of the £10.5 million for programming, £4 million is allocated for central management costs and overhead at CNTD and SCI.

Country-focused expenditure: The remaining £6.5 million goes towards costs associated with MDA delivery in countries. There has been considerable scrutiny around the £6.5 million, development of a cost monitoring protocol over the first two years of the programme, piloting the cost monitoring protocol in Liberia Cote d’Ivoire and Mozambique, and eventually reporting on costs per treatment delivered in these three countries (March 2013 ICOSA progress update). Analysis of expenditure across the three countries revealed highest cost areas related to per diems and allowances for training (>50%) and implementation (>20%). Plans for how this data would be used, e.g. to inform delivery model adaptation and budgeting discussions between ICOSA staff and PMs, has not featured in ICOSA reports nor in discussions and it remains unclear how the research will inform policy and practice.

In May ’13, an indicator was added to the new log frame to track the implementation of the cost monitoring protocols in countries. Progress in this area has been slow, and may be further hampered by staff continuity issues with the departure of SCI’s health economist and some contention as to the appropriateness of the methodology to informing management decisions and budgeting as opposed to informing academic publications. The table below summarises data available on country delivery cost and we can see that the costs compare favourably with the cost of vaccinations ($0.45 for polio) or treatment of other NTDs.

Year of study	Country	Cost including drugs (USD)	Delivery cost only, excluding drugs (USD)
2012	Mozambique		$0.10
2013	Cote d’Ivoire	$0.64	$0.42
2013	Liberia	$0.47
2004-2006	Niger	$0.47 = school-based $0.41 = community based
2003-2006	Uganda	$0.54 school based

However it is difficult to conclude much else from the data above, given different years of publication, different methodologies for cost inclusion and allocation, different country contexts. Even amongst the three studies conducted recently and with the same methodology for cost accounting, there is little similarity between costs. We know that the programmes in Mozambique, Cote d’Ivoire and Liberia differ from each other in important respects, not only scale and maturity, so this is not terribly surprising. Data from more countries and analysis of contextual detail will be required before we can draw conclusions. One thing that is clear from the data above is that ICOSA has an incentive to maintain operations in countries like Mozambique, with a large scale at a low cost per treatment delivered. This in turn gives the Mozambique PM considerable power over ICOSA, which may explain why the Mozambique PM has been shirking on financial and treatment reporting duties.

The potential for integration of ICOSA activities with other programmes having similar communication and education needs, delivery channels or M&E needs offers further opportunities for cost sharing and gaining efficiencies and greater effectiveness. This subject – what opportunities have already been leveraged and what opportunities could be further seized - is covered in Section 5.

Central level expenditure: DFID receives a monthly invoice with an aggregate amount charged to i) a lump sum fee for management personnel and ii) a lump sum fee for technical personnel. There are no systems to track central level costs by country, expenditure categories, project outputs. The bid document and inception report provide a work programme and a costing of staff, but no links between the two which would justify the time allocation of staff proposed. The budget should have been justified in a bottom up manner, estimating how much time it takes to perform the different functions envisaged and therefore how the time allocations proposed would be justified according to the maturity and capacity of different country programmes, how much support each requires from ICOSA staff, how economies would be achieved as the programme goes to higher scale. In the absence of this level of detail, it is impossible to ascertain whether the central level resource spend is being used economically and efficiently, and thereby providing value for money. Going forward, better value for money may be achieved if ICOSA explicitly decides with a country that it will i) only provide funds (in exchange for health impact data), ii) provide funds with managerial and financial systems support rather than technical support or iii) provide a fuller scale package (well-defined and tailored to each context) of managerial, financial and technical support. These options might also place countries more squarely in the driving seat of the support they are receiving.

Recommendations
- ICOSA should provide a bottom-up justification of its management and technical costs, showing the time and costs of staff and their relation to the work plan. It should show how it is optimising the use of staff with appropriate skills and experience.
- ICOSA should transfer greater control of funding to national programmes, subject to management capacity and fiduciary risk; national programmes should have more control over TA budgets, allowing them to source technical assistance from ICOSA or elsewhere.

Effectiveness: In the short term, effectiveness can be defined as having health impact. Health impact is a function of effective targeting (further a function of outputs 1 & 2[7]), effective implementation/delivery (output 5[8]) and then individual compliance with actually swallowing the PCT. It is also a function of good quality PZQ (output 4[9]). Longer term, effectiveness is a function of less tangible issues like government capacity built for mapping, planning, delivery/implementation and M&E (Outputs 3, 5 & 6[10]) as well as developments in Water and sanitation and behaviour change (and in the shorter term, ICOSA’s linking in with WATSAN).
[7] ## Output 1 Countries selected and project implementation plan finalised. Output 2 Priority areas selected by mapping of infected populations
[8] ## Output 5 Project countries implement MDA for schistosomiasis and soil-transmitted helminths (STH)
[9] ## Output 4 Drugs procured and delivered to countries
[10] ## Output 3 National Strategy plans developed in selected countries. Output 5 Project countries implement MDA for schistosomiasis and soil-transmitted helminths (STH). Output 6 National programmes refined through M&E Results.

Country visits revealed a concern in several settings that the cost focus and constant budget trimming (which resulted partly from the VAT debate and belief that the overall budget would be reduced) may have had repercussions on quality of MDA delivery. The ICOSA team informed DFID that it could deliver the same number of treatments with the VAT reduced budget, because SCI would pitch in some of its discretionary funds to cover the difference. In fact what was happening was countries were being squeezed – asked to reduce their budgets but not their treatment numbers. In Zanzibar for example, the community sensitisation budget had been cut back to untenable levels as a result of ICOSA having less funds due to the VAT issue. This cut back was surprising, given the recognition (as with polio) that needs for community sensitisation increase in low-endemicity settings (people start to recalculate the risk/benefit ratio of treatment and feel they can do without). Post MDA focus group discussions funded by SCORE showed the result of insufficient community sensitisation; community members said they did not take the medicine because they did not know the CBD “he’s not a health worker” or they said they did not see the point of taking the PZQ as “I’m not going in the river. In Zambia, the PM was similarly asked to decrease the budget twice but without decreasing treatments delivered. The PM has been concerned that cost formulas from countries with more concentrated populations, more mature programmes, and lower per diem rates (these are government mandated and not under the control of the PM) did not apply to the Zambian setting. She fears that the forthcoming September MDA might have taken cost cutting a bit too far and wonders if she should have negotiated harder for a reduction in regions covered rather than reducing the budget. Certainly it was clear that the PM and her ICOSA-funded TA would have benefitted from collaborative support to build the budget bottom up, trying to understand who is best placed to deliver the training at different levels of the cascade and how many days would be required at each level given the length of the training and travel time. The current budget was built by the ICOSA funded TA based on what he thought were comparable programmes in immunization campaigns. Per diems for central supervision of training were a major cost driver of the budget, yet it became clear during the MTR visit that the estimates in the budget did not directly match the work plan.

Targeting: Choosing countries with high prevalence and large hitherto untreated populations is a key parameter in achieving the highest health impact per pound invested, enhancing effectiveness. Could ICOSA have got better VfM by targeting different countries? The table below shows the disease prevalence and treatment need of ICOSA countries as compared with two countries ICOSA could have instead chosen for Phase 1, Ethiopia and DCR. The table does not show how well the treatment needs are being met, for example by other funders. Ethiopia and DRC have similar prevalence to other countries in ICOSA’s portfolio but a massive volume of need which has been relatively unmet by other funders. Arguably, ICOSA could have provided more value by targeting these countries with unmet MDA and technical needs during Phase 1. However, there are tensions between maximising health impact and achieving long-term sustainability. If the priority is long-term sustainability, then the choice of countries might be skewed towards Group III countries like Niger and Uganda (or Zanzibar), where there is a possibility of eliminating SCH as a public health problem. If the priority is achieving the greatest short-term health impact, then Group I countries with the heavy infections and low treatment rates might be prioritised, even though operations in these countries may be more challenging. In the end it is hard to criticise ICOSA’s choice of countries, as a number of factors needed to be balanced, not only unmet disease burden, but also the entire budget envelope relative to size of need and also the balance between a sustainability emphasis on Group III countries focus or an impact focus on Group I countries.
As reviewed previously under Output 5, the actual vs. projected allocation of MDA treatments has been rather more concentrated than expected – 80% to three countries – and this raises some questions about whether actual practice is following strategic choice and intent with regard to allocations for maximum health impact.

Country	Prevalence[11]	Annual numbers requiring treatment[12]
Uganda	25%	8 mn
Zanzibar	20%	“Unknown” according to the WHO Strategic Plan 2012[13]
Niger	15%	5.3 mn
Zambia	32%	4.3 mn
Tanzania	36%	9.5 mn
Cote d’Ivoire	40%	3.7 mn
Liberia	55%	1 mn
Malawi	47%	6.4 mn
Mozambique	55%	12.8 mn
DRC	28%	17 mn
Ethiopia	32%	21 mn
[11] From "GBD Estimation Strategy Report for SCH", Report to Expert Group prepared by Rashmi Jasrasaria, Chris Murray, Mohsen Naghavi.
[12] Annex 4, Schistosomiasis Progress Report 2001-2011 Strategic Plan 2012-2020, WHO 2012
[13] The ICOSA Inception report May 2011 also does not provide an estimate of health need nor of MDA treatment numbers it intends to supply to Zanzibar, as Zanzibar is bundled together with mainland Tanzania in the estimates

Effectiveness also relates to choosing the areas within a country where prevalence is highest, which is ensured through burden of disease mapping and consequent targeting. ICOSA has funded mapping work in all but two countries (which already had mapping data) and in a few cases, ICOSA is doing more than funding the mapping by contributing expertise to the mapping exercise. Guidance for mapping and how to translate mapping results into MDA implementation at country level is provided by the WHO Strategic Plan for SCH; this advises on which operational choices are appropriate in different country contexts with different NTD goals, most appropriate target populations and distribution channels, treatment intervals, and complementary water and sanitation interventions. As mentioned previously, ICOSA was unsuccessful in influencing the government to target all the areas with highest SCH disease burden in Tanzania. There have also been issues (as yet unresolved) about mapping protocols and sentinel site selection and whether to randomise blindly or try to account for the focal nature of the disease. ICOSA has offered different advice vs. WHO and many ICOSA countries have been mapped following ICOSA advice. It is as yet unclear whether this advice will prove to be problematic when it comes to determining baseline prevalence and impact from MDA. Discussions with WHO are ongoing on this issue and countries are in limbo (Tanzania) or are proceeding with work anyway according to the best judgement they can make (Zambia).

Effectiveness also depends on central government commitment to control SCH and STH; this is a key criterion in the selection of countries ICOSA works with and it is monitored in the log frame as evidenced by the country having included SCH and STH control objectives in their National Strategic Plan. However, the quality of plans and their implementation is variable, as is the resource the government provides to NTD strategic and planning capacity at Ministry level. Some programmes (e.g. Liberia) have a substantial team involved in NTDs while others (e.g. Zambia) have one person covering NTDs, as well as all communicable diseases and even non-communicable diseases as well. One aspect that perhaps has not been fully appreciated is the extent of in-kind funding governments provide to these programmes; the value provided in drug logistics alone – ordering, clearance from the port, storage, delivery - can run into millions of pounds. Despite these signs of government commitment, the MTR team’s assessment is that a more proactive approach by ICOSA was needed to advocate with government, shape strategic plans and influence their quality and implementation.

Health impact is crucially dependent on whether the PCT distributed is actually taken up by the target individuals. Methods of understanding and ensuring compliance include directly observed therapy (DOT), research into KAPs using focus groups or anthropological/social science methods, coverage validation surveys. When the delivery is school-based, MDA for NTDs uses directly observed therapy; the teachers observe the pupils taking the pill in school-based distribution. However, the pupil can still hide the pill in their cheek or simply not attend the school on distribution day. Community based distributors may also directly observe in community based programmes or (as in Zanzibar) the CBD may leave the correct number of pills with the head of household to give to other family members when they return home. In most settings, compliance has not been a significant issue so far, as the programmes are relatively new and there is demand, especially in settings of high prevalence. But as the programmes mature, prevalence declines and communities start to feel SCH risks are lower, compliance issues may arise. (See previous comments on post-MDA focus group results in Zanzibar.) Stakeholders agree that there are questions around understanding compliance and the evidence needs to improve, and, consistently, the ICOSA bid had intended to incorporate relevant anthropological and social science research. However, the only work ICOSA is funding at present has been in Malawi - the standard coverage protocol used to quantify and validate the coverage in the national target group and some KAP work.

Equity: A key issue in terms of equity is how the project is reaching children not in school and other high risk groups. A community based approach, as well as school-based MDA, is the appropriate response.[14] However the strategies being deployed in various countries vary and in Zambia for instance, there was no clear strategy for reaching out-of school children and this was also the case for other ICOSA-supported countries. Reaching out of school groups is more difficult, more expensive, and more risky (e.g. higher risk of empty stomachs - which increases the risk of side effects - and a less controlled environment for post MDA side effect monitoring). Nevertheless it is necessary as a means of reaching adults likely to be suffering most from the disease and reaching more women and children (including girls who are more likely to be out of school).
[14] http://gnntdc.sabin.org/files/press_releases/Community-directed_vs_School-based_treatment_Tanz.pdf
For SCI’s standard coverage survey protocol (as yet only implemented in Malawi) villages or communities have been chosen as the sampling unit to ensure all school age children have a chance of selection regardless of school enrolment. This allows SCI to estimate the proportion of all school age children treated. The coverage survey also determines gender-specific coverage and collects key information on why people do not take part in MDAs. During FY4, there will be coverage surveys in Cote D’Ivoire, Tanzania, Uganda and Zanzibar (funds for this have been included in their budget). CNTD-supported countries are not yet planning to implement a coverage validation survey.[15]
[15] The health economist’s role in the CNTD countries was to provide the technical assistance on protocol and budgetary guidance, whereas that role was covered in the SCI countries by SCI programme managers. CNTD workplans and budgets for this year had to be developed without the health economist’s input, given her departure. Rather than hold the contracting process back until a new health economist was in place, the plans and budgets were agreed to as they stood particularly in light of the fact that treatment is not taking place until the last quarter of this calendar year. The idea was that this would give ICOSA time to either have a newly recruited health economist, or for CNTD to address this gap. Given delays in recruitment, ICOSA has started to pursue the latter. Funding will be made available for the surveys either from the unrestricted funding available at SCI (which is already backstopping activities for this year) or from the additional DFID funding if it is online when required.
### Recommendations
- ICOSA should implement a transparent process for budget scrutiny based on VfM criteria of economy, efficiency, effectiveness and equity.
- Budgets should be matched to work plans that optimise efficient and economic use of staffing, transport and other resources
- Activities required for sustainable and effective delivery should not be cut where this jeopardises effectiveness and sustainability. Activities such as development, training, sensitisation, and monitoring are generally core requirements for service delivery.
- ICOSA work plans should include adequate investment in relations with government and other local stakeholders to build partnership working and long term sustainability.
- Work plans and budgets should address hard-to-reach populations, such as out-of-school children and adults at high risk, even though this may increase average cost.
## 4.2 Programmatic Sustainability
Programmatic sustainability is a function of value for money (including health impact over time as the effectiveness variable - discussed in previous section), country ownership, capacity building, and contribution to global public goods (knowledge) with which all programmes can be improved.

With regard to contribution to global public goods and evidence, there are many issues that came up in interviews and during country visits which need stronger evidence, for example:
- transitioning from control towards breaking the transmission cycle
- Use of more sensitive diagnostics in low prevalence settings
- the optimal frequency of MDA, especially where prevalence has dropped below 10% either because of previous treatment or because of low endemicity.
- the debate about choosing sentinel sites based on the foci of SCH rather than choosing randomised locations (NB: ICOSA has advised to follow the latter course whereas PMs are concerned SCH will be under-reported with this method and it appears to be out of alignment with WHO recommendations)
- social science research into KAPs, compliance, engaging communities
- cost effectiveness and ways of working with WATSAN
- Motivating and managing volunteers/community based distributors (CBDs)
- Operational questions around targeting and delivery to high risk adults and out of school children
- Risk management with regard to community based distribution and less control over feeding and post-PCT observation and monitoring; receiving PCT on an empty stomach may increase likelihood of side effects and these are less likely to be monitored and managed outside the school based setting. PMs in at least 4 countries interviewed had concerns about this.

In general, country PMs and other stakeholders were aware of WHO guidance but stated implementing the guidance in practice sometimes became an issue when financial or programmatic constraints meant that the guidance could not be followed precisely. This is where ICOSA staff should be able to provide some value, but in some of the countries surveyed, ICOSA advice is not being fully leveraged or it is not consistent with WHO guidance (as in the sampling issue with regard to mapping and sentinel sites).

Operational researchers funded through SCORE, the Children’s Investment Fund Foundation (CIFF) and other programmes stated their appreciation for the support from SCI and CNTD and the opportunity to “piggyback” operational research onto ICOSA funded MDA. However, there was some contention about the balance between academic publications versus making available what (is perceived to be inappropriately guarded) data SCI has already, more speedily for the benefit of public health policy and programmatic improvement. Stakeholders also report that SCI’s previous behaviour with regard to IP around publications has affected relations in some countries. However, the fact that complete datasets from mapping surveys are shared with the Global Atlas of Helminth Infections (GAHI) http://www.thiswormyworld.org/) seems to be a positive step in promoting global public goods; this is an open access information resource on the global distribution of SCH, STH and lymphatic filariasis (LF).

With regard to sustainability through country ownership and capacity building, ICOSA states that it has a philosophy of avoiding expatriate presence in country, preferring to fly expert staff into country for weeks at a time. As mentioned elsewhere in this report, adhering to a strict philosophy may not be flexible enough to meet diverse country needs; funding staff (not necessarily expatriate staff) to support the programme in country is not necessarily a detriment to country ownership and capacity building. It really depends on how the support is implemented and to what degree the country is in the driving seat. There is a view that the current model gives countries more ownership but in reality countries had little input in the ICOSA business case process[16] and in at least one country, Tanzania, they do not appear to have much say in what support they receive from ICOSA either.
[16] For example, some countries might have preferred to receive funding directly from DFID while getting technical support from WHO. Other countries might have preferred the Nigeria model whereby funders are allocated regions in which to support integrated NTD control.

### Recommendation
ICOSA funding provides the MDA platform onto which can be leveraged for operational research. Where data is generated which has public health value, the priority should be timely release of data into the public domain, and as allowed for by data ownership agreements with countries and in support of global public goods. National programmes should have more control over technical assistance budgets, allowing them to source technical assistance from ICOSA or elsewhere.
## 4.3 VfM and sustainability of Output 4: PZQ Supply
Crown Agents (CA) has been very positively reviewed by all stakeholders. They have been described as responsive and efficient in meeting programme needs.

One example of CA securing cost savings was documented in the March 2013 progress report. Crown Agents sought comparative quotations from the freight agent (Greenshields Cowie) securing substantial freight savings on many of the ICOSA contracts. For example a saving of approximately $51,000 USD was secured for the project on the cost of shipping PZQ when compared to the supplier’s original freight quotes. CA achieved significant savings on microscopes as well by sourcing outside of the standard nominated agents. Costs have been maintained on many other items including urine filters, Kato-Katz kits, weighing scales and height poles, Hemocure analyzers and the majority of the laboratory consumables. Although end users in Liberia claimed that the vehicles procured by Crown Agents were not fit for purpose given the difficult road conditions, the vehicles were purchased in accordance with EU procurement directives, as is the requirement with all goods purchased through CA.

Approximately 80% of the £14.5 million GBP channelled through CA goes towards PZQ purchase, so PZQ price is a major cost driver of the programme. International stakeholders including WHO had been advocating for increases in the quality requirements of PZQ, given unprecedented scaling up of treatments expected to be delivered. This resulted in an agreement that DFID funded purchases should be approved by a WHO Expert Review Panel (ERP), regardless of whether the supplier’s PZQ had already been reviewed by a stringent regulatory authority. The ERP process[17] delayed the start of PZQ procurement and after a 15 month process starting from December 2010, only 2 PZQ suppliers ended up being accepted into active framework agreements for ICOSA, while 5 are non active framework holders, who would require additional work to their dossiers to meet the full requirements.
[17] The ERP technical review was an additional step in the procurement process and slowed down issuing PZQ framework contracts. Some of the delay was attributable to the length of time that it would take for suppliers to provide the requested information to the ERP team.

The PZQ price paid by Crown Agents rose by 25% between Years 1 and 3 of the existing ICOSA programme. It was not possible to get access to benchmark prices due to confidentiality. Agents procuring with USAID funds have a wider supply base due to the fact that they are not restricted to ERP approved suppliers (though approval by a stringent regulatory authority is required) and one agent registers their own label in countries, allowing them to source from multiple suppliers to fill that label. However, the unpredictability of USAID’s funding, restricted to annual budget allocations, is negatively perceived by suppliers. Information on how these factors balance out, in terms of prices paid by USAID agents, is unavailable.

Given the fact that the current programme relies 100% on procured product, it is very sensitive to even small price changes in PZQ. Approximately 35% of ICOSA Phase 2 will be procured by CA, while 65% will be obtained from donated supplies from Merck Serono. Therefore there will remain a requirement for purchased PZQ for ICOSA 1 and 2, and the programme remains at risk from dependence on a small number of suppliers (currently only 1). If the most competitively priced supplier increases price or exits the market, or for supply security reasons it is deemed appropriate to split tenders among suppliers, then Crown Agents may have to pay a higher overall average price, thereby reducing the tablets procured, and thus, the number of people who can be treated. Thus this area remains a key risk for the programme.

Better economies can be realised (theoretically) through decreased prices of PZQ, but reduced prices are unlikely to be achievable in the current market environment given i) suppliers are being asked to make investments to achieve WHO ERP approval and ii) only two suppliers gained ERP approval, and only one of the two approved sources has actually supplied the programme. Thus the programme is not only at risk of price increases but it is also at risk of supply insecurity. The ERP process is slightly different than the standard WHO PQ process, as a discrete group, with a limited budget and timeframe, was called together to approve the PZQ suppliers for the DFID programme. It was recently announced that PZQ will now be eligible for approval under normal WHO PQ process, with two benefits i) more flexibility for ongoing approvals, if changes to the API occurs, and ii) WHO PQ is more high profile than ERP.[18]
[18] The ERP exercise is not in the public domain therefore other supply organisations would not be able to piggy back on the information.  The WHO PQ scheme will be public knowledge and therefore the list (as per the Pre-qualification list used by the Global Fund to Fight AIDS, TB and Malaria) would be available for all to use, which may have benefits to suppliers in terms of marketing their quality assurance status.

Crown Agents has made some proactive approaches to suppliers, e.g. holding discussions with Hetero to try and diversify the supply base. More could be done as well to secure the interest of current suppliers. During reviewer interviews with the two suppliers who had been approved, these suppliers were unaware of expected PZQ volumes the programme would be expected to procure over time – a key “pull” that could be used to maintain their interest in the programme, especially given these will scale up during Phase 2. This information could be shared with suppliers (after all, it will go public when the new business case for Phase 2 is published) with the caveat that CA cannot guarantee which proportion of the overall demand will be allocated to individual suppliers, nor can the timing of demand be assured as it relies to a degree on country capacity for scale up. Even without such guarantees, the fact that the money is ready and waiting to procure and investments are being made to build country capacity for delivery should prove to be attractive to suppliers.

The BMGF plans to update a market study into PZQ in 2014. This may or may not coincide with decisions Crown Agents will need to make for Phase 2 – how to approach the market strategically with the aim to lure in additional suppliers. While approaches to Hetero could be fruitful, it is suggested that attention be given to companies whose product has already been registered in many African countries, so although the company’s dossier would still need to pass the PQ hurdle, at least the in-country registration bottleneck would not slow things down. EU directives prevent CA from guaranteeing a purchase volume to a supplier, however if the actions recommended (Section 8) do not yield any new applications to PQ, then other options may need to be considered. For example, independent agents can communicate more intensely with suppliers to understand their needs/help them overcome bottlenecks (push strategies), or it might be possible for BMGF to engage in some innovative financing options (e.g. advanced contracting - “pull” strategy) to strategically shape this market.

The reliance of the project on purchased drug, at least for Phase 2, has been reduced by the expansion of the Merck Serono donation programme to WHO, formally agreed in February 2013. Merck Serono stipulates that their donation is only targeted at SAC and also that their donation should be sole supply into the countries accepted. This presents a certain rigidity which may not be compatible with ICOSA’s health impact aims nor with a country’s best interests. The issue remains unresolved and reviewers understand that negotiations between WHO and Merck Serono are ongoing.

Crown Agents has been asked to deliver on a “carriage and insurance paid” (CIP) basis. SCI clears the drugs except in Zambia, where the Medical Stores clear drugs. In Cote d’Ivoire, receipt and clearance of drugs was delayed. CA was tempted to suggest that they should rely on CA’s agents for clearance in some countries. CA could easily offer DAP (delivered at place) instead of CIP quotes.

Recommendations
- The market situation to aim for would be to split tenders amongst a diverse supply base
- To get to this ideal situation, several things need to happen: CA needs to be incentivised through the project log frame to make the supply base more diverse. They can work with new suppliers to help them understand the requirements for PQ technical acceptance and encourage suppliers by sharing information on the global size of the market and plans for a new RfP during 2014. The log frame should be amended with indicators: By end of 2014, CA should have at least 3 WHO approved suppliers in active framework agreements. A new framework agreement process takes 3 to 4 months, and WHO PQ is expected to take about 6 months. Therefore work to get suppliers interested and technically acceptable should be proceeding over the remainder of 2013 and early 2014.

5. Partner Linkages

The MTR team was asked to consider how well the project links up work of other partners, for example with other NTD control efforts - the integration of delivery or the sharing of resources where needed – and links with water and sanitation. In this section we review what progress has been made and what further opportunities can be seized on the programmatic side. We also discuss a possible way to incorporate indicators on integration into the new log frame. Finally, we discuss the ways in which Crown Agents links up with relevant stakeholders.

## 5.1 Programmatic Linkages
The hypothesis is that by integrating country NTD activities, potential implementation savings can be made and programme effectiveness enhanced. The rationale for integration depends on:
- Overlap of diseases in same areas
- Similar intervention strategies or delivery channel
- Similar drugs of choice (e.g. Oncho and LF both use Ivermectin)
- Limited resources
- Attainment of maximum impact on disease reduction

The rationale and opportunities for further integration will be country and district specific and progress will likely be driven by i) whether there is a process for partners to identify opportunities for cost-sharing ii) relationships between individuals who have the interest and potential to work more closely together and iii) the commitment of government, donors and other stakeholders to the concept of integration. ICOSA can be credited with making some progress in this area, although some attempts have been held back by factors outside ICOSA’s control. Further progress can be made by taking a change management approach - supporting individual, as well organisational and systems changes, towards integration objectives.

During interviews with stakeholders, the following examples were identified as opportunities the ICOSA programme had already leveraged for further integration.
M&E
ICOSA and RTI Envision have begun using the same reporting template. The CNTD country manager has been heavily involved in this work stream.
Mapping
- In November 2012, a coordinated mapping of SCH/STH and LF was conducted in Cote d’Ivoire using DFID funding through both SCI and the CNTD in Liverpool.
- In Zambia, mapping has been coordinated between SCH, STH and trachoma, however this proved to be inefficient as the mapping activities were incompatible. The school-focused SCH/STH team had to wait around while the Trachoma people visited villages and the Trachoma team had to wait around while the SCH/STH samples were delivered and analysed in the labs.
Training
Integrated training for MDA takes place in a number of countries Tanzania, Mozambique, Liberia.
MDA Delivery
MDAs are delivered as part of Child Health Days in Uganda and Malawi where deworming is conducted alongside Vitamin A supplementation, bednet delivery, and delivery of hygiene and sanitation message providing a potential additional health benefit to participants.

Communications
In Malawi, promotional material production will be cost shared with Sightsavers and Save the Children

The following examples have been cited as missed opportunities or opportunities still to be seized:
Mapping
The situation in Tanzania demonstrates the difficulty that can occur when a country implements an integrated NTD programme, yet the donor funds a vertical disease programme. The rationale for involving CNTD in ICOSA had been the potential for integration of LF with SCH and STH, but in practice, these programmes are still running in parallel, linked to funding and contract modalities as well as different personnel in charge in different countries. In Tanzania, mapping of LF with SCH in the northern lakes region has not yet been unable to proceed, and the programme’s lack of knowledge about the LF situation has held up SCH treatments in this high prevalence area. Joint budgets developed for LF/SCH in Tanzania did not solve the problem.
MDA Delivery
- Zambia has the intention to deliver MDA during school health month but was not able to in 2013, due to delays noted previously, and resulting in cost implications for the September ’13 MDA.
- In Zambia, there has been no LF money from DFID while the new DFID business case is in the approval process. This resulted in missed opportunities for planning, cost sharing on TA and MDA delivery with LF.

With regard to WATSAN and NTD integration opportunities, international stakeholders interviewed widely agreed that this is a necessary but aspirational, longer term target. However, in the MTR team’s view based on country visits, it may be a little simpler than that. Leveraging such opportunities at the country level comes down to having a process for NTD and WATSAN managers to periodically meet and look for opportunities to share resources and co-operate; it may simply be a matter of relationships and having a process to co-ordinate. During the Zambia MTR visit, consultants met with the UNICEF rep, who explained the criteria for investment decisions in latrines and stated that she was open to opportunities to jointly plan school health and nutrition interventions and M&E.

The MTR team was asked to develop log frame indicators that could be used for Phase 2 to gauge whether increased integration was being managed. This is a complex endeavour because each country’s situation is so different and therefore opportunities and constraints to integration will differ markedly. The team was not able to develop quantitative indicators but recommends three options for tracking progress in this area:
- An appraisal of integration options should be carried out, as was the intent stated on page 36 of the second annual report: “The hypothesis is that by integrating country NTD activities potential savings in implementation can be made, but the extent of the savings will depend on the extent of co-infections. An appraisal of alternative implementation options and potential savings for each country will be carried out to inform stakeholders of the scale of any benefits, and / or any additional costs that might be incurred. It should also identify any potential barriers and facilitators.”
- Annual reports can document case studies of opportunities which have been seized and what was the context in which such opportunities were possible (e.g. the supporting factors which made integration possible and/or how possible barriers were overcome.)
- A standardised survey can be sent to PMs to gauge a baseline level of integration and progress made since baseline. An example of what such a survey might look like is provided in Appendix 9.

## 5.2 Crown Agents Stakeholder Linkages
Crown Agents has been working effectively with partners and communicates often and in a timely manner. The process and timing from which orders come from countries to SCI, and then to Crown Agents, appears to be working effectively. CA sends out emails every Friday to communicate with ICOSA about tendering processes and any issues. CA gets SCI requests for PZQ each year in May and conducts a tender once per year. CA attends the PMB meetings in March and keeps up to date on programmatic issues through these meetings.

CA communicates with RTI (who procures with USAID money) and WHO at the annual WHO meeting to co-ordinate PZQ supply. The USAID funded “Envision” programme now splits implementation, and PZQ procurement, between two groups. Thus Family Health International (FHI) as well as RTI are involved now in PZQ procurement. Until now, there has been enough supply for all procurement agents to draw upon and no issues with co-ordination. The issues are more felt at the supplier end – with suppliers complaining about the complexity of managing three different tenders for the full PZQ requirements. Each supplier has to check with their API (active pharmaceutical ingredient) producer to make sure he can obtain of the full API quantity requested in the request for proposals (although realising that he is unlikely to win the bid to supply the full quantity). API suppliers in turn see a demand for three times the actual volume they will actually be asked to supply in reality[19] and consequently, they raise prices to account for excess demand over supply. Suppliers state that they would prefer a bilateral, firm contract, confirming exact quantities required and they opine that this would reduce prices they could offer. However this would not be an option for CA, as EU regulations require a competitive tendering process.
[19] Donor A puts out a request for 100 million tablets. Formulators 1 2 and 3 participate in the tender. All three contact API supplier X and ask for the API to support 100 million tablets. API supplier X does not know that Formulators 1 2 and 3 are quoting on the same tender. The API supplier X might think Formulator 1 wants to supply the US veterinary market, Formulator 2 is responding to Donor B’s tender and Formulator 3 is responding to Donor A’s tender. So from the standpoint of the API supplier, it looks as if there is 3x the supply need versus the reality. In consequence of this apparent excess demand over supply, API supplier raises his prices.

6. Alignment of Management and Processes with Programme Needs

“An army marches on its stomach” (attributed to Napoleon Bonaparte)

An army requires strategy and tactics, technical weaponry, skill and courage. It also needs pay and rations, and shovels for the latrines. Getting the pay, rations and shovels in the same place as the soldiers requires precision in planning, timing and communication.

No less than the La Grande Armée, ICOSA is undertaking a great continental campaign. No general can afford to neglect that pay and rations arrive on time, however fine the artillery. Likewise, ICOSA’s management and processes need to be aligned to support its technical pre-eminence in control of SCH, in order to ensure that it delivers the proposed 75 million treatments for Phase 1, and 200 million treatments by 2017, for Phases 1 and 2 combined.

This section reviews how well management and processes are aligned with present and future programme needs.

## 6.1 Robustness of the planning and reporting processes and in relation to programme needs

### 6.1.1. The challenge of achieving objectives on time
The planning framework for ICOSA is the programme log frame. This sets out the quantified requirement for MDA (Outcome), to be achieved through planning, mapping, drug delivery, and M&E. Planning for, and demonstrating, the achievement of both Outcome and Outputs is a prime reporting requirement.

The latest annual and mid-year reports to DFID do not focus clearly on the achievement of these objectives on time. These reports lack a section that clearly addresses the outcome (formerly purpose) achieved compared with target; nor do they clearly quantify the shortfall in an output, where it is “on-going” rather than achieved.

Closer inspection of reports shows some inconsistency in reporting and that ICOSA continues to be behind target. In January 2013, ICOSA reported that it had achieved 6.3 million treatments, It was thus behind the log frame target of 14.25 million, in part attributed to delayed supplies of PZQ. However, ICOSA reported that it anticipated delivery of 17.8 million treatments by March 2013 (ICOSA Annual Report 2012, p4). It gave a different view, however, in the Progress Report October 2012 to March 2013, reporting that it estimated it had achieved 12.2 million treatments by March 2013, 5.6 million less than it anticipated two months earlier. In March 2013, ICOSA was thus still 2 million short of its 2012 target, and 5.6 million short of its own anticipated achievement.

We found little evidence that managers are focused on achievement of the outcome. We did not find regular feedback either within SCI or CNTD showing performance against targets. There neither appears to be periodic reporting, nor reporting at the end of a major activity, nor exceptional reporting of delays or problems. Trip reports by managers were either perfunctory, providing no indication of national programme status, or simply unavailable. Nor was it clear who was responsible for achieving a target, or to whom they were accountable. In both SCI and CNTD, the lack of accountability for performance supported by clear performance targets is a major concern.

Shortfalls in numbers treated to date may be regarded as moderate. However, the pace of delivery will need to increase very rapidly in order to deliver the further 72 million[20] treatments targeted by the end of 2014. This is no small operational challenge.
[20] Cumulative target by end 2014: Phase 1 countries: 43.98m+Phase 2 countries 39.79m=83.77m Less progress to March 2013: 12.2 million Target April 2013-December 2014= 71.6 million

The lack of concern is surprising, because there is no doubt of the personal and organizational commitment to delivering at scale to meet the needs of populations at risk. It is at the core of their strategic plans to “reach national coverage… in the countries in which SCI is currently working” (SCI Strategic Plan 2010-2015) and to achieve “treatment for all at-risk populations” (CNTD Strategic Plan 2011-2015).

ICOSA staff expressed “faith” that this would be achieved, but there was little evidence to back this up, and the programmes visited had suffered serious delays.

#### Recommendations
- ICOSA should establish a clear and prompt framework for reporting global and country performance against target, periodically (e.g. monthly or quarterly); and on completion of major activities; and for reporting exceptional reports whenever delays or issues threaten.
- All reports to DFID, as well as the log frame itself, should clearly state achievement of the outcome against target or milestone
- ICOSA and partnership members should establish a clear framework of staff accountability for the achievement of performance targets

### 6.1.2. Balancing Empowerment and Risk
ICOSA takes its lead from national NTD programme managers and NTD Master plans. Both CNTD and SCI play an on-going role in the development of national institutions, including staff, committees and partner coordination at national level. However, this development is a gradual process, even though programme managers in both Tanzania (mainland) and Zambia reported strong progress. In practice, national resources are likely to be restricted, and both ICOSA and others have provided technical assistance (ICOSA in Malawi and Zambia) or seconded staff (Envision/RTI in Tanzania mainland) to bolster them.

In this context, it is possible to argue that performance or failure is outside ICOSA’s control, because the pace and manner of implementation is determined by national programme managers, WHO and other partners. Thus, ICOSA’s Progress Report October 2012 to March 2013 attributes delays in implementation in Zambia to Ministerial changes to subsistence rates, the Programme Manager’s maternity leave and delays in ethical approval by the ministry, and attributes delays in Tanzania (mainland) to a doctors’ strike, a national census and other local factors.

This implies a very high degree of external risk outside ICOSA’s control. It also implies that local institutions are the primary cause of delay – the slowest ship in the convoy – and that ICOSA can therefore do little to reduce these. Some interviewees indicated that they accepted delay as inevitable and normal, an attitude that sometimes bordered on complacency.

However, investigation indicated that local partners were not always the slowest ship in the convoy, and that at least some element of the delay was due to ICOSA. Thus, in Zambia, factors delaying MDA included delays in mapping that were in turn caused by delays in funding from ICOSA, and competing demands for technicians deployed by CNTD on mapping for LF. ICOSA also delayed in issuing the contract for MDA in time for delivery in July; it was still outstanding in September, at the time of the consultants’ visit, and threatened to curtail delivery due to start two weeks later. In Tanzania, uncertainty of ICOSA budgets in 2012, and delays in finalising a contract in both UK and Tanzania also appear to have contributed to delays of over one year in MDA, and to be a factor in scaling back the number of regions served by ICOSA. Maternity leave of UK staff may also have affected the ability of ICOSA to pursue implementation.

However, some of the most important factors have resulted from complex interactions between national ministries and partners. Thus, representatives of CNTD and SCI met in early 2012 to discuss coordination of mapping for LF and preparation for SCH, but were unable to follow through the LF mapping process as promptly as desired. This delay was cited as a major obstacle to implementing MDA for SCH in new regions.

Even though ICOSA’s approach seeks to build local ownership and capacity for delivery, it retains a duty to deliver the outputs and outcome of the programme. This requires ICOSA to reduce or mitigate the external risks to the programme, and to provide a high standard of disciplined management to ensure that its own services reliably meet the requirement of national programmes.

Interviewees were consistent in their recommendations to reduce uncertainty and delay. They stressed the importance of stronger in-country presence by ICOSA to advocate the ICOSA programme, to negotiate and to build partnerships with both statutory and other partners in NTD control, and to plan interventions.

National staff focused on the practical requirement for an agreed multi-year framework for planning ICOSA’s engagement, reliable information on future availability of funds, including budget ceilings and parameters, prompt contracting and release of funds. In some cases, these practical contributions were more important than technical contributions to SCH control, which are now largely provided by in-country expertise and WHO guidance.

#### Recommendations

- ICOSA’s Risk Management framework should highlight potential delays in implementation outside its control, and also seek to mitigate them. The Risk Management framework should be consulted and amended as required, to adjust programme schedules.
- Log frame targets should either be scaled back to reflect risk, or new ways of working provided to mitigate risk.
- Having established the risks and targets, ICOSA needs to accept accountability for programme delivery on time.
### 6.1.3. Use of Project Management Disciplines
Successful delivery of MDA requires the management of complex and interdependent tasks, from advocacy and contracting to reporting and evaluation. As we have seen, failure or delay in any of these areas is likely to result in reduced or delayed outcomes.

Both CNTD and SCI use some project management tools to assist this. Thus, the ICOSA Annual Report 2012 shows an Annual Timeline for Project Management Activities (See Appendix 7). ICOSA also produces schedule charts for each country (See Appendix 8 for Zambian example).

However, these tools do not appear to be used to track and correct performance in practice. Delivery on time is crucial for performance. For instance, at the global level, an ICOSA plan shows that budgets were to be approved in February 2013, but in practice they were not agreed until June 2013. In the absence of final contracts, budgets remain uncertain in both Tanzania and Zambia. Changes and delays in budgets and contracts have been a major factor in delaying implementation. At the country level, slippages are similarly unnoticed. Thus the latest Zambia schedule does not show that the distribution of drugs in Zambia has slipped from July to September.

Effective project management requires not only setting out clear plans, but adjusting these in the light of performance, changing circumstances, and other experience. Without these, there is a risk that slippage becomes uncontrolled.

Project planning was too late and ill-defined to support prompt delivery. Thus, planning and budgeting for Zambia’s campaign for MDA implementation to 1.7 million people in June 2013 only started in February / March 2013 as the previous mapping phase approached closure. The distribution slipped from June to July to September. Even in September, two weeks ahead of the latest planned MDA implementation date, the contract for funding had not been signed, IEC materials were not yet printed, and it was unclear which and how many national staff would be involved in district supervision. The lack of planning was evident at the smallest level: the team arrived late on site for a pilot distribution demonstration, and had not completed their teaching notes. While the team demonstrated great knowledge and enthusiasm, a considerable step-up will be required for effective delivery to 1.7 million people.

ICOSA’s planning does not reflect the full scope and interdependency of plans. SCI and CNTD Country workplans currently focus only on Outputs, not on the key critical activities required to deliver them, such as agreement on regions, signature of contracts and release of budgets. These plans do not include the many tasks that have to be undertaken before implementation can take place. There need to be milestones for these stages, such as engagement with stakeholders, formation of a task team, a memorandum of understanding, coordination of mapping or sentinel sites with other agencies, an outline multi-year plan and budget and contract signature.

The lack of planning was particularly evident in relation to budgets and contracts. CNTD’s 2012 budget for Zambia was only signed in December 2012, despite an initial payment made in January 2012. The budget for 2013 MDA was developed in Feb/March 2013, but not agreed with ICOSA until July, and the contract is still not in place. ICOSA was thus far behind the ministerial budget timetable requiring officials to prepare the annual budget in September of previous year. (Our visit coincided with the preparation of the 2014/15 budget, for which ICOSA had not developed any contribution). Similar problems were described in Tanzania (mainland), and in Zanzibar, where delays in contract amendment resulted in non-payment of field staff.

Predictability of aid is an important principle of the Paris Declaration. DFID’s agreement of a multi-year agreement with ICOSA should facilitate this. Yet ICOSA only agrees short-term interventions with national programmes. Thus, a round of mapping and a round of MDA in the same year may require 2 separate contracts. Both ICOSA and national programme managers (and programme managers interviewed in a 2012 review of LF elimination) stressed the need for multi-year planning and predictable budgets. As in all walks for life, ICOSA faces budget uncertainties, but this should not prevent it from improving the predictability of multi-annual funding for national programme managers, who can then reflect this in NTD Master plans, national medium-term economic frameworks, and annual budgets.

The disciplines of project management, which could greatly improve ICOSA’s performance and alignment to national planning, are notably absent from ICOSA’s approach. Without a common method, such as PRINCE2 for project management and governance, or tools such as Microsoft Project for focusing on the planning and use of resources to achieve outputs, ICOSA will struggle to achieve its outcome or outputs at the required scale, on time and on budget.

Not all problems can be overcome by planning, but the adage attributed to Benjamin Franklin, “Failing to prepare is preparing to fail”, is relevant here. The consequence of delay in Tanzania is that 7 of 8 regions originally proposed for inclusion in the Tanzania programme in 2011 will go untreated for two or more years. Even a more modest delay in Zambia has consequences for programme efficiency and impact, as it no long coincides with the joint training and promotion that took place as part of a regular school health promotion month in July.
#### Recommendations
- ICOSA should invest in the development of systems and processes to deliver its outcome and outputs on budget and on time: a common methodology for project management across ICOSA, including SCI, CNTD and CA, should be at the heart of this.
- ICOSA project plans should include preliminary as well as implementation and evaluation activities, e.g. advocacy, partnership development, negotiation, planning, contracting and funding
- ICOSA should engage national programmes in developing outline plans and ways of working over longer periods. These may be reflected in memoranda of understanding, multi-year plans and budgets, aligned to national planning processes
### 6.1.4. Planning for Supplies
ICOSA experienced serious delays in the first year of the contract, related largely to Crown Agents’ difficulties in identifying suppliers able to satisfy WHO and other quality requirements. However, these difficulties appear to have been well communicated to ICOSA, which reports excellent relations with Crown Agents. Crown Agents attends the Programme Management Board regularly, and has regular contacts with SCI. Although the price of purchased PZQ remains uncertain, both Crown Agents and ICOSA, are confident of continuing delivery.

The provision of much larger volumes of donated PZQ, however, creates new logistic challenges. WHO is central to this. It was reported that country PMs had to be reminded to make their applications ahead of an August deadline.

The logistic requirements in country are also considerable. NTD staff had not engaged with Zambia’s Medical Supplies Ltd, until they accompanied the consultants. The medical supply system appeared well managed, and was piloting delivery direct to facilities. It is essential that the management of NTD supplies take account of medical supply systems and constraints: medical stores have limited space to keep stock for more than 30 days; they also need to manage distribution within their regular monthly or quarterly delivery cycle. Donated medicines often pose problems to medical stores because they need to be kept longer and have irregular delivery requirements. In this case, ICOSA will need to match WHO’s annual ordering cycle with the much shorter cycles of local storage and delivery.
#### Recommendation
ICOSA should work closely with WHO and others to ensure reliable drug supplies on time, and support national programmes in building effective working relations with distribution chain managers for local storage and delivery.
## 6.2 Robustness of the financial management and reporting processes in relation to programme needs
Section 6.2.1 refers to the integration of financial and general management.
Sections 6.2.2 to 6.2.5 deal with the detail of accounting practice, locally and by ICOSA globally. Recommendations are made at the end of the section.
### 6.2.1 Integration of financial and general management
This section examines the financial management and reporting processes used by CNTD and SCI. Financial management needs to be closely aligned to other reporting, so that budget and work plan form an integrated whole. The recommendations above emphasised the importance of budgeting and financial reporting processes as part of general planning and reporting.

In practice it was not easy to find adequate linkages between work plans and budgets, to evaluate what resource, and hence what budget is required, to undertake an activity. At the central level, it is important for the staff and travel resource to be derived from the activities stated in the workplan. Similarly, at country level MDA implementation and other budgets need to be built up from, and scrutinised against, the work plan and relevant cost benchmarks. An example of the latter was that a major component of the Zambia MDA cost was provision for 24 national managers (or 12 for two weeks) to participate in the MDA programme. However, it was unclear from both the work plan and discussion whether 12 staff were available for two weeks to do this, whether they were aware of their involvement, or how they would be trained. Project planning disciplines need to be used to highlight such resource requirements and confirm that personnel will be trained and available for the period planned.

Currently, country budget scrutiny is limited to peer review, and on requiring national programme managers to cut budgets to fit budget ceilings. While both of these can be useful, country budgets need primarily to be scrutinised against the resources required to deliver the activities specified in the work plan.

ICOSA is rightly concerned to minimise the cost of delivery. However, without clear links to work plans, national managers lacked a framework to discuss the implications of budget cuts, and considered that budgetary cuts were imposed inconsistently. Cuts to training, social mobilisation and IEC materials were a frequent concern, because of their expected impact on service quality and uptake.
### 6.2.2. Local Accounting Practice
Financial controls and audit standards of funds held overseas area incomplete and below standards described the proposed business case.

The Business Case reports that SCI has experienced audit from the US Office for Management and Budget and others. However, in terms of the specific countries where ICOSA is supporting programmes through SCI and CNTD, there is a need for considerable progress to provide the controls set out in the Business Case.

Controls set out in Business Case	Observations of Review Team
Before any money is transferred to a country programme, Imperial College develops a research contract with each country which states the annual budget ceiling available against specific work plans and deliverables.	IC does not have research contracts with countries where ICOSA programme is managed by CNTD. Funds for Zambia and Tanzania were released ahead of contract.
Each contract is allocated a purchase order to ensure funds are committed from the total award budget and to ensure country transfers do not exceed the agreed budget ceiling.
Each country programme is allocated a unique sub account code to enable robust financial management of individual programmes. The sub account structure separates the country programmes, enabling in-depth analysis.	The sub account structure does not enable in-depth analysis, because funds are not reliably coded by output, activity or funding. A system to provide this has been attempted but not implemented robustly.
SCI continuously monitor and ensure all financial transfers match the agreed workplan and specific activity-based budget, and cover a limited time span.	SCI only monitors funds in programmes directly managed by SCI; there is less SCI control over funds managed by CNTD, which does not manage overseas funds monthly. There is no regular reporting of overseas accounts, in cases where funds are held overseas, but no expenditure is currently taking place.
A strong emphasis on robust internal financial controls, accounting records and reports from each financial transfer are received and reconciled in a timely fashion (monthly) and the receipts must be received before subsequent transfers are authorised.	Accounting controls vary between and within countries. Only SCI, not CNTD, requires scanned accounting records to be provided to UK. Excel files submitted as accounting evidence are more easily altered than accounting ledger files. The audit trail of transactions is not always clear.
Praziquantel and albendazole are donated by the pharmaceutical companies through WHO. When cleared from customs these drugs are stored and accounted for by the Ministry. There is no commercial market for these drugs therefore there is minimal risk of theft.	PZQ is also purchased by Crown Agents. However, Regardless of source (purchased or donated) there is limited risk of divergence.
An audit is carried out in at least two countries each year, and more if any irregularities are detected or suspected.	There is no regular process of risk identification, audit planning or execution.

There is considerable variation in accounting practice between locations, and between SCI and CNTD. Accounts were kept by i) a manual cash book (Unguja, Zanzibar) ii) an Excel spreadsheet used as a cash book (Tanzania mainland), which we were advised is more common, and iii) a combined cash book and Excel analysis sheet (Zambia).

No manual or electronic double-entry accounting ledgers were in use, though at least one accountant had some familiarity with these. Manual and, especially, Excel-based, cash book systems lack many of the standard controls provided by well-implemented double-entry accounting ledgers. The latter are commonly used in similar environments by other development programmes, where trained staff are available.

The audit trail of a single transaction was reviewed on each site. In two cases this was clear, but in Zambia, it was not readily possible to trace the selected transaction back to the record of the individuals receiving payment. This weakness in control is compounded because CNTD, unlike SCI, does not require original documents to be sent or scanned to head office.

Overseas balances are either kept i) within ministerially controlled accounts dedicated to the ICOSA contract (Uchenga, Zanzibar) ii) within ministerially controlled accounts holding funds from a number of foreign donors (Zambia) iii) within accounts wholly owned and operated by Imperial College (Tanzania mainland).

In Zambia, the accountant could not readily identify the balance held on the ICOSA account as it had apparently been consolidated with the balance of DFID funds held for the LF programme.

All ICOSA expenditure is consolidated within the ledger of Imperial College. Expenditure subcontracted to CNTD is also consolidated within the ledger of LSTM. Whereas both SCI and CNTD regard funds transferred overseas to ministerial or third party accounts as spent, SCI regards funds transferred to Imperial Accounts overseas as unspent, until it has received evidence of expenditure.

### 6.2.3 ICOSA Control of Local Accountancy Operations
Accountancy services may be provided by a ministerial employee, or an accountant funded by ICOSA. The staff met in Zambia and Tanzania all reported some training in accountancy and demonstrated book-keeping skills.

SCI’s contract specifies accounting and audit requirements, and provides an accounting template. SCI has an accounting manual, and is currently updating this. It is also developing a template to facilitate cost analysis. CNTD’s contract does not mention accounting requirements beyond the requirement to submit a “narrative and financial report in CNTD financial template”.

Contact between ICOSA and local accounting staff is limited. Although both SCI and CNTD accounting staff have made visits to a few overseas locations, there is no regular process of supervision or internal audit. CNTD ran a training workshop for finance staff in 2012.

At the time of our visit, SCI’s Assistant Accountant was working closely with the Tanzania (mainland) accountant on developing the Excel cash book to provide detailed cost analysis. However, another local accountant had concerns about practical processes of bank reconciliation and accounting for fuel usage, but did not know who to address these concerns to.

### 6.2.4 Local Reporting
Local reporting routines vary, according to the requirements of SCI and ICOSA, and according to the practice of the local office. SCI requires scanned copies of all vouchers to be provided to its Imperial College office, where they are printed and stored. It also requires an electronic – but not printed or signed – copy of the Excel cash book monthly, and bank statements. However, where no expenditure is made in a month, SCI does not require a report. Thus, no report had been provided on expenditure in Tanzania mainland since February 2013, despite holding balances of over £200,000 in the Tanzania account.

CNTD only requires a financial report on completion of each stage of the contract. This is also supported by a list of transactions, which is generated separately from, and not necessarily reconciled with, the cashbook or underlying vouchers.

### 6.2.5 Consolidated reporting and cost analysis
LSTM and Imperial College accounting ledgers are primarily designed for university purposes, and neither system records a high level of detail about CNTD or SCI activities, coding only summary expenditure at the contract or country level. Although this is sufficient for highly consolidated reporting to DFID, it provides little further information.

As analysis is not available from IC’s corporate ledger, SCI and CNTD have to conduct subsidiary analysis to find the costs of activities and functions, for the purpose of cost or value for money analysis. Two staff are temporarily employed to recode ICOSA transactions. Such exercises are likely to be error-prone, as well as labour intensive.
#### Recommendations
ICOSA needs to ensure that financial planning and reporting processes are integrated within the work planning and reporting process, and that budgets and expenditure are reviewed within the context of the work plan.

- SCI and CNTD should jointly commission a review, redesign and project plan for a financial system to provide common accounting standards and reporting framework for all funds transacted overseas and in the UK, while allowing flexibility to accommodate local capacities and requirements. This should specify
  - Standard electronic reports showing budgeted and actual expenditure, as well as cost analysis by activity (mapping, MDA) and function (transport, IEC materials, subsistence), and balances held
  - Integration with budgeting and work planning at all levels
  - Monthly reporting requirements to include scanned or actual documents, signed and authorised prints of ledger, Excel or cash book, bank statements
  - Standards and safeguards for data entry systems, whether cash book, Excel or accounting ledger
- All offices should report monthly whenever unspent balances are held, whether or not expenditure has taken place in the month
- ICOSA should conduct an annual review of financial risks across all partners (SCI, CNTD and, if appropriate, CA), to inform an annual work plan that includes development, training and audit.
## 6.3 Skill mix in relation to programme needs
Both CNTD and SCI staff evince a strong professional understanding of their work, but there are major areas of unmet need i) Ensuring prompt delivery of services to support scaling up ii) Control of finances iii) Effective cover for absent staff.

The first two of these have already been discussed. The third issue, effective cover for absent staff, was a recurrent issue in discussion. Staff resignation, reorganisation and maternity leave had all posed problems for continuity in both SCI and CNTD.
### 6.3.1 Staff Profile
ICOSA staff stressed the importance of “technical” skills related to SCH and STH, as well as general management skills. CNTD and SCI were therefore asked to list the qualifications, management experience and technical experience of full and part time staff on the ICOSA programme.

Reported qualifications and experience of SCI and CNTD staff partly or fully funded by ICOSA
Post	SCI	CNTD	Total	Qualifications	Experience
Director	1	1	2	2XPhD natural/health sciences	25-45 years technical, academic, managerial, advisory
Senior Project Manager, Country Programme Managers, Biostatistician and M&E Manager, full time TA	5	2	7	6XPhD, MD / 7XMSc	4-33 years technical, / academic, managerial, advisory
Research Assistants	0	2	2	2 X MSc natural/health science / 1 X MSc Project Management	2-3 years technical and/or managerial
Other Managers	1	1	2	1X MSc Env studies, / 2XBSc Dev Studies, Geog / 2X Further education in management	Up to 24 years management, teaching
Administrators	1	1	2	BA Politics, Languages	Up to 13 years administration

ICOSA is staffed predominantly by highly qualified specialists in natural and health sciences. Nine senior staff have qualifications in a relevant natural science or health science to Masters level, and 8 have a doctorate. This is by far the largest staff group. By contrast, only one member of staff, a research assistant has a post-graduate qualification in a management discipline. No staff have a qualification in finance or accounting.

However, staff were reported to have considerable experience in management. Their reported management and technical experience ranges from 4 up to 45 years.

ICOSA therefore primarily operates as a professional grouping of highly qualified specialists under the supervision of a highly experienced director who is also a professor. They receive a small amount of support from research assistants, general managers and administrators. The LATH manager supporting CNTD has only two days a month for ICOSA. However, an LSTM accountant also provides services to CNTD.

Organisations typically maximise the productivity of their high value professionals by complementing them with people who have other, often less specialised and sometimes less costly, skills. Thus, health care organisations deploy large numbers of junior doctors, nurses, and low cost staff with specialist skills like phlebotomy, and only a small number of senior consultants.

The preponderance of senior specialists in ICOSA, however, leaves gaps. Most notable are the training gaps in management and finance. The directors, senior project manager and national programme managers all report extensive management experience, and indeed are entrusted with major management and financial responsibility for the ICOSA programme. However, they do not have training in this area. ICOSA has to look outside for financial and operational management expertise.

IC has a long history of management education, but only one, non-specialist, manager has so far taken advantage of the Imperial Leadership and Management Development Programme.

#### Recommendations
- CNTD and SCI need to review the deployment of staffing to the ICOSA programme. The review needs to take account of ICOSA’s needs for a wide range of disciplines, including finance and management, as well as specialism in SCH and STH.
- ICOSA needs to use specialist staff for specialist advice, rather than as a general resource for programme management.

### 6.3.2 Flexibility and partnership working
The division of work into country programmes means that SCI and CNTD have largely separate areas of activity. Although CNTD and SCI staff meet at the PMB and academic or WHO events, there is not a high level of practical engagement between SCI and CNTD in implementation.

As small organisations, they are susceptible to fluctuations in workload and staff availability. Maternity leave can cause extended gaps in management.

It is not currently possible to estimate the time required to do an ICOSA country programme manager’s job, in the absence of a specification of activities or time recording. However, there was a great fluctuation in availability of staff due to maternity leave and other causes.. There was also concern that some staff could be overloaded, with responsibilities within ICOSA for country programmes, as well as other responsibilities across ICOSA, or outside ICOSA.

These problems were acute in relation to monitoring and evaluation, which requires joint working between CNTD and SCI. Staff changes, maternity leave and competing responsibilities were identified as factors affecting the performance of the M&E working group. The group itself ceased to meet in mid 2012. There is no current place for resolving key M&E issues, such as approaches to sampling, and these issues appear to be outstanding to the detriment of ICOSA.

#### Recommendations
- ICOSA needs to quantify staff capacity and requirements across SCI and CNTD, and identify flexible ways to meet needs, based on staff availability and competences.
- Annual work plans should specify the number of days of staffing required for each country programme, and ICOSA as a whole. Where one implementing partner cannot meet the need, staffing needs should be met by the other partner or externally.

### 6.3.3. Integrating the Professional Mix
The ICOSA programme requires a diversity of professional skills and experience, ranging from epidemiology and parasitology to finance, logistics, project and operational management and negotiation.

It is a concern that interviewees did not always show respect for each others’ professions and technical disciplines, because all of these are required for successful implementation. In interviews there was a tendency to make a false division between “technical” skills (health or natural science related) and “management” or “finance” even though these are technical areas in their own right.

This division is reflected in CNTD’s attempt to make separate provision for management and finance. In 2011, it created a CNTD manager post but found this unsuccessful. In 2012 it declared the post redundant and created Chief Operating Officer post, currently not funded by ICOSA. There is an expectation that both posts should relieve the “technical specialists” of the burden of management and finance; also that, relieved of this burden, specialists should be free to pursue their country programme development without “interference” of management or finance. This is not a reasonable expectation, because country programmes need to implement very challenging programmes, and delivery a quality product, on time and on budget. In short: country programme managers are managers, and so need managerial competences within their team to inform their decisions.

The attempt to divorce management and finance from “technical” managers has not been a success. In practice the relation of the CNTD COO to ICOSA has been unclear, and lines of authority between CNTD staff, Director and COO have become so confused that CNTD is now managed by an externally chaired executive committee.

SCI’s approach is that managers should be both technical specialists and generalist managers, though in practice none of the specialists has management training. The review team noted with concern the view that SCI needs a COO, and that both the COO and the Senior Project Manager, should report separately to the Director. The appointment of new staff is only like to be successful if the task and skill gap have already been clearly identified, and care has been taken to integrate the reporting lines of existing as well as newly hired staff. In any configuration, it is important to clarify whether specialists will act purely as advisers, or as managers. If the latter, they must have all the requisite skills, or act under close professional guidance in areas outside their skill set, such as management and finance. In any case, the configuration must be affordable, making an economic use of all professional staff.

#### Recommendations
- ICOSA should develop an annual staffing requirement, based on the work plans of each country and ICOSA as a whole. It should ensure that each programme team can draw on the managerial and finance and other skills, as well as skills specific to SCH and STH, sourced from within or outside CNTD and SCI.
- ICOSA’s staffing budget should be based on its annual staffing requirement, not on core staffing which is not clearly justified.
- ICOSA should make best make best use of professional staff below the PhD/Manager level, particularly to work on details of planning, budgeting and implementation; it should reserve higher level staff for tasks which need their particular skills and experience.
- The cost of overall management of ICOSA should be clarified within the work plan.

7. Key Risks, Opportunities, Threats to Programme’s Impact

The MTR team was asked to consider key risks, opportunities or threats to the programme’s expected impact caused by changes in global context and assess mitigation strategies. The table below and proceeding paragraphs present the programme risks identified in the most recent business case made for expanding ICOSA support to £50 million, the probability and impact score from the business case, mitigation strategies recommended in the business case, and the MTR team’s view on those risks, given findings of the MTR. MTR team’s recommended revisions to probability or impact scores are placed in brackets.

Risk	Probability	Impact
1. PZQ shortage as a result of shortfalls in donations or procurement.	2 [3]	3
2. PZQ price rise.	2 [3]	2 [3 – given Phase 1 is entirely procured]
3. Poor compliance with treatment	1 [2 in low-endemicity settings]	3
4. Difficulty in scaling up as a result of lack of country capacity for implementation and/or logistical difficulties	2 [1 in established programmes, 3 in less mature programmes]	2
5. Difficulty in scaling up on part of contractor	1 [2]	3 [3 for new programmes, 1 for established programmes]
6. Conflict affects implementation	2	2
7. Resistance to PZQ and side effects	1 [2 for side effects]	1
8. Climate change risk	1 [2]	1
9. Exclusion of hard to reach	2 [3]	1
10. Motivation of community volunteers	1	1

Key: 1 = low risk, 2 = medium risk, 3 = high risk
Scores within brackets are the MTR team’s suggested revised scores

1. PZQ shortage as a result of shortfalls in donations or procurement.
Probability = 2 [3] Impact = 3
Mitigation Strategy recommended in business case: Successful procurement in Phase 1 after initial delays but continued close liaison with WHO, USAID, Merck Serono and manufacturers is required in order to ensure adequate supplies either donated or purchased. Continued market due diligence is required to determine best procurement strategy which manages supply and price risk. The allocation between Crown Agents for PZQ purchase and SCI should be kept explicitly flexible to allow for evolution of the market. MTR view: Given that CA is now sourcing from a single supplier, there is a need to expand the supply base.[21] Specific actions for CA to take are outlined in Section 8 of this report. CA to be evaluated on expanding number of WHO-approved suppliers having an active framework agreement for supplying ICOSA.
[21] A new opportunity as well as a risk, which has arisen since the inception of the ICOSA programme, comes from the January 2012 announcement that Merck Serono will scale up its offer of donated PZQ from 25 million to 250 million treatments per year. This opportunity relates more to the expanded Phase 2 programme, and offers the potential to reach more beneficiaries with less funds. It also diversifies supply risk, as the expanded programme can source partly from CA and partly from Merck Serono donations. However there are a couple of risks. One potential risk arises if this offer shrinks the size of the commercial market, thereby causing commercial suppliers to exit or raise prices in pursuit of an end game strategy. A second risk relates to restrictions on the Merck offer, firstly i) the stipulation that countries can only source from Merck (not from a mix of donated and procured supply) if they choose to take up the donation offer. From a country perspective, this creates a supply risk, as (in any sole supply situation) the buyer faces uncertain supply if the single supplier defaults. A second restriction on the Merck offer is the fact that donated product can only be used in school age children. Therefore, considering the two restrictions on the offer, this offer is only valid for countries which have no high risk adult populations (as they would have no option to source commercial supply alongside the Merck donated product).

2. PZQ price rise.
Probability = 2 [3] Impact = 2 [3 – given Phase 1 is entirely procured]
Mitigation Strategy recommended in business case: As above, under PZQ shortage. Crown Agents will manage PZQ market strategically, in liaison with other procurers and Merck Serono as a product donor. New framework exercise will need to be conducted, to allow for changes in the supply base, the increase in purchase funds (demand side change), and the need for extension of contract validity over timeframe of phase 2. MTR view: as above under supply shortage

3. Poor compliance with treatment
Probability = 1 [2 in low-endemicity settings] Impact = 3
Mitigation Strategy recommended in business case: Unlikely in schools as treatment is closely supervised. Compliance in the community to be monitored by SCI through surveys. SCI uses distributors selected by the community (i.e. are trusted). The strategy of community selected distributors has been very successful in other programmes, e.g. it is the mainstay of the African Programme for Onchocerciasis Control. MTR view: Probability needs to be differentiated for different settings. Low-endemicity settings have higher risk (probability 2) for compliance issues and mitigation includes increased community sensitisation, research into KAPs. The MDA delivery channel also has potential to influence compliance as CBDs not always using DOTs, and side effects can be more common where people taking PCT on an empty stomach. Mitigation: linking up with feeding programmes, increased investment in BCC and health education, enrolling support of health workers for credibility and side effect management. Compliance has been less of an issue in high prevalence settings, (probability 1)

4. Difficulty in scaling up as a result of lack of country capacity for implementation and/or logistical difficulties
Probability = 2 [1 in established programmes, 3 in less mature programmes] Impact = 2
Mitigation Strategy recommended in business case: SCI support is intended to help build country capacity and overcome logistical difficulties. Utilise NGOs with capacity and continue to build capacity through community, government and NGO efforts to minimise this risk. MTR view: Probability rating needs to be differentiated for new versus established programmes. For new programmes, probability rating increases to 3. For established programmes it decreases to 1. Having a large portfolio of countries and ability to move funding around to countries based on progress will help mitigate. ICOSA will need to better tailor support to varied country bottlenecks so that it is not so reliant on 3 countries to take up 80% of treatments.

5. Difficulty in scaling up on part of contractor
Probability = 1 [2] Impact = 3 [3 for new programmes, 1 for established programmes]
Mitigation Strategy recommended in business case: Finding appropriate staff to manage scale up at SCI is not considered a major risk.SCI will continually appraise staffing levels, and DFID will monitor this aspect. MTR view: Probability rating increases to 2, impact increases to 3. Probability increases because ICOSA has not demonstrated capacity to scale up in countries visited in the time-scale planned, and still needs to develop time-bound planning system. It will need to harness new skills and systems as it tailors support to varied country needs. This has held back progress in Tanzania as well as countries with less history of SCH programmes, so must be considered a wide-spread risk.

6. Conflict affects implementation
Probability = 2 Impact = 2
Mitigation Strategy recommended in business case: There are plans for a gradual expansion of implementation year by year in DRC in Phase 2 which is not yet approved. SCI will work with the government to select the areas to be treated in a five year timetable with emphasis on safety, prevalence and intensity in deciding which areas to include in the first two years. SCI will seek to work with trusted community leaders and NGO to minimise disruption in case of insecurity. MTR view: Cote d’Ivoire and Liberia are Phase 1 countries emerging from conflict. Mitigation: as above for DRC and also ability to move country allocations from one country to another is key.

7. Resistance to PZQ and side effects
Probability = 1 [2 for side effects] Impact = 1
Mitigation Strategy recommended in business case: Resistance not yet encountered and good evidence that risk is low. Very few side effects have been recorded (and are transient), and people are warned about them before taking the tablets. The project will monitor this and investigate cases experienced. MTR view: Resistance probability is low within the timeframe of ICOSA but side effect probability rating should be increased to 2. During pilot MDA in Zambia, 4 pupils out of 150 treated experienced transient and minor side effects, which were easily managed in the school setting. Likelihood of side effects increases alongside i) greater numbers treated ii) more empty stomachs where feeding programmes not provided or communities are poorer. The potential impact of side effects increases as MDA is provided in less controlled settings (i.e. in communities/outside schools) as the beneficiary may not be managed by a health worker or trained professional and may start false rumours or put others of receiving treatment. In mitigation of possible resistance developing, ICOSA should monitor research in relation to resistance or reduced efficacy of PZQ, and contribute data if available.

8. Climate change risk
Probability = 1 [2] Impact = 1
Mitigation Strategy recommended in business case: Climate change impact is low in course of project. Project will commission work on potential future impact of climate change. MTR view: The need for research is highlighted by a growing awareness of climate extremes and weather shocks[22]. These may affect geographical distribution related to changes in rainfall and water levels within programme period.
[22] E.g. Malawi’s Growth and Development Strategy 2012-2016 reports over 40 “weather-related disasters” betweeen 1970 and 2006.

9. Exclusion of hard to reach
Probability = 2 [3] Impact = 1
Mitigation Strategy recommended in business case: Use community- as well as school-based programmes including community volunteers. The project will place greater emphasis on reaching out of school children, and a specific indicator has been included in the log frame. Other strategies may include the use of Child Health days which concurrently deliver immunisation, bednets and micronutrient supplementation through the health system.
MTR view: Subsequent to MTR country visits and interviews, exclusion of hard to reach now viewed as more probable due to several factors i) side effect risks as described under 7, ii) challenges in managing and motivating CBDs, as described under 10, and iii) recognition by both PMs and ICOSA that non-enrolled SAC and high risk adults are more expensive to reach and can easily absorb entire budgets. It is also more operationally challenging to reach these groups and many country PMs feel insecure about tackling the management side of this strategy. Improving reach to disadvantaged groups may increase average cost per treatment, but will also improve health impact as they are likely to have a greater disease burden.

10. Motivation of community volunteers
Probability = 1 Impact = 1
Mitigation Strategy recommended in business case: This issue is not specific to this programme but a broader, well-recognised potential problem whenever community health workers/volunteers are involved in service delivery. SCI will work closely with governments and other partners to consider different ways to motivate volunteers, based on available evidence internationally. MTR view: Children in school are generally compliant and DOTs strategy can be used to ensure compliance. School teachers are salaried employees. The move to CBDs brings a whole set of new challenges, and given the principal channel of SCH PCT has been the school, ICOSA has relatively less experience in dealing with motivation of CBDs, compliance of out of school children, children under 5, at risk adults. USAID contractors work through CBDs routinely, given the range of NTDs they support, but with significant investment in both central and district level capacity building. The USAID sub-contractor in Tanzania conveyed the significant challenges brought by drug logistics to CBDs as well as motivation and management of the CBDs. Possible mitigation options include: research, partner with others who have used the CBD channel and understand its challenges, increase presence on the ground during learning stages.

8. Recommendations and Actions

Recommendation	Action	Date
1. Management Systems
Improved Reporting: Internal reporting as well as reporting to DFID needs to be tightened in terms of clarity and timeliness. Reports should clearly state the objective expected by a certain date, what was actually achieved by the date, and with a quantification of the shortfall, where it is “on-going” rather than achieved.	CNTD and SCI to establish common mechanisms and templates for reporting performance, against ICOSA logframe output and outcome targets, 6 monthly to DFID and at least quarterly to PMB	Draft templates for DFID review and approval due Dec 2013
Tighter allocation of responsibility - Managers need to be responsible for achieving outcomes and objectives within supportive management structures.	Conduct internal management reviews within CNTD and SCI, at least quarterly, of performance against work plan targets for all country programmes and other areas, e.g. M&E, finance; and to record action taken	First review: Nov2013
Better planning: Successful delivery of MDA requires the management of complex and interdependent tasks; ICOSA’s planning does not reflect the full scope and interdependency of plans. Plans currently focus only on Outputs, not on the key critical activities required to deliver them, such as agreement on regions, signature of contracts, release of budgets. Plans do not reflect the many tasks that have to be undertaken before implementation can take place. There may need to be milestones for these stages, such as engagement with stakeholders, formation of a task team, a memorandum of understanding, coordination of mapping or sentinel sites with other agencies, an outline multi-year plan and budget and contract signature.	SCI and CNTD to review the existing 2013-14 work plans with current skill set / Develop a proposal for skills gap analysis and identify training needs and source the appropriate action-learning training in project planning and management for UK programme managers and assistants / Develop workplans for 2014-15 with external project management support / Establish planning and reporting cycle for 2015 and beyond	2013-14 Workplan review complete by end Nov 2013 / Proposal for review Nov 2013 / 2014/5 draft workplans complete by February 2014
Systems need to be put into place to track central level costs by country and expenditure categories (related to project outputs). Central budget and staff time should be justified bottom up based on the work plan, not proposed top down as percentage of ICOSA staff time. Senior staff should be used economically, bolstered by more junior or less specialised staff. There are notable gaps in management and finance.	Disaggregate invoices to DFID to show number of fee days per individual charged on the invoice / For 14/15 work plan, develop detailed budgets for central and country cost centres, providing transparent information on assumptions behind the budget and allocating costs of travel, staff etc to cost centres and activities in accordance with logframe and work plan. / Establish reporting process (e.g. time sheets) to track actual costs for 14/15 for programme managers and directors, to include all support and development costs / Report back to DFID on lessons learned about actual cost allocation compared to expected (as per assumption based budgeting). Use info to adapt/improve budgeting of central staff time, travel etc for 15/16 workplan and budget.	Invoices to DFID change immediate / Develop budget for all cost centres and activities by Feb 2013 / Establish reporting system to track costs by March 2013 / Compare budget with actuals for half years to Sept ’13 and March ‘14 / Report back to DFID on lessons learned by April 2013
Similarly, systems need to be put in place to clarify what skill sets and what number of days are required to meet the activities required by work plans, countries, or project outputs. There has been a great fluctuation in availability of staff due to maternity leave and there is concern that some staff could be overloaded. These issues cannot be resolved and/or appropriate cover provided until annual staffing requirements have been clarified, based on the work plans of each country and ICOSA as a whole.	See above
Financial management: This needs to be closely aligned to other reporting, so that budget and workplan form an integrated whole, detailing resource required to do a job, and hence what budget is required. This needs to improve at both the central level for ICOSA employees as well as at country level for MDA implementation.	Conduct review of UK and international accounting, budgeting, reporting and audit requirement to meet planning, management, VfM and all reporting needs / Specify accounting and financial management system to meet needs of ICOSA, UK and international partners, including common accounting framework for cost centres and activities.. Verify system meets requirements of DFID, IC, LSTM and local partners. / Review audit requirements in conjunction with external auditor. / With auditor, plan and establish internal audit process to address risks across ICOSA programme, and report six monthly to PMB. Include summary of audit report in reports to DFID.	Review complete by Dec 2013 / Implementation plan and internal audit plan agreed Feb 2014 / UK implementation in place Apr 2014 / International implementation in place by Sept 2014 / Internal audit report to PMB and DFID by July 2014
2. Support to countries
ICOSA needs to assess carefully what its comparative advantage is and to design specific country objectives, taking into account of other major players, including USAID. ICOSA should help identify and respond to needs for greater technical as well as managerial support where this is required, including work plans and budgets, mapping, MDA, M&E and interruption of transmission	- Incorporate specific country objectives into country work plans / - Include provision for tailored technical and management support, and learning plans to countries in 2014/15 workplan where required / - Before country visits, ICOSA should draw up TOR, setting out the objectives and activities, including the influencing and advocacy agenda.	Timing aligned with 1c above: / - 2013-14 Workplan review complete by end Nov 2013 / - 2014/5 draft workplans complete by February 2014
ICOSA needs stronger in-country presence in some countries to advocate the ICOSA programme, to negotiate and to build partnerships with both statutory and other partners in NTD control, and to plan interventions.	Include provision for stronger in-country presence in 2014/15 workplan where required	To align with 1c above
Detailed planning will need to be done by countries to facilitate integration with other NTDs, with the health system and with other sectors where this is appropriate. This should form part of the “design specific country objectives” highlighted in point 2a. above from the previous annual review	- Conduct baseline review of integration in each country, identify opportunities to further integration objectives in each country, and outline plans for influencing and taking forward these objectives. / - Allow appropriate level of country and stakeholder engagement through stakeholder partner meetings scheduled Jan – March / - Report on progress every 6 months	Baseline study completed by May 2014. / Plans to further integration objectives included in next year’s country work plans / Reports on progress every 6 months
ICOSA needs to develop and implement a capacity development strategy linked to change management. This should also form part of the “design specific country objectives” highlighted in point 2a. above from the previous annual review	Participatory diagnostic done with each country and include plans for meeting needs in next year’s work plan	By March 2014
Reaching non-enrolled children is key to stronger health impact. Countries have practical concerns and challenges on this issues and ICOSA staff should coach them through the issues and help problem solve.	Allow enough time in country visits for relationship-building and coaching to work through such challenges. / Document each country’s plan (or reasons for lack of a plan) for reaching non-enrolled children in annual workplans and post-trip reports.	Annual work plans and post-trip reports
ICOSA managers should be encouraged to take a proactive influencing and change management role. ICOSA work plans should include adequate investment in relations with government and other local stakeholders to build partnership working and long term sustainability.	ICOSA country workplans should contain a confidential section describing the political economy dynamics, and if there is something ICOSA managers seek to influence, e.g. in order to improve health impact, government endorsement or efficiency of the programme. Pre-trip reports should outline a strategy for pursuing influencing and advocacy objectives and post trip reports should update on progress. Ad hoc meetings should be pulled together to brainstorm and discuss resolution of difficult challenges.	Incorporated into next work planning exercise and into pre and post trip reporting
ICOSA should provide an agreed multi-year framework for planning ICOSA’s engagement, reliable information on future availability of funds, including budget ceilings and parameters, prompt contracting and release of funds. Many countries felt that these practical contributions were more important than technical contributions to SCH control, which in many ICOSA countries is largely provided by in-country expertise and WHO guidance.	Explore potential for development of a framework for national multi-year plan / and memorandum of understanding with each country, considering feasibility in the context of Imperial legal and financial systems. (AF to follow up with DG)
3. Contribution to evidence base
As part of 1.c. it should be clear what contribution (through paying for staff time or other) ICOSA funding is making towards improvement in the evidence base.	Explore potential for linkages with the DFID Implementation research bid current out for tender
SCI needs to manage the balance between academic publications versus making available what data SCI has already, more speedily for the benefit of public health policy and programmatic improvement.	Include reports of third party uses of ICOSA-derived data as well as SCI/CNTD publications within ICOSA report	October 2013 report to DFID
SCI’s differences with WHO with regard to methodology for site selection for health impact monitoring need to be resolved so that countries have clear guidance.	Meeting with stakeholders and WHO	Resolved by Dec 2013

4. PZQ
PZQ: Crown Agents should intensify discussion with suppliers on WHO qualification process, convey new (expanded) market size projections, and issue a new call for proposals for framework agreements. Crown Agents should be evaluated on expanding number of WHO approved suppliers having an active framework agreement for supplying ICOSA.	By Nov 5th, CA to get in touch with WHO to understand specific requirements for PZQ PQ, timelines, (and to clarify situation with Shin Pong). CA to let WHO know of its plans, as follows: / 1. By Nov 11th,CA to: email all potential suppliers[23] to communicate a) expansion of demand CA will procure assuming Phase 2 ICOSA goes ahead (explain UK govt public announcements and high likelihood of proceeding) b) opening of WHO PQ for PZQ, explain process and requirements, give contact details of WHO point of contact for PZQ PQ c) CA’s intent to reissue RfP for new framework during Qtr 4 of 2014. Explain that manufacturer submission to PQ would ideally happen by Feb 2014 in order to allow WHO sufficient to PQ before CA’s RfP. Explain how procurement with CA works, which countries are include in ICOSA, and the need for in-country registration. Explain that CA intends to follow up individually to ascertain interest and answer questions. / 2. By end of Nov, CA to phone all suppliers to hear their reaction to email, ask if they have any additional questions, understand what possible constraints they face in supplying PZQ or meeting PQ standards. / 3. By Feb 1st, CA to communicate with WHO PQ to find out if there have been any additional PQ submissions. / 4. CA, SCI and DFID to meet in early Feb to reassess situation. / Logframe for expanded ICOSA support to include target of 3 active framework suppliers by Dec 2014	- See under actions / - New call issued in 2014 / 3 suppliers with active framework agreements by Dec 2014
[23] Prime targets are the 5 are non active framework holders plus others which have emerged since the last RfP (e.g. Shin Pong and Chemogroup, Medopharm, Hetero)

# Appendix 1: Schedule of Work and Inputs
1: Meeting with DFID
2: Team visits to SCI and Crown Agents offices to undertake interviews with staff. (We propose to schedule the SCI meeting on a date convenient for CNTD staff to attend, thereby alleviating the need for the team to travel to Liverpool). The focus is on gathering quantitative and qualitative evidence on the programme’s achievements against outputs as well as questions posed in the MTR TORs.
3: The team will do a desk review of evidence. This will include a review of relevant policies/strategies, reports, financial data, reviews and evaluations, websites and online materials to gather supporting evidence.
4: Drawing on the information gathered in 1 and 2, the team will generate hypotheses for further investigation and validation with external stakeholders, develop data collection tools (such as topic guides and semi-structured interview schedules) to support stakeholder interviews.
5: The team will use semi-structured interviews with external stakeholders, identified via purposeful sampling, as the main source of information relating to needs, gaps, perceptions and opportunities. If contentious issues arise during interviews, the interview sample related to that issue will be expanded, in order to generate greater sample size and validity of findings. We propose 26 phone interviews, comprised of the following (See Appendix 3 for suggested names of key informants):

- Donors: USAID (2), BMGF (1),
- Implementers: RTI (1), IDA (1) CNTD – follow up (2)
- WHO: (3)
- Global Network for Neglected Tropical Diseases (2)
- Academics (3)
- CA suppliers: Cipla and Microlabs (2)
- Phone calls to 3 stakeholders from 3 countries additional to Tanzania and Zambia. (9) This the team will have interviewed stakeholders from 5 ICOSA countries in total. (3 countries surveyed by phone and 2 countries visited – see below)

To maximize efficiencies, the consultants will divide up the interviews, therefore they will need to co-ordinate the interview approach and communicate interview results with each other.
6: After having conducted the 26 phone interviews, and having a very good sense of the programme and what factors need to be validated at country level, the team will visit two ICOSA countries to undertake a more comprehensive evaluation of work in country, its contribution to health impact and to country capacity. The proposed schedule is as follows:

Monday 2nd Sep travel
- Tues 3 – Thurs 5 Sep in Country A.  (3) days
- Fri 6 Sept Country B (1) day
- Travel Saturday from Country B to Country C
- Monday 9 Sep to Wednesday 11 Sep  in Country C. (3) days
Travel back to UK Thursday morning
1 day (.5 day each country) for country specific document review (1)

7: The team will collate and analyse findings from the internal review and the external stakeholder validation.
8: Presentation of findings to DFID and ICOSA team
9: Final draft report submitted, feedback obtained, and a Final report incorporating feedback submitted.

Inputs

Category	Assumption	Cheri _ TL	Richard_ TM
In person interviews in UK with grantee(s)	SCI & CNTD and Crown Agents – assume half day in person with SCI/CNTD and then CA plus follow up calls (Richard given more time as he’ll be relatively more focused on management issues)	2.5	3
Phone Interviews	26 interviews, 1.5 hours per interview to cover prep and post. (divide up between team)	3 days (16 interviews)	2 days (10 interviews)
Field visit countries	1 day country-specific prep/document review + 7 days of in-country meetings	8 days	8 days
Team communication and meetings (incl. sharing results of interviews)	phone calls, in person meeting	1	1
Literature and document review	Relevant literature and internal policies/strategies, reports, financial data, reviews and evaluations.	1	1.5
Team leader management	Planning, scheduling, management = day (timetable, theories to test, question guide to use with telephone interviews and for in country visits, report template, identification of key stakeholders, clarification on roles and responsibilities)	1
Data analysis			.5
Presentations	Debriefing in London (incl. prep time and time actually presenting)	1	1
Annual review form		.5
Evaluation report	Assume 6 pages per day * 4 days = 25 pages from Cheri + 12 pages from Richard	4	2
Report amendments	Assume 6 people comment and half a day to respond to each reviewer’s comments = 3 days	2	1
Meeting attendance	June 27th SCI Open Day	1
		25	20

1. SCI responsible for field visit logistics/scheduling as well as document collection for literature/document review.
2. Team member to lead on analysis and write up of the following research questions (and contributes to other questions)
- Analyse robustness of planning and reporting processes
- Assess whether the project has the most appropriate skill mix
- Analyse robustness of financial management and reporting processes
1. Team leader to lead on evaluating and scoring based on outputs 1-6, and lead on questions related to meeting technical and management needs of countries, linking up with other NTDs, key risks, while contributing to the above questions under Richard’s lead. Cheri also leads on writing other sections (method, exec summary, annexes) with contributions from Richard.
2. Both team members to contribute to “Assess efficiency and effectiveness of programme implementation, sustainability and VfM”

# Appendix 2: Key Informants

Name	Organisation
UK Interviews
Delna Ghandi / John Gibb / Peter Clarke	DFID
David Dolling / Miho Abe	Purchasing Manager, Supply Chain Services, Crown Agents / Supply Chain specialist

Professor Moses Bockarie / Dr Maria Robello / Ben Koudoue / Deborah Edwards / Darren Watkins	CNTD, Liverpool School for Tropical Medicine / CNTD / CNTD / LATH
Professor Alan Fenwick / Dr Lynsey Blair / Kieran Bird / Dr Narcis Kabatereine / Ruth Tipples	SCI, Imperial College / SCI / SCI / SCI / Dept of Infectious Diseases Epidemiology
Phone Interviews
Professor Peter Hotez	National School of Tropical Medicine at Baylor College of Medicine, Houston
Dr David Rollinson	Natural History Museum, London
Julie Jacobson	Gates Foundation
Professor Dan Colley	University of Georgia, Athens, Georgia
Dr Lorenzo Savioli / Dr Sylvio Montresor	World Health Organization
Dr Eric Ottesen / Katie Zoerhoff / Katie Crowley	RTI International
Angela Weaver	USAID
Neeraj Mistry	Global Network for Neglected Tropical Diseases, Sabin Institute
Dr NK Kothari	Microlabs
Dr Rahul Lande	Cipla
Marieke Korsten	IDA Foundation
Professor Templeton	Imperial College
Professor David Crompton	Retired academic and Chair of WHO STAG
Professor Tim Allen	London School of Economics
Dr Pamela Venning	Chief Operating Officer, CNTD
Dr Wendy Harrison / Fiona Fleming	Technical Direction, SCI
Frank Gotthardt	Merck Serono
Professor David Dunne	Cambridge Univ.
Dr Karsor	PM Liberia
Dr Edridah	PM Uganda
Dr Jemu	PM Malawi
In country interviews
Yolisa Nalule	Programme Manager, SCI, Tanzania
Liz Taylor	DFID, Tanzania
Dr Upendo John Mwingira / Frank / Bernard / Ali	National Coordinator NTD, Tanzania / Drug Logistics Officer / Financial Officer / Accountant
Dr Julius Massaga	Director, Research Coordination and Promotion, National Institute for Medical Research, Tanzania
Dr Ursuline Nyandindi	National Programme Manager, School Health, Tanzania
Dr Alphoncina Nanai	National Professional Officer, NTDs, WHO, Tanzania
Gosbert Slanslaus Katunzi / Christina Mbise	Country Director, Sight Savers Tanzania / Programme Manager
Jim Cox	Country Director, IMA World Health, Tanzania
Dr Khalfan Mohammed / Dr Juma Mosi / Mr Simba / Shibu Ali	NTD Programme Manager, Zanzibar / Deputy Programme Manager / Deputy Programme Manager / Acountant
Dr Mutale Nsakasholo-Senkwe	NTD Programme Manager, Zambia
Lancelot Mutare / Kennedy	Ministry of Education, Zambia
John Ngosa	Logistics Director, Medical Supplies Ltd, Zambia
Mr M Nyanga / Ms Simanza	Head Teacher, Chanyanya Basic School, Zambia / Deputy Head Teacher
Robert Mvula / Immaculate Chimbwe	Principal Accountant, Min. of Health, Zambia / Assistant Accountant

# Appendix 3: Interview Guide -Country Based Informants

Intro
Tell me about your role
What do you see as priority needs in schisto specifically and in NTDs more generally?

Impact[24]
[24] Hypothesis to test: quantitative measure of clinical outcomes is problematic. What further research needs to be done to improve the impact indicators in logframe?
- Could we have data on quantity delivered vs. what was projected to be delivered?
- Could we see coverage validation surveys that have been done? What are the challenges with this?
Sentinel site surveys:
looking at infection (intensity vs. prevalence over what time frame and relevance of cohort – longitudinal studies have new 6 year olds) and morbidity (attribution?)
Unpick black box between MDA tablet delivery and health impact:
Shorter term:
Which groups targeted, how often treated
Compliance – as function of whether they swallow the pill, absence of adverse events, community sensitized)
Drug effectiveness (as function of resistance)
Absence of confounding variables which also affect health impact
Likelihood of reinfection: (as function of change in KAPs and change in WATSAN situation)
Longer term:
Change KAPs for sustainable impact
Institutional change - health systems and human capacity - for sustainable impact
WATSAN
- How do you decide who to target (which regions, communities, villages and individuals), how often to give MDA, through which channels to give it (including consideration of alignment/synergies with other disease programmes or other implementers). What sort of challenges do you encounter as you make decisions about targeting? How do you resolve these challenges?
- WHO guidelines: what challenges do you encounter as you try to interpret/translate them into your own setting?
- Compliance: what challenges have arisen, how are they dealt with? consent, how do you know not hiding in cheek? Has there been any social science research to look into KAPs? Have there been any formal surveys of beneficiaries (e.g. as part of coverage surveys?) to look at issues such as how beneficiaries heard of the programme and why it wasn’t taken up when offered (by groups or individuals who refused). If there has been such research, how have the results influenced policy and practice with regard to delivery and BCC work? Community sensitisation, do you see opportunities for communities to take greater ownership of the programme? What could support this?
- What evidence is there of health impact? How do you monitor baseline and post MDA prevalence, intensity and morbidity? What challenges do you have as you monitor these things? What have been the results?
- How are children out of school reached? How are at risk adults reached? How do you define at risk adults? Has there been any ops research to inform these areas?
- Is any health or behaviour education provided alongside MDA?
- Questions to test sustainable impact: evidence base increased, transmission interrupted, human capacity building and health systems strengthening, KAPs of population changed

Training[25]
[25] Need better indicators for this re: quality and quantity.
- Has ICOSA provided training of drug distributors, lab technicians, health workers? How does that work – is it training of trainers?
- What specifically are they being trained in? E.g. programme management (which aspects?) mapping (assessment of existing data, protocol development, data collection surveys), M&E, disease surveillance.
- What was the method used previously and what is it now, post training? (see if we can pull out some ops mgmt mapping/BPR case studies)
- NSPs – what was ICOSA’s contribution to those? How has ICOSA influenced them and how have NSPs influenced ICOSA?
- Has ICOSA influenced standard protocols for data collection. How are these aligned with requirements of others (e.g. govt systems, requirements of drug donors, requirements of other donor agencies like USAID and requirements of other implementers like RTI)

Integration[26]
[26] Hypothesis to test: challenges to further integration include donor restricted funding to single disease area, implementer expertise specific to 1 disease area, govt wishes/strategy as well as govt technical silos and structure, and implementer not judged on integration in logframe (no reward). Need to develop indicators for integration to provide that reward.
- What other NTDs are in the country?
- Which other implementers are working in country?
- Greater/missed opportunities in joint mapping, training, planning, delivery, data sharing, monitoring?
- How does the government join up NTDs with each other or join NTDs to other disease areas (what systems, staff, resources are shared?)
- How is it linking in with other NTD control programmes? (e.g. using similar delivery systems, people, matching up maps so as to prioritise areas for delivery, etc, using similar data collection or reporting systems)
- As far as opportunities for integration, what opportunities have already been seized? What more could be seized (e.g. in terms of better alignment, communication, shared resources)?
- How do you see the pros/cons of integration – in which situations does it work well, and in which situations does it make less sense or have limitations?
- How is ICOSA linking in with Watsan in your country?[27]
  [27] More opps for joint mapping/planning/intervention delivery rather than in parallel?
- How well are the MoE and MoH linking up to deliver MDA? Any challenges there and how overcome?

Management
- Data - Who owns it? Who has access to it?
- Recoding no of treatments delivered: how data captured? how long before info reaches different levels? How is accuracy checked?
- Meds reaching delivery points on time?

Value for money
- What cost data is available on delivery? How was the data collected and analysed? What sort of challenges did you come up against when deciding how to allocate some of the costs? How did you resolve those decisions? How did you account for transactions costs of countries? How did you deal with apportioning staff time? How confident are you that the end result of the costing study is robust? How will the data be used to influence policy and practice?
- Is there any drug wastage due to expiry or improper storage handling? How are import duties dealt with? Are there delays at central level in getting drugs cleared? Are there challenges in getting drugs from centre to peripheral level? (perhaps good to map the processes of all the moving parts coming together in different countries to provide a flavour of the complexity and how/if ICOSA helps ease the complexity)

Conclusion
(testing counterfactual) Where would schisto control be in your country in the absence of ICOSA? In your view how would things have evolved otherwise? What are the stumbling blocks to full transition of schisto control at the moment? (from ICOSA to government)

# Appendix 4: Agenda for meeting with Crown Agents
Overview of CA’s role: key personnel at CA, fund allocation to PZQ versus other purchases, strategies for achieving value for money, how CA interfaces with other organisations – SCI, CNTD, National Programmes, RTI and IDA

Overview of the PZQ market: i) supply side: current suppliers and other potential suppliers (in relation to their ERP status), prices, security of supply, API sources and their security/any noteworthy supply side trends and ii) demand: split of demand/purchases globally and amongst pubic buyers, how does demand side information/orders flow into the procurement process and affect procurement decisions? Are Crown Agents engaged in any work which goes beyond getting PZQ at the best price, i.e. market management and looking longer term at the market supply situation? What are CA’s contractual obligations to ICOSA programme/DFID in this regard?

Outline the planning, negotiation and execution of the procurement process, both of drugs and other supplies. How does CA make decisions about which procurement strategy to follow, i.e. whether to award all to one bidder, split tenders etc?
# Appendix 5: Survey: Scope and Scale ICOSA Contribution
Please place an X under one choice (1, 2, 3 or 4) for each line to indicate how intensive was the technical support provided by ICOSA to the particular activity on that line.	1	2	3	4	(Optional) comments on whether this level of support was appropriate (A), insufficient (I), or excessive (E) given the needs of the context
Policy and Strategy development:
Support to NTD advocacy with high level officials
Support to development of national strategic plan
Support communication between stakeholders
Support to increased work with WATSAN
Support to strategy for reaching non enrolled children
Support to strategy for reaching high risk adults
Support to mapping:
Assessment of pre-existing data
Developing protocols for new mapping
Diagnostic capacity building or training
Data collection
Data analysis
Managerial support:
Detailing procurement requirements
Planning logistics of MDA roll-out
Support to constructing budget for master plan
Funding gap analysis
Support to development of training modules/materials
Communications and sensitisation support :
Support to communication strategy development
Support to social mobilisation
Support to health education materials development or training
Support to M&E:
Support to sentinel site selection
Support to cost data templates/ guidance on cost analysis
Support to coverage validation

Key to numbered responses:
1 = ICOSA (SCI or CNTD) provided funding only to this activity. We had the technical expertise in house and/or relied on WHO or other partners and did not require assistance (other than funding) for this particular activity
2 = ICOSA staff (SCI or CNTD) provided some limited technical assistance or advice, e.g. brief discussion every few months
3 = ICOSA staff (SCI or CNTD) provided more substantial technical inputs into this activity, e.g. monthly communication and responsive support to deal with challenges we encountered
4 = ICOSA (SCI or CNTD) provided essential technical support, without which the activity would not have moved forward as well or as quickly. We were in communication almost every week and ICOSA helped us with the detail of implementing the activity (possibly also through funding local TA)
# Appendix 6: Survey Results ICOSA contribution

# Appendix 7: Extract from ICOSA Annual Report 2012

# Appendix 8: Zambia Schedule of Activities, CNTD September 2013

# Appendix 9: Baseline Survey of Integration
	Not at all integrated	Integrated partially with other NTDs	Integrated partially with wider health systems and health services
Effective mechanisms and working relationships between all NTD partners and government in support of national master plan
Use of national medical stores for drug clearance, storage and distribution
Implementation
Training
Community sensitisation
Mapping
Coverage validation
PCT delivery across all NTDs
Advocacy
Registration of target population
Health education and promotion
Riding on existing platforms established for other health services in schools and communities (e.g. school health days, basic health package, immunization days)
Integration within local health systems for planning, delivery and accountability
Integration within wider community and local government for planning, delivery and accountability
Co-operation with WATSAN in planning, implementation and M&E
Involvement of Ministry of Education in planning, implementation and M&E
Timely progress in implementation and reporting of the Master Plan

# Appendix 10: Additional Indicators from May 2013 log frame

M&E
Output Indicator	Milestone by 2012	Status
1.1 Percentage of targeted districts submitting reports 90 days after MDA	40%	Not yet evaluated
1.2 Validated coverage of children not at school by gender	At least 50% (M/F) in 1 country (Malawi)	Achieved. But further progress may be stalled due to staff continuity issues. / Males 15.49% (n=45, range 4%-27%) - Malawi / Females 14.76% (n=52, range 3%-26%) - Malawi
1.3 % of heavily infected individuals from baseline by country	None set for 2012	*Tanzania: S.h.=7%, S.m.=4.1% / Baseline data analysis by: / April 2013 – Malawi, Mozambique / May 2013 – Liberia / August 2013 – Zambia / November 2013 – Cote d’Ivoire

This section is trying to look for evidence of appropriate targeting so that health impact from treatments can be maximised. Coverage validation has been conducted so far only in Malawi and it was revealed that non enrolled SAC are 5 times less likely to get MDA vs. SAC in school.

Strategies identified to promote elimination of SCH in low endemic settings
Output Indicator	Milestone by 2012	Status
1.1 Identification of transmission hotspots where adjusted PCT should be focused	30% of hotspots treated by adjusted PCT	Work in progress in Niger, Uganda and Zanzibar
1.2 Percentage of heavily infected individuals in hotspots	Baseline data collected for Uganda and Niger by end 2013	Zanzibar has collected baseline data = 15%

Reduced costs of treatment as a result of efficient implementation
Output Indicator	Milestone	Status
1.1 No of countries with financial cost per treatment determined	6 countries by 2014	No 2012 indicator
1.2 Direct financial cost per treatment by country	By 2012 (baseline): / Cote d’Ivoire: £0.28 p / Liberia: £0.31 p / Data on all other countries to be available by 2013	Achieved for CdI and Liberia as well as Mozambique

Already covered previously