Type of Review: Project Completion Review

Project Title: Further Maintenance to Calshot Harbour - 202996

Date started: 4/11/2011	Date review undertaken:	29/8/2012

Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The UK provided £435,255 assistance to Tristan Da Cunha to support on-going maintenance of the harbour breakwaters, to safeguard the existing structures.

What were the expected results?
The expected results were based on building the islands capacity for maintenance and implementing successful maintenance works. These were set out as: / Tristan has the capacity to do immediate repairs as damage occurs to the breakwaters. / Maintenance effectively implemented on the breakwaters.

What was the context in which UK support was provided?
Calshot Harbour on Tristan da Cunha was originally constructed in 1967, with extensions and additional work continuing until 1994. The breakwaters however have always been susceptible to damage. This is because a shallow water design was extended to intermediate depths. The armour units designed for the shallow depths are therefore smaller than the desired design size, which means that in more extreme wave conditions damage is inevitable. There have been three sets of repair works carried out by international contractors in recent years, in 2008, 2009 and 2011. / During the 2011 Emergency Repair Project, it was identified that the roundhead of the western breakwater was suffering damage and loss of units. Storms during the winter of 2011 following the emergency repair exacerbated the condition making the need for maintenance/repairs more critical. / DFID in consultation with the island administrator judged that there was continuing potential for damage to occur, until a more permanent solution can be found and implemented. A decision was therefore taken to set up a maintenance project which would empower the islander’s to be able to do their own repairs. This used technical assistance – engineers from WSP Africa Coastal, the local labour force and equipment already on island ( some of which was purchased through the 2011 Emergency Repair Project). / Harbour works on Tristan da Cunha can only take place in the summer months approximately late Jan to May, due to weather conditions. The island is extremely remote and can only be accessed by sea. This project had to be set up and approved in a relatively short time frame to enable contracts to be signed, so that personnel, equipment, and materials could be shipped in time to catch the 2012 weather window. This was successful. Materials were shipped in November 2011 on the Baltic Trader, tools and consumables shipped by the Edinburgh on 12 January 2012, and personnel (technical assistance) on the Maria S Meriam on 17 January 2012.

## Section A: Detailed Output Scoring

Output 1: Tristan da Cunha has island capacity to do immediate repairs as damage occurs on the breakwaters.
Final score and performance description: A+ / The indicator for this output is that an island responsive maintenance team would be trained before the end of the project. / This has been fully achieved. The maintenance project sent out a team of two engineers from WSP Africa Coastal and one technician from Liebherr Nenzing (crane manufacturer.) Prior to their arrival, Tristan Da Cunha Public Works Department deployed a team during the December Holiday period, to start preparing a site area and to reassemble the 3.5 tonned dolos moulds, to ensure the earliest start possible once the engineering team arrived. They also began crushing and grading rock for use in the concrete mix. This early start ensured that there was always enough stone available for casting concrete and no delays, due to material availability, were experienced. / Work on the breakwater maintenance project was advertised island wide and not just restricted to PWD staff. The work was then distributed among all applicants to allow fishing to continue as usual, spreading the benefits of the project as wide as possible. The applicants were divided into three groups two of which contained fisherman and one which did not. The three groups rotated each working two days per week, although this did mean a slightly slower start up process, the plus side was that a larger number of people have been exposed to this type of construction work.
Final results: Three teams of 14 people were trained through the project. Four of each team on crushing and grading of aggregate, the other ten on casting, quality testing and stock piling of dolos. A team of 6 people worked on the placing of dolos on the breakwater structure. Placing dolos underwater required the assistance of one or two of the engineers, in the water. / WSP have documented the process for grading crushed stone, concrete mix design, methodology for casting and curing dolos well. This provides a step by step “How to” guide, which will serve as a useful reference in future. The islanders, PWD and administration, in carrying out their early preparation works, ensured that they would make best use of the WSP team’s limited time on island, and were also fully supportive when improvisation was required. (Eg the fabricating lifting brackets, getting the Liebherr Crane fully operational which took considerable perserverence, working with less than ideal graded aggregate.) / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review?N

Output 2: Maintenance is effectively implemented on the island
Output 2: final score and performance description: A+ / The indicators for Output 2 were: / 3.5 tonne dolos cast on island / All missing dolos on the western breakwater replaced. / All borrowed dolos on the eastern breakwater replaced. / This output has been fully met in terms of indicators 1 and 2, and exceeded in that greater numbers of dolos for the western breakwater were needed than the original estimate. During the 2010/11 Emergency Repair Contract, an estimate was made that 150 x 3.5 tonne dolos units would be required to re-establish the roundhead on the western breakwater. The approach for this project needed to make maximum use of the WSP engineers time on island, as well as recognising that the island teams required assistance to learn how to cast new dolos of sufficient quality. The methodology proposed therefore was to start to remove/borrow some of the less critical dolos units on the eastern breakwater, stockpile and then place these on the western breakwater round head, with a view to replacing the eastern breakwater units further down the line. This then allowed for new dolos to be cast to complete works on the western breakwater and replace the borrowed dolos on the eastern breakwater.
Final results: A total of 60 dolos units were borrowed from the eastern breakwater, and a total of 142 dolos were placed on the western breakwater while WSP were on island. The island workers then continued to place a further 73 dolos units after WSP departed. This was more than had been assessed by the initial survey/estimates, as further damage had occurred since these were carried out. / Although new dolos cast have been replaced now on the eastern breakwater, Tristan da Cunha will need to continue with this work to fully replace all that were borrowed, which allows for an emergency stockpile to be maintained, and then used by the island as needed following future storm damage. / This work was well executed, with clear well thought out methods, set out for future reference in WSP’s final report. Although replacement of borrowed dolos is a work in progress – there is no reason why Tristan cannot fully replace all borrowed dolos in due course, as they now have the necessary skills and competences to cast and place dolos. / Impact Weighting (%): 50% / Revised since last Annual Review?N / Risk: Medium / Revised since last Annual Review?N

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? N / 1.2 Final Output score and description: A+ / The overall output score is graded at A+. Photographs taken during the different stages of project implementation appear to show that good quality works have been undertaken in a well organised manner, with the assistance of the WSP team. The fact that the islander’s have continued casting and placing dolos blocks using the skills and experience gained through this and previous projects, indicates that they have built up their capacity well and have confidence in their skills. This work should now continue until there is a stockpile of dolos units available on the eastern breakwater.
Direct feedback from beneficiaries / Feedback from the Administrator on Tristan Da Cunha is that the project progressed well, building capacity of the island staff to replace damaged or washed away dolos as required in the future.
1.4 Overall Outcome score and description: A+ / The willingness of the islander’s and the administration to participate so whole heartedly in this project is both an asset and an achievement. Calshot harbour is highly vulnerable, and the time taken to mobilise assistance can never be as short as desired, due to both the remoteness and the complex logistics of getting goods and personnel in. The fact that Tristan da Cunha now has experienced people, willing to safeguard their harbour, and do what they can to prevent its deterioration is commendable, and says a lot about the island’s integrity and determination to maintain their self-sufficiency. / 1.5 Impact and Sustainability / The project has certainly improved the condition of the western breakwater roundhead. Due to the short time in which the project could be carried out there was no time or equipment to resurvey and thoroughly prepare the dolos slope, instead WSP had to apply their experience to pack the best possible slope that conditions allowed, generally working from the 10 tonne dolos section and following the contours around the breakwater towards the leeside. Images of the work which was completed by islanders show that the slope achieved appears to be good, although some time after storms generating waves of 9m height and windspeeds greater than 100km/h damaged four units. These have since been replaced. The current status of the breakwater should not be seen as durable or sustainable due to the size of the dolos, but at least the island does now have capacity to effect an immediate repair without needing to call in assistance from the outside world.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y / The project was achieved for £435,255, significantly less than the original budget which was set at £530,000. / 2.2 Key cost drivers / The main cost drivers for this project were: / Local costs (including vehicles, plant and equipment hire; local salaries, spare parts etc.) £ 171,751 / TC – WSP Engineers £125,460 / Imported equipment and materials £138,044 / Total £435,255 / 2.3 Was the project completed within the expected timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / The only change to this project was that the western breakwater suffered further damage following the survey conducted in 2011, and required more dolos placing than had been envisaged when formulating the business case. Since the process of repair aimed to borrow dolos from the eastern breakwater, casting new dolos, placing borrowed and new dolos on the damaged western roundhead, and then replacing dolos on the eastern breakwater, the increased number used meant that it was not possible to replace borrowed units from the east. This is not in itself a problem. The dolos used were not critical to the structural integrity of the eastern breakwater, and the skills built through this project means that recasting of new dolos could continue without external assistance, and replacement continued over a longer time frame. / 3.2 Set out what plans are in place for an evaluation. / There are no plans in place for an evaluation of this project. It is known that 3.5 tonne dolos units are too light for the sea conditions encountered by the breakwater, and that it is liable to continued future damage. Instead efforts will be directed (when OTD human resources allow) at defining a more permanent solution. This is likely to be a two stage project with the first phase aimed at producing design concepts and a detailed design for the most suitable concept. The second phase would be implementation, subject to business case/ funding approval.

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? N / This was a medium risk project. / 4.2 Risk funds not used for purposes intended / The risk of funds not being used for purpose was low. / 4.3 Climate and Environment Impact / Climate and environment impact in terms of carrying out the repairs on an existing structure were deemed to be neutral. It should however be noted that the maintenance was carried out using the size of dolos which are currently available on Tristan da Cunha, which are known to be too light for the deeper sea conditions at the end of the harbour. This type of reactive maintenance cannot therefore carry any guarantees. If conditions worsen generally in Tristan da Cunha and seas and storm conditions become more severe, say due to climate change effects there is every possibility that storm damage to the harbour structures and particularly the breakwaters could increase in the future.

5. Value for Money
5.1 Performance on VfM measures / Value for money cannot be absolutely quantified for this project. Without maintenance work it is likely that the western breakwater roundhead could have been completely washed away – although it is impossible to put a timing on this. Replacing or significantly repairing this would have been both costly and logistically challenging, given the remote location and the fact that it is only possible to work in the austral summer period. Carrying out this maintenance with the dolos available should have lessened the probability of substantial damage occurring before a longer term solution can be implemented. / 5.2 Commercial Improvement and Value for Money / This project was implemented by single sourcing WSP engineering expertise, contracted through resource centre agreed rates. The project required a knowledge of Tristan’s Breakwaters and the work required to cast and place new dolos, and to teach and transfer these skills to island teams. WSP from their experience of designing and supervising the previous repairs in 2010/11 were considered to be best place to deliver this. An open competition, followed by award to a new consultant/contractor would not have provided the service with the same level of continuity and momentum. / 5.3 Role of project partners / The administrator in Tristan da Cunha was a key stakeholder, supporting this project to empower Tristan da Cunha to take action when the breakwaters become damaged. The administration and PWD played a key role in organising the islanders to work on this project, and prepare the ground for the arrival of materials, equipment and the WSP engineers. DFID used information and consulted with all stakeholders to develop a business case and gain funding approval, in sufficient time to allow the project to start within the austral summer of 2011/12. / 5.4 Did the project represent Value for Money : Y / Value for money will be shown, if the breakwaters continue to stand until a more permanent solution can be implemented. Tristan’s new capacity to tackle on going repairs is an asset, in that it helps to promote the longevity of the breakwaters. The size of units however mean that this and future work cannot be fully guaranteed to withstand future weather events.

6. Conditionality
6.1 Update on specific conditions / No specific conditions applied.

7. Conclusions
This project was successful in terms of building the island capacity to be able to do immediate repairs to the breakwater, as dolos are damaged or washed away in the future, through a process of learning by doing repairs to the western breakwater roundhead. This has to a degree secured the western breakwater roundhead, although the results as mentioned previously in the report cannot be guaranteed with the size of dolos used (3.5t). Tristan da Cunha can now continue to monitor the breakwater conditions after storms, but now is much more empowered to take action to prevent further progressive deterioration if units are washed away or damaged.

8. Review Process
This review was written by OTD infrastructure adviser Amanda Duff based on the draft final report received from WSP dated 20 June 2012, and subsequent follow up emails with queries to WSP and the Administrator of Tristan da Cunha.