Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Building a Reliable Investment Climate in Kenya
Programme Value: £13.6 Million		Review Date: March 2015
Programme Code: 203348	Start Date: 19 March 2013	End Date: 31 March 2017

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review
The project’s outputs are proceeding well, with an output score of A ‘Outputs met expectations’. Highlights from each Output are as follows:
- Output 1: Reformed regulatory environment (A): launch of the new Business Environment Delivery Unit in the Ministry of Industrialisation and Enterprise Development (MoIED), reflecting the high priority placed by the Presidency on improving Kenya’s Doing Business indicators. Launch of the Kenya National Electronic Single Window System (KNESWS) to speed up the clearance of exports and imports, attended by heads of state from Kenya, Uganda and Rwanda.
- Output 2: Effective competition (A): MoIED is already implementing an action plan drafted by the project to revive the textiles/garments industry. Estimated consumer savings of $1.2m a year from lower supermarket prices in Nairobi from a recent ruling by the Competition Authority of Kenya that the project supported.
- Output 3: Effective environment for public private partnerships (A+): with the project’s help, the Director of GoK’s PPP Unit believes that it is now stronger than the equivalent institutions in Ghana and Nigeria.
- Output 4: Strengthened demand and evidence base for investment climate reform (A): the Kenya Private Sector Association (KEPSA) has started a change management process to better fulfil its advocacy mandate and financial sustainability, with them for the first time charging members for attendance at a recent event with the President.

Key lessons learnt since the last review include that Machakos County appears to be lacking political will to improve its business environment; and that the Competition Authority is under dynamic leadership and so its worth DFID and other development partners engaging with them more.

Summary of recommendations for the next year
The full list of recommendations is summarised on page 5. The key ones include:
- In order to achieve the Outcomes, it is critical to develop coalitions for change that can push through the approval of laws (warehouse receipts, SEZ) and the implementation of regulations (seeds, PPP), reforms (Doing Business), action plans (manufacturing) and processes (Single Window).
- Reviewing whether some activities should be dropped (pyrethrum, tourism) to free resources for higher impact activities.
- WBG allocating greater staff resources to the project given risks of staff currently being stretched too thin to maximise impact.
- Updating the logframe to incorporate the new work on business taxation and investment policy; add gender sensitive indicators; and better capture some activities.
- Changing the Annual Review timing to be in sync with the WBG’s own reporting cycle.
- Conduct detailed VfM and Theory of Change analysis that can inform WBG’s mid-term evaluation.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203348/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203348/documents/

Outline of the programme

The UK Government is providing £13.6 million to contribute to poverty reduction by improving the environment for businesses and economic development in Kenya. BRICK reflects the prime Minister’s Golden Thread and G8 narrative on economic growth and institutional reform. BRICK is a four year programme approved in 2012 and is funding the delivery of four outputs:

1. Regulatory reforms: Improved business environment through reduction in burdensome red tape that prevents Kenyan businesses from rapidly industrialising and growing to their full potential at both the national and county levels (30%)
2. Effective competition among and between firms in markets that are essential for the growth of the agribusiness sector and increased opportunities for the poor (30%)
3. Supportive environment for the private sector to participate in provision of infrastructure, such as energy and transport, which are needed for employment and growth thorugh public private partnerships (30%).
4. Strengthened demand and evidence base for investment climate reform in Kenya (10%)

This support is reqired because the Government of Kenya has limited capacity to design and manage modern reform processes, or to procure world class reform advisers. The programme is expected to result in effective transfer of skills and knowledge on reforms to national/sub-national institutions’ staff.

Most of BRICK’s funding, 78%, is channeled through the International Finance Corporation (IFC) for the benefit of their Kenya partners who include quasi-government bodies, regulatory agencies and selected units within government (both at national and county level). BRICK’s support to KEPSA is currently valued at £1.4million to support the strategy formulation and implementation aimed at improving its capacity to execute its advocacy mandate and support it to financial sustainability.

BRICK contributes to the Kenya OP vision on “stimulating growth, led by the private sector and with a focus on job creation; and improving service delivery. The following are some of the programme’s expected results:
1. reduction in regulatory burdens and red tape on private sector and businesses by about $20 million annually over the life of the programme
2. reducing the number of days relating to starting a business, registering property and getting an electricity connection from, respectively, 32, 73 and 146 to 20, 30 and 60 days
3. improve the quality of environmental regulation (measured by a World Bank index) by 10%
4. reduce by 50% the number of procedures to register a small business in Kenyan cities, namely, Nairobi, Mombasa and Kisumu

The programme is also expected to contribute to a number of transformative reforms in the sector, including:

1. reformed regulatory environment at national and sub-national level, improving conditions for business and demonstrating how new County Governments can support local business
2. effective competition policies in sectors that also help the growth of small businesses and increase welfare of participating poor consumers who pay high prices for basic food stuff
3. conducive environment for PPPs, especially in infrastructure and export competitiveness

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
There is currently weak evidence to judge progress to the Outcome targets, being too soon to see any change in the Outcome indicators and the Theory of Change is too vague (see M&E section). However, from the key risks to the Outcomes (see Risk section) it is critical to develop coalitions for change for the approval of laws (warehouse receipts, SEZ) and implementation of regulations (seeds, PPP), reforms (Doing Business), action plans (manufacturing) and processes (Single Window). Output 4 facilitates the use of KEPSA and reform champions in GoK for such coalitions, but recent analysis by DFID suggests that the reforms must also be in the interests of political elites. Ensuring this is therefore a top priority.

Current evidence on each of the Outcome indicators is as follows:
- Compliance cost savings ($50m by 2016, $82m by 2019): generated by the regulatory reform, competition policy, trade logistics and taxation components. The last two are generating some evidence of savings (see VfM section).
- Investment climate reforms (5 at national level and 10 at county level by 2016): generated by regulatory reform, trade logistics and business taxation.[1] One national-level reform to getting credit was acheived in 2014, which the WBG recommended to GoK.
  [1] A ‘reform’ is measured by WBG as a 10% reduction in time and/or cost to firms.
- Private sector investment generated ($30m by 2016, $220m by 2019): generated by PPPs, agribusiness, renewable energy, SEZ and investment policy. The target can be met if there is an investor for the Nyali Bridge, which is feasible.
- Sector showing improved performance (4 by 2016): sector-specific targets for this need to be defined, but achieving systemic change is difficult and takes time.
- PSD champions (10 by 2016): too early to judge.
- KEPSA’s financial sustainability (70% of KEPSA’s target): KEPSA aim to reduce grant funding from 80% in 2014 to 20-30% by 2018, implying a logframe target of 66% grant funding by mid-2016.[2]
  [2] Assuming constant progress over the period in reducing depdendnce on grants, KEPSA need to have brought the share of grants down to 55% by the end of 2016. Since the project finishes in the middle of 2016, this can be increased to 60%. The logframe target is 70% of KEPSA’s target. 70% of the 20% fall from 80% to 60% is 14%, so the logframe target means they need to be at 66% grants by mid-2016.

Overall output score and description
The output score is A ‘Outputs met expectation’. This is based on the following:
- Output 1: Reformed regulatory environment (A): WBG have supported GoK in setting its agenda for improving Kenya’s Doing Business indicators, resulting in launch of the new Business Environment Delivery Unit. Work with counties on streamlining the issuing of construction permits and business licenses has started well, except in Machakos. The Kenya National Electronic Single Window System (KNESWS) was launched by heads of state from the region, but requires a strong political push for GoK agencies to use it. A new component on business taxation was started.
- Output 2: Effective competition (A): MoIED is making good use of the project’s support on manufacturing, starting implementing an action plan drafted for the textiles/garments industry. Support on warehouse receipts, seeds and pyrethrum is proceeding as planned, but now needs some strategic decisions to be made. The Competition Authority of Kenya is strengthening is capacity and a new component on investment policy was started to facilitate increased FDI into Kenya.
- Output 3: Effective environment for public private partnerships (A): with the project’s help, the capacity of the PPP Unit is improving quickly, with its Director believing that it is now stronger than the equivalent institutions in Ghana and Nigeria. Momentum has picked up on Special Economic Zones, with the project helping to get the draft SEZ law updated and resubmitted to parliament.
- Output 4: Strengthened demand and evidence base for investment climate reform (A): this is a new output focused on the demand for reform (both intenral and external), to complement the other outputs on the supply side. The change management process for KEPSA to better fulfil its advocacy mandate and financial sustainability is on track, and the project’s investment climate diagnostics work is starting to ramp up well. A new component was added to create at least ten private sector development ‘reform champions’ within GoK, who can push internally for reforms.

Key lessons
- Machakos County appears to be lacking political will to practically improve its business environment despite the rhetoric. It would be good to share experiences such as this across the office to inform our engagement with counties.
- The Competition Authority is under dynamic leadership and so its worth DFID and other development partners engaging with them more.
Key actions
Component/issue	Action	Timeline	Who
Cross-cutting	WBG and DFID senior management discuss whether WBG can allocate greater staff resources to the project or cut down on its complexity.	3 months	Adrian
	DFID Head of Office to meet with the MoIED Cabinet Secretary and Presidential Delivery Units to discuss: priorities for the new Delivery Units; and how to ensure elite backing for the Industralisation Strategy and SEZ.	2 months	Linet
County regulatory	DFID visit at least one pilot county to get feedback	3 months	Linet
Trade logistics	DFID facilitate meetings with Kentrade, IFC and TMEA on how to get GoK agencies to use KNESWS, and agree on the extent to which delays at the Port are being caused by lack of infrastructure or inefficient bureaucratic processes.	3 months	Strahan & Dennis
Manufacturing	DFID discuss and agree with WBG on priorities for influencing and supporting MoIED’s Industrialisation Strategy and its implementation.	1 month	Strahan
Innovation	DFID clarify with WBG the scale of the innovation workstream, and identify linkages with work that DFID East Africa Research Hub is funding on innovation.	3 months	Julia
Tourism	DFID clarify with WBG if another short-term initiative on tourism is justified.	1 month	Strahan
Agribusiness	DFID discuss and agree with WBG on: extent that they can coordinate more closely with other stakeholders working along agribusiness value chains; the scale of the activities necessary to achieve the targets with sustainability.	3 months	Strahan
Competition Policy	DFID consider ways to provide further support to CAK.	6 months	Strahan
	USAID be introduced to CAK for their public procurement programme.	1 month	Strahan
PPPs	Decision taken by DFID on whether to support the PFF and if so, the timeline.	6 months	Dennis
Renewable Energy	Evidence needs to be provided on the use of the renewable energy portal by private sector investors; and the uptake of guidelines and regulations by GoK needs to be monitored.	3 months	Virinder
SEZs	DFID to discuss with WBG and JICA political economy issues around SEZs, and in particular how to ensure support for the Dongo Kundu SEZ from Kenya’s political and business elites.	1 month	Strahan
KEPSA	Ensure that KEPSA staff members are clear on what their role is in increasing financial sustainability, and are empowered to fulfil this role.	6 months	Dennis
PSD Champions	If not fully underway by 90 days from this Review, DFID should ask these reources to be withdrawn and/or refocused.	3 months	Linet
Investment Climate Diagnostics	WBG design the in-depth manufacturing study to address (where possible) key policy questions raised by MoIED and key issues for policy influencing identified by WBG (in consultation with DFID).	1 month	Strahan
Logframe	Output indicator 1.2 replace Machakos SBP with Nyeri investment portal.	3 months	Strahan
	Output indicator 1.4 changed to percentage of transactions using KNESWS.
	Add Output and Outcome indicators for business taxation and investment policy.
	Agree quality criteria for the action plans for Output 2.1
	Agree criteria for ‘improved performance’ of subsectors for Outcome indicator 4.
	Add an additional output indicator to 2.3 to capture further agribusiness activities.
	WBG to suggest gender indicators for the logframe, with support from DFID.	3 months	Linet
Risk	WBG and DFID senior management meet to discuss whether more could be done to build coalitions of change for some of the key reforms, and if so, how.	3 months	Adrian
	DFID and WBG manager meet with each component team to explicitly assess risks to non-acheivement of Output milestones for 2015.	1 month	Linet
M&E	WBG to finish ToC diagrams for the components and DFID to finish the ToC diagram for the programme as a whole.	3 months	Strahan
	Hold next Annual Review around September 2015 to align with WBG reporting.	6 months	Linet
	Make plans for a follow-up study of the project around 2018.	6 months	Caroline
	Progress Reports report against WBG’s revised results framework.	3 months	Linet
VfM	DFID conduct detailed VfM analysis of the programme	3 months	Strahan

Has the logframe been updated since the last review? Yes, see below.

Summary of responses to issues raised in previous annual reviews (across all outputs)
- Revise the logframe to capture all output-related activities, ensure indicators and milestones are realistic and measurable, and re-assess the Outcome and Impact level objectives: done. Also, an a fourth output was added to capture the KEPSA component and new capacity building component.
- Explore options for gaining beneficiary feedback: done. Two impact studies being conducted at the firm and farmer levels, and GoK counterpart satisfaction levels have been put into the logframe.
- Support to GoK to address coordination gaps to ensure success of programme implementation: the new Industrialisation Secretariat within MoIED has improved coordination between GoK agencies, but further improvements could be made. WBG and DFID should continue to discuss this with GoK.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Reformed regulatory environment
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	2014 Planned	2014 Actual	Extent met
Output Indicator 1.1 (National regulatory reform): Capacity score of the Doing Business Unit of MoIED	1	1 / (budget)	Met (A)
Output Indicator 1.2 (County regulatory reform): Number of web-based regulatory portals developed and fully transactional on Construction Permits (CP) and Single Business Permits (BP) (cumulative)	CP:0 SBP:0	CP:0 SBP:0	Met (A)
Output Indicator 1.3 (County regulatory reform): Number of county officers satisfactorily trained (cumulative)	0	0	N/A
Output Indicator 1.4 (Trade logistics): Number of GoK agencies conducting business process reviews of import and export procedures (cumulative)	1	1 / (Kentrade)	Met (A)
Output Indicator 1.5 Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance (MoIED, County govts, KenTrade)	70%	100% / (MoIED - Satisfied, KenTrade - Satisfied County govts – N/A)	Met (A)

Component 1: National regulatory reform
Progress against indicators:
- DB Unit capacity: improving Kenya’s performance against the Doing Business indicators increased significantly as a priority for GoK, with the Ministry for Industrialisation and Enterprise Development (MoIED) mandated to lead the agenda. The project presented and discussed a Doing Business action plan with MoIED, and technical support was provided to the Unit, which was launched on 8 October 2014 by the Deputy President. The capacity score is based on how many out of nine generic conditions are met for an effective organisation.[3] Currently only the budget condition is unambiguously met, with a budget of KSh 120m that is sufficient to meet their operational expenses.
  [3] The 9 conditions are as follows: appropriate mandate and organisational chart formally agreed; suitable staff in place according to organisation chart; operational procedures agreed to deliver services effectively and efficiently; staff satisfactorily trained in operational procedures; all staff have gained experience in applying the procedures to deliver services; management is ensuring that lessons learnt from applying procedures are being used to improve services; organisation is coordinating effectively with other stakeholders in government to deliver its mandate; organisation has the budgetary resources it needs to deliver its mandate; organisation is headed by a ‘reform champion’.
- Client satisfaction – MoIED: MoIED were ‘Satisfied’ with support from WBG. They were very satisfied with the quality of the assistance provided, with the action plan provided by the project fully used to set their reform agenda. However, they said there was sometimes a lag in support due to the main expert working on a number of other countries. WBG disagree that there was any lag.
Other progress: at the Treasury’s request, the project provided support to its eCitizen portal to automate over 10 GoK services (including the Office of the Auditor General and the Kenya Revenue Authority), by digitising the e-registry platform that WBG had already developed for Kenya.
Issues: more resources are needed to support the reforms at the Ministries, and they are not getting sufficient traction from other Ministries in implementing the reforms. Coordination may be necessary from the Office of the President (where a new Delivery Unit is being set up) or an inter-ministerial committee.

Component 2: County regulatory reform
Progress against indicators:
- Construction and business permits: the number of pilot counties was increased from three (Mombasa, Kisumu and Nairobi) to five (adding Nyeri and Machakos) after the Council of Governors advised that a rural county should be included. However, due to a lack of demand from Nairobi, support to it will be limited to automating the planning process to enhance the electronic construction permitting system. By June 2014, Single Business Permit (SBP) reports had been drafted for all four counties. Their reform recommendationsfor Kisumu and Mombasa were validated, while Machakos and Nyeri were still providing comments. Construction Permit reports were drafted for Kisumu and Mombasa, and their reform recommendations validated.
- Client satisfaction – County govts: it has not been possible to interview them this time.
Other progress: in addition to SBP and construction permits, it was agreed to provide support to Nyeri and Machakos on investment promotion, focused on setting up investment portals.
Issues: Machakos continually delayed signing the cooperation agreement with WBG and so it was decided to no longer provide them with support due to a lack of high-level political commitment. Embedding and sustaining this work requires engagement with the Assocation of Governors.

Component 3: Trade logistics
Progress against indicators:
- Business process reviews: by June 2014, a business process review of Kentrade was conducted, to streamline their role in the cargo clearance process. Reviews of a further 14 trade facilitation agencies have subsequently been made to enable them to receive and approve applications for permits electronically through the Kenya National Electronic Single Window System (KNESWS).
- Client satisfaction – Kentrade: Kentrade were ‘Satisfied’ with support from WBG. They were very satisfied with the quality of the assistance, and thought that the support from the project (and also from the Investment Climate Facility – see below) had enabled the System to be implemented at least two yeas earlier. However, delays in procurement meant that they could not be ‘Very Satisfied’.
Other progress: KNESWS was officially launched in May 2014 at an event attended by heads of state from Kenya, Uganda and Rwanda. It is an electronic platform that provides a single entry point for the clearance of documents for importing and exporting, to reduce cargo clearance times and costs. At launch, the system was functioning with a few modules with seven government agencies connected to it.[4] GoK bought the software themselves, while development partners (IFC, Investment Climate Facility, USAID) have provided assistance on the processes around it and capacity building of stakeholders. The IFC’s specific support to date has included: training and study tours for Kentrade; analysis of legal issues and ICT needs of GoK agencies, development of standard operating procedures; facilitating setting up of an epayment system using the KRA payment gateway, and a communications strategy. Support has also been provided to get Kenya Bureau of Standards to take a risk-based approach to checking cargo.
[4] Kenya Revenue Authority (KRA), Kenya Bureau of Standards (KEBS), Kenya Plant Health Inspectorate Service (KEPHIS), Pharmacy and Poisons Board (PPB), Port Health, Horticultural Crop Development Authority (HCDA), and the Directorate of Veterinary Services (DVS).
Issues: some of the seven agencies are slow to switch completely to using KNESWS, most notably the KRA who are currently only using it for 30% of their approvals of import declaration forms (and are responsibe for 76% of transactions). Although the KRA had committed to using KNESWS for all transactions by the end of February 2015, this has not been done. Any new KRA system needs to take account of the KNESWS – TMEA and IFC should coordinate on this. Internet connectivity and basic equipment for officers at border posts and Mombasa are lacking, which the project will be addressing.

Component 4: Business Taxation
Progress against indicators: indicators are not in the logframe since this component has just started.
Other progress: training delivered to 100 government officials (including county representatives) on drafting tax legislation and regulations; engagement with government to improve the tax procedures code; conducting a study of the tax burden in the agribusiness sector; and strong KRA engagement throughout the programme design process.
Issues: WBG are having problems accessing GoK tax data which may delayed implementation. It is unclear if this is because it doesn’t exist, GoK is unwilling to share, or there are time lags in retrieving it.

Summary of responses to issues raised in previous annual reviews
- Review choice of which counties to pilot in and planned activities: done (see above).
- Clarify with Registrar General’s Office whether business registration can be done at county level: the suggestion from the Office was to decentralise some services to cities that can serve sub-regions e.g. Mombasa, Kisumu and Nakuru.

Recommendations
- National regulatory reform: DFID Head of Office to meet with the MoIED Cabinet Secretary and the new Presidential Delivery Unit, to discuss priorities for the new Units, including how to ensure sufficient cooperation from other Ministries.
- County regulatory reform: DFID visit at least one pilot county to get feedback; output target be updated to add replace Machakos SBP with Nyeri investment portal.
- Trade logistics: DFID set up a meeting of Kentrade, KEPSA, IFC and TMEA on how to apply greater pressure on GoK agencies to use KNESWS (such as the Presidential Roundtable process); change logframe indicator to percentage of transactions using KNESWS.
- Business taxation: add logframe indicators for the expected results.

Output Title	Effective competition
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	2014 Planned	2014 Actual	Extent Met
Output Indicator 2.1 (Manufacturing): Number of industrial sector action plans that meet quality criteria and are adopted by GoK (cumulative)	0	0	N/A
Output Indicator 2.2 (Tourism): Number of short-term tourism initiatives completed (cumulative)	1	1 / (tourism directory)	Met (A)
Output Indicator 2.3 (Agribusiness): Number of laws and regulations drafted to support agribusiness (cumulative)	2	2 / (WRS & seeds)	Met (A)
Output Indicator 2.4 (Competition Policy): Number of laws and regulations drafted to increase market competition (cumulative)	2	2 / (various – see below)	Met (A)
Output Indicator 2.5 (Whole Output): Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance (MoIED, MoEAACT, MoA, CAK)	70%	100% / (MoIED - Satisfied, / CAK – Very Satisfied / MoEAACT, MoA – N/A)	Met (A)

Component 5: Manufacturing, Tourism & Innovation
Progress against indicators:
- Industrial sector action plans: on MoIED’s request, value chain studies have been drafted for textiles/garments, furniture and leather, and a prioritisation of food-processing sub-sectors. For textiles/garments the action plan has been agreed and started implementation, while the others are still being discussed. They will be part of GoK’s industrialisation roadmap, which the Ministry is drafting with help from McKinsey. Quality criteria to assess the action plans have not yet been agreed between DFID and WBG. Drafts are generally to a good quality but shoud include risks.
- Tourism initiatives: the online tourism product directory is now live on the Magical Kenya website (www.magicalkenya.com) run by the Kenya Tourism Board. It will be publicly launched shortly.
- Client satisfaction – MoIED: MoIED were ‘Satisfied’ with support from WBG. Although very satisfied with the quality of the studies (as evidenced by their adoption already of the textiles/garments action plan), they felt that the studies had taken too long (over a year). However, DFID’s view is that these delays were due to good quality assurance provided by WBG, and so were justified.
- Client satisfaction – MoEAACT: it has not been possible to interview them about the tourism work.
Other progress: a full-day workshop was organised in April 2014 with the Ministry of Education Science and Technology on the proposed Kenya Observatory for Science, Technology and Innovation.
Issues: the other short-term tourism initiative that was planned (an accommodation grading system) has been shelved following consultation with Kenyan industry stakeholders. Alternatives being pursued are assistance to Kenya Wildlife Service, and a study quantifying tourism’s contribution to the economy. However, the impact of additional work will be limited without better national and international market segmentation, and an improvement in the security situation.

Component 6: Agribusiness
Progress against indicators:
- Laws and regulations drafted: on warehouse receipts, the Warehouse Receipts Bill was approved by Cabinet in August 2014. This is to allow farmers, producers, and traders of agricultural commodities to access bank loans by using as collateral their warehouse receipts issued against commodities deposited in warehouses. On seeds, the Kenyan seed sector is dominated by a state seed monopoly, limiting productivity and the entrant of new market players, and by a pervasive counterfeit seed trade. Three WBG-supported seed sector regulations to tackle anti-competitive practives have been submitted to the Cabinet Secretary for publication in the Kenya gazette. On pyrethrum, comments on draft regulations were provided to eliminate restrictions on competition.
- Client satisfaction – MoA: it has not been possible to interview them.
Other progress:
- Warehouse receipts: a roadmap for the initiative was agreed with MoALF. A pilot is ongoing with 2,500 farmers and 6 banks. Training of farmers, operators, banks and the public sector is planned.
- Seeds: roadmap was agreed with MoALF, and a study on the impact of fake seeds is underway.
- Pyrethrum: roadmap was agreed with MoALF, and a strategy to revitalise the sector drafted in consultation with stakeholders. A study of the market for pyrethrum in the EU and US was conducted.
Issues:
Warehouse receipts: rollout of the training at a larger scale is necessary to ensure sufficient uptake.
- Seeds: ensuring implementation of the regulations will be a big challenge given the political economy. Also, there are many players in seeds with it unclear that IFC are coordinating fully with them all.
- Pyrethrum: the issues ailing the sector go beyond competition and are more complex than earlier envisaged. WBG needs to think carefully whether recovery of it is feasible, and if not to withdraw and redeploy resources to ensure value for money.

Component 7: Competition Policy
Progress against indicators:
- Laws and regulations drafted: two sets of guidelines have been completed, one on restrictive trade practices, merger controls and exemptions to horizontal restrictive trade practices, and another on cartel detection, merger reviews and fines. The guidelines on fines have already been used in settling a case of price fixing between two supermarket chains in Nairobi, and a case with Safaricom.
- Client satisfaction – Competition Authority of Kenya (CAK): Very Satisfied with WBG support. The local presence of WBG staff with expertise on competition policy was very welcome. However, there was a concern that WBG staff are spread too thinly as they cover the whole region.
Other progress: the WBG team drafted protocols between CAK and three sector regulators (telecoms, civil aviation and the Central Bank) to ensure coherent competition enforcement, and facilitated six workshops for CAK staff, business associations, journalists and two universities (around 100 people).
Issues: the head of the CAK has a high level of ambition and good ideas on how to create change. He is keen to generate public debate about the cost to the poor of agricultural regulation, and to work on preventing uncompetitive behaviour by county governments and bid-rigging in GoK procurements.

Component 8: Investment Policy
Progress against indicators: indicators are not in the logframe since it has just been started.
Other progress: the objective of the investment policy component is to improve the policy environment for foreign investment in Kenya, in particular through improved facilitation of investment at national and county levels. In the first year there are two main workstreams: drafting an FDI strategy for Kenya that assesses the barriers to attracting and retaining investors (informed by a investor survey); and in parallel achieving some quick wins at national and county level, such as setting up an investor tracking system. An 2 day training workshop of officials from 10 counties and KenInvest, KAM and KNCCI has been held.
Issues: KenInvest must be transformed as an institution if it is to play a key role. WBG have good ideas for how to stimulate this, but it may take time. There is also a need for a cross-ministerial leadership team since KenInvest is under MoEACCT, while MoIED also has a big interest in attracting FDI.

Summary of responses to issues raised in previous annual reviews
- Decide how to respond to strong demand from GoK to scale up support on tourism and innovation: WBG and DFID have decided not to scale up the tourism work due to security problems and lack of cohesion between stakeholders in the sector. A decision on innovation needs to be taken.
- Some provision in the agribusiness implementation plan should be retained to tackle new emerging value chain work: MoALF have requested support on additional value chains, but WBG and DFID’s position has been that sufficient progress needs to be first seen on the existing work.

Recommendations
- Manufacturing: DFID discuss and agree with WBG on: quality criteria for the action plans; targets for ‘improved performance’ of each subsector (for Outcome indicator 4); and priorities for influencing and supporting MoIED’s Industrialisation Strategy and its implementation.
- Innovation: DFID clarify with WBG the scale of the innovation workstream, and identify linkages with separate work that DFID East Africa Research Hub is funding on innovation.
- Tourism: DFID clarify with WBG whether the additional short-term initiative on tourism is justified.
- Agribusiness: DFID discuss and agree with WBG on: extent they can coordinate more closely with other stakeholders on agribusiness; targets for ‘improved performance’ of each subsector; the scale of the activities needed to achieve the targets; and an output indicator to capture further activities.
- Competition Policy: DFID and should consider options to provide more support to the Competition Authority, and USAID may want to talk to them about public procurement.

Output Title	Effective environment for public private partnerships
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	2014 Planned	2014 Actual	Extent Met
Output Indicator 3.1 (PPPs): Number of PPP regulations (R) and Fiscal Commitment and Contingent Liability (FCCL) frameworks (F) drafted through adequate consultation (cumulative)	R:1 F:0	R:2 F:0 / (National PPP regulations)	Met (A)
Output Indicator 3.2 (PPPs): Number of GoK officials satisfactorily trained in the PPP Unit (cumulative)	4	5	Met (A)
Output Indicator 3.3 (PPPs): Number of PPP transaction feasibility studies at national (N) and county (C) level completed and approved by PPP Committee	N:0 C:0	N:1 C:0 / (Kenyatta University Hostels)	Overacheived / (A+)
Output Indicator 3.4 (Renewable Energy): Number of laws, regulations and e-portals drafted to support renewable energy (cumulative)	3	3 / (Electricity Bill; net metering; renewable energy e-portal)	Met (A)
Output Indicator 3.5 (SEZs): Number of laws (L), regulations (R), site feasibility reports (F), market demand reports (M), developer requests for proposals (D) and investment targeting strategies (I) drafted to support investments in SEZs (cumlative).	L:1 R:0 M:0 D:0 I:0	L:1 R:0 M:0 D:0 I:0 / (SEZ Law)	Met (A)
Output Indicator 3.6 (SEZs): Capacity score of the SEZ Authority.	0	0	N/A
Output Indicator 3.7 (Whole Output): Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance (e.g. PPP Unit, ERC, MoIED)	70%	100% / (PPP Unit –Very satisfied; / MoIED – Very Satisfied; ERC – Satisfied).	Overacheived / (A+)

Component 9: Public Private Partnerships (PPPs)
Progress against indicators: overall on track:
- Regulations & fiscal frameworks: by June 2014 national PPP regulations had been drafted to operationalise the PPP Act, and have now been approved by parliament and gazetted; county PPP regulations have later been drafted for consultation.
- Training PPP Unit: the PPP unit is now fully staffed and operational to support GoK in designing and implementing PPPs. 5 staff have initially been trained (although data on satisfaction ratings was not collected), and a training company has been hired to roll out training to more of their staff and also the 36 nodes in GoK contracting authorities (line Ministries, parastatals, county governments). Four national consultants have been recruited to provide support on Legal, Technical, Financial and External Affairs. The unit’s website (www.pppunit.go.ke) is live.
- Feasibility studies: the project is to provide targeted support to six ‘first mover’ PPP projects taken from GoK’s list of around 60 priority PPP projects.[5] One feasibility study has so far been conducted and approved for the Kenyatta University Hostels project.
  [5] Nyali Bridge, Mombasa; Mombasa-Nairobi Highway; Nairobi-Nakuru Highway; Nairobi Southern Bypass O&M; Thika Road O&M; and Kisumu Port.
- Client satisfaction – PPP Unt: the PPP Unit were ‘Very Satisfied’ with support from WBG, since although there have been delays in implementation, the transformation in GoK’s capacity on PPPs has been considerable. They now consider themselves to be stronger than their counterparts in Ghana and Nigeria, despite those countries having started working on PPPs earlier than Kenya.
Other progress: Six PPP transaction advisors been procured. There appears to be good political support, with the Presidency wanting regular udates on progress. Plans for a Public Facilitation Fund (PFF) to scale up financial and technical support to PPPs have been drafted, including a viability gap fund to attract investors for financially non-viable projects that have high development impact.
Issues: The main issue has been delays in procurement (particularly of transaction advisers) that have held up the project pipeline. The two stage procurement procedures required by WBG and staff turnover at the Bank are partly to blame for this. However, the Unit will now procure transaction advisors in advance of need to shorten the procurement cycle.

Component 10: Renewable Energy
Progress against indicators:
- Laws, regulations & e-portals: Progress had been made on the main areas of work. The renewable energy portal (www.renewableenergy.go.ke) was launched in July 2013 but we lack evidence on its use by private sector investors. Best practice guidelines and draft PPA templates were developed and handed over to the Energy Regulatory Commission (ERC). Net metering and wheeling draft regulations were developed and disseminated (jointly with the EU PDF programme) but GoK has not formally adopted them. Pilot sites were to be identified for net metering and are in progress. Comments were provided to the GoK task Force on the draft Energy Bill and Electricity policy and the uptake of comments is being tracked. The Nationwide Demand and Cost assessment for off-grid electrification in Kenya study has been initiated at the request of the ERC. This is aimed to fast track rural access to electricity and help identify opportunities for commeriaclly sustainable mini grids.
- Client satisfaction – ERC: The ERC is Satisfied with the support and responsiveness of the WBG, mentioning that the work on the renewable energy portal and the draft regulations has been useful.
Other progress: The Competion Authority and the Privatisation Commission are undertaking energy product market regulation studies which could be linked to the work being done under this programme.
Issues: There are broader challenges with the single utility model (Kenya Power) and the uniform tariff model in Kenya which is affecting the private sector entry into the transmission and distribution sectors, especially for off-grid and mini- grid renewable energy sector. There is need to carry out an assessment of the various regulatory permits and licences required by investors/developers in this sector for off grid and mini grid projects that can enhance energy access.

Component 11: Special Economic Zones (SEZs)
Progress against indicators: on track:
- Laws, regulations, site feasibility reports, market demand reports, developer requests for proposals & investment targeting strategies: the SEZ component has two objectives: to support the development and adoption of a new globally competitive SEZ legal and regulatory framework; and to help GoK to attract at least one international developer and one anchor investor, based on the new SEZ framework. This has been held up by delays in approving the SEZ Law, which was originally submitted to parliament in 2013 but was not approved due to elections. Under BRICK, the WBG have reviewed the law to incorporate devolution and reassess the incentives structure. It has subsequently been approved by Cabinet and submitted to Parliament. In parallel, WBG have been working closely with JICA and MoIED to identify the most suitable location for the first SEZ, with a comprehensive assessment of two potential sites, of which the Dongo Kundu site in Mombasa has been selected. A market demand report for the Dongo Kundu site is the next planned output.
- Capacity of SEZ Authority: establishment of the Authority is pending approval of the SEZ Law.
- Client satisfaction – MoIED: MoIED were ‘Very Satisfied’ with support from WBG, saying that the consultant providing them with technical assistance was to a very high standard.
Other progress: WBG have also provided capacity building to MoIED on SEZ best practice, which was influential in getting agreement on issues that were holding up Cabinet approval.
Issues: there are two main risks. Firstly, insufficient political support for SEZs, which further delays the SEZ Law being passed by Parliament and prevents its implementation. And secondly, that two many SEZs are worked on at the same time, stretching GoK resources too thinly to enable any of the SEZs to be successful. There is also concern that with the move of the WBG adviser to a global expert role, they will have less time available to spend on the project.

Summary of responses to issues raised in previous annual reviews
Agree next steps for the renewable energy component given that work on the wheeling regulations is not possible: WBG team to work instead on regulation to promote off-grid electricity.

Recommendations
- PPPs: WBG should aim to minimise further staff turnover on the PPP workstream; DFID should consider providing support to the PFF as part of its successor funding on PPPs for BRICK, and influence other development partners to do the same.
- Renewable Energy: evidence needs to be provided on the use of the renewable energy portal by private sector investors; and the uptake of guidelines and regulations by GoK needs to be monitored.
- SEZs: DFID to discuss with WBG political economy issues around SEZs, and in particular how to ensure support for the Dongo Kundu SEZ from Kenya’s political and business elites.

Output Title	Strengthened demand and evidence base for investment climate reform
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		New component	Impact weighting % revised since last AR?	New component

Indicator(s)	2014 Planned	2014 Actual	Progress
Output Indicator 4.1 (PSD Champions): Number of GoK officials satisfactorily trained on private sector development (cumulative)	0	0	N/A
Output Indicator 4.2 (KEPSA): Extent that a Change Management Plan is drafted and implemented to help make KEPSA 'fit for purpose'	Change Mgt Plan drafted to make KEPSA fit for purpose	Drafted in Dec 2013	Met (A)
Output Indicator 4.3 (Private Sector Consultation): Number of BRICK components for which private sector inputs have been received through adequate consultation	N/A	N/A	N/A / (is a new indicator so no data collected for the period)
Output Indicator 4.4 (Investment Climate Diagnostics): Number of Investment Climate reports produced (P), formally launched (L) and rated as Satisfactory on average by targeted GoK agencies (S)	P:2 L:1 S:n/a	P:2 L:1 S:n/a / (Manufacturing export competitiveness; micro and small enterprise development in Kenya)	Met (A)

Component 12: Private Sector Development (PSD) Champions
Progress against indicators:
GoK officials trained: no training was conducted by June 2014 since the component was in design. However, In November 2014, an investment policy and promotion training was conducted attended by 10 counties, Keninvest, KAM and the National Chamber of Commerce. 97% of the participants rated it from satisfactory to excellent. The objective was to share knowledge and tools to attract, facilitate, retain and grow investment.
Issues: the component appears to be proceeding slowly if it is to achieve the 2015 milestone of 10 GoK officials being satisfactorily trained on private sector development, since this requires exposure for a carefully selected group of officials to a wide range of topics. If not fully underway by 90 days from this Review, DFID should ask these reources to be withdrawn and/or refocused.

Component 13: KEPSA
Progress against indicators:
- Change management plan: the new business strategy was drafted in December 2013. It makes recommendations for how KEPSA can better discharge its advocacy mandate and improve its financial sustainability. At the time of this review, good progress was being made towards the milestone for 2015 of “Plan approved by the KEPSA Board and at least 50% implemented”. The KEPSA Board signed off on it in April 2014. Staff have been recruited (on policy, research, advocacy and membership) to meet the new strategic objectives, while existing staff are changing their day to day behaviour and owning the new strategy. For the first time, event fees were charged for joining the December 2014 Presidential Roundtable.
- Private sector consultation: this indicator is to track how consistently WBG are consulting with key private sector stakeholders in each of the separate components, given that it is essential to ensure that reforms are appropriately designed and sustainable. No target was set for 2014 given that it was agreed after the reporting period. A methodological note for how it is to be monitored has been provided by WBG, but it is not clear whether data collection has started.
Other progress: WBG have provided two consultants to KEPSA. One is supporting KEPSA with investment climate issues and the other with legal issues. As a result, KEPSA feels its quality of engagement with Parliament on legislative issues has improved and it is now able to track almost in real time various investment climate reforms and provide its inputs.

Issues:
- A systemised approach to performance management is yet to be finalised, with Strathmore University helping KEPSA to establish a Balanced Scorecard performance tool and set trackable strategic targets down for individual KEPSA staff. This should be prioritised.
- Better policy dialogue depends on new staff getting down a learning curve and the CEO enabling them to engage top counterparts.
- In the first year of the new Government, KEPSA had felt that the quality of engagement was low. However, there has been a step up recently – agreement on biannual Presidential business to Government meetings (on business environment & sectoral issues). The December 2014 event was seen as effective by comparison with previous ones. In addition, the CEO is now part-embedded in office of the President two half days weekly, working on range of policy matters e.g. administrative management of business policy issues and promoting foreign investment.

Component 14: Investment Climate Diagnostics
Progress against indicators:
Investment climate reports: By June 2014, two main reports were produced with BRICK funding: ‘Manufacturing Export Competitiveness’, and ‘Micro and Small Enterprise Development in Kenya: a Review of Policies, Institutions and Programs’. Only the latter was publicly launched as a Sector Economic Outlook Note at an event with KEPSA. The component appears to be on track to achieve the milestone of an additional give reports produced by June 2015. Assessment of the quality and dissemination of these will be done for the 2015 Annual Review.
Issues: there is a risk that WBG produce reports without adequate attention to their dissemination and policy influencing around them. For instance, it comes as a surprise that the manufacturing export competitiveness study was not actively disseminated in-country. However, it has been published on WBG’s website, and some of its findings were incorporated into the recent manufacturing report in the Kenya Economic Update (KEU). More recently, WBG have been doing an excellent job in disseminating the KEU report, which has been presented in a number of fora. WBG have been consulting with stakeholders to decide on the focus of the informality report on the 2013 Enterprise Survey. They should do the same for the in-depth manufacturing study, with MoIED staff expressing to DFID a strong preference to be consulted on it to inform their industrialisation roadmap.

Summary of responses to issues raised in previous annual reviews (where relevant)
Include a capacity building component across the programme: this has been done in the form of the PSD Champtionsn component (see above).

Recommendations
- PSD Champions: check that plans for the rest of the 2015 reporting year are sufficient to meet the milestone.
- KEPSA: ensure that KEPSA staff members are clear on what their role is in increasing financial sustainability, and are empowered to fulfil this objective.
- Investment climatic diagnostics: WBG design the in-depth manufacturing study to address (where possible) key policy questions raised by MoIED and key issues for policy influencing identified by WBG (in consultation with DFID).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key costs are as follows: consultants 35%; staff 34%; travel 13%; and administrative fees and expenses 9%. The breakdown of the budget by the different programme components is as follows: county regulatory reform 16%; PPPs 15%; agribusiness 14%; trade logistics 12%; manufacturing, tourism and innovation 11%; SEZs 10%; KEPSA 10%; business taxation 7%; investment policy 7%; competition policy 7%; renewable energy 5%; national regulatory reform 4%; PSD champions 3%; investment diagnostics 1%; with 3% unallocated (initially intended for work on property taxation in Mombasa which has been delayed).

The WBG are currently not able to complete DFID Kenya’s VfM Actions Template, since it goes beyond their normal reporting to donors. On Economy, they follow WBG’s standard procurement procedures which are of a high standard. On Effectiveness, they are following a number of good practices. Firstly, wherever possible they require GoK contributions as a sign of commitment to ensure sustainability. For instance, for the agribusiness component they have required a 20% contribution from MoALF. Secondly, they have been proactive in engaging parliamentary committees in order to expedite passing of the SEZ and Warehous Receipts Bills. And thirdly, they have only provided assistance to GoK agencies that have demonstrated sufficient demand for assistance e.g. in their choice of counties. We currently lack information on their practices to promote Efficiency.

VfM performance compared to the original VfM proposition in the business case
The VfM indicators that can be applied to the programme are the following:
- Economy: one of their biggest inputs is consultants, and so benchmarking of their consultancy fees would be appropriate. Their commercial rules preclude them from sharing with DFID the actual fees they are paying, but at the time of doing this Review, they have agreed to share their fee bands.
- Efficiency: WBG are charging a 5% trust fund administration fee, which is in line with DFID guidance. The budget agreed in the DFID-IFC MoU charges 10.5% of each component to programme management and supervision. However, WBG have to date not been willing to report on what this has been spent on, and so it is not possible to benchmark BRICK’s admin costs against other projects.
- Cost effectiveness: two measures may be used here:
  - Cost per compliance cost savings: this is proposed by the IFC in the DFID-funded ‘Value for Money in Investment Climate Report’.[6] This can be used to compare the regulatory reform, competition policy and trade logistics components, since planned compliance cost savings have been estimated for each, and actual savings will be gathered.
    [6] Currently in draft, most recent version August 2014.
  - Investment leverage ratio: the ratio of donor funding to private investment generated. This can be used to compare the PPP, renewable energy and SEZ components, since planned investment generated has been estimated for each, and actual investment generated will be gathered.
- Economic return: for some components, cost benefit analysis can be conducted. These are:
  - Trade logistics: the project has funded a ‘Baseline Survey on the Benefits of the Single Window System in Kenya’ which estimates both the economic benefits and costs. A key assumption underpinning this analysis is that cargo clearance delays at Mombasa Port are largely caused by administrative procedures as opposed to delays in the physical movement of the cargo itself. This is essential to resolve, since DFID is funding improvements to infrastructure at the Port which rest on the opposite assumption. The benefits may be attributed to the WBG and Investment Climate Facility based on Kentrade’s view that without their support, the Single Window would have been delayed by two years.
  - Competition policy: the WBG team are working with the Competition Authority to estimate the economic impact on firms and consumers from various actions taken by the Authority. For instance, the WBG helped the Authority to rule recently against two supermarkets operating in the Central Business District of Nairobi who were limiting their price competition. WBG estimate that this resulted in consumer savings of $1.2m a year. The Competition Policy component itself has a total cost of $1m, and so from that ruling alone its costs have been covered with a high return.
  - Warehouse Receipts and County regulatory reform: impact studies are being conducted into the impact of the warehouse receipts and business registration reforms on incomes and job creation. This can inform cost-benefit analysis of each component.

DFID has explored with the WBG whether the programme could be used as an official pilot for VfM analysis. However, there appears to be insufficient interest from the WBG centrally in this. DFID should therefore do the analysis suggested above itself, ideally before WBG’s own mid-term review of the programme.

Assessment of whether the programme continues to represent value for money
The project is likely to continue representing value for money but needs further analysis:
- Results: are on track, with the project scoring an A for its Output results. Progress against its Outcomes is harder to judge and will require greater attention to political economy.
- Costs: remain on track (see Financial management below).
- Risks: remain at Medium (see Risks below).
- Theory of Change: this needs to be further analysed to check is validity (see M&E below).
- VfM practices: these appear good for Economy and Effectiveness, but it would be good to learn more about how WBG are promoting Efficiency.
- VfM measures: full analysis of these is yet to be done, but initial evidence emerging (such as on consumer savings from the Competition Policy component) suggests the potential for very high returns.

Quality of financial management
DFID has cumulatively disbursed £8.14 million out of £12.6million to IFC and KEPSA (£1.38 million) since the approval of BRICK to support the implementation of project activities. The delivery of the programme activities is on track with the spending forecasts. The KEPSA component has however exhausted its funding allocation and will require a cost extension in order for DFID to continue its current commitment to support the implementation of the change management strategy aimed at strengthening the institution’s capacity and propelling it to sustainability.

Date of last narrative financial report	29 September 2014
Date of last audited annual statement

Recommendations:
- DFID conduct detailed VfM analysis of the programme, including gathering information on WBG processes to promote Efficiency, benchmarking consultancy and administrative costs, comparing cost effectiveness between components, and cost-benefit analysis of the trade logistics component.
- DFID bring together WBG, TMEA and Kentrade to agree on the extent to which delays at the Port are being caused by lack of infrastructure or inefficient bureaucratic processes.

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk
The current version of the BRICK live risk matrix is attached in Annex. The key risks to achieving the Outcomes are given as follows:
- Delays of legal enactment: the Warehouse Receipts Bill and SEZ Law have been drafted and are pending approval by Parliament. WBG have been taking a proactive approach to managing the risk of delays by raising the awareness of the relevant parliamentary committees.
- Political support and reform champions: for a number of components much of the technical work has been done, with achieving the Outcomes dependent upon political support e.g. implementation of seed regulations, manufacturing action plans, Doing Business reforms, and the Single Window. GoK commitment to improving the business environment is higher than any time since 2008, providing an opportunity to assist Kenya to address some of the key constraints quickly if we are opportunistic. WBG and DFID need to be more politically savvy to ensure this support, building coalitions of change that includes not just the private sector facilitated by KEPSA, but also sections of the political and business elite whose interests are potentially aligned, and the media and general public.
- PPPs and political sensitivity: the selection of PPP projects for political not technical reasons is given in the risk matrix as having a High residual probability and High residual impact. This should be doublechecked as if true, it requires much greater senior management attention.
The key programme-level risks to achieving the Outputs are as follows:
- National referendum: this will delay all projects with GoK. Having been originally flagged by WBG, this risk has been added to DFID Kenya’s Operational Plan risk matrix.
- Poor coordination between components: with such a large number of components across two organisations, there is a risk that potential synergies are missed. The integration of World Bank and IFC staff under the Trade and Competitiveness Practice should assist this. Having a shared high-level Theory of Change that shows how all the components are linked may also help (see M&E section).
- Fraud & corruption: still remains low; propoer checks and balances including audit and due diligence assessments have been built into the programme’s management to mitigate risks.

The key risks to each invidual Output are covered under the Issues for each Output above.

In order to be useful for project management, the risks should be based on explicit analysis of progress towards Output and Outcome targets.

Outstanding actions from risk assessment
- WBG and DFID senior management meet to discuss whether more could be done to build coalitions of change to support some of the key reforms, and if so, how.
- DFID meet with each component team to explicitly assess risks to non-acheivement of Output milestones for 2015.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme is on track with delivery; £6.8million of the funding has already been disbursed to IFC and £ 1.3million to KEPSA for project implementation; this leaves a balance of £4.5million projected to be disbursed to IFC by December 2015.

Performance of partnership(s)
WBG partners have been able to secure strong working relationships with counterparts, and are now getting an unprecedented level of demand from GoK for assistance as it prioritises economic development. Counterparts have rated highly the high technical quality of WBG support, but often flagged a lack of timeliness due to WBG procurement processes or staff being shared across a number of countries and programmes. Apart from the procurement problems for the PPP component, these procurement issues do not appear to be a serious problem, with procurements below $50,000 able to be handled by WBG locally. Regarding staffing levels, the project manager has argued that sharing of staff across countries is the way the WBG operates everywhere, and he is not aware of staff constraints being an issue limiting delivery in any component. Further discussion on this staffing issue are warranted.

KEPSA contracted the strategy formulation and implementation process to Farasi consultants and the two organisations continue to have a good working relationship. KEPSA is currently in the process of procuring a consultant to help develop a balanced scorecard as a performance management tool and involves DFID in major procurements e.g. of strategy consultants and key personnel.

Asset monitoring and control
The asset monitoring and control under the IFC component is governed under the IFC-DFID MoU.[7] The KEPSA component is governed under the KEPSA-DFID MoU[8] which is not explicit on asset control.
[7] It is stated: “IFC commits to utilize the funds provided by donors for the purpose of financing the activities  of the program (including equipment and furniture) within the framework of the program in accordance with IFC policies and procedures and any provisions and conditions detailed in the MoU. Any equipment purchased can be transferred to the project beneficiaries or disposed according to IFC procedures upon termination or closure of the project”
[8] KEPSA will administer and account for the Contribution in accordance with its financial regulations and other applicable rules and procedures and practices and keep separate records and accounts for the Project. The Contribution will be solely for the element of the ‘Institutonal Strenthening and Policy Support Programme’.

Recommendations:
WBG and DFID senior management discuss whether WBG can allocate greater staff resources to the project or cut down on its complexity.

G: CONDITIONALITY (½ page)

The BRICK programme does not use government systems for delivering its results. DFID Kenya has therefore judged that the PPs do not apply in the detailed management and monitoring of this programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The Theory of Change (ToC) provided in the DFID Business Case was too basic. WBG have therefore drafted ToC diagrams for some components, while the DFID lead adviser has drafted an overarching ToC diagram for how all of the components contribute to the Outcomes and Impacts. These should be completed, with the assumptions used to: a) check the validity of the ToC; b) update the assumptions in the logframe; c) update the risk matrix; and d) inform M&E plans. Ideally ahead of WBG’s mid-term evaluation in May.

Various pieces of research have either been commissioned by WBG or are about to be:
- Agribusiness: a study on the effects of a warehouse receipts system on farmers incomes.
- Business registration: a study on the effects of changing business registration rules on job creation.
- Trade logistics: a study baselining the cargo clearance process at the Port and does a cost-benefit analysis of the Single Window.
- Competition policy: WBG have provided a framework for impact assessment to the CAK, and will soon be releasing estimates of the economic impact of recent reforms or restrictions.

There is a significant lag to the Outcome results, with WBG seeing many of them occurring in 2019 despite the project finishing in 2016. There is therefore a strong case for a follow-up study of the project around 2018. Plans for this should be made now as part of a review of the Wealth Creation portfolio.

The logframe currently has no indicators related to gender. DFID and WBG both have specialists in the gender analysis of private sector development projects, who should be tasked to work together.

Monitoring progress throughout the review period
Nearly all of the indicators in DFID’s revised logframe are taken from WBG’s results framework. This is to minimise transaction costs and maximise accountability. Since WBG’s reporting period is from July to June, there is a need to change the timing of DFID Annual Reviews from March to September. This Annual Review in March therefore scores the project against the milestones from July 2013 to June 2014, and the next Review around August will use the milestones from July 2014 to June 2015.

The six monthly Progress Reports on the project produced by the IFC donor coordination team provide a summary of what has been achieved, the issues and next steps. However, they are currently not reporting using the WBG’s revised results framework, which DFID’s logframe is based upon. This reduces its usefulness as a way to track results.

Recommendations
- WBG to finish ToC diagrams for the components and DFID to finish the ToC diagram for the programme as a whole.
- Make plans for a follow-up study of the project around 2018.
- WBG to suggest gender-sensitive indicators for the logframe, with support from DFID.
- Hold next Annual Review around August 2015 to align with the WBG reporting cycle.
- Progress Reports report against WBG’s revised results framework.

Endnotes