Flag B
Business Case

Infrastructure for Climate Resilient Growth in India

Summary Sheet

Title: Infrastructure for Climate Resilient Growth in India
Project Purpose: To strengthen the resilience and livelihood security of the rural poor in India, by supporting the construction of better quality and more productive infrastructure under the Mahatma Gandhi National Rural Employment Guarantee Scheme.
Programme Value: £10 million		Country/ Region: India
Project Code: 204794	Start Date: June 2015	End Date: June 2019
Overall programme risk rating:	Medium
Quest Number:	4893282, 4893396, 4893368, 4893429

Intervention Summary

What support will the UK provide?
We will provide £10 million technical assistance over four years (2015-2019) to improve the quality of the rural infrastructure built under the Mahatma Gandhi National Rural Employment Guarantee Scheme (MGNREGS). The programme will target some of the poorest and most vulnerable people in India, especially poor women, improving their resilience to climate change and making their livelihoods more secure.

What are the main programme activities?
We will select a Management Agency through a competitive process to provide:
Technical assistance at national level to the Ministry of Rural Development, which will:
- Generate evidence and share it, so as to (a) inform a stronger policy focus on the design and implementation of infrastructure under MGNREGS, and (b) strengthen the evidence base on how better physical assets can support livelihoods that are more resilient to flood, drought and high temperature.
- Strengthen MGNREGS systems and processes to ensure better delivery, especially the construction of better planned and better quality infrastructure that improves the resilience of the rural poor. This will include the development of innovative, especially IT based, tools.
Technical assistance to strengthen implementation in selected districts in three states, which will:
- Strengthen the capacity of state governments and local implementation agencies to better plan, build and monitor the construction of physical assets under MGNREGS;
- Strengthen the capacity of technical organizations such as academic institutions, technical engineering institutions, training organizations, Civil Society Organizations and development of a cadre of technical resource people (`barefoot engineers’) to support the implementation of MGNREGS.

Why is UK support required?
60% of people in India depend for their livelihoods on rain-fed agriculture which is vulnerable to changing weather patterns and extremes. On current trends, over 120 million poor people (particularly women and girls) will remain highly exposed to climate driven hazards by 2030. However, rural infrastructure that is well planned and constructed can reduce the impact of drought and floods by ensuring good irrigation, and help restore the natural resource base. MGNREGS invests nearly £4 billion annually in constructing rural infrastructure, while ensuring a wage guarantee to nearly 40 million households.

Although MGNREGS has great potential to reduce the vulnerability of poor families, reviews have consistently found that the assets being built are of low quality and inadequately linked to poor people’s livelihoods. More effective investment in rural infrastructure through MGNREGS to support rural economic growth would ultimately reduce the need to keep funding the scheme, and reduce the likelihood of having to call on external assistance due to the impact of severe climate driven extreme drought, and flood in the future.

The government has recently taken specific policy measures to respond to this challenge, such as requiring a minimum of 60% of the built assets to be for agriculture related activities. However, these measures are in the initial stages, need better evidence to fine tune the policies, and more technical capacity, especially at state level, to implement them.

We are uniquely placed to support this shift because of DFID’s track record of supporting sustainable livelihood and safety net schemes in India and elsewhere, and because of world class UK expertise on these issues including through the Met Office/ Hadley Centre, British Geological Survey (BGS), Natural Environment Research Council, the Centre for Social Protection, IDS Sussex, and so on (see further at paragraph 19 below).

What are the expected results?
The programme will deliver the following results directly attributable to UK support:
- Improved livelihood security and adaptive capacity of 5 million poor to the impacts of flooding and drought;
- Increase in return on investment from the physical assets built under MGNREGS;
- Reduction in loss and damage to public infrastructure from climate extremes;
- Increased evidence base for development of policies to integrate climate in MGNREGS physical assets;
- Improved technical skills of local youth, women and girls, women’s Self Help Groups (SHGs) and local civil society organisations (CSOs) e.g. 2000 `barefoot engineers’ trained on civil engineering concepts;
- Improved systems and processes including through IT based tools to support construction of high quality assets.

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?
The project would help deliver DFID’s recently agreed TA strategy for India. The project draws on the analysis in DFID India’s Inclusive Growth Diagnostic since it targets women, poorest groups such as Scheduled Caste, Scheduled Tribe and Dalits and agriculture workers in poorest districts that have benefited least from India’s GDP growth over the last fifteen years. It combines upstream policy influence and state level capacity building to deliver transformational change through a national programme. Strengthening government systems should improve the efficiency and effectiveness of public sector spend, so that the dividends from economic growth better reach the poor. The project has a compelling cross HMG and International Climate Fund rationale: it would demonstrate the UK’s commitment to support those who will suffer most from climate impacts, which has been central issue in efforts to broker a climate deal under the UNFCCC, and it would be a flagship example of how a climate resilience programme could support economic development.

Finally, the project is based on strong demand from the Indian government for UK technical assistance, which would provide complementary finance through MGNREGS.

What are the key risks to the success of the programme?
The programme level risk is judged to be medium. The primary risk relates to the implementation weaknesses, transparency and potential corruption in MGNREGS at national or state level which may adversely affect the scheme’s reputation and achieving the desired outcome under this programme. We will mitigate this by: (i) rigorous monitoring and evaluation; (ii) engaging closely with government, building on our existing relationships at central and state level; (iii) focusing on those districts and blocks where government is making a particular effort to strengthen MGNREGS effectiveness; (iv) working where local community based organizations, such as women’s Self Help Groups, are active including through the Ministry of Rural Development’s Social Audit initiative..
Strategic Case

One third of the world’s poor people, approximately 300 million, live in India on less than $1.25 a day[1]. On current trends, despite significant progress over the last fifteen years, over 120 million poor people will remain highly exposed to climate related hazards by 2030 in India, more than in any other country.[2] This persistent vulnerability is due to the dependence of more than 60% of the population on agriculture for their livelihoods. Indian agriculture is particularly vulnerable to weather variability and climate change because it is largely rain-fed, with rainfall concentrated in the four monsoon months.[3] Women and girls are disproportionately vulnerable: as crop yields decline and natural resources become scarcer, women’s workloads increase reducing their access to basic amenities like education, water and health services[4] and compromising their time for economic activities and household tasks.
[1] UN Millennium Development Goals report, 2014
[2] i.e. more poor people in India will be highly exposed to climate related hazards than in any other country: The geography of poverty, disasters and climate, extremes in 2030; ODI; 2013
[3] In 2011 Maplecroft Global Risk Analytics ranked India as the second most vulnerable country to the impacts of climate change after Bangladesh.
[4] South Asia: Shared Views on Development and Climate Change; The World Bank 2009

Better physical assets strengthens the resilience of the poor
Sustainable livelihoods are those which can cope with stresses and shocks. Durable and productive physical assets contribute to sustainable livelihoods by providing irrigation services, drought management and restoring the natural resource base. These services can provide a stable income and also improve food security for the poor.[5] Sound rural infrastructure, particularly for irrigation and water management, is therefore key to the livelihoods of the poor and strengthening their resilience to climate change[6]. Various livelihood and natural resource management programmes provide evidence that the income and agricultural productivity of poor farmers increases due to better physical assets. For example, the Independent Commission on Aid Impact (ICAI) review of DFID’s Western Odisha Rural Livelihood Programme found that water management structures built under the programme improved agriculture productivity in 70% of watershed areas and also provided continued benefit two years after programme completion. The review also found that 70% of marginal farmers reported improved capacity to cope with drought.
[5] DFID Sustainable Livelihoods Framework
[6] IISD, IUCN and NRSEI (2003) `Livelihoods and Climate Change: Combining disaster risk reduction, natural resource management and climate change adaptation in a new approach to the reduction of vulnerability and poverty’, A Conceptual Framework Paper Prepared by the Task Force on Climate Change, Vulnerable Communities and Adaptation (www.unigraphics.mb.ca)

Various central and state development programmes support the construction of rural infrastructure. The most significant of these is the Mahatma Gandhi National Employment Guarantee Scheme (MGNREGS)[7], under which poor people are paid a basic wage to construct physical assets for up to 100 days per household each year. With an annual budget of nearly £4 billion, reaching approximately 40 million poor households annually[8], it is the largest labour-based social safety net programme in the world. It has particularly benefitted women, landless people and minorities, reducing distress migration by providing local employment.
[7] This was launched in 2005 under an Act of Parliament: the Mahatma Gandhi National Rural Employment Guarantee Act (MGNREGA). Studies and research use MGNREGA and MGNREGS interchangeably.
[8] MGNREGS has provided 40-50 days employment to 40m households (200 million people) annually for each of the last three years (IDFC 2013 India Rural Development Report 2012-13, Chapter 7)

The physical assets constructed under MGNREGS in rural areas typically include water harvesting tanks, soil and water conservation structures, anicuts[9], irrigation wells, canal repair works and drought proofing measures such as afforestation. MGNREGS funds both community assets as well as individual assets for Scheduled Castes, Scheduled Tribes and people living Below the Poverty Line. These assets can improve ground water levels; increase irrigated area and increase crop productivity to provide additional and sustainable livelihoods for the rural poor.
[9] Dams for regulating water flow for irrigation

Poor quality of physical assets under MGNREGS
Although MGNREGS has great potential to increase the adaptive capacities of poor rural families (beyond wage payments to households), reviews of MGNREGS have consistently found that the physical assets built are of low quality and have inadequate linkages with the livelihoods of poor people[10]. Common reasons for this failure include: (a) the lack of policy focus on assets, (b) weak evidence base on how to use the assets to strengthen climate resilience, (c) weak/ overstretched state and local capacity leading to lack of participatory planning, and poor technical design (see Annex 1 for detail).
[10] 12th Plan Steering Committee on Rural Livelihoods and Rural Governance, Planning Commission India http://planningcommission.gov.in/aboutus/committee/wrkgrp12/rd/strrep_rd.pdf

MGNREGS failure in this regard means that the Indian government is continuing to provide billions of pounds of support to the rural poor each year through MGNREGS, rather than the MGNREGS budget being an investment in the economic development of the rural poor, thereby reducing both the future need to keep funding the scheme and the likelihood of having to call on external assistance due to the impact of severe climate driven extreme drought, flood etc. in the future.

The Government of India’s response
The Indian government has largely been focused on improving the governance of MGNREGS, addressing issues related to delay in wage payment, transparency and corruption. However, despite limited evidence for designing policies which could lead to building better quality assets under MGNREGS, the government has undertaken a few initiatives, especially:
1. Setting a guideline that at least 60% of the works constructed under MGNREGS should support agriculture and allied activities;
2. Developing a strategy for the convergence of MGNREGS with National Rural Livelihood Mission;
3. Publishing a strategy for greening rural development in India, including measures to make communities more climate resilient and improve natural resource conservation under MGNREGS;
4. Initiating a Cluster Facilitation Team (CFT) programme (£21 million over three years) to provide technical support to Panchayat[11] and communities to improve the governance and implementation of MGNREGS. Key CFT deliverables include ensuring at least 75 days of work for Scheduled Caste/ Scheduled Tribe households, payment within 15 days and facilitating participatory planning of works.
  [11] Gram Panchayat is the lowest level governance institution in India in rural areas. There are more than 200,000 Panchayats in 6500 Blocks in India.

These initiatives are all in their initial stages. Better evidence is needed to fine tune the policies, and more technical capacity, especially at state level, to implement them.
What are other donors doing?
Other donors have concentrated on improving the basic functioning of MGNREGS, e.g. ensuring wage guarantee payments are made to the rural poor. UNDP, in particular, has supported the Ministry of Rural Development since the scheme started. It supports capacity building of communities and other stakeholders through awareness generation and mobilization of youth for participatory planning, education and training.

GIZ is supporting the Ministry with a small evidence building programme in 12 Gram Panchayats (out of 200,000) to research how better implementation of MGNREGS (especially improved design and maintenance) can deliver environmental benefits.

How would the proposed programme deliver transformational change?
The proposed programme, Infrastructure for Climate Resilient Growth in India (ICRG-India), will provide technical assistance (TA) to the Ministry of Rural Development (MoRD) and three states to improve the design and implementation of MGNREGS, safeguarding previous investments. The focus will be on assets which lead to resilience through groundwater recharging, development of micro irrigation facilities and integrated afforestation and horticulture. These assets would enhance livelihood security of the rural poor, particularly of those dependent on rain-fed agriculture. This, in turn, could lead to the long term transformation of rural livelihoods in India.

The TA will transform MGNREGS by strengthening policy making at the centre, especially through the incorporating more research and evidence. It will also transform delivery by working with state level scientific and engineering institutions as well as capable technical Civil Society Organisations to strengthening state capacity and creating a stronger institutional environment that would last beyond the programme. Through training and capacity building of MGNREGS functionaries, scientific assessments, research and evidence generation, lessons sharing and applying innovative ICT based tools, the programme will demonstrate effective ways of participatory planning, technical design of climate resilient works and implementation of works. Lessons from state level implementation will be fed back to the centre to shape delivery of the entire MGNREGS programme.

The intervention will emphasise the inclusion of women and girls, marginal farmers and excluded groups, especially by engaging strongly with local community based organizations such as women Self Help Groups (SHGs). Ensuring their voice, choice and control over physical assets will ensure their overall improved resilience by addressing issues such as elite capture and corruption.

1. ICRG will focus on Bihar, Odisha and Chhattisgarh[12], reaching 100 blocks in all. The blocks will be selected in consultation with the Ministry of Rural Development and state governments during the inception phase. The selection will be based on the following criteria:
  [12] The States have been identified in consultation with the Ministry of Rural Development and it is currently flexible.
  1. High level of poverty and vulnerability of poor to climate extremes;
  2. High potential for constructing physical assets to improve the adaptive capacity of the poor;
  3. Good level of MGNREGS governance, for example through the presence of active local community based organizations such as women’s Self Help Groups.
The programme will directly improve the resilience of nearly 5 million rural poor people, and through the lessons learned it will impact the entire MGNREGS scheme which covers all 6500 blocks across India.

Why should the UK support this programme?
This programme will help deliver DFID’s TA strategy for India, supporting a new development relationship with India. It combines upstream policy influence with the generation of evidence from pilot implementation and state level capacity building to deliver transformational change. An MGNREGS, which built strong and productive rural assets, and strengthened the livelihoods of the poor would reduce the need for continuing such an extensive rural safety-net scheme. The new Indian government is particularly focused on MGNREGS as an investment, and wants to make this aspect of the scheme much more effective.

The programme fits well with DFID India’s Operational Plan, Country Poverty Reduction Diagnostic (CPRD) and the International Climate Fund strategy. India’s CPRD includes economic development, women and girls and environment as top strategic priorities. The programme proposes intervening in three low income states, of which Odisha and Bihar are DFID priority states where a significant investment has been made by DFID in poverty reduction. Chhattisgarh is one of the six states in which DFID is supporting implementation of the state’s climate change action plan under the Climate Proofing Growth and Development Programme. By strengthening rural resilience to a changing climate the programme will help safeguard previous investments.

We have strong demand from the Government of India. MGNREGS is delivered by the Ministry of Rural Development. The ministry recognises the challenges set out above and has asked for DFID’s technical assistance, recognizing our track record in India and expertise in sustainable livelihoods, poverty reduction and climate resilience (discussed further below). The programme will significantly extend our engagement with central government, and help strengthen our overall relationship with the Government of India.

The programme will have a transformational impact on the resilience and livelihoods of the rural poor especially women. The intervention will have wider impact locally by building the skills of rural youth, especially women, which would enable effective implementation of other rural development programmes. This includes the National Rural Livelihood Project (covering 13 high poverty states and 622 blocks) and the Integrated Watershed Management Plan which address rural poverty including through building physical assets. It will also have wider impact nationally since MGNREGS itself provides an excellent platform to transfer lessons and scale up implementation across the country. One of DFID’s Asian regional climate change programmes, Climate Proofing Growth and Development (CPGD), could provide a mechanism for sharing lessons across the region.

The intervention will improve overall value for money of the government’s spending by leading to convergence of MGNREGS with other public and private funds. In particular, the intervention would support convergence with other central programmes, especially the National Rural Livelihoods Mission (NRLM) and the Integrated Watershed Management Plan (IWMP). It will also develop strategies to attract private sector funds such as Corporate Social Responsibility (CSR) funds of companies in areas such as skill development and establishing market linkages of the livelihood opportunities created through physical assets.[13]
[13] The Company Law of Government of India mandates Indian companies with a specific turnover and profit to spend 2% of their profits for CSR activities. The allowed list of activities is well aligned with the focus of this programme which includes poverty reduction, environment sustainability and employment enhancing vocational skills.

The UK is uniquely well placed to respond to this request from the government due to:
  1. DFID’s extensive experience supporting climate resilience, sustainable livelihood and safety net schemes in developing countries.

DFID’s experience in India: DFID has an exemplary track record of supporting state level rural development and climate resilience programmes in India. This work continues through the Poorest Areas Civil Society (PACS) programme (£25m, 2008-15) and the Odisha Modernising Economy, Government and Administration (OMEGA) programme (£19m, 2011-16). Completed programmes of note include the Western Orissa Rural Livelihoods Programme (£23m, 2000-2012) – the first programme to be given a completely clean bill of health by ICAI – the Madhya Pradesh Rural Livelihoods Programme (£16m, 2004-2013), the Andhra Pradesh Rural Livelihoods Programme (1997-2007), the Karnataka Watershed Development Project (1998-2005) and the Western Ghats Forestry Project (1992-2001). Lessons from PACS and OMEGA have been incorporated into the programme design.

DFID’s experience in the region and internationally: DFID’s Asia Regional Team is implementing a £28.5 million Climate Proofing Growth and Development programme which aims to enhance climate resilience in five countries in South Asia including India. Its focus on mainstreaming climate impacts in planning and budgeting directly complements this programme.

DFID also has experience of working on safety net schemes to build climate resilience e.g. Chars Livelihood programme in Bangladesh (now in Phase 2, £72m, 2009-16), Kenya Social Protection Programme (£122m, 2007-17), the Ethiopian Productive Safety Nets programme (now Phase 2, £213m, 2010-15), and most recently, the Building Resilience and Adaptation to Climate Extremes and Disasters programme (£130m, 2013-17) focused on the Sahel.

  1. World class UK expertise in the planning and implementation of climate resilient infrastructure

ICRG will enable the Government of India to access world class UK expertise, particularly in climate science, infrastructure, social sector research, and monitoring and evaluation. Numerous government, academic and private sector organizations have this expertise. The UK Met office and UK’s Natural Environment Research Council are working with the Indian Ministry of Earth Sciences to better forecast the precise timing of monsoon rains in India on which the majority of farmers depend for agriculture. The climate change PRECIS model developed by the UK Met office has been globally used to assess impacts of climate change, including in India. The British Geological Survey (BGS) has developed various tools and models for better prediction and decision making which would be useful in designing assets under MGNREGS. Among non-profit and academic institutions 3iE (partly funded by DFID), the Centre for Social Protection, IDS Sussex, and Manchester University have all carried out extensive systemic reviews, evaluations, impact assessments and policy analysis of social protection and sustainable livelihood programmes including MGNREGS. These institutions have partnered with leading Indian academic institutes such as IISc Bangalore and IIT Delhi for carrying out research on MGNREGS. The programme will seek to benefit from this UK expertise by engaging during the programme and encouraging long term partnerships with Indian counterparts.

Links to HMG/DFID strategic priorities
The programme is an excellent fit with the UK’s strategic priorities. The programme:
will help deliver our new technical assistance programme to India;
- will directly contribute to one of the UK’s twenty four “we will” commitments: “we will help millions of poor people protect their livelihoods from the impact of climate change” [14];
  [14] UK Aid: Changing Lives, Delivering Results. https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/67584/BAR-MAR-summary-document-web.pdf
- contributes to DFID Business Plan Impact indictors: Number of people DFID supports to cope with the impacts of climate[15];
  [15] ICF Key Performance Indicators https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/253682/ICF-KPI-summary.pdf
- will deliver against the ICF key performance indicator as well as DFID’s corporate results framework (DRF) indicator: Numbers of people supported to cope with the effects of climate change;
- will also help deliver other ICF indicators:
- Value of assets/economic activities protected or made less vulnerable;
- Volume of public finance mobilised for climate change purposes as a result of ICF funding (increased due to more effective demand under MGNREGA, including through better planning);
- Improved capacity of developing countries to tackle climate change.
- will contribute to DFID’s economic development vision by focusing on inclusive development and responsible management of natural resources and managing dangerous climate change. It will directly contribute to: “Policies and investments that encourage inclusive, broad-based economic growth and are founded on sustainable use of natural resources” [16];
  [16] DFID Economic Development Strategic Framework https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/276859/Econ-development-strategic-framework_.pdf
- The ICF Thematic Paper on Adaptation (ICF March 2011) identified India as one of six priority countries that combines very high vulnerability with the capacity to deliver.

Link to other donors in India
ICRG builds on the UNDP and GIZ programmes and also initiatives of Indian government. The governance improvement support, especially that provided by UNDP, should ensure that our programme can focus squarely on improving the quality of assets and resilience of the poor under MGNREGS. We will engage closely with GIZ’s small demonstration programme to incorporate the lessons learned into our programme.

Impact and Outcome that we expect to achieve:
The desired impact is reduced vulnerability of the rural poor’s livelihoods across India to climate risks, and increased ability to recover from shocks and stresses, especially those due to climate extremes, without compromising their current and future prospects.

The intended outcome is improved quality of the physical assets under MGNREGS demonstrated in three states in India. It is expected that the intervention would directly result in improved resilience of approximately 5 million rural poor including women and girls. By strengthening central government and state capacity and supporting lesson learning, the programme will mainstream climate resilience in the world’s largest labour-based social protection programme.

The outcome will be achieved by the following outputs produced or delivered directly by the intervention:

Evidence generated and shared nationally to (a) inform a stronger policy focus on the design and implementation of public works based programmes, and (b) strengthen the evidence base for how better physical assets can build more climate resilient livelihoods. This evidence will also be shared regionally and more widely.

More capable states able to ensure stronger local implementation including through more capable communities able to undertake improved planning, implementation and monitoring of physical assets under MGNREGS.

Enhanced capacity of technical organizations such as academic institutions, technical engineering institutions, training organizations, CSOs active in watershed and rural infrastructure development and network of technical resource persons such as `barefoot engineers’ for providing effective technical support to existing system of MGNREGS implementation.

A cross-cutting output to strengthen the MGNREGS systems and processes needed to support construction of better quality infrastructure and improved resilience of rural poor, including through development of innovative tools (especially IT based).

What will happen if DFID doesn’t intervene?
The Indian government has taken some initiatives to build durable assets, but is constrained by lack of short term technical capacity and rigidities in budgeting which make it difficult to fund pilot programmes. No other donor has the depth of expertise and ability to provide sustained support of this sort.

On current trends there will be more poor people in India highly exposed to climate related hazards than in any other country by 2030[17]. This programme is intended to transform this trajectory by improving the quality of the rural assets constructed under MGNREGS, and thereby making the livelihoods of the rural poor more resilient to a changing climate. Without the rapid transformation that our technical assistance could support more of the rural poor would remain more vulnerable to the impacts of flood, sea level rise, drought and high temperatures, and we would be more likely to see continuing calls for short term humanitarian assistance.
[17] The geography of poverty, disasters and climate, extremes in 2030; ODI; 2013

India is also a significant partner in the international climate change negotiations. Providing this support will demonstrate UK commitment to supporting climate resilience for the poorest, which is particularly important in the run up to the COP21 negotiations in Paris. Without such practical demonstrations of commitment our position will be weaker.

Will the programme lead to a sustainable outcome?
The MGNREGS scheme is mandated by an Act of Parliament. The programme will support the Indian government’s plan of transitioning MGNREGS from a social safety net scheme to one that stimulates rural growth through investment in productive assets which provide sustainable employment to rural poor[18]. Thus the government is both committed to the MGNREGS and has strong incentives to embed the results of this programme, which should lead to a sustainable outcome.
[18] Mentioned by Minister Jairam Ramesh in Preface of the “Summary of suggestions proposed by Committee for Revision of MGNREGA Operational Guidelines

There are also strong incentives for local government to build better quality and productive assets under MGNREGS. The benefit of MGNREGS has so far reached primarily to wage earners and not so much to communities as a whole. Better planned and better quality assets will provide economic benefits to villages in terms of improved agriculture and livelihood services.

What are the main concerns with respect to feasibility?
The main concern is about the availability of technical capacity at local level, where the overstretched Block level engineers[19] may struggle to incorporate additional technical aspects in design and implementation of works. In order to tackle this, the preferred option discussed below proposes building the skills of local youth including by developing a cadre of `barefoot engineers’ to carry out technical planning, measurement and maintenance of assets. In addition, the programme will be delivered through technical CSOs at local level. The feasibility of this has been widely proven with experiences of their effective role played in programmes like PACS and is consistent with the strong push from central government to use the local level knowledge that exists in CSOs. The programme has been discussed with range of stakeholders including state governments, technical CSOs, academic and research institutions all of who have emphasised the importance of this support.
[19] There is one engineer per Block, covering up to 20 Panchayats / 200 villages.

Gender equality
The programme has considered gender equality in its design, delivery and monitoring to be compliant with the Gender Equality Act. MGNREGS has consistently met its legal requirement of providing at least 33% of wage income to women (for example, women’s participation was 53.01% in 2012-13). This high participation is achieved by having the same wage rate for men and women, crèches for the children of women workers, limited working hours and ensuring work is available locally[20]. However, a UN Women study found that the benefits gained by women under MGNREGS have been more as individual workers rather than as a community[21]. It found that their participation in asset planning had been low and that they had limited control over the assets constructed so that they did not much benefit from the assets.
[20] MGNREGA for Environmental Service Enhancement and Vulnerability Reduction: Rapid Appraisal in Chitradurga District, Karnataka; Tiwari et al 2011 http://orissa.gov.in/e-magazine/Orissareview/2013/Feb-Mar/engpdf/76-80.pdf
[21] Empowerment Effects of the NREGS on Women Workers: A Study in Four States; Economic and Political Weekly, 2010

The design, implementation and monitoring of this programme has taken into account these issues, in particular:
- Participation of women: Participation of women in village level planning will be ensured by greater awareness generation and mobilization of local women’s Self Help Groups. Women leaders of Panchayats and Gram Sabhas will be especially sensitized to actively participate in asset planning process and to encourage others. The programme will also build the capacity of women’s Self Help Groups at village and cluster level so that they become technically competent to implement MGNREGS. This would be an integral part of the institutional capacity building component of the programme.
- Asset planning and ownership: Gender based criteria will be introduced in the planning of assets.
- Management of assets and quality assurance: The programme will facilitate development of a pool of `barefoot engineers’ to assist in planning, designing and maintenance of assets. Priority will be given to selection and training of women bare-foot engineers.
Monitoring and evaluation: Specific indicators will be included to monitor women’s participation, their active role in implementation and resilience benefits accrued from physical assets built under MGNREGS through DFID’s support. The programme will also assess the impact of the programme on the well-being of women and girls by adding gender related indicators to the Ministry of Rural Development’s Social Audit initiative.
## Appraisal Case

What are the feasible options that address the need set out in the Strategic case?

Option 1: DFID does nothing new
The argument for doing nothing new is that the physical assets may be strengthened to some extent under existing interventions. For example, a small component of DFID’s Poorest Areas Civil Society (PACS) programme (£25m, 2008-15) seeks to improve the uptake of MGNREGS by creating awareness among rural poor about their entitlements and rights. Also, the Odisha Modernising Economy Governance and Administration (OMEGA) programme has a small component to improve governance aspects of MGNREGS. These interventions focus on improving the governance aspects of MGNREGS, but this may indirectly improve the quality of assets. These interventions are, however, finishing soon.

In addition, a small UNDP intervention will demonstrate participatory planning for selection of assets in seven Blocks, although the major focus of the programme will be on improving transparency and creating demand for labour under MGNREGS. Also, a small GIZ programme has recently started which aims to generate evidence on how assets can improve environmental benefits in 12 Panchayats. Both these programmes are of small scale and do not directly support implementation of better quality assets and improved resilience of the poor.

Advantages
None.

Disadvantages
This would not result in transforming the approach to physical assets under MGNREGA. Such a transformation requires institutional capacity building at central and state level, with attention to systems strengthening to ensure feedback and lesson learning. This would miss the opportunity to maximize the lessons learned from the PACS and OMEGA programmes, and leave their legacy more vulnerable. Without improving the quality of the assets the assets will degrade more rapidly, needing more frequent repair and / or replacement thereby limiting the development of sustainable livelihoods.

Option 2: £10 million Technical Assistance over four years to: a) central Ministry of Rural Development for policy development and lesson learning, and b) three state governments to support more effective planning, implementation and monitoring of physical assets under MGNREGS.

This is our preferred option. Under this option, technical assistance would be provided both at central policy level and at state level. The programme will strengthen India’s overall capacity to integrate climate resilience into planning and implementation of physical assets. Targeted assistance would address the key issues that lead to building poor quality assets under MGNREGS (Annex 1). The programme would support central government to design and modify policies that lead to transformational change across the country, reinforcing the current emphasis on assets and developing a better understanding of how to improve resilience to climate change. At state level the programme would improve the participatory planning for selection of physical assets, increase technical capacity of local implementation agencies to design better quality assets, ensuring that the lessons learned are shared across MGNREGS.

National Level: the programme would work directly with the Ministry of Rural Development’s MGNREGS Division to strengthen national level research, policy and training. A small team of technical and policy experts would provide advice on developing tools and processes, creating knowledge and generating high quality evidence which could enable the Ministry to take more informed decisions. The programme would support documentation of best practices in print, audio or visual including films, reports, write-ups etc. It would also facilitate MoRD in streamlining training content and development of training modules. The team would work closely with the National Resource Group (NRG), a technical group formed by MoRD to advise on policy matters related to physical assets. The programme would identify key policy areas in consultation with NRG and provide relevant research and evidence generation support. More detail on proposed activities at Annex 2

State Level: the programme would provide technical assistance to three of the poorest and most vulnerable states in India: Bihar, Odisha and Chhattisgarh. 100 blocks would be identified as pilot blocks in consultation with MoRD and state governments during the inception phase of the programme. In each state, state level programme teams would support participatory planning, and technical planning and design (especially for groundwater recharging; irrigation facilities; integrated afforestation and horticulture; plus any other assets subsequently identified as significantly contributing to the sustainable livelihood and resilience of the poor), as well monitoring, and maintenance. The programme would strengthen implementation capacity by strengthening the technical capacity of state level institutions as well as strengthening civil society and community based organisations, as well as training a pool of `barefoot engineers’ with one for every Gram Panchayat.[22]
[22] Special focus will be given on skill building of women to become barefoot engineers. State Governments will meet the cost of their salaries.

The private sector is increasingly involved in poverty reduction and climate resilience in India. The programme would also explore the scope for public-private partnerships in areas such as skill development of rural poor, especially women and girls. Many companies are investing in social and environment related programmes, not least due to the recent Corporate Social Responsibility (CSR) Act which mandates 2% of profit earned to be spent for CSR activities. In addition to this, leading UK companies with a strong focus on sustainability, such as Marks and Spencer and Unilever, operate in India.

Advantages
This Option would deliver transformational change: the two key reasons for the poor quality of assets created under MGNREGS, are lack of evidence on how to ensure the assets best enhance the resilience of poor, especially to climate driven shocks and stresses, and lack of technical capacity amongst those implementing MGNREGS. The targeted support under this option would address both these issues, ensuring that the lessons learned from state level implementation were integrated into national policies. There is strong evidence that effective change requires engagement at both levels.[23]
[23] The 12th Five Year Plan of Planning Commission a belief among the rural poor that they will get work only when the government decides to ‘open’ work. It further found that whereas 6% of MGNREGS funds are available for administration support only half of this is used on average due to lack of local administration and technical capacity. The report also points that while greater water security, flood and drought proofing has been reflected as a major objective in the Act (MGNREGA), lack of technical inputs and support at local level the objective has not been fully met. The Plan, therefore recommends building capacity of locals for social mobilization and technical support. This implies that any additional initiative without any local level capacity building support would have limited acceptance and thereby would have low to medium impact on strengthening of structures. http://planningcommission.nic.in/plans/mta/11th_mta/chapterwise/chap12_rural.pdf

Disadvantages
This option would commit us to one particular national scheme with continuing state level engagement for four years. However, the evidence suggests that it would be very hard to deliver transformational change more quickly and without engaging at both centre and state. One option we also considered was to only engage in one state. However, in order to engage at sufficient scale we need to be active in a minimum of 100 Blocks, and given the spread of Blocks most likely to satisfy our selection criteria this means engaging in three states. The proposed management arrangements (see below) enable the programme to learn and have the flexibility to adapt.

Option 3: £3 million Technical Assistance over four years to central ministry for high leverage catalytic activities to improve delivery of MGNREGS

This option would provide support only at national level to the Ministry of Rural Development to support formulation of policies and guidelines and other initiatives which can facilitate strengthening of physical assets at the local level. It would also strengthen the evidence base on how better assets could improve poor people’s livelihoods and strengthen their resilience to climate change. This would entail the activities set out under Option 2 National level.

Advantages
This option would strengthen our relationship with the central Ministry of Rural Development. Given that MGNREGS is a national scheme central government policies and guidelines play an important role. For example, central initiatives such as electronic fund management system and social audit have helped improve transparency and reduce delays in wage payment under MGNREGS. Better policies and guidelines could also therefore improve the enabling environment, including for ongoing donor programmes by DFID (PACS and OMEGA), UNDP and GIZ.

Disadvantages
The outcome on the ground is less certain as the desired impact is achieved only indirectly. One specific downside to a centre-only push is the difficulty of setting incentives that tailor the response to specific local circumstances and capacities, which inevitably leads to weak implementation. This matters especially in India given its size and diversity with large numbers of people with varying degrees of vulnerability to climate change and adaptive capacity.

Improving demand from vulnerable poor people, in particular, requires local level interventions. The most recent annual review of DFID’s PACS programme suggests that the presence of CSOs and empowered groups in villages have ensured significant improvement in delivery of the scheme to benefit the most vulnerable.

Strength of the evidence base for each option

The strength of evidence for each option is shown below. It shows that the evidence base is high for our preferred Option 2.

Options	Evidence rating
Option 1: DFID does nothing new	Low evidence that this would lead to desired outcome and impact / The Annual Review of DFID’s PACS found that demand under MGNREGS has increased and people have more information about works built under MGNREGS. But there is no evidence on improved quality of assets through the governance support provided to MGNREGS under PACS. The 2013 Annual Review of OMEGA programme finds that there is an increase in uptake of climate resilient works under MGNREGS due to participatory planning support. However, no evidence exists on improved quality and durability of these assets due to the intervention. / UNDP and GIZ interventions are at very initial stage and therefore no concrete evidence exists on how these interventions are leading to climate resilience of rural poor under MGNREGS.
Option 2: Targeted technical assistance providing a) policy level support to central Ministry of Rural Development, and b) implementation support to three state governments	High evidence that working at central policy level would lead to desired outcome and impact (provided coupled with local engagement) / MGNREGS is a national scheme which is implemented at state level based on central guidelines and policies. There is evidence that central policy measures, such as modification in payment systems using IT based systems have improved transparency in the scheme, provided they are coupled with strong local engagement. For example, the Electronic Fund Management System and Electronic Muster Roll Management System have resulted in reduction in payment delays and are now used in most of the states in India[24]. Therefore, it is very likely that central level push on improved quality of assets would have significant impact if it is coupled with local level implementation support. / High evidence that providing technical assistance at local level would lead to desired outcome and impact / Annual reviews of DFID’s livelihood programmes such as Madhya Pradesh Rural Livelihood Programme (MPRLP) and Western Odisha Rural Livelihood Programme (WORLP) suggests that better community mobilization, participatory planning, micro-planning and strengthening of local institutions such as Gram Sabhas and women Self Help groups (SHGs) have laid the ground work for income generating activities, creation of assets and address issues such as elite capture. The evaluation of WORLP and PACS further highlights that active involvement of CSOs has led to a positive change in attitude of government officials in the region, and to improved service delivery. There are global examples also of successful bottom up approaches for enhancing resilience of communities including the Participatory Rural Management Project in Vietnam funded by the World Bank and IFAD which has resulted in significant reduction of poverty in the country. / The Annual review of OMEGA programme of DFID India also finds that the number of climate resilient assets constructed under MGNREGS increased by participatory planning initiatives of civil society organizations. With technical assistance from the OMEGA programme the Koraput block in Odisha, India received the MGNREGS National Award for 'Effective Initiatives under MGNREGS Administration'. The Technical Assistance team worked closely with district and block level officials and piloted participatory planning process and social audit of MGNREGS which led to recognition by the Government of India. This recognition demonstrates the importance of working at local level to strengthen MGNREGS system and would be relevant for strengthening asset quality also. / The MGNREGA Sameeksha which is a compilation of case studies of MGNREGS highlights that when planned and executed well the assets have resulted in positive return on investment, sometimes exceeding 100% in one year. The report refers to a study which found that economic benefits of the assets built under MGNREGS in Saurashtra was more than in Junagadh in Gujarat State. Technical design has been referred as one of the factors for this. / Various evaluations and assessments of MGNREGS performance have pointed out that local level resources and their capacities are the key driver of success of MGNREGS in general and creation of durable assets in particular. / The official evaluation of MGNREGS by the MoRD recommends the following: “To ensure greater dissemination of information and participation of rural people at every stage of MGNREGS, from planning to execution, the MGNREGS Guidelines emphasise the need for state and district governments to involve CSOs as resource agencies. CSO involvement will also aid the process of social audits and help with increased transparency and accountability in implementation of the Act.” This clearly highlights the importance of local technical assistance through CSOs which the option also proposes to do. / Another evaluation of MGNREGS by IISc Bangalore based on primary data collected from four states shows that conversion of structures created under MNREGA as productive assets would require adequate technical supervision and greater involvement of farmers.[25] / A research by IWMI found that high quality technical support was one of the main reasons for these assets to provide economic benefit. / The Government of India Watershed Development Guidelines also stresses on importance of decentralization and rural community participation in planning, implementation and monitoring of works. Evidence from the Participatory Rural Management Project in Vietnam funded by the World Bank and IFAD also suggests that participatory approaches ensured poverty reduction by reaching out to poor households and ensuring inclusion of all in the development process.[26]
3. Work at central ministry level on high leverage catalytic activities to improve delivery of MGNREGS.	Limited evidence that working only at central policy level would lead to desired outcome and impact / MGNREGS is a central government scheme and the desired impacts of the programme depend significantly on the national level guidelines and initiatives. There is evidence that improved guidelines and approaches such as Electronic Fund Management System (EFMS), convergence with other programmes and social audit of MGNREGS for improving overall accountability and transparency in MGNREGS implementation have delivered improved governance and implementation of the scheme. However, success has required support for local engagement. Limited evidence exists on how these central government policies have resulted in improving the quality of assets.
[24] MGNREGA Report to the People, Ministry of Rural Development, Government of India 2014; http://nrega.nic.in/netnrega/writereaddata/Circulars/Report_People_Eng_jan_2014.pdf
[25] Environmental Benefits and Vulnerability Reduction through MGNREGS, IISC Bangalore, MoRD and GIZ, 2013
[26] Using community driven approaches to reduce rural poverty, IFAD; http://www.ifad.org/events/reducingpoverty/vietnam.pdf

Economic Appraisal

The Economic Appraisal is based on the premise that the programme will (a) improve the economic benefits realized by the rural poor who depend on these assets for their livelihoods, and (b) reduce the loss of public investment due to damages to these assets from weather extremes. While the programme would deliver these economic benefits in the intervention Blocks directly, DFID’s focus on strengthening state capacity as well as on the implementation system at all levels would help scale up these benefits across the country.

Benefits:
60-70% assets built under MGNREGS are related to water conservation, irrigation, land development and drought proofing which directly benefit the rural poor who depend on agriculture for their livelihoods. Therefore, the direct benefit of the assets can be measured in terms of incremental income that farmers realize due to increased irrigated area, increase in crop productivity, additional fish stocks, improved access to fuel wood and greater availability of drinking water. There is limited quantitative data available as there has been no systematic evaluation of economic benefits from the assets built under the scheme. However, there are case studies which typically provide a range of incremental economic benefits realized by the rural poor from the assets. These case studies are of assets which are built, used by people, and sustained over a period of time despite weather related shocks.

A comprehensive literature research found that the incremental income from MGNREGS assets varies from 33% to 106%[27]. This is due to the increase in irrigated area, increase in soil moisture content, increased water table and new afforestation/ horticulture activities. Various indirect benefits have also been observed including easier access to drinking water for people and livestock, and a decrease in distress migration particularly of women and girls.
[27] PEAKS Evidence on Demand team

In addition to increased incremental income, better built assets are also more resistant to weather extremes and will have a longer life. Thus, public investment is protected from being lost due to climate driven extremes such as flooding. A study by IFC suggests that the capital depreciation of infrastructure may increase by 10-20% due to climate change. However, there is lack of evidence on depreciation of small scale rural infrastructure. Several MGNREGS case studies found that as much as 80% of assets can be washed away due to flooding as they were not of good technical quality or properly located[28]. Another study in Gujarat of tiny dams constructed using sand bags found that 85% of these dams were damaged and became useless due to lack of technical planning and delay in implementation[29]. This is further corroborated by World Bank’s 2011 report “Social Protection for Changing India Vol II” which found that many assets are washed away the next monsoon.
[28] Dhananjay et al, 2011, Role of MGNREGA in Rural Asset Creation in India- An Analysis, Journal of Global Economy (ISSN 0975-3931), Volume 7 No 4, October-December, 2011
[29] Shah, H. and Mistry, P. 2012. The invisible bags: A case study of Bori Bandhs constructed under MGNREGA in Gujarat. February, Ahmedabad: DISHA. http://mgnrega-disha.org/the_invisible_bags.pdf

Attribution of Benefits to DFID’s TA options:
Our intervention will improve the quality of assets ensuring that they provide the full potential economic benefit. There is limited data on the quality of assets constructed as this is not currently measured under MGNREGS (data exist only for rate of completion which may be related). There, however, are case studies and state specific research which provide information on quality of assets, in particular:
1. A study in Rajasthan of water harvesting structures found that 80% assets were washed away from floods[30];
  [30] ibid
2. A study in Madhya Pradesh found that only 25% of farm ponds built under MGNREGS were properly utilized as only these had lining to make water available for irrigation[31]. This implies that only 25% of assets are best quality assets.
  [31] MGNREGA Sameeksha: An anthology of research studies on MGNREGA between the period 2006-2012, Ministry of Rural Development, India
So, we have assumed from the above that 20% assets are resilient to weather extremes. However, only 25% of these assets are technically sound to provide the maximum economic benefit to rural poor. This implies that only 5% of total assets are of best quality and enhance the overall resilience of rural poor. 15% of total assets are of average quality and 80% are washed away.

The incremental income from different qualities of assets has been assumed as next step. In the absence of strong evidence, we have taken a conservative approach assigning the range of incremental income found in the literature to each asset category. For the best quality assets, we have taken the incremental income to be the mid-point of the incremental benefit range (33% to 106%) which is 69%. For average quality assets, we have assumed the mid-point of lower half of incremental benefit which is 51%. Poor quality assets are assumed to have 0% incremental benefit.

The above estimates were cross checked with the Ministry of Rural Development (MoRD) and leading field based experts and practitioners. Two organizations PRADAN, Jharkhand and PRAN, Bihar were consulted, the leading civil society organizations providing technical support at state level in design and capacity building support for implementation of MGNREGS. While they agreed on the incremental income from these types of assets, they suggested that the percentage of non-viable assets was closer to 60% than 80%. So, the final distribution in the baseline scenario assumed for economic assessment is the following:

Table 1: Baseline Proportion of Assets
Quality of Assets	Incremental income	% in total asset mix
Best quality	69%	10%
Average quality	51%	30%
Washed away/ not used	0%	60%

Table 1 also represents the no-intervention scenario.

With targeted TA support at central policy and local level under Option 2, the percentage of best quality assets will increase. The programme will strengthen the technical capacity of local implementation agencies and adopt scientific ways of planning and implementation of physical assets. This direct support in selected Blocks is likely to increase the quality of assets and therefore the proportion of best quality assets should increase significantly. The MGNREGA Sameeksha found a higher survival rate of plant saplings in Madhya Pradesh compared to Jharkhand and attributes this to careful planning, execution and maintenance required for ensuring the feasibility and durability of works[32].
[32] i.e. 90% survival rate after four years compared with 0%

Table 2: Option 2 Proportion of Assets
Quality of Assets	Incremental income	% in total asset mix
Best quality	69%	30%
Average quality	51%	40%
Washed away/ not used	0%	30%

Option 3 will provide only central policy support, indirectly improving the quality of assets through more available evidence and supportive policies. This support will not directly strengthen capacity at execution level and therefore the improvement will not be as significant as under Option 2. This is modelled by increasing the proportion of average quality assets compared with low quality.

Table 3: Option 3 Proportion of Assets
Quality of Assets	Incremental income	% in total asset mix
Best quality	69%	10%
Average quality	51%	40%
Washed away/ not used	0%	50%

The next step was to consider a typical asset built under MGNREGS with a design life of 10 years. The capital cost of this asset provided under MGNREGS was taken from the scheme guideline and incremental income over the entire design life was calculated using the incremental income percentages set out above. The benefits were then discounted using a discount rate of 10% and 3.5% to calculate the present value of the benefits. The discount rate of 10% was chosen as it is commonly applied in Indian projects whereas 3.5% is the discount rate recommended in the Green Book.

Costs:
The cost includes capital investment made under MGNREGS and DFID’s technical assistance. The capital investment is taken from MGNREGS Operational Guidelines and includes any administration cost currently provided by the Ministry of Rural Development. The assets will require additional agricultural inputs costs seeds, and fertilizers, and have maintenance costs. However, the benefits mentioned above are taken as net incremental benefits which already factor in input and other costs. The capital cost invested under MGNREGS has been assumed to be invested over two years. Under Option 2 and Option 3, the incremental technical assistance cost was calculated for the asset. Under Option 2, the incremental cost is 4% of the capital cost and under Option 3 the incremental cost is 1% (see Annex 3). These costs were then distributed over a period of four years which is the proposed programme period. The costs were discounted using a discount rate of 10% and 3% to calculate the present value of the costs.

A World Bank study of large infrastructure found that the cost of making infrastructure resilient to climate is in the range of 1-2%[33]. MGNREGS’ basic approach is to build assets with a larger labour than material component. We have therefore assumed that there will not be any additional capital cost for making assets climate resilient. However, additional technical and administrative support may be required e.g.for funding the salaries of barefoot engineers. Therefore, 1% of total capital cost of assets has been assumed in the financial model as incremental cost to make the assets more resilient to weather extremes. This incremental cost can be accessed from existing allocated Administration Budget of total MGNREGS budget as only 3% out of the allocated 6% budget is currently utilized.
[33] The Costs of Adapting to Climate Change for Infrastructure http://siteresources.worldbank.org/EXTCC/Resources/407863-1229101582229/DCCDP_2Infrastructure.pdf

Benefit Cost Ratio:
The discounted Benefits and Costs were then divided to calculate the Benefit Cost Ratio. The following results were obtained[34]:
[34] Please refer to Financial modelling Sheet for Economic Appraisal - Quest No. 4893438

Options	Quality of asset	%	Average BCR		Average BCR (Weighted)
	Discount rate		10%	3.5%	10%	3.5%
Baseline Scenario- Option 1	Best quality (Incremental income- 88%	10%	3.35	4.56	1.08	1.47
	Average quality (Incremental income- 51%)	30%	2.47	3.37
	Washed away/no utilization (incremental income 0%)	60%	0	0
DFID Intervention Option 2	Best quality	30%	3.19	4.35	1.90	2.59
	Average quality	40%	2.36	3.21
	Washed away/no utilization	30%	0	0
DFID Intervention Option 3	Best quality	10%	3.29	4.50	1.30	1.77
	Average quality	40%	2.43	3.31
	Washed away/no utilization	50%	0	0

The results show that Option 2 has the highest Benefit Cost Ratio under the discount rates of both 10% and 3.5%. Sensitivity analysis was also carried out by changing the proportion of assets achieved under this programme in the preferred option. The sensitivity analysis does not alter the conclusion as Option 2 remains the preferred option with the highest Benefit Cost Ratio.

	Asset type	%	BCR (10%)	BCR (3.5%)
DFID Intervention Option 2	Best quality	30%	1.90	2.59
	Average quality	40%
	Washed away/no utilization	30%
DFID Intervention Option 2 (Sensitivity analysis)	Best quality	20%	1.58	2.15
	Average quality	40%
	Washed away/no utilization	40%

Option 2 will reduce number of assets which are either washed away or not used at all. By reducing the loss/ no use of assets from 60% to 30%, in 100 Blocks the avoided loss of public investment through this investment will be nearly £15 million[35].
[35] Investment in 100 Blocks in MGNREGS on water conservation, irrigation, plantation and other agriculture related physical assets is around £50 million per year. (source- MGNREGS MIS)

In summary, the Economic Appraisal shows that the incremental Benefit Cost Ratio (BCR) of both Option 2 and Option 3 is more than one. Option 2 is recommended as the Benefit Cost Ratio is higher, i.e. 2.59 using a discount rate of 3.5%. Sensitivity analysis has been carried out in anticipation of risks that expected improvement in quality of assets may not be achieved due to external factors related to governance of MGNREGS. The Sensitivity Analysis shows that the BCR remain high for Option 2 which demonstrates that the recommended option is robust. In addition to direct economic benefits the indirect benefits are also high under Option 2.

Recommendation
The three Options are compared in the table below.
Table: Comparison of Options

Criteria	Option 1: Do nothing	Option 2: / Policy + Implementation support	Option 3: Policy support only
Transformational potential	0	3	2
Replicability- potential for scaling up across the country and region	1	3	2
Buy in from Indian Government	0	3	1
Strength of evidence	1	2	1
Ease of attribution of results	0	3	1
Addresses the range of variety and complexity of the challenges	1	3	1
Builds on existing expertise and investments by DFID	0	3	1
Length of time to develop and start implementing	0	2	3
Staff time needed to develop and manage	0	2	2
Total	3	24	14

Option 2 is recommended as the preferred option because:
1. Decades of development experience in India and beyond underlines the need to engage at the grass roots level in order to bring about transformational change (see, for example, DFID (2007) Transforming Rural Livelihoods in India);
2. India’s climate resilience challenge is huge and varied – nearly three-quarters of the country will require support mechanisms for climate change adaptation, across widely varying agro-ecological zones[36], Option 2 provides the best chance for addressing this;
  [36] Based on superimposing biophysical and socio-economic vulnerability assessment maps for India, Development Alternatives (2011) Low Carbon Climate Resilient Development Prospects for India.
3. It has the highest Benefit Cost Ratio.
Theory of Change for the preferred Option (Option 2)
Assumptions

Increase resilience of the rural poor across India to climate risks, and increased ability to recover from shocks and stresses, especially those due to climate extremes, without compromising their current and future prospects

Impact
-Improved quality of physical assets leads to sustainable livelihoods and climate resilience of poor.
-National and state government programmes, policies and budgets remain focused on poor and marginalized people

-Government able to incorporate lessons learned into rules, and drive capacity building beyond target areas
-Poor people are able and willing to engage directly and through CSOs acquire technical knowledge and affect government decision making at village/ block/ district/ state levels
-CSOs make service providers more responsive and accountable to poor people, including socially excluded
- Capacity and skills of technical organisations, CSOs and government is used and retained during and after the programme.

Outcome

Improved quality of the physical assets constructed under the Mahatma Gandhi National Rural Employment Guarantee Act, India’s flagship social protection programme, in target areas

Outputs
Evidence generated and shared nationally (and regionally) for better policy

More capable state governments able to ensure stronger local implementation through improved planning, implementation and monitoring of physical assets under MGNREGS.

Enhanced capacity and skills of technical organizations e.g. academic institutions, engineering institutes, CSOs, women Self Help Groups, Barefoot Engineers for providing effective and sustainable technical support to creation of rural physical assets

Robust MGNREGS systems and processes supported by effective tools (e.g. IT based applications) to support scale-up of models

Inputs
Climate risk mapping, vulnerability assessment, scientific studies related to climate variability

Develop innovative tools and processes (e.g. IT based applications) for easier access to information by communities for better planning and implementation of assets.
Strengthen government’s knowledge management system through improved database, MIS, technical guidelines, training modules, etc.
Create a network of technical organizations which can provide support in making assets more resilient to climate.
Training and capacity building of Panchayats, SHGs and CSOs in 100 blocks in three states
Action research, impact assessment, evidence generation and work on evidence to policy development

The programme is based on evidence that better participatory planning combined with strengthened technical capacity at implementation and policy level will lead to better constructed physical works under MGNREGS that will improve the livelihoods of poor people and will strengthen their resilience to climate extremes. The key assumptions underlying the theory of change and their evidence are shown in the table below:

Theory	Assumption	Evidence
Outcome to impact	Better quality assets enhance resilience of rural poor.	More than 60% of assets built under MGNREGS are related to water conservation and irrigation such as check dams, water harvesting tanks, repair of canals and ponds, and irrigation wells. A study by Indian Institute of Forest Management looking at adaptation opportunities from MGNREGS found that the assets have positive impact on food security and water scarcity with cases of 100% shift from un-irrigated to irrigated land. A study by IISc Bangalore also found that assets built under MGNREGS have increased water table, increased irrigated area and improved soil moisture content of farm fields. An IWMI review found that wherever built well investments made in the assets have been recovered in a single year. A study of assets in Kerala also found that better experience of implementation and maintenance of assets has resulted in more productive benefits. With durable asset creation as one of the programme’s key objectives, the Government of India recognizes MGNREGS as one of the 24 initiatives to adapt to climate change. / The programme will itself generate more evidence in this regard and therefore suggests detailed assessments during the initial phase.
	National and state government programmes, policies and budgets remain focused on poor and socially excluded people	Based on the review of MGNREGS, the new government intends to provide benefits to the poorest communities and focus on developmental aspects of MGNREGS beyond direct employment. Strong evidence of this is shown by MoRD’s strategy to focus on the 2500 poorest and backward blocks, and new guidelines for building at least 60% assets for agriculture and allied activities, as well as the intention to converge MGNREGS with the National Rural Livelihood Mission.
Outputs to outcomes	Government able to incorporate lessons learned into rules, and drive capacity building beyond target areas	One of the main outputs of the programme is to strengthen government systems and processes to build climate resilient infrastructure under MGNREGS.
	Poor people are able and willing to engage directly and through CSOs, to affect government decision making at village/ block/ district/ state levels	There is strong evidence from DFID India’s livelihood and rural development programmes such as PACS, WORLP, MPRLP and OMEGA that involvement of civil society organizations has increased participation of rural poor in government schemes. (Reference- Annual Reviews)
	CSOs make service providers more responsive and accountable to poor people, including socially excluded	Annual review of PACS programme of DFID India suggests that CSOs have made service providers and government more responsive and accountable to poor and socially excluded.
	Capacity and skills of technical organizations, CSOs and government is utilized and retained during and after the programme.	Strengthening institutional capacity for building climate resilient assets is the focus of this TA programme. A bottom up approach to build capacity at all the levels- poor people, village level institutions (Gram Sabha, Women Self Help groups), Panchayats, Blocks, Districts and state/central level would result in capacities and skills developed at each level.
Inputs to outputs	Key institutions and government departments are willing to work together in this programme	The programme will be implemented closely with the Ministry of Rural Development and State Government departments. The lack of technical capacity for building good quality infrastructure has been widely recognized. Poor quality infrastructure has resulted in low participation of stakeholders in MGNREGS. This poor experience will need to be overcome to ensure that village institutions and government departments would actively participate in the programme.
	Capacity building activities improve skills and systems of institutions and government departments	The TA programme would utilize conventional proven capacity building techniques as well as innovative methods of training and capacity building.

Additional Technical Appraisal

Political economy
The programme design has been intensively discussed with Indian Ministry of Rural Development and will help deliver the new government’s strong emphasis on ensuring the assets built under MGNREGS help develop productive sectors such as agriculture. In order to strengthen the uptake of findings, the programme Steering Group will include representatives from other key government ministries especially the Ministry of Finance (MoF) and the newly formed NITI Aayog (erstwhile Planning Commission) responsible for advice the Prime Minister on taking policy decisions. The new government is also strongly focused on enhancing climate resilience in all developmental programmes including rural development programme.

The programme will build on strong state partnerships that DFID has in Bihar, Odisha and Chhattisgarh. Odisha and Bihar are DFID priority states where a number of development programmes including support to MGNREGS governance through OMEGA and PACS is being provided. In Chhattisgarh, we have built a strong relationship with the State Government for supporting implementation of their State Action Plan on Climate Change.

Poverty impact and inclusivity
On average, MGNREGS has provided more than 40 days of employment to participating households, successfully addressing the distress migration that is prevalent in rural India. By strengthening the assets on which they rely for their livelihoods, the support will enhance the economic resilience of the rural poor[37]. The programme will particularly help families from Below the Poverty Line households, Scheduled Cast and Scheduled Tribes as their individual assets can be funded under MGNREGS.
[37] MGNREGA for Environmental Service Enhancement and Vulnerability Reduction: Rapid Appraisal in Chitradurga District, Karnataka, Tiwari et al 2011 http://www.lse.ac.uk/asiaResearchCentre/_files/epwArticle14052011.pdf

The intervention states (Bihar, Odisha and Chhattisgarh) are among the poorest states in India with a high percentage of people living below poverty line (40%, 34% and 33% respectively[38]), and depending on agriculture and natural resources for livelihoods[39]. The dependence of the majority of the population on agriculture and the vulnerability of the predominant rain-fed agriculture to climate mean that building better quality assets would lead to significant impact on poverty reduction the respective states.
[38] Press note on poverty estimates, Govt. of India, Planning Commission 2013 http://planningcommission.nic.in/news/pre_pov2307.pdf
[39] 61.8% of population in Odisha depends on agriculture. The sectoral growth declined from 11.01% in 2012-13 to -3.25% in 2013-2014 due to cyclone Phailin followed by recurrent floods. Similarly, 80% of Bihar’s population is dependent on agriculture for livelihoods and out of total 38 districts 28 are affected by floods on regular basis. The state is also highly vulnerable to drought with all 38 districts being declared drought affected in the year 2010. In Chhattisgarh also 80% of population depend on agriculture for livelihood and according to Chhattisgarh State Action Plan on Climate Change, 15 out of 27 districts are drought prone.

Participation of Scheduled Castes and Scheduled Tribes in the scheme has seen decline over past few years[40]. The scheme also has not been able to target small and marginal farmers both as workers as well as beneficiaries of work on their private lands. To address this, MoRD has enhanced its focus on the 2500 poorest and most backward districts for better implementation of MGNREGS. Most of these priority districts are in the Bihar, Odisha and Chhattisgarh which have high percentages of Scheduled Castes and Scheduled Tribes and also have significant population affected by Left Wing Extremism. Please see section 109 on risks associated with Left Wing Extremism and mitigation strategies.
[40] Impact of MGNREGA on rural labour market- ICRISAT, 2014

Impact on climate change and environment
Programme is focussed on minimizing the impact of climate change on vulnerable and poor people
According to IPCC, climate vulnerability is a function of exposure, adaptive capacity and sensitivity. Better built assets under MGNREGS would be less sensitive to impacts of climate change particularly flooding. Assets such as irrigation infrastructure, water conservations structures and plantations improve the adaptive capacity of poor by allowing them additional income avenues. Option 2 further aims at mainstreaming climate change in MGNREGS implementation system and enhancing skills of poor, women and girls on planning, designing and implementation of assets. This will result in building more capable government and communities with enhanced skills and knowledge to tackle climate change issues, strengthening their adaptive capacity. Under this option, the programme would directly improve resilience of poor in Odisha, Bihar and Chhattisgarh who are highly vulnerable to impacts of flooding and drought. Through demonstrative effect and influencing central policies towards climate resilience the intervention would improve resilience of poor across the country in more than 6000 blocks.

Programme would result in climate change mitigation and environmental benefits:

Stronger physical assets would lead to multiple environmental and climate change mitigation benefits. Key benefits include increased soil moisture content, increased water table depth, reduced soil erosion and biodiversity conservation. Reduced soil erosion and increased afforestation activities under MGNREGS through the proposed intervention would directly result in carbon emission reductions by facilitating carbon sequestration.

Impact of climate change on achievement of outputs, outcomes and impacts

There is a risk that frequent events of extreme floods can damage the physical assets created under the programme thereby affecting the desired outcome and the impact of the programme. While this programme focuses only on improving the quality of assets permissible under MGNREGS, the states of Bihar, Odisha and Chhattisgarh are in process of implementing their State Action Plans on Climate Change (SAPCC) which seeks to reduce the risks associated with climate driven extremes in their respective states. DFID India, under a regional Climate Proofing Growth and Development (CPGD) programme, is supporting these states to implement their SAPCCs. This programme would be strongly aligned with CPGD.

What measures can be used to monitor Value for Money for the intervention?

Economy
Economy refers to ensuring lowest cost of procurement of goods and services within project design, and focuses on making sure that the unit costs are benchmarked against market norms[41]. This programme’s economy will be measured in terms of the management fee unit cost for programme delivery. The Management Agency responsible for delivering this programme will be selected through a competitive process. Comparison will be made with ongoing DFID India programmes such OMEGA and PACS and the Asia Regional Team’s Climate Proofing Growth and Development programme in India. These programmes are of similar scale and implemented through a Managing Agency selected by DFID.
[41] DFID’s Approach to Value for Money (VFM); Department for International Development

Efficiency
Efficiency relates to how well inputs are converted to outputs. It will be measured in terms of costs per output of this programme, while maintaining acceptable quality of outputs. The key outputs that will be measured are the following:
- % of technical staff in MGNREGS implementation system trained on climate change planning, monitoring and implementation competencies;
- number of local implementation organizations including women Self Help Groups trained on participatory and climate compatible planning of physical assets;
- number of institutional mechanisms created to mainstream climate in MGNREGS;
- number of evidence pieces, policy and knowledge products developed;
- number of tools and processes developed to make the implementation system efficient.

The unit cost of these outputs will be tracked over time under this programme, as well as compared with similar programmes of other donors and DFID India. For example, GIZ and UNDP are supporting the Ministry of Rural Development on capacity building, policies and evidence generation under MGNREGS. DFID’s PACS and OMEGA programmes also provide technical assistance of a similar nature.

Effectiveness
The effectiveness of the programme will be measured in terms of outcome indicators as identified in Log frame. At impact level, the effectiveness will be measured in terms of number of vulnerable poor made more resilient per unit technical assistance investment. At outcome level, the effectiveness will be measured in terms of the following:
- Amount of public investment directed for climate resilience of vulnerable poor;
- Improvement in Return on Investment from the physical assets built under MGNREGS;
- Improvement in completion rate of assets in MGNREGS;
- Reduction in losses and damages to physical assets due to climate extremes;

Since the evidence base on these outcomes is limited, particularly in terms of baseline, the Management Agency will collect related information during the inception phase. This will form the basis of monitoring results achieved through this programme.
## Summary Value for Money Statement for the preferred option
The Programme is designed to have a transformational effect on the world’s largest labour-based social safety net programme. By providing technical support to improve quality of assets built under MGNREGS, the proposed ICF investment would deliver direct benefits to approximately 5 million people with a Benefit Cost Ratio of 2.59 under the preferred option, as well as avoiding the loss of £15 million pounds of public money and enhancing the effectiveness of the £4 billion spent annually by the Government of India on MGNREGS.

Over the medium term the programme will support a shift from MGNREGA as a social safety net only to an investment in rural economic development, reducing the vulnerability of hundreds of millions of poor people to flooding, drought and high temperatures.

The programme will be managed to ensure value for money throughout the project cycle, including through competitive tendering, using output based payments to encourage innovation, allowing an inception period to collect baseline data, as well as including a break clause to allow for potential re-orientation of the programme after 18 months implementation. Value for money metrics for economy, efficiency and effectiveness will be monitored on a quarterly basis throughout the programme.

Commercial Case
## A. Clearly state the procurement/commercial requirements for intervention
DFID will competitively procure a Management Agency, either through an open tendering process or through an existing framework agreement, with support from the Procurement and Commercial Department (PCD) under a service contract for up to £9.5 million. The Management Agency will provide technical assistance to the Ministry of Rural Development and also to the state departments implementing MGNREGS in Bihar, Odisha and Chhattisgarh. We anticipate that the Management Agency will form a consortium of international, national and local organizations to deliver this programme. The anticipated budget split between different components is discussed further in the Financial Case.

At central level the Management Agency will manage a Research and Innovation Fund, under which international/ national experts would be sub-contracted to carry out high value evidence generation, research and policy analysis and developing innovative IT based tools and processes for integrating climate resilience under MGNREGS. This has the potential to enhance existing Indo-UK policy and research partnerships.

At state level the Management Agency will provide technical capacity building support to MGNREGS implementation agencies in three states (delivering in 100 Blocks). We anticipate that the Management Agency will engage local organisations including state based technical organisations and Civil Society Organizations for delivering the activities. Our pre-contract market engagement has confirmed the feasibility of this approach.

DFID will directly manage £0.5 million which will be used for (a) priority work during the start-up period, before selecting the Management Agency, (b) independent monitoring and evaluation, (c) financial audit over the lifetime of the programme, and (d) supporting lesson learning and strategic communications. The agencies/ organizations shortlisted to do such activities will be contracted through a competitive process.
## B. How does the intervention design use competition to drive commercial advantage for DFID?
A competitive tendering process will be used to select the Management Agency. The process will be managed by Procurement and Commercial Department (PCD) either through open tendering in the Official Journal of the European Union (OJEU) or under the Wealth Creation framework’s Lot B: Rural Economic Development, Livelihoods, and Natural Resource Management.

To ensure value for money, all contracts will be output-focussed, with payments linked to the achievement of agreed outputs / milestones. The Terms of Reference for the Management Agency will set out the required outputs and encourage suppliers to propose innovative and workable solutions. Bidders will be expected to submit fully-costed proposals with a detailed breakup of direct and indirect cost that include robust methodologies and timelines. Costs will be benchmarked against the market. Shortlisted bids for the Management Agency will be reviewed by DFID in consultation with the Indian Ministry of Rural Development using the appropriate Technical and Commercial Evaluation process. The selection criteria would insist on local/ international experience and methodology, and also give weight to innovation and proposals to increase value for money by the supplier.

The tender notice will state that bids would be welcomed both from single agencies and from multiple agencies joining up to form partnerships or consortia. Allowing consortia to bid means that we are more likely to be offered the range of skills required – programme management, access to international expertise, and technical capabilities. We expect non-governmental organisations and other agencies with strong experience in livelihoods, natural resource management and social protection to be part of competing consortia.

In the event that the Management Agency plans to sub-contract the delivery of specific services, it will be required to comply with DFID’s standard procurement practices when sub-contracting and procuring goods and services. Any sub-contracts and associated fees/ costs will need to be agreed with DFID.

The Research and Innovation Fund which will be managed by the Managing Agent will competitively select innovative ideas which would then be supported for full development and piloting. This will allow leading organisations with niche expertise from the UK and elsewhere to partner with Indian counterparts for joint research, innovation and evidence generation activities.
## C. How do we expect the market place will respond to this opportunity?
During the design phase of the programme, we undertook initial market analysis to identify what expertise was available in India, the UK and elsewhere, and how to best access this expertise so as to achieve value for money. A comprehensive market assessment was carried out by Climate, Environment, Infrastructure and Livelihoods Professional Evidence and Applied Knowledge Services (CEIL PEAKS). The assessment identified more than twenty UK based organizations with expertise in social protection programmes, climate science and modelling, policy research and evidence generation and designing climate resilient infrastructure. A summary of the assessment is attached in Annex 4.

Initial discussions with potential UK based organizations such as Centre for Social Protection, IDS Sussex, Manchester University, Grantham Research Institute LSE, HR Wallingford, Mott McDonald, Ricardo-AEA, IIED and ODI has indicated their interest in this programme. In India, consultation with a range of technical CSOs (e.g. PRADAN, Development Alternatives), existing DFID India suppliers and leading academic institutions like Indian Institute of Technology (IIT) Delhi and the Indian Institute of Science (IISc) Bangalore was carried out. All these organizations have experience of working on MGNREGS, livelihood and natural resource management programmes in India. They have also expressed strong interest in participating in this programme.

Several Indian agencies, including the Indian Institute of Science Bangalore and Indian Institute of Technology (IIT) Delhi are already partnering with leading UK based academic and research institutions on rural development programmes in India and specifically on MGNREGS. Subject to the outcome of the competitive processes set out above, the programme could foster these partnerships and develop new partnerships which could be beneficial beyond the programme period. We will also engage the Ministry of Rural Development further to identify more potential partners including government agencies like National Institute of Rural Development and State Institutes of Rural Development who have supported the Ministry on MGNREGS and other rural development programmes.

A pre-bid meeting with potential suppliers would be held as part of the procurement process to ensure that the suppliers understand the requirements of the programme before the bidding process is undertaken. This will also help potential bidders to form the right kind of consortium to deliver this programme.
## D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?
Key cost drivers: The key cost elements will be the professional fees of the Managing Agency. Although the contract will be output based to enable DFID to minimize risk and incentivize the Managing Agency to perform better and on time, the detailed breakup of the costs, including fee rates, provided by the Managing Agency will be assessed against market benchmarks.

Monitoring cost drivers: Benchmarking with other programmes in India, regionally and globally will be undertaken to ensure that unit costs are competitive. Appropriate safeguards and sanctions to ensure satisfactory performance will be written into the contract. Monitoring arrangements of the programme will include key performance indicators to monitor quality and timely performance. Linking payments to achievement of contract deliverables will ensure support management oversight including early identification of emerging risks.
## E. What is the intended Procurement Process to support contract award?
As discussed above a competitive tendering process will be used to select the Management Agency. The evaluation of bids will be done in close collaboration with the Ministry of Rural Development. The evaluation criteria will include knowledge of the climate resilience livelihood and natural resource management sector, previous similar experience, a proven record of delivery quality and value for money in commercial management performance.
## F. How will contract and supplier performance be managed through the life of the intervention?
In the case of a consortium partnership, a single contract will be issued to the lead consortium partner who will be responsible for managing other partners. An inception period of six months will be included in the contract to enable development and agreement of quarterly milestones for the remainder of the programme. A break clause after eighteen months will allow for substantive review of progress and possible re-orientation. A standard termination clause in the event of unsatisfactory performance will be included in the contract.

The Management Agency will be required to submit reports on a quarterly basis providing summaries of progress against the mutually agreed milestones and log frame indicators. DFID will hold regular review meetings with the agency, especially to inform each Annual Review. Partner government Ministries at national and state level, as well as programme beneficiaries will also be engaged in review processes. DFID will carry out an annual audit of the Agency to ensure financial compliance and value for money, and to establish costs and outputs for future years based on delivery of previous years’ outputs. Annual post-procurement reviews will be undertaken on a sample of any sub-contracts let by the Management Agency.

The supplier would be part of DFID India’s Key Supplier Management (KSM) programme since this is a complex programme would be a high value contract. The supplier would also be monitored through the Contract Performance Review (CPR) programme for India. The KSM and CPR are managed by the Commercial Adviser in India along with support from programme teams.

## Financial Case
## A. What are the costs, how are they profiled and how will you ensure accurate forecasting?
The programme will provide technical assistance of £10 million from International Climate Fund resources over 4 years (2015/16-2019/20). The Table below shows the indicative break-up of programme costs. Year 1 spend is low to allow for the time taken to procure the Managing Agent.
Table: Indicative Programme Costs
Spending Modality	Budget Head	Outputs	Year*/ £ millions				Total (million)	%
			Yr 1	Yr 2	Yr 3	Yr 4
Component 1: / TA contract with Management Agency (£9.5 million)	Technical capacity building of implementation agencies and supporting institutions (£7 million)	Output 1: Strengthened technical skills of MGNREGS functionaries and implementation system	1	2	1	1	5	70
		Output 2: Enhanced technical capacity of supporting institutions	0.1	1.0	0.5	0.4	2
	Research and innovation fund / (£2.5 million)	Output 3: Innovative ICT based tools and processes developed	0.1	0.5	0.5	0.2	1.3	25
		Output 4: Evidence generated, research and knowledge created and disseminated	0.3	0.3	0.3	0.3	1.2
Component 2: / DFID (£0.5 million)	A programme post, management, monitoring and evaluation	M&E and support during inception period (before MA is contracted)	0.20	0.10		0.20	0.5	5
		Total	1.7	3.9	2.3	2.1	10	100.00

Accurate forecasting will be achieved as follows. The Managing Agency will submit detailed financial and narrative progress reports, on a quarterly basis, which will also include an assessment of risks associated with delivery. These reports will project realistic spend the financial year broken down by quarter on all major budget lines. The Managing Agency will be required to inform DFID in advance of any unexpected potential significant changes in forecasts. The Programme Manager will rigorously reconcile these forecasts against (i) relevant data on Aries; (ii) work plans and budget; (iii) previous reports; and (iv) previous disbursements and past spending trend. Any discrepancies will be raised immediately with Managing Agency and necessary changes to forecasts will be agreed. The DFID Programme Manager will develop a strong working relationship with the Managing Agency enabling effective and pro-active engagement on programme issues including interrogating the financial projections. The Senior Responsible Owner (SRO) programme will prepare a Delivery Plan which will include delivery risks and strategies to ensure accurate forecasting is made in the programme.
## B. How will it be funded: capital/programme/admin?
The programme will be funded from DFID’s central programme resources budget, under the International Climate Fund.
## C. How will funds be paid out?
Technical Assistance funds will be paid by DFID to the Management Agency. The fund managed directly by DFID will be paid to consultants selected through a competitive process for specific activities as described in the Financial Case.

During the inception phase the Managing Agent will submit a work plan with quarterly milestones. Payment will be made in arrears on a quarterly basis against satisfactory delivery of outputs as per this work plan. The Management Agency will submit a quarterly progress report along with invoice for fees and expenditure.
## D. What is the assessment of financial risk and fraud?
The financial risk and fraud is assessed medium-low. The key risks are around any of the sub-contracted work managed by the Management Agency. Particularly, for capacity building activities at local level the Management Agency may need to sub-contract one or more local Civil Society Organizations (CSOs). The financial and management capacities of these CSOs may be medium to low. To address this, the following measures will be taken:
- The Managing Agency will be assessed based on their financial management performance and past experience of working with CSOs and ensuring compliance of sub-contracted work as per DFID’s requirements;
- The Managing Agency will be required to select CSOs with at least basic financial and management experience. The threshold will be agreed between DFID and the Managing Agency during the inception phase;
- The Management Agency will be required to maintain strong financial and management information systems to prevent fraud and misuse; achieve value for money; and comply with the Foreign Contribution Regulation Act and Income Tax requirements of CSOs as per Indian laws.

The SRO will highlight this as a key risk in the Delivery Plan and regularly review it to take necessary measures. The Ministry of Rural Development and State governments will be engaged on this and their advice will be sought at regular Steering Committee and Management Committee meetings.
## E. How will expenditure be monitored, reported, and accounted for?
DFID will directly oversee the Management Agency. Component wise/ year wise budgets will be set on ARIES. Purchase Orders will be created once contracts are put in place. This will ensure approved allocation and budgetary ceilings are not breached. All expenditure will be against pre-agreed fee rates and project costs. Expenditure will be monitored, reported and accounted for on an annual basis, and will form part of the Annual Review cycle. The SRO will be responsible for ensuring that all procedures for financial reporting, accounting and audit are fully complied with. On a day to day basis the Programme Officer will ensure that financial transactions are well managed. Payment will be made against successful delivery of agreed milestones and achieving expected outputs.

Management Case

A. What are the Management Arrangements for implementing the intervention?
DFID’s resourcing strategy: The A2 Climate and Environment Adviser of the Energy Climate and Growth Unit (ECGU) of DFID India will be the Senior Responsible Owner (SRO) of this programme. The SRO would draw support from A1 Senior Climate Change Adviser (0.3 FTE) and B1 Programme Manager (0.25 FTE) for overall management and monitoring of the programme. A Programme Funded Post will be created for managing the programme especially the £0.5m component which DFID will directly manage. This will also enable intensive preparatory work before the Managing Agency is contracted. Cross cutting DFID experts in governance, gender, economic and M&E will be drawn appropriately as and when required. Annual Reviews will draw on the cadre 10% contribution of advisers across DFID.

Governance strategy: A Management Agency will be contracted for day to day management and delivery of outputs at the programme level. The ECGU Programme team will meet formally (at least quarterly) with the Managing Agency. Progress against the outputs will be subject to oversight by DFID on a quarterly basis which will form a key determinant for release of funding. Financial reports, compliance and administrative functions will be managed by the DFID India programme manager. The DFID programme management team will coordinate component reporting as necessary to meet DFID Annual Review requirements. The Managing Agency will be contractually responsible for programme delivery including implementation, monitoring of the programme as well as ensuring technical and financial reporting.

The programme will have the following governance structure to ensure strategic oversight and guidance:
A Steering Committee at central level comprising members of MoRD, DFID and a representative from respective State Governments. The Steering Committee will be chaired by the Joint Secretary (MGNREGA) of MoRD and will meet bi-annually. The Committee will review programme progress, provide necessary steer, help the programme to respond to any change in context and develop national level strategies for large scale replication of the results across the country. Subject to agreement the Committee will also include representatives from GIZ and UNDP who are providing complementary support to MoRD on MGNREGS.

State level management committees, one per state, comprising members of State Rural Development Departments (including MGNREGS, National Rural Livelihood Mission, IWDP) and DFID. The Management Committee in each State will be chaired by the Secretary Panchayati Raj Department or any equivalent person nominated by him/her. It will include experts nominated by State Governments and members of DFID partner organizations working on other DFID programmes in respective States. The Management Committee would ensure that the programme achieves its objectives and also develop strategies on scaling up the results across the state. Each State committee would also meet bi-annually.

An Independent Advisory group comprising of members from non-government organizations, think tanks, academic institutions and private sector would also be formed which will provide technical advice to the Steering Committee and State Committees. The Chair of the Advisory Group will be nominated by the Ministry of Rural Development. The group will guide on effective use of the Research and Innovation Fund by suggesting pilot activities, identifying areas of policy importance and developing strategies for convergence for overall economic development, poverty alleviation and climate resilience of rural poor.

B. What are the risks and how these will be managed?
The key programme risks are as set out in the Table below
	Risk	Prob.	Impact	Mitigation strategy
		H/M/L
1.	Government makes modifications on MGNREGS goals, priorities and implementation processes.	L	H	The probability of this risk is low as the programme is designed to help deliver the new government’s focus on MGNREGS as an investment in rural economic growth. The programme has been designed in close collaboration with the top officials in the central Ministry of Rural Development. The core objective of improving resilience of poor under MGNREGS remains. Flexibility would be kept under the programme to accommodate procedural changes to how MGNREGS is implemented. The Steering Committee and State Management Committees will advise on any potential risks and suggest modifications if required.
2.	Implementation weaknesses / corruption and/or other scandals at national or state level adversely affect reputation	M	H	At State level, the programme would work in only those pilot Blocks where overall governance of MGNREGS is good, typically where civil society organizations are active. These Blocks will be selected from the 2500 priority blocks identified by Ministry of Rural Development (MoRD) for effective implementation of MGNREGS. The Ministry has also committed to provide effective support on this aspect. In addition, the main objective of the programme is to strengthen MGNREGS system’s capacity on planning, implementation and monitoring of assets. Risks would be further mitigated through independent audit of programme and a proactive communication strategy.
3.	Reduction in economic growth rates (national and state) erodes commitment to progress on poverty and rural livelihoods in practice.	L	M	We will monitor the situation in programme areas. Work with national, state and local government proactively.
4.	Project functionaries at district, block and village level have inadequate knowledge of schemes	M	H	This will be a key focus of capacity building. The government has taken various initiatives recently to enhance knowledge and awareness about MGNREGS. In the intervention States, we will also benefit from current DFID support to strengthen MGNREGS governance.
5.	Private sector unwilling to cooperate	L	L	The private sector will be engaged in a strategic way through participation in the Independent Advisory Group.
6.	NGOs, civil society, technical institutions unwilling or unable to cooperate	L	M	Engaging and building their capacity will be a key focus of the programme. Engage with service providers to ensure services are delivered and to set standards for performance. Extra weight would be given to contractors which have experience of successfully managing a number of CSOs and technical partners.
7.	Local political elites and vested interests are able seriously to disrupt implementation of the programme.	L	H	The mitigation strategy would be (a) careful selection of Blocks, (b) engage and maintain dialogue with elites, and (c) to work in coalition with others – especially civil society organisations.
8.	Extremists disrupt delivery of sustainable rural livelihood programmes	M	M	Maintain effective local dialogue and contact with law enforcement agencies. Blocks with limited extremist presence would be selected. Also, Duty of care for suppliers will be ensured by DFID.
9.	Major natural disaster disrupts implementation of the programme.	M	M	The risk of a major natural disaster occurring in part of the country high, but impacts would probably be limited to one region. Integrated natural resource management and watershed principles of designing physical assets would reduce the impact of weather extremes on physical assets.

C. What conditions apply (for financial aid only)?
Not applicable.

D. How will progress and results be monitored, measured and evaluated?
A comprehensive Monitoring and Evaluation Framework will be designed by the Management Agency in the inception phase of the programme. The framework will be based on the Log Frame and Theory of Change and will clearly specify the timely delivery of the expected results. The evaluation framework will draw on central DFID work on ICF indicators and methodology. A six month inception phase will enable collection of baseline data. The Framework will be agreed with DFID and by the Steering Committee of this Programme.

- The milestones and deadlines set out in the M&E framework will be included in the programme’s Delivery Plan;
- Progress will be reviewed on a quarterly basis by the SRO and on half yearly basis by the Steering Committee and State Management Committee. The Management Agency will produce a quarterly report which will form the basis of the six monthly reviews;
- Annual Reviews will be undertaken in line with standard DFID requirements. This will be led by DFID or by independent experts commissioned by DFID.
- The Annual Review at the end of Year 2 will be preceded by an independent assessment of progress against planned results. This will inform discussion in advance of the contract break clause (which is set at 18 months after the start of the contract) to agree forward strategic priorities and work plans, identify key lessons and risks, and consider what changes are needed to maximise the likelihood that long term outcome indicators are achieved.
- A Project Completion Review will be carried out at the end of Year 4 to assess the overall performance, sustainability and impact of the programme.
- An independent impact evaluation (commissioned and managed by DFID) will be undertaken in the final year. There are three key questions DFID particularly wants to understand in evaluating the programme:
1. Attribution – where were only DFID’s actions decisive for change?
2. Cost-effectiveness – how can DFID show it managed costs optimally and how does this compare to Technical Assistance interventions in other sectors?
3. Sustainability – how has the Government of India sustained policy change institutionally?