Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to Malaria Control in the Democratic Republic of Congo
Programme Value: £39.5		Review Date: 7 April 2015
Programme Code: 203458	Start Date: 8/05/2013	End Date: 30/09/2019

Summary of Programme Performance
Year	Year 1 / 2014	Year 2 / 2015
Programme Score	A	A
Risk Rating	M	M

Summary of progress and lessons learnt since last review.

This programme consists of three components, as follows:
- Component 1: Distribution of bednets[1] in Kasai occidental
  [1] Throughout this document, the generic term ‘bednet’ is used to refer to long-lasting insecticide treated nets (LLINs).
- Component 2: Increasing the availability and accessibility of first-line quality-assured artemisinin-based combination therapies (QAACTs) in the private sector, and
- Component 3: Strengthening the capacity of the National Malaria Control Program (Programme National de Lutte Contre le Paludisme, PNLP) with a focus on their ability to generate and use information.

The previous annual review was carried out in March 2014. At that time, component 1 had entered the implementation phase, following approval of the breakpoint transition in December 2013. Due to the uncertainty, complexity and challenges surrounding the other two components, the design phase for these was extended to one year and ended in Sepember 2014. This additional time has enabled Population Services International (PSI) to make an in-depth assessment / analysis of the Artemisinin-based Combination Therapy (ACT) and Rapid Diagnostic Test (RDT) market in Kinshasa, identify risks and propose a mitigation plan. Following this, components 2 and 3 entered the implementation phase in November 2014.

Component 1
PSI procured 4,425,255 bednets to cover all 44 health zones in Kasai Occidental through a traditional mass distribution approach using fixed distribution sites. It was originally intended that the distribution be managed exclusively by PSI, but in the end this was done jointly with IMA World Health (IMA), the current implementer of DFID DRC’s primary healthcare programme Accès aux Soins de Santé Primaire (ASSP). This change was made in reponse to an offer of a donation of bednets from Against Malaria Foundation (AMF) to be distributed by IMA in nine of the 44 health zones using a door-to-door approach approved by the PNLP.

Recent findings from Demographic and Health Survey 2013-14 (DHS) have demonstrated the progress made in DRC in term of ownership and use of bednets, even if there is still a discrepancy between them: 70% of households have at least one bednet, and 56% of children under five and 60% of pregnant women slept under a bednet the night before the study. However, these figures also show that there remains further progress to be made in achieving high levels of coverage. We are expecting that the findings from the ongoing surveys carried out by DFID DRC’s other malaria programme “Support to universal access to long lasting insecticide-treated nets in Equateur” will clarify the factors influencing the use and non-use of bednets.

Components 2 and 3
The DHS reveals that amongst children under five who had had fever within two weeks before the study, 55% sought treatment, but only 6% received an ACT. Furthermore, the bulk of care-seeking for fever occurs in the private sector, but the quality of care in this sector is poor[2]. This is a major public health concern. Making QAACTs available in the private sector is a pioneering project in DRC, and has had the advantages of leveraging additional funding from the Global Fund, and of fostering collaboration with the Clinton Health Access Initiative (CHAI) in the development /design of a national strategy for ACT and RDT distribution in the private sector. Other donors/agencies may be attracted by this first experience in DRC.
[2] According to findings from ACTWatch 2013, fewer than half of providers in public and private facilities in Kinshasa could name one of first-line treatments for uncomplicated malaria recommended by PNLP (Artesunate-Amodiaquine or Artemether-Lumefantrine), and only 14% of drug shop providers could name a first-line treatment.

By distributing approximately 3.8 million bednets[3] and 17 million doses of QAACT and by strengthening malaria surveillance with the rehabilitation and equipment of ten sentinel sites, this programme is fully in line with DFID’s Results Framework for Malaria, including the four pillars that are identified as necessary to support achievement of malaria mortality and morbidity reduction: improve the quality of services, expand access and increase demand, support innovation and global public goods, and focus on impact and results. DRC is the country with the second largest burden of malaria worldwide, and this programme is also contributing to achieving the distribution of 9 million bednets as set out in the DRC Country Operational Plan.
[3] This figure differs somewhat from the anticipated figure of 4.425 million bednets. See subsequent sections of the annual review for explanation.

Acronyms

ACT	:	Artemisinin-based Combination Therapy

AL	:	Artemether-Lumefantrine

AMF	:	Against Malaria Foundation

AMF-m	:	Affordable Medicines Facility – malaria

ASAQ	:	Artesunate-Amodiaquine

ASF	:	Association de Santé Familiale (PSI’s affiliate in the DRC)

ASSP	:	Accès aux Soins de Santé Primaire (Access to Primary Health Care)

CHAI	:	Clinton Health Access Initiative

CHW	:	Community Health Workers

DFID	:	Department for International Development

DHIS2	:	District Health Information System 2

DPM	:	Direction de Pharmacie et Médicament (Pharmacy and Medicines Directorate)

DPS	:	Division Provinciale de la Santé (Provincial Health Division)

DRC	:	Democratic Republic of the Congo

FDSS	:	Fonds de Développement des Services de Santé (Health Services Development Fund)

IMA	:	IMA World Health

ICP	:	Inter-Personal Communication

LLIN	:	Long-Lasting Insecticide-Treated Nets (generally referred to as ‘bednets’ in this document)

MSP	:	Ministère de la Santé Publique (Ministry of Public Health)

OJEU	:	The Official Journal of the European Union

PMI	:	President’s Malaria Initiative

PNLP	:	Programme National de Lutte Contre le Paludisme (National Malaria Control Programme)

PSI	:	Population Services International

RDT	:	Rapid Diagnostic Test

STPHI	:	Swiss Tropical Public Health Institute

QAACT	:	Quality-Assured ACT

WHO	:	World Health Organization

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203458/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203458/documents/

Outline of the programme

The UK is supporting the delivery of approximately 4.4 million long-lasting insecticide-treated bednets (LLINs) through a mass campaign. In addition, the UK will support key objectives of DRC’s National Malaria Control Programme (Programme National de Lutte Contre le Paludisme, PNLP) which addresses some of the major constraints to improved malaria control in the country such as a lack of information and capacity for planning and limited availability of Artemesinin-based Combination Therapies (ACTs).

4,425,255 bednets were procured to cover 44 health zones in Kasai Occidental. However, whilst planning was underway, the PNLP expressed a need to pilot a door-to-door approach to distribution, using a donation of bednets from Against Malaria Fundation(AMF). This had the following consequences:
- The number of health zones to be covered by mass distribution from fixed distribution points under this programme was reduced to 35, and hence the estimated number of bednets to be distributed was reduced to 3,745,000
- IMA World Health (IMA) took over responsibility for implementation in the remaining nine health zones under DFID DRC’s primary health care programme Accès aux Soins de Santé Primaires (ASSP), using a door-to-door approach to distribute the bednets provided by AMF
- The 676,000 bednets which would have been distributed in these nine health zones (but which were no longer required for this purpose as a result of the donation from AMF) were transferred to IMA for routine distribution in other health zones supported by ASSP.

The total budget for this “design and build” programme is £39.5 million over six years (2012/13-2018/19) approved in the business case. After the design phase, the value of the contract signed with the lead consortium was £36 million.

The programme is made up of three main components:
- Component 1 (£15.8 million) – the distribution of between 3.5 to 4 million bednets in the DRC. This allows DFID to achieve results at lower risk, but through less sustainable interventions with less long-term impact on key partners including government.
- Component 2 (£14.5 million): Improving availability, accessibility and affordability of quality-assured artemisinin-based combination therapies (QAACTs) in the private sector in Kinshasa. The private sector accounts for approximately 70% of antimalarials dispensed in DRC, but only 2.6% of these are quality-assured QAACTs. This means that a large number of people are receiving treatment that is not quality assured, and has the potential to drive the emergence and spread of artemisinin resistance. The PNLP has identified this as a priority issue, and there is potential to deliver transformational impact by supporting its efforts in this area.
- Component 3 (£4.7 million): Strengthening the capacity of PNLP with a focus on their ability to generate and use data for decision making. There are limited data on the epidemiology of malaria in DRC, on the availability and effectiveness of key interventions in the country, and on the best mechanisms for delivering these. The data that do exist tend to be of limited availability or quality, and are poorly used. This is a key constraint to the effectiveness of malaria control in DRC, and hinders the PNLP in fulfilling its strategic leadership function.

The programme is being delivered by a consortium led by PSI-ASF (Population Services International and their local affiliate Association de Santé Familial). Implementation of components 1 and 2 is led by PSI, and of component 3 by the Swiss Tropical Public Health Institute (STPHI).

The value of the current contract signed between DFID and PSI is £36.1m GBP. They have not been contracted for the full value of the business case in order to ensure that DFID could respond flexibly to needs as they arose during the life of the programme. The contract for this programme took longer than expected to procure following approval of the business case in September 2012. PSI won the OJEU standard international competitive tender process and the contract was signed in late September 2013.

The programme was set up with separate design phases for component 1 and components 2 and 3, which have progressed at different rates. The design work for component 1 (bednets) was approved internally within DFID DRC in December 2013. For components 2 and 3, the design phase was extended until the end of September 2014.

The implementation phase for component 1 (bednets) began in December 2013. For components 2 and 3, the implementation phase has recently started and the amended contract was signed by PSI on 13 November 2014.

Expected results

Through this programme, the UK will:
- Support the distribution of approximately 3.7 million bednets
- Help to make 17 million doses of QAACT available to the populationof Kinshasa through the private sector
- Set up or rehabilitate ten sentinel surveillance sites for malaria.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

This annual review was conducted in April 2015 but the process started in March with the quarterly meeting held by PSI, involving the key malaria stakeholders: USAID, WHO and Government representatives including the PNLP, the Directorate of Medicines and Pharmacy (DPM) and provincial medical inspectors from the four provinces in which mass distributions of bednets were implemented in 2014. PSI was represented by their local team and their regional programme support team based in Nairobi. The process included a review of the risk matrix and a presentation by PSI of the progress made by the programme to date.

The annual review covers the period from March 2014 to March 2015 and draws upon data provided by the quarterly narrative reports, and PSI’s presentation on 14 April 2015.

Implementation of component 1 started in January 2014 after 3 months of design phase. The following activities have been carried out, and according the schedule: macroplanning, training, implementation of a household census, supervision, and microplanning. The mass campaign was launched on time in November 2014. The key main activities remaining are: interpersonal communication (IPC)[4] to encourage better use of bednets, ongoing / continuous distribution bednets aimed at sustaining universal coverage until the next campaign, and implementation of a post-campaign survey to provide data on household level coverage.
[4] Interpersonal communication refers to a process in which trained individuals systematically visit each household in order to have face to face discussions with household members regarding the programme and the importance of bednet utilisation.

Implementation of components 2 and 3 was delayed due to the extension of the design phase for these components from the original three months to 12 months: during the initial three months, it became clear that the issues were of a level of complexity that required more detailed analysis prior to implementation, and so DFID and PSI mutually agreed to extend the design phase for these components (this was consistent with the assessment made at the time of the approval of the business case that these components were higher risk). This additional time allowed PSI to make a deeper analysis of the situation, to promote the development of a viable market for QAACTs in Kinshasa based on the market constraints identified, and to support PNLP to develop a 2015 National Workplan for strenthening the sentinel surveillance of malaria in DRC. In addition, the extended design phase created an opportunity for the programme to attract other donors such as Global Fund and CHAI. The participation of these additional partners enabled the programme to expand in scale, such that the entire population of Kinshasa will be covered.

The breakpoint transition for components 2 and 3 was approved in September 2014 and the contract amendment was signed in November 2014. Since then, a series of preparatory activities have been implemented prior to startup of the full distribution of ACTs and RDTs expected to begin in June/July 2015. These activities have included the following:
- Identification of five World Health Organization (WHO)-approved manufacturers of ACTs
- Identification of five local importers
- Obtaining approval from the Global Fund to use the Green Leaf logo[5] on ACTs and preferential prices negotiated by the Global Fund with ACT manufacturers
  [5] The Green Leaf logo is a recognisable emblem owned by the Global Fund that signifies to consumers that the medicine is quality-assured.
- Recruitment of local staff
- Development of Ministry of Health (Ministère de Sante Publique, MSP) training guides for malaria case management in the private sector
- Ordering RDTs for the first two years of the programme
- Mapping registered pharmacies in Kinshasa
- Requesting authorisation from the MSP to use RDTs in registered pharmacies
- Advocacy sessions with owners of pharmacies and drug shops
- Selection of two agencies to work on ACT / RDT communication campaigns
- Advocacy for tax and tariff reductions
- Baseline assessment of eleven existing sentinel sites, and
- Updating the risk matrix.

Signature of contracts with manufacturers and importers is expected in May 2015 and then the first quantity of subsidised ACTs will be transported by airplane in order to permit distribution to commence on the planned dates.

Annual outcome assessment

The anticipated outcome of the programme consists of improved control of malaria in DRC. According to the logframe, the overall outcome performance is measured by three indicators:

Indicator	Objective (by March 2015)
% of individuals in households who slept under a bednet the previous night in targeted health zones in Kasai Occidental	80%
% of children under 5 years who received quality-assured ACT among those receiving any antimalarials in the private sector in Kinshasa.	10%
Number of quarterly (routine and sentinel surveillance site) data validation sessions by PNLP at central level.	Two quarterly data validation sessions by PNLP

The mass campaign was successfully completed in November 2014 with approximately 2.8 million bednets distributed. Approximately 934,548 further bednets remain available for ongoing/continuous distribution to sustain universal coverage over time. A post-campaign survey to measure the achievements of the programme in terms of bednet coverage is planned for June 2015 (according to WHO norms, the post-campaign survey should be carried out six months after the distribution has taken place). The pre-campaign survey carried out in October 2014 has already provided the baseline to be used.

The majority of pre-requisites for effective implementation of 2 and 3 components were realised (the outstanding pre-requisite consists of final signature of the contract between PSI and QAACT manufaturers). In view of this and the fact that the distribution of bednets is complete, the programme is on-track to achieve / reach its overall outcome. The performance of PSI and its sub-contractors has been satisfactory, as demonstrated by the timely completion of the mass distribution and the successful delivery of the design phase deliverables for each of the programme components (including preparatory work for components 2 and 3), but we will encourage them to be more proactive in anticipating some activities such as negotiation of the contract with manufacturers.

Three mobile phone operators (Airtel, Orange, and Vodacom) were involved to provide SMS messages to promote the mass distribution campaign and raise awareness of correct and consistent bednet use. With regard to component 2, the Global Fund has contributed substantial additional resources for the procurement of QAACTs (6.6 million doses) and RDTs (1.7 million units) for the private sector in Kinshasa, and CHAI collaborated with the PNLP to develop the national strategy for private sector malaria case management.

Overall output score and description

The programme’s performance is measured according to each of the following three outputs:

Output title	Overall output score	Impact weight	Comments
1. Increase to at least 80% the use of LLINs by pregnant women and children under 5 in Kasai Occidental by 2018	A	50%	Output met expectation (pending results of the post-campaign survey).
2. Increase availability, accessibility and affordability of QAACT in the private sector in Kinshasa	B	30%	Output moderately did not meet expectation . Pre-requisites are in place, and the logframe milestone is planned for March 2016. Contract with manufacturers not yet signed.
3. Improve availability and use of information for malaria control in DRC through increased capacity of the malaria control interventions	A	20%	Output met expectation. Pre-requisites are in place, and the logframe milestone is planned for March 2016.

1. Mass distributionof bednets: At the end of the campaign 2,813,925 LLINs were distributed against the the milestone of 3,745,000. The target set in the logframe was over-estimated and was based on data from the macroplanning process. The household census and the microplanning process found that the number of bednets required was in fact lower, and this figure was corrected: the full number of beneficiary households received bednets, and there is a remaining stock of approximately 934,548 bednets that could be used in continuous distribution mechanisms to sustain the universal coverage achieved by the programme. To make the continuous distribution most efficient, we must diversify distribution beyond the traditional channels (antenatal care and immunizations activities), and there is an opportunity to explore new channels such as school- and community-based distribution.
2. The initial milestones for components 2 and 3 are planned for March 2016 in the logframe, as the design phase lasted for one year and the contract was signed in November 2014. However, with the progress made and with the pre-requisites for effective implementation in place, the programme is on track to achieve the expected results.

Key challenges

Discrepancy between the number of bednets procured and the number distributed: It was necessary to initiate the procurement of bednets nine months before distribution was due to start. In order to achieve this, macroplanning data were collected one year before the distribution. The household census and microplan carried out two months before the distribution revealed that the size of the target population and hence the number of bednets required were in fact smaller than the macroplanning data had suggested.

Delayed start up for interpersonnal communication (IPC): Implementation of IPC was delayed as this approach is new to the PNLP and in DRC, and it was necessary to update the supporting materials and adapt them to the Congolese context.

Theft and fraud: there was an episode of theft of bednets in Dekese health zone and an instance of fraud involving an ASF staff-member. Investigations are underway and the Fraud unit has been informed.

Limited number of accredited private sector pharmacies in Kinshasa: The Directorate of Pharmacies and Medicines (DPM) has identified 120 pharmacies, 78 of which are fully accredited and 17 of which are going through the accreditation process. The programme has requested permission from the DPM to begin work with 20 accredited pharmacies in year 1, and is currently awaiting the response.

Policy regarding the use of RDTs in private sector pharmacies: national health policy currently does not allow the use of RDT in pharmacies. The programme has requested approval from the MSP to pilot the distribution of RDTs in private sector pharmacies, and is currently awaiting the response.

Key lessons

The involvement of local authorities and civil society organisations in preparatory activities for the bednet distribution campaign (as was the practice in the previous campaign implemented in 2011) contributed to the success of the bednets campaign in Kasai Occidental, including by building awareness of fraud and mismanagement risks. Involvement of the provincial government exempted the trucks transporting the bednets from payment of road tolls.

The use of a fiduciary agency to manage payments to campaign staff and for services at the peripheral level is best practice for reducing the risk of financial mismanagement (in the previous campaign, the funds were provided directly to public service providers to implement key activities of the distribution, and the risk of mismanagement of funds was high).

The appointment of data managers at the health zone level helped to improve data quality and increase reporting speed and completeness from the operational level to the provincial level and from the province to the national level.

Given the numerous partners supporting the PNLP, strong coordination is needed to avoid overlap and duplication of activities. To a considerable extent this is provided by the weekly partners’ meeting which is convened and chaired by the PNLP, but ongoing effort needs to be made to optimise coordination.

The innovative approach of this programme has attracted other donors and partners (GF, CHAI, AMF) and has reinforced partnership.

The shared breakpoint between components 2 and 3 meant that the complexity of the former component led to delays in moving into implementation of the latter. To some extent, these delays could have been avoided by having independent breakpoints for each programme component.

Key actions

DRC has completed a first cycle of bednet distributions across the country, and a second cycle of distributions is now underway. PNLP, DFID and other key malaria stakeholders should now begin discussions on updating current approaches to the prevention of malaria, including ways of increasing the use of bednets (a finding from the DHS 2013-14 was that there is still a substantial gap between the ownership and use of bednets). These discussions will be informed by the operational research carried out by DFID DRC’s “Support to Universal access to Long Lasting Treated Nets in Equateur Province” programme. The topics of this reseach are the following: the durability of bednets, the determinants of bednet use and non-use amongst the population and a review of the first cycle of mass distribution campaigns in DRC.

Has the logframe been updated since the last review?

Yes: at the end of design phase, the impact weightings were revised to 50%, 30% and 20% for components 1, 2 and 3 respectively, and the milestones for components 2 and 3 were changed to March 2016.

Recommendations

By June 2015, PSI should develop a plan for a continuous distribution mechanism to maintain the level of coverage by using the remaining 934,548 bednets.

By June 2015, PSI and DFID should discuss with PNLP how to develop a strategy (and associated guidance) to pilot school- and community-based distribution.

By May 2015, PSI should review the budget for component 1 in light of savings made by the programme, taking into account plans for continuous bednet distribution.

By June 2015, PSI should update the logframe, taking into account plans for continuous bednet distribution and anticipated changes to the market for QAACTs in Kinshasa.

DFID should work with PSI to improve the financial forecast and increase accuracy before the new financial year.

## C: DETAILED OUTPUT SCORING

Output Title	Increase to at least 80% the use of LLIN by pregnant women and children under 5 in Kasai Occidental by 2018
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones March 2015	Progress	Comments
Number of LLINs distributed during the mass LLIN distribution campaign in targeted health zones in Kasai Occidental	3,745,000	2,813,925	Met expectation: / The milestone was established on the basis of macroplanning data. The actual number of bednets required was found to be lower during the microplanning stage, and this latter number was subsequently distributed during the mass campaign. The balance of bednets (ie those procured but not distributed in the mass campaign) will be used for an ongoing continuous distribution, in order to maintain coverage.
% children under 5 years old who slept under an LLIN the previous night in targeted health zones in Kasai Occidental	≥80%	To be determined by the post campaign survey due to take place in June 2015	There is currently no specific concern that the milestone will not be met.
% pregnant women in Kasai Occidental who slept under an LLIN the previous night in targeted health zones in Kasai Occidental	≥80%
% households with at least one LLIN in targeted health zones in Kasai Occidental	≥80%
Number of radio and TV spot broadcasted in Kasai Occidental on LLIN	49,868	11,348 broadcast items (3,882 radio spots, 3,808 radio malaria songs, 1,866 TV spots, and 1,792 TV malaria songs) / 591,612 rapid SMS messages	Moderately did not meet expectation. / It is reasonable that the number of broadcast items was lower than initially anticipated, as: / 1) The target was set taking into account all 44 health zones in the province. During implementation nine health zones were allocated to the partner IMA. / 2) Following findings from the pre-campaign survey, more emphasis was put on interpersonal communication rather than mass communication. / Nonetheless, the number of broadcast items was lower than anticipated, even taking into account these factors.

The steps to be followed in planning a mass bednet distribution campaign (as recommended by the PNLP) and the objectives of each of these are described below:
- Macroplanning - Obtain an overview of the mass campaign, broadly estimate the campaign’s needs and establish a schedule of activities
- Procurement - Order bednets based on the needs estimated during the macroplanning, select the transporters from the point of manufacture to the distribution sites
- Pre-campaign survey - Establish a baseline for the indicators that will be used to measure the programme’s achievements through the post-campaign survey
- Training - Update the knowledge and skills of key actors involved in the campaign on elements such as the household census, data analysis, supervision etc
- Microplanning (including household census) - Determine specific details of the implementation of the campaign, including precisely determining the number of beneficiaries
- Distribution of bednets
- Post-campaign survey

Beside these steps, there are also support activities that include coordination, supervision and behaviour change communication.

Based on the 2013 macroplan, 4,425,255 bednets were ordered and procured to cover 44 health zones using a traditional mass distribution approach. However, during the planning process the PNLP said that it wanted to pilot a door-to-door distribution approach in nine of the health zones, using bednets donated by the Against Malaria Foundation (AMF). The consequence was that 35 health zones were to be covered by the mass distribution (using bednets procured by this programme) and nine health zones with the new approach (using bednets provided by AMF).

This released 676,000 bednets that had been procured by this programme for these health zones, but which were no longer needed. These bednets have been made available to IMA for routine distribution through DFID DRC’s health system strengthening programme Accès aux Soins de Santé Primaires (ASSP).

Summary of bednet stock procured for the programme

Bednets ordered	Utilisation during the campaign		Quantity	Comments
4,425,255	Distributed to target households	2,813,925		Distributed in 35 HZ
	Lost		764	Further information is awaited from PSI on these bednets
	Transferred to IMA		676,000	For routine distribution in ASSP zones
	Stocked in PSI/ASF warehouses		659,137
	Undistributed at the HZ level		275,411
	Damaged in PSI/ASF warehouses		18
4,425,255			4,425,255

The bednet distribution campaign was launched on 20 November 2014, one month earlier than initially planned. Before the launch, several preparatory activities were undertaken to build awareness of the campaign and of the importance of correct and consistent bednet use:
- 7,763 community health workers (CHWs) were trained to complete the household census in 35 health zones
- 1,105,361 residences were visited (1,103,358 traditional households and 2,004 non-traditional residences such as schools, hospitals and hotels) by trained CHW during the household census.
- 35 budgeted microplans were prepared, reviewed and validated by the PNLP and provincial health authorities
- 49,486 bednet vouchers, 51,030 posters, 1,310 megaphones with batteries, 8,364 T-Shirts, and 37 banners were distributed at the health zone level
- 591,612 SMS were sent during 19-25 November, in French and Tshiluba (the local language)
- A pre-campaign survey was carried out in September 2014 by the STPHI in collaboration with the Kinshasa School of Public Health, the key findings of which are as follows:

No	Indicator	Results
1	Percentage of households with at least one LLIN	37.9%
2	Percentage of households with at least one LLIN per 2 people	3.9%
3	Percentage of individuals in a household who slept under a LLIN the night before the study	18.4%
4	Percentage of children under 5 (CU5) who slept under a LLIN the night before the study	24.2%
5	Percentage of pregnant women who slept under a LLIN the night before the study	20.7%
6	Percentage of households exposed to messages about malaria	59.5%

These findings reveal a sharp decline in LLIN possession in the three years between the 2011 and 2014 campaigns and will be used as a baseline to measure the progress achieved by the programme through the post-campaign survey planned for June 2015.

In terms of behaviour change communications (BCC), 24 radio stations and six TV stations were used to broadcast key messages in Tshiluba and French regarding the distribution campaign and the importance of correct and consistent bednet use to prevent malaria. Beside this, the programme also worked with three mobile phone operators (Airtel, Orange, and Vodacom) to send 591,612 rapid SMS messages to promote the use of the bednets. The impact of this will be assessed through the post campaign survey, in the the level of bednet use amongst beneficiaries.

The programme has recruited 20 women’s groups and 200 schools to undertake inter-personal communication (IPC) activities in their communities alongside existing community health workers. However, there has been a delay in the implementation of this activity due to the fact the PNLP recommended a review/update of the IPC malaria flip chart before the starting. Implementation of IPC will now start in May 2015, and it is not thought that this delay will have any negative implications.

In the end, 2,813,925 bednets were distributed in 35 health zones against 3,745,000 planned on the basis of the macroplan. The balance of 934,548 bednets is available in the province and will be used in the coming months for ongoing/continuous distribution and to replace bednets that are identified during IPC as having been destroyed or damaged.

Output Title	Increase availability, accessibility and affordability of QAACT in the private sector in Kinshasa
Output number per LF		2	Output Score	B
Risk:		High	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones March 2016	Progress	Comments
Volume of QAACTs supplied through private sector importers in DRC (non-cumulative target)	1,900,000	Preparatory activities are underway and are largely complete, and distribution of QAACTs is due to start shortly. The milestone date (March 2016) has not yet been reached.	Based on current progress, the programme is on track to meet these milestones by March 2016
% of seleted private sector outlets in programme areas with Green Leaf QAACTs in stock (among outlets with any antimalarial in stock)	20%
% of private sector outlets in programme areas selling programme-supplied QAACT for children at or below the recommended retail price	To be determined during logframe review
Number of RDTs distributed through private sector outlets in Kinshasa (cumulative target)
Number of radio and TV spots on the GreenLeaf logo broadcast in Kinshasa c(non-cumulative targets)

The design phase for this component lasted for one year until September 2014, and the contract amendment was signed in November 2014. Since then, preliminary activities have largely been completed, and distribution is now ready to commence.

Through this component, the programme will provide a subsidy (in the form of a co-payment), which will be applied to guaranteed orders from identified importers to their respective manufacturers. The commodity co-payment will be 65% of the negotiated Global Fund price in years 1 and 2, reducing to 25% in year 3, 15% in year 4, and 0% (no subsidy) in year 5. The subsidy will be just one part of a wider programme of interventions, which will include working with the government to reduce taxes/tariffs, working with the DPM to improve regulation, introducing RDTs to improve case management, and behaviour change communication to stimulate demand.

The Green Leaf Logo (as previously used in other countries by the Affordable Medicines Facility – malaria Initiative AMF-m and now by the Global fund) will be included in the product packaging by the manufacturers. This will demonstrate to consumers that these are quality controlled and should be sold at a recommended retail price.

Full impementation is expected to begin in June/July 2015 (with commodities becoming available after the signature of a contract between PSI and maufacturers on 15 May 2015). In preparation for this, the following achievements have been made since signature of the contract in November 2014:
- The contract between PSI/ASF and QAACT suppliers has been drafted, based on the Global Fund AMF-m model
- An agreement between PSI/ASF and local QAACT importers has been drafted
- Approval has been requested from the Secretary-General of the MSP for private sector pharmacies to administer RDT to clients with fever seeking malaria treatment, and the response is awaited
- The DPM has been assisted to complete data collection for its private sector pharmacy mapping exercise (pharmacies identified by the DPM as meeting minimum standards will serve as Special Malaria Care Outlets for the programme)
- Approval has been obtained from the Global Fund to use the Green Leaf logo and Global Fund pricing
- Approval has been obtained from the Global Fund to procure QAACTs and RDTs for private sector distribution in Kinshasa under the 2015-2017 New Funding Model grant. This means that Global Fund will provide 6.6 million QAACTs and 1.7 million RDTs to be distributed in Kinshasa in synergy with this programme.
- Five WHO-approved manufacturers of Artesunate-Amodiaquine (ASAQ) and Artemether-Lumefantrine (AL) have been identified to participate in the programme
- Five local importers (AMT-PHARMA, WAGENIA, CONCORDE, SAGA-AFRICA, and PHARMEX) have been identified to participate in the programme
- MSP training guides for case management, stock management and quality assurance in the private sector have been developed
- 464,364 RDTs (sufficient for years 1 and 2) have been ordered
- Advocacy sessions with owners of pharmacies and drug shops have been carried out
- Strengthened partnership has been developed with CHAI to support the development of a national strategy for malaria case management in the private sector, which is now in place
- The risk matrix has been reviewed and updated.

As soon as the contract is signed between PSI and manufacturers, the commodities will be transported by air to allow implementation to begin in June/July 2015.

Output Title	Improve availability and use of information for malaria control in DRC for increased capacity of malaria control interventions
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones March 2016	Progress
Number of sentinel sites rehabilitated/created and provided with equipment (cumulative targets)	3	Not relevant for the period covered by this AR
Number of sentinel sites providing timely and complete reports (cumulative targets)	3	Not relevant for the period covered by this AR
Number of surveys (insecticide and drug resistance, pre and post campaign) implemented (cumulative targets)	8	Not relevant for the period covered by this AR

The lack of strategic information limits the basis upon which the National Malaria Control Programme (PNLP) can develop effective policies and strategies for Malaria control. The objective of this component of the programme is to enhance the capacity of PNLP to generate and use information for decision–making by developing a strong, high-quality malaria sentinel surveillance system in DRC. The programme will also strengthen the capacity of national academic institutions and the PNLP in carrying out operational research and in developing evidence-based strategy. In addition, the programme will work to improve the financial management capacity of the PNLP team.

With ongoing decentralisation in the health sector, the number of sentinel sites has increased from 11 to 26, corresponding to the number of new Provincial Health Divisions (Divisions Provinciale de la Santé, DPS). This programme will be able to support only ten, but 16 others will receive support from PMI and the Global Fund.

Since signature of the contract in November 2014, the following key activities have been undertaken:
- Organisation of two sentinel site workshops to exchange ideas and information, and to develop the draft technical guidelines for malaria sentinel surveillance and the list of sentinel site indicators
- Assessment of 11 existing sentinel sites in 11 provinces, and development of background information and selection criteria for 15 new sites (thereby eventually corresponding to one sentinel site per DPS once decentralization has occurred)
- Selection of the 15 new sentinel sites
- Meetings with the MSP Directorate in charge of health information and key stakeholders to discuss plans for District Health Information System 2 (DHIS2)[6] and opportunities for collaboration to strengthen PNLP data management capacity
  [6] DHIS2 is a flexible IT system for collecting and centralising health information.
- Identification of ten priority sentinel sites to be rehabilitated by the programme
- Development of a 2015 national workplan on sentinel surveillance of malaria in DRC
- Mapping of actors in DRC involved in operational research relevant to the programme
- Development of a National malaria operational research workplan for 2016-2020.

The programme is now ready to start the work on sentinel surveillance and will be able to provide key information for decision making in the coming years.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Commodities and related costs (especially in-country transportation of bednets from point of entry to point of distribution) have been key cost drivers during this financial year. The financial reports show that 86% of the annual expenditure was on the mass distribution of bednets, completed in December 2014. PSI’s expenditure is lower than DFID’s disbursement due to the delay in signing the contract between PSI and the ACT manufacturers (as there was a need to get the approval from Global Fund to use their negociated price and Green Leaf logo in this programme).

Budget category	Budget total (Contract Budget)	Total FY 14-15 expenditure by PSI	Total FY 14-15 disbursed by DFID	% of total disbursement
Health supplies and related cost (LLINs and RDTs)	£ 10,389,579.00	£4,043,986	£4,839,742	55.56%
Furniture/equipment	£ 512,826.00	£228,662	£228,662	2.62%
Promotion and communication	£ 3,241,106.00	£229,039	£229,039	2.63%
Subcontracts	£ 4,342,429.00	£272,150	£272,150	3.12%
Travel	£ 2,032,010.00	£448,292	£448,292	5.14%
Training	£ 1,691,822.00	£660,292	£660,292	7.58%
Research, monitoring and evaluation	£ 2,438,647.00	£59,131	£59,131	0.67%
Office	£ 3,208,926.00	£394,393	£394,393	4.52%
Consultants and services	£ 1,352,545.00	£301,187	£301,187	3.45%
Staff	£ 4,459,865.00	£648,263	£648,263	7.44%
Administration and procurement fees	£ 2,383,929.00	£629,182	£629,182	7.23%
Total	£ 36,053,684.00	£7,914,577	£8,710,756	100%

In total, 19% of annual disbursement is spent on indirect costs and 81% on programme delivery.

VfM performance compared to the original VfM proposition in the business case
At the time of the business case, the unit cost of bednets in Kasai Occidental was estimated at £4.57 including all programme costs. The actual cost will be assessed in May 2015, taking into consideration that the campaign was eventually implemented in only 35 health zones out off 44, with a saving of £1 million.

The unit cost for ACTs was not estimated in the business case.
The unit cost of these drugs will be calculated for the two first years as soon as the contracts with the manufacturers are signed (expected in May 2015), taking into account the subsidies of 65% for the two first years and additional costs such as transport and taxes.

Assessment of whether the programme continues to represent value for money

With approximately £1 million of savings made in the mass campaign and 900,000 bednets remaining, it is likely that the actual unit cost for bednets will be lower than was estimated in the business case. For this reason, PSI and DFID are planning to meet in May 2015 to discuss the unit cost of the interventions implemented by the programme. As bednets are recognised by the national malaria programme (PNLP) as an important and cost effective intervention to prevent malaria in DRC, the programme now intends to maintain the level of coverage achieved through the mass distribution by implementing continuous distribution of bednets in Kasai Occidental, with an emphasis on interpersonnal communication to promote bednet utilisation.

With the support of the Global Fund, Kinshasa benefited from a mass distribution of bednets in 2014, followed by ongoing routine distribution. Making subsidised QAACTs available in the private the sector (where the majority of the population seeks care for malaria treatment) will have the advantage of further decreasing malaria morbidity and mortality. Bednets and ACTs in combination are likely to offer better value for money than each intervention alone. In term of this programme’s impact, it is expected that malaria case management will improve in the private sector, regulation of the private sector will be strengthened, there will be better understanding and application of national policy by private sector actors, and supply of, access to, and demand for affordable QAACTs will be enhanced. As an additional result, the risk emergence of ACT resistance will be reduced.

By establishing a strong, high-quality malaria sentinel surveillance system in DRC and strengthening the capacity of PNLP to produce and utilise data and evidence, the programme will provide reliable information for decision-making related to the need for and effectiveness of various malaria interventions/strategies.

Quality of financial management

DFID has disbursed only 80% of the forecasted amount for last financial year, and disbursement of 20% of the amount planned for ordering drugs has been delayed by ongoing discussions with drug manufacturers.

Weaknesses in PSI’s forecasting have led to variations against quarterly forecasts. However, PSI has met reporting requirements with detailed financial reports and timely audited statements. DFID and PSI are exploring ways to improve PSI’s accuracy on forecasting for future payments.

Date of last narrative financial report	11/03/2015
Date of last audited annual statement	June 2014

E: RISK

Overall risk rating:

Medium

Overview of programme risk

Component 1
During implementation of the bednet mass distribution campaign, a case of theft of bednets was identified in Dekese health zone, and a fraud involving ASF staff and local radio stations in Kasai occidental also took place. Investigations are still underway and we are waiting for the final conclusions. The fraud unit was informed as soon as DFID DRC was aware of this situation.

Management of the remaining 934,548 bednets will be included in the risk matrix to ensure that they are not exposed to the theft or damage. The bulk of these (659,137) are stocked in the PSI warehouse, which is guarded by a security team. The remaining 275,411 are stocked at health zones (where they are being monitored by health zone management teams and PSI), and will be prioritised for distribution.

The fiduciary agency was hired to manage resources at peripheral level to reduce risk of mismanagement and fraud encountered during previous campaigns.

Components 2 and 3
These elements – particularly component 2 – are higher risk as they are innovative and have yet to be implemented. Details of the risks are contained in the risk matrix. The risk matrix for component 2 has been reviewed as part of the annual review process. A summary of key risks identified is as follows:

Institutional and regulatory context
Weak regulation of private sector pharmacies: Even in pharmacies that are accredited, it is likely that sub-standard anti-malarial drugs will be sold alongside QAACTs provided by the programme, and application of clinical protocols may not be sufficient (for example, QAACTs may be administered in the absence of a parasitological diagnosis of malaria). The programme will mitigate these risks by training and supervising service providers, and the communication campaign will emphasise the advantages of systematic malaria testing in improving care.

Current GoDRC policy does not support the use of RDTs in pharmacies. The programme is working with the MSP to obtain approval for the use of RDTs in accredited pharmacies. Whilst such approval is anticipated, it is not yet certain when this will occur. In the absence of such approval, the programme will focus on private sector clinics (as opposed to pharmacies), in which the use of RDTs is currently permitted.

Counterfeit QAACTs: It is possible that non-quality assured anti-malarial drugs bearing a counterfeit Green Leaf logo may appear. This will be addressed by the use of lot numbers and laboratory sampling to check for the presence of counterfeit drug.

Market risks
There is a risk that some or all of the subsidy to the cost of QAACTs will be captured by service providers, rather than being passed on to benefit service users. This risk will be minimised by maintaining a very short supply chain (the programme will provide QAACTs directly to service providers, rather than through intermediaries). Furthermore, consumers will be informed of the appropriate sale price of QAACTs through mass and inter-personal communication, and will be provided with a hotline to report instances of sale at elevated prices.

There is additionally a risk that QAACTs may leak into alternative outlets in Kinshasa, or to other parts of DRC. On one level this might be seen as a form of success, in that this would demonstrate demand, and displace the consumption of poorer quality anti-malarials. However, it may also dilute the impact of the programme, and create opportunities for the sale of QAACTs at elevated prices. The programme will therefore monitor the stock of participating outlets (including through the use of using mobile technologies), and implement measures (such as stock-checks) to identify sales of QAACTs through other outlets.

Reduction of subsidy: It is planned that the level of subsidy to the price of QAACTs will progressively diminish over the course of the programme. This means that the price of QAACTs is expected to rise accordingly, which creates a risk that the market presence of these drugs will not be maintained. There are several mechansisms envisaged to mitigate this:
- Demand for QAACTs will be generated and maintained through mass and inter-personal communication, as well as by introducing QAACTs to the market at at a high level of subsidy at the start of the programme. The programme will gather information on willingness to pay for QAACTs, both through focus groups and routinely through programme data on consumption / sales.
- Advocacy work is being carried out by the programme to encourage GoDRC to withdraw taxes on he importation of QAACTs, and this will continue. If this succeeds, the price of QAACTs may be maintained at a lower level despite reductions in subsidy.

Competition with local manufacturers of ACTs: ACTs are produced in DRC, but none of the local manufacturers is quality-assured by WHO. Reports have been received that local manufacturers have expressed concern that the subsidies for QAACTs will harm their business. Whilst the programme does not intend to cause harm to local business, it is intended to enhance the presence of QAACTs in the market, for public health purposes. In order to reconcile these interests, the programme will seek to work with local manufacturers with a view to helping them to seek pre-qualification of their product from WHO.

Limited capacity of the PNLP: The changes in the regulary framework and tax regime referred to above will need to be initiated and led by the PNLP. Lack of capacity in the PNLP may limit its effectiveness in implementing this role. The programme will seek to strengthen this capacity through component 3 in particular, which is intended to strengthen the availability and strategic use of evidence by the PNLP.

Outstanding actions from risk assessment
The risks identified and the management of them are being discussed with PSI. Risks will continue to be reviewed and the risk matrix updated throughout implementation. Given the innovative nature of the programme, it is likely that new or different risks will emerge during implementation. The programme will need to remain alert and responsive to these.

During the review of the logframe, consideration should be given to whether indicators can be devised and included, that will support monitoring and management of key risks.

Outstanding actions from due diligence

A comprehensive Due Diligence Assessment (DDA) was conducted with PSI DRC team in person and their Deputy Regional Director over the phone. The DDA was signed off by DFID DRC Head of Office on 27 October 2014 (Quest 4706468). The recommendations of the DDA and the status of each of these are as follows:

DDA recommendation	Status
DFID to be advised of timing of Internal Audit visits and consider requesting a meeting with the team to better understand risk environment	Outstanding: Awaiting the visit of PSI Internal Audit by the end of June 2015.
PSI to include the risk matrix with updates and future actions as part of their quarterly reporting	Implemented: An updated risk matrix is part of the quarterly reports.
DFID to maintain their current practice of seeking confirmation of forecasts at regular intervals, and also seeking to improve communication and understanding with PSI finance team	Ongoing: In our monthly meeting , this point is included in the agenda .
Ensure that PSI’s recognised purchase and distribution processes are detailed in their financial and narrative reports, and that funds to contractors are clearly set out in reporting to DFID.	Implemented: PSI sends quarterly detailed financial reports. Additional information is also produced on DFID’s demand.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The bednet distribution component has been delivered in the timeframe planned in the Business Case. The mass distribution was completed in November-December 2014. The post-campaign study will be undertaken 6 months after the mass campaign, as planned.

As predicted in the previous annual review, two components (ACTs and PNLP capacity strengthening) are running one year behind the planned timeframe. The design phase took 12 months to assess all the risks linked particulary to the distribution of QAACTs in the private sector. Accordingly, the contract with PSI has been extended by a year.

Performance of partnership(s)

The programme is implemented under the leadership of the National Malaria Control Programme (PNLP) and is contributing to fulfilment of their objectives. PSI, PNLP, and STPHI have regular joint programme review meetings to discuss progress and next steps. The quarterly joint review is an opportunity for PNLP, DFID, and PSI/ASF to update each other on progress and challenges and plan for future activities. The review provides interested parties with a common understanding of the programme and fosters ownership by the PNLP and MSP.

PSI/ASF successfully collaborated with the fiduciary agency (Fonds de Développement des Services de Santé, FDSS), which was contracted to manage funds and procure services at the peripheral level as well as provide financial reporting and reconciliation documents. This approach was successful in that it improved the time it took to complete financial reporting and reconciliation and decreased the risk of funds mismanagement at the peripheral level.

PSI is working with local commercial transporters to move bednets from PSI central and provincial warehouses to health zones. PSI is also working with local radio and TV stations to broadcast key messages about routine distribution, malaria prevention and correct use of bednets. PSI will also work with local NGOs, drug manufacturers, first-line buyers and local pharmacies in Kinshasa.

Asset monitoring and control

PSI keeps good electronic and physical records of programme assets. PSI’s project manager reviews the assets inventory on a quarterly basis as per PSI guidance and DFID’s contract provision on assets. The updated assets list is sent to DFID as an annex to the narrative report every six months.

PSI is currently assessing the assets that were used in Kasai Occidental for the mass campaign, with a view to returning some to Kinshasa, and retaining others there for use in the ongoing/routine distribution.

G: CONDITIONALITY

Update on partnership principles (if relevant)
H: MONITORING & EVALUATION

Evidence and evaluation

Component 1

The post-campaign survey planned for June 2015 will measure the achievements of the programme, following a pre-campaign survey carried out in October 2014 in order to provide a baseline for key indicators.

The programme is also drawing upon findings from the ongoing studies implemented by DFID DRC’s other malaria programme (“Support to Universal access to Long Lasting in Equateur “) to improve the use of bednets and inform discussions with PNLP on updating the current strategy for malaria prevention. The topics of these studies are as follows:
1. Determinants of bedbet use and non-use among the population in DRC: The main objective of this study is to explore and identify the causes of non-use of LLINs and the expectations of beneficiaries, so that these can be addressed in order to optimise bednet use.
2. The durability of LLINs in the DRC context: The objective of this study is to determine how long bednets remain in acceptable condition whilst in use, in order to inform adjustments to the frequency of and arrangements for bednet distributions in the DRC.
3. The cost effectiveness of the distribution of routine distribution following mass distribution of bednets: The objective of this study is to determine the unit cost of routine distribution, and the level of coverage and use of bednets in the health zones with routine distribution of bednets following a mass campaign, compared to those without.
4. Review of the first cycle of mass distributions of bednets in DRC: The objective of this study will be to review the first round of mass distribution campaigns that has taken place in the DRC since the first strategic plan was issued in 2009, in order to draw lessons for the next cycle of mass distributions.

The programme is also drawing upon national surveys including the DHS 2013-14 and ACTWatch outlet surveys. The former has revealed an increase in bednet ownership and use in DRC: 70% of households have at least one bednet, and 56% of children under five and 60% of pregnant women slept under a bednet the night before the survey.

Components 2 and 3

The programme has designed a strong monitoring and evaluation framework to be put in place in the coming months as soons as QAACT distribution begins. This includes both research and routine monitoring.

In terms of research, six topics are planned during the life time of the programme:
1. Household survey - fever treatement
2. Household survey - behaviour change communication
3. Medicine retail survey
4. Exit interviews
5. Mystery client service
6. Qualitative research

The majority of these will be implemented annually, and will provide evidence needed to adjust the programme approach during the course of iplementation.

Routine monitoring will use mobile technology to collect data on a regular basis (weekly or quarterly). This will be done through implementation of DHIS2, in synergy with other donors.

Monitoring progress throughout the review period

The main activities of the programme were implemented under the leadership the PNLP with the involvement of PSI and DFID. The consequence is that 21 PNLP national staff, 70 provincial PNLP teams, 27 PSI/ ASF monitoring officers and two DFID advisers participated in campaign surpervision activities.

PNLP, DFID , PSI , MSP and other key malaria stakeholders (PMI, WHO) were also involved in the principal activities carried out during the design phase and in decision-making on the approach to be implemented by the programme.

PSI and the DFID team meet on a regular basis (monthly) to discuss and update the progress of the programme.

This annual review process consisted of the following components:
- Meeting with malaria control stakeholders: workshop 30-31 March 2015
- PSI presentation on annual progress and gender review: 14 April 2015 (DFID private sector and social development advisers attended)
- Halfday workshop on risk review
- Review of quarterly financial and narrative reports