# Programme memorandum
# UK Post Conflict Development Programme for Northern Uganda
# October 2009 – October 2014
CONTENTS

SUMMARY AND RECOMMENDATIONS

PROJECT DETAILS

  1. Project Description

  1. Programme Appraisal

  1. Lessons and Evaluation

IMPLEMENTATION

  1. Management Arrangements

  1. Timing

  1. Funding

  1. Contracting and procurement

  1. Accounting and Audit

  1. Monitoring, Reporting and Measuring Progress

RISKS

  1. Programme risk rating

CONDITIONALITY

Annexes

ADF	Allied Democratic Force
AMREF	African Medical and Research Foundation
ARP	Amnesty and Reintegration of Ex-Combatants
BFP	Budget Framework Papers
bop	Balance of Payments
BTVET	Business, Technical, Vocational Education and Training
CNDP	Congrès National pour la Défense du Peuple - Congolese Tutsis
DANIDA	Danish International Development Agency
DALY	Disability Adjusted Life Years
DDP	District Development Plan
DFID	Department for International Development (UK)
DLB	District Land Board
dprt	District Peace and Reconciliation Team
DRC	Democratic Republic of Congo
DRR	Disaster Risk Reduction
ELU	Environmental Liaison Unit
EOC	Equal Opportunities Commission
EPRC	Economic Policy research Centre
ERA	Economic Recovery Analysis
EU	European Union
EVI	Extremely Vulnerable Individual
FARDC	Forces Armeés République Démocratique du Congo
FDLR	Forces Démocratiques de Libération du Rwanda
FDS	Fiscal Decentralisation Strategy
FINMAP	Financial Management and Accountability Programme
FPA	Final Peace Agreement
FTE	Full Time Equivalent
FY	Financial Year
GDP	Gross Domestic Product
GNU	Government of National Unity
GoU	Government of Uganda
Gov	Government
HUMC	Health Unit Management Committee
ICC	International Criminal Court
ICOR	Incremental Capital Output Ratios
ICRC	International Committee for the Red Cross
IDA	International Development Association
IDP	Internally Displaced People
IGG	Inspector-General of Government
IOM	International Organisation of Migration
IRP	Infrastructure Rehabilitation and Urban Improvement Programme
JLOS	Justice and Law and Order Sector
KIIP	Karamoja Integrated Disarmament and Development Programme
LC	Local Council
LEAD	Livelihoods and Enterprises in Agricultural Development Programme
LEDU	Local Economic Development Unit
LEMU	Land and Equity Movement in Uganda
LG	Local Government
LGDP	Local Government Development Programme
LGfc	Local Government Finance Committee
LGMSDP	Local Government Management Service Delivery Project
LGPAC	Local Government Public Accounts Committees
Lgsip	Local Government Sector Investment Plan
llg	Lower Local Government
LRA	Lord’s Resistance Army
M&E	Monitoring and Evaluation
MAAIF	Ministry of Agriculture, Animal industry and Fisheries
mdgs	Millennium Development Goals
MGLSD	Ministry of Gender, Labour And Social Development
Mof	Ministry of Finance
mofped	Uganda’s Ministry of Finance, Planning and Economic Development
molg	Ministry of Local Government
MONUC	United Nations Organisation Mission to the Democratic Republic of Congo
mops	Ministry of Public Service
MTTI	Ministry of Trade and Tourism
NDP	National Development Plan
NEMP	National Environment Management Policy
NER	Net Enrolment Rate
NGO	Non-governmental Organisation
NIMES	National Integrated Monitoring and Evaluation Strategy
NPA	National Planning Authority
NPV	Net Present Value
NRM	National Resistance Movement
NU	Northern Uganda
NUDC	Northern Uganda Data Centre
NUPER	Northern Uganda Public Expenditure Review
NURD	Northern Uganda Reconstruction and Development Group
NUREP	Northern Uganda Rehabilitation Programme
NUS	Northern Uganda Survey
NUSAF	Northern Uganda Social Action Fund
nuti	Northern Uganda Transition Initiative
NUYDC	Northern Uganda Youth Development Centre
OCHA	Office for the Coordination of Humanitarian Affairs
OPM	Office of the Prime Minister
OVC	Orphans and Vulnerable Children
PCDP	Post Conflict Development Programme
PEAP	Poverty Eradication Action Plan
PETS	Public Expenditure Tracking System
PFM	Public Finance Management
PHC	Primary Health Care
PMC	PRDP Monitoring Committee
PNFP	Private Not-for-Profit
prap	Peace Building and Recovery Assistance Programme
PRdp	Peace, Recovery and Development Plan
PWDs	People with Disabilities
sdu	Strengthening Decentralisation in Uganda
SGBV	Sexual and Gender Based Violence
SME	Small and Medium Enterprises
Spring	Stability Peace and Reconciliation in Northern Uganda
SSR	Security Sector Reform
SWAY	Survey of War Affected Youth
UBOS	Ugandan Bureau of Statistics
UIA	Ugandan Investment Authority
UK PCDP	UK Post Conflict Development Programme for Northern Uganda
UN	United Nations
UNFPA	United Nations Population Fund
UNHCR	United Nations High Commissioner for Refugees
Unicef	United Nations Children Fund
UNPRAP	United Nations Peace Building and Recovery Assistance Programme
UPDF	Ugandan People’s Defence Force
Usaid	United States Agency for International Development
WHO	World Health Organisation
YDP	Youth Development Programme
YOP	Youth Opportunities Programme

Summary and Recommendations
  1. In the last 20 years, most parts of Uganda have enjoyed uninterrupted economic growth, poverty reduction, political stability and relative peace. However, the conflict between the Government of Uganda (GoU) and the Lord’s Resistance Army (LRA) prevented the people in northern Uganda from enjoying these benefits.
  2. The conflict has now subsided. GoU recognises that Uganda’s progress towards the Millennium Development Goals (MDGs) will only improve if the north is stable, peaceful and productive. GoU has issued a Peace Recovery and Development Plan (PRDP) to consolidate peace, tackle the root causes of the conflict and improve welfare.
  3. The UK Post Conflict Development Programme for Northern Uganda (UK PCDP) will support the GoU’s PRDP. The goal of UK PCDP is to build a peaceful, vibrant northern Uganda with increased opportunities for the people of the north and reduced poverty for all of Uganda. The purpose is to create economic, social and political opportunities that improve the lives of people affected by conflict.
  4. The UK PCDP is firmly aligned behind the PRDP and the Poverty Eradication Action Plan (PEAP) which will soon be replaced by a National Development Plan (NDP). It is harmonised with other development partners’ plans and is complementary to planned and ongoing DFID Uganda programmes.
## Outputs and Outcomes
  1. The UK PCDP will support the GoU to deliver immediate benefits of peace and promote the long-term transformation of northern Uganda by:
- enhancing local government (LG) capacity for equitable service delivery including the construction/rehabilitation of 4,600, clinics, schools, health workers’ and teachers’ housing – resulting in health and education benefits for over one million users;
- promoting private sector-led growth, investment and employment by creating almost 10,000 jobs with an economic impact of £3.5 million per annum;
- providing basic literacy to more than 65,000 youth, skills training for more than 95,000 youth, and micro-enterprise/ job placement support to 25,000 youths;
- delivering targeted social protection to 27,000 extremely vulnerable individuals returning to their homes from the internally displaced peoples camps;
- establishing GoU structures to support national reconciliation.
  1. The programme will deliver on key White Paper 4 commitments, specifically:
- Focusing on peace-building and state-building approach.
- Promoting economic growth - the main thrust of our programme.
- Maintaining 50% bilateral spend on public services through our support to local governments.
- Creating more jobs through our youth programme.
- Supporting the most vulnerable in a downturn through our social protection component.

## Funding
  1. The total cost of the PRDP over three years is £367m. The GoU recognises that three years are not sufficient to address the causes and consequences of decades of conflict. The PRDP will set the foundations for longer term recovery and development.
  2. DFID’s will contribute £100m over five years and will target both immediate needs and longer term recovery.
  3. . Other donor contributions to the PRDP now stand at £126.99m mainly from the World Bank, the US, the European Commission (EC), Norway, and Sweden. This is a conservative estimate as full details of all donor funding to the PRDP are yet to be provided.
  4. Over 60% of the programme will be delivered through existing GoU service delivery structures. Other components will be delivered through UN agencies and NGOs, the private sector and communities.
  5. The overall programme risk rating is medium. The main programme risks are: (i) a decline in GoU’s commitment to recovery in northern Uganda; (ii) resources do not reach the intended beneficiaries or is politicised; (iii) a return to conflict. Mitigation measures have been developed for all identified risks.
  6. Conditionality is restricted to GoU compliance with Development Partnership Arrangement (DPA) commitments to poverty reduction, protection of human rights and improved financial management and accountability.

PROJECT DETAILS
  1. Project Description
## What problems will the programme address?
    1. The conflict led to loss of lives and displacement of over 2 million people. The direct cost of the war to the economy was estimated at US $1.3 billion, or 3% of annual GDP, in 2002. For significant periods the affected population were unable to farm their land and access basic social service and had to rely on humanitarian assistance. Between 2006 and 2009 the total cost of the humanitarian response in Uganda was £497m, of which DFID contributed £60m.
    2. As a result of the conflict poverty levels in the north are 30% above the national average. Kitgum, a district in northern Uganda, has the lowest life expectancy in Uganda at 29 years[1]. The consequences of the conflict have intensified perceptions that the north was marginalised by the GoU.
      [1] National life expectancy is 50 years
    3. The conflict has now subsided and the GoU has issued a Peace Recovery and Development Plan (PRDP) .The goal of the PRDP is to consolidate peace and lay the foundations for recovery and development in northern Uganda. The PRDP is a three year £367m plan built along four Strategic Objectives (SOs): i) consolidation of state authority; ii) rebuilding and empowering communities; iii) revitalization of the economy and iv) peace building and reconciliation. The GoU has committed to fund 30% of the PRDP and has requested development partners to meet remaining costs.
    4. While preferring sector budget funding for the PRDP, the GoU recognises that other off budget mechanisms are required due to Government capacity constraints, especially at the district level. Some PRDP interventions will be delivered through the UN, NGOs and the private sector.
    5. The UK PDCP has been developed to support the GoU to deliver the PRDP. The goal of the UK PCDP is to build a peaceful, vibrant northern Uganda, with increased opportunities for the people of the north and reduced poverty for all of Uganda. The purpose is to create economic, social and political opportunities that improve the lives of people affected by conflict.
    6. This programme will: improve access to key basic social services – especially health and education; reverse the economic stagnation ;tackle youth unemployment; tackle extreme poverty and vulnerability and support national reconciliation and conflict resolution processes.
What will the money be spent on?
    1. Our support will be delivered mainly through mechanisms recommended in the PRDP:
Output I: Enhanced Local Government (LG) capacity for equitable service delivery. This will support PRDP SO 1 (Consolidation of State Authority).
What
DFID funds will be used to: construct/rehabilitate 4,600 clinics schools, to build housing for health workers and teachers; provide an incentive package to attract and retain public sector staff; and procure technical assistance to support key district officials to improve results-based planning, accountability and transparency.
How
- In the short term support will be provided through the Northern Uganda Social Action Fund (NUSAF II) which is a £60m, 5-year World Bank funded programme. It is targeted at improving livelihoods, rehabilitating and building social infrastructure, and building the capacity of GoU and LG institutions. NUSAF II will be delivered through LGs and in alignment with targets in District Development Plans. Community labour will be used in the rehabilitation and up to 60% of the budget will pay wages benefiting 2 million people, 50% of them women.
- In July 2011, support under this output will then switch to on-budget earmarked financing for northern Uganda (see point 2.2.5 below).
- TA will be provided to: (i) central government to develop the incentives package; and (ii) to Lira and Gulu LGs to improve planning, accountability and transparency; to communities to engage in monitoring PRDP implementation.
Output II: Fostering private sector led growth and employment opportunities. This will support PRDP SO3 (Revitalization of the Economy).
What
An Economic Recovery Analysis (ERA) will identify barriers to economic growth and provide policy makers and donors a sound evidence base for resource allocation. A small grant scheme will promote market-led agricultural development, promote trade and create 8,900 new jobs in northern Uganda. .
How
- TA will be provided to the Uganda Investment Authority (UIA) to carry out the ERA.
- The grant scheme will be administered through an organisation with experience in this area.
Output III: Better future prospects for young people. This will support PRDP SO2 (Rebuild and empower communities returning from displacement).
What
We will provide vocational, literacy and life skills to 150,000 young people. Skills development will be linked to future market needs: 2,500 young people will be helped into jobs. We will support a consortium of NGOs to carry out inter-community youth sport and cultural exchange programmes to foster national reconciliation.
How
- We will build the capacity of the GoU/ Commonwealth Northern Uganda Youth Development Centre (NUYDC). NUYDC is a GoU project partially sponsored by the British Council/ Commonwealth Secretariat and administered through the office of the Prime Minister (OPM).
- Our funds will be spent on: (i) constructing and equipping the centre; (ii) developing the curriculum; (iii) promotion of the youth centre; (iv) training and job placement.
Output IV: Social support to the extremely vulnerable individuals (EVIs). This will support PRDP SO2 (rebuilding and empowering communities).
What
Over 300,000 extremely vulnerable IDPs are still displaced. 27,000 of them are either, elderly, sick, or disabled. They want to return home but lack the resources to do so.
How
- We will fund the UN and NGOs build houses for the most vulnerable.
- We will provide cash transfers for EVIs and generate lessons for scaling up national social protection programmes with GoU.
Output V: National reconciliation. This will support PRDP SO4 (Peace Building and Reconciliation).
What
The GoU is developing a National Reconciliation Bill to take this process forward. Setting up an Equal Opportunities Commission (EOC) to address ethnic imbalances in key public sector positions was flagged as one of the key steps towards reconciliation.
How
- DFID resources will support the GoU to set up the EOC and other institutional arrangements required for national reconciliation.
- We will fund key civil society actors to engage in the national reconciliation process.
Output VI: Monitoring for conflict sensitivity and peace building.
What
We will seek to ensure that this programme does no harm, and that overall recovery process addresses the drivers of conflict and delivers tangible peace building results.
How
A consortium of local and international NGOs will be supported to: carry out conflict sensitivity monitoring; develop an early warning system for the recovery process; and support OPM to include conflict sensitivity in its results frameworks.
## Who will benefit?
    1. UK PCDP benefits will extend to the 40 districts of northern Uganda. Targeted components will focus on Gulu and Lira districts, which have the capacity to pilot innovative approaches which can be rolled out to other districts. The impact of conflict was highest around these two districts[2]. Although support is targeted at the north, the programme will have national impact given that improvements in LG agencies can be replicated nationwide
      [2] /	FPA defines the conflict affected areas as: Acholi sub-region, Lango sub-region, Teso sub-region and West Nile.
  2. . Programme Appraisal
How did we become involved?
Background:
    1. GoU and HMG agree that Uganda’s overall performance on the MDG targets will only improve if the north is stable, peaceful and productive. Addressing the underlying causes of conflict and fragility, and reducing regional disparities are therefore common goals.
### How does this fit with GoU strategies, DFID policies and with other donors
    1. The programme is firmly aligned behind GoU policy and processes. It seeks to support the delivery of the PRDP which feeds into broader GoU priorities articulated in the PEAP.
    2. The programme design is consistent with DFID thinking on best practice on private sector development in fragile states and the new State Building and Peace Building thinking. It is also informed by DFID’s work on best practice in recovery and transition programmes. The programme is a product of a joint HMG effort.
### Why are we doing it this way
    1. GoU offers three main funding mechanisms for donors to support the PRDP:
i	On-budget earmarked financing for northern Uganda – funding through central government’s financial account to increase sector grants for northern Uganda. This is close to the model of the Protection of Basic Service programme in Ethiopia. The funding will be clearly tracked though to Northern districts and will be based on a dialogue with government focussed specifically on achieving results in northern Uganda and the Peace, Recovery and Development Plan, in addition to the existing general budget support dialogue on broader national policy and budget priorities.

ii	On-budget project support - e.g. the World Bank‘s Northern Uganda Social Action Fund II, and other time bound projects such as infrastructure rehabilitation. These modes of support are also channelled via the central government to specific district and community level bank accounts. However they are subject to additional World Bank safeguards to manage fiduciary risk.

iii	Off-budget project support - e.g. support to UN pooled fund for recovery, NGO consortia, grants to SMEs, social protection options including cash/vouchers for work, and conditional/unconditional cash transfers.

    1. The programme we are proposing is a combination of all 3, beginning with ii and iii and transitioning to i in 2011. We intend to provide on-budget earmarked financing for northern Uganda to local government from July 2011 onwards to strengthen state functions. TA from the first 18 months of the programme will have helped refine planning, financial management and accountability. We will also support civil society and community capacity to demand good governance. The Norwegians and Swedes will be providing on-budget earmarked financing for northern Uganda and we will use lessons from their experience to inform our decision to switch to on-budget earmarked financing in 2011.
    2. Our work on Joint Budget Support will also support GoU ability to deliver in northern Uganda as part of a nationwide effort to improve results.
    3. The next elections will take place in Uganda in early 2011. Should on-budget earmarked financing for northern Uganda then not prove feasible given fiduciary and governance concerns, we will keep Ministers informed and ask Ministers for a decision on a combination of ii and iii above. During the period between now and the elections, we will develop contingency plans to explore alternative channels for sustaining DFID support. We will advise ministers accordingly.
    4. The chosen approach balances the short-terms needs of the north (transformative/peace building) while generating long-term improvements in the GoU structures (developmental/state building). 60% of the programme will be delivered through GoU systems and will support locally defined priorities.
    5. The programme recognises the potential of economic growth to provide a sustainable basis for lasting peace. Long term interventions build government capacity to effectively perform its roles, which will lead to better poverty reduction outcomes. The youth component will boost growth and reduce risks associated with a huge unemployed young population. UKPCDP is also targeted at supporting people’s ability to demand accountability while also tackling immediate issues of vulnerability and disillusionment.
    6. Innovative approaches to improve LG responsiveness, results-based planning, accountability and transparency will have national-level impact. This programme will complement innovative approaches being developed under our Financial Management and Accountability (FINMAP) programme aimed at strengthening systems for expenditure tracking, results monitoring and auditing. This programme will link in to and be complemented by our broader national-level accountability SWAP.
Sequencing of activities
    1. The on-budget earmarked financing for northern Uganda will commence 18 months from the programme start date (2011/12) if conditions outlined in 2.2.5 are met. Programme components listed below will commence as soon as we receive approval:
- Technical assistance to Gulu and Lira local governments on planning, accountability and transparency.
- Housing and cash transfers for the most vulnerable.
- Support to infrastructure through the GoU/ World Bank Northern Uganda Social Action Fund II (NUSAF II).
- The youth basic literacy and skills training programme.
- Support to community user groups to manage social facilities and demand accountability.
Stakeholder involvement
    1. DFID and the British High Commission (BHC) have consulted with GoU representatives at the central, national and district level, civil society, the private sector, programme beneficiaries and key development partners.
    2. All key stakeholders have shown strong support for the GoU by aligning their resources behind the PRDP. Most resources for the recovery effort will be channelled through implementation modalities similar to those being suggested by us. Programme components like the youth development programme are ground breaking. Key areas like supporting the revival of basic livelihoods have been sufficiently covered by other partners like the EC.
Economic Appraisal [3]/
[3] /	See Economic Appraisal Annex
    1. The £100 million will deliver total economic benefits worth 2.5 times the cost of the programme.  Direct benefits of £211m at present value (NPV) have been identified in the economic analysis. However, even higher indirect benefits can be expected if we consider that the total benefits of restoring and maintaining peace - around £3.3bn. If this peace dividend is attributed according to the contribution to increased public spending in northern Uganda, DFID would be responsible for a benefit of 19% of the peace benefits, or £650m at present value.
Table 1: Cost benefit analysis
	Costs / (£ m)	Discounted Costs	Discounted Benefits	Benefit : Cost Ratio	Indicator
Total Benefit			647.7		GDP
Education
Health	27.20	22.9	59.7	2.6	Primary school years
Governance	27.20	22.9	64.0	2.8	DALYs
Grant Scheme	9.80	8.2	31.0	3.8	Diversion reduced
Youth Development	15.00	10.9	28.7	2.6	ERR
Social Protection	12.15	10.2	22.7	2.2	ERR
Other	4.00	3.4	8.1	2.4	Marginal income utility
Total	4.65	4.5
Indirect Benefits	100.00	83.0	214.2	2.5

### Contribution to Growth and Poverty Reduction
    1. The grant scheme will create 9,800 new jobs, 5,400 of which will be attributable to DFID funding, and the rest to co-funding from partners. The Youth Programme (YDP) will generate 500 jobs per annum, amounting to 2,500 jobs over the period with an annual benefit of £1.1m. DFID will directly support the creation of 7,900 jobs in total.
    2. Estimated growth in per capita income during the recovery period is 3% per annum. Part of this growth will be attributable to this programme. TA to local government to facilitate better results based management, planning and to improve accountability and transparency should reduce leakages from corruption and improve the efficiency of government resource use.
## Social Appraisal[4]/
[4] /	See Social Appraisal Annex
    1. The programme will deliver a reduction in poverty depth – i.e. the depth below the poverty line at which people live - of 27% over 5 years, and improved social services to over one million people. It will deliver specific benefits to those most in need, including enabling 200,000 children to complete primary education; providing improved basic education, literacy and vocational skills to over 150,000 youth; and supporting 27,000 disabled and extremely vulnerable people to return to their homes. Programme outcomes will be disaggregated by sex where possible.
    2. The programme will promote increased involvement of the beneficiaries in the delivery of social services and will support the demand for greater accountability. The YDP will integrate youth participation in the detailed design. The programme will ensure that demand for governance improvements are tempered to prevent unrealistic expectations, dissatisfaction and conflict.
## Institutional Appraisal[5]/
[5] /	See Institutional Appraisal Annex
    1. We will recommend a switch to on-budget earmarked financing for northern Uganda in July 2011 after satisfactory institutional assessments of GoU capacities as outlined under 2.2.5. Programme components to be delivered outside the mainstream GoU channels have taken the capacity of partner institutions into account:
- SME grant scheme will be managed in partnership with the Private Sector Foundation based on an institutional assessment of eligible agencies.
- The ERA will be done through the Uganda Investment Authority (UIA) which is well suited to perform this task.
- Northern Uganda Youth Development Centre (NUYDC) and the community polytechnics appear well suited to perform these roles, but further capability assessment will be carried out.
- DFID will conduct a full appraisal of the GoU institution chosen to take forward the reconciliation process. In the absence of political will, civil society-led reconciliation mechanisms will be considered.
## Political Appraisal
    1. During the conflict, northern Uganda suffered at the hands of the central government as well as the LRA. This reinforced decades of national political and administrative dominance by western and central ethnic groups. Thus, in the north, public perceptions of central government are poor and characterised by mistrust. However, there is no substantive interest at present, even among opposition political leaders in northern Uganda, for greater political autonomy.
    2. Although peace talks began in 2006, the Final Peace Agreement has not yet been signed and the roots of the 23-year conflict are deep. The continued commitment of government and President Museveni will be critical to ensuring continued peace and development of the north. The PRDP is an important opportunity for the central government to allay northern suspicions that it lacks the will to address the impact and roots of the conflict.
    3. A key incentive for the ruling party to improve conditions in the north is to win the northern vote in the 2011 elections. If the NRM does win, the risk that central government interest will ebb is considered only medium. The NRM has a further incentive to embed stability in the north as a buffer against any resurgence of the LRA. The LRA and their supporters do not currently seem intent on a new campaign of violence in Northern Uganda and are dispersed in the DRC and Southern Sudan. Pressures could intensify, however, as elections in Sudan may take place within a month of the Ugandan elections in 2011 or if the peace process in Sudan breaks down.
    4. Land is a sensitive political issue throughout Uganda, including in the north. There is a risk that vulnerable returnees may not be able to protect their land or that weaknesses in land administration and justice deter investment. Weak systems for resolution of land conflicts mean that tensions are not satisfactorily resolved. The government is drafting a new land policy which aims to alleviate these problems in the medium to long-term. The PCDP has been designed to ensure that land-related tensions are not exacerbated by the programme. Specifically, the grants scheme will ensure that any small business applying for a grant has proof of tenure and that the scheme does not support land grabbing.
    5. The PCPD’s close alignment to the GoU’s growth and poverty reduction strategies has resulted in support by government and partners at the central, district and community level. Preparation of the programme was based on a lengthy multi-stakeholder consultation process led by the government. It addresses both shorter term requirements of peace building and longer-term needs of state building.
    6. Programme design allows for regular monitoring and changes in funding arrangements in response to socio-political conditions. DFID will conduct a joint political assessment with the BHC annually. Conflict-sensitivity monitoring of the PRDP will also allow us to review programme components as they are implemented and inform our annual reviews so that we can adjust the programme accordingly.
## Environmental Appraisal [6]/
[6] /	See Environmental Appraisal Annex
    1. As all activities must comply with GoU policies and regulations for environmental management, for which the structures are sound, environmental risks are estimated as low. The programme contains specific interventions to generate a positive environmental impact, for example training young people on environmental management. Beneficiaries of the grant scheme must demonstrate the environmental viability of their initiatives.
## Fiduciary Risk Assessment [7]/
[7] /	See Fiduciary Appraisal Annex
    1. The programme’s fiduciary risks include:
- Politicisation of allocations – if funding is not allocated based on objective criteria.
- Untimely transfer or reduction in the GoU’s contribution.
- Failure of LGs to represent the interests of the beneficiaries, resulting in inefficient and ineffective uses of programme resources.
- The fiduciary risks associated with NUYDP include the risk of corruption by programme participants and participating employers, and non-completion or partial completion of programme requirements.
    1. Each programme output includes provision for fiduciary risk management including: additional safeguards for on-budget project support; a deferral of on-budget earmarked financing for northern Uganda or a switch to other delivery mechanisms; strengthening local government’s ability to plan and account; strengthening of civil society as a check on government action; and guidelines for fiduciary management of YDP, the Grant Scheme and cash transfers.
  2. Lessons and evaluation
    1. Programme design was informed by best practice and lessons-learned from DFID post conflict recovery programmes; our experience of working in Uganda; and consultation with development partners. These lessons include:
    2. The Need for Flexibility. The nature of conflict-affected environments means that programmes must respond swiftly and alter priorities accordingly. The M&E element of the programme and the conflict sensitivity monitoring will enable DFID to adapt to ensure maximum impact.
    3. Delivering benefits to the north while also contributing to national development. This will ensure the people of northern Uganda are the direct beneficiaries of the programme, but that relationship building between the north and GoU is strengthened.
    4. Uganda has been selected as a focus country for OECD-DAC work on reform of the international architecture for recovery, in which DFID is playing a leading role. There is potential for the recovery programme to generate best practice on country led recovery and transition programming.
    5. Full details on how the performance measurement framework provides the best basis for judging success are provided in section 3.6 below.
Implementation
  1. Management arrangements
    1. This programme is a joint funding arrangement managed in association with the GoU and in partnership with other donors. The Office of the Prime Minster (OPM) responsible for overall management and coordination of the PRDP, still needs to clarify all the PRDP implementation arrangements. Although GoU has expressed a preference for direct budget support, its absorptive capacity is too weak for DFID to channel all of the £100m through government structures.
    2. Within DFID, programme management will be led by the Recovery and Development Adviser (RDA) supported by the MDG Results Adviser, the Recovery Programme task team, an Economic Adviser and programme administration team. Advisory inputs across this team will amount to 7.4 Full Time Equivalent DFID staff.
    3. DFID Uganda staffing levels are not sufficient to manage and administer such an ambitious programme. For this reason, a satellite office to take day to day monitoring of the programme and the management of relationships with partners and districts will be set up in Gulu. We will seek to work closely with OPM (possibly co-located), with the ultimate intention of merging the satellite office into OPM.
    4. DFID is responsible for overall management of the programme and for reporting on outputs and impact, but specific components of programme delivery will be outsourced to the GoU, NGOs and TA providers.
  2. Timing
    1. Implementation will begin by the end of 2009 but impact and outcomes will be spread over the 5 year (2009- 2014) life span of the programme.
  1. Funding
  2. Of our resources £65.35m will be allocated for social services and governance; £15m for economic growth; £12.15m for youth opportunities; £2m for social welfare; £3.5m for reconciliation; and £2m for conflict sensitivity monitoring and M&E. DFID’s contribution can be accommodated within the existing aid framework and allocations from the Capital Departmental Expenditure Limit (CDEL). A detailed outline of funding by mechanism and spend profile over the course of the programme is included at Annex A
    1. Operation and Maintenance: There are significant operation and maintenance costs associated with UKPCDP. The expansion of health and education services requires ongoing financing by GoU to meet recurrent costs arising from the investment in infrastructure. Costs are consistent with GoU commitments and will form part of our continued dialogue on output one.
    2. Ownership of DFID funded Assets: There will be minimal DFID-funded assets involved. Any equipment purchased for the programme will be retained by the GoU or programme implementing agencies to ensure programme sustainability.
  2. Contracting procurement and distribution
    1. DFID Head Office will manage international tendering for TA activities above the international tendering threshold. DFID Uganda will manage restricted tendering below the tendering threshold
    2. World Bank will monitor the procurement under NUSAF II. UNHCR have sound procurement procedures which provide sufficient safeguards for non-DFID procurement. The GoU will procure all goods and activities funded through on-budget earmarked financing for northern Uganda.
    3. The 2007 performance review reported procurement as an area of high performance for all districts. Challenges remain in terms of manipulation of tender outcomes, collusion in the pricing of tenders, political involvement in procurement processes and delivery of poor quality work. TA should lead to improvements in these areas.
  3. Accounting and Audit
    1. On-budget earmarked financing for northern Uganda will be subject to GoU procurement, accounting and audit procedures. Tranches will be disbursed after satisfactory fiduciary assessment has been undertaken, in line with standard local government and procedures developed in Uganda. It is expected that TA financing will occur through contracts.
    2. Financial controls will be in accordance with the procedures set out in the Fiduciary Appraisal[8]/.
      [8] /	See Appendix 9.
    3. Other non governmental recipients of funds will maintain financial expenditure records for the duration of the programme. All records will be available to DFID.
    4. Independent, annual auditing will be contracted for the grants scheme and YDP.
  4. Monitoring, Reporting and Measuring progress
    1. Project progress will be monitored quarterly by DFID against agreed work plans, and through joint GoU/ DFID annual reviews and DFID membership of key coordination fora. This will be supplemented by a mid-term review and evaluation as an opportunity for corrections to the programme.
    2. Our results management process will be aligned with the national planning context including the PEAP, PRDP and NDP to support a GoU-led recovery programme. OPM is currently developing a results matrix to monitor PRDP implementation. The matrix will be available within 6 months of the PCDP starting.
    3. The mandate for coordinating data collection for the PRDP rests with OPM. The TA team will allocate 40% of their time with the OPM to develop a joined-up approach to results-based management. They will prepare and submit quarterly and annual reports based on data collection and analysis to the MDG Results Adviser and other partners.
# 4. Risks
    1. The overall programme risk rating is medium as identified risks can be mitigated. The opportunity to consolidate peace in the north is enormous, especially if Museveni sees a need to woo the northern vote in a tight election. The major risk is that the GoU political commitment to deliver the PRDP will wane, especially after the 2011 elections.
  2. Each output has been assigned a level of risk:
- Output 1 (medium) - governance activities are implemented through GoU structures and TA to local governments in the first 18 months of the programme. Resources will only be disbursed when systems for accountability are sufficiently robust.
- Output 2 (medium/high) - economic component depends on the credibility of an untested and unknown private sector in the north. Risks are mitigated by development of our understanding, piloting activities and effective management of the risks through TA, and evidence of increased trade in the north, including cross-border trade with Sudan.
- Output 3 (medium) - risks are linked to delivering labour market opportunities for youths which may not exist and that the programme is not sustainable. These risks will be mitigated by ensuring that opportunities developed are tailored to the demands of the market and that the government owns the programme.
- Output 4 (medium) – there is a risk that social funds are captured by the less poor. DFID will continue to influence NUSAF II, NGOs and LGs to monitor and improve targeting.
- Output 5 (medium-high) – lack of political will could make output five untenable or if implemented, the LRA or GoU may fail to adhere to the terms of the FPA. Alternative delivery mechanisms mitigate the first risk whilst ongoing conflict monitoring will mitigate the latter risk.
  1. Corruption remains a risk but will be mitigated through the provision of TA to support demand and supply side governance. This will be complemented by our broader accountability programme. The GoU is making real progress on the management of public sector standards and systems and this programme will assist this process.
  2. Conflict sensitivity: A consortium of NGOs will monitor local dynamics and programme implementation to ensure conflict-related risks are flagged and mitigated.
## Monitoring Risks
  1. Risk monitoring will be undertaken through the annual fiduciary risk assessment, governance reviews and the regular monitoring and evaluation reports. The quarterly reports will include analysis of the status of the risk management activities and propose remedial measures adjustments as appropriate. The same analysis and commentary will be required of the annual perception surveys and midterm and end term evaluations.
5. CONDITIONALITY
  1. In accordance with the Paris Declaration and Accra Agenda DFID is committed to working with mutually agreed conditions based on national development strategies. Given Uganda’s commitment to international partnership principles, alignment behind government-led strategies and systems is the limit of DFID conditionality. Conditionality is restricted to GoU compliance with DPA commitments on poverty reduction, protection of human rights, and improved financial management and accountability. Monitoring will include:
- GoU implementation of the PRDP, PEAP and NDP.
- Budget allocations for basic education and health.
- Conduct of elections, and treatment of excluded groups, candidates and supporters during and after both local and national elections.
- Improved budget disbursement and reductions in waste (improved frontline service delivery).
- Documented improvements in PFM (Annual audit reports, LG annual assessment reports and FRAs).
  1. In the event of a violation, DFID will adhere to guidance set out in the “How to Note: Implementing the UK’s Conditionality Policy” which provides guidance on appropriate and proportionate responses to breaches of partnership commitments.