Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Supporting Stability and Promoting Democracy in the Occupied Palestinian Territories (SSPD) referred to by its Arabic name of ‘Tajaawob’.
Programme Value: £2.72m		Review Date: May 2015
Programme Code: 202886	Start Date:09/2013	End Date: 06/2016

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A+
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

The programme has scored an ‘A+’ in the current Annual Review, indicating steady performance since the last Annual Review in June 2014 (A). All outputs either met or are exceeding expectations of delivery as established by the targets.

The table below summarises the 2014 Annual Review output scores
#	Description	Score	Weighting
1	Strengthened advocacy skills in Palestinian Civil Society (CS) through the delivery of Tajaawob advocacy cycle with individuals and communities.	A+	50%
2	Authorities able to understand and engage with communities and Civil Society Organisations through new and improved mechanisms	A	20%
3	Strengthen capacity of Palestinian media to reflect community-led issues of marginalized voices, including women and youth.	B	30%
Overall Score		A	100%

Key lessons learned since last review

The key programmatic lesson has been that much more needs to be done to capture evidence in the final year. This is a pilot programme which was intended to generate evidence about what works in the field of social accountability in the unique OPTs context. As a result, the British Council has been requested to allocate sufficient staff resources and implementing partners’ time to capture lessons and provide evidence.

Progress against previous recommendations
The 2014 Annual Review had the following recommendations:

Output 1: To improve overall participation in the Communications Advocacy and Leadership Programme (CALP) training sessions, and to undertake a gender analysis to identify the specific barriers to women’s engagement. As a result of the analysis, a marked improvement has been seen over the last year, e.g. in changing training sessions which encouraged more women to participate.

Output 2: New engagement mechanisms should be introduced together with a long-term strategy to ensure sustainability of those mechanisms. In the period covered by this Annual Review, the programme introduced new engagement mechanisms with authorities: however, they are not yet sufficiently embedded within ministries to be considered sustainable.
Output 3: a renewed focus on the delivery of the TV production output. This was adequately addressed by the production of two TV debate shows.

Summary of recommendations for the period June 2015 to June 2016:

No.	Type/level	Description
1	General	DFID to agree with British Council a revised logframe by June 2015 including a new output focused on evidence (detailed recommendations are in the individual output sections.
2	General	DFID should maintain close oversight of programme activities in Gaza by revising and reviewing progress reports.
3	General	DFID should ensure they maintain good relationships with consortium partners as well as with the British Council to enhance communication, through the establishment of a formal steering group mechanism that meets once every quarter.
5	General	Implementation of the recommendations will be tracked in the delivery plan

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1202886/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1202886/documents/

Outline of the programme
The UK provided £2m from 2012/13 to 2014/15 to help Palestinian civil society become more inclusive and effective at holding the Palestinian Authority (PA) to account. The programme uses a mix of training and grant funding to help Palestinians understand and influence those that are spending money and making decisions on their behalf. The programme was extended as of April 2015 by 15 months with an additional contribution of £720,000. The total value of the programme from 2012/13 to 2015/16 is £2.72m.

Context
UK policy is that the Occupied Palestinian Territories (West Bank, Gaza, East Jerusalem) or ‘OPTs’ constitute the land that should – as a result of negotiations between the parties – form the basis for a future Palestinian state. The UK’s ultimate goal is the creation of a sovereign, independent, democratic, contiguous and viable Palestinian State living in peace and security side by side with Israel. As part of this, the DFID programme is supporting the development of a peaceful, functioning Palestinian state and society.

Legitimacy
The PA faces a crisis of legitimacy in the eyes of many Palestinians resulting from the expiration of its political mandate. Democratic processes were suspended following the takeover of Gaza by Hamas in 2007. No parliamentary or Presidential elections have taken place since 2006 and the Palestinian Legislative Council has not met since 2007. There is both public disillusionment and a broad disconnect between the leadership and ordinary Palestinians. The result is a dangerous ‘democratic deficit’ across the OPTs which this programme seeks to address.

The lack of a viable political horizon given the failure of the current round of the Middle East Peace Process (MEPP) negotiations to end Israel’s occupation and facilitate the establishment of a sovereign Palestinian state has only compounded popular disenchantment.

Hamas was the de facto authority in Gaza between 2007 and June 2014. The UK has a no-contact policy with Hamas. The Interim Technocratic Government, established in June 2014, now has responsibility across the West Bank and Gaza. The UK supports the Interim Government, which includes ministers based in Gaza. This has opened up options to step up work in Gaza within the parameters of the UK’s counter terrorism obligations and continuing no-contact policy with Hamas.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome statement is: Palestinians are better able to hold their authorities to account

Outcome indicators 1 and 2 have both achieved the 2015 milestones and so we consider them to be on track.

Outcome	2015 / Milestone	Actual	Progress towards achievement of Outcome Indicators / Status Rating
Outcome indicator 1: No. of case studies which demonstrate improved engagement of Palestinian Civil Society and which meet DFID quality assurance	6	7	Exceeded: The 7 case studies that demonstrated improved engagement of civil society focused on the following topics, and that where quality assured by the DFID Governance Adviser: / 1.The Campaigns Advocacy Leadership Programme / 2.Impact of media capacity building and support to media platforms to amplify the voice of marginalised communities / 3.Lessons from the Lijan mahallija as a model of community participation / 4.Lessons from advocacy campaigns by the lijan mahallija / 5.Tajaawob on wheels initiative / 6.The Social Accountability Expo / 7.The consortium model
Outcome indicator 2: % of people who have completed the Communications and Advocacy Leadership Programme (CALP) and report having used the training in a practical way	50% utilizing it (50% of those are women)	60% (73%)	Exceeded: The second CALP, conducted this year, underwent changes to make it easier for women to participate. This has been successful with 60% (15 out of 25) actively using the training, of which 11 (73%) are women.

Overall output score and description

The overall score is A (outputs exceeded expectation). See detail in the table below.

#	Description	Score
1	Strengthened advocacy skills in Palestinian CS through the delivery of Tajaawob advocacy cycle with individuals and communities.	A+
2	Authorities able to understand and engage with communities and CSOs through new and improved mechanisms	A
3	Strengthen capacity of Palestinian media to reflect community-led issues of marginalized voices, including women and youth.	A+
Overall Score		A+

Key lessons

A programme of this nature takes time to deliver results and generate evidence. In particular, it takes time to build trust with communities, as well as to embed new processes in ministries i.e. a significant amount of time is needed to lay out the foundations for a successful outcome. As a result, the initial two years timeframe for this programme have been assessed as too short. Consequently, the programme was extended for 15 months in order to exploit the potential for greater impact. Future programmes of this nature should have longer timeframes in order to address this.

Establishing formal accountability mechanisms with the PA has been a slow process despite willingness on the part of the PA to engage with the programme. It takes time for a bureacraacy in a challenging environment to apply these changes, and to allocate the time and personnel needed to follow up and champion them. A key success factor has been that these changes are seen as locally led and responding to the needs of the communities, so strengthening their credibility with the authorities.

Setting up ‘bottom up’ accountability mechanisms, independently of the PA , have been simpler, more immedate and effective routes to effecting change. These include e.g. ‘Officials on Wheels’ (officials and politicians are brought together with citizens via a mobile radio forum) and ICT tools (such as Khadamati, piloted to provide an online map of water services in Bethlehem with immediate feedback to service providers).

A consortium-led approach to programming – with six partners - takes time to bed down. However, one advantage is that the consortium members are locally and internationally respected, adding credibility and legitimacy to the community committees and the programme.

The programme within the complex governance structures in a context of occupation has had its challenges. The business case model for engaging with communities on advocacy has been a useful tool in circumventing these challegnes. For example, working with different communities under different political realities (e.g. Area C, B and A) has been an effective way of disentangling the different challenges facing these communities. This programme has helped provide a space for constructive discussions for communities to negotiate and prioritise specific needs, under very difficult political circumstances.

Key actions

DFID to finalize a revised logframe by June 2016 including a new outcome indicator focused on policy changes as a result of the project’s activities, and a new output focused on evidence.

Has the logframe been updated since the last review? Yes. The logframe output indicator 1.2 was revised in December 2014 to reflect the difficulty faced by implementing partners in delivering the planned training in Gaza as a result of the conflict in the summer of 2014. The target for number of participants finishing the CALP course was reduced from 45 to 30.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened advocacy skills in Palestinian CS through the delivery of Tajaawob advocacy cycle[1] with individuals and communities.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N
[1] Advocacy cycles are advocacy skills training packages that are designed to follow trainees and accompany them through different stages during the programme to ensure continuity of skills learned.

Indicator(s)	Milestones (2015)	Progress
1.1 No.of advocacy cycles which have reached: Stage 1 (definition & capacity building) Stage 2 (advocacy design & delivery) Stage 3 (embedded)	Stage 1 (0)[2] / Stage 2 (2) / Stage 3 (3)	Stage 2 (5) / Stage 3 (8)
1.2 No. of people who have completed the six month Communications and Advocacy Leadership Program (CALP) (of which women)	30 (10)	38 (18)
1.3 % of participants who have completed CALP and report at least satisfied with the training (women)	80% (80% women)	86.17% (85.62%)
1.4 % of participants of advocacy training who report at least satisfied with the training (women)	0	N/A [3]
[2] Stage 1 (definition and capacity building) was completed in Year 1.
[3] Community-based advocacy training ended after Year 1.

Key Points
Indicator 1.1: The 2015 milestone was significantly exceeded. At stage 2 (advocacy design & delivery) the communities of Mograqa, Qalqilya, Jerusalem and Azzoun designed and delivered a total of 5 advocacy campaigns. At stage 3 (embedded), or where the campaign has reached its policy change goal with authorities, 8 community advocacy campaigns have been completed in Qalqilya, Frush Beit Dajan, Um Salamona, Mograga and Hableh, and several authorities have made commitments to improve targeted services.

Indicator 1.2: The 2015 milestone was significantly exceeded. In the last Annual Review there were 13 (5 women) who completed the CALP. This year, an additional 25 (13 women) completed the training bringing the total to 38 (18). The target for indicator 1.2 was reduced in November 2014 from 45 to 30 as the training in Gaza was unfortunately postponed due to the conflict in the summer of 2014.

Indicator 1.3: The 2015 milestone was significantly exceeded. There has been a marked improvement since the first Annual Review where the result was 77.5% (56% women). Responding to a recommendation made in the last Annual Review, significant changes were made to the process for recruitment and delivery of training, particularly in terms of accommodating women’s needs, thereby improving the completion and satisfaction rates of trainees. For example, training times were made flexible to accommodate women’s domestic or childcare responsibilities.

Indicator 1.4: Advocacy training for community committees was completed in Year 1 of the programme. No target was therefore included for the period covered by this Annual Review.

Summary of responses to issues raised in previous annual reviews (where relevant): The 2014 Annual Review had two recommendations. The first was to improve overall participation in the CALP training sessions, and the second to undertake a gender analysis to indentify the specific barriers to women’s engagement. Based on this, the CALP training sessions were reorganized to ensure better participation by women. This has been achieved as evidenced by the results in output indicators 1.2 and 1.3.

Recommendations:

R 1.1: Consolidate the output indicators on training to better reflect the work to be delivered in the extension period.
R 1.2: DFID should ensure the milestones for this output are sufficiently ambitious since they were significantly exceeded.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Authorities able to understand and engage with communities and CSOs through new and improved mechanisms[4]
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N
[4] Engagement mechanisms are platforms where Civil Society and communities can engage with government bodies or authorities responsible for the devlivery of services to the people (e.g. the Citizen Report Card under 2.2.)

Indicator(s)	Milestones	Progress
2.1 No. of engagement mechanisms presented to authorities.	5 (cumulative)	5
2.2 No. of engagement mechanisms which are receiving feedback (being utilized) from public.	3 (cumulative)	3

Key Points
Indicator 2.1: The 2015 milestone was met. At the time of the last Annual Review, 3 Ministries had been presented with engagement mechanisms: Ministry of Education (MoE), Ministry of Social Affairs (MoSA) and the Ministry of Planning (MoPAD). Since then, 2 new Authorities have been approached, the Ministry of Local Governent (MoLG), and the Municipalities in the Qalqilya Governorate. MoLG were presented with a community development mechanism through which communities can apply for limited grant funding (between $5000 and $12000 per community, to be raised by MOLG) which responds to their specific social development needs. So far, this is focused on the communities the project works with. The Citizen’s Report Card (CRC) mechanism was used with the Qalqilya municipalities to identify service failures on the waste collection process.
Indicator 2.2: The 2015 milestone was met. In the previous year, the programme established the Beneficiary Forums (BFs) with MoSA and held some hearing sessions in Hableh municipality. In the year covered by this Annual Review, the following engagement mechanisms have been receiving feedback:
1. Three Beneficiary Forumss in Nablus, Qalqilya and Bethlehem have started to provide feedback to MOSA. This feedback included concerns around the selection of families for the assistance, the quality of food provided through food stamps, and the level of assistance provided. MOSA has already acted on complaints from the BFs in Bethlehem and Nablus about the quality of food and satisfactorily resolved the issue;
2. The Citizen Report Card (CRC) process with the MoE focused on Parent Councils has also moved forward. The MoE approved the CRC and questionnaire as a permanent part of the official Parent Council guidebook. These tools can now be accessed and used by all West Bank communities to provide evidence to strengthen the role of Parent Councils in advocating for issues beyond extra-curricular planning and towards issues of real concern to parents and their children;
3. The CRC with Qalqilya Municipalities focused on the waste collection process. An action plan was developed following hearing sessions between the municipalities, Joint Service Council and the community committee on the CRC findings. Some areas have been addressed and the committee will continue to monitor progress against the action plan.
Summary of responses to issues raised in previous annual reviews (where relevant): The 2014 Annual Review recommended focusing on approaching different authorities with engagement mechanisms and developing a long-term strategy to ensure sustainability of those mechanisms. Implementing partners have focused on developing new bottom-up engagement mechanisms rather than new top-down mechanisms with additional PA institutions, as it takes time to develop and establish these mechanisms within ministries. Ensuring sustainability of these mechanisms will be addressed during the extended period.

Recommendations:
R 2.1: DFID and the British Council to agree what quality feedback by citizens should look like by June 2015.
R 2.2: DFID and British Council to consider including ‘bottom-up accountability mechanisms’, e.g. ICT tools, as engagement mechanisms by June 2015.
R 2.3: British Council should prioritise sustainability of these mechanisms in the extension period, including providing a sustainability strategy by September 2015.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthen capacity of Palestinian media to reflect community-led issues of marginalized voices, including women and youth.
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 No. of training sessions on outreach to marginalised communities delivered to media houses	4	4
3.2 No. of discussion and debate shows between CS and authorities broadcast on radio and TV.	20 radio and 1 TV	38 radio shows / 2 TV shows

Key Points

Indicator 3.1: The 2015 milestone was met. 2 training workshops in Gaza focused on improving report making, presentation, content enhancement, programme preparation and storytelling skills, recording on location, filming on location using smartphones, and audio and video report preparation. Another training session focused on editorial values, where to find stories, writing for radio and ethics of journalism. Finally, a session that included coaching (20 times per quarter) by BBC Media Action for the individual radio programmes took place to strengthen production of these shows.

Indicator 3.2: The 2015 milestone was significantly exceeded. A total of 38 radio shows and 2 TV shows have been broadcast since the last Annual Review. The main reason there has been a siginficant overacheivement is the new partnership that was formed with 24 FM radio station. All in all, there were 23 productions by BBC Media Action of the “Tajaawob” radio show: the 30 minute-show typically included radio ‘packages’ highlighting issues from 6 of the Tajaawob marginalised communities. Two TV shows ‘Hur el Kalam’ (BBC MA) were produced and each hosted one government official. There were also 15 productions of ‘On the Spot’ (24 FM) that involved each of the programme’s five West Bank communities together with relevant decision makers.

Summary of responses to issues raised in previous annual reviews (where relevant)
The last Annual Review recommended prioritising the TV production output; this recommendation was adequately addressed as evidenced by the production of two TV debate shows. However, radio remains the main medium for this work.

Recommendations
3.1: Retain Indicator 3.1 in order to report against it in the Project Completion Report despite no training taking place in the extension period.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The funds for this programme are channelled through an implementing partner, the British Council which manages the consortium model. The two most significant cost drivers are staff costs and the CALP training. This programme is about effecting change and as such requires building trusting relationships through mobilisation efforts, accompaniment and explicit capacity building and training. This requires an intensive use of human resources which was anticipated in the Business Case.

VfM performance compared to the original VfM proposition in the business case
DFID Palestinian Programme’s Value for Money strategy contains commitments to appraise and monitor value for money throughout a project’s life through the use of unit costs for inputs (economy), outputs (efficiency) and outcomes (cost effectiveness). For this project, these unit costs translate into the following:

Economy: Cost of training activities compared to other training activities in OPTs. Administration costs below 15%. The target was to keep admin costs on all three outputs to a maximum of 15%. During the first year outputs 2 and 3 crossed the 15% threshold but lower costs for output1 kept the average administration cost for the three outputs at 15.17%. The British Council has delivered on the commitment to decrease the percentage spend on administration costs. In fact, in the second year, outputs 1 and 3 saw an administration spend of less than 10%, while output 2 remained below the 15% threshold at 14%. The average spent on administration for the second year was 8%.

Efficiency: Cost of training per person compared to other training activities in OPTs: The first year of implementation, the cost per training per person ranged between 350 USD to 820 USD (including consultant fees, admin costs, and venues). The second year saw costs per person reduced to between 120-140USD. As the British Council has used trained locals to conduct courses for the second year, there has been a saving of approximately £59,000 on training costs the second year.

Cost effectiveness: Effectiveness is reported at the end of the project, as outcomes take time to materialise.

Economic return: Although it is not possible at this stage to estimate the Net Present Value of the project, this will be done in the evaluation using data gathered from the monitoring system. In particular, the economic impact of the PA policy changes resulting from the project will be estimated and compared with their cost. The extent to which further policy changes can be expected from the project after its end will also need to be estimated.

Assessment of whether the programme continues to represent value for money
The project continues to perform and is delivering the expected outputs with an overall score of A+. We therefore consider the programme continues to represent value for money.

Quality of financial management
British Council
British Council provides quarterly financial reporting and forecasting, this also includes a section on Value for Money. Invoices are provided on quarterly basis. There have been significant challenges with programme forecasting, due to the large number of implementing partners within the consortium led by the British Council and the ability to extract accurate forecasts from them. The DFID team has supported the British Council to establish a clear improvement plan to provide more robust forecasting. Although there has been slight improvement in the last quarter, there is room for improvement in the upcoming period.

Date of last narrative financial report	10/12/2014
Date of last audited annual statement	10/12/2014

E: RISK (½ page)

Overall risk rating: Medium

The overall risk of the programme is still judged as Medium.
Annex 1 provides an update to the Risk Matrix.

Overview of programme risk
In addition to updating the risks in the original Business Case, we have also identified the following emerging risks:

Risks	Mitigation Actions
A change of government- The end of the Interim Technocratic Government could lead to a Hamas-led government or one including Hamas members in either or both the West Bank and Gaza.	We would need to consider the composition of any new government, and review legal advice on Hamas’ stated positions and options for working with non-Hamas members of any such government
DFID and SSPD West Bank-based programme managers have limited access to Gaza.	We will closely monitor the situation and put in place remote monitoring procedures, including video conferencing.
Tensions between Hamas and Fatah lead to a breakdown of the Technocratic government, and Hamas assumes control over public services in Gaza.	The programme will monitor the political situation in Gaza closely, and if appropriate, suspend/end activities.
Ministries/Communities in the West Bank are unable to absorb or utilize proposed engagement mechanisms	The programme will work closely with Ministries and communities to make sure that these mechanisms are institutionalized and utilized as best as possible.
The PA is unable to respond to unrealistic expectations of citizens.	The programme will manage expectations and calibrate activities to support the PA rather than challenge it.

Outstanding actions from risk assessment (N/A)
Risks continue to be treated in line with the Risk Matrix. There are no outstanding actions from risk assessments.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe (Yes)
During the first year of implementation the project had a significant underspend of 25% (see Annual Review 2014). This was attributable to a number of factors, for example time was needed to delineate and streamline interventions by consortium partners, However a remedial process was put in place with the implementing partner and the consortium and, as a result, the level of underspend has decreased to an estimated 3.6%. The programme has now been extended for 15 months with an allocation of £720,000.

Performance of partnership (s)
The British Council, as the consortium lead, reports on activities on a quarterly basis. This includes an extensive narrative report as well as financial reporting. The programme draws on lessons from around the world but delivers through local partners. SSPD was designed as a pilot programme using a consortium approach led by the British Council with five partners, both Palestinian and international. These are: Oxfam GB, BBC Media Action, Aman, Miftah and Palvision. In the cost extension, the number of partners will be reduced. Oxfam GB is not currently able to deliver their specialised advocacy training model in Gaza. The British Council will continue to work with Aman and Palvision, while DFID will continue to fund BBC Media Action centrally.

Asset monitoring and control
Not Applicable

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

This programme does not provide direct funding to the partner government. Nevertheless, a country level assessment of the Partnership Principles was carried out in April 2015 and found that the PA continues to deliver on the Partnership Principles under increasing fragile and volatile conditions. On the commitment relevant to this programme, namely on ‘strengthening domestic accountability’, there has been some progress, including the development of a National Development Plan that sets out commitments to Palestinians in areas of service delivery.

The last Parliamentary elections took place in 2006 with Hamas winning with a significant majority. Since then there been no Palestinian Parliament. In June 2014 the PA and Hamas signed a reconciliation agreement, with the prospect of elections within six months. The agreement included actions on reconvening the Palestinian Legislative Council (the parliament) and a commitment to work towards elections. In December 2014, a ‘roadmap’ towards the reintegration of Gaza and West Bank public administrations was drafted with public agreement from the President and Hamas (at least parts of it) in March 2015. However, there has been little tangible movement on progress towards reintegration/reconciliation agreements.

As part of this programme DFID will continue to monitor the fourth commitment, in tandem with the country level assessment of the Partnership Principles, which is carried out every quarter.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
An evaluation is planned during the cost extension period. DFID has worked with programme partners on identifying the questions that formed the basis of the TORs, and a consultancy has been identified to carry out the evaluation. As the programme has been extended till June 2016, an evaluation will take place between June and September 2015. This programme is very much viewed as a pilot programme, designed to generate evidence, collect data, and provide analysis. The extended period will focus on gathering this evidence.

Monitoring progress throughout the review period
The programme comes under the OPTs Governance and Security Pillar and is managed by the Governance Adviser and Project Officer as well as the Team Leader who is the SRO. In line with DFID’s SMART Rules, a delivery plan was completed in January 2015.

This Annual Review was conducted by the DFID Palestinian Programme Governance and Security team (Project Officer and Governance Adviser), in consultation with implementing partners, and quality assured by DFID OPTs Deputy Head of Office and the Regional Results Adviser.

The review was drafted based upon the following information sources:
- The Business Case
- The 2014 Annual Review
- Quarterly Reports
- Feedback from beneficiaries during field visits and Tajaawob Expo 2015.
- 6 monthly field visits to communities
- Monthly meetings with implementing partners

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process

Annex 1

Supporting Stability and Promoting Democracy (SSPD) Risk Matrix - Updated February 2015

↗	Risk increasing	→	Risk staying the same	↘	Risk decreasing

Type	Risk	Mitigation	Probability		Impact		Trajectory
Prevailing	A deterioration in relations between the Government of Israel and the Palestinian Authority triggers violence and instability, especially in Gaza.	The programme will continue to work with partners in geographic areas where it is possible to do so.	Medium		High		↗
New	A change of government- The end of the Interim Technocratic Government could lead to a Hamas-led government or one including Hamas members in either or both the West Bank and Gaza.	We would need to consider the composition of any new government, and review legal advice on Hamas’ stated positions and options for working with non-Hamas members of any such government	High		High		↗
New	DFID and SSPD West Bank-based programme managers have limited access to Gaza.	We will closely monitor the situation and put in place remote monitoring procedures, including video conferencing.	High		Medium		↗
	Output to outcome risks
Prevailing/updated	Independent media and journalists subjected to censorship and political harassment.	Commitments will be monitored through this programme and where we have concerns they will be raised through our scheduled talks on progress against our Memorandum of Understanding.	Low to medium		Medium		→
Prevailing/Updated	Young people continue not to see the value in engaging in policy dialogue.	The programme will trial innovative uses of social media and technology to engage with young people in ways that matter to them. We will be realistic about the overall impact we can have and target particularly excluded young people.	Medium		Medium		↘
Prevailing	Tensions between Hamas and Government of Israel increases and leads to increased instability in Gaza.	The programme will monitor the security situation in Gaza and if appropriate, suspend activities.	Medium		High		↗
Prevailing	Diversion of funds to individuals or entities promoting terrorism.	DFID will not provide any funds directly to the community, ministries or individuals. The programme is working with established Palestinian partners who will implement all activities. The substance of interactions will be focused on improving service delivery by the Interim Technocratic Government to Palestinians.
New	Tensions between Hamas and Fatah lead to a breakdown of the Technocratic government, and Hamas assumes control over public services in Gaza.	The programme will monitor the political situation in Gaza closely, and if appropriate, suspend/end activities.	High		High		→
New	Ministries/Communities in the West Bank are unable to absorb or utilize proposed engagement mechanisms	The programme will work closely with Ministries and communities to make sure that these mechanisms are institutionalized and utilized as best as possible.	Medium		High		→
New	The PA is unable to respond to unrealistic expectations of citizens.	The programme will manage expectations and calibrate activities to support the PA rather than challenge it.
Activity to output risks
Prevailing/updated	Inadequate capacity in Palestinian NGOs and civil society organisation to manage and deliver programme activities.	Palestinian NGOs and civil society organisations are in general well-developed and have good capacity.		Low		Low	↘
Prevailing/updated	Risks of Fraud; / Poor quality surveys, already chosen category from the public to answer surveys. / false expenses claims by contracted NGO’s / Marginalized groups are falsely presented and identified.	The service provider has hired well-known trusted NGO’s with proven work experience in the projects fields. / The service provider has formed a steering committee who will be monitoring and anticipating any possible fraud risks, to mitigate accordingly / DFID Project Officer, Finance Officer and Governance adviser follow up work plans, review financial reports, and attend some of the projects’ workshops to evaluate the work type and level.		Low		Medium	→