Annual Review

Title: Humanitarian Protection for Vulnerable Refugees and Host Communities in Jordan
Programme Value £ (full life): £15m		Review Date: May 2019
Programme Code: 300537	Start Date: April 2018	End Date: March 2021

Summary of Programme Performance
Year	1
Programme Score	A
Risk Rating	Minor

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

A. Summary and Overview

Description of programme
The Syrian refugee crisis has placed a significant burden on Jordanian services at a time that the country is facing its own economic and social challenges. Syrian refugees and other vulnerable groups (including people lacking documentation, people with disabilities or mental health conditions, female-headed households, and children) can face significant difficulties in accessing the health, protection and other services they require to ensure their right and wellbeing are protected.

Through this programme, DFID is providing up to £15 million over three years to International Medical Corps (IMC), Norwegian Refugee Council (NRC), and Humanity and Inclusion (HI) to deliver life-changing activities to address basic protection needs of 62,167 of the most vulnerable Jordanians and refugees (including Syrians), in a way that promotes sustainability and resilience, and which also builds the capacity of local actors. Activities include:
- Legal counselling and case management (e.g. to enable people to marriage and birth certificates);
- Health support for people in remote communities including persons with disabilities (PwD) requiring physical rehabilitation, mental health support and psychosocial services;
- Child protection case management;
- Training for health professionals, community leaders and local NGOs; and
- Awareness-raising and advocacy through continuous community outreach and social media campaigns.

This programme was designed alongside the partners mentioned above where DFID is contributing to existing services. Providing protection services with the aim of improving people’s wellbeing is an area of focus deemed important to engage in where the needs in Jordan for these services are great. This programme is a result of an open call for proposal conducted in 2017 out of which these three partners were selected.

While the programme is made of different components, DFID is seeking to strengthen how partners work together holistically on these issues in Jordan.

During the period in review, the context supporting this intervention did not change significantly from that outlined in the business case, although there were some changes in the legislative environment regarding documentation and legal assistance. There was a decrease in the number of refugees forcibly deported back to Syria and access to work permits improved. While there has been some easing of Government of Jordan (GoJ) policy on registration and access to services, the need for support still exists.

During this first year of implementation, partners identified areas of interventions where refugees and vulnerable Jordanians are critically in need of health and protection interventions through needs assessments. Activities were designed to respond to identified specific needs. All affected populations received support regardless of age, gender, sexual orientation, religion and political affiliation addressed in the humanitarian principles of humanity, impartiality, independence, and neutrality. In relation to people with disabilities, beneficiaries were identified through outreach activities in the community, open access to the safe spaces for all community members, and referrals for specific individuals either externally from other agencies or internally from programs.

The programme activities are represented within the Jordan Response Plan[1] and designed to gradually prepare for the handover of services from international organisations to both local organisations and to the Government of Jordan (GoJ) institutions to effect sustainable impact. Partners are encouraged to set out their exit strategy from the outset.
[1] http://www.jrpsc.org/

Enhanced due diligence assessments were conducted for all three partners to assess the strength of systems and policies in place to safeguard and protect vulnerable people and children from sexual harassment and abuse. This was given due importance as the programme involves working with children and vulnerable people across Jordan. All partners have the relevant policies in place, mechanisms for reporting abuse, and mandatory training of staff on these policies.

This annual review, for the first full year of the programme’s life, is based on partners’ annual reports, as well as consultations held in the run up to this review, recent field visits to see operations in Amman and Irbid and an annual review meeting held in May 2019. The programme is set to be completed by 31/03/2021.

Summary supporting narrative for the overall score in this review
The programme has scored an A overall, and implementation is on track with the majority of output indicators achieved or moderately over-achieved. The limited number of moderately under-achieved indicators are on track to be rectified and we are confident they will catch up in the coming years.

Recommendations for the year ahead
A number of lessons learnt have been identified through this Annual Review process. Key points include:

All partners to assess milestones included in various indicators and where needed to revise and increase targets to address overachievement.

- Partners to review their approach to protection mainstreaming in a holistic way to ensure adequate and systematic needs identification, referrals[2], and information-sharing.
  [2] By referrals, we mean the referral of cases to agencies or to the government to receive services that the agency itself cannot provide.
- Partners to review their approaches to measuring and classifying referrals and promote more consistent and effective management and tracking of referrals at interagency level. Cost of transportation should be regularly reviewed to enable beneficiaries to access services.

Conduct a gender and inclusion assessment of the programme of all three elements of the programme that examines what has been done to date, and makes recommendations for strengthening, covering: a) an assessment of the extent to which gender is mainstreamed across project processes including the identification, selection, stakeholder engagement, and implementation of capacity and community awareness projects; b) a time bound gender and inclusion action plan for the programme setting out concrete steps for mainstreaming gender within all activities and conducting inclusive engagement processes; and c) capacity building for the Ministry of Health (MoH) to take forward the plan after the closure of the programme.

Partners to develop capacity building plans with enough time to implement them, and to press local partners on the areas which need most support. Partners to focus on integrating local partners into their monitoring structures.

NRC to improve their offer for persons with disabilities, through finding accessible premises, incorporating Washington Group (WG) questions[3], engaging more with disability NGOs and legal rights for refugee people with disabilities.
[3] http://www.washingtongroup-disability.com/washington-group-question-sets/

DFID and partners to review the theory of change (ToC) in relation to the logframe during the quarterly programme reviews and annual reviews, applying logframe changes if necessary, no later than three months before the next annual review.

Follow-up with partners on recommendations following the review of the safeguarding due diligence assessments by the Social Development Adviser, which focus on strengthening the systems of downstream partners.

## B: DETAILED OUTPUT SCORING

Output Title	Training and capacity building of key stakeholders including NGO staff, GOJ staff and community leaders
Output number per LF		1	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones for this review (March 2019)	Progress (March 2019
1.1 # of national, local authorities, lawyers, jurists, law students and legal aid providers trained on access to justice issues for refugees	75	166 (221%)
1.2 # primary health care providers receive training, for example mhGAP[4], early detection/ early intervention (ED/EI) and mental health and psychosocial support (MHPSS)[5]	124	154 (124%)
1.3 # of community actors and leaders that are empowered to support protection needs both in community settings and camps to influence service provision	139	159 (114%)
1.4 # of projects which reflects improved inclusive practices after HI tailored coaching to the service provider	4	0 (0%)
1.5 % of training participants demonstrating an improved knowledge in topics covered	70%	85% (121%)
[4] To support primary healthcare providers in identifying and referring mental health patients
[5] HI’s target is for the number of primary healthcare centres, the number of staff trained in the centres is extracted from the narrative reports

Provide supporting narrative for the score
This output focuses on the training and capacity building of different actors on the key elements of this programme. This includes activities by all three partners to improve capacity, increase outreach, and enhance the quality of the programme.

Indicator 1.1 exceeded expectations. Achievements were driven by two local legal NGOs (Tamkeen and Justice Centre for Legal Aid-JCLA), supported by NRC. Tamkeen works with Syrians to support them in getting access to work permits, and JCLA takes on cases that involve the Shari’a court (including family law) as well as criminal cases. The reason for this overachievement is that training and capacity building events have taken place not just according to original workplans but also based on the availability of the participants, the operational needs and the opportunities that arise. If an opportunity comes up with a relevant institution to provide a training, then this opportunity is seized. For example, if NRC needs to engage with a new group of volunteers in a specific area to deliver its operational priorities, trainings for volunteers are organised accordingly, even if not originally forecasted.

Indicator 1.2 which measures the number of health care providers who received training on mhGAP (see footnote 4), early detection and early intervention (ED/EI) and mental health and psychosocial support (MHPSS) is slightly overachieved by IMC due to a larger than anticipated number of staff requiring MHPSS related trainings put forward for training by the MoH. Training was provided to primary healthcare providers in MoH primary health care (PHC) centres across different locations in Jordan. IMC provided on-site support in the clinics where it operated mental health services. The people trained were from a range of governorates across Jordan and not concentrated in Amman, showing a balanced geographical spread.

Indicator 1.3 which measures the capacity of community leaders to influence poor people's decisions to access services also overachieved. The health system in Jordan is struggling to cope with the influx of refugees, especially evident in some specialised services (disability care, mental health) which were under-developed prior to the crisis. Through this programme, direct assistance for people with disabilities and mental health conditions are complemented by building the capacity of local organisations (JOHUD, Cerebral Palsy Foundation, Community Development Centre Wehdat and Totangi Hospital) to improve their systems and technical capacity. The number achieved slightly exceeded the target as NRC was able to identify a higher number of volunteers through community-based organisations with a wide reach.

Indicator 1.4 has not delivered in the first 12 months of this programme. This is mainly because it has taken longer than expected to embed disability inclusion in organisational processes. HI supported 7 organisations to mainstream inclusion in their projects and organisational processes, namely: Norwegian Refugee Council (NRC), Danish Refugee Council (DRC), World Vision (WV), Nour Al Hussein Foundation (NHF), International Relief and Development (IRD), and UN Women. Inclusion and accessibility assessments in all these organisations and action plans were developed, although it is still to be seen how these will be operationalised. The organisations are planning to implement the action plans to improve disability and inclusion mainstreaming in their programming. We are confident that the targets will be met during year two of the programme as HI has developed the plans with the organisations and there continues to be demand from NGOs for this service.

Indicator 1.5 is linked to indicator 1.2 where agencies conduct pre and post evaluations to measure the degree of acquired knowledge through the trainings provided.

Lessons identified this year, and recommendations for the year ahead linked to this output
There is considerable need and willingness for training and capacity building on protection issues. There are considerable gaps in national systems and it’s recommended that partners engage more with the relevant ministries through the right channels in order to support them in the context of a protracted crisis.

One recommendation is for IMC to strengthen advocacy with the Ministry of Health to develop Guidelines, Standard Operating Procedures, and Patient Protection for MHPSS services. This can contribute to the sustainable impact of the programme, and to strengthening national systems on MHPSS service provision.

Moreover, there is an immediate need to continue discussions with the MoH and MoSD for streamlining ED/EI and referral protocols for services, particularly for children. This requires the development of guidelines and training on their use between the two ministries on the central but also the decentralised local level. This will ensure a sustainable framework for service provision in the future while contributing to system strengthening.

Output Title	Awareness is raised amongst beneficiaries and other community members on protection issues, and research is produced to influence advocacy and policy change
Output number per LF		2	Output Score	B
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones for this review (March 2019)	Progress (March 2019)
2.1 # of social media campaigns run to promote refugee rights and social cohesion	2	1 (50%)
2.2 # of direct beneficiaries and community members who received information (on legal services and disability inclusion)	30,200	24,096 (80%)
2.3 Number of periodic reports and policy briefs produced on barriers to rights for refugees in Jordan[6]	2	3 (150%)
[6] This primarily measures the production of reports rather than their effectiveness

Briefly describe the output and provide supporting narrative for the score
This output focuses on raising awareness of beneficiaries, the community, and other stakeholders to promote people’s rights and improve access to services.

Indicator 2.1 only achieved 50% of the target where NRC only ran one social media campaign in the reporting period. The campaign focused on birth registration where NRC worked with a company to produce a video on birth registration. Following this campaign, NRC had disagreements with the company and partnered with a different provider which caused some delays in achieving the target for this year as planned. We are confident that the new partnership will achieve the targets set for NRC to work with other agencies providing legal services and focus on the topics of birth registration, marriage registration, and the registration of Syrians with the Jordanian authorities. This partnership is expected to deliver on the missed target as well as milestones set for the second year of the programme.

Indicator 2.2 which measures the number of people who received information on disability inclusion, MHPSS, and counselling and legal assistance did not meet the target by a small margin. NRC expanded its operations in Amman, Balqa, and Madaba by increasing the number of incentive-based volunteers for the programme as well as expanding help desks. Supported by NRC, Tamkeen community facilitators conducted awareness sessions that covered an array of topics related to the Jordanian Labour Law, including minimum wage, employment contracts and work permits, and specific processes for issuing work permits for Syrian refugees. The underachievement is due to less people than expected attending sessions and some delays in the beginning of the programme as activities were being set up.

Around two-thirds of the beneficiaries of information sessions are female. Possible reasons, as revealed during discussions with beneficiaries, suggest that women face disproportionate consequences of not having the right documentation (marriage certificates and birth certificates for their children). Most of the women and girls seeking legal redress turn to JCLA after experiencing violence. They are provided with information, referrals for other services, legal advice, and legal representation in both Sharia and criminal courts.

Indicator 2.3 is slightly overachieved.
The reports produced are:
- Briefing note on the Pardon Law issued in January 2019, and how it affects the legal issues of refugees
- Findings and Recommendations on Protecting Work Rights of Refugees in Jordan (shared in the Brussels Conference)
- Needs assessment of asylum seekers and refugees coming from countries other than Syria

As part of the preparation for the Brussels Conference on Syria hosted by the European Union, NRC advocated for core metrics associated with the Jordan Compact (e.g., work permit count) to be adjusted to promote decent work and economic inclusion. NRC was successful in directly influencing the creation of new metrics that are relevant to the creation of decent work and economic growth.

In addition to the above, awareness on protection issues was also raised amongst beneficiaries and other community members through Community Based Rehabilitation (CBR) used by HI to empower the community and increase their uptake of services. CBR volunteers reach children and their families, identify their needs, provide home-based interventions, and raise the community’s awareness on disability. This included speech therapy training (following the finding that speech impairments are a major need in the field among identified children), information management training, and awareness-raising sessions on safeguarding.

Lessons identified this year, and recommendations for the year ahead linked to this output
Raising awareness and working directly with the community to facilitate the flow of information and referrals can play a very important role in increasing the access to services, particularly on civil documentation. As refugees and vulnerable groups are generally fearful of approaching authorities, working through local NGOs can greatly improve outreach and positive engagement leading to the improved protection of people.

That being said, there is increasing need for awareness-raising for Syrian refugee employees on work rights and work permits, which are limited to a few sectors. Despite the GoJ introducing some flexibility within work permits in certain sectors, those without permits risk exploitation, abuse, low wages, and conflicts with local communities. Itinerant Syrian refugee communities are found throughout Jordan in informal tented settlements (ITSs), concentrated in agricultural areas.

The creation of a CBR network in the community has contributed to the safety and dignity of Syrian refugees and vulnerable Jordanians by providing opportunities for cash-for-work, especially for people with disabilities.

Output Title	Vulnerable persons receive direct assistance, and have increased access to services
Output number per LF		3	Output Score	A+
Impact weighting (%):		55%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones for this review (March 2019)	Progress (March 2019)
3.1 # of direct NRC beneficiaries who received (a) legal counselling and (b) direct legal services	(a) 12,086 / (b) 1,168	(a) 18,468 / (b) 2,454 / (158%)
3.2 # of vulnerable people who received comprehensive rehabilitation services	600	1,638 (273%)
3.3 # of IMC beneficiaries receiving specialised mental health (MH) and child protection (CP) case management services at static centres and from mobile medical units (MMUs)	1,888	1,959 (109%)
3.4 # IMC beneficiaries receiving the social assistance protection package for three months (incremental)	100	103 (103%)
3.5 # of most vulnerable people referred by HI to external services	243	847 (349%)

Provide supporting narrative for the score
This output includes the core services provided by all three partners under this programme. These are legal assistance, mental health services, and services to people with disabilities.

The target for output 3.1, which counts people receiving legal support, was exceeded. The overachievement of the target for this indicator was due to the expansion of the provision of court representation by lawyers employed to support the issuance of legal and civil documentation for Syrian refugees. This new approach was piloted by NRC to free up the time of its own paralegals to undertake more complex cases, where external lawyers dealt with cases that were more straightforward. In this way, for example, a total of 7,450 beneficiaries were supported with obtaining the Ministry of Foreign Affairs (MoFA) stamp for legal and civil documentation. NRC started the pilot of legal representation through external lawyers in Amman and Balqa governorates. The implementation of this approach proved to be particularly challenging as judges were not knowledgeable about specific regulations put in place by the GoJ for the issuance of birth and marriage certificates for refugees. With the support of external lawyers, the cases were represented and awareness on applicable law increased, enabling the programme to reach more people than originally planned.

The target for indicator 3.2 which captured delivery of comprehensive rehabilitation services by HI was significantly overachieved. HI’s partner, Nour Al-Hussein Foundation (NHF), provided comprehensive services to 1,638 beneficiaries, including 894 in Zaatari camp and 744 in Azraq camp. The most needed services were physiotherapy and occupational therapy, followed by speech therapy and special education services and lastly psychosocial support. In Azraq camp, most needed services were physiotherapy, occupational therapy, special education, speech therapy and psychosocial support sessions. As part of the comprehensive rehabilitation services, NHF provided assistive devices and prosthesis to 150 beneficiaries in Zaatari camp, and 105 beneficiaries in Azraq camp. The reason for the overachievement is due to the diversity of services provided by NHF, which has a number of staff specialised in different rehabilitation areas. HI has discussed the revision of these targets with NHF and will seek to increase them in line with the level of services being delivered.

The target for indicator 3.3 has been slightly overachieved. In addition to MHPSS, the programme supported vaccination and nutrition among vulnerable children and mothers through JOHUD, a national NGO. Some of these services were delivered through mobile medical units (MMUs) to reach remote locations.

Output 3.4 met expectations. The families of children who were assessed to have particular protection concerns (for example: child labour, early marriage, risk of abuse) were provided with cash grants over a three-month period. The cash grants were unconditional, with their links to protection outcomes continuously reviewed. Delivering on this target was challenging for IMC due to the problem it faced with the cash grant service provider relating to operational and technical issues. This negatively affected the beneficiaries identified in Q1 and Q2, who had to wait for an extended period to receive the cash. Errors with ATM cards prevented beneficiaries from withdrawing money from cash machines. This forced many beneficiaries to travel long distances to shops to collect the cash leading to increased transportation costs and lost time. IMC has therefore changed the service provider, with further details in the VfM section.

Output 3.5 substantially exceeded expectations. During the previous year, HI referred 847 persons to external protection services, including 767 persons in camps and 80 in host communities. Referrals in Amman started in Q1, and then increased further in Q2 due to the increased capacity building of CBR volunteers. Most beneficiaries referred in Zaatari camp required medical assessments. The main reason for overachievement regarding this target is the development of the CBR volunteer network who were committed to the referrals as mentioned under output 2, as well as HI signing memoranda of understanding (MoUs) with a number of other NGOs to facilitate referrals between HI and those respective agencies.

Lessons identified this year, and recommendations for the year ahead linked to this output
Stigma and shame around mental health issues within the community is a challenge. IMC and HI should continue to conduct awareness raising activities with vulnerable families and their communities on topics such as psychological first aid, self-care, mental health services, and mental health concerns; aiming to reduce stigma and raise awareness of the importance of accessing specialised mental health care.

IMC should continue with plans to explore providing cash assistance using the Jordan Post Office, which it used previously before moving to the new provider. However, as this modality is more expensive as compared with that provider, a thorough Value for Money assessment should be undertaken. Another lesson is for IMC to further refine its selection criteria for protection cash assistance, and regularly follow-up with families to ensure they are aware of the purpose of the grant, as well as the impact it is having on protection risks.

During field visits we met with two legal aid partners of NRC, Tamkeen and JCLA. While both seem to be delivering well, conversations revealed a weakness in systems to oversee the quality of legal services, which affected JCLA’s ability to be accountable to the affected population. Going forward this needs to be improved by further strengthening the beneficiary feedback and complaints mechanism.

The targets set for this output were clearly not realistic, resulting in big variations. This is due to a number of reasons set out above. It is recommended that the partners and DFID realign targets to be more realistic through more careful analysis of the context and the adjustment of the logframe during quarterly monitoring meetings.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The programme theory of change is based on a combination of comprehensive protection, legal, disability inclusion, and mental health case management activities targeted at vulnerable persons. These activities are complemented by referrals for protection needs, direct cash assistance aimed at breaking the cycle of negative coping mechanisms (e.g. child labour, child marriage, trafficking, modem slavery) and psychosocial challenges faced by vulnerable communities. Together these activities have generated a strong protection package that contributed to better decision-making capabilities for refugee households.

During year one, based upon the baseline results obtained at the start of the programme, no significant changes were required or made to the project design. Throughout the reporting period, the project effectively contributed to the implementation of DFID’s strategic objectives and cross cutting principles of strengthening resilience and response to crises. Specifically, the project has contributed to improving access to comprehensive mental health, legal, and child protection services for those residing in some of the remote areas of Jordan. The project also contributed to the overall improvement in wellbeing of beneficiaries and reduction in protection risks.
A number of indicators were exceeded and could have usefully been revised during the second and third quarters to be more realistic, but as this programme is in its first year this is not surprising and care will be taken in outer years to ensure greater accuracy of targets based on the findings of this review.

The success of the overall outcome of meeting people’s needs by increasing their access to services, however, also depends on a variety of internal and external factors. During field visits, conversations with beneficiaries showed that meaningful exercising of rights is much more prevalent when it comes to securing accessing health services rather than legal services to support exercising housing and work rights, mainly due to the more complex nature of the problems and limitations in the legal framework of Jordan.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The overall impact of the programme is that refugees and vulnerable members of the host community live in safety, security and enhanced wellbeing. Where the overall outcome is that the needs of the most vulnerable met by greater access to expanded and strengthened protection, rehabilitation and legal services.
Full data will only be available upon completion of the project in 2021. However, observations, key informant interviews, and small surveys through which the partners are collecting data show that the programme is broadly on track towards achieving outcomes and impact.

This data suggests that some of the key assumptions underpinning interventions are holding.
For example, NRC found that 98% of beneficiaries (out of a target of 80%) served under the programme are reporting being able to exercise their rights (by using information and legal counselling to issue civil documentation). Additionally, 67% of HI and IMC beneficiaries (out of a target of 70%) are showing an increase in functional independence as a result of rehabilitation services and mental health support.

Explain major changes to the logframe in the past year
N/A as this is the first review. No major changes were made to the programme last year. Milestones and targets for a number of outputs should ideally have been increased ensuring targets were ambitious and realistic and VfM is maintained – this will be done in future.

Describe any planned changes to the logframe as a result of this review
The logframe should be revisited early next year making it more reflective of complementary approach of multiple partners which will include inter-agency knowledge sharing, training, and beneficiary referrals (for example, most of the IMC programme and HI’s early detection / early intervention are linked). An integrated package of services meeting multiple vulnerabilities will achieve outcomes across a range of protection concerns which are DFID priorities.

With many of the targets for this annual review having been exceeded a recommendation from this annual review is that targets for the forthcoming years are revised soon in light of this overachievement and a more realistic level set. By stretching milestones for future years of the programme year the partners will be challenged to drive efficiency through costs and outreach. This will lead to better use of resources reaching a greater number of beneficiaries. It is therefore a holistic approach, moving away from ‘silo’, as is the case with current programming where partners largely worked in isolation.

There is room for improvement in measuring outcome/impact level results or progress. The business case states that the programme contributes directly to a) tackling the causes of instability, insecurity, and conflict and b) sustainable change by handing over services through working with government ministries to develop legislation and build capacity. The current logframe does not include clear indicators to capture that level of change. Going forward the logframe could include indicators measuring the longer-term impact of the programme, including conflict-sensitivity indicators that can help capture changes in the context that can affect the conflict and political context and opportunities.

For example, we could measure how many refugees play a more active role in the formal work sector because of resolved documentation gaps, including work permits. Additionally, we can measure how many children have improved access to education thanks to case management, or how many children avoid negative coping strategies thanks to cash disbursements. There is a possible link to be made with safety and security. The team could also explore if there is a geographic overlap with any other CSSF programmes where indicators measuring social stability are being used and could support this logframe.

## D: VALUE FOR MONEY
Assess VfM compared to the proposition in the Business Case, based on the past year
This programme is being managed by three strategic partners: IMC, NRC and HI. The key cost drivers include staffing costs and procurement for goods and services.

All partners have worked with DFID before and have proven records with adhering to policies and procedures when considering the principles of Value for Money. In addition, all partners have been submitting their quarterly reports, which include measures taken to ensure commitment to VfM across all programme activities. There are no specific VfM indicators in the logframe.

Economy
Staffing: The highest cost driver for the programme has been attributed to staffing costs. Across all partners and based on the varying specialties offered, the programme relies on highly qualified technical staff to drive activities. To ensure technically qualified staff were recruited, partners have used rigorous assessments for the hiring of their staff focusing on the selection of high-quality national candidates where local talents can be empowered while costs are managed.

Partner spending on staffing costs has been within the allocated budget with minor variances throughout the year with a larger proportion of staff being national staff. Where the process of nationalising posts is incremental to ensure continuity of high-quality services, partners have taken other measures to reduce staffing costs. For example, NRC has reduced the number of senior programme managers from 2 (split for two geographical areas) into 1 post covering all areas. This resulted in cost savings of 40%. Moreover, the number of programme coordinators was reduced from 6 to 4, resulting in cost savings of 33%. In parallel, NRC was able to invest some of these savings in increasing the number of contracted lawyers to increase the quality of services and be able to reach more beneficiaries.

Procurement of goods and services: All partners have shown commitment to stringent procurement policies and procedures to ensure open, transparent and competitive costs without compromising on quality. Where possible, and through competitive bidding, partners encouraged local supply of products and services to increase impact on local economy creating opportunities for local income generation.

During this year of implementation, IMC developed a procurement plan for the entire duration of the grant and coordinated internally with the relevant departments to ensure timely initiation of procurement. Moreover, the closure of UK-funded programmes in southern Syria (as a result of changing conflict dynamics) freed up some assets that were already procured and present in Jordan. Some of these assets (mainly office equipment) were donated to both IMC and HI which reduced the need for procurement. Saved costs were invested in direct project delivery.

Efficiency
At the start of the programme, DFID negotiated a reduction of overhead costs by 1-2% with all partners to redirect funding to serve more beneficiaries, hence maximising the efficiency of the services provided.

Partners have used internal tools to monitor spend against budget, using monthly reports to track progress of spend against outputs, and using integrated mechanisms to maximise on cost management.

There were key headlines that reflected on efficient behaviours to mitigate disruption to programme implementation whilst prioritising reach and services to vulnerable beneficiaries:

Time efficiency: Although there were delays in securing Jordanian government approval, time was invested in the meantime to collaborate with downstream partners to finalise agreements, technical tools and cost calculation tools, whilst ensuring that volunteers were identifying beneficiaries to be served under the programme. Having the opportunity to complete these technical and administrative tasks whilst awaiting approval ensured that partners were able to commence activities as soon as approvals were gained, eliminating any disruption to the programme implementation.

Cost per beneficiary: We have seen successes with partners regarding delivering beneficiary targets while remaining flat to budget. As an example, IMC reached 7,076 beneficiaries versus a planned reach of 5,229 (+35%) whilst maintaining planned spend for year one. The cost per beneficiary can vary significantly by partner activity but we will continue to track the calculations of cost per beneficiary made in the business case and note efficiency gains.

Effectiveness
All partners are considered as technical leaders in their field of work and as such, they have worked rigorously to develop and utilise effective and routine reviews, visits and surveys to assess the effectiveness of services provided to the beneficiaries. Effective monitoring systems and tools were developed by partners to maximise programme achievements, ensuring that challenges were managed without delay or impact on the beneficiaries. Investment has also been made to define minimum requirements and qualifications to identify new recruits and build capacities for existing teams and downstream partners to deliver aligned and consistent service provisions to beneficiaries.

The community-based volunteer networks are also an important component to increase effectiveness through a wider outreach of beneficiaries and home follow up visits for patients as well as referrals to other services offered by other organisations. In the case of HI as an example, CBR volunteers have disabilities themselves or are parents of disabled children and are helping raise awareness about this issue to reduce taboos in their community, thus positively impacting effectiveness.

Outcome indicator results referred to in Section C above also reflect the effectiveness of the programme where partners have been able to meet and exceed the set targets.

Equity
Working with three different partners in delivering this programme improved the equity preposition of the services provided, as different partners work across different areas of Jordan and serve different vulnerable groups with specific needs. Volunteers working directly to identify beneficiaries have been equipped with the right training and are using assessment tools to identify people in dire needs while ensuring gender sensitivity is mainstreamed along through this process. Having a balanced gender and nationality selection of community volunteers supports the wider reach out to all parts of the community, and since the services offered by the programme are open for all vulnerable people based on need rather than nationality or status it helped mitigate community tensions as well.

Partners continued to show commitment to support beneficiaries who were unable to reach the services provided through conducting home visits, which helped ensure access to some of the most vulnerable families living away from services.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
This programme represented Value for Money across the 4Es whereby all three partners increased reach to beneficiaries vs targets, whilst managing this increase within budget. Also, partners managed to develop an internal referral network between each other to provide beneficiaries with a more comprehensive service provision. An example of cooperation would be NRC’s ICLA sessions held at IMC’s hospital (through cooperating with IMC) in North Jordan that targets mothers, mothers to be and new-born babies.

Based on the above analysis, the programme should continue from a VfM perspective as the original business case proposition holds, with demonstrated efforts by partners to monitor and manage cost drivers, improve efficiencies, deliver effective programmes, and ensure equity in reaching the most vulnerable. In the context of the wider DFID Jordan humanitarian portfolio, this is the only programme that is delivered by INGOs where other activities are delivered by UN organisations, thus it is difficult to make direct comparisons. However, this further justifies its need to continue as these organisations have lower overhead costs as well as providing quality specialised services to the most vulnerable with demonstrated effectiveness.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation
The overall risk rating for this programme remained “minor” throughout the first year. Although the overall risk rating remained unchanged, it is important to highlight some areas that did see a change in residual risk rating.

There was only one severe risk identified in the business case and that related to exchange rate fluctuation affecting activities. Mitigating actions identified included close monitoring of the exchange rate fluctuations, contingency measures by partners to react to depreciating currency value and for partners to actively look for savings to reduce expenses where possible. Over the past year, the value of the GBP stabilised thus reducing this risk from severe to minor.

Security conditions deteriorating in Jordan were initially ranked as major; this risk has subsequently been updated as minor due to the situation in southern Syria stabilising from a conflict perspective, reducing the risk of conflict overflow into northern Jordan where partners operate.

As reported by partners, there were some specific risks related to the implementation of the programme such as NRC where lawyers from a broad range of legal aid providers were reportedly threatened to be disbarred by the head of the Jordanian BAR Association for undertaking pro bono legal aid work. This has been an ongoing issue in Jordan where the BAR sees this as unfair competition to lawyers but in the absence of pro bono legal aid vulnerable people would not be seeking representation to begin with. To mitigate this risk NRC ICLA have changed the title and job descriptions of legal officers to “legal counsellors”. NRC is also working with external partners to draft common advocacy messages to be presented to the government. This risk is regularly monitored by DFID and NRC and not seen to pose a direct risk to the programme at this time.

Another example of a partner specific risk has been reported by HI whereby a local service provider identified through the programme showed resistance to work with the HI team and receive the agreed number cases without getting additional staff incentives. To counter this challenge, HI identified another partner who will resume services for beneficiaries in and around Baqa camp.

Safeguarding
An enhanced safeguarding due diligence assessment has been completed for all three partners in accordance with the SMART Guide. All partners have the relevant safeguarding policies in place where staff are regularly trained on procedures and have to read and sign codes of conduct outlining their responsibilities. Staff are also aware of reporting mechanisms, and work is being done with downstream partners to strengthen their systems. Language is included in sub-grant agreements to reflect downstream partner responsibilities, but more work needs to be done to improve systems of local organisations to protect staff and beneficiaries against sexual exploitation and abuse. Governance and HR structures in the organisations also incorporate safeguarding measures where partners have protection points of contact to monitor, train, and report any cases that might arise. In addition to that, interview processes include considerations of safeguarding when interviewing potential candidates who might work closely with children and vulnerable groups, and reference are sought before a person is hired.

The DFID Jordan team will follow-up closely with partners on specific recommendations and action points that resulted from the enhanced due diligence process and will discuss at quarterly meetings.

Conflict Sensitivity
DFID’s approach to conflict sensitivity was discussed with all three partners and an initial assessment was made to assess the degree to which the partners are aware of conflict sensitivity and how they incorporate it into programming. The business case indicates that minimum standards of conflict sensitivity have been incorporated into the programme approach, and below are examples of how this was tackled by partners in the past year.

As part of NRC’s ICLA expansion to Zarqa governorate, NRC’s ICLA team worked with its protection team to hold a ‘do no harm’ workshop for volunteers in that location. Key risks and mitigation measures were discussed, and a number of recommendations were agreed upon for moving forward. The findings of the workshop focused on increased community tensions between Syrians and Jordanians due to the limited job opportunities, specifically within the context of the high unemployment rate in Zarqa. NRC will mitigate this by offering volunteer opportunities (with some compensation through stipends) and will continue to run a transparent recruitment process; prioritising Zarqa residents. Moreover, in Mafraq, NRC is using a theatre modality to deliver sensitive messages on child marriage and the legal implications of undocumented children. The DFID team watched one of the performances during a field visit which was very powerful and well-received by the community. In addition to that, NRC works with a wide network of community-based organisations (CBOs) to diversify its field presence and mitigate for any perceptions of bias.

HI focuses its efforts on transparent and clear mechanisms for beneficiary selection and ensures the inclusion of all vulnerable people within the communities that it is working in. Moreover, staff are trained to disengage when the risk of causing harm outweighs HI’s intervention. This was demonstrated when HI staff disengaged from the Sahab area following tensions arising in the community towards HI. It then sought opportunities to deliver services in other areas based on need.

Another example is IMC’s work throughout project implementation to continuously discuss and communicate activities with local authorities, communities and, local organisations. It continues to encourage social cohesion through activities in its protection centres and consults with different stakeholders of different nationalities on the criteria for beneficiary selection.

Following the completion of this Annual Review, the DFID Jordan team will review each partner’s conflict sensitivity approach in comparison with the ‘Conflict Sensitivity Matrix’ developed at the Business Case stage. This is to gauge areas of improvement and offer support if needed.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
All three partners delivered timely quarterly narrative and financial reports, which are due one month after each quarter ends. The reports generally adhered to the guidance provided and included the needed information on progress in addition to reporting on Value for Money, conflict sensitivity, and beneficiary feedback. As the programme progressed, the narrative reports contained valuable contextual information but that took attention away from simple reporting on progress against the agreed milestones. The DFID team had discussions with all three partners to simplify reporting and this has resulted in more focused and succinct reports in Q4.

All partners have submitted their annual audited accounts (AAAs) in accordance with their financial year and within six months of it ending. All are unqualified. NRC and HI are due to submit the 2018 reports by the end of June 2019.

The DFID Jordan team has had regular conversations with partners on risks to the programme as well as the delivery chain. Partners are required to update their programme risk registers every quarter along with the submission of the quarterly reports. This is accompanied by a narrative section that explains any changes and mitigation measures. This is discussed with partners at quarterly meetings and ad hoc when needed. Moreover, partners have completed delivery chain risk maps that highlight the delivery chain, the amounts disbursed to downstream partners, and risk and mitigation measures associated with working with these specific partners. Partners have shared the agreements that they have signed with downstream partners, which reflect DFID risk requirements, particularly on aid diversion. The due diligence assessments completed of partners also looked carefully at downstream partner management and recommendations are being followed up. There is no major risk in working with any of the downstream partner associated with this programme as direct partners are in close collaboration with them with oversight of activities.

IMC is paid quarterly in advance as it does not have sufficient reserve funds to undertake activities, whereas HI and NRC are paid quarterly in arrears. Payments to IMC are made based on quarterly forecasting where IMC spent 71% of the forecast in Q1, 70% in Q2, 93% in Q3, and 95% in Q4. Overall, it had a 2% variance from the approved budget for the 2018/2019 financial year. NRC spent 100% of the approved budget for the financial year, while HI spent 76% of the approved budget. The latter was due to project delays highlighted in the output assessment above. The unspent balance was carried over for the following two financial years.

All partners provide DFID with an asset register for assets purchased through this grant, and this is updated quarterly. The list also includes assets donated to the partners from UK-funded programmes that were destined to southern Syria but had to close down. The DFID Jordan team conducted some spot checks of assets during field monitoring visits and no concerns were raised.

To improve our partnership, we continuously engage in dialogue with all three partners where we held a programme kick-off meeting in May 2018 to agree on the joint logframe and discuss programme monitoring and how we work more efficiently together. The meeting also included a session with downstream partners to hear from them and address any concerns they might have. A follow-up meeting was held in May 2019 in preparation for this Annual Review where we discussed challenges and the sustainability of the programme with both the direct and downstream partners. We received positive feedback on these events and will continue to have these discussions with partners.
Date of last narrative financial report(s)	30 March 2019
Date of last audited annual statement (s)	NRC: 31 December 2017 / IMC: 30 June 2018 / HI: 31 December 2017

G: MONITORING, EVIDENCE & LEARNING
Monitoring
The DFID team has regular quarterly meetings with partners and field visits of operations in Jordan where engaging with downstream partners and interacting with beneficiaries for feedback are the main purposes during these visits. As a total, two meetings and two field visits were conducted per partner and a comprehensive round table session was attended by all partners pre the drafting the annual review to discuss progress and any challenges.

All partners have mechanisms in place to collect feedback and complaints from beneficiaries and this is done internally through monitoring teams using different tools including surveys, focus group discussions, home visits, email and phone hotlines, complaints boxes and routine reporting by downstream partners. Partners, through their monitoring, evaluation, and learning (MEAL) teams coordinated training sessions to train internal field teams along with their downstream partners to improve their monitoring and evaluation tools on how to collect relevant information to track progress and report to donors.

This Annual Review was led by DFID Jordan Humanitarian Adviser with input from the Social Development Adviser (SDA) and Programme Manager. The SDA and PM do not work directly on the programme and provided external input and reflection on the programme. They conducted field visits to all three implementing partners and joined the roundtable discussion referenced above. Quarterly reports, meetings, and field monitoring visits undertaken throughout the past year also informed the drafting of this report. The report was also reviewed by the DFID Jordan DESA Conflict Adviser and the Lead Humanitarian Adviser.

Evidence
The evidence collected by partners through regular monitoring feeds into their wider planning as well as programme design. Outcome monitoring involves regular surveys of beneficiaries by partners’ respective monitoring and evaluation (M&E) units where trends are reviewed and reported to DFID. Moreover, partners have held workshops to reflect on the first year of implementation as well as monitor the success of new activities (for example, the external lawyers contracted by NRC). These pieces of evidence are also shared with DFID, including recommendations; where the team follows up with the NGOs on the implementation of these recommendations.

All partners report data disaggregated by age, gender, and location (by governorate and district where data is collected). All partners collect data and upload it onto their internal data management systems which feeds into their reporting to DFID.

There is a planned external evaluation by NRC to cover the ICLA programme over the past 3 years (where DFID was also a contributor under a previous grant). DFID was consulted on the ToR, and NRC has contracted a consultant who will begin work in June for a report to be ready by August. DFID will dicuss the findings with NRC and wider partners and use these findings to inform the direction of the future programme.

Learning
The programme has used several key learning points identified from consistent monitoring during implementation to improve overall effectiveness of services and adapt accordingly.

Key learning points and corrective actions taken included:

Sahab area resistance to the early detection/ early intervention (ED/EI) programme (as community members expected personal benefits that HI would not provide) offered by the HI team which responded by identifying a new area to work and provide their services in. It is important to ensure that partners conduct a thorough scoping exercise for their targeted areas prior to implementation since services provided are sensitive and need community engagement and support to ensure success in their delivery, and also respond to people’s needs in those areas.

IMC faced operational and technical related challenges during Y1 with the current service provider. In response to this issue, IMC plans to return to the previous service provider “Jordan Post Office” as their experience with them was an easier and more straightforward process despite being more expensive as compared to the other service provider. Overall, it succeeded in achieving the desired outcome of supporting people’s safety and wellbeing with dignity; delivering a higher quality service. While DFID supports a move to mobile money as it provides more efficiencies and potentially more financial inclusion, IMC’s experience has provided important learning related to using this delivery mechanism for cash for protection. Mainly, the mobile service provider could not disburse cash to beneficiaries under 18, suffered from a number of technical issues, and did not make it possible to recover unspent funds as per IMC’s standard operating procedures (SoPs).

Totangi hospital, an MoH hospital based in Amman which HI is working with on capacity building, has been challenging in terms of delivering weekly agreed rehabilitation targets and has requested incentives for their therapists to counter increased caseloads. Consequently, HI have signed an MOU with the Community Development Centre in Baq’a camp to avoid disruption to the programme. Although HI acted quickly to reduce disruption to their services, it is important to work closely with local service providers to align on targets, ensuring that they can be delivered against agreed conditions to avoid conflicting interests.

In the case of NRC, changes had to be made on job role titles to avoid potential legal implications by the Head of the Jordanian Bar Association (JBA). It was identified during the implication phase that the legal basis for these implications were linked to the fact lawyers cannot work in companies unless they provide legal advice services. Mitigation actions taken to change the job titles will protect individual lawyers against procedures initiated by JBA.

Progress on recommendations from previous reviews
This is the first annual review of this programme. However, as DFID has funded these three agencies to deliver similar activities under previous programmes, we have reflected on recommendations from the Project Completion Reviews of the previous programmes.
Recommendations to partners included:
- Partners to incorporate recommendations from the final external evaluations undertaken at the end of the previous grants into the new programme, particularly looking at protection outcomes of activities.
- Partners to build in sufficient start-up times for new activities and to develop capacity building plans with enough time to implement them, and to press partners on the areas which need most development.
- DFID to work closely with partners on refining outcome indicators to align them more closely with the outputs.
- Partners to set more realistic targets for outputs.
- Partners to improve their financial forecasting to prevent future underspends, with strict oversight from DFID at each quarterly review.

On outcomes and incorporating learning from external evaluations; DFID met with each partner separately along with the DFID Jordan Statistics Adviser, and refined outcome indicators for this programme to reflect areas of change, focusing on protection. Recommendations from external evaluations conducted by IMC and HI were incorporated into the design of this programme. NRC’s upcoming evaluation can also inform programme changes.

Financial forecasting has improved considerably as reflected in section F, and partners have built in sufficient start-up times for new activities (for example for the mobile medical unit) and have worked closely with downstream partners to develop capacity building plans that are realistic and fit-for-purpose.

Partners continue to achieve more than the set targets for most outputs and while there are justifications and positive efficiency gains, DFID should continue to encourage partners to plan more accurately.