Programme Completion Report

Indonesia Climate Change Trust Fund

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime.

Review Date:	Feb-Apr 2015

Title: Support for the Implementation and Preparatory Arrangements of the Indonesia Climate Change Trust Fund
Programme Code: 201672	Start Date: / 22 March 2010	End Date: / 31 December 2014

Summary of Programme Performance

Year	2010-2011	2011-2012	2012-2013	2013-2014	PCR
Programme Score	No data	A	B	A	A
Risk Rating	Medium	Medium	Medium	Medium

Financial Position

Original Programme Value	GBP 4,700,000
Extensions/ amendments	Extended until 2012; additional contribution of GBP 1,500,000 / Extended until 2013 / Extended until December 2014
Log-frame revisions (with dates)	Revised February 2014
Total programme spend	GBP 6,200,000 was transferred to UNDP. A final financial report is due from UNDP by end June 2015 and unspent funds will be returned to DFID. The estimated remaining balance is around GBP 400,000, meaning that total spend of DFID funds is an estimated GBP 5,800,000.

Follow up actions required following closure

UNDP will produce the final project report and programme expenditure report within six months of project close and refund the balance as per the agreed Cost Sharing Agreement. Unspent funds at the end of the programme are estimated at GBP 400,000.

List of Abbreviations

APBN	Anggaran Pendapatan dan Belanja Negara (Government State Budget)
BAPPENAS	Badan Perencanaan Pembangunan Nasional (National Planning Agency)
BMKG	Badan Meteorologi Klimatologi dan Geofisika (National Weather and Climate Agency)
DNPI	Dewan Nasional Perubahan Iklim (National Climate Change Council)
GHG	Greenhouse Gases
ICCTF	Indonesia Climate Change Trust Fund
RAN-GRK	Rencana Aksi Nasional Penurunan Emisi Gas Rumah Kaca (National Action Plan on Reduction of Greenhouse Gas Emission)
RAD-GRK	Rencana Aksi Daerah Penurunan Emisi Gas Rumah Kaca (Regional Action Plan on Reduction of Greenhouse Gas Emission)
REDD	Reduced Emission form Degradation and Deforestation
Satker	Satuan Kerja (Working Unit)
SGP	Small Grant Programme
SOP	Standard Operation Procedures
UNDP	United Nations Development Programme

A. Introduction and Context

DevTracker Link to Programme documents:	http://devtracker.dfid.gov.uk/projects/GB-1-201672/documents/

Indonesia is the world’s fourth most populous country, a continent-sized archipelago of 17,000 islands. It is a major emerging economy and one of the world’s largest emitters of greenhouse gases. It holds the third-largest area of tropical forest and 70% of the world’s deep tropical peat soils (which sequester massive reserves of carbon).

Reducing emissions and moving onto a low carbon growth path is a high priority for the GoI. In 2009, Indonesia announced ambitious plans to tackle the growth of emissions and called for international support to help it achieve even greater reductions. Driven by mutual interest in tackling issues of climate change and sustainable growth, the UK has committed to working with Indonesia to help it move to a low carbon based economy, to meet its national emissions targets and for both countries to achieve an ambitious global deal through international negotiations.

The Indonesia Climate Change Trust Fund (ICCTF) is the first national government trust fund institution in Indonesia, and globally one of first examples of a national mechanism to fund climate change action. It was established in 2009, with the goal of supporting a nationally owned climate change response in Indonesia, in the context of emerging policy commitments on climate change following the UNFCCC Bali COP in 2007. It is administered by the Ministry of Development Planning (BAPPENAS), with UNDP acting as the interim Fund manager. The Fund seeks to mobilise, manage and allocate funding in alignment with Indonesian development priorities in order to efficiently and effectively contribute to: (i) the implementation of GHG emission mitigation measures and climate change adaptation activities; and (ii) the mainstreaming of climate change issues into national, provincial and local development planning.

The establishment of ICCTF demonstrates the commitment of GoI to address climate change under the principles of the Jakarta Commitments[1] to enhance national ownership of aid programmes and improve aid coordination.
[1] http://pendanaan.bappenas.go.id/index.php?option=com_content&view=article&id=22

The origins of the ICCTF can therefore be seen as drawing together the national climate change agenda and the development effectiveness agenda. The ICCTF was jointly launched by Bappenas and the Ministry of Finance, and was intended to align and pool international financial resources with national investment strategies and domestic budgetary funds in an innovative, transparent and accountable manner. Broadly speaking, the ICCTF has three thematic windows: energy, land-based mitigation, and adaptation and resilience. These thematic windows cover almost all of Indonesia’s mitigation priorities in the national climate change action plan (RAN-GRK).

The UK contributed a total of £ 6,200,000 to the ICCTF - (£4.7 million in 2010 and £1.5 million in 2011. Other contributions to the trust fund came from Australian Aid (AusAID) who provided US$ 1.4 million, Swedish International Development Agency (SIDA) which provided US$ 332,000 and United Nations Development Programme (UNDP) which contributed US$ 80,000 at the start of the project.

The purpose of this Project Completion Review is to assess the success of the ICCTF project in achieving its stated outputs, and their contribution to the project purpose and goal over the life of the project. It provides a final assessment against the logframe, the extent to which the project has achieved its objectives, and analysis of learning and recommendations for the future.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment – A (programme met expectations)

The goal of the programme was to enhance the GoI’s leadership on climate change by establishing a national climate change trust fund. This in turn was to be achieved by a “learning by doing” process through the selection, funding and implementation of a range of climate change projects, supported by capacity building for relevant units in GOI and the development of an underpinning regulatory framework. The interim trust fund platform was to be managed by an external party (UNDP) and handed over to GOI once all the preparatory steps had been achieved.

The establishment and operation of a national climate change trust fund was an innovative programme for Indonesia to embark on, with few precedents internationally. With the successful establishment in 2014 of a national trust fund that complies with international best practice, the project has succeeded in delivering its outcome targets thus far. However, the ICCTF is a very small part of Indonesia’s climate finance picture, and to succeed over a longer timeframe it must scale up. A recent review of climate finance in Indonesia found that there was $324 million in international support directed to Indonesia[2]. With capitalisation of $11.4 million, the ICCTF remains one of the smaller actors in the domestic climate finance landscape.
[2] Climate Policy Initiative 2014. The Landscape of Public Climate Finance in Indonesia

The planned outputs of the ICCTF programme were:

Output 1. Priority climate change projects selected, supported, monitored and evaluated. These projects were focused on three thematic funding windows: a) Land-based Mitigation; b) Energy and c) Adaptation and Resilience
Output 2. Functioning policy dialogue and increased awareness of ICCTF nationally and internationally
Output 3. Capacity of ICCTF governance and related stakeholders (Government of Indonesia and CSOs) developed

Achievements against these outputs include:-

Output 1: Six climate change projects (two for each window) were selected, monitored, and evaluated; sixcapacity building activities to support project assessment/selection and proposal development were held ; four financial management spot checks were conducted.
Output 2: National Action Plan on Greenhouse Gas Reduction (RAD GRK) guidelines were launched; Three ICCTF newsletters published; ICCTF participated in UNFCCC COP from 2011 to 2014; Twelve formal and informal policy dialogues and six major public awareness events were held to increase public awareness of ICCTF at national and international levels;
Output 3: Bank Mandiri was appointed as National Trust Fund Manager; 19 capacity development programs for GoI and CSOs were implemented; a Ministerial Decree on ICCTF Trust Fund[3] was issued; A National Fund Manager was appointed; ICCTF’s database system was established; ICCTF personnel contract was transferred from UNDP to GoI; initial implementation of fundraising strategy was completed.
[3] KEP.33/M.PPN/HK/.03/2014

As described in Section (F) below, the programme faced significant delays during its implementation and was extended three times, leading to tension between donors and the programme. DFID and other donors undertook joint monitoring and reviewed programme performance periodically. Despite some concerns over the performance of the interim fund manager and Secretariat particularly concerning delayed implementation, the programme’s achievements are significant. This is borne out by the fact that both DFID and USAID are currently considering placing programme funds into the newly-established trust fund.

Appraised against the targets set for this programme, ICCTF is judged to have met expectations. However, it should be noted that we have reservations about the quality of the ICCTF sub-projects, and it is not clear from ICCTF’s own evaluations that these delivered lasting climate change impacts. This aspect does not feature in DFID’s logframe so the programme is not formally assessed against this criterion for the purposes of this review, but does remain a concern for future phases of ICCTF operation. Potential donors to ICCTF will want assurance that future projects will deliver substantive and lasting impacts as well as meeting financial and administrative requirements.

The legal basis for ICCTF
A preparatory phase under the interim management of UNDP was called “Preparatory Arrangements for the Indonesia Climate Change Trust Fund” (PREP-ICCTF). This was established through two Ministerial Decrees[4] by the Minister of National Development Planning in 2009. In addition to these Ministerial Decrees, the Government of Indonesia issued Presidential Regulation No. 80/2011 to provide further guidance on trust funds.
[4] No. KEP. 44/M.PPN/HK/09/2009 and No. KEP. 59/M.PPN/HK/09/20I0

The legal basis for the establishment of the ICCTF is BAPPENAS Ministerial regulation No 13/2013 and its revision No10/2014 which accredits the ICCTF as a national trust fund and assigns a Board of Trustees and Fund Manager to implement the ICCTF. To implement the regulation, BAPPENAS issued a further ministerial decree[5] regarding the establishment of the Board of Trustees of ICCTF.
[5] Ministerial Decree No 97/M.PPN/HK/10/2014

As a trust fund representing the GoI, ICCTF was approved under the BAPPENAS budget allocation to receiving state budget (APBN) funds in 2015. Initially, USD 1.5 million has been committed annually for at least 5 years, with the funding disbursement started in 2015. These state funds will be allocated for the ICCTF secretariat operational expenses and to initiate new projects (via a small grants program).

Output Score and Description: A – Outputs met expectations.

Lessons and how these have been shared

Anticipating and responding to project delivery challenges is critical.

The success of this project was strongly dependant on effective decision making (by the Steering Committee before the Fund was established and then the Board of Trustees after Fund inception), and in particular how these were able to anticipate and respond to the inevitable challenges of project delivery. It appears that that decision making processes within both was hindered by administrative challenges, in particular the ability to convene the SC/Board members on a regular basis. In retrospect, it may have been unrealistic to expect senior government representatives to engage heavily at the management level, without due consideration of the workload expected of them on the Board. This should have been identified in the risk management strategy during the design phase to feed into an improved design of the Board and its roles and responsibilities.

The ICCTF could usefully draw on the lessons from the Green Climate Fund (GCF) where the post of the Trustee is distinguished from the Board. The GCF Board acts as the Steering Committee, overseeing the management of the Trustee (World Bank). This way, decisions regarding fund disbursement and other routine tasks could be taken outside of the Board meetings. By overcoming management challenges, the ICCTF could focus its resource better on its main task as the National Fund Entity. However this is the first such trust fund operational in Indonesia and the ministerial decree to establish ICCTF did not separate these functions.

A more strategic approach to engaging stakeholders and beneficiaries could have obtained greater levels of buy-in to the ICCTF.

A major focus of the programme was to prepare finance and management systems to enable the operation of ICCTF. This involved activities to support a transition plan from the interim management (UNDP) to a National Trust Fund and National Fund Manager (Bank Mandiri). As a result, other than the pilot projects, most of the activities were targeted at ICCTF staff and focused on strengthening their capacity in finance and human resource management. However, as a National Fund Entity seeking national and international recognition, reaching out to stakeholders to increasing the profile of ICCTF is also crucial, and could have been done better.

An outcome-focused framework is important to ensure lasting environmental benefits
The ICCTF log frame is heavily based on input-based metrics. In this framework the success of the project is measured by how much the implementing partner conducted certain activities, not the actual effectiveness and impact of these activities on climate change policy nor their ultimate environmental outcome. This is perhaps understandable given the necessary focus on capacity building and administration during the initial phase of support to the trust fund, but any future support of ICCTF should focus far more on outcomes.

In terms of the value of lessons learned from ICCTF, it should be noted that there are two other related trust funds in Indonesia: the Millennium Challenge Account-Indonesia (MCA-I), which is already operational, and the Fund for Reducing Emissions from Deforestation and forest Degradation in Indonesia (FREDDI) – which is still under discussion. ICCTF has already influenced the establishment of MCA-I, and with FREDDI still to be established, the lessons learned remain very relevant for this and other similar institutions in Indonesia.

## C: DETAILED OUTPUT SCORING

Output Title	Priority Climate Change Projects (Land Based Mitigation, Energy, Resilience and Adaptation)
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	35
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target (2014)	Progress
1.1 Number of proposals received	Call for small grant proposals conducted; / At least six proposals received under Small Grant Program for 2014	Overall Progress: Exceed expectation / Steering Committee recommended nine shortlisted proposals and Technical Committee selected six proposals by March 2014
1.2 Number and type of activities conducted or supported by ICCTF secretariat for the project selection	Six capacity building programs on project proposal strengthening conducted for line ministries and CSOs	Overall Progress: Exceed expectation / Achievement / Seven capacity building programmes on strengthening project proposals were conducted for national stakeholders. The workshops focused on requirements and mechanisms as well as finance and administration of ICCTF Projects
1.3 Number of Climate Change Project selected, monitored, and evaluated	Impact Evaluation conducted at the end of projects (Health, Agriculture and Forestry) and shared with donors	Overall Progress: Partially Met / The ICCTF conducted impact evaluation for the three phase 1 projects. A second phase of project activity was delayed which meant that a further projects (Health, Agriculture and Forestry) closed in Q3 2014, so the impact evaluation period fell after project closing.

Key Points

Indicator 1.1: Number of proposals received

A – Output met expectation

To date ICCTF has conducted six pilot projects, three under a first phase and another three under a second phase. These projects covered all of its three thematic windows.

Table 1. Projects supported through ICCTF
Pilot Project Name/Description	Executing Agency	Total Budget	Expected Output	Project Sites
1) Research and Technology Development of Sustainable Peat Land Management to Enhance Carbon Sequestration and Mitigation of Greenhouse Gas Emissions	Ministry of Agriculture (MoA)	US$ 1,166,208	1) A scientifically-based policy and strategy on sustainable peatland management informed by accurate degraded peat land maps; 2) Improved / capacity of peat land research and management; and 3) Dissemination of information to stakeholders regarding the national programme on the utilization and management of peat land. In the second phase, the project aimed to improve the model for sustainable management of degraded peat land to mitigate greenhouse gas emissions and optimize crop productivity.	• Banjarbaru, South Kalimantan; / • Jabiren, Central Kalimantan; / • Muaro, Jambi; / • Pelalawan, Riau.
2) Extension of (1)	MoA	US$ 1,509,000		Expanded coverage to include the province of Papua
3) Energy Conservation and CO2 Emission Reduction in Industrial Sector (Phase 1).	Ministry of Industry (MoI)	US$2,035,966	Standard Operating Procedures, System Information Management of Energy Audit from each participating industry	18 cities all over Indonesia
4) Public Awareness, Training and Education Program on Climate Change Issue for All Level of Societies in Mitigation and Adaptation.	BMKG (the Agency of Meteorology, / Climatology, and Geophysics	US$1,127,917	radio programs, training for trainer modules for field extensions and educational module on climate change	Serdang Bergadai, North Sumatra; / Batu, Malang, East Java; Bau-Bau, / Sulawesi; Kamal Muara, North Jakarta; / Indramayu, West Java
5) Assessment and mapping of health vulnerability to the changing Dengue Hemorrhagic Fever (DHF) and malaria disease patterns induced by changing climate and develop / community-based adaptation measures	Ministry of Health	US$879,000	to tackle this threat / The expected outcome of this project is the increased capacity of health officials, officers and policy makers to design policies and make decisions based on additional information linking climate change, DHF/malaria and the distribution of vulnerable population.	21 districts and cities in five provinces (West Sumatera, DKI Jakarta, East Java, Central Kalimantan, and Bali).
6) Biomass energy in Madura. / Supports the enhancement of sustainable management of community-based wood pellets production as biomass energy to support low carbon economy and climate change mitigation in Bangkalan district in Madura province	Ministry of Forestry	625,000	1) Measurement of the CO2 net emissions on the demonstration plots of the ‘Biomass Energy Estate’ (area designated for biomass production,; 2) Establishment of a partnership for managing the wood pellet industry; and 3) Improvement of local socio-economic conditions through generation of alternative income source.
TOTAL		US$ 7,343, 091

All of the projects were completed. The Projects included in Phase 1 were been evaluated and audited by an independent auditor, while the projects included in Phase 2 have not yet had impact evaluations.
By 2013, as part of ICCTF’s effort to diversify support for climate change action in Indonesia, the ICCTF developed its Small Grant Programme (SGP) as a funding mechanism to support non-governmental organizations including Civil Society Organizations (CSOs), research institutions, and universities/academies. This mechanism is part of ICCTF’s long-term strategy to diversify the modalities of climate change programmes and to meet the needs of non-government based target groups.

The initial plan was to schedule the Call for Proposal in 2013, with a target of six small grant proposals. During the implementation, the Call for Proposal was delayed and it was finally announced in January 2014, with one month application period until February 2014. The ICCTF reported that the delay was caused by the Secretariat’s decision to prioritise the finalisation of the national ICCTF legal and operational framework, as well as more time in preparing the guidelines and other supporting documents.

The ceiling of funding for proposals was up to IDR 500 million (approx. US$45,000), with implementation starting by Q1 2014 and ending by the end of Q4 2014, meaning that the grants covered 6-8 months of activity. During the Call for Proposals period, the Secretariat received 196 proposals. In-depth assessment was conducted by an expert panel for each window, resulting in nine shortlisted proposals, three, for each window which were submitted to the Steering Committee in March 2014.

The following six proposals were agreed. The Letter of Agreement for all partners was signed in May/early June 2014 and ended in November 2014.

Table 2. List of ICCTF Small Grant Programme Projects
No	Title	Grantee	Location
1	Enhancing Carbon Sequestration in Community Forest	AruPA	Yogyakarta
2	Public-Private Partnership Model in Tackling Deforestation and Forest Degradation	Forestry Faculty – IPB	Bogor, West Java
3	Planning and Information System for Street Lighting Energy Efficiency	Politeknik ATMI	Surakarta, Central Java
4	Adaptation on Seaweed Aquaculture	Humaniora	Kendari, South East Sulawesi
5	Strengthening Climate Information System for Farmer and Fisherman	PIKUL	Kupang, East Nusa Tenggara
6	Strengthening Coastal Community Resilience through Participatory Multimedia Technology	BINGKAI Indonesia	Yogyakarta

The expectation and exit strategy of these small grant projects should have been clearer from the outset of the project. During the field visits, SGP Partners reported that the six-month project duration was insufficient. One respondent mentioned that the effective implementation of the project was even less due to some administrative issue, such as negotiation, contracting, and reporting. Additionally, partners were forced to adjust the cycle of activities in the targeted community such as planting and harvesting within the limited schedule. While the programme period is sufficient to implement the activities, additional time would have been useful to oversee the implementation and to provide support for initial troubleshooting.

Indicator 1.2 Number and type of activities conducted or supported by ICCTF secretariat for the project selection

A – Output met expectation

ICCTF conducted a series of workshops and meetings for projects assessment/selection for various stakeholder groups. The focus of the activities were determined based on needs as identified by ICCTF Secretariat.

As an example, in June 2013, the ICCTF secretariat conducted a workshop on adaptation project proposal development, which covered the development of an adaptation proposal starting from concept note through to the logical framework analysis. This workshop was relevant in light of ICCTF’s interest to access the UNFCCC Adaptation Fund.

In 2014, aligned with the plan to develop smooth transition from UNDP to MWA, the ICCTF focused their activities on capacity building programmes to develop project proposals for line ministries and CSOs.

Seven capacity building activities were conducted. The list includes support from ICCTF to the National and Regional Climate Action Plan (RAN-RAD GRK) Secretariat in organizing events and socialization of monitoring, evaluation, and reporting in three locations: East Nusa Tenggara, South Kalimantan, and North Maluku. These activities were aimed to improve stakeholders’ understanding of the monitoring, evaluation and reporting of regional climate action plan activities and to provide a simulation of GHG emissions reduction.

Other ICCTF activities supported the development of project proposals, as listed in the following table.

Table 3. Capacity Building Programme on Project Proposal Strengthening for Line Ministries and CSOs

Indicator 1.3 Number of Climate Change Projects selected, monitored and evaluated

A – Output met expectation

The agreement between DFID and UNDP requires impact evaluation of ICCTF-funded projects to be commenced six months or more after the end of the projects. The objective is for ICCTF to document the lessons learned in selecting projects, disseminating funding and monitoring the implementation of the projects. Three impact evaluations have been done for Phase I (2010 – 2012) projects. Based on the information from the secretariat and cross-checking with project partners, the evaluation for Phase II projects have not yet commenced as they only finished in late 2014 (less than 6 months ago).

The Impact Evaluation for the Phase I projects was implemented by comparing the before/after condition and analysing how the project interventions contributed to impacts. Summary findings are presented in the table below:

Table 4. Impact Evaluations for Project Phase I (2012)
No.	Project	Grantee	Highlights of Finding
1	Public Awareness, Training and Education Program on Climate Change Issue for All Levels of Society in Mitigation and Adaptation	BMKG[6]	The project did succeed in providing more information about climate change. However, the chosen method of using radio as the communication tool is ineffective because most farmers and fishers do not have radio. Therefore, there is no significant improvement on people’s knowledge about climate change. / The target to use extension workers as the main channel in communicating climate change related information to farmers and fishers is not effective due to the lack of knowledge of the extension worker. There were no enough activities to improve wider extension workers’ knowledge on climate change. / Climate change module for students cannot be mainstreamed into the national curriculum, but it can be used by teachers to enrich their perspectives and teaching materials. / Learning from the socialization done by BMKG, Bau Bau local government developed local socialization team comprising of local agencies and local media.
2	Research and Technology Development of Sustainable Peat Management to Enhance Carbon Sequestration and Mitigation of Greenhouse Gas Emission	Ministry of Agriculture	There are more resources with additional capacity to measure greenhouse gas emissions. However, there is no information on the implication of this results. / Identification of greenhouse gases emissions; / Four demonstration plots of low emission peatland areas were established in four provinces; / The income and knowledge of local communities are improved, especially related to climate change and peatland management. However, the additional income only occurs during the project period.
3	Implementation of Energy Conservation and CO2 Emission Reduction in Industrial Sector (Phase 1)	Ministry of Industry	The project can be used as reference for other similar industries to include energy efficiency principles into their business plan. However, there is insufficient data to confirm this. / Project data is no longer updated after project closure. / There is no further information/clarity on the follow up plan to conduct energy audit for the steel, pulp, and paper industries. Therefore the CO2 emission reduction cannot be monitored.
[6] Badan Meteorologi, Klimatologi dan Geofisika = Meteorology, Climatology and Geophysics Agency

The impact evaluation describes poor availability of baseline data, making it difficult to measure progress. The evaluation found that there were limited stakeholder consultation and involvement during the project design. As a result, the selection of activities were not suitable to answer the needs of the beneficiaries and lacked support from local stakeholders.

Regarding the Phase 2 project evaluations, the Secretariat explained a budget for these was not allocated in 2014 because all projects ended between August and November 2014 and the Impact Evaluation cannot be started until at least 6 months after the project closure. There was no information available on whether the evaluation will be budgeted for the next phase of the ICCTF programme. Clarification is also needed to understand the extent to which impact evaluation should be done for the small grant programmes. In this regard, the logframe should be targeted more towards outcome and impact, instead of input-based activities.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous Annual Report raised the need to develop a modified monitoring and evaluation approach suitable for the small grants programme. In response, the ICCTF Secretariat developed Project Management Guidelines to implement the Small Grant Programme which covers the entire cycle of project management: (i) planning; (ii) implementation; (iii) monitoring, reporting, evaluation, and audit; (iv) closing. Further field testing with partners would be useful to check whether the guidelines are suitable for small projects of this nature, particularly considering their limited duration.

Recommendations for future programmes
Although the ICCTF did successfully implement a small grant programme, the limited scale and duration of these projects raises questions about their value. From the evaluations conducted, it is not clear that the projects will have lasting impacts. The ICCTF should consider carefully the design of any future calls for projects to ensure that longer term sustainability of impacts is a key criterion.

ICCTF should evaluate the second round of projects, drawing together lessons learned (together with those from phase 1) in order to improve the quality of future projects.

To achieve the purpose of strengthening project proposals to meet the requirements under the thematic windows, it is recommended that capacity building programmes should also include technical aspects of proposals, not just administrative and management aspects.

At an administrative level, the ICCTF Secretariat should practise good management of supporting documents (e.g. Terms of Reference, notes of meeting, training modules) to support future monitoring and evaluation.

Output 2

Output Title	Functioning policy dialogue and increased awareness of ICCTF nationally and internationally
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target (2014)	Progress
Number and type of policy dialogue conducted	Six national policy dialogues conducted	Overall Progress: Met / Achievement 2014: / There were three national policy dialogues held in 2014: / Technical Policy Coordination Forum for Climate Change, June 2014 / Follow up meeting on Policy Coordination Forum, September 2014 / ICCTF NAMA Summit in September 2014 / Earlier reports counted ICCTF Steering Committee meetings as national policy dialogues, based on the fact that they bring together a wide range of national policy players. Although it is not clear that they meet the spirit of this target, we do not feel that we can change this retrospectively. Including these means that the target was met.
Number and type of awareness raising activities conducted	Implementation of awareness raising including: / Regular quarterly newsletter / Participation in COP / Media/journalist award/fellowship	Overall Progress: Completed / Achievement 2014: / ICCTF published 2 (out of 4) quarterly newsletters in 2014; / ICCTF attended COP 20 in Lima, Peru and organised two side events / ICCTF conducted ICCTF Media Fellowship 2014 in collaboration with AJI (Independent Journalist Alliance). / Note: / The ICCTF communication strategy is available for 2013 only

Key Points

Indicator 2.1: Number and type of policy dialogue conducted.

A - met expectation

As defined in 2014 log frame, a meeting can be considered as a “policy dialogue” when it encompasses a broad spectrum of climate change and development policy issues. The dialogue should aim to improve coordination and information sharing among ICCTF, GOI, development partners, CSO and private sectors. It may include SC meetings, policy coordination forums, workshop and discussion meetings. However, the log frame refers to national policy dialogue, differentiating these from other (presumably non-national) meetings. Inferring from the log frame, it is more suitable to define the term of “national policy dialogue” as “discussions conducted at national level involving stakeholders outside of ICCTF’s structures and programmes”.

The Secretariat of ICCTF submitted a list of 17 meetings in 2013 and 2014 classified as “national policy dialogues”. A number of these may not be deemed to be “national policy dialogues” either because the meeting was not attended by stakeholders outside of ICCTF’s structures and programmes or the meeting was not held at national level. However, earlier precedents suggest that meetings such as ICCTF Steering Committees could be counted, so it is not reasonable to apply a stricter interpretation retrospectively. With this caveat in mind, the programme met its targets. However, it is stretching credibility to count a meeting attended by two representatives of the Indonesia Business Council for Sustainable Development with one staff member from ICCTF Secretariat as a national policy dialogue, indicating that clearer definitions should be used in future, if output-based targets are used at all.

Indicator 2.2: Number and type of awareness raising conducted.

A – Output met expectation

ICCTF had a communication strategy for 2013. The latest Annual Report (2013-2014) mentioned that it was being revised, but a 2014 strategy was not seen. It is not clear whether activities conducted in 2014 also referred to the same communication strategy.

The first output under this strategy is the quarterly newsletters. In 2014, ICCTF has published two quarterly newsletters: Newsletter Issue 14 (January – March 2014[7], and Newsletter Issue 15 (April – June 2014,)[8]. The newsletter are published on ICCTF’s website, distributed at ICCTF events and sent to ICCTF donors. The Secretariat has not published newsletters for the periods of July – September and October – December 2014.
[7] http://www.icctf.or.id/download/newsletter/ 33e75ff09dd601bbe69f351039152189.pdf)
[8] http://www.icctf.or.id/download/newsletter/6ea9ab1baa0efb9e19094440c317e21b.pdf

As part of its international profiling activities, ICCTF has participated in a series of UNFCCC – COP Meeting since 2012. In COP 20 in Lima in 2014, ICCTF organized two side events in collaboration with Bappenas and GIZ. The first event, titled ‘Media and Climate Change: Lessons Learned and Best Practices‘, presented ICCTF’s collaboration with the media to promote public awareness on Climate Change. Two of four winners from ICCTF Media Fellowship Programme (one from Berita Satu TV and one from Tempo Magazine) shared their works and experiences on reporting about climate change impacts and the development implications. The other parallel event, titled “Indonesia’s Mitigation Framework: From Commitment to Implementation Progress” presented the review results and lessons learned from the implementation in forestry and land use sectors (REDD+) as well as energy and waste sectors. The second event also discussed the way forward of Indonesia climate change as well as the future of NAMAs, REDD+ and INDCs[9].
[9] Nationally Appropriate Mitigation Activities, Reduced Emissions from Deforestation and Degradation, and Intended Nationally Determined Contributions.

ICCTF also held several other awareness raising activities, listed below:

Table 5. ICCTF Awareness-raising activities
No.	Date	Programme	Participant	Objective
1	May 2014	ICCTF Media Fellowship 2014		The ICCTF Media Fellowship 2014 was held to support the mass media in educating public on climate change. At the end of the fellowship, the representative of three teams with the best media coverage will be facilitated by ICTTF to cover the UNFCCC-COP 20 in Lima, Peru. See the following link broadcast by AJI on the activity
2	7 May 2014	Launching of Media Fellowship 2014	AJI Jakarta, ICCTF, Editor and Journalist Senior, Media Fellowship candidates	Public Discussion and Launched Media Award on May 7th, 2014 in collaboration with AJI (Independent Journalist Alliance) Jakarta and followed by the launching of ICCTF Media Fellowship 2014.
3	30 May 2014	Announcement of Media Fellowship Winner on May 30th, 2014	AJI Jakarta, ICCTF, Editor and Journalist Senior, Media Fellowship candidates	The announcement of ICCTF Media Fellowship Award took held on May 30th, 2014 at ICCTF Office. The activity was conducted in collaboration with Alliance of Independent Journalist (AJI) Jakarta. The selection committees that consisted Senior Editor and Journalist from national media have selected 10 out of 61 proposals. The nominees for ICCTF Media fellowship 2014 are: five proposals from Printed Media; three proposals received from Online Media; and two from Television.
4	7 June 2014	First Workshop on ICCTF Media Fellowship	ICCTF, AJI, Media Team (Tempo, Berita Satu TV, The Jakarta Post, Kontan)	ICCTF and AJI Jakarta held the first workshop for 10 media teams coming from across Indonesia that have been chosen as the winners of ICCTF Media Fellowship 2014. The workshop discussed various of topics including adaptation and mitigation of climate change, environment service towards climate change mitigation, from HuMa Foundation, efficiency and tourism industry from WWF Indonesia, the study of health vulnerability as a result of climate change impact for malaria disease and dengue fever from Ministry of Health, tips on how to produce good and solid environmental journalistic works
5	24 June 2014	Donor and Journalist Visit to ICCTF-MoFor Project Site in Bangkalan, Madura on June 23-25	Donor and Media	Donor and Journalist Visits to Bangkalan of Madura were organized by ICCTF Secretariat on June 24th, 2014. The visits aimed to present Biomass Energy and Wood Pellet industry project to a wider audience and highlight lesson learned. Approximately 30 representations from media such as LKBN ANTARA, Tempo, Kontan, Jakarta Post, Jakarta Globe, and Jawa Timur Television (JTV), a member of Jawa Pos Group and donor representatives (UNDP, USAID, Millennium Challenge Account Indonesia (MCAI), Climate and Development Knowledge Network (CDKN), Embassy of Denmark, and GIZ)) participated in the event
				The coverage of donor and journalist visits can be accessed in the following links:
				ANTARA http://www.antaranews.com/berita/440896/berkah-kaliandra-berkat-pelet-kayu
				Kontan http://nasional.kontan.co.id/news/di-2015-bappenas-tambah-dana-iklim
				Kontan http://industri.kontan.co.id/news/wood-pellet-si-pengganti-batu-bara/2014/06/24
				Kontan http://nasional.kontan.co.id/news/icctf-kenalkan-proyek-wood-pellet-terintegrasi
				Tempo http://koran.tempo.co/konten/2014/06/30/345699/Memanen-Energi-dari-Kaliandra
				Jakarta Globe http://www.thejakartaglobe.com/news/madura-pioneering-eco-friendly-firewood
6	August - October 2014	Community Outreach to Kabupaten Kepulauan Seribu	Five schools in Jakarta; Community at Kepulauan Seribu; ICCTF Secretariat; Bappenas; Yayasan Terumbu Karang Indonesia (TERANGI) – a local organisation	ICCTF implemented a program called ‘Corals Adoption Corals with School Children’. The activities included the following activities: (i) socialization meetings on climate change and methods of adopted coral targeted to five junior high schools in Jakarta that specialized in marine and fisheries subjects; (ii) developing design adoption of coral; (iii) coral platform submersion activity by inviting a wider audience such as school students, teachers, and media
6	13 October 2014	Project Closure of Media Fellowship Awards on 13 October, 2014	Bappenas, ICCTF, AJI Jakarta, CSOs, Vice Ministry of PPN / Bappenas, Senior Advisor of Ministry of Forestry, etc.	ICCTF MEDIA FELLOWSHIP 2014 Closing Ceremony and Launching Book ' Media and Perubahan Iklim'

Summary of responses to issues raised in previous annual reviews (where relevant)

Response to previous Annual Report recommendations:
- In the 2014 AR, UKCCU suggested that ICCTF should improve dialogue with a wider range of stakeholders. ICCTF has approached universities and private sector representatives, although based on ICCTF’s notes, the discussions were more about membership of the Board of Trustees than wider climate issues. Also there is no record on whether any meeting with CSO and non-conventional development partners took place.
- The last AR recommended that communications activity should be more targeted and strategic. However, this seems unlikely to be the case in the apparent absence of a communication strategy for 2014.
- Some policy dialogues and awareness activities have included potential donors to ICCTF such as USAID, MCAI and CDKN, as suggested.

Recommendations for future programmes
- As discussed above and in other parts of this PCR, the project logframe should be designed more toward outcome and impact, not input;
- Clearer definitions and expectations of what is to be achieved are essential, e.g. what are the definition and success indicators for a national policy dialogue?
- It is important for ICCTF to have an ongoing strategy of communications and outreach.
### Output 3

Output Title	Capacity of ICCTF governance, and related stakeholders (Government of Indonesia and CSOs) developed
Output number per LF		3	Output Score	A
Risk:		High	Impact weighting (%):	45%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target 2014	Progress
Number and type of capacity development programmes for ICCTF and related stakeholder (GoI and CSOs)	10 capacity building activities conducted for ICCTF governance and related stakeholder (GoI and CSOs)	Overall Progress: Completed / Achievement: / Nine capacity development programs conducted: / One thematic workshop for GoI and CSO / NGO were conducted / Four strategic discussions on Trust Fund legal establishment, financing system, fundraising development and action plan with Bappenas, State Auditor and development partners / Four national and international conference/training participated by relevant Bappenas and ICCTF officer
Number and type of activities conducted to establish a fully staffed and functioning ICCTF national trust fund	The ICCTF Board established as legal Task Force under BAPPENAS and operational; / Executive Director mobilised; HR strategy revised; / ERP System operational; / 6 workshops and 3 conferences/seminars participated; / 3 training conducted; / Certification by an international audit firm conducted	Overall Progress: Met / Achievement 2014: / The Board of Trustees was established and met twice in 2014; / The Board was established as a Task Force (for state budget purposes) in November 2014. / 7 SOPs are in place and 6 are fully implemented. / New Executive Director was recruited and HR Strategy was revised. New staff are currently being recruited. / Enterprise Resource Planning (ERP) System is in place. The audit should verify whether the functions of both ERP Finance and HRIS are fully operational in 2014. / 8 workshops and 1 trainings conducted / 1 training for staffs conducted / International audit conducted by Morison International on findings and gaps of the operation. Findings yet to be published.

Key Points

Indicator 3.1: Number and type of capacity development programmes for ICCTF and related stakeholder (GoI and CSOs)

A – Output met expectation

Starting in July 2013, as part of its capacity development for stakeholders, ICCTF Secretariat conducted monthly thematic discussion/workshop for GoI representative and CSO/NGOs. The first discussion focused on provincial spatial plans to identify priority areas for mitigation activities, the second thematic discussion in August 2013 focused on the climate insurance projects to recognize the opportunities and challenges in developing climate insurance for the agriculture sector. In addition, ICCTF also held six workshops on codes of conduct (bylaws) and fund-raising development between relevant units of Bappenas and development partners. Capacity building activities are detailed in the table below:-

Table 6. Capacity Building Programmes
No	Date	Program	Participant	Notes
1	20 June 2014	Focus Group Discussion	See notes	ICCTF has conducted a Focus Group Discussion on thematic climate change issues: ‘Improving Information on Fish for Fisherman’. The discussion was attended by c. 50 participants from government and related stakeholders included local and international organizations working on fishery issues. The resource persons were included representative from Balai Pengembangan Observasi Laut (BPOL) of Bali; BPPT, Fakultas Perikanan & Ilmu Kelautan IPB, Ilmu Kelautan UNDIP Semarang.
2	3& 25 April 2014	Discussion on ERP Financial System on 3 & 25 April 2014	ICCTF Secretariat Staff	The discussion was intended to adjust and improve the ERP system, particularly on the following chapters: Face Form, Financial Section, Inputting tax, monthly expenditures. It is expected that the revisions on ERP system to be finalized by the end of April 2014 in order to allow the system be fully operated.
3	15-16 September 2014	Participation in the USAID Adapt Asia-Pacific Third Annual Forum 2014	Finance Manager, Head of Secretariat	Two senior staff of ICCTF attended a workshop on “Strengthening Country Systems to Access and Manage Climate Change Adaptation Finance in Asia and the Pacific” in Cambodia on 15-16 September, organized by UNDP. The Head of Secretariat presented Indonesia’s experience in financing a project related to climate change on behalf of Bappenas.
4	3 & 12 June 2014	Socialization on ERP training for human resources and program management	ICCTF Secretariat Staff	A meeting on ERP system hosted by the Secretariat to educate the ICCTF staff with the system with aimed on the familiarity of the staffs to operate on day-to-day basis. The ERP Human Resource Integrated System (HRIS) itself was expected to be fully functioning by June 2014.
5	18-20 June 2014	Results-based Monitoring (RBM) Trainings	All ICCTF Secretariat Staff	UNDP Jakarta Office facilitated a training to develop the capacity of ICCTF staff and executing agencies (MoFor, MoA, MoH) as well as project management unit of Small Grant Programs in implement provision of Results-based Management.
6	15-17 October 2014	Strategic meeting and team building of ICCTF Staff	ICCTF, Bappenas, GIZ	A three-day workshop conducted to: (i) provide the ICCTF staff and its partners with a common understanding on the goal of ICCTF as a national trust fund; (ii) enhance communication between ICCTF and all relevant stakeholders; and (iii) discuss milestones of ICCTF beyond 2014. / Over 30 participants attended the event with presentations made on Current Status of ICCTF, ICCTF Future Plan, and ICCTF Landscape: Assessment of Function as well as discussion on Developing Action Plans and Milestones.
7	22 October 2014	Workshop on ICCTF funding mechanism	ICCTF, Bappenas, GIZ, Ministry of Finance, Consultant GIZ	ICCTF in collaboration with BMUB-GIZ organized a half-day workshop to discuss ICCTF funding mechanism. The objective of this workshop was to obtain feedback and input from relevant stakeholders from funds, fiscal policy Directorate under Ministry of Finance on fund flow mechanism. Approximately 37 participants attended the workshop
8	27-31 October 2014	AMI Training Programme GM 5" Effective Capacity Development - Making Change Happen"	Planning, M&E Manager	The training sponsored by GIZ as part of capacity building of ICCTF staff. Four-day training aimed to provide the managers and senior staff on how to access the capacity situation of stakeholders and how to design a capacity development strategy. The training provider was AMI Asian Management Institute Ltd.
9	17-19 December 2014	Workshop to discuss Annual Work Plan 2015	ICCTF, CDKN, Bappenas, GIZ	ICCTF organized a-three-day workshop to discuss 2015 annual work plan and procedures related to the use of government state budget (APBN). Some representatives from CDKN, BMUB-ICCTF project, and Bappenas (Multilateral and Bilateral Development Funding, Pejabat Pembuat Komitmen/Commitment Making Officer) were invited to share their upcoming work plan and activities. Other agendas including fundraising strategy and Green Climate Fund requirements were also discussed during the workshop.

Indicator 3.2: Number and type of activities conducted to establish a fully staffed and functioning ICCTF national trust fund

A – Output met expectation

3.2.1 The development of the Board of Trustees

The National Trust Fund was established based on Ministerial Decrees on the Board of Trust Funds, and on the membership of the Board, which were enacted in April 2014. These two decrees formed the legal basis for the establishment of ICCTF. The Board of Trustees was established in June 2014 and met twice in 2014.

Prior to the first Board meeting, the ICCTF Steering Committee members and the newly appointed Board members representing non-government and civil society groups met on June 13, 2014 to plan the first Board meeting. In an effort to accelerate the understanding and knowledge of the new members, the ICCTF Secretariat assisted these members in the preparation for the meeting.

The first meeting of the Board (June 27, 2014) was to introduce Board members to their roles and responsibilities and to update them on progress of ICCTF activities and transition milestones. The meeting decided to approve Bank Mandiri as the Fund Manager and to formally appoint the Executive Director. The second meeting (October 3, 2014) endorsed the business plan and its fundraising strategy. However, it could not decide the endorsement of the Bylaws due to the low number of board members attending the meeting. Concern about the lack of attendees was raised by Coordinating Ministry of Economic Development and as result a quorum of 50% of board members+1 (i.e. 6 out of 11 members) for decision making was agreed.

The Bylaws adoption process consists of a series of email discussions, technical meetings and consultation with each Board members for almost a month before it was finalized in November 2014 The Task Force was also established under Bappenas. The allocation of government state budget (APBN) is IDR1.5 billion (US$1.25m), mainly for staff salaries and other routine operational expenses.

To support its operation as Trustee, ICCTF has launched seven Standard Operating Procedures (SOPs): project management, monitoring and evaluation, financial, purchasing goods and services, information technology & communication, human resources, and asset management. Most of the SOPs are fully implemented, except the financial one that required adjustment due to the transition of the Board to its formal status asTask Force.

ICCTF is currently experiencing challenges to its decision making process. Up to now, this can largely be explained by the disruptive effect of the transition to a new government in November 2014 which entailed significant changes and uncertainty for Bappenas, including the departure of a key Minister (Pak Lukita) who had been an important figure in ICCTF’s development. To avoid losing momentum, it is important that ICCTF activity resumes as quickly as possible, in particular to re-establish the meetings of the Board so that key decisions can be taken.

There are some indications that the role of the Board of Trustees may need to adjusted, in particular with regard to the time commitment needed for members. In retrospect, it may have been unrealistic to expect senior government representatives to engage. Whilst the similar arrangements were used during the interim ICCTF phase, it should be noted that the work load of Steering Committee at that period was different from that expected from the Board during the full implementation of the Trust Fund. As the first government-funded National Fund Entity on Climate Change, it is to be expected that ICCTF governance may need to be reviewed periodically.

A National Fund Entity manages the influx of bilateral and multilateral climate change finance, but its role does not stop there. It should be able to match the provisions of these financing to Indonesia’s climate change development plan, policies and financing priorities. Since the funding may come in different type and requirement, it is necessary to ensure that the decisions on funding disbursement could be taken in flexible timeframe, so the Trustee should expect to take timely management decisions.

The ICCTF could potentially learn from the Green Climate Fund (GCF) which distinguishes the Board and the Trustee. Its Board consists of government representatives, thus it can be considered similar to the ICCTF. However, the Board acts as a Steering Committee, overseeing the management of the Trustee - the World Bank. The World Bank has the mandate to decide beyond operational matters, including matching financing to programmes. As a Trustee it will report to the Board. In this way, strategic decisions regarding fund disbursement and other routine tasks do not have to wait until the Board meets. The Board also monitors and evaluate the performance of the Trustee.

3.3.2 Human Resources and Enterprise Resource Planning (ERP) Systems

The ICCTF Executive Director (ED) was formally appointed by the Board with a six month probation contract. His contract was extended for a further two months under Bappenas until February 2015 to bridge the government staff recruitment procedure currently on going. His contract was terminated in April 2015 due to his performance in fundraising. The new ED is appointed in late April 2015 with the strong objective on fundraising.

In order to ensure high standards of operation, ICCTF has developed systems of Enterprise Resource Planning (ERP) in two areas: Finance and Human Resource. The effective use of the ERP systems will support ICCTF staff. Currently the ERP Human Resource Integrated System (HRIS) is finalized and ICCTF staff are being familiarized with this system, while the ERP Finance system is undergoing adjustment and improvement.

3.2.3 Training/Conference Participation

In 2014, ICCTF Staff participated in one workshop and two training activities. Their participation was designed to increase their knowledge and capacity as well as to expand their network in the climate change community. One of the training events on Result-based Monitoring for the project management was delivered in-house, while the other events were held externally.

Table 7. List of Workshop/Training/Conference Participated
No	Date	Program	Participant	Objective
1	15-16 September 2014	Participation in the USAID Adapt Asia-Pacific Third Annual Forum 2014	Finance Manager, Head of Secretariat (representing Bappenas)	Participation in the USAID Adapt Asia-Pacific Third Annual Forum 2014 in partnership with UNDP “Strengthening Country Systems to Access and Manage Climate Change Adaptation Finance in Asia and the Pacific”. A senior staff of ICCTF (Finance Manager) attended the two-day workshop in Cambodia on 15-16 September. In addition, the head of ICCTF Secretariat (Bappenas) presented Indonesia’s experience in financing a project related to climate change.
2	18-20 June 2014	Results-based Monitoring (RBM) Trainings	All ICCTF Secretariat Staff	Human resource capacity development of ICCTF staff and executing agencies (MoFor, MoA, MoH) and project management unit of Small Grant Programs through provision of Results-based Management Training (RBM) which was facilitated by UNDP Jakarta Office
3	27-31 October 2014	AMI Training Programme GM 5" Effective Capacity Development - Making Change Happen"	Planning, M&E Manager	The training was sponsored by GIZ as part of capacity building of ICCTF staff. Four-day training aimed to provide the managers and senior staff on how to access the capacity situation of stakeholders and how to design a capacity development strategy. The training provider was AMI Asian Management Institute Ltd.
4	1-12 December 2014	UNFCCC Lima Climate Change Conference	ICCTF, Bappenas	An event titled Indonesia’s Mitigation Framework: From Commitment to Implementation Progress was held to present the review results and lesson learned from the implementation in forestry and land use sectors (REDD+) as well as energy and waste sectors. The event also undertook inputs and views on how Indonesia could develop and improve its future NAMAs, REDD+ and INDC.

3.2.4 Audit

An internationally-compliant audit had been executed by Morison International, focusing on the ICCTF fiduciary management. This is an internal report and is not published, in line with Bappenas regulations. A further independent audit of ICCTF will be commissioned by the State Auditor, and this will form part of the financial report to be received by DFID as part of the final report on ICCTF.

Summary of responses to issues raised in previous annual reviews (where relevant)

Progress occurred in refer to the previous Annual Report recommendations:
- Appointment of Bank Mandiri as National Fund Manager is done and endorsed by the Board in its first meeting.
- Interim recruitment of the Executive Director is complete and permanent recruitment using government procurement is underway.
- Full set of Board members are in place and meetings have been conducted twice in 2014.
- A project to assess the accessibility of ICCTF to global funds such as adaptation funds and GCF is being prepared with support from CDKN.
- A business plan and fundraising strategy were finalized and endorsed by Board in their second meeting.
- Establishment of legal task force unit to manage funding that comes from State Budget has taken place.
- From the ICCTF and project documentation collected, it appears that UNDP did not devote full time staff to ensure a smooth transition process. These been discussed several time between UKCCU and UNDP, including through previous annual review recommendations but action was not taken by UNDP.

Recommendations for future programmes

As mentioned above, it is important that the ICCTF Board begins to meet regularly, in order that timely decisions can be made by the Trust Fund. If it becomes apparent that the time commitments of Board members limits the performance of the Board, it is recommended that ICCTF learn from the structures and modalities of other climate change financing trust funds such as the GCF.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

The project was approved in 2010 and does not have a Business Case. It does have a submission to the then Head of Office, for the initial support of GBP 4.7 million. This does not include a programme timescale. Therefore the references used here are the Annual Reviews written in 2013 and 2014.

Key cost drivers and performance

The project costs are within the budget however spending over the lifetime of the project has been slow (with no-cost extensions to 2013 and then 2014) and there are unspent funds in end 2014 of approx. GBP 400,000.

Table 8. ICCTF budget summary

 VfM performance compared to the original VfM proposition in the business case

There were no specific vfm indicators for UNDP in the Submission. DFID’s funds were merged within a multi-donor programme so specific vfm metrics for our funds are not available. Some key programme parameters are assessed against DFID’s vfm framework below.

Economy (inputs at the right price)

The main cost drivers for the programme came from (i) UNDP’s administration fees, (ii) the cost of sub-projects funded through the PREP-ICCTF programme, and (iii) all other the costs including establishing the ICCTF secretariat, communications etc.

(i) UNDP’s administrative fees of 7% are in line with national and international benchmarks.

(ii) After deduction of UNDP’s fees, 85% of the remaining funds were spent on sub-projects. These were delivered by a range of competitively selected public sector partners, universities and civil society organisations following calls for proposals. The sub-projects funded by ICCTF went through a rigorous selection process including screening by the ICCTF secretariat, the ICCTF technical committee, and final decision by the ICCTF Steering Committee. UNDP as the fund manager exerted an advisory role in deciding on those sub-projects, and ensured project proposals and work plans and institutional arrangements met UNDP standards before funds could be transferred.
For ICCTF, UNDP bore a greater share of project costs that is normally the case. The Letter of Arrangement between UNDP and DFID states that all direct costs of implementation will be borne by a given project as identified in the project budget. However, UNDP decided to charge all the direct project support costs to the UNDP country office. This included the direct technical support to the Secretariat in helping them to prepare documents, organize meetings and implement project-specific activities, as well as the costs of going on monitoring and evaluation missions and ICCTF workshops. This meant that the project funds were not used for UNDP’s direct implementation cost. In other comparable programmes such day to day technical support costs are charged as direct costs.
(iii) the remaining 15% of funds were spent on establishing and running secretariat, conducting training and capacity building for staff, communication, monitoring and evaluation etc. For services delivered by external consultants, UNDP has a global template for setting fees for consultants. This is adjusted to the country context based on local market and price surveys. Each category of consultant has a different range of fees based on educational background and years of experience. Once a project TOR is prepared, the level of expertise required to deliver results is determined with reference to the degree of complexity of the assignment. Fees will then be based on the education and experience of the consultant in line with the rates established for different educational attainment and years of experience. Cost assessment is then based on the price proposal of the selected candidate against the fee rate that had been established by UNDP.

Efficiency (converting inputs into programme outputs) and Effectiveness (outputs leading to outcomes)

The ICCTF programme did not have a Theory of Change, and as noted above, its logframe was heavily dominated by output-based indicators. So there is not a clearly articulated sequence linking inputs to outputs and then to outcomes and impacts. However, as can be seen from the logframe, the overall objective of the ICCTF programme was to enhance the GoI’s leadership on climate change by establishing a national climate change trust fund. This in turn, was to be achieved by a “learning by doing” process through the selection, funding and implementation of a range of climate change projects, supported by capacity building for relevant units in GOI and the development of an underpinning regulatory framework. The interim trust fund platform was to be managed by an external party (UNDP) and handed over to GOI once all the preparatory steps had been achieved.
The programme has successfully delivered results through the chain of processes outlined above, meeting relevant logframe targets. It is clear that the original programme design greatly under-estimated the time taken to complete this task, but nonetheless, the desired outcomes and impacts have been achieved. The programme must therefore been seen as performing satisfactorily in vfm terms against the efficiency and effectiveness metrics.

Assessment of whether the programme represented value for money

Based on the assessment above, yes, it did represent value for money

Quality of financial management during programme

As described in Section H below, ICCTF accounts were approved without qualification by the state auditor.

UNDP operates to internationally compliant standard of financial management. UNDP regularly submitted certified audit reports on the programme, most recently:

Date of last narrative financial report	June 2014
Date of last audited annual statement	June 2014

A final financial report will be submitted within 6 months of project close.

E: RISK

Quality of risk management over the life of the programme

At the beginning of the project, the main risk described in the Submission was whether ICCTF will be ineffective or will fail. It also included risks about ICCTF’s influence over government policy or action on climate change as well as the risk of only a few development partners being interested in contributing to ICCTF. The overall level of risk was judged to be Medium-High. Those risks remained the same until 2012, and other risks were identified in the 2013 Annual Review. Concerns regarding establishment of other climate change trust funds (MCA and FREDDI) emerged and required ICCTF to address these issues.

Despite the successful delivery of a functioning trust fund, risks around the influence over government policy and action remain, and should continue to be addressed by ICCTF.

More recently risks have centred on securing sustained funding beyond December 2014. This was addressed in ICCTF’s Business Plan for 2014 – 2020, finalised in November 2014, most directly through the fundraising strategy. Current indications suggest that both DFID and USAID intend to place additional funds into the TF, which is a positive start. This aspect should remain a focus for ICCTF to ensure its long-term success.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

This was weak. At the time of the project submission (for approval of the initial tranche of GBP 4.7 million), UNDP’s project documents suggested that the project activities would be completed over 2010 and early 2011, with establishment of the Trust Fund by mid 2011 and project close by mid 2012. This was clearly not achieved, and the project was extended on three occasions before its eventual close in December 2014. This delay was due to the procedural difficulties in establishing key structures, exacerbated by changes to national legislation in 2011 which required additional preparatory work. As the first of its kind in Indonesia, ICCTF was subject to particularly strong scrutiny. High staff turnover during the later preparation stage led to shifting priorities in activities and changes in ICCTF management structures. Concerns were also raised by donors about the level of support offered by UNDP for the ICCTF secretariat. However, despite many requests that UNDP should dedicate greater staff time for ICCTF, donors felt that this was not adequately addressed right up to the end of the project.

Performance of partnership(s)
UNDP delivered this project in partnership with the Government of Indonesia, with resources from DFID and other donors. By project close, the key objectives had been delivered, so ultimately this should be judged a successful partnership. However, donors were dissatisfied on many occasions by the slow delivery of the programme, indeed one significant donor (AusAid) resigned from the Steering Committee and withdrew entirely from the project as a result of their frustrations. With hindsight it can be seen that many of these problems arose because of unrealistic expectations regarding the time it takes to deliver a novel and complex programme of this nature, so all parties – donors, UNDP and GOI – could learn lessons about setting realistic objectives when initiating future programmes of this nature.

Asset disposal and value obtained by DFID

All Project assets and services were procured in line with applicable UNDP rules and regulations. Throughout the life of the project, assets used by the GoI remains the property of UNDP. In principle, UNDP will hand over the assets to Bappenas upon closure of the project. This will be covered by UNDP’s project closure report, due six months after project close.

H: MONITORING & EVALUATION)

No DFID evaluation of ICCTF is planned.

The ICCTF’s monitoring and evaluation (M&E) system includes six criteria that apply to projects and programmes but they do not all have to be used in every case. These criteria are: efficiency, effectiveness, impact, transparency, relevance, and sustainability. These are designed to inform present and future decisions on projects and programmes by all stakeholders.

In the most recent reporting period, the following methods of monitoring and evaluation were undertaken: financial audit, financial spot check, programmatic monitoring, and internal evaluation of project progress.

Financial Audit
An independent financial audit process for Bappenas as the Implementing Partner for the Preparatory Arrangements for the Indonesia Climate Change Trust Fund (PREP-ICCTF) was conducted by the State Auditor for ICCTF’s Fiscal Year 2013 and the report was published on March 2014. The audit covers internal controls including financial reporting, project implementation management, compliance with UNDP’s rules, as well as checks and evaluation on the design and effectivity of the internal management controls. The audit concluded that the Implementing Partner of PREP-ICCTF had effectively complied with the internal control as stipulated by the UNDP.

Financial Spot Check
In June 2014, financial spot checks was performed to the Phase II of ICCTF funded projects with the line ministries: Ministry of Agriculture, Ministry of Forestry and Ministry of Health. The objectives of this spot check were: (i) to review financial reporting (fairness of expenditure and test of detail as necessary in ensuring appropriate and accountable use of resources towards achievement of projects objective); (ii) to ensure that Guidelines and SOP for ICCTF Project Funded is fully implemented; (iii) to follow-up the findings from State Audit 2014.

Programmatic Monitoring
Monitoring visits were conducted both for projects with the line ministries and the small grants projects. The objectives of this instrument is to capture the overall progress of the project as well as to obtain information from the project including to perform spot check to the field. In addition, the visits aimed to identify the gaps in project implementation. In 2014, monitoring were done to projects of Ministry of Agriculture, Ministry of Forestry and to a small grant project for seaweed cultivation in Southeast Sulawesi. The monitoring of the SGP was commenced in June 2014 and was designed to (i) gather baseline data to be used for monitoring and evaluation; (ii) conduct monitoring to check the readiness of the program implementation as well as to document the initial conditions before the implementation of the program; (iii) ensure project guidelines can be followed (iv) check the proper location of project activity; (iv) check the acceptance of local people/communities regarding the project implementation within their area.

Internal Evaluation of project progress

An internal evaluation meeting was conducted with an external research institute and was designed to review the progress of the Ministry of Health project. The meeting concluded with the following outcomes: (i) finalization of upcoming activities including field monitoring to some project sites; (ii) plan for expenditures until August 2014; (iii) plan for publication and dissemination of the result of projects.

The above monitoring and evaluation instruments were focused on tracking progress made by the projects and the capacity of the implementing partner to run the project. In this regard, the design lacks instruments to measure the objectives of ICCTF’s investment strategy in contributing to the reduction of greenhouse gas emissions. This commitment is outlined at the beginning in the project selection criteria where, among others, ICCTF’s funded projects must contribute to the national priorities as described in the mid-term development plan. Therefore, it is very important to use GHG inventory and monitoring systems to measure the overall contribution of the ICCTF to the objective as well as to measure the impact of programmes and their alignment to overarching climate change commitments in Indonesia. This is an important action for ICCTF in the future, to ensure that project results can be seen to contribute to relevant provincial level plans (RAD-GRK) and the national level plan (RAN-GRK). This will be of critical importance to international donors considering potential contributions to ICCTF in the future.

PROJECT COMPLETION REVIEW

This review was written by Paul Chambers, Senior Energy Adviser, UKCCU. The author met with Beate Trankmann, UNDP Country Director and colleagues.

Research and input was carried out by Smita Notosusanto, Gustya Indriani, Dwi Rahardiani and Eka Melisa of Oxford Policy Management Limited, under contract to UKCCU.

OPML conducted:-
- Desk review of relevant documentation
- Consultations with the main programme partners - BAPPENAS, the ICCTF Secretariat, and the United Nations Development Programme (UNDP);
- Discussions with relevant UKCCU team members;
- Meetings with selected beneficiaries of ICCTF (i.e. Ministry of Industry, Ministry of Forestry, Ministry of Agriculture) and small grant project partners;
- Meetings with Steering Committee members.

List of interviewees
No	Name of Respondents	Title/Institution
1	Ida Suriany	Deputy Programme Manager, UK Climate Change Unit
2	Noorsalam Nganro	Executive Director, ICCTF Secretariat
3	Bjoern Firscher	Finance Director, ICCTF Secretariat
4	Rudy Hartono Sabri	ICCTF Secretariat
5	Achmad Zaky A.	Sutri-NAMA, GIZ
6	Ario	Sutri-NAMA, GIZ
7	Dwi Nugroho	Direktur, Perkumpulan ARUPA
8	Budhi Sayoko	UNDP
9	Tomoyuki Uno	UNDP
10	Minyoung Kim	UNDP
11	Didi Mardjimi	Consultant, UNDP
12	Syamsidar Thamrin	Bappenas
13	Ni Komang Widiani	Planning, M&E Associate, ICCTF Secretariat
14	Amin Budiardjo	Former National Manager at ICCTF Secretariat
15	Sri Lasmi	Head of sub-Directorate for Right-based Forest and Partnership Development, Ministry of Forestry
16	Daru Asycarya	Consultant, Ministry of Forestry
17	Endang	Consultant, Ministry of Forestry
18	Fabby Tumiwa	Member of MWA from CSO IESR
19	Agus Purnomo	Former member of ICCTF SC from DNPI (National CC Council)
20	Haryadi Himawan	Former project manager at Ministry of Forestry
21	Kyai Irham	Community leader, Bangkalan
22	Noeryanto	Extension worker, Bangkalan
23	Sarupan	Farmer, Bangkalan
24	Fajar	Perkumpulan ARUPA
25	Sugiyono	Head of farmer group Jasema, Terong Village
26	Rubikem	Head of women farmer sub-group, Terong Village
27	Sugiran	Hamlet coordinator, Terong Village
28	Nur	Member of farmer group Jasema, Terong Village
29	Yatmi, Sarti, Sokiyem, Sudiyati, Miyati, Ponijem, Painah, Tini, Parmisih, Wagisah, Dalmi	Members of women farmer sub-group, Terong Village
30	Aries	Perkumpulan Bingkai
31	Pahing	Senior fisherman, Drini Village
32	Yanto	Secretary of fishermen group, Drini Village