## Logframe
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Yemen Social Protection Programme (YeSP)
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021) |  | Assumptions
Reduction in extreme poverty and vulnerability in Yemen | Percentage of ECTP and SFD beneficiaries in IPC 3 and IPC 4 districts (a) ECTP (b) SFD (c) SFD CfN-Covid-19 | Planned | NA | (a) 96% (b)70% (c)70% | (a) NA (b)70% (c)NA |  | SFD uses different targeting indicators for the CfN and CfW other than the IPC. Districts for Nutirion are selected based on the malnutrition, density of unmet needs (defind list of nutrion sub-cluster), availability of health and therapeutic services. IPC indicators are updated, so the district IPC level may change with the next update
Achieved
Source
SFD Bi-annual Reports, SFD Cash for Nutrition Programme Report & UNICEF PC8 and PC9 Report
OUTCOME | Outcome Indicator 1 |  | Baseline (Dec 2019) | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021) |  | Assumptions
Yemen's remaining social protection institutions are preserved and strengthened to provide income protection and increase the resilience of the most vulnerable | Percentage of SFD's Crisis Response Plan funded | Planned | 56% | 70% | 10% (from the new strategy) |  | Conflict situation does not deteriorate and SFD is able to continue programming in all governorates. Covid-19 does not affect SFD programming or instiutional capacity or implementation. Conflict situation and Covid-19 does not affect ECT operations Other donors continue to fund social protection in Yemen. DFID continues to advocate for social protection funding in Yemen. Humanitarian needs do not increase. Donor pressure and incentives are sufficient to deliver meaningful reform of social protection and humanitarian cash programming. DFID attribution of results will be calculated by SRO and PM each calendar year according to DFID % contribution to overall funds. CRP II activites will be automatically rolled over into CRP III in 2021 Price of food items don't increase due to inflation and currency exchange fluctuations Purchasing on credit can also refer to trust from the supplier to give sampled beneficiaries food on credit and therefore, beneficiaries access to food. Also buying on credit is a habit and not neccessirly correlates to a change in behaviour becasue of the cash assistance. Security situation allows for data collection in the targeted areas (due to security situation in the targeted areas for the CfN-COVID-19 response it might be difficult to conduct sample data collection as security forces sometimes prevent data collection.
Achieved
Source
SFD Bi-Annual Reports
| Outcome Indicator 2 |  | Baseline (Dec 2019) | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Percentage of beneficiaries surveyed who state (i) 'highly satisfied' or (ii) 'satisfied' with ECTP support or 'satisfied' or 'very satisfied' with SFD's SSN payment/support (a) ECTP (b) SFD (c) SFD CfN-Covid-19 | Planned | (A) i. 46%, ii.53% (b) 86% (not disaggregated in former survey), (c) NA | (a) i. 35%, ii. 60% (b) i. 35%, ii. 55% (c) i. 35%, ii. 55% | (a) i. 35%, ii. 60% (b) i. 35%, ii. 55% (c) NA
|  | Achieved |  | (a) i. 48%, ii. 51%, (b) i. 17%, ii. 77%, (c) i. 47%, ii.
Source
SFD Bi-annual Reports, SFD Cash for Nutrition Programme Report & UNICEF PC8 and PC9 Report
| Outcome Indicator 3 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Percentage of sampled ECTP and SFD beneficiaries reporting to purchase food on credit once a week (a) ECTP (b) SFD (c) SFD CfN-Covid-19 | Planned | (a) 21% in PC7 (b) NA, (c) NA | (a) 20% (b) 50% (c) 50% | (a) 20% (b) 50% (c) NA
|  | Achieved |  | (a) 19% (b) 81% (c) 81%
Source
SFD Bi-annual Reports, SFD Cash for Nutrition Programme Report & UNICEF PC8 and PC9 Report
| Outcome Indicator 4 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Percentage of sampled beneficiaries report decreasing the daily number of meals eaten at least once a week (a) ECTP (b) SFD (c) SFD CfN-Covid-19 | Planned | (a) 21% in PC7 (b) NA, (c) NA | (a) 20% (b) 30% (c) 30% | (a) 20% (b) 30% (c) NA
|  | Achieved |  | (a) 23% (b) 15% © 35%
Source
SFD Bi-annual Reports, SFD Cash for Nutrition Programme Report & UNICEF PC8 and PC9 Report
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR)
SRO 0.3, PM 0.6
OUTPUT 1 | Output Indicator 1.1* |  | Baseline (June 2019) | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021) |  | Assumptions
SFD and WB/UNICEF ECTP deliver responsive social protection that increases the resilience of the most vulnerable households in Yemen | Total number of beneficairies of SFD Cash for Work beneficiaries (Total number of i. women, ii, IDPs) | Planned | 310,688 (i. 25%, ii. ) | 60,328 (i. 30%, ii. 20%) | Target to be confrimed at end of 2020 |  | District outreach depends on availability of SFD funds Cash transfer for Nutrition COVID-19 is based on the assumption that DFID will provide additional funding to reach the target Cash distribution per HHs are average figures - not based on monthly transfers but as a total for the HH - similarly with the CfN the amounts are averages for the whole duration of the project Disability data for output 1.7 will be collected and reported on anecdotally DFID attribution of SFD results is calculated at 14.2% *SFD's results are reported on a cumulative basis. For output indicators 1.1, 1.2 and 1.3, an estimated target for Milestone 1 has been calculated on the assumption that the results counted in 2020 (cumulative total minus baseline amount), will be split evenly across the calendar year. SFD report on a calendar basis in their management information system and this does not align with FCDO annual review timelines, therefore we have split the annual achievement and the Sept 2020 result will be reviewed in the AR (which reflects results achieved between July 2019 -June 2020). We have included the December 2020 cumulative target and we will check the actual results achieved against this in the first quarter of 2021. We will be receiving disaggregated data against these indicators by geography, age, gender, disability
Dec 2020 (cumulative)
401,180 (i. 30%, ii. 20%)
|  | Achieved |  | 37,955 (i. 27%, ii. 14%)
367,930 (i. 27%, ii. 14%)
Source
Jan 2019 to June 2019 SFD Progress Report (baseline), 2019 Annual Report and Jan 2020 to June 2020 Progress Report (Sept 2020 target), 2020 Annual Report (Dec 2020 target)
| Output Indicator 1.2* |  | Baseline (June 2019) | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Number of Village Saving and Loan Associations groups formed and activated by SFD | Planned | 84 | 77 | Target to be confirmed at end of 2020
Dec 2020 (cumulative)
200
|  | Achieved |  | 9
216
Source
Jan 2019 to June 2019 SFD Progress Report (baseline), 2019 Annual Report and Jan 2020 to June 2020 Progress Report (Sept 2020 target), 2020 Annual Report (Dec 2020 target)
| Output Indicator 1.3* |  | Baseline (June 2019) | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Number of MF loans issued by SFD (Total number of women) | Planned | 35,643 (36%) | 6,238 (40%) | Target to be confirmed at end of 2020
Dec 2020 (cumulative)
45,000 (40%)
|  | Achieved |  | 34,218 (32%)
51,036 (26%)
Source
Jan 2019 to June 2019 SFD Progress Report (baseline), 2019 Annual Report and Jan 2020 to June 2020 Progress Report (Sept 2020 target), 2020 Annual Report (Dec 2020 target)
| Output Indicator 1.4 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Total number of CSSF-funded (i) SFD COVID-19 response Cash for Nutrition beneficiaries (Total number of mothers of children with disabilities) and (ii) Cash for Nutrition beneficairies from wider programme | Planned | n/a | NA | (i) 21,000 (1%) ,(ii) 36,462
|  | Achieved |  | NA | 23118
Source
SFD Cash for Nutrition Quarterly Report and Completion report
| Output Indicator 1.5 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Number of districts reached with ECTP and SFD cash assistance (both DFID and non-DFID attributable) (a) ECTP (b) SFD (c) SFD CfN-Covid-19 | Planned | (a) 333 (b) 218 (c) NA | (a) 333 (b) 278 (C)7 | (a) 333 (b) 278 © NA
|  | Achieved |  | (a) 333 (b) 278 ©tbc
Source
SFD Bi-annual Reports, SFD Cash for Nutrition Programme Report & UNICEF PC8 and PC9 Report
| Output Indicator 1.6 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Amount of cash distributed (DFID funding only) to ECTP and SFD beneficiaries in US$ (a) ECTP (per month) (b) SFD Cash for Works (per project) (c) SFD CfN-Covid-19 (per month) | Planned | (a) NA | (a) 12 (b) 533 (c) NA | (a) 12 (b) 533 (c) 33
|  | Achieved |  | (a) 11.94 (b) 595 (c) NA
Source
SFD Bi-annual Reports, SFD Cash for Nutrition Programme Report & UNICEF PC8 and PC9 Report
| Output Indicator 1.7 |  | Baseline (PC7) | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Number of ECTP beneficiaries paid in Payment Cycle 8 (% female) | Planned | 1422413 | 1.5m (45%) | 1.5m (45%)
|  | Achieved |  | 1,435,529 (48%)
Source
UNICEF PC8 and PC9 Report
IMPACT WEIGHTING (%)
50%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
SRO 0.3, PM 0.6
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021) |  | Assumptions
Institutional strengthening of SFD | MIS developments in place (a) gaps identified, (b) TBC based on specific steps outlined in MIS report (to be confirmed and agreed with SFD) | Planned | n/a | (a) complete (b) TBC | (a) NA (b) TBC |  | Unique beneficiary identifiers are available for SFD beneficiaries from cash transfers - issuing unique identifies in the form of national IDs will require working with civil registration offices, building their capacities to reach population and cover the cost of issuing the ID cards for beneficiaries COVID19 doesn't affect SFD's operations and beneficiaries ability to obtain national IDs Security situation allows beneficiaries to get national IDs Inclusion strategy, DFID to fund and support SFD develop inclusion strategy
|  | Achieved |  | (a) Complete (b) NA (c) 5 (d) 1
Source
?
| Output Indicator 2.2 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Robust risks management processes in place (a) Risk management lead appointed (2020) (b) Structured risk management and escalation process in place (2021) (c) Number of monthly internal monitoring reports (2020) (d) Number of quarterly updates to donors (2020) | Planned | n/a | (a) Complete (b) NA (c) 5 (d) 1 | (a) NA (b) Complete ©15 (d) 5
|  | Achieved |  | (a) Complete (b) NA (c) 3 (d) 2
Source
SFD risk updates
| Output Indicator 2.3 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Percentage of all SFD beneficairies with a unique identifier | Planned | n/a | 30% | 40%
|  | Achieved |  | 38%
Source
SFD MIS
| Output Indicator 2.4 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Percentage of beneficiary complaints across SFD projects responded to within 1 month | Planned | n/a | 75% | 85%
|  | Achieved |  | 94.5%
Source
SFD Bi-annual Reports
| Output Indicator 2.5 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Number of quarterly results reports submitted to DFID (following DFID's standard template) disaggregating results by district, gender, age group (and disability from 2021) for key indicators (agreed at the start of the calendar year with DFID) | Planned | n/a | 1 | 4 reports, 2 data returns
|  | Achieved |  | 1
Source
SFD Bi-annual Reports
| Output Indicator 2.6 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| Number of SFD engagements with cash harmonisation and social protection system strengthening discussions | Planned | n/a | 3 | 6
|  | Achieved |  | 2
Source
SFD Bi-annual Reports
| Output Indicator 2.7 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2021)
| SFD interventions reach the most vulnerable (a) Targeting and inclusion guidelines developed (b) Guidelines used to inform development of the next Crisis Response Plan (c) Strategy finalised (d) TBC – based on actions identified in the strategy | Planned | n/a | (a) in progress) (b) NA (c) NA (d) NA | (a) complete (b) complete (c) complete (d) TBC
|  | Achieved |  | (a) NA
Source
Donor review meetings and project prioritisation strategy
IMPACT WEIGHTING (%)
50%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
SRO 0.3, PM 0.6

## Old logframe
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Yemen Social Protection Programme (YeSP) (Phase 1) - 300527
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share | All SFD results are indicative, calculated on S3 @ $510.6m. DFID share is calculated on basis of 18% of results from SFD and 15% from SWF.
To contribute to a reduction in extreme poverty and vulnerability in Yemen. | Percentage of rural population living below national poverty line | Planned | 40.1% in 2005/06
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share | Assumptions
To build and support strong and adaptive social protection systems which provide safety nets, basic services and enhanced livelioods for the most vulnerable people in Yemen. | # people benefitting under YeSP (% female) a. SFD: # direct beneficiaries of wage employment (# of wage beneficiaries of Safety Net &Community and Local Development programmes) (i. 30% female, ii. 20% IDPs/returnees, 35% youth) b. SWF: # direct beneficiaries of emergency cash transfers | Planned |  | x a. 150,413 (i. 45,124, ii. 30,083, iii. 52,645) b. 8m | x a. 150,413 (i. 45,124, ii. 30,083, iii. 52,645) | 8.16m (44%) a. 150,413 (i. 45,124, ii. 30,083, iii. 52,645) | 8.47m (x) a. 451,238 (i. 135,372, ii. 90,248, iii. 157,933) b. 8m | 1.28m (44%) a. 81,223 (i. 24,367, ii. 16.245, iii. 28,428) b. 1.2m
|  | Achieved |  | a. 263,225 (i. 108,517, ii. 17,369, iii. 112,502) b. | a. 85,031 (i. 14,038, ii. 9,894, iii. 48,794)
Source
SFD M&E Unit will provide annual reports using MIS data; WB YECRP and UNICEF reporting
| Outcome Indicator 2 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
| # people with access to key services (50% female) | Planned | 0 | 792,216 (396,108) | 792,216 (396,108) | 792,216 (396,108) | 2,376,647 (1,188,324) | 427,796 (213,898)
|  | Achieved |  | 0.74m | 1505681
SFD M&E Unit will provide annual reports using MIS data
| Outcome Indicator 3 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
| # working days created from all interventions | Planned | 0 | 5328888 | 5328888 | 5328888 | 15986665 | 2877600
|  | Achieved |  | 5.71m | n/a
Source
SFD M&E Unit will provide annual reports using MIS data
| Outcome Indicator 4 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
| a. # pregnant women and mothers (8% mothers of children with disabilities) and b. # children benefitting from nutrition interventions (50% girls) | Planned | 0 | a. 70,000 (n/a) b. 60,000 (n/a) | a. 35,000 (2,800) b. 12,000 (6,000) | a. 35,000 (2,800) b. 12,000 (6,000) | a. 140,000 (5,600) b. 84,000 (12,000) | a. 25,200 (1,008) b. 15,120 (2,160)
|  | Achieved |  | a. 71,414 b. 65,484 | a. 3,246 (n/a) b. 30,804 (15,401)
Source
SFD M&E Unit will provide annual reports using MIS data
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
47m
INPUTS (HR) | DFID (FTEs)
0.6 SDA, 0.8 PM
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share | Assumptions
Maintain and expand saftey nets | SFD: # people with direct safety net support, including: a. direct beneficiaires of cash for work (i. 30% female, ii. 20% IDPs/returnees, iii. 30% youth) b. # direct beneficiaires of conditional cash for pregnant women and mothers undertaking nutrition screening (8% mothers of children with disabilities) | Planned | 0 | a. 133,727 (i. 40,118, ii. 26,745, iii. 40,1188) b. 70,000 (n/a) | a. 133,727 (i. 40,118, 26,745, iii. 40,1188) b. 35,000 (2,800) | a. 133,727 (i. 40,118, ii. 26,745, iii. 40,118) b. 35,000 (2,800) | a. 401,180 (i. 120,354, ii. 80,235, iii. 120,354) b.140,000 (5,600) | a. 72,214 (i. 21,664, ii. 14,442, iii. 21,664) b.25,200 (1,008)
|  | Achieved |  | a. 190,913 (i. 44,657, ii. 16,045, iii. 113,617) b. 71,414 (n/a)
Source
SFD M&E Unit will provide annual reports using MIS data
| Output Indicator 1.2 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
| SFD: # indirect beneficiaries of cash for work a. # households (HH) b. # people in the HHs | Planned | 0 | a. 68,164 b. 477,144 | a. 68,163 b. 477,143 | a. 68,163 b. 477,143 | a. 204,490 b. 1,431,430 | a. 36,808 b. 257,657
|  | Achieved |  | a. 116,209 b. 813,463 | a. 59,628 b. 417,396
Source
SFD M&E Unit will provide annual reports using MIS data
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
50% | SWF: # people benefitting from unconditional emergency cash transfers (45% female) | Planned | 0 | 1.5m (45%) | 1.5m | 8m (3.6m) | 8m (3.6m) | 1.2m (540,000)
|  | Achieved |  | 1.402m (47%)
Source
WB YECRP and UNICEF reporting
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
20.8m
INPUTS (HR) | DFID (FTEs)
0.6 SDA, 0.8 PM??
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share | Assumptions
Restore and improve access to basic services | Local development: # village councils formes/activated | Planned | 0 | 650 | 1250 | 1250 | 3150 | 567
|  | Achieved |  | 1420 | 1447
Source
SFD M&E Unit will provide annual reports using MIS data
| Output Indicator 2.2 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
| Water & sanitation: a. # people benefitting from access to improved water b. # people benefitting from access to improved sanitation c. # beneficiaries that have received cholera awareness messages | Planned | 0 | a. 200,000 b. 12,000 c. 320,000 | a. 200,000 b. 12,000 c. 320,000 | a. 200,000 b. 12,000 c. 320,000 | a. 600,000 b. 36,000 c. 960,000 | a. 108,000 b. 6,480 c. 172,800
|  | Achieved |  | a. 174,723 b. 19,919 c. 920,336 | a. 119,137 b. 26,556 c. 902,811
Source
SFD M&E Unit will provide annual reports using MIS data
| Output Indicator 2.3 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
| Education: a. # students with access to education (72% female) b. # teachers, facilitators and community members trained (30% female) | Planned | 0 | a. n/a b. 1,270 (360) | a. 1,740 (1,260) b. 520 (156) | a. 3,712 (2,688) b. 520 (156) | a. 5,452 (3,948) b. 2,310 (672) | a. 981 (706) b. 416 (121)
|  | Achieved |  | a. n/a b. 1,639 (363) | a. 165 (126) b. 0
Source
SFD M&E Unit will provide annual reports using MIS data
| Output Indicator 2.4 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
| Health: a. # people benefitting from access to health services (53% female) b. # trainees in identification of psychosocial needs for severe stress and trauma (30% female) | Planned | 0 | a. n/a b. 698 (209) | a. 304,404 (162,548) b. 698 (209) | a. 0 b. 698 (209) | a. 304,404 (162,548) b. 2,094 (628) | a. 54,793 (29,259) b. 377 (113)
|  | Achieved |  | a. n/a b. 1,245 (315) | a. 131,596 (68,631) b. 3,659 (1,763)
Source
SFD M&E Unit will provide annual reports using MIS data
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
30% | Roads: Length of roads improved (km) | Planned | 0 | 457 | 457 | 457 | 1371 | 247
|  | Achieved |  | 266 | 290
Source
SFD M&E Unit will provide annual reports using MIS data
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
11.4m?
INPUTS (HR) | DFID (FTEs)
0.6 SDA, 0.8 PM
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share | Assumptions
Enhance livelihood opportunities | # active microfinance clients/borrowers (i. 40% female, ii. 10% youth) | Planned | 0 | 80,000 (i. 32,000, ii. 8,000) | 10,000, (i. 4,000, ii. 1,000) | 10,000 (i. 4,000, ii. 1,000) | 100,000 (i. 40,000, ii. 10,000) | 18,000 (i. 7,200, ii. 1,800)
|  | Achieved |  | 83,761 (i. 14,239, ii 16,800) | 30,647 (i. 18,421, ii. 10,745)
Source
SFD M&E Unit will provide annual reports using MIS data
| Output Indicator 3.2 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
| # income generating activities created/sustained | Planned | 0 | 240 | 600 | 660 | 1500 | 270
|  | Achieved |  | 0 | 66
Source
SFD M&E Unit will provide annual reports using MIS data
| Output Indicator 3.3 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
| # businesses supported (# PHC women workers supported) | Planned | 0 | 3,000 (228) | 3,000 (304) | 3,240 (228) | 9,240 (760) | 1,800 (136)
|  | Achieved |  | 6,557 (510) | 2,518 (228)
Source
SFD M&E Unit will provide annual reports using MIS data
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline | Milestone 2018 | Milestone 2019 | Target 2020 | Total | DFID share
10% | # job opportunities created/sustained from microfinance services | Planned | 0 | 5000 | 7000 | 10000 | 22000 | 3960
|  | Achieved |  | 2049 | 16126
Source
SFD M&E Unit will provide annual reports using MIS data
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
3.1m?
INPUTS (HR) | DFID (FTEs)
0.6 SDA, 0.8 PM, 0.4 Economist
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 2018 | Milestone 2 | Target 2020 | Total | DFID share | Assumptions
Institutional strengthening | % SFD beneficiaries satisfied with project participatory approach | Planned | 0 | 70% | 70% | 70% | 70% | 70%
|  | Achieved |  | 93%
Source
| Output Indicator 4.2 |  | Baseline | Milestone 2018 | Milestone 2 | Target 2020 | Total | DFID share
| % SWF beneficiaries receiving the full transfer amount | Planned | ??? | 100% | n/a | n/a | 100% | 100%
|  | Achieved |  | 99.5%
Source
WB YECRP and UNICEF reporting
| Output Indicator 4.3 |  | Baseline | Milestone 2018 | Milestone 2 | Target 2020 | Total | DFID share
| % registered grievances that are addressed | Planned | 0 | 80% | 80% | 80% | 80% | 80%
|  | Achieved |  | SFD: 97.5% SWF: 97.7%
Source
IMPACT WEIGHTING (%) | Output Indicator 4.4 |  | Baseline | Milestone 2018 | Milestone 2 | Target 2020 | Total | DFID share
10% | # cash for work and unconditional cash beneficiairies who are spending their money on food and basic needs | Planned | ??? | 70% | 70% | 70% | 70% | 70%
|  | Achieved |  | SFD: 74% SWF: 91%
Source
SFD M&E Unit will provide annual reports using MIS data; WB YECRP and UNICEF reporting
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
0.6 SDA, 0.8 PM

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Output 1.4 | Sub target (ii) added to reflect additional funding to support cash for nutrtion programme in Ibb | Manisha Bath | 2021-02-02
2 | output 2.5 | Changes "Number of biannual results reports submitted to DFID (following DFID's standard template) disaggregating results by district, gender, age group (and disability from 2021) for key indicators (agreed at the start of the calendar year with DFID)" to "Number of quarterly results reports submitted to DFID (following DFID's standard template) disaggregating results by district, gender, age group (and disability from 2021) for key indicators (agreed at the start of the calendar year with DFID)" | MB | 2021-07-29
3 | All indicators | Changed date of milestone 2 from Sept 2021 to Dec 2021 | MB | 2021-07-29
4 | output 2.2d | Changed target from 3 to 5 to reflect 4 Qs in 2021 and 1 Q at the end of 2020 | MB | 2021-07-29
5 | output 2.2c | Changed target from 9 to 15 to reflect new Dec milestone (no. of months between Sept 2020 and Dec 2021) | MB | 2021-07-29
6 | output 2.5 | Changed target from 2 to 3 to reflect the number of reports we will recive this year and clarified there will still be 2 data returns | MB | 2021-07-29
7
8
9
10
Changes to the output inidicators are explained in the following submission:
57656949

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.