Project Completion Review

Title: Programme for Improving Mental Health in Low Income Countries (PRIME)
Final Programme Value £ (full life): £7,977,172		Review Date: 4 July 2019
Programme Code: 201446-104	Start Date 1 May 2011	Final End Date: 30 April 2019

Summary of Programme Performance

Year	2012	2013	2014	2015	2016	2017	2018	2019
Programme Score	A	A+	A+	A+	A+	A	A+	A+
Risk Rating	Sev	Sev	Sev	Sev	Mod	Mod	Mod	Mod

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-201446/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-201446/documents

A. Summary and Overview (1-2 pages)

Description of programme and what it has achieved

The Programme for Improving Mental Health Care (PRIME) was an eight-year Research Programme Consortium (RPC), which aimed to generate high quality research evidence on the implementation and scaling up of treatment programmes for priority mental disorders in primary and maternal healthcare contexts in low resource settings. The RPC was led from the University of Cape Town, South Africa; King’s College London and Harvard University, USA. Partners involved a diverse consortium including Addis Ababa University, Ethiopia; Transcultural Psychosocial Organization, Nepal; Makerere University, Uganda; Sangath, India; the University of KwaZulu-Natal, South Africa; London School of Hygiene and Tropical Medicine; and the World Health Organization (WHO).

More than 13% of the global burden of disease is due to mental illness, including mental, neurological and substance abuse disorders. However, 4 out of every 5 people with mental illness in LMIC go without mental health care. With its research, PRIME aimed to address this by researching on how to improve the coverage of treatment for priority mental disorders and integrate mental health care into primary and maternal healthcare systems. The specific conditions included in the research were depression, alcohol use and psychosis, with the addition of epilepsy in Nepal, Uganda and Ethiopia. PRIME achieved this by developing district specific integrated mental healthcare plans (MHCPs) in Ethiopia, India, Nepal, South Africa and Uganda, implementing and evaluating the feasibility, acceptability and impact of the MHCPs in primary healthcare and scaling these MHCPs up to other districts or sub-districts in the PRIME countries.

PRIME has published widely, with 18 publications in the last year alone, bringing the total to 105 over the lifetime of the Programme. There were 20 presentations of its work in the last year, and 92 in total; http://www.prime.uct.ac.za/prime-publications). Findings and publications by PRIME have been widely cited.

The Programme took care to include research findings in policy and practice in all countries that formed part of the RPC. Findings have already been taken up in nine additional countries (Sri Lanka, Zambia Tanzania, Mozambique, Fiji, Burundi, South Sudan, Democratic Republic of Congo). In addition, PRIME influenced plans, strategies or guidelines including significant inputs into the WHO mhGAP operations manual (https://apps.who.int/iris/bitstream/handle/10665/275386/9789241514811-eng.pdf?ua=1).

Findings from an evaluation, conducted by PRIME, show that it is feasible to integrate mental health into primary care in low resource settings and yield significant improvements in clinical outcomes. But this requires substantial investment in training, supervision, and health system strengthening. A substantial increase in uptake of services was identified, with over 20,000 primary care visits during the implementation phase. However, the impacts across the countries were varied.
In Ethiopia, PRIME found no improvement in treatment coverage, no increase in facility detection, but significant improvements in clinical and functioning outcomes for individuals with depression, psychosis and epilepsy who received care. In India, no improvement in treatment coverage was found, a small improvement in facility detection and modest improvement in clinical outcomes for individuals with depression and alcohol use disorder (AUD) who received care. In Nepal, findings showed moderate to large improvements in treatment coverage, moderate to large improvements in facility detection and initiation of treatment, and small to moderate improvements in clinical symptoms and functioning for individuals with depression, AUD and psychosis who received care. In South Africa, PRIME found a significant improvement in detection of depression and AUD and a significant improvement in clinical outcomes for individuals with depression who received care. In Uganda, results showed a small non-significant improvement in treatment coverage, a significant improvement in facility detection of depression and AUD (which was not sustained over the longer term) and improvements in clinical symptoms and functioning in individuals with depression and epilepsy and improvements in functioning in individuals with psychosis who received care.

There is evidence for an increase in mental health spending because of the advocacy generated by PRIME.

The extension phase of PRIME (years 7-8) was used to provide dissemination of findings, partnering with countries beyond the PRIME network and helping to facilitate broader investments in mental health and mental healthcare. A key challenge had been to ensure adequate quality of care, which PRIME addressed by implementing robust Quality Improvement measures in all countries.

The final year of PRIME was utilised for finalising data collection and dissemination of findings and publishing key papers. It was also used to wrap up the programme in ways that data and findings will sustain the Programme beyond its end.

Ultimately, the PRIME Consortium has demonstrated that integrating mental health into primary care can be highly successful and identified the various benefits in terms of access, coverage and outcomes of treatment. There is no direct successor programme for PRIME funded by UK Aid, but future work will be needed to identify options for large scale-up and integration into the wider health systems in multiple contexts.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Establish and maintain an efficient and well managed RPC which draws on the strengths of each partner to deliver a high-quality research programme that achieves the RPC’s goal and purpose
Output number per LF		1	Output Score	A
Impact weighting (%)?		10	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Proportion of the following key RPC deliverables completed in consultation with all consortium partners: - Contracts between partners - PRIME country personnel recruited - M&E framework including logical framework refined - Detailed financial management plan for Phases 2 and 3 - Capacity Building Plan agreed - Research uptake Plan agreed	Key programme documents have been reviewed and revised as needed during years 7 and 8 to improve progress towards achieving outputs, purpose and goal of RPC	Achieved: Key programme documents (publication policy, / expression of interest policy, logframe) and processes (meeting structure, lines of accountability) reviewed and revised as needed to achieve the intended outcomes and impact
1.2 Number of meetings held during inception phase of key governance groups (PMG; CAG; CMG)	All groups have continued to meet as planned during the life of the consortium (4 meetings annually of the PMG, 2 meetings annually of the CAG and monthly CMG meetings)	Achieved: The PRIME Management Group, Consortium Advisory Group, Country Management Group and PRIME Management Team met as planned
1.3 Draft mental health care plans for priority disorders in primary care and maternal care available	Completion of a revised integrated mental healthcare plan based on results from the implementation and scale up evaluations	Achieved: The mental healthcare plans revised in all five / countries

Provide supporting narrative for the score
This output met expectations. Various management and steering groups of the Programme met as expected and the strengths of the international partnership was demonstrated in an invited paper in Global Social Welfare (https://link.springer.com/content/pdf/10.1007%2Fs40609-018-0128-6.pdf).
In all countries with active community advisory boards (India, Ethiopia, Uganda), the Programme conducted at least one meeting or dissemination event. Across all countries, 23 meetings were conducted at implementation and scale up sites and 67 with policy makers. These meetings were focussed to ensure sustainability of the MHCPs after the end of the programme, for example, in Chitwan the PRIME Nepal team met with all the Municipalities to ensure the services would be supported in future.
The team participated in policy meetings to use the lessons from PRIME to inform scale up in other
Districts in Uganda and South Africa. The Programme was involved in Regional and International Policy meetings e.g. the British Academy of Medical Sciences meeting on Global Mental Health research in the era of the SDGs in London and Community health interventions for common mental disorders in Dubai.
Key documents were revised where needed, in consultation with consortium partners. The RPC risk register and logframe were revised and the PRC has made arrangements to make PRIME data available on request from August 2019, to ensure other researchers may request access to PRIME data to analyse and publish the findings from PRIME.
The MHCPs have been revised in all countries using various approaches, building on the evaluations of the implementation and scale up phases, workshops and meetings at district level, quality improvement processes and lessons from further implementation in other districts. Changes made to the MHCPs will be included in publications describing the evaluation of the implementation and scale up phases and disseminated in PRIME policy fora.

Lessons identified this year linked to this output and recommendations for future programmes
The success of PRIME is as much due to the high level of technical expertise as it is due to the good management of the RPC with a true partnership model.

Output Title	A coherent body of high quality, peer-reviewed and policy relevant research that makes a significant contribution to understanding the implementation and scaling up of packages of care for mental disorders.
Output number per LF		2	Output Score	A+
Impact weighting (%)?		50	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Research project is implemented in countries (d1)	Evaluation of scale up completed in 4 PRIME countries. All research projects completed or at analysis stage. (Target 45% projects completed and 53% in analysis	Achieved: Data collection for scale up evaluation completed in all five countries and analysis underway. 48% of projects completed and 52% in the analysis phase.
2.2 Number of high-quality policy relevant primary research papers by RPC partners published in peer reviewed publications (A3). Number of conference presentations by RPC	95 papers published 80% with a LMIC home institution lead or co-author; 80% with a Female lead or co-author; 70% with a Female LMIC home institution lead or co-author, 70% open access) (A3), 80 conference presentations	Moderately exceeded: 105 PRIME papers published (98% with LMIC home institution lead or co-author; 87 % female first or co-author; 70% with a female LMIC home institution lead or co-author; 95% open access); 92 conference presentations
2.3 Number of partner institutions who collaborate and publish with each other. (E7)	At least 5 partner institutions collaborated on at least 2 non-PRIME outputs >5	Moderately exceeded: All 9 partner institutions collaborated on at least 2 non-PRIME outputs.

Provide supporting narrative for the score
The output moderately exceeded expectations. Data collection in the scale up sites in all five countries completed and remaining data analysis is underway. This included quality of care studies in India and Nepal and scale up facility profiles in Uganda. All the studies conducted as part of PRIME have been completed (48%) (defined as one paper submitted or published using the data from that study) or are in the analysis phase (52%).
During the final year, the Programme has focused on writing up the outcomes and case studies from each country to understand the process of implementation and lessons learned. An additional 18 peer-reviewed papers were published adding to a total of 105 papers over the lifetime of the Programme (a full listing of all publications is http://www.prime.uct.ac.za/prime-publications). A key contribution this year was the Lancet Commission on Global Mental Health and Sustainable Development which laid the foundation for future work to improve mental health globally and can be partially attributed to PRIME (https://www.thelancet.com/commissions/global-mental-health). PRIME published papers on characterising the burden, treatment gap and detection of mental illness, perinatal depression, the experiences of people living with mental health conditions and evaluations of the processes and outcomes of implementation of PRIME (e.g. https://doi.org/10.1371/journal.pmed.1002748) including a pragmatic randomised controlled trial on the effectiveness of using community counsellors in Nepal (e.g. https://doi.org/10.1192/bjp.2018.300). An additional 15 papers are under review. The RPC made 20 conference presentations, including at the International Marce Society Biennial Meeting 2018, Bangalore, India, and the Word Psychiatric Association Meeting in Addis Ababa in November 2018, bringing the total to 92. 69% of PRIME’s papers have a Southern lead, 98% a Southern lead or co-author, and to highlight their capacity building, 38% of publications were led by PhD students. 48% of the papers were led by women and 70% had a Southern woman as a lead or co-author. 95% of PRIME papers are open access.
An analysis of partnerships within PRIME showed that only seven partners had collaborated with each other on an academic publication before PRIME started. Since 2017, all PRIME partners have published with all other PRIME partners on at least two non-PRIME academic publications. This shows the impact this consortium has had on building sustainable research partnerships that are likely to continue beyond PRIME.

Lessons identified this year linked to this output and recommendations for future programmes
The RPC has had an excellent record of academic outputs over its lifetime and this should be a good foundation for sustaining and scaling up the capacity and knowledge that PRIME generated.

Output Title	Effective communication of relevant research findings and their uptake by national and international stakeholders to influence policy and practice in the study
Output number per LF		3	Output Score	A+
Impact weighting (%)?		20	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Number of PRIME products disseminated to policy makers and donors across relevant sectors via multiple channels (conferences, high level briefings, workshops etc.) at the following levels: Local, National, International (A4, D2, D3)	At least 110 PRIME products disseminated to policy makers and donors; At least i) 15,000 page views and ii) 200 downloads on websites and blogs (disaggregated by UK based, LMIC based or other) since the start of the RPC. (Downloads will only be counted from the revision of the website in Sept-Nov 2017); PRIME team describe what they have identified as the top 5 most effective research uptake (e.g. engagement/dissemination) activities that they have been carried out in the reporting period	Moderately exceeded: 128 PRIME products disseminated to donors, policy makers and other relevant stakeholder groups. 68,617 unique page views (38,734 from LMIC, 10,518 from UK, 19,365 from other) since RPC started and 3,121 downloads: 1,463 from LMIC, 667 from UK, 991 from other, from Oct 2017. 5 most effective engagement activities reported
3.2 Participation of mental health service users and community groups in mental health care	MH service users taking an active role in service planning or delivery of mental health care in all PRIME countries and PRIME have shared findings with the CAB (India, Uganda and Ethiopia) and other where PLMI are represented	Achieved: Mental health service users involved in aspects of service / planning and/or delivery and the findings shared with the CAB in India, Uganda and Ethiopia where people living with mental illness are represented
3.3 Number of PRIME citations in the media	At least 225 media citations of PRIME or PRIME outputs	Moderately exceeded: PRIME cited 274 times in local and international media
3.4 Number of citations of PRIME outputs in research articles/other academic publications, curricula or training materials	1500 citations of PRIME outputs	Significantly exceeded: PRIME cited 3148 times in Google Scholar and 2017 times in Scopus

Provide supporting narrative for the score
This output has moderately exceeded expectations. PRIME disseminated 128 products including policy briefs, website articles, research tools, newsletters, infographics and videos to various stakeholders including policy makers and donors. The five most effective engagement activities of PRIME include:
1. Global Ministerial Mental Health Summit, October 2018, London)
2. The WHO mhGAP forum, October 2018 (https://www.who.int/mental_health/mhgap/forum_2018/en/)
3. Sierra Leone Workshop, February 2019: lessons from PRIME to support the implementation of Sierra Leone’s National Mental Health Policy and Strategic Plan.
4. Mozambique workshop, September 2018: sharing PRIME model, tools and experiences with 35 stakeholders including Ministry of Health representatives and practitioners.
5. PRIME dissemination event, March 2019, London
PRIME continued to engage people living with mental health conditions in the planning and delivery of services. In Uganda, members of the user support groups as well as the mental health service groups met to discuss challenges and possible solutions. In Nepal, service users were involved in the training and supervision of primary healthcare workers and the community sensitisation program. In Ethiopia, service users shared their stories to teach community members and to train primary care staff. A model of mental health service user involvement in monitoring of the quality of care and advocacy is being piloted as part of a PhD project nested within PRIIME. In South Africa, service users serve as representatives on clinic committees and provided feedback on their experiences at routine clinic staff meetings.
PRIME’s work was cited 274 times in local and international media. A key product was the PRIME documentary film, Hear our Voices: mental health in the developing world (premiered in London on 6 March at King’s College London). PRIME has been cited 3148 times in Google Scholar and 2017 times in Scopus.

Lessons identified this year linked to this output and recommendations for future programmes
This RPC has been strong on dissemination and communication and have successfully influenced policy at country and global levels.
Output Title	Capacity exists in study countries to conduct and effectively disseminate research to improve access to mental health care
Output number per LF		4	Output Score	A+
Impact weighting (%)?		20	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Number of externally funded policy-relevant research grants successfully applied for; and level of funding achieved. (E2)	At least 2 externally funded research grants successfully applied for or received from 2017 onwards.	Moderately exceeded: 5 grants received since 2017, value of >£9,300,000
4.2 Number of researchers who complete higher training and/or successfully apply for fellowships (E7 & E7.1)	3:7 (M: F) PRIME researchers successfully graduate with PhD*	Moderately exceeded: 8 women and 5 men have graduated with a Phd. 1 woman has submitted
4.3 Number of research publications and other research outputs by PRIME partner groups (E7)	Research publications by partner groups increase by 5% since end year 7	Significantly exceeded: Cumulative research publications by / partner groups increased on average by 14% from 2017 to 2018

Provide supporting narrative for the score
This output has moderately exceeded expectations. There is evidence to show that PRIME have built both institutional and individual capacity within PRIME. During the final year, PRIME successfully obtained 2 grants aligned to the objectives of PRIME:
1) MRC funded Indigo Partnership led by Prof Sir Graham Thornicroft, to develop and test new methods to reduce stigma in China, Ethiopia, India and Tunisia.
2) Psychosocial Rehabilitation and peer support for people with schIZophrEnia in South Africa (PRIZE): a pilot cluster- randomised trial led by Dr Carrie Brooke-Sumner and Prof Laura Asher with the support of Profs Inge Petersen and Charlotte Hanlon. PRIZE is based on the psychosocial intervention developed by PRIME South Africa (https://doi.org/10.1080/15332985.2016.1220439) and will expand the intervention to a larger area in a different district.
Since 2017, PRIME have received five grants aligned with PRIME objectives. This brings the cumulative total to >£36 million. These grants will ensure that the institutional capacity built through the programme will remain and strengthen the networks built through PRIME.
PRIME put an important focus on building academic capacity. Twelve of the 18 papers published in the last year and 9 of the 15 under review were led by PRIME PhD students. 13 of the 21 PhD students have now graduated (8 women and 5 men). For the remaining 7 students, all data collection has been completed or will be funded through another source. Supervision will continue after the end of PRIME. At the PRIME dissemination event in March 2019, five PhD students took part in a panel discussion (their work will be disseminated through the Mental Health Innovation Network (https://www.mhinnovation.net).
Additional capacity building work through PRIME included the development of “Evidence to Practice”, an online course for mental health professionals working in the Pacific Islands. This course was designed to build the capacity of mental health professionals to develop and evaluate MHCPs using an implementation science approach.
Another focus of the consortium was to increase the capacity of researchers to analyse and publish research findings. Cumulative research publications by partner groups have increased an average of 14% across partners from 2017 to 2018.

Lessons identified this year linked to this output and recommendations for future programmes
The RPC has been very effective in capacity building by building a clear focus into their portfolio and theory of change. The new grant (PRIZE, see above) is an example of how one of PRIME’s PhD graduates is now leading their own grant. This is particularly relevant in an area that has many capacity gaps globally.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved
There is strong evidence that PRIME achieved its stated impact and all its impact indicator milestones.
PRIME research evidence and/or tools are being used in more districts across the 6 PRIME countries than anticipated (Impact indicator 1). And there is evidence in all five countries that there is an increase in mental health spending (Impact indicator 2). The PRIME work has been cited in 16 international documents which are likely to inform policy (Impact indicator 1.3). In particular, PRIME has influenced the programmatic work of WHO by testing and providing feedback on mhGAP products and training materials over the last eight years and informing and directly contributing to the mhGAP Operations Manual. As a result, countries implementing mhGAP (>100) have benefited from the experience and lessons learned in PRIME.
There is also good evidence that PRIME has achieved the intended outcomes. Of 3 outcome indicators, only the first remained with a target for the final year, while others were completed earlier in the programme. PRIME influenced at least one policy, guideline, practice, plan, strategy, roadmap and/or
leadership initiative, or product included in treatment guidelines at the sub-national level or national level in each PRIME country (Outcome Indicator 1.1)

Summarise the programme’s theory of change and major changes to it in the past year
The PRIME theory of change assumed that achieving outputs would enable PRIME’s world class research, on implementation and scaling up of treatment programmes for mental disorders, to be adopted by policy makers & practitioners for the benefit of the poor, particularly women. It further assumed that this would contribute to the impact of widespread implementation of mental health programmes that improve the health and socio-economic status of individuals, particularly women and those living in poverty.
The PRIME RPC Theory of Change (ToC) (Figure 1) was developed from the original research proposal to complement the PRIME logframe. It described the anticipated path towards achieving the impact of improved health and socioeconomic status of individuals, particularly women and those living in poverty. On reflection the PRIME team concluded that the way in which the outcome occurred was less linear than outlined in the ToC. For example, many of the changes to practice and policy as a result of PRIME were made before the evaluation of implementation was finalised. This could have been for several reasons, such as 1) the integrated nature of the PRIME programme, which sought to make sustainable changes in the way the health services were organised and delivered as part of the implementation of the MHCPs. For example, to ensure psychotropic medication provision by the health facilities in one particular district, the PRIME team started the process of ensuring that these are added to the free drug list prior to implementation, 2) the momentum generated by PRIME, an ambitious multi-country internationally funded study, gained the attention of policy makers, some of whom were involved in the grant from the outset, 3) the leveraging of funds to add on to PRIME research, such as the European Union funded Emerald consortium which focused on health systems strengthening and financing, 4) the calibre and visibility of PRIME partners who are nationally and internationally respected, and 5) the timing of the programme, which occurred at a time where global mental health had started to gain recognition and international priority following the Lancet Series on Global Mental Health in 2007. This policy window meant the policy makers were likely more receptive to the work of PRIME. Although the impacts can also be attributable to other funding such as Emerald, PRIME was undoubtedly the initial starting point and catalyst for most of these other grants in PRIME countries which expanded, built upon and extended the PRIME work, networks and institutional capacity.
Overall, the expected results in the ToC chain remained valid. One assumption, i.e. that ‘countries and their health systems remain stable and enable PRIME to implement and evaluate the programme’ has not held true in all PRIME countries. For example, unrest in Ethiopia created challenges for final stages of data collection, and in India, the challenges of transferring funds to local partner (Public Health Foundation India), delayed the transfer of funds from the University of Cape Town. These challenges have been managed well, causing only minor delays to activities.
There was a high risk that the assumption of ‘political buy-in is obtained despite competing priorities’ does not hold true in Nepal, where the decentralisation of the government system posed risks to sustainability of programme achievements. However, this risk did not substantially challenge the overall results as PRIME continued to prioritise engagement with policy makers and are working to navigate the government changes to maintain momentum gained and buy-in from key stakeholders.

Figure 1: PRIME Theory of Change

Explain major changes to the logframe in the past year
A number of changes to the logframe were recommended in last year’s annual review, were all taken up by the RPC in consultation and agreement with the DFID Health Research Team. All changes related to the extension of the Programme and the fact that some of the milestones had been achieved before the final year, which focussed mostly on final data collection, publication and dissemination. The changes to individual indicators are shown below:

Logframe indicator	Orig. target (Apr. 2018)	New target (April 2019)	Actual achievement
Impact 3 / No of research products cited in intl. documents that inform policy	>12	>14	16
Outcome 1 / # of districts using RPC evidence per study country; / # of programmes in other countries using RPC evidence or methods	≥4 / ≥9	≥5 / ≥9	Achieved for PRIME countries; / Likely to have been achieved
Output 2.2 / # of papers published; / % with a LMIC home institution lead or co-author; / % with a Female lead or co-author; / % with a Female LMIC home institution lead or co-author; / % open access; / # of conference presentations	85 papers; / 80% LMIC lead; / 80% female lead; / 70% female LMIC; / 70% open access; / 70 conf. presentations	95 papers; / 80% LMIC lead; / 80% female lead; / 70% female LMIC / 70% open access; / 80 conf. presentations	105 papers; / 98% LMIC lead; / 87% female lead; / 70% female LMIC; / 95% open access; / 92 conf. presentations
Output 3.1 / # PRIME products disseminated to policy makers and donors; / # page views; / # downloads on websites and blogs; / Top 5 most effective research uptake activities	≥110 products disseminated; / ≥20,000 / ≥200	≥110 products disseminated; / ≥15,000 / ≥200	128 / 68,617 / 3,121 / 5 most effective research methods have been chosen as per the annual report
Output 3.2 / MH service users taking an active role in service planning or delivery of mental health care in all PRIME countries		As before and PRIME have shared findings with the CAB (India, Uganda and Ethiopia) and other where PLMI are represented.	Mental health service users are involved in aspects of service / planning and/or delivery; findings were shared with / the CAB in India, Uganda and Ethiopia / (see report for details).
Output 3.4 / # citations of PRIME outputs	1,100	1,500	3,148 (Google Scholar) / 2,017 (Scopus)
Output 4.2 / Ratio (M:F) PRIME researchers successfully graduate with PhD	3:6	3:7	8 women and 5 men have graduated (1 woman submitted)

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme
The programme ran initially for 6 years and was extended for 2 year to give an 8-year duration at an extra cost of approximately £2m. The reason for the extension was twofold: i. to consolidate and build on the research results of a strong performing RPC and ii. to bridge the gap whilst DFID was commissioning new research. The PRIME programme, together with the other RPCs, was closely scrutinised to ensure that any approved extensions provided value for money and that proposed workplans offered a series of deliverables that would closely support other work being conducted in the sector.
The scope of the programme exceeded initial plans and the approval of the extension supported additional research including conducting randomised control trials in Nepal and South Africa to further evaluate some of the PRIME implementation work. In addition, it allowed PRIME to respond better to policy maker demands for specific types of evidence and to publish 105 peer review publications. PRIME district sites established institutional capacity which acted as a starting point for other studies such as multi-country EU funded Emerald grant, the National Institute of Mental Health funded COBALT trial in South Africa, ESSENCE programme in India, Wellcome Trust funded RISE cluster randomised trial and IDEAS – DFID funded through MRC in Ethiopia.
Economy: PRIME ensured economy in the conduct of the programme including procurement of goods and services, where possible minimised programme costs, including holding meetings at venues with no hire costs. Most meetings were held remotely to minimise outlay and restricting travel had a positive impact on the environment.
Efficiency: PRIME maximised the research funding and institutional capacity, by leveraging multiplier funding of approximately £30m to complement their work. For example, efforts by PRIME to engage government also helped other mental health research initiatives in Madhja Pradesh (India), such as ESSENCE, funded by the US National Institutes of Health. The relationships built by PRIME made it easier for Sangath and the Ministry of Health to discuss a long-term collaboration in mental health.
Effectiveness: At National level PRIME influenced the development of mental health policy and practice. For example, the inclusion of psychotropic medication on to the free drug list; in Nepal the inclusion of PRIME tools in the roll out of district based mental health teams in South Africa; drafting guidelines for integration of mental health component in Health and Wellness Centres in India and establishing regular procurement and supply chain management of psychotropic drugs across the Indian state of Madhya Pradesh. At international level PRIME made significant contributions to WHO’s programmatic work including testing and giving feedback on various WHO tools and materials and providing direct input into the mhGAP Operations Manual – currently used by WHO in all regions, in more than 100 countries.
Equity: PRIME ensured an equitable distribution of resources across partners in low- and high-income countries and Partners held their own budgets, to enhance transparency. Equity was an underlying principle of the PRIME RPC with a specific focus on the vulnerable group of people living with severe mental health conditions. For example, before PRIME involvement in Soda (Ethiopia), people with severe mental health illness were not able to access any treatment – the nearest treatment available was in the district of Butajira. In addition to providing training and supervision to the healthcare and community workers in how to identify and treat mental illness, the PRIME Ethiopia team worked to ensure the sustainability of the programme by helping the district to start a revolving drug fund to secure adequate and ongoing supply of medication. As a result, PRIME estimate that around 81% of people living with severe mental illness in Soda have been treated, with a significant reduction in suicide.

E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme
PRIME held monthly investigator meetings with all partners to assess progress and challenges. Risk was re-assessed every 6 months and the risk register is updated to reflect changes.
The Consortium Advisory Group (CAG) made up of experts in the field provided advice/ oversight, and met 2 to 3 times a year. Over the course of the programme the CAG met mainly by telephone, which, due to the remoteness of some of the participants was challenging and may have prevented it from delivering on all aspects of its role. Attempts to arrange face-to-face meetings were generally unsuccessful.
At the end of the programme, PRIME was considered by DFID to be “Moderate” risk overall:
Context (Moderate): the programme operated in the same countries since inception and, despite some challenges, overall, the countries were reasonably stable with no significant risk to the research being conducted
Delivery (Moderate): the partners had worked together for a long period of time and had deep understanding of their respective roles within the consortium. Each partner was key to the success of the programme and all provided research results that fed into the end results
Operational (Minor): The programme did not required large amounts of DFID programme staff time, and any developing issues were resolved quickly, with no negative impact to the work of the consortium.
Safeguards (Moderate): although there was little direct risk to those involved through implementation of the research, PRIME worked with large vulnerable groups
Fiduciary the University of Cape Town systems were robust, that PRIME had adequate controls in place to mitigate the risk of misappropriation. PRIME oversaw local partner finances and there was little, or no, evidence of funding going astray. In isolated occasions when concerns were raised, the potential risk proved to be small and mitigation measures were quickly put in place to reduce the likelihood of recurrence
Reputational (Moderate): when dealing with mental health illness there was always the possibility of reputational issues arising
Intellectual (Minor): developing mental health policies and researching various types of mental illness was not considered to generate a serious risk

PRIME identified risks at the end of the programme:
- After the end of PRIME it may not be possible for Mental Health Care Plans (MHCPs) to be sustained in all scaled up sites. This is predominantly due to ongoing training, supervision and technical support needed, not being available. Nepal is a strong exception as there has been buy-in from most of the municipalities in the Chitwan district where provision of mental health services will be provided a primary care level and the National Health and Training Centre (accredited to provide PRIME training) will take this aspect forward.
- Although PRIME has published 105 papers there are large amounts of data still being analysed and written up for publication and there is a risk they will not be completed. PRIME is seeking to mitigate this risk by i. maintaining a publication list where progress will be reviewed after PRIME is completed and ii. making data freely available on request to those interested in analysing and writing up data which has not been included in the publication list.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues
During the programme period PRIME built a good understanding of DFID’s financial requirements towards fiduciary risk/ financial reporting/ forecasting and acted to ensure that appropriate measures were in place to meet DFID’s needs. Forecasting was provided in a timely manner and the DFID programme team were alerted when there were significant changes that otherwise could have resulted in under/ overpayments against agreed budgets. Although there were some forecasting variances from year-to-year at the end of the programme PRIME spent £7,918,722 out of a contracted budget ceiling of £7,977,172. This represents an overall variance of 1% which is highly accurate over an 8-year period.
Invoices were usually presented around 6-8 weeks after the period of the claim, a similar timescale to the other RPCs, and these were supported by a financial narrative report showing how funds had been allocated to specific activities.
In 2015 the Indian Government removed the ability of the lead Indian partner, Sangath, to receive foreign currency. At that point Sangath’s technical role in the programme was coming to an end and the main focus was to disburse funds (normally in advance) to a second Indian partner (PHFI) who did not have sufficient financial reserves to pay upfront. As Sangath could no longer support PHFI, DFID and PRIME staff found a solution and agreed to pre-pay PHFI based on estimated outlay on a rolling six-month basis. These payments were monitored as part of the quarterly invoicing and the funds held by PHFI were kept to a minimum.
Annual Audited Statements were provided by the University of Cape Town and the auditors made no qualifying remarks during the period of the programme. The statement did not show the DFID contribution separately from other income, so PRIME submitted a “letter of comfort” each year signed by their Auditors to provide assurance that DFID funds to PRIME were captured appropriately.
PRIME maintained an Asset Register, and the final version was reviewed. DFID instigated an “Exchange of Letters” and agreed to transfer ownership of the assets to the PRIME partner institutions on the basis that they will continue to be used for development purposes and will be decommissioned appropriately when they reach the end of their shelf-life.
Throughout the programme we have met regularly and built good relationships with members of the PRIME core team and this close interaction helped to strengthen this aspect of the programme. All requests for ad-hoc information were quickly provided and used to support DFID corporate requirements.

Date of last narrative financial report	17 June 2019
Date of last audited annual statement	23 June 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring
This review was carried out by members of the Health Research Team in DFID’s Research and Evidence Division. Since the last Annual Review, the DFID Senior Responsible Owner (SRO) and Programme Manager attended two Consortium Advisory Group meetings by telephone and attended the PRIME dissemination event and launch of the documentary film ‘Hear our voices’ in early 2019. The DFID team had face-to-face meetings with members of the PRIME consortium and used supporting materials such as the PRIME annual report, the PRIME website, data from the online platform ResearchFish, and key articles PRIME outputs to complete this this PCR.
The PRIME internal monitoring and evaluation used the following approaches to monitor progress within the consortium:
1. Quarterly narrative and financial reports from all partners, including detailed reports on personnel, meetings, research outputs, research uptake outputs, capacity building activities, graduate students and a short narrative highlighting major achievements and barriers.
2. Regular weekly meetings of the PRIME Management Team, monthly meetings of a core group of PRIME partners, quarterly meetings of the PRIME Management Group, annual PRIME meetings of key partners, and weekly or fortnightly meetings within each country team.
3. Monthly Implementation Logs included all field activities in the implementation and training sites including training, supervision, meetings and research activities.
4. Country teams continued to make field visits to the implementation and scale up sites during the implementation phase to ensure the MHCPs were implemented as planned.

Evidence
There have been no significant changes in the evidence base during the reporting period. PRIME continued to generate high quality research that built upon the limited evidence available on mental healthcare integration in LMIC. Evidence from the broader research community continued to support the importance of the PRIME work. For example, the Lancet Commission on Global Mental Health and Sustainable Development highlighted the importance of the provision of mental health services as part of a Universal Healthcare Package. A good compilation of the PRIME ‘legacy’ is the PRIME homepage http://www.prime.uct.ac.za/prime-impact.
The PRIME RPC included an evaluation of its outcomes, which led to two published papers with further ones on the way. PRIME used this knowledge to inform further scale up through other programmes, for example, the CDC funded MHINT project in South Africa, the NIHR funded ASSET programme in Ethiopia and South Africa and the NIMH funded ESSENCE project in India. The PRIME MHCPs have been revised in all PRIME countries. The changes will inform work with policy makers in the committees, for example, the revision of the National Mental Health Strategy in Ethiopia.
With respect to ‘Leave no one Behind’, PRIME was mindful that people living with mental health conditions are a vulnerable group and ensured that their experience was reflected in its work and results. Qualitative research on the experiences of people living with severe mental health conditions, alcohol use and epilepsy in Ethiopia, influenced the PRIME results. Quantitative data incorporated gender and age into the analysis.
All papers using primary data made explicit the geographical location of the research and cross-country papers presented data disaggregated by country. Most of the monitoring data collected in the last year was at service level and therefore PRIME were not able to disaggregate by gender, age or disability.

Learning
PRIME’s ways of working, including partners based both in PRIME countries and in other institutions, allowed the Programme to distil the lessons based on the results of the analyses in a rigorous way. Some of the key lessons identified to date include:
1. It is feasible to improve clinical and functioning outcomes of people living with depression, alcohol use disorder, epilepsy and psychosis, using primary care systems in low resource settings
2. Participatory development of district level mental health care plans is vital, and approaches such as Theory of Change are essential tools for collaboration, buy-in and evaluation design
3. Integrating mental health into primary care in low resource settings is not possible through training primary care practitioners alone. Further substantial investments are needed to strengthen health systems, expand competencies of community health workers to deliver psychosocial interventions, and provide ongoing supervision and support for these health providers. Continuous quality improvement is a vital tool in this regard.
4. Any Programme to make an improvement in population level treatment coverage needs demand side interventions as well as supply-side interventions. Demand-side interventions at the community level can include pro-active community case detection, Community Informant Detection Tool using community health workers in Nepal and the community-based case-detection approach used in Ethiopia), stigma reduction activities, and community education programmes.
5. Further research is needed on the scaling up of such treatment packages for larger populations, and the implementation of treatment packages for other priority disorders, for example disorders of childhood and adolescence.

Progress on recommendations from annual reviews for this programme
PRIME identified the challenge of balancing time and resources to both maximise dissemination of outputs versus publication writing. The PRIME leadership team and country teams should continue to maintain oversight of time and resource management to ensure that opportunities to disseminate results are maximised without impacting on the writing and publication of PRIME research, particularly the key outcomes papers. The PRIME publication list should be reviewed monthly to ensure work remains on track. (ongoing)
Progress: PRIME continued to balance dissemination with writing and publications with a high number of papers. PRIME reviewed the key publications in their weekly and monthly meetings with the full publication list reviewed on a quarterly basis.
PRIME is in an intense final phase of writing up their findings, including revising the district mental healthcare plan model. It will be important to ensure that this updated version is disseminated and shared effectively, particularly to those currently using and rolling out the old plan (ongoing).
Progress: PRIME revised the MHCPs in all countries, but the changes have not been substantial. Further changes were embedded in publications, operational documentation for future programmes and communications with policy makers. Lessons learned through PRIME have been integrated in the WHO mhGAP operations manual.
A key challenge during the reporting year has been for PRIME PhD students (many of whom are also key members of PRIME staff, e.g. PIs and project coordinators) to balance their scientific work with other broader needs of the programme. Now that field work is winding down, this challenge has reduced but with the demands of key dissemination events and activities over the final year, and with potential increase in focus on new grants and projects that are starting, PRIME should closely monitor progress, including setting clear deadlines and protecting time for publication writing (ongoing).
Progress: PhD students have shown great progress both within the Programme and in their academic achievements. An additional 8 students graduated. Twelve of the 18 papers published in the last grant year and 9 of the 15 under review were led by PRIME PhD students.
Recommendations to amend the logframe
Progress: All changes to the logframe were discussed with the DFID SRO and Programme Manager and integrated into the logframe.
Learning objectives for PRIME during the final year of the programme include: identifying the barriers to success of implementing and scaling up integrated district metal healthcare plans, and strategies that can be used to overcome them.
Progress: This was part of PRIME implementation and outcomes papers, which will be published across countries.
PRIME should upload research outputs and outcomes into ResearchFish after March 2019.
Progress: This has been completed and all inputs entered into ResearchFish.
Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Programme for Improving Mental Health Care (PRIME) – Research Programme Consortium (RPC)
Programme Value: £6,057,045		Review Date: September 2014
Programme Code: 201446	Start Date: July 2010	End Date: April 2017

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	A	A+	A+
Risk Rating	High	High	High

Summary of progress and lessons learnt since last review

Recommendations from last review
The RPC needs to maintain progress and help those countries where progress has been slightly slower than expected, so that the key research programmes are completed on time.

Financial forecasting needs to be improved and it is important that the RPC does not allow the substantial additional funding from other sources to displace planned DFID-funded expenditure.

It will be important to continue to prioritise key research activities which lead directly to the planned outcomes. The RPC is producing important findings already and these should continue to be shared, as appropriate, with WHO.

## The RPC is working hard and has a clear, coherent strategy for carrying forward research uptake activities. In the next and subsequent years, it will be important to gauge the impact that the various products, programmes and meetings are having, particularly to document any changes in policy or legislation that directly result from the RPC’s activities. Liaison with WHO will continue to be important.

## There was good early progress with capacity development activities which has been further consolidated in the second year. The RPC must carefully prioritise activities, using the additional external funding to build and not divert from the RPC’s activities. Continued liaison with WHO is important.

Summary of recommendations for the next year
Continue to focus on timely budget spend against the agreed projections. This needs further improvement during the next year. Important to ensure that substantial multiplier funding, which is most welcome and impressive, does not result in any displacement of DFID-funded expenditure, as this could potentially increase the underspend problems. This has not happened so far but RPC Senior Managers will need to keep under review.

As the RPC starts on the final phase (Scaling-up of proven interventions), important to quickly finalise any outstanding research studies, so that effective dissemination and research uptake can take place before the end of the RPC. Important to move on from research dissemination into genuine scaling-up of proven methodologies and to develop an appropriate indicator for this in the logical framework

Continue to focus on establishing strong working relationships with key policy makers, not only in Ministries of Health but also in Ministries of Finance and Offices of President. The short tenure of key policy makers is an acknowledged problem and can only be overcome by the investment of time and effort to provide orientation to new staff.
Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Programme for Improving mental Health Care (PRIME) – Research Programme Consortium (RPC).
Programme Value: £6,017,407		Review Date: September 2015
Programme Code: 201446	Start Date: May 2011	End Date: April 2017

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score	A	A+	A+	A+
Risk Rating	High	High	High	High

Summary of progress and lessons learnt since last review

PRIME is performing strongly and on track to provide world class evidence on implementation and scaling up of treatment programmes and having this adopted by policy makers for the benefit of the poor. There has been a substantial (on average 239% higher) increase in treatment for those suffering from mental health disorders in PRIME countries. PRIME has a strong country and global resonance amongst policy-makers, particularly within the health sector and academia. Examples include Ethiopia’s National Mental Health Strategy, Ministers championing the cause, developing state plans in India, and improving national training curricula.

PRIME have completed their baseline and Mental health Care Plan (MHCPs) studies in five countries. However, the cohort studies, faced recruitment challenges and are not complete. It is recommended that PRIME now focus in on 3 countries (rather than 4) to ensure good study depth and quality and provide adequate time for dissemination.

PRIME has addressed the key recommendations from last year’s review. Progress includes improved budget spend against agreed projections. There was no significant underspend and variance (allocation to spend) remained under 10%.

Summary of recommendations for the next year
Output 2: To maintain emphasis on quality and country context, Output 2.1 should reduce from “Evaluation of scale up completed in 3 PRIME countries (instead of 4) by January 2017.

Output 3: PRIME should clarify areas where user participation in Community Advisory Boards (CABs) has not been successful and how they will overcome this. In areas where there is good participation, they should maintain emphasis on the quality of participation and level of influence, to be reported in the next annual report.

Output 4: PRIME should continue to seek advocates and opportunities within their country partnerships and champions within Government Ministries and report progress in the next annual report.

Risk: PRIME to follow up WHO and Addis Ababa University to ensure all financial risk audits are complete across all RPC partners by March 2016.

Commercial: PRIME should provide a brief comment on the status of their asset register and the frequency of review, in their next annual report.

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Programme for Improving Mental Health Care (PRIME) – Research Programme Consortium
Programme Value: £6,017,407		Review Date: September 2016
Programme Code: 201446	Start Date: May 2011	End Date: 30 April 2017

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	A	A+	A+	A+	A+
Risk Rating	High	High	High	High	Moderate

Summary of progress and lessons learnt since last review
PRIME is conducting research into the feasible and acceptable components and packages of care for priority mental health disorders and how can they be integrated into routine primary health care and maternal health care in low- and middle-income countries. PRIME’s work has been used to inform international policy at the World Health Organisation (WHO) and nationally in Nepal. There has been a 115% increase in the number of men and women receiving evidence-based treatment in sites in India, Nepal and Uganda. PRIME delivered their final research uptake strategy which included documentary films and the use of social media, and policy briefs for the World Bank High Level Meeting in Washington DC (April 2016). Country-based mental health care plans are progressing well and on track to meet their targets, including the case studies, cohorts and community surveys.

Key results during the reporting period include publication of 27 peer reviewed journal articles (11 with female first author); completion of a cohort study with 3,058 individuals recruited; and 20 PhD students (13 women) enrolled.

PRIME addressed all the recommendations from previous reviews, including an independent midterm evaluation. Key challenges during the year included delays due to factors, such as the Ugandan elections and the fuel crisis in Nepal. The team have worked to overcome challenges in implementing the country level mental health care plans, including harmonising data collection tools and work on quality improvement plans.

Summary of recommendations for the next year
In the final year of delivery PRIME should aim for the highest level of output results, particularly on research products, publications and uptake.

Output 2: During the final year of delivery, PRIME should stretch its research publication target (Indicator 2.2) from 40 to 65 peer review publications and 55 conference presentations.

Output 3: The number of media citations (Indicator 3.3) targeted for the end of the RPC should double from a target of 80 to 160. The number of research publication citations (Indicator 3.4) should be increased from 400 citations to 1100 for Google Scholar and 650 for Scopus.

Annual Review - Summary Sheet
Title: Programme for Improving Mental Health Care (PRIME) – Research Programme Consortium (RPC)
Programme Value: £7,977,172		Review Date: 6th October 2017
Programme Code: 201446	Start Date: May 2011	End Date: 30th April 2019

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017
Programme Score	A	A+	A+	A+	A+	A
Risk Rating	High	High	High	High	Moderate	Moderate

Summary of progress and lessons learnt since last review
PRIME continues to be a well-managed and effective RPC, doing research on implementing and scaling up care for priority mental health disorders. It has robust systems and processes in place to maintain appropriate oversight at RPC and country level and allow for open communication and engagement between staff and stakeholders. Key achievements during the reporting period include: at least one substantial influence on policy and practice in each PRIME country (see section B for details); the use of PRIME evidence in at least 83 districts in PRIME countries (Ethiopia:15, India:51, Nepal:8, South Africa:5, Uganda:3); publication of 9 peer reviewed journal articles (100% with a southern based female lead or co-author), £14.2m of funds leveraged for scale-up of PRIME activities; and a cumulative total of a 117 formal requests for PRIME support, collaboration and/or sharing of PRIME tools from a range of public and private organisations, including 9 LMIC governments - at least 5 programmes in non-PRIME countries are now using PRIME evidence or tools.

PRIME is involved in many influential fora and policy initiatives and the programme has contributed to the increased profile of mental health on the international agenda. PRIME delivered 23 conference presentations during the reporting period and was featured at the WHO/World Bank meeting (in Washington DC) ‘Out of the shadows: making mental health a global development priority’. In addition, four senior members of the PRIME team are editing the Global Mental Health Lancet Commission, which will be published in early 2018 and will include substantial content from PRIME. PRIME is partnering with WHO to provide case studies and tools to be used in the mhGAP 2.0 Operations Manual. The WHO mhGAP is a primary care clinical guideline for the detection and management of common mental health problems in primary care and is currently being implemented in over 100 countries. The Operations Manual, due to be launched in October 2017 will provide a district level planning tool for implementing and scaling up mhGAP and will draw substantially on PRIME tools and experiences.

PRIME has addressed all recommendations from previous reviews. Key challenges during the year included: exchange rate fluctuations; the cancellation of the licence of PRIME`s lead India partner (Public Health Foundation India) by the government due to new regulations for foreign funding; the declared state of emergency in Ethiopia in 2016; and the political transition to federalisation in Nepal. The team have managed these challenges well, keeping DFID appropriately informed. As PRIME enters its 7th year, the team should assess the impact of the delays caused by these external challenges and ensure that the objectives of the extension phase remain realistic.

Summary of recommendations for the next year

The following changes to the logframe are recommended and should be made by December 2017:
- incorporate the new DFID results framework indicators into the logframe
- Ensure extension phase activities are reflected in the logframe and targets are set for 2018 & 19 are clearly defined.
- Update logframe assumptions, many still refer to the inception phase
- Increase output indicator targets for 2.2. and 3.3 (as detailed under output recommendations)
- Closely monitor the impact of delays in research activities on achieving extension phase objectives

Annual Review – post April 2018

Title: Programme for Improving Mental Health Care (PRIME) – Research Programme Consortium (RPC)
Programme Value £ (full life): £7,977,172		Review Date: September 2018 (reporting period 1st April – March 31st)
Programme Code: 201446-104	Start Date: 1 May 2011	End Date: 30th April 2019

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017	2018
Programme Score	A	A+	A+	A+	A+	A	A +
Risk Rating	High	High	High	High	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201446/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201446/

A. Summary and Overview

Description of programme
It is estimated that 10.4 % of the global burden of disease is due to mental, neurological and substance use disorders with a significant proportion in low- and middle-income countries (LMICs). This equated to 258 million disability adjusted life years (DALYs) in 2010. Despite this burden, is it estimated that almost four out of five persons with severe mental disorders in LMICs did not receive any treatment in the previous year[1][2].
[1] Kohn R, Saxena S, Levav I, Saraceno B. The treatment gap in mental health car. Bull World Health Organ 2004; 82 (11): 858-66.
[2] WHO. Mentlah health gap action programme (mhGAP): Scaling up care for mental, neurological and substance use disorders. Geneva. World Health Organization; 2008

In order to address this, there have been numerous calls for the implementation and scale up of evidence-based treatment in LMICs but there remains little evidence on how to practically develop and implement this within the significant financial, human resource and system constraints.

The Programme for Improving Mental Health Care (PRIME) is an eight-year DFID-funded Research Programme Consortium (RPC) working in 5 countries; India, Uganda, Ethiopia, Nepal and South Africa. The programme aims to generate high quality research evidence on the implementation and scaling up of treatment programmes for priority mental disorders (depression, alcohol use and psychosis, with the addition of epilepsy in Nepal, Uganda and Ethiopia) in primary and maternal healthcare contexts in low resource settings. It seeks to achieve this through the following overlapping phases and activities:
- Inception (2011-12) - develop district specific integrated mental healthcare plans (MHCPs) comprising packages of mental healthcare for delivery in primary and maternal healthcare.
- Implementation (2012-16) - implement the MHCPs in partnership with Ministries of Health in PRIME countries (Uganda, Ethiopia, South Africa, India and Nepal), and evaluate the feasibility, acceptability and impact of these plans in primary healthcare and maternal healthcare.
- Scaling Up (2016-17) - evaluate the scaling up of these packages of care at district or sub-district levels.
- Extension (2017-19) – use data and evidence gathered during the implementation and scale up phase to refine the PRIME MHCPs, publish findings and ensure PRIME research is understood, effectively shared, and used to inform policy and practice.

Summary supporting narrative for the overall score in this review
The programme has scored an A+. PRIME has continued to function effectively as a consortium, achieving or exceeding all our logframe targets. Research activities have included the data cleaning and analysis of the implementation phase of PRIME, the completion of scale up in Ethiopia, Nepal and South Africa (n=59 facilities), quality improvement work in all five countries and a specific focus on developing and implementing maternal mental health interventions. 23 peer reviewed publications and 13 presentations at scientific conferences in the last grant year. Research uptake activities have included ongoing engagement with the media and 82 meetings with policy makers and planners at district, national and international levels have been produced. Different audiences are engaging in PRIME`s work, including academics (cited 2223 times in Google Scholar), media (206 media citations) and policy makers; PRIME research has been cited in 13 international documents which are likely to affect policy and practice, including the draft WHO mhGAP operations manual, and various national and sub-national policy documents in PRIME countries.

Recommendations for the year ahead
- PRIME has identified the challenge of balancing time and resources to both maximise dissemination of outputs versus publication writing. The PRIME leadership team and country teams should continue to maintain oversight of time and resource management to ensure that opportunities to disseminate results are maximised without impacting on the writing and publication of PRIME research, particularly the key outcomes papers. The PRIME publication list should be reviewed monthly to ensure work remains on track. (ongoing)
- PRIME is in an intense final phase of writing up their findings, including revising the district mental healthcare plan model. It will be important to ensure that this updated version is disseminated and shared effectively, particularly to those currently using and rolling out the old plan (ongoing).
- A key challenge during the reporting year has been for PRIME PhD students (many of whom are also key members of PRIME staff, e.g. PIs and project coordinators) to balance their scientific work with other broader needs of the programme. Now that field work is winding down, this challenge has reduced but with the demands of key dissemination events and activities over the final year, and with potential increase in focus on new grants and projects that are starting, PRIME should closely monitor progress, including setting clear deadlines and protecting time for publication writing (ongoing).
- Amendments to the logframe should be made as outlined in section C (by December 2018).
- Learning objectives for PRIME during the final year of the programme include: identifying the barriers to success of implementing and scaling up integrated district metal healthcare plans, and strategies that can be used to overcome them.
- PRIME should upload research outputs and outcomes into ResearchFish after March 2019.