PROJECT NAME	Foundation for Civil Society Programme 2011 - 2015
IMPACT	Indicator					Baseline			Milestone Y1					Milestone Y2					Milestone Y3					Milestone Y4					Assumptions
Tanzania is democratically governed and has achieved its 2025 vision in the fight against poverty and a better quality of life for all its citizens;;	Improved Tanzania’s ranking on selected governance and accountability indices	Planned				45.2 (percentile ranking, WBI, 2008)			46					47					48					48					Continued government commitment to political and governance reforms
		Achieved
						Source
						World Bank Institute Governance Indicators
	Indicator					Baseline			Milestone Y1					Milestone Y2					Milestone Y3					Milestone Y4
	Improvements in political and civil rights.	Planned				Political Rights (4); Civil Rights (3); / (Freedom House 2009)			Political Rights (4); Civil Rights (3);					Political Rights (3.5); Civil Rights (2.8);					Political Rights / (3); Civil Rights / (2.5);					Political Rights / (3); Civil Rights / (2.5);
		Achieved
						Source
						Freedom House; Afrobarometer; US State Department reports / Tanzania Human Rights Reports

OUTCOME	Indicator					Baseline				Milestone Y1					Milestone Y2					Milestone Y3					Milestone Y4					Assumptions
More citizens (especially poor and marginalized) are more empowered to participate, influence and monitor pro-poor policies and budgeting processes for improvement of service delivery in Tanzania by 2015	% of citizens saying they make a difference by publicly expressing views on local issues that affect them		Planned			53% (2007)					65%					80%					Continued GoT commitment to reforms and creating enabling environment for citizen participation in monitoring policy and service delivery
			Achieved					87.76%
			Source
			FCS’s commissioned survey
	Indicator					Baseline					Milestone Y1					Milestone Y2			Milestone Y3					Milestone Y4
	Proportion of citizens reporting satisfaction on quality of delivered basic services by the government		Planned			44%					60%					60%
			Achieved					54.55%
			Source
			FCS’s commissioned survey
INPUTS (£)	DFID (£)		Govt (£)			Norway, SIDA, Netherlands, CIDA, Swiss (£)					Total (£)					DFID SHARE (%)
	£8.0 million		-			£14.7 million					£22.7 million					35%
INPUTS (HR)	DFID (FTEs)
	0.2 FTE – Governance Advisor / 0.1 FTE – Deputy Programme Manager
OUTPUT 1	Indicator					Baseline					Milestone Y1					Milestone Y2					Milestone Y3					Milestone Y4					Risks
IMPACT WEIGHTING 25% / More citizens are more aware of their civic rights and responsibilities
	number and quality of new CSOs supported to promote civic and human rights (A)				Planned			0					15					15					15					15					See BC and submission for details
					Achieved					13					33					104
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database; (# supported by FCS x % of DFID fund)
	Indicator					Baseline		Milestone Y1					Milestone Y2					Milestone Y3					Milestone Y4				Risks
	Number of men and women enabled by DFID to access quality and user friendly information on services, rights and entitlements (A)				Planned			0.5		1m					1m					1m					1m				See BC and submission for details
					Achieved					936,000					2,737,973					2.36m
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database; (# enabled by FCS x % of DFID fund)
	Indicator					Baseline					Milestone Y1					Milestone Y2					Milestone Y3					Milestone Y4		Risks
	Number of new CSOs supported to increase citizens involvement in local government planning and budgeting exercises (A)				Planned		0					15					15					15					15		See BC and submission for details
					Achieved					26					11					5
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database; (# supported by FCS x % of DFID fund)
INPUTS	DFID (FTEs)				DFID (£)			Govt (£)					Other (£)					Total (£)
						-

OUTPUT 2	Indicator					Baseline					Milestone Y1				Milestone Y2					Milestone Y3					Milestone Y4					Risks
IMPACT WEIGHTING 20% / Increased CSOs role in contributing to improved transparency at a local level i.e. how LGAs/GoT allocate and utilize public resources	Number of new CSOs supported to mobilize citizens through the implementation of Public Expenditure Tracking (PETS) at local levels (A)				Planned			0					9				9					9					9					See BC and submission for details
					Achieved					10				12					22
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database / (# supported by FCS x % of DFID fund)
	Indicator					Baseline					Milestone Y1				Milestone Y2					Milestone Y3					Milestone Y4					Risks
	Number of new CSOs supported to mobilize citizens through the implementation of Public Service Delivery Surveys (including Social Accountability Monitoring) at local levels (C)				Planned			0					5				5					5					5					See BC and submission for details
					Achieved					12				7					15
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database
INPUTS	DFID (FTEs)				DFID (£)			Govt (£)					Other (£)					Total (£)
						-

OUTPUT 3	Indicator					Baseline					Milestone Y1				Milestone Y2					Milestone Y3					Milestone Y4					Risks
IMPACT WEIGHTING 20% / increased CSO involvement on empowering women, addressing gender inequities and issues affecting other vulnerable groups	Number and quality of new CSOs supported to sensitize and empower women on their land rights (C)				Planned			0					36				36					36					36					See BC and submission for details
					Achieved					38				44					36
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database / (# supported by FCS x % of DFID fund)
	Indicator					Baseline					Milestone Y1				Milestone Y2					Milestone Y3					Milestone Y4					Risks
	% of women enabled to effectively take up leadership positions in the communities (CBOs, CSOs and LGAs) (C)				Planned			0					35%				35%					50%					50%					See BC and submission for details
					Achieved					36%				36%					36%
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database
	Indicator					Baseline					Milestone Y1				Milestone Y2					Milestone Y3					Milestone Y4					Risks
	Number and quality of CSOs supported by DFID to address issues affecting people with disability, pastoralists and other minority groups (including land, livestock and environmental issues) (A)				Planned			0					20				20					20					20					See BC and submission for details
					Achieved					25				45					55
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database / (# supported by FCS x % of DFID fund)
INPUTS	DFID (FTEs)				DFID (£)			Govt (£)					Other (£)					Total (£)

OUTPUT 4	Indicator					Baseline					Milestone Y1				Milestone Y2					Milestone Y3					Milestone Y4					Risks
IMPACT WEIGHTING 20% / Strengthened CSOs organizational capacity and policy engagement effectiveness	Number and quality of new CSOs supported by DFID on institutional and organizational capacity (A)				Planned			0					90				100					100					100					See BC and submission for details
					Achieved					171				92					107
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database(# supported by FCS x % of DFID fund)
	Indicator					Baseline					Milestone Y1				Milestone Y2					Milestone Y3					Milestone Y4					Risks
	% increase of policy dialogues with active participation of CSOs (C)				Planned			25%					60%				35% (revised downwards)					80%				80%					See BC and submission for details
					Achieved					30%				76%					82%
					Source
					FCS Semi-Annual and Annual Reports
	Indicator					Baseline					Milestone Y1			Milestone Y2					Milestone Y3					Milestone Y4					Risks
	Proportion of FCS supported CSOs with improved overall impact capability increased (C)				Planned			55%					60%			65%					65%					65%					See BC and submission for details
					Achieved					61%			68%					85%
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database
INPUTS	DFID (FTEs)				DFID (£)			Govt (£)					Other (£)					Total (£)

OUTPUT 5	Indicator					Baseline					Milestone Y1			Milestone Y2					Milestone Y3					Milestone Y4					Risks
IMPACT WEIGHTING 15% / Foundation for Civil Society is delivering high quality services and is efficiently and effectively managed and governed	Number of monitoring visits to grantees (C)				Planned					180			180					450					450					See BC and submission for details
					Achieved					168			236					465
					Source
					FCS Semi-Annual and Annual Reports / FCS Audited Financial Statements
	Indicator				Baseline			Milestone Y1					Milestone Y2					Milestone Y3					Milestone Y4					Risks
	Number of applications received and processed on time (C)				n/a			1500					1500					2000					2000					See BC and submission for details
					Achieved			2152					2462					3307
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database
	Indicator				Baseline			Milestone Y1					Milestone Y2					Milestone Y3					Milestone Y4					Risks
	% of CSOs supported by FCS that implement projects in the rural areas (C)				21% of grantees are located in rural areas and 40% of grantees implementing projects in rural areas (2010)			50%					65%					75%					75%					See BC and submission for details
					Achieved			59%					51%					51%
					Source
					FCS Semi-Annual and Annual Reports / FCS Grantee Database
INPUTS	DFID (FTEs)				DFID (£)			Govt (£)					Other (£)					Total (£)