Annual Review - Summary Sheet

Title: Humanitarian support to Central Africans and Central African refugees in Cameroon and Chad
Programme Value: £35 million (including £7m contingency that can be activated on Ministerial approval)		Review Date: July 2015
Programme Code: 204852	Start Date: 17 July 2014	End Date: 31 March 2016

Summary of Programme Performance
Year	2014/15
Programme Score	A
Risk Rating	High

Summary of progress and lessons learnt since last review

The 2015/16 £35 million Business Case for responding to the Central African Republic (CAR)[1] Humanitarian Crisis was approved in 2014 and included two outcomes focusing on refugee populations in Cameroon and Chad and on affected populations inside CAR. Outcome 2 (refugee programmes of £10 million in 2014 and £4.5 million in 2015) were the first to be implemented from July 2014 to July 2015 and form the major focus of this Annual Review. Programmes under outcome 1 for populations inside CAR began later (start up in April 2015) as funding was until that point provided through a previous Business Case (DevTracker 4408472). A brief assessment is made in this Annual Review of their progress in starting up.
[1] This and all further abbreviations are referenced in the annex.

Overall the programme has made good progress and achieved its stated outcome of significantly reducing suffering and saving lives among CAR refugees.

The cumulative number of people reached under the programme is 250,068 vs. a target of 352,100. The original target was not achieved as it was based on a UNHCR planning figure for the number of refugees expected to arrive in Cameroon in 2014 (higher than the final number of people who arrived) and following changes in the beneficiary counting methodology. UK funding has helped agencies provide a successful response to emerging needs and bring assistance up to minimum standards. Significant mortality drivers such as malnutrition have been brought under control thanks to DFID and other contributions. On that basis we assess the programme is achieving its outcome.

By the end of 2014 with the support of DFID and other donors, assistance in refugee sites in Cameroon started to reach minimum emergency response standards in water, food and emergency shelter.[2] Among people reached with food and nutrition assistance, Global Acute Malnutrition prevalence dropped to below emergency thresholds. The recovery rate for children suffering acute malnutrition was brought up to higher than target levels. Of particular concern were food and nutrition pipeline breaks in Cameroon in 2015. While the situation in camps has improved, there are still significant gaps due to serious under-funding. These included limited sanitation (latrines), durable shelter and livelihoods opportunities. In Chad the total Central African refugee population has been profiled but there have been gaps in assistance coverage.
[2] Programme information from WFP project report for EMOP 1200689, MSF and UNHCR project reporting to DFID.

Recommendations:
- DFID to follow up with partners on the use of cash and local procurement to deliver food in Cameroon and to closely monitor the food and nutrition pipeline.
- DFID to continue to coordinate closely with other donors on programme funding and prioritisation and continue to undertake quarterly field visits.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Not yet live on DevTracker
DevTracker Link to Log frame:	Not yet live on DevTracker

Outline of the programme

The UK has supported the humanitarian response in the Central African Republic (CAR) since July 2013 through three business cases. The first two Business Cases (£5 million in 2013 and £18 million in 2014) provided emergency multi-sectorial assistance to populations in CAR affected by the conflict. The third Business Case for £35 million approved in 2014 aimed to address both the needs of CAR refugees and CAR populations until March 2016. It included a £10 million allocation for CAR refugees released in 2014, as well as £13.5 million for affected populations inside CAR and £4.5 million for CAR refugees both released in April 2015. It also includes a £7 million contingency facility through which funds can be released subject to Ministerial approval.

This Annual Review focuses on the performance of the refugee assistance programme but also includes brief comments on progress being made with the recently released funding to programmes inside CAR and for CAR refugees.

The CAR refugee programme aims to support Central African refugees and other vulnerable people (third country nationals, returnees and host communities) in Cameroon and Chad following the unprecedented levels of violence in CAR from late 2013. It includes:
- £6.5 million through the United Nations High Commissioner for Refugees (UNHCR) to provide multi-sectorial assistance for refugees in Chad (£1.5 million) and Cameroon (£5 million).
- £2.5 million through the World Food Programme (WFP) to provide food and nutritional assistance in Cameroon.
- £1 million for Médecins Sans Frontières (MSF) for emergency healthcare and malnutrition assistance in Cameroon.

Context

Several rebel groups (the Seleka coalition) joined together in December 2012 in CAR to launch a series of attacks, leaving them eventually in control of CAR in March 2013. A gradual breakdown of law and order ensued along with a total collapse of administration and basic services. Violence took a sectarian turn from 2013. CAR’s Muslim population was accused of supporting Seleka forces, which included many Muslim combatants among its ranks. Self-appointed defence groups (anti-Balakas) started fighting back against the Selekas, and as they progressed, turned their weapons against the unprotected Muslim population. In the final months of 2013, outbreaks of fighting between belligerent forces led to arbitrary killings and looting, culminating in clashes in December that killed more than 2,000 people in a matter of hours. Bangui’s entire population of 800,000 and the population of most towns sought refuge at once alongside African Union and French peace-keeping troops, leaving in the space of a week a million people displaced. Internally displaced Muslim people found themselves on sites surrounded by anti-Balaka forces and at risk of violence if they should leave their enclave. Much of CAR’s population – and specifically its Muslim population – was forced to flee to neighbouring countries in convoys and on foot.

Around 300,000 people fled CAR for Cameroon, Chad and the Democratic Republic of the Congo in the first quarter of 2014 including 127,000 who fled to Cameroon and 14,000 who fled to Chad. Chad also received around 120,000 returnees[3]. This has brought CAR’s overall refugee population to 462,000 people. Whilst initial convoys brought people from the capital with some of their properties, many people had been stranded for months in camps with little access to food and services before fleeing or spent months traveling on foot. Refugees arrived in extremely poor condition particularly in Cameroon, which many reached after months of hardship in CAR’s forests and repeated attacks by anti-Balakas.
[3] Second or third generation migrants of Chadian nationality who for many had been born in CAR and had lost all ties with Chad.

More than 90% of refugees arrived in Cameroon without any asset.[4] By May 2014 acute malnutrition had reached extremely high levels.[5] UN agencies and NGOs had more of a development oriented set-up in Cameroon and were challenged by the scale and severity of humanitarian needs.
[4] According to estimates provided by humanitarian agencies to DFID in a July 2014 assessment in Cameroon.
[5] In May 2014, global acute malnutrition rates had reached up to 25-30% and severe acute malnutrition rates 10% amongst refugee populations in Cameroon.

Priority was given to registration and profiling by UNHCR in order to determine the needs of the new caseloads and to provide urgent assistance and protection.

By the end of July DFID had assessed that the humanitarian response for Central African refugees urgently required funding[6] to support a response that was and remains severely under-funded. In Cameroon, DFID was in 2014 the third largest humanitarian donor to the Strategic Response Plan, with a contribution equivalent to 16% of all funding. The most significant early contribution to the response came from the UN CERF in April 2014, but agencies such as UNHCR, WFP and MSF relied mainly in the first six months of 2014 on internal borrowing facilities. The US in June and the UK in July were the first donors to provide large commitments (i.e. exceeding £2 million), followed shortly by the European Commission's Humanitarian Aid and Civil Protection Department (ECHO).
[6] DFID field visit report. DFID submission to support the regional response to CAR refugees in Cameroon and Chad in July.

The humanitarian response was slow to take off due to limited humanitarian expertise in country, and slower to be funded by donors including DFID for lack of visibility around humanitarian needs. This enabled problems to last longer than required, such as high malnutrition rates.

Summary of humanitarian assistance under this business case

Programme component	DFID partners
Support for refugees in Cameroon and Chad in FY[7]14/15 (£10m)	MSF in Cameroon (£1m), WFP in Cameroon (£2.5m), UNHCR Chad (£1.5M), UNHCR Cameroon (£5m)
Support for refugees in Cameroon in FY 15/16 (£4.5m)	WFP (£1.5m), START network NGOs (£3m)
Support for CAR populations in FY 15/16 (£13.5m)	CHF (£2m), ICRC (£2m), NGO health consortium (£3m), NGO livelihoods/protection consortium (£3m), FAO (£3m), Monitoring & Evaluation (£0.5m) / (NB. ICRC and CHF payments made at the very end of FY 14/15)
[7] Financial Year.

NB. The business case includes a further £7 million of contingency funding that can be activated on Ministerial approval.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

DFID has reached under this programme 250,068 people vs. a target of 352,100 people (including double counting across agencies[8]). This includes Central African refugees as well as other vulnerable people affected by the crisis including Chadian returnees and vulnerable host communities. The difference between target and achievement reflects changes in counting methodology rather than shortcomings in programme delivery. UNHCR’s planned reach in Cameroon was based on projected arrivals of 180,000. These plateaued however at around 127,000. DFID also agreed with UNHCR to review its beneficiary counting approach. Factoring in the response’s quality and effectiveness, the programme was judged to have met its expectations (score A).
[8] This means that one person might have benefited under multiple programmes and have been counted multiple times.

UNHCR Cameroon reached 60,000 people vs. 180,000 people targeted. This was not a reflection of performance but represented a revision of the number of refugees who had finally arrived in Cameroon. The number of people reached also had to be revised to reflect the highest number of people reached through any one UNHCR sector intervention funded by DFID. Through DFID funding and other support, UNHCR was able to upgrade water and sanitation facilities on sites up to standards and provide all refugees with transitional shelter.

UNHCR Chad reached 72,068 people vs. 56,000 people targeted. UNHCR estimates that a protracted caseload of 80,545 refugees also benefited from the assistance in some sectors.[9] UNHCR also aimed to address gaps, taking on more responsibilities towards returnees than originally planned.
[9] DFID funding represents 7% of the UNHCR operation requirements - the current financial reporting is multi-donor and includes activities funded by both DFID and other donors.

WFP reached 88,000 people via general food distributions for a period of three months vs. 86,100 targeted. WFP faced serious pipeline disruptions, affecting the overall quality of assistance, and is exploring local procurement and cash options as potential alternatives. Despite this, in 2014, WFP’s response contributed to bringing malnutrition rates below emergency thresholds in all but two sites.[10]
[10] For DFID’s corporate reporting on unique beneficiaries reached with cash and food, the total number of people reached with food is 88,000. Beneficiaries did not receive cash assistance.

MSF reached 30,000 beneficiaries in Cameroon with healthcare support as anticipated. Its intervention supported by UK funding enabled it to bring recovery rates for complicated malnutrition cases above 90% (vs a target of 75%).

Overall, we assess that in a very complex and fluid operating environment the programmes were successful in meeting the needs of the target populations and contributed to stabilising the humanitarian situation and that outcome broadly met expectations. A more comprehensive assessment of the quality of delivery is provided in the section on Value for Money and in output scoring.

Overall output score and description

Outcome 1 (CAR)
Output 1: Will be fully reviewed under the Programme Completion Review due in June 2015.
Output 2: Will be fully reviewed under the Programme Completion Review due in June 2015.
Output 3: Will be fully reviewed under the Programme Completion Review due in June 2015.
Output 4: Will be fully reviewed under the Programme Completion Review due in June 2015.

Outcome 2 (CAR refugees)
Output 1: Food Security B – Output moderately did not meet expectations.
Output 2: Health A+ – Output moderately exceeded expectations.
Output 3: Multi-Sector A – Output met expectation.
Output 4: Will be fully reviewed under the Programme Completion Review due in June 2015.

Key lessons

- To avoid a reduction in food and breaks in food assistance, DFID will need to ensure partners consider alternatives for delivery, such as cash and local procurement as far as possible and before significant breaks in food delivery occur.
- DFID Field visits were critical in capturing the experience of beneficiaries at the receiving end of assistance and highlighting programme quality issues. This information was not always captured in partner reports but has enabled DFID to remain sighted and support quality assistance.
- Consider the incentives that drive good partner practice and how DFID can support these (e.g. clear and meaningful targets at the onset of arrangements, responding to beneficiary feedback, and flexibility in responding to any programme course correction required if beneficiary needs change).
- The scale and severity of refugee needs in this crisis led DFID to make the decision to start funding in a new country. The success of the intervention in providing life-saving assistance and the dramatic improvement in malnutrition and mortality indicators justify this decision to intervene. DFID might have intervened earlier by taking a no-regret approach and conducting needs assessments sooner, in the absence of clear evidence around needs (other than refugee figures).

Key actions
- Partners to report on the indicators and targets provided in programme proposals to DFID. Partners should make clear the rationale for any changes to these if they occur. This not only allows DFID to better monitor performance but may identify early opportunities for UK support such as advocacy or resources to help address issues.
- DFID to follow up with partners on the use of cash and local procurement to deliver food in Cameroon.
- DFID to continue to coordinate closely with other donors on programme funding and prioritisation and continue to undertake quarterly field visits.

Has the logframe been updated since the last review?

N/a – new programme.

## C: DETAILED OUTPUT SCORING (1 page per output)

Outcome 1 - CAR

The four outputs under this outcome encompass activities that have only been under implementation since April 2015 and so progress is only assessed in brief. A comprehensive review will be conducted as part of the Project Completion Review due in 2016.

Output Title	Livelihoods and food security - The agro-pastoral production in the targeted areas is improved and reinforced
Output number per LF		1	Output Score	N/A
Risk:		High	Impact weighting (%):	/
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	/

Indicator(s)	Target	Progress	Output score
Number of people reached through general food distribution and cash transfers by ACF)/DRC/SI	480	N/A	N/A
Number of people reached through livelihood assistance by ACF/ DRC/ SI	158,750
Proportion of the targeted population improving their Coping Strategy Index Score	50%
Number of people reached through general food distribution, cash and voucher (GFD) by the ICRC	8,932
Number of people reached with livelihood assistance by ICRC	4,015
Number of people reached in food security/livelihood sector by CHF	3,540
Number of people who have received livelihood assistance through the FAO	172,060
Proportion of FAO project beneficiaries that are not induced to resort to negative mechanisms at least for six to eight months	85%

This component started in April 2015 and will last until March 2016. We are therefore not in a position at this stage to score it against key milestones or to review the impact achieved by partners.

In the first quarter of this component, the ICRC has completed procurement and started timely distributions for up to 10,000 households.

FAO has completed procurement for the first phase of the agricultural season in April and signed agreements with its partners. FAO and partners reported lower groundnut germination rates at delivery points than expected (60% vs. 80% expected) due to goods piled by transporters on top of the fragile seeds. This problem particularly affected FAO partners that received larger loads (including the Solidarites International consortium). FAO has been liaising with partners and preparing to provide a top up of seeds suitable for the second phase of the season as replacement for beneficiaries.

The SI consortium was able to identify beneficiaries (15,000 households) and distribute seeds on time in the first phase of the season. All three partners in the consortium noted some problems with groundnuts and SI and DRC were in contact with FAO to obtain a top up for their beneficiaries. SI had agreed to distribute paddy seeds to beneficiaries, but was faced with last minute reluctance from beneficiaries (who had previously agreed to these seeds) who expressed the need for technical support due to their limited familiarity with the seeds.[11] The 12 tonnes of rice were nonetheless distributed, though SI was not able to provide the required technical support on cultivation techniques, creating the risk of lower than expected returns.
[11] FAO has confirmed that paddy has been cultivated in this part of Ouham.

All organisations still have to implement post-planting monitoring, which will highlight strengths and weaknesses in the operation. FAO has noted substantial concerns with rainfalls in 2015, which have come even later than in 2014. As of July, the rainy season has not fully started in Northern parts of the country, which places the harvest at risk.

Recommendations:
- SI to ensure its team have access to technical advice from an agronomist.
- DFID to monitor additional seed distribution and post-harvest monitoring.

Output Title	Health and nutrition - Affected population have an improved access to healthcare
Output number per LF		2	Output Score	N/A
Risk:		High	Impact weighting (%):	/
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	/

Indicator(s)	Target	Progress	Output score
Number of beneficiaries reached in the healthcare sector by ICRC	30,422	N/A	N/A
Number of beneficiaries reached in the healthcare sector by CHF	40,296
Number of beneficiaries reached in the healthcare sector by the IMC consortium	269,354
Health service utilization rate (based on number of beneficiaries reached with new consultations)	1
Number of acute malnutrition cases from the targeted areas that gain access to treatment	1,277
2.6. Cured rate among children treated for MAM and SAM	>75%
Number of health facilities with access to sanitation with a ratio of 1 latrine/ 20 users	10

This component started in April 2015 and will last until March 2016. We are therefore not in a position at this stage to score it against key milestones.

A number of activities implemented by the ICRC and the IMC consortium are continuations of 2014 DFID-funded activities. The IMC consortium encompasses SC and MENTOR Initiatives. SC, MENTOR and the ICRC have continued the work carried out in 2014 in primary and secondary healthcare, mobile clinics and through community health workers. SC is working in Basse-Kotto, MENTOR in Ouham and Ouham-Pende and the ICRC primarily in Nana Gribizi and Bangui, with views to expanding to Ouaka.

IMC’s activities are aimed at new health posts and communities in Haute-Kotto. IMC has completed its recruitment and has begun providing mobile consultations and supervisions at health facilities. IMC staff have supervised new health centres every other week in between April and June 2015 and have organised three mobile clinics weekly. Mobile clinics were slightly less frequent than planned due to mounting insecurity on the access roads. Between April and June 2015, Save the Children has reported a high mortality rate among complex malnutrition cases at Alindao hospital and has planned to identify remedial measures with the support of the consortium members. These problems had already been identified and reported upon in DFID’s CAR 2014 Programme Completion Review. OXFAM’s recruitment and procurement is ongoing. A number of water points identified for refection will not be in the immediate vicinity of the health posts (though they will be within 500m). OXFAM and consortium partners therefore plan on identifying suitable mechanisms to ensure centres have adequate access to water (including adequate storage facilities).

Recommendations:
- DFID to monitor solutions implemented to tackle mortality at Alindao hospital.
- DFID to monitor that water storage facilities are adapted to health centres’ water needs.

Output Title	Protection - Central Africans enjoy an improved protection environment
Output number per LF		3	Output Score
Risk:		High	Impact weighting (%):
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?

Indicator(s)	Target	Progress	Output score
Number of beneficiaries supported in the protection sector by the CHF	14,360	N/A	N/A
Number of beneficiaries supported in the protection sector by the SI consortium	74,600
Increase in the % of people who have perceived an improvement in their protection and safety situation	+25%
Number of GBV survivors who access remedial services through IMC, DRC and ICRC.	N/A

This component started in April 2015 and will last until March 2016. We are therefore not in a position at this stage to score it against key milestones.

During this first quarter, the ICRC has continued to carry out standard protection activities, including on the protection of civilians, in detention and on family reunification.

Over this quarter, DRC has received 280 people in its listening centres. DRC has also worked with 30 protection committees, of which 5 were receiving additional support to resume functioning.

Output Title	Performance of the system and coordination - The CHF actively contributes to strengthened humanitarian coordination and response
Output number per LF		4	Output Score	N/A
Risk:		High	Impact weighting (%):
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?

Indicator(s)	Target	Progress	Output score
4.1. Percentage of overall funding received from all donors by 30 June 2015 is allocated before 31 December 2015	>80%	N/A	N/A
4.2. Percentage of projects monitored through field visits within their project duration	40%

This component started in January and will last until December 2015. We are not yet in a position to score it against key milestones.

In the first six months of its operations, the CHF has released a first allocation and has launched its second allocation, due to be finalised in July. The CHF has also started rolling out risk management tools, including a partner performance index, which helped inform its second allocation.

Outcome 2 – CAR refugees

Output Title	Food security - Central African refugees receive basic food assistance in Cameroon.
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target	Progress	Output score
Number of people reached through general food distribution (GFD) in Cameroon.	March 2015: 86,100 / March 2016: 59,467	88,000 (for a period of 3 months) / N/A	B / N/A

Key Points

The WFP programme aimed to deliver urgent food (general food distribution or GFD) and nutrition commodities (blanket and targeted supplementary feeding) to meet the basic food and nutrition needs of CAR refugees in Cameroon. DFID started its support to WFP in July 2014 and extended it in 2015. WFP’s performance in the period under review has been mixed, with positive results in reducing global acute malnutrition in 2014, but also extensive pipeline breaks in 2015 caused by external factors and insufficient oversight.

WFP has delivered the quantity of food under the DFID grant as anticipated. The number of people reached slightly exceeds targets as funding was redirected from DFID funded nutritional activities. WFP received a contribution from another donor specifically for nutrition and they reallocated DFID funding to better meet food needs. The WFP annual report for Cameroon indicates that the latest figure on the proportion of the overall population reached was 57% compared to the 66% target (with a highly nomadic population, the whereabouts of a proportion of refugees could not be identified).

Monthly screening undertaken on all children aged 6-59 months indicated a decrease in the prevalence of GAM among beneficiaries targeted by food and nutrition assistance. The rate dropped from 15.2% in May to 2% in December 2014 for children aged 6-59 months. The mortality rate declined significantly among children treated for moderate malnutrition from 0.43% in June to 0 in September 2014. But there are still challenges. UNHCR survey at the end of 2014 in the seven refugee sites found that malnutrition was still above emergency thresholds in two sites, suggesting more endeavours will be required to screen all children and provide a comprehensive package of food and nutrition support.

The recovery rate for children with MAM increased from 65 per cent in June to 67% (vs. a target of 75%) according to the latest follow-up in January 2015. The MAM treatment mortality rate at latest annual report is however well below the target which is positive. WFP report that severe food security situation as well as harmful young child feeding practices presented challenges to recovery from malnutrition.

The delivery of DFID funded commodities was delayed with breaks in essential GFD to refugees. Port congestion at Douala presented delays to delivery. WFP also had to replace sorghum, which was picked up by WFP quality checking as not fit for consumption. This required in turn DFID to extend the WFP contract end date from 31 March to 31 July 2015. Locally procured rice, replacing the sorghum, has now been delivered. DFID’s monitoring visit in April 2015 also picked up pipeline breaks and ration reductions in February and March 2015 (a 2 month break in preventative blanket supplementary feeding, and a reduction to half rations for two week periods in GFD in February and March).[12]
[12] According to DFID field visit report.

WFP also had to resort to loaning commodities from the CAR regional emergency operation to meet an urgent gap in their underfunded Nigerian refugee operation (approved by DFID and since replenished). Some efforts have been made by WFP to explore alternatives to ration reductions and pipeline breaks as a last resort, including local procurement and cash assistance. WFP has now finalised a market assessment and is considering the use of cash rather than commodity (in-kind) assistance.

Overall, we assess the output moderately did not meet expectations given WFP’s failure to provide steady supplies particularly in GFD.

Recommendations

DFID to prioritise engagement in country with WFP on overall pipeline management and opportunities for local procurement and cash assistance.

DFID to monitor challenges for delivery likely to result in ration reductions and pipeline breaks and opportunities to help address these challenges.

Output Title	Health and nutrition - Central African children in Cameroon receive treatment for acute under-nutrition.
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target	Progress	Output score
2.1. Rehabilitation recovery rate (%) for children suffering SAM who have received MSF Community Based Management of Acute Malnutrition.	September 2014: 65%. / October 2014: 75%.	September 2014: Garoua Boulai 97% and Batouri 80% (MSF areas of intervention). / October 2014: Garoua Boulai 97% and Batouri 93%.	A+
2.2. Number of people reached with MSF health interventions.	30,000.	30,000.	A

The MSF programme aimed to deliver emergency healthcare and therapeutic treatment for severe acute malnutrition. MSF was the first INGO to respond to the crisis in 2014 by setting up mobile clinics and providing medical care on refugee sites complemented by water and sanitation activities to address the crisis.

MSF has met and exceeded agreed targets by reaching 30,000 people with urgent health interventions[13] and exceeding the final 75% recovery rate for children with SAM.
[13] The overall beneficiaries for MSF programme for Central Africans in Cameroon is 50,000 (30,000 people reached with UK funding).

Central Africans generally arrived in Cameroon in an extremely poor condition with very high rates of malnutrition: GAM reached up to 25-30% and SAM rates 10% in June 2014. The baseline recovery rate for children suffering SAM was 59% in Garoua Boulai and 61% in Batouri at July 2014. By September MSF had exceeded their 65% recovery rate for children suffering SAM. MSF’s overall programme objective was to stabilise and reduce mortality and morbidity rates amongst Central Africans. Mortality rates were reduced to acceptable levels across the MSF area of intervention to 0.1 - 0.3 by October (against a target of under 5 mortality rate <1). A small cholera outbreak occurred in November 2014. However a multi-partner response plan was immediately implemented with MSF leading on health and the outbreak was successfully contained.[14]
[14] MSF reporting to DFID.
While the immediate emergency phase has passed, MSF has noted that attention is still needed to ensure the stability and quality of healthcare. At the end of the DFID funded MSF programme the number of patients in the intensive therapeutic feeding centres remained high and with a still unstable situation in Central African Republic, MSF has extended its operations in Cameroon to at least the end of 2015.

Recommendations

DFID to monitor MSF handover to more development orientated partners over 2015.

Output Title	Multi-sectorial (UNHCR) - Central Africans arriving in Cameroon and Chad as refugees have their most basic needs met, including shelter and water and sanitation.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	65%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Targets	Progress	Output score
3.1. Average supply of water per person per day in the 7 refugee sites reaches a minimum of 15 litres per day in Cameroon (WASH).	December 2014: > 15.	16.4 at December 2014. However the sites of Gado 1&2, Borgop and Mbilé still had less than 15 litres per person per day. / 19 at March 2015.	A
3.2. Number of emergency shelters provided in Chad (Shelter).	636.	3,386.	A
3.3. Number of people reached with UNHCR multi-sector assistance in Chad.	56,000.	72,068 of the new caseload of refugees and returnees, although a protracted caseload of 80,545 benefitting from the assistance in some sectors.	A+
3.4. Number of people reached with UNHCR multi-sector assistance in Cameroon.	180,000 (overall number of anticipated refugees).	60,000 (the highest number of people reached through any one UNHCR sector intervention).	A-

Key Points

The UNHCR programme in Cameroon aimed to ensure the protection of refugees, including through registration, the provision of shelter and non food items, access to water, sanitation and hygiene as well as healthcare. UNHCR also supported access to education through the rehabilitation and construction of school buildings. In Chad, the programme supported the needs of refugees and ‘returnees’[15] across sectors, including shelter and infrastructure, water and sanitation and protection.
[15] Returnees are people of Chadian nationality who have had to flee CAR during spikes of sectarian violence in 2013-14. Many are second of third generation migrants and no longer have family or social ties in Chad.

In Cameroon, thanks to UK funding and other donors, UNHCR report that 100% of refugees on sites had access to transitional shelter and 90% of people were accommodated in family shelters with access to 3.5 sqm per person by the end of this intervention. UNHCR has begun to roll out semi-durable shelter but were not able to generalise this across the response as they did not have sufficient funding. UNHCR has provided non food items (such as water storage, cooking utensils and clothes) as well as soap to refugees. DFID found that not all beneficiaries had managed to get the full package of items, while hygiene items were not replenished at the required frequency. By mid-2014, 40 people were using one latrine in camps in Cameroon. By the end of 2014 this had been improved but over 20 people were still using one latrine. An average of 6.4 litres of potable water was available to people on sites per day by mid-2014. By the end of 2014, this had increased but was still less than 15 litres at three sites, and UNHCR reported delays with the construction of boreholes.

The situation improved in 2015 with the average consumption reaching 19 litres per person per day, except for Gado where water trucking continues. This indicator does not however cover Central Africans living outside of sites (some 50% of people) for whom assistance has been even more limited than within the UNHCR refugee sites. The coverage of assistance has been hampered by underfunding – the Cameroon Strategic Response Plan for 2014 was just over 40% funded at November 2014[16], but eventually reached 58%.
[16] According to agency reporting captured in the November 2014 DFID field visit.

In Chad and despite understaffing, UNHCR was able to profile 70% of the targeted Chadian returnee population and 100% of Central Africans thanks to UK funding but it has been challenging to meet humanitarian needs overall. UNHCR had aimed to construct 636 emergency shelters using DFID resources. Changes in the composition of the beneficiary caseload required adapting the targets. The need for emergency shelter also increased significantly with an increase in the size of the population in need and the high number of single-person households. As a consequence funding was adjusted by UNHCR between budget lines and 3,386 shelters were constructed under DFID funding against a planned 636 with 12,485 people benefitting from these shelters. UNHCR report they were able to register Central African refugees as anticipated and 70% of the targeted returnee caseload though were challenged by understaffing. There were also gaps in assistance: for shelter, at October, nearly 30% of temporary shelter needs in Gaoui and Danamadja were not covered and 62% of shelter needs at transit site of Sido and 27% at Doyaba.

Recommendations

Continue to monitor UNHCR delivery in Chad and in Cameroon including funding pipelines and UNHCR’s ability to achieve coverage of assistance across operations and sectors.

Continue to monitor the situation of refugees both inside and outside of the camps in Cameroon including any arising assessments on nutrition and specifically the potential causes of under-nutrition, e.g. limited water and sanitation.

Output Title	Multi-sectorial (START) - Central Africans receive multi-sector assistance both in refugee camps and outside of camps in communities in Cameroon.
Output number per LF		4	Output Score	N/A
Risk:		Medium	Impact weighting (%):	/
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target	Progress	Output score
4.1. Number of people reached with multi-sector humanitarian assistance with START network activities.	March 2016. 179,526 people (91,196 female, 88,330 male)	N/A	N/A
4.2. Start Network mechanisms deliver rigorous decision-making for selecting projects and learning.	June 2015. Decisions made by the Project Selection Committee are well-documented in meeting minutes and transparent selection criteria are used. Decisions are based on needs analyses, evidence of the project’s engagement with affected people and the technical strength of proposals. / March 2016. Lessons learned have been documented with evidence of adjusting programmes in response to emerging needs analyses, engagement with affected people and the findings of their technical teams. Programmes are course-corrected if needed.	N/A	N/A
4.3. Proportion of beneficiaries (5481) who report an increase in vegetable production and acceptable food consumption score at the end of the project.	March 2016. At least 80%.	N/A	N/A

This output will be assessed at the 2015 annual review as it is too early to draw conclusions about the START network programme. The START network is an NGO consortium, which DFID supports to empower its members to collectively identify and respond to humanitarian needs. NGO proposals are submitted for peer review to the START network which functions as a funding mechanism through donor support.

The beginning of the DFID grant to START network NGOs in Cameroon has seen several teething problems arising from the use of a new mechanism. The project selection process was difficult in part perhaps due to the numerous interests represented at the table. This should be taken into account in the composition of local project selection committees. There were also communication problems between the START Network and agencies in country on the scope of the call for proposals, which could in future be avoided through improved communication.

There were some delays getting funds to partners in Cameroon. DFID was slow to make a first payment to the START network due to protracted internal negotiations around payment in advance of need. One of the two START funded partners, ACF UK, was then slow to pass on the funds to ACF in Cameroon and to its consortium partners which only received the funds in July. The START network is working to ensure that lessons are learnt and changes to the process enacted.

Recommendations:

- Monitor impact of delays at DFID, START and partner level on operations;
- DFID to review process of integration of lessons learnt into the START network’s processes.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Under this section we review the Value for Money (VfM) performance of outcome one.

Key cost drivers and performance

MSF: By far the highest cost was for staffing (51% of total project costs). The cost of international staff (comprising doctors, logistics and health managers) was 63% more than budgeted for, as the workload and working conditions did not allow a decrease in the size of the team or an increase in the length of mission duration (beyond 3 months). International travel costs for staff were higher than anticipated for the same reason.

Costs for equipment and supplies were originally forecast to be 25% of the total budget, but in fact were 13% of the total budget partly due to a timely MSF procurement which took place before the start of the DFID funding. The replenishment needs from July to October (the period of the DFID grant) were limited to medical consumables. The cost of supporting hospital inpatient referrals in the emergency response in Cameroon was greater than forecast by MSF (increase by 228%) but was examined and is consistent with requirements under the national Ministry of Health system. The other cost driver for MSF increasing significantly was the subcontracted service cost (221%) – to support sufficient security for operations. However the increase was not material relative to the total cost of the project (less than 1% of total funding).

WFP: Two expensive airlifts were used during the period of the EMOP to prevent pipeline breaks however these occurred before DFID started funding. Of UK funds spent during the period of the 2014 emergency operation 75% was spent on food and related costs, 17% was spent on direct support costs, and 8% was spent on indirect support costs. Some efforts have been made to drive down transport costs, through local procurement. In 2014 WFP also utilised local procurement to address gaps in general food distribution. Air lifts have been avoided and efforts have been made to limit road transportation through multiple and new food storage sites.

UNHCR: In Chad 45% of DFID funds were spent on providing emergency shelters at a cost of $339/unit (which is line with global practice for shelter in remote insecure environments). Including shelter, support for site operations was 61% of the total expenditure, WASH services were 15% of total expenditure, protection services were 16%, and indirect costs were 7% of the total grant. Targets and expenditure differed substantially in most sectors, as a result of funds being reprogrammed when shelter needs were substantially higher than predicted due to larger numbers of refugees and Chadian returnees than anticipated.
We are awaiting the final financial statement for UNHCR Cameroon (due June 2015). .

VfM performance compared to the original VfM proposition in the business case

The business case followed DFID’s approach to VfM, the Efficiency, Economy and Effectiveness (3Es) model. Equity is also considered under this annual review. An assessment of projects proposed in the business case focused on speed, quality/appropriateness and cost.

Speed

Speed was critical because of the extremely high malnutrition and mortality rates in new arrivals from CAR and the lack of capacity in Cameroon in early 2014 to take on a response of this size and severity.

MSF responded rapidly but in the first months the response was difficult - agency coordination was lacking as well as partners with the capacity to respond at scale. UNHCR was the first UN agency to scale up from March, relying on extensive internal borrowing facilities to begin a response. By that point more than 55,000 Central Africans had already arrived in Cameroon. There were a limited number of NGOs operating at the onset of the crisis.[17] WFP worked closely with UNHCR and later on with MSF to provide emergency rations as soon as possible after refugees entered and were registered. WFP also declared a Level 3 disaster internally to have access to adequate surge facilities and respond to the looming malnutrition crisis. WFP liaised closely with UNHCR so that they had good information on new arrivals.[18] From April/May WFP significantly scaled up. By July more actors were responding and coordination had improved.[19] DFID ability to monitor the speed of scale up in Chad was more limited with a lack of in country presence but we do know that agencies faced challenges, for example the rainy season significantly delayed the implementation of shelter in returnees’ sites and understaffing presented challenges.
[17] According to agencies responding - in reports to DFID and in field visits.
[18] DFID intervention review summary.
[19] According to agency reports to DFID.

The response was also slow in the donor community including DFID. Lack of information around needs and local absorption capacity precluded visibility over this aspect of the CAR crisis, until alarming malnutrition rates were made public after six months.

Quality/ appropriateness

In Cameroon, coverage in 2014 has been somewhat limited to refugee sites (where 50% of Central African refugees are living). The coverage of assistance for refugees living off-sites, i.e. in the community and in the bush has been patchy. Efforts were made to increase coverage towards the end of 2014 - UNHCR has conducted a rapid needs assessment in villages to survey gaps in water and sanitation in September and October. By January 2015 WFP was reaching approximately 70% of refugees who had been registered.[20] Early on in the emergency agencies with a presence in Cameroon were stretched to provide assistance across all sectors required, but as new agencies arrived and agencies were able to enhance their staffing, capacity increased. UNHCR prioritisation included a strategy of meeting the needs of the most vulnerable on sites before reaching out further to those people offsite.
[20] As at January, 135,132 newly registered refugees with WFP able to reach some 93,000 of these people.

DFID noted some good examples of beneficiary feedback mechanisms during quarterly visits. For instance, WFP ran ad hoc checks during distributions to verify that families had received appropriate items. WFP’s post-distribution monitoring report in 2014 picked up that some refugees were not aware of the assistance available to them and WFP have taken steps to improve transparency and communication. DFID also held discussions with small groups of beneficiaries to gather feedback over assistance. In April 2015 discussions with beneficiaries brought issues to light including that some people reported they had not received a full NFI package and important items needed to be replaced. Beneficiaries repeatedly highlighted in 2014 livelihoods as a substantial gap in the response (mainly caused by underfunding).[21]
[21] According to DFID field visit reports.

As part of quality, equity is a key focus (and as outlined in the business case) the DFID funded projects must demonstrate they aim to overcome challenges and reach out to the most vulnerable and remote populations.

In Cameroon, humanitarian agencies have struggled to reach refugees living off-site (approximately 50% of the Central African refugees registered from 2014) and host communities. A key challenge for UNHCR has been funding – with a generally underfunded operation UNHCR have resorted to prioritising the bringing of sites up to minimum standards. However UNHCR has reported that they continue registration and efforts at locating groups.

To demonstrate equity, the programme must also demonstrate how they reach vulnerable populations including women and girls. In Cameroon, UNHCR profiling activities during the registration process have sought to identify those with specific needs and vulnerabilities, such as survivors of SGBV, unaccompanied minors and separated children, elderly persons, women requiring specific attention, persons with disabilities and those who need immediate psychological support. However the procedures for the Best Interest Determination for children was still under discussion and approval during the reporting period. Activities implemented by UNHCR and partners have focused on improving mechanisms to prevent gender-based violence in refugee settings and providing assistance to victims through lighting in public places, community policing systems, and medical, psychosocial, and economic support to all reported cases of SGBV. Coverage of these activities is incomplete but it has improved.

WFP has also considered gender in programming and monitor protection risks. The July 2014 post-distribution monitoring report in Cameroon explored decision making on food and protection (e.g. 9% of refugees living off-site noted the existence of early marriage in their community as a coping mechanism against lack of food). Pipeline breaks and ration reductions in 2015 are concerning in light of this. Agencies also mentioned to DFID their worry about negative coping strategies because of lack of income generation and livelihood opportunities.

MSF did not implement an activity in the initial proposal ‘Medical screening including SGBV and psycho-social support for any new arrival or newly registered refugee’ in Gado. The Cameroon Red Cross was in charge of new arrivals’ screening and redirecting them to adequate health-care system. MSF medical activities were however systematically integrating comprehensive psychological approach during any medical and nutritional consultation. All programmes are also collecting disaggregated data including gender.

Reporting to DFID indicates measures are being undertaken to avoid doing harm, including in the set up and training of community vigilance committees (including appropriate referral of incidents to camp management) and agencies were cognisant of responding and considering tensions arising from the pressure placed on local resources as a potential source of conflict.

Cost

A comprehensive review of cost per beneficiary ratio between the beginning and end of the Business Case will be undertaken once the financial reporting for all projects is received.

Assessment of whether the programme continues to represent value for money

The programme is representing good value for money in a difficult operating environment.

Agencies have undertaken measures to improve value for money. WFP has pre-positioned supplies near main points of entry, and have established new warehouses on sites to enable faster delivery. Airlifts are avoided. WFP is exploring cash assistance options. But given the continued high levels of malnutrition (UNHCR 2014 nutritional survey) improved understanding of the root causes is needed to more effectively target appropriate packages of food and nutrition interventions.

UNHCR has also provided a unique and necessary service in its response. While there were challenges in coordination at the start, this intervention represents good value for money as DFID visits have found UNHCR has taken steps to improve coordination. The negative impact of the counterfactual (UNHCR not having adequate funds available to respond) would be very severe, and have a very negative impact on the response and likely other development activities in the region and with host communities. We will continue to monitor UNHCR funding levels in 2015.

Quality of financial management

Payments were made based on memoranda of understanding and accountable grants. Financial statements are received and reviewed along with progress reports before payments are made, and show expenditure and forecast of the tranche to be made. We are still awaiting financial reports from UNHCR Cameroon.

E: RISK (½ page)

Overall risk rating: High.

A comprehensive risk register was developed as part of the Business Case process approved in December 2014. The overall risk level for the programme is considered high, however this is a result of the components of the programme operating inside CAR. For the components supporting refugees in Cameroon and Chad, where the operating environment is much less insecure, the risk rating is better described as medium. While there are significant risks including an unpredictable situation in CAR mitigation measures are in place. Quarterly monitoring visits and a greater focus on due diligence and UK engagement in CAR and the region has reduced these risks.

The Risk Register addresses the following risks:
- Context specific risks (conflict, fighting, unanticipated refugee influx, regional crises spill into Cameroon and Chad).
- Implementation (e.g. staff security, financing gaps undermine impact of UK funding, fraud and theft).
- Strategic (CAR regional response deprioritised in context of other Level 3 (L3) crises, CAR L3 ends, or chronic/structural crises including aid dependency).
- Technical (intervention not in line with humanitarian principles and/or is not conflict sensitive, protection including the needs of women and girls and not sufficiently provided for).

We do not judge programme risks in Cameroon and Chad to have changed substantively over the first year of the programme.

Outstanding actions from risk assessment

None.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The 2014 programme was delivered against the planned timeframe with the exception of WFP.

Performance of partnership(s)

Important lessons include that DFID needs to remain flexible to arising needs, including the ability to support course corrections of programmes and extending arrangements as needed to allow for some predictability in financing (and therefore partner expenditure). DFID provided a tranche to UNHCR in the third quarter of 2014 with the expectation that funds would be utilised by the end of 2014. But we need to give agencies longer lead times on pledges and flexible programme implementation periods. Partners should provide clear indicators and targets and clearly explain variations, e.g. changes in caseloads and report against indicators provided. MSF did this very well and was quick to respond to questions. UNHCR reporting was generally late – DFID relied heavily on field visits for an update on operations.

Asset monitoring and control

No specific concern has been identified. All partners have suitable processes to manage assets.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not relevant.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Partners have shared with DFID good evidence informing their programmes. Initial evidence gathered includes MSF baseline health data and WFP screening data. UNHCR also finalised a nutrition survey of refugees on sites/camps at the end of 2014 and WFP a post-distribution monitoring report which was comprehensive and transparent and has informed interventions. WFP also finalised an internal review of their Level 3 response for Central African refugees and UNHCR undertook to review programmes. MSF did not include evaluation as part of the final report and budget to DFID but put a system of epidemiological surveillance and monitoring in place in March 2014 and MSF is undertaking internal evaluations of the project as part of their exit and closing strategy.

DFID has not planned an external evaluation of the programme.

The theory of change in the original business case still holds and does not require review but refugee operations have generally been underfunded and we judge from DFID field visits that agencies have understandably chosen to prioritise life-saving food, shelter, WASH and healthcare and protection assistance which has limited support to refugees to resume income generating activities.

DFID quarterly visits to Cameroon and quarterly phone calls with UNHCR in Chad have informed any change to the programme as a result of new evidence. Partners have provided evidence that they have disaggregated data by sex and where most relevant, by age. There is evidence that other needs have been considered, for example by UNHCR Chad in supporting people with specific needs – an activity expanded from the target of those with physical disabilities to older people, children at risk of school dropout and patients with medical specific needs. The programmes have also responded to changes in the caseload of people affected by the crisis in Central African Republic; in Chad, this meant a changing caseload of Central African refugees, Chadian refugees, and also an older caseload of Central Africans and hosting communities to maintain community cohesion.

Monitoring progress throughout the review period

DFID does not have a country office in CAR, Cameroon or in Chad. DFID has engaged in 2015 a regional humanitarian adviser based in Yaounde who is well placed to continue to provide oversight of programmes benefiting refugees in the region. Since 2014, UK based staff have undertaken quarterly visits to programmes in CAR and Cameroon to check project progress. Visits to Cameroon include meetings with beneficiaries and other stakeholders, national government officials, DFID partners and other humanitarian agencies. DFID also undertakes calls with partners on a regular basis and on issues arising – for Chad, DFID ensured quarterly partner phone calls over the programme period in the absence of field visits.

Partner performance has been monitored and reviewed and captured in the intervention review sheets before financial allocations have been made. Agencies have provided DFID attributable results however for some UN partners this is challenging as practically, in their operations, they do not internally demarcate DFID vs. other donor funding against specific projects.

Direct beneficiary feedback has been an important element of the programme, including with women, with men, and young people.

ANNEX 1 – List of abbreviations

ACF	Action Contre la Faim
CAR	Central African Republic
CERF	Central Emergency Response Fund
CHF	Common Humanitarian Fund
DRC	Danish Refugee Council
ECHO	EU Humanitarian Aid and Civil Protection directorate
EMOP	Emergency Operation
FAO	Food and Agriculture Organization
GAM	Global Acute Malnutrition
GFD	General Food Distribution
IMC	International Medical Corps
INGO	International non-governmental organisation
MAM	Moderate Acute Malnutrition
NFI	Non-Food Items
SAM	Severe Acute Malnutrition
SC	Save the Children
SGBV	Sexual and Gender Based Violence
UN	United Nations
VfM	Value For Money
WASH	Water, Sanitation and Hygiene
WFP	World Food Programme