Annual Review (AR) - Building Disaster Resilience in Pakistan (BDRP)

Title: Building Disaster Resilience in Pakistan (BDRP)
Programme Value £ (full life): £33.89 million		Review Date: May 2019
Programme Code: 203264	Start Date: July 2014	End Date: September 2020

Summary of Programme Performance
Year	2015	2016	2017	2018	2019
Programme Score	B	B	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5573566.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/46859979.xlsx

A. Summary and Overview

Description of programme
The Building Disaster Resilience in Pakistan Programme (BDRP) aims to increase Pakistan’s capability to reduce disaster risk through better planning, preparedness and response at government and community levels. Aligned with the Government of Pakistan’s (GoP) National Disaster Management Plan, DFID Pakistan works closely with the National, Provincial and District Management Authorities for programme delivery.

The programme is divided into two Phases – Phase I (September 2016 – September 2018) and Phase II (October 2018 – September 2020[1]) and has two components:
[1] After Secretary of State’s approval in 2014, the original budget of £76.3 million was reduced to £40.8 million as part of the UK Spending Review (2015), with some reduction in scope from that in the original Business Case. Later in 2018, it was agreed that programme duration would be reduced further by two years with an aim to align with the end date for DFID Pakistan Multi-Year Humanitarian Programme (MYHP) – September 2020. The alignment provides space for DFID to consider how future programming can focus opportunities to align humanitarian and resilience activities where appropriate, focus on a trajectory from preparedness to response and recovery through a set of integrated programmes. BDRP Phase II will end in Sept 2020 with a total budget of £33.8 million.

Component I - Building community resilience through Community-Based Disaster Risk Management (CBDRM) by introducing practical measures to mitigate the risk from disasters and increase resilience to shocks. Selected villages and communities are involved in the development of hazard and resource maps and risk management plans. This component is delivered through a consortium, led by Concern Worldwide in partnership with ACTED, Welthungerhilfe (WHH) and International Rescue Committee (IRC), together with their respective downstream partners in some districts.

Component II - Strengthening District, Provincial and National Disaster Management architecture through increased provincial and district technical capacity in hazard mapping, preparedness and contingency planning, as well as response. This element is delivered by the Food and Agriculture Organization (FAO), United Nations Development Programme (UNDP) and World Food Programme (WFP), with FAO being the lead agency.

Component III – Third Party Monitoring (TPM) to complement internal consortium monitoring and increase accountability, oversight and evidence-based learning on the programme, and to inform the design of future humanitarian and resilience programming in Pakistan. Phase II of this component has recently been contracted to Integrity and its local partner VTT Global.

This review period covers the final four months of Phase I and the start-up of activities under Phase II during the last eight months. Under Phase I, the programme worked in two districts each in Punjab (Rajanpur and Muzaffargarh) and Sindh (Ghotki and Kashmore). In Phase II, the programme has scaled up work in Punjab and Sindh and expanded into Khyber Pakhtunkhwa (KP), based on district vulnerability profiles. The nine districts in Phase II are:

- Punjab - Rajanpur, Muzaffargarh, Jhang;
- Sindh - Ghotki, Kashmore, Tharpakar, Dadu;
- KP - Chitral and DI Khan.

The review team used the log frame milestones for Phase II as outputs in Section B. However, the overall scoring for outputs has combined the achievements under the last four months of Phase I and those of the start of Phase II.

The programme steering committee (PSC), chaired by the National Disaster Management Authority (NDMA) meets semi-annually and includes representatives from the NDMA, Provincial Disaster Management Authorities (PDMAs), other provincial government department and line ministries, respective multilaterals (FAO, WFP and UNDP) and International Non-Governmental Organisation (INGO) and local Non-Governmental Organisation (NGO) consortia and DFID.

Programme interventions are strongly focused on how they will contribute to reducing gender inequality and the programme is in line with the Gender Equality Act. One of the programme’s aims is to target women and female headed households who are amongst the most vulnerable to natural disasters and data is disaggregated by sex. BDRP is 100% funded through UK International Climate Finance (ICF).

Summary supporting narrative for the overall score in this review
The programme scored an ‘A’. All the outputs are on track to achieve their targets and recommendations. The programme is well placed to achieve its main objective of building resilience of crisis-affected communities but there is room for improvement based on lessons learnt. It is important to note that during the first few months of Phase II, a drought emergency was declared in some districts in Sindh including those where BDRP is operating. Considering this, partners undertook some realignment of activity and stepped up engagement with humanitarian colleagues to strengthen overall support to communities in this situation. In the coming year, focus needs to be given to the second output involving government system strengthening to ensure programme outcomes are sustainable at all levels.

This year saw the transition from Phase I to II and allowed the team to review the significant success of Phase I, which included:
- 3019 households in targeted areas benefitted from livelihood related field interventions;
- 2500 beneficiaries trained on good agriculture practices, Climate Smart Agriculture (CSA) and Disaster Risk Reduction (DRR);
- 76 demo plots established to test, validate and document community-level and on-farm agricultural resilience-building initiatives;
- 12 Disaster Risk Management (DRM) and DRR plans & strategies developed and adopted by target stakeholders;
- 2,943 people trained with new DRR/DRM Skills; and
- 4,738 people from education, health services and DRM sectors trained in Disaster Preparedness and Response Planning

Key achievements under Phase II include:
- 432 community-based disaster risk management structures established including 403 Village Disaster Management Committees (VDMCs) and 29 Union Council Disaster Management Committees (UCDMCs);
- 332 people trained with new DRR and DRM skills;
- Capacity building and training of 420 farmers in environmental management and sustainable farming; and
- Strengthened systems for cross consortia learning and coordination between FAO and Concern Worldwide.

Recommendations for the year ahead
The following are key recommendations for the year ahead, with corresponding plans for tracking, to ensure that these are followed up in the monthly meetings with partners.

- DFID should visit the field in the next few months: The team should continue to undertake regular field visits. The last visit was to Sindh in February 2019 and due to external factors, we have not been able to visit since.
- Seek more consistent attendance in the Programme Management Committee (PMC) Meetings: Whilst it was agreed that this is a useful forum for information gathering, lesson learning and work planning, there needs to be more consistent attendance from key stakeholders, especially from provincial government. DFID with FAO and Concern Worldwide should explore how to strengthen attendance further, especially from relevant government departments and better share and capture what is discussed.

- Monitoring and evaluation (M&E): Key stakeholders and partners should continue to work to ensure TPM analysis and recommendations are captured and incorporated into their work and that their own learning is effectively captured.
  - Effective M&E remains a priority, to both assess how the programme’s outcomes have been met and see how this will continue after the programme’s end and should feed into the new DFID Humanitarian and Resilience programme.
  - Strengthening of beneficiary feedback mechanism will be explored with TPM and field visits of DFID staff.

Local Government Acts (LGAs) and BDRP Sustainability: DFID and programme partners need to closely work with respective government counterparts to ensure any relevant risks emerging are managed and mitigated including development of an appropriate sustainability/exit strategy by December 2019.

- Logical framework: DFID team to work with all programme partners to review and finalise logical framework indicators by October 2019 for next year’s annual review and programme completion review. Indicators and targets to be specifically considered are as follows:
  - Identify better measures for quality of institutional changes;
  - Strengthen link between output 1 and 2 indicators considering feasibility of measuring local community involvement in policy making process.

Value for Money (VfM): Drawing on the data from inception and implementation phase activities, DFID and partners should review and update the agreed VfM template with supporting narrative at least semi-annually (particularly with an aim to systematically capture wider benefits of continued support under Phase II to Phase I communities) to ensure its usefulness.

More coordination between partners in both components: The BDRP team has encouraged coordination among partners. However, it needs further follow-up by the lead organizations of both the delivery components.

DFID should further identify synergies with other programmes across the portfolio: The programme has worked with Multi Year Humanitarian Programme (MYHP) and other teams across DFID Pakistan this year, but has found it challenging to engage others, it has been difficult to get social development support due to resourcing constraints. Next year, team should continue to deliver messaging across the office to encourage others to engage.

The annual review also provided the opportunity to review activities and lessons to inform the design of a new merged humanitarian and resilience programme currently underway (Building Resilience and Addressing Vulnerability to Emergencies or BRAVE). The programme will aim to reduce vulnerability and increase resilience of those most at risk to recurrent and large-scale disasters, whilst providing humanitarian aid as needed. Specific recommendations for the new programme have been provided under outputs and wherever they seem feasible.

## ACRONYMS

ADCRMOP Agriculture Disaster & Climate Risk Management Operational Plans
AEZ	Agro-Ecological Zones
AR	Annual Review
ARBI	Agriculture Resilience Building Initiative
AAWAZ	Urdu word for “Voice” – DFID’s Voice and Accountability Programme in Pakistan
BDRP	Building Disaster Resilience Programme
BoQ	Bill of Quantity
BRAVE	Building Resilience and Addressing Vulnerability to Emergencies
CDMC	Community Disaster Management Committee
CBDRM	Community Based Disaster Risk Management
CSA	Climate Smart Agriculture
CW	Concern Worldwide
DDMAs	District Disaster Management Authorities
DFID	Department for International Development
DRM	Disaster Risk Management
DRR	Disaster Risk Reduction
FAO	Food and Agriculture Organisation of the United Nations
FFS	Farmer Field School
GFDRR	Global Facility for Disaster Reduction and Recovery
GoP	Government of Pakistan
HRI	Household Resilience Index
(I)NGO	(International) Non-Governmental Organisation
ICF	International Climate Fund
IRC	International Rescue Committee
KP	Khyber Pakhtunkhwa
KPI	Key Performance Indicator
LFA	Logical Framework Agreement or Log Frame
LGA	Local Government Act
LFFS	Livestock Farmer Field School
M&E	Monitoring and Evaluation
MYHP	Multi Year Humanitarian Programme
NDMA	National Disaster Management Authority
NGO	Non-Governmental Organisation
PC-1	Planning Commission Proforma
PCD	Procurement and Commercial Department
PMC	Programme Management Committee
PDMAs	Provincial Disaster Management Authorities
PPA	Partnership Principles Assessment
PSC	Programme Steering Committee
PWDs	People with disabilities
R&R	Risk and Resilience
SDG	Sustainable Development Goals
SEED	Sustainable Energy and Economic Development
SNG II	Sub National Governance Programme
SOPs	Standard Operating Procedures
SRM	Strategic Relationship Management
ToC	Theory of Change
ToRs	Terms of Reference
TPM	Third Party Monitor
TWG	Technical Working Group
UC	Union Council
UCDMC	Union Council Disaster Management Committees
UCDMP	Union Council Disaster Management Plan
UCRF	Union Council Response Forums
UK	United Kingdom
UN	United Nations
UNDP	United Nations Development Programme
US	United State
VDMC	Village Disaster Management Committees
VfM	Value for Money
WASH	Water, Sanitation and Hygiene
WFP	World Food Programme
WHH	Welthungerhilfe
WOS	Women Open School

## B: DETAILED OUTPUT SCORING

Output Title	Target communities have resilience building measures in place (disaggregated by community structures, households)
Output number per LF		1	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of community-based disaster risk management structures established and functioning effectively	225 Village Disaster Management Committees (VDMCs) and 18 Union Council Disaster Management Committees (UCDMCs) are established	403 VDMCs and 29 UCDMCs are established / Indicator Score: A++ / (Substantially Exceeded Expectations)
1.2 Number of people who have benefitted from improved Water, Sanitation and Hygiene (WASH)	- Procurement of materials / - Finalisation of Terms of Reference (ToRs) / Bill of Quantities (BoQs) for handpumps and water supply schemes	- Procurement of materials has been initiated / - ToRs/ BoQs for hand pumps and water supply schemes finalised / Indicator Score: A / (Achieved)
1.3 Number of people who have benefitted from improved DRR infrastructure (bunds, embankments, protection/retaining walls, raised bed platforms, evacuation routes, water harvesting structures)	- Identification of schemes and process of feasibilities initiated through Technical Working Group (TWG) and VDMC / - Procurement of materials / services for triggering exercises initiated; / - ToRs/BoQs for activities finalised	Identification of schemes and process of feasibilities initiated through TWG and VDMCs. / Indicator Score: B / (Moderately did not meet expectations)
1.4 Number of people who have benefitted from disaster resilient shelters	- Identification of beneficiaries and process of feasibilities initiated through TWG, VDMCs, BOQs prepared / - Materials procurement initiated	- Identification of beneficiaries and process of feasibilities initiated through TWG, VDMCs, BOQs prepared; and / - materials procurement initiated / Indicator Score: A / (Achieved)

Supporting narrative for the score
This output aims to support communities to have resilience measures in place by building the capacity of communities and establishing community structures. This output has mostly achieved all milestones and has scored an A.

The CBDRM component of the programme is led by Concern Worldwide (CW) in partnership with ACTED, Welthungerhilfe (WHH), and International Rescue Committee (IRC) in disaster prone districts of Pakistan. During Phase I the programme only, targeted flood affected districts. However, the scope of Phase II has expanded to include drought and earthquake prone districts. The marginalised groups like women, children, people with disabilities (PWDs) and the elderly are a primary focus of all interventions of the BDRP programme.

The final report by the third-party monitors (December 2018) and Midterm review by Concern Worldwide (September 2018) for Phase I have been reviewed as part of this review. Several recommendations have been taken forward already in Phase II. Therefore, this review covered those that are higher priority or where additional action is suggested.

Key achievements:
Overall the Household Resilience Index (HRI) increased for the target communities. Nearly 33% of households transited from low-resilient to the medium and high resilient category[2]. This demonstrated that the programme has been instrumental in upgrading households’ resilience category. The mid-term review by Concern Worldwide and the final Third-Party Monitoring (TPM) report outlined several achievements from Phase I under this output:
[2] Concern Worldwide developed a Household Index (HRI) for calculating household resilience based on five dimensions (early warning system/disaster risk reduction, water and sanitation, shelter, protection, livelihoods). A baseline was conducted at the start of Phase I and categorised HHs accordingly into high, medium or low resilience.

- 28 Union Council Resilience Forums formed. In Ghotki district, all seven Union Council Resilience Forums (UCRFs) have been registered as community-based organizations with the Social Welfare and Bait-ul-Mal Department;
- 28 Union Council Emergency Response Teams formed;
- Emergency Response Toolkits procured and pre-positioned;
- 310 Model Household Shelters (MHSs) established;
- 300 small to medium scale infrastructures constructed or rehabilitated benefiting 63,000 people;

There has been significant progress in initiating delivery for Phase II:
- 463 community structures, out of which 436 Village Disaster Management Committees (VDMCs) and 27 Union Council Disaster Management Committees (UCDMCs) formed;
- During the reporting period, a detailed risk and resilience (R&R) exercise continued from the first quarter and 50 R&R assessments were conducted. In Sindh, 7 profiles were developed in Ghotki, 7 in Kashmore, 7 in Dadu and 5 in Tharparkar. In Punjab, 5 profiles were developed in Jhang, 7 in district Muzaffargarh and 7 in Rajanpur. In KP, 5 profiles were developed in DI Khan. The main findings from the R&R assessments will be included in the Union Council Disaster Management Plans (UCDMPs) at the later stages and viable solutions will be identified through participatory action planning; and
- Between December 2018 and February 2019 an extensive baseline assessment was conducted. This included the Washington Group questions for disability, demonstrating best practice and has provided new comparisons between communities affected by flood and drought.

Lessons identified this year, and recommendations for the year ahead linked to this output
- There are strong examples of best practice and approaches which should be shared across DFID from the Concern Worldwide Consortia. Specifically, their Standard Operating Procedures (SOPs) which prevent doing harm and their Grievance Redressal Mechanism model provides strong learning and highlights key challenges.
- The mid-term review conducted by Concern Worldwide indicated the need for Phase II to support the same districts from Phase I to sustain the community infrastructure. DFID should work with partners to look at best practice for improving sustainability of these. The current model is reliant on village committees registering as NGOs which has been a challenge. Both DFID and partners also need to take into account the new Local Government Act (LGA) legislation in Punjab for sustainability of these community forums.
- Resources, time and capacity for leave no one behind should be reviewed. There were clear examples that demonstrate the need for more resources for harder to reach groups which should be considered in programme design.
- Ghotki is a very remote district in Sindh where there was lower community involvement and engagement rates. Communities had low literacy rate, the culture is traditionally more conservative with limited women’s participation. Therefore, stronger systematic social mobilisation and more dedicated resources are needed to reach these areas.
- There were challenges delivering in rural areas to reach the household numbers to meet the criteria for village selection. Generally, they are set in smaller settlements of 50 households. Therefore, the population for a village was more scattered and was logistically challenging. In addition, social cohesion between these settlements was not homogenous. DFID and Concern Worldwide partners should look at collecting best practices for engaging these communities.
- The last field visit from the DFID programme team took place in Feb-19. Therefore, it is recommended that the programme team conduct a field visit to review the recommendations within 3 months to validate recommendations for this component.
- The Community Based Disaster Risk Management Committees are generally created using existing structures. Buying into existing power dynamics can serve to further reinforce exclusion of certain groups and decrease the likelihood of women’s involvement. The Concern Worldwide team should look at creative ways to involve women in decision making, particularly around beneficiary selection. The monitoring and evaluation should measure women’s involvement in the selection and prioritisation of projects and beneficiaries compared to men. This should be reported on in the next annual review.
- Given the nature of recommendations the team should highlight the need for more support for a DFID Social Development Advisor and/or Conflict Advisor. The DFID Pakistan Office and Governance Group should consider how this advisory support should be resourced going forward.

Output Title	Target stakeholders have improved skills and systems to develop, plan and apply DRM and DRR strategies and SOPs
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of strategic and policy documents developed	- Validation and Dissemination of Agro-ecological zones[3] (AEZ) reports in 2 provinces (Punjab and Sindh) / - 1 Stakeholder Capacity building plan / - Process initiated for the preparation of Agriculture Resilience Building Initiatives (ARBI)[4] document in 5 new districts / - Process initiated for 9 district climate smart agriculture profiles	- Validation completed of AEZ reports in 2 provinces (Punjab and Sindh) / - 1 Stakeholder Capacity building plan developed / - Process initiation completed for the preparation of ARBI document in 5 new districts / - Process initiation completed for all 9 districts climate smart agriculture profiles / Indicator Score: A / (Achieved)
2.2 Number of DRM/DRR plans, strategies and structures developed and adopted by target stakeholders	- Process initiated for the KP provincial Agriculture Disaster & Climate Risk Management Operational Plans (ADCRMOP)[5] / - Process initiated for district ADCRMOPs	- Process initiated for 5 district ADCRMOPs, with no progress on provincial level. / Indicator Score: B / (Moderately did not meet expectations)
2.3 Number of people trained with new DRR/DRM Skills	FAO: / - 90 persons trained through 3 capacity building events / UNDP: / - 40 persons trained through 01 Provincial level DRR & Climate Change Adaptation (CCA) training / Concern Worldwide: / - 90 UCDMC members (45M & 45 F) / - 675 VDMC members (450 M & 225 F)	FAO: / 107 persons trained through 4 capacity building events / UNDP: / No training on DRR/DRM conducted so far. UNDP has identified the potential partner and agreement signing is in process. The training is planned to be delivered during the third quarter of 2019 / Concern Worldwide: / - For UCDMC training hiring of consultant is in process / - 225 VDMC members (M 122, F 103) trained on HVCA / Indicator Score: B / (Moderately did not meet expectations)
2.4 Number of advisory structures established and functional at district, provincial and federal level (KPI-14 - FAO)	- 3 Provincial Management Committee (PMC) meetings (One each for Sindh, Punjab and KPK) / - 1 Programme Steering Committee (PSC) Meeting	3 PMCs and 1 PSC completed as per the target / Indicator Score: A / (Achieved)
[3] Agro-ecological Zones are geographical areas exhibiting similar climatic conditions that determine their ability to support particular agriculture.
[4] ARBIs represent a set of best agricultural practices considering hazards and climate change impacts in targeted districts
[5] These plans represent integration of disaster risk management and climate change adaptation in agriculture

Supporting narrative for the score
This output is about the level of knowledge among government and disaster management practitioners, i.e. the right skills and adequate resources to plan, prepare and respond to a disaster enabling them to implement stronger DDR and DRM strategies. Overall, the output has met expectations and scored an A considering processes to achieve all indicator milestones are well in place. The final deliverables for milestones 2.2 and 2.3 have been slightly behind schedule mainly due to the delay in finalising Concern Worldwide’s contract amendment for Phase II[6] and bureaucratic churn within provinces post last year’s general election.
[6] The contract amendment for Concern Worldwide for phase II took longer than anticipated i.e. it took almost 13 months to process and finalise the amendment. Consequently, phase II implementation was also delayed by a month.

Key Achievements:
Key achievements under Phase I are;
- The AEZ for Punjab and Sindh was designed and endorsed by government. Furthermore, the government has prepared 6 PC-1s[7] linked to beneficial crops highlighted by the AEZ;
  [7] Planning Commission Proforma 1 (PC-1) – is a planning tool for the development and execution of any projects in Pakistan Government Departments.
- In Phase I, UNDP developed two provincial level Public Private Partnership strategies which were disseminated amongst stakeholders;
- ADRMOPs and implementation guidelines prepared for Muzaffargarh, Rajanpur (Punjab), Ghotki, Kashmore (Sindh) during Phase I. Under Phase II similar support will be extended to Chitral, Dera Ismail Khan (KP), Jhang (Punjab), Tharparkar, and Dadu (Sindh);
- A total of 332 government officials received capacity building trainings on DRR and DRM Skills;

There has been significant progress in setting up the delivery for Phase II:
The first Provincial Management Committee (PMC) and Programme Steering Committee (PSC) meetings of BDRP Phase II were held successfully in the National Disaster Management Authority (NDMA) Office in Islamabad and Provincial Disaster Management Authority (PDMA) offices in Sindh, Punjab and Khyber Pakhtunkhwa (KP). During these forums, Phase I lessons learnt and the areas where provincial government support was needed was highlighted. The PMC meetings (chaired by relevant Director Generals of the PDMAs: KP, Sindh, Punjab) and PSC (led by Chairman of NDMA) has provided an opportunity for collective planning and coordination.

Lessons identified this year, and recommendations for the year ahead linked to this output
There are some key lessons that are important to consider for future programming:
- More systematic involvement of Planning and Development Department could be looked into in future programme on resilience. PDMA has a limited capacity and a mandate to provide response only. Planning and Development department broader role overseeing development initiatives could play key role in mainstreaming resilience;
- BDRP should collaborate with Sub-National Governance (SNG) Programme II[8] to strengthen the commitment of government to include resilience and climate change into development plans.
  [8] DFID Pakistan’s Subnational Governance (SNG) programme works in KP and Punjab and provides support to both governments in budgeting, planning and decentralisation reforms. SNG’s work is relevant for BDRP as public financial management reforms directly affect all service delivery sectors
- The implementation of government strategies needs to be monitored more closely. This could include measurement of how government strategies are developed, whether this has been done effectively and if there are key capacity gaps. This could be collected through qualitative data. The team could revise the log frame to include this.
- Implementation plans developed should include processes for government to consult and work with local communities to ensure these plans are adapted the local context. This should be considered by UN consortium when supporting government implementation plans.

Output Title	Target communities are introduced to sustainable livelihoods and environmental management practices for resilience building
Output number per LF		3	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of community level on-farm agricultural resilience building initiatives and new improved environmental management practices demonstrated which support resilience and sustainable livelihoods	FAO: / - 3 ARBI practices demonstrated / - 10 Climate Smart Agriculture (CSA) demo plots established / - 25 sessions of Farmer Field schools (FFS)/Women open Schools (WOS)/Livestock Farmer Field Schools (LFFS) conducted / Concern Worldwide: / - Identification and trainings of 405 farmers	FAO: / - 3 ARBI practices demonstrated / - 10 CSA demo plot established / - 57 sessions of FFS/WOS/LFFS (12 FFS, 32 LFFS and 13 WOS) conducted / Concern Worldwide: / - Identification and trainings of 420 (F 420) farmers completed / Indicator Score: A+ / (Exceeded Expectations)
3.2 Number of households in targeted areas (most vulnerable 20%) that have benefitted from diversified livelihood options	Identification of farmers, training providers and procurement of materials	Identification of farmers, training providers and procurement of materials / Indicator Score: A / (Achieved)

Supporting narrative for the score
This output aims to introduce communities to sustainable livelihoods and environmental management practices for resilience building. In continuation of the agenda to build the capacity of consortium partners, FAO arranged training workshops on “Climate Smart Agriculture” (CSA) that was well attended by 39 participants from government departments of all three provinces (Sindh, Punjab and KP). In addition to formal training, FAO also extended support to the consortium partners in different activities by providing technical guidance particularly in Hazard Livelihoods and Vulnerability (HLV) assessments, CBDRM planning and research and up-scaling of resilience building initiatives/climate smart agriculture.

Successes against this output this year include:
- 3 ARBI practices were demonstrated – these present a set of best agricultural practice options considering hazards and climate smart elements and included line sowing in the Muzaffargarh district and introducing farmers to alternative wet and dry rice methods.
- 10 CSA (climate smart agriculture) plots were established and farmers introduced to new climate smart methods e.g. climate smart resilience to pesticides.
- 57 Farmer field schools, women’s open schools and livestock farmer field schools – this has exceeded the milestone of 25 and shows the push this year to promote learning and capacity building. These schools offer a participatory training approach following a set curriculum. Both the curriculum and style of teaching has been flexible and tailored to farmers. The schools also promote social inclusivity, democratic learning and communal cohesion. Partners have also observed indirect successes such as confidence building amongst women.
- Identification and trainings of 420 farmers completed, against a milestone of 405.
- 27 one-month vocational skill training sessions were conducted. There were 547 beneficiaries (285 male and 262 female) including 20 people with disabilities;
- Several activities exceeded targets (e.g. the plantation of 55,965 multipurpose agro-forestry plants, 6750 packages of vegetable production and training) demonstrating stronger Value for Money (VfM) than originally planned.
- Concern Worldwide specifically supported women of all active ages including active older women beneficiaries in the establishment of home-based kitchen gardens (KGs) coupled with trainings that will enhance domestic level food security and nutrition.

A market assessment study to identify non-traditional livelihood packages for women has been undertaken. This identified the following areas: computer skills, hospitality and hotel management, wood carving, lab technician, solar panel repairing, cooking and baking. The programme aims to support women in developing these skills through public/private training institutions and will explore market opportunities to address the constraints for women’s employment. In the next year, the feasibility of implementing this in this context and in these communities should be further explored with the communities.

Lessons identified this year, and recommendations for the year ahead linked to this output
Proactive involvement of agriculture extension workers should be sought so as to have more sustainability to FFS work. It is recommended to have SOPs for involving extension workers in FFS work.
- There has been innovation in data collection and sharing, and in addition to regular meetings with partners who are in the field regularly. As the review team were not able to visit the field during this review, it is recommended that the team should visit the field in the first quarter of the final year.
- The TPM will monitor the whole programme – it is recommended that an independent evaluation also takes place to gauge the sustainability of the FFS and measure impact. The TPM should also evaluate the value and effectiveness of kitchen gardens[9].
  [9] TPM final report is due in September 2020. This should be covered in that report.
- Livelihood diversification – DFID and partners should further explore feasibility and sustainability of livelihood diversification with linkages with market to ensure sustainability. This could include working across DFID with other programmes looking at economic opportunities and basic services.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Programme’s theory of change and any major changes in the past year
The programme’s theory of change (ToC) was revised during the inception phase of the programme in April 2017 as outlined in the previous annual reviews (see annex 1 – appended below). The ToC has not been changed since, however learning on particular assumptions has led to changes in the types of activities delivered. The outputs follow a sequence starting with formation and empowerment of CBDRM structures followed by capacity building of CBDRM structures and resilient livelihood interventions. Finally, the ToC elaborates targeting, key thematic areas of change as well as the stakeholders the programme is working with.

Contribution to the expected outcomes and impact
It has been challenging to test the impact ‘Poor people in Pakistan (especially women) are more resilient to natural disasters’ as a disaster has not hit the communities targeted. Therefore, their resilience to these shocks cannot be measured.

The programme is on track to achieving its outcome - “Increased capacity of communities and the Government to reduce disaster risk, though better planning, preparedness, response, and resource allocation at the governmental and community levels”.

Outcome indicator 1 (Number of people whose resilience has improved as a result of project support) has been achieved. The baseline for Phase II was established. For Phase I, nearly 33% of households transited from non-resilient to the resilient category. The target of Outcome Indicator 2 for Phase I (DRR sectoral strategies, policies and plans adopted by stakeholders) were also met.

Major changes to the log frame in the past year
Under BDRP Phase II, the programme has scaled up work in Punjab and Sindh and expanded into KP. Given this scale up, changes to the programme budget, implementation plans and timeframes, the programme logical framework was revised accordingly. The last Annual Review also recommended a revision to the programme logical framework for BDRP Phase II, to ensure the indicators used are of most relevance to the programme. Learnings from Phase I were also considered while revising the Phase II logical framework. Key changes include:

- IMPACT: Baseline value and a target is incorporated for impact indicator 1 (these were missing in the old version). Impact indicator 2 has been removed because the programme design for both phases does not include any large-scale activity on improving food security, nutrition and debt levels of a household. Note - this indicator was included based on the original design/scope of the programme, however, the original budget of £76.3 million was reduced (to almost half i.e. £40.8 million) as part of the UK Spending Review (2015), and this resulted in some reduction in scope from that in the original Business Case.
- OUTCOME: Indicator 1 definition and targets for both indicator 1 and 2 have been slightly revised ensuring their relevance with the agreed interventions of BDRP Phase II.
- OUTPUT: Indicator definitions and targets of output 1, 2 and 3 have been slightly revised to align these with BDRP Phase II interventions.
- MILESTONE TIMELINE: The timing of the milestones is changed to bring in line with the AR timing. This is was one of the main learnings from Phase I.
Proposed changes to the log frame as a result of this review
The DFID team should work with all programme partners to review and finalise log frame indicators by October 2019 for next year’s annual review and programme completion review. Indicators and targets to be specifically considered are as follows:
- Identify better measures for quality of institutional changes;
- Strengthen the link between output 1 and 2 indicators considering feasibility of measuring local community involvement in policy making process.

## D: VALUE FOR MONEY

Key cost drivers and performance
The existing budget for BDRP is less than originally planned (see page 1 of this review). Reduced budgets directly impact the scale of the programme; however, key cost drivers identified in the business case remain unchanged. For example, the deployment of technical experts on a full and part time basis was identified as a key cost driver which remains valid post budget reductions. The unit cost of these experts was reviewed during the competitive bidding process. The DFID team continues to monitor unit cost through implementation with an aim to achieve efficiency savings where possible.

Assess VfM compared to the proposition in the Business Case, based on the past year
The VfM case made at the business case stage still holds i.e. a CBDRM treated village hit by a disaster will require reduced emergency assistance compared to a non-treated village. However, the increased scope per village and reduced number of villages (due to reduced overall budgets) will impact the overall reach of the programme. A fresh look at the VfM templates, workplans and implementation under Phase II suggests that there will be additional and wider benefits (as compared to the ones proposed at Business Case stage) of the additional CBDRM activities being carried under revised scope[10].
[10] In Phase I, BDRP programme was focussing on flood prone districts only. However, the inclusion of districts Tharparkar and Chitral in second phase of BDRP has increased the scope of the programme from flood prone only to both drought and multi hazards (flood, earthquake etc). Concern Worldwide conducted an assessment study for contextualization of activity package for Tharparkar (drought affected) and Chitral (earthquake prone) and determined revised sets of interventions that are most appropriate for these two districts.

During Phase II implementation - to ensure sustainability and in consultation with programme team, communities and government counterparts - implementing partners are continuing to work with communities from Phase I villages to ensure that the practices introduced, and investments made, continue beyond the end of the programme. This will be in addition to new districts/villages agreed (based on vulnerability profiling) for Phase II.

Given the high costs of emergency assistance and frequency of disasters in Pakistan, increases in resilience at the community level are expected to result in reductions in both the immediate impacts, and in the cost of recovery following a natural disaster. A 2012 study[11] from Ethiopia, Kenya and Bangladesh suggests that wider benefits of building resilience in a drought hit area will significantly outweigh its costs leading to the conclusion that investment in resilience is value for money.
[11] Cabot Venton, Courtenay. 2012. ‘Economics of Early Response and Disaster Resilience: Lessons from Kenya and Ethiopia’ and https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/226156/TEERR_Bangladesh_Report.pdf

Recommendations:
- There is a need to increase/improve the reporting against effectiveness indicators in the templates in line with Phase II commitments while the quality of VfM analysis in quarterly reports require further improvement.
- Drawing on the data from inception and implementation phase activities, DFID and partners should review and update the agreed VfM template with supporting narrative at least semi-annually (particularly with an aim to systematically capture wider benefits of continued support under Phase II to Phase I communities) to ensure its usefulness and to inform the design of any potential future programme.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
Pakistan remains prone to natural hazards and disasters, including floods, earthquakes, and drought. The Global Facility for Disaster Reduction and Recovery (GFDRR) reports that 9% of the national territory is at risk from two or more hazards, representing almost half the country's population.[12] During 2002-2012 more than 80% of the country’s 124 districts have been hit by natural disasters, with some 33 million people affected. Conflict, insecurity and violence across Pakistan compounds vulnerability, undermining coping mechanisms and challenging effective response. In turn, natural disasters can erode fragile peace and security gains. Poor people are the most widely exposed, and disasters increase their vulnerability to malnutrition, disease, increased debt and exploitation.
[12] GFDRR Natural Hotspots Study: A Global Risk Analysis 2005. As per this Risk Assessment, Pakistan is prone to two or more hazards (including floods, earthquakes and droughts). Although the floods will only affect 9% of the national territory, the areas affected (Indus delta and Karachi) are densely populated putting 40.1% of the population at risk.

In addition to human suffering, most recent natural disasters have caused US$17.1 billion of losses to the economy. In 2010 alone, the monsoon flooding of the Indus river in Pakistan led to a humanitarian disaster affecting approximately 20 million people, destroyed homes, crops, and infrastructure and left millions vulnerable to malnutrition and waterborne disease. Estimates of the total number of people killed ranged from 1,200 to 2,200, while approximately 1.6 million houses were damaged or destroyed, leaving an estimated 14 million people without homes. The damage caused by floods in 2010 and 2011 was estimated at US$10billion and $3.7billion respectively.

In a disaster-prone country, investing in resilience which continues to reduce people’s vulnerability, and enable better and more appropriate responses to emergencies remains VfM. This investment does not negate the need to support people who have been affected by humanitarian disasters in the short to mid-term. DFID Pakistan continues to deliver through a complementary Multi-Year Humanitarian Programme allowing for a more strategic response to humanitarian emergencies. Where there are opportunities to ‘build back better’, the humanitarian programme seeks to ensure that options (whether house-building or similar) are as resilient as possible. The DFID team is working on bringing humanitarian and resilience programming together from 2020, not only to achieve cost savings but also to better reflect recent experience about new ways of undertaking resilience and response interventions.

E: RISK

Overview of programme risk and mitigation
The programme risk rating remains ‘moderate’. Following on from lessons from Phase I, both lead partners have managed risks and disruption well during Phase II initiation by including robust contingency plans in their proposals and proactive communication with the programme team at DFID. The programme team manages a comprehensive risk register for the programme as part of its delivery plan. The register categorised risks along all six categories under DFID’s risk framework. For each risk identified, a series of mitigation measures are in place, along with an indication of responsibility for these measures. In addition, a comprehensive strategic relationship management (SRM) process was followed with Concern Worldwide and a due diligence assessment refresh is planned for FAO with all recommendations regularly tracked and implemented. The main risks include:

Delivery
The registration requirement for INGOs and NGOs to operate in Pakistan remains the key risk for programme delivery. Under the CBDRM consortium, Concern Worldwide, WHH and Help Age have had their registrations renewed. However, the registration status of IRC and ACTED remains under consideration which could cause delays in programme implementation. The DFID team is in regular communication with consortium partners on this issue and contingency plans exist should operations have to be curtailed. In addition to a robust contingency plan, it is important that members of the consortium have regular coordination and sharing of programme information with both DFID and relevant government departments.

Operational
With less than 18 months to programme closure, sustainability of programme interventions, specifically community forums, is another key challenge for the programme. The community forums created under BDRP have resulted in explicit linkages between the citizens, the influencers and the decision makers to leverage each other’s resources and mitigate disaster risks within communities. The project will exit with a big number of trained citizens across all intervention districts for which partners need to ensure an appropriate exit strategy according to the prevailing context within each province. E.g. Partnership between citizens forums and elected local or municipal governments; coalitions and partnerships with CSOs and CSO Networks (specifically other DFID/donor programmes).

External Context
Last year’s general election and the consequent political transition in Pakistan impacted on the implementation of the programme, particularly in Punjab due to the rapid staff turnover within relevant government departments. The recently passed Punjab Local Government Act 2019 also heralds a significant departure from the past in terms of substantial devolution to local governments. District level local government is to be replaced by Tehsil/ municipal level local bodies, taking local government down to the grass roots. DFID and programme partners need to work closely with respective counterparts to ensure any relevant risks emerging from these changes are managed and mitigated.

On the environmental front, any large-scale monsoon floods may divert the focus of the concerned district governments and partners from the resilience programme. Also, the severity of drought in Tharparkar may trigger forced migration from the area and hence affect the BDRP programme interventions.

Safeguarding
Given the programme targets addressing vulnerability, gender and disability, safeguarding actions to prevent abuse and exploitation should remain a priority for the programme. This risk is being managed well through a comprehensive safeguarding analysis developed in close coordination with programme partners and conflict sensitive approaches with clear communication, ensuring community involvement, ownership and satisfaction. An accountability framework (beneficiary feedback and accountability to target population) has also been developed for the programme and put in place.

Recommendation:
DFID and all programme partners need to closely work with respective government counterparts on an ongoing basis to ensure any relevant risks emerging from the changes in local government structure are managed and mitigated, including the development of an appropriate sustainability / exit strategy by December 2019 according to the prevailing context within each province.

Update on partnership principles
This programme includes provision of technical assistance to government of Pakistan through public bodies through both the institutional strengthening and the CBDRM component. It does not include financial aid to government. The Partnership Principles Assessment (PPA) is regularly discussed with the Economic Affairs Division, Government of Pakistan at the federal level. The PPA was last discussed in March 2019 during our Bilateral Assistance Talks. The PPA sets out DFID’s assessment of the Government of Pakistan’s commitment to the four partnership principles, as demonstrated through its policies and action for reducing poverty and achieving the Sustainable Development Goals (SDGs). These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability.

DFID Pakistan’s overall assessment is that the government is demonstrating a credible commitment to the four principles. Progress towards the SDGs and poverty reduction is proceeding, albeit slowly, given the challenges. Progress on human rights is mixed. On public financial management and anti-corruption, the direction of travel is broadly neutral, with some improvements in the areas of transparency on budgets, progress on audit and procurement, more openness on corruption and an appetite to tackle this at the highest levels.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

BDRP has utilised 39% of the total available budget to date (Mid-May 2019). Considering the remaining duration of the programme and current level of commitments, the programme is likely to underspend by around £2 million (6% of the available budget) by the programme end. The table below summarises budget utilisation, against various programme components.

Component	Budget	Spend	%age Utilisation
Design Work for Building Resilience to Disaster in Pakistan	90,072	90,072	100%
Community Based Disaster Risk Management	25,337,622	10,117,156	40%
Monitoring, Reviews, Assessments and Management Cost	3,464,037	58,495	2%
Institutional Capacity Building of Government Agencies	5,000,000	3,000,000	60%
Grand Total	33,891,731	13,265,723	39%

Both lead partners’ performance remained satisfactory during this transitioning year particularly due to their flexible and adaptive approach. Concern Worldwide and FAO undertook a thorough analysis of the contexts in which they work to test that the activity packages were suitable and relevant. This was a good investment of time and effort as it allowed them to be flexible and adaptive in their approach during this transitioning period. However, these frequent changes in the context and programme implementation plans at times make it difficult to manage programme resources through certain delivery modalities. E.g. Concern Worldwide’s contract has been amended 5 times to date and another amendment is currently underway. A solution to this contractual constraint is being discussed with Procurement and Commercial Department (PCD).

Concern Worldwide and FAO submit regular reports against agreed templates and timelines which allow DFID to closely monitor all programme deliverables (logical framework indicators and agreed payment milestones), learn lessons and set the future workplan of respective components accordingly. Both partners have achieved most of their agreed milestones set to date.

A new supplier Integrity has been engaged in May-19 under an output-based contract to monitor all programme activities and give an independent assessment of how the programme is being delivered including validation of key programme milestones. Integrity will submit monthly monitoring reports that will significantly enhance programme oversight and evidence-based learning.

Coordination amongst BDRP and other DFID/Donor Programme Partners:
Coordination amongst respective programme partners is of utmost importance for effective programme delivery. Both lead partners have maintained coordination mechanisms through steering committee meetings with NDMA, programme management committee meetings with PDMAs for the successful implementation of the programme, both at strategic and operational levels. Concern Worldwide and consortium members are regularly meeting with district authorities/DDMAs and the line departments to ensure their agreement and technical support for the programme implementation. Based on learning from Phase I, coordination is strengthened between programme partners; however, there is room for further improvement.

Strategic Relationship Management (SRM) and Due Diligence:
Concern Worldwide was formally reviewed for the first time under the Strategic Relationship Management (SRM) process for DFID commercial partners in Feb 2019. Its performance over the period under SRM analysis was slightly below average due to contextual, coordination and financial management challenges including VfM monitoring and assessment. DFID appreciates Concern Worldwide’s senior management's recognition and responsiveness to these issues particularly around financial management. Risk management and sharing of risks remains good and is necessary for working together in the prevailing country context.

FAO’s capacity and capability, systems, policies and processes are assessed and monitored through a comprehensive due diligence assessment recently conducted for another DFID Pakistan programme. A refresh of BDRP programme specific due diligence is due this year in July.

Asset monitoring and control
Concern Worldwide and FAO have adopted DFID’s asset management policy. Comprehensive asset registers to record all assets purchased using programme funds are robustly managed and reported to DFID quarterly. In addition to DFID spot checks, the Third-Party Monitoring (TPM) firm is also mandated to carry out spot checks in partners’ field offices (including downstream partners). The team will continue to follow up on the asset spot checks and relevant recommendations through regular field visits.

Recommendations:
- DFID programme team should check flexibility of budget adjustments with PCD to adjust sub-budget lines without the need for a formal amendment.
- Joint field visits and programme reviews should be planned and conducted considering DFID Humanitarian (MYHP) and AAWAZ II programmes to strengthen synergies and cross learning.
- The strategies, framework and plans developed necessitates the involvement and more strategic engagement with Planning and Development Department (specifically in Punjab) to enable DFID and partners to mainstream approaches and ensure they are embedded in government functions. This recommendation is mainly to consider in the design of any future humanitarian and resilience programme.

Date of last narrative financial report(s)	Concern Worldwide & FAO – April 2019
Date of last audited annual statement (s)	Concern Worldwide - September 2018 for FY 2017 / FAO audited statements are pending

G: MONITORING, EVIDENCE & LEARNING

Monitoring
This annual review was led by programme managers and the Senior Responsible Owner (SRO). Technical input was received from across DFID Pakistan. The process included interviews with government stakeholders and partners and a desk-based review of partner reports. Due to Ramzan constraints, the team was not able to visit the field.

In Phase I, GLOW consultants provided third party monitoring for the CBDRM activities – the reports from these field visits provided DFID with the assurance that activities were delivered and agreed milestones achieved. The reports also enabled DFID to collect evidence of suppliers’ performance. These reports were shared with partners and lessons incorporated into Phase II.

Downstream visitors visit the field on a monthly basis, interview beneficiaries and see how the programme is working on the ground. As well as feeding this into higher level meetings on a monthly basis, this year the programme has utilized mobile technology to provide a more efficient way of feeding back real-time data (as discussed in output 3). Partners also work closely with project implementation units to build capacity and ensure standardisation of results collection to capture progress accurately.

Programme partners meet on a regular basis with key stakeholders in the PMC meetings and Programme Steering Committee (PSC) meetings. The PMCs include programme partners, government officials at a district, provincial and national level and are a way of reviewing progress, sharing feedback and lessons and work planning. It is also an opportunity to discuss any challenges and risks. Partners have commented on how helpful this forum is, but that attendance can be mixed and that in the next year it would benefit from more consistent cross-stakeholder attendance.

DFID also meets partners on a regular basis to discuss progress and has made field visits to targeted districts to enable DFID staff to see real time results.

Partners report to DFID on progress on a quarterly basis and both consortia produced a final report at the end of Phase I both to evaluate progress, but also to reflect on lessons to inform the next phase.

Gender Act Compliance - As part of this review, compliance with the International Development (Gender Equality) Act 2014 was also assessed. BDRP remains compliant with the stipulations of the Act. All programme partners continue to have a key focus on creating and maintaining gender parity in community groups and interventions supported through BDRP programme. Gender segregated data of beneficiaries is collected for all performance indicators, where feasible and is regularly discussed during programme management and steering committee meetings.

Evidence
The evidence collected from monitoring reports and meetings with stakeholders suggests that the programme is on track to meet its objectives.

This year saw a focus on gathering research and evidence on drought. FAO and its partners made substantial efforts to gather evidence from Sindh, Balochistan, Ghotki and Kashmore, conducting drought needs assessments which then directly fed into drought risk management strategies and action plans. Concern Worldwide and partners also conducted drought assessments and baseline studies for new areas for phase II e.g. Tharparkar to ensure that interventions are informed by evidence.

Learning
As the programme transitioned from Phase I to Phase II, a final progress report was shared with key stakeholders including the NDMA and key learnings from phase I were shared with the PDMAs, DDMAs and other relevant government departments through national and provincial inception workshops. Partners also conducted closure workshops in targeted districts. This ensured key lessons were captured and incorporated into the next phase.

As the programme progresses it continues to adapt and learn by doing e.g. improving the ways of delivering training to better suit the needs of beneficiaries and it will continue to embed learning. Embedded in the programme is continuous analysis e.g. hazard, livelihood and vulnerability assessments and piloting of activities. The team has also piloted new forms of learning for beneficiaries and has seen that ‘learning by doing’ has allowed more farmers to observe and replicate good practice.

This year has seen strengthened cross consortia coordination with joint quarterly work planning meetings, joint visits and engaging on a more regular basis. This has both improved coordination of programme activities, but also enabled cross programme learning. This has ensured that the two strands complement one another and has led to better cohesion of activities e.g. FAO technical expertise and Concern Worldwide outreach have worked together. The consortia used this shared learning to successfully deliver joint national and provincial inception workshops for BDRP Phase II. However, in the next year it is recommended that more of this learning is recorded to ensure it is not lost through institutional change.

The programme team in DFID sought to encourage learning from other programmes e.g. the MYHP through joint field visits. DFID will continue to explore linkages with other programmes over the next year.

The learning from BDRP has been incorporated into planning for the new DFID combined resilience/humanitarian programme with lessons being reflected in theory of change and overall programme design. In the next year the team should work to ensure this learning is not lost and that BRAVE is developed as per best practices.

Progress on recommendations from previous reviews

Recommendation	Action
Partners to strengthen engagement and coordination with local and provincial government in Sindh. DFID should also submit Phase I progress reports with all stakeholders including the NDMA, PDMA and DDMAs.	There has been significant progress and improvement in this area across the programme. / Examples of success for FAO consortium include the WFP School Safety Programme which was coordinated with the Sindh education and literature department and the education secretariat. / Concern Worldwide has established effective relationships with line departments in 9 target districts including: agriculture; agriculture extension; public health; engineering; irrigation; livestock; livestock extension; health; social welfare; education and forest. At a provincial level, successes include working with the Directorate of Animal Husbandry to train Community Livestock workers and working with the Directorate General to establish an Information and Communication Technologies (ICT) weather forecasting system. / DFID shared final progress reports with the NDMA.
Engage with other DFID programmes including: The Multi-year Humanitarian Programme (MYHP); AAWAZ II, Sub National Governance programme (SNG II) and SEED	BDRP has actively sought to identify linkages with other programmes this year. This has included joint partner meetings and field visits with the MYHP team and a concerted effort to identify synergies. Technical advisors from across DFID have been involved. This has all led to shared lesson learning.
Cross-consortia learning: DFID should work with partners to strengthen coordination and communication between the two BDRP consortia to ensure complementarity between the activities.	All parties agree that cross-consortia coordination and learning has improved. / DFID team worked with partners and ensured that internal coordination between them has been strengthened. This has been achieved through: / - joint field visits with Concern Worldwide and FAO / - Quarterly joint catch up meetings with Concern and FAO / - developed a joint workplan for Phase I for both FAO and Concern Worldwide / - Logical framework updated with both Concern Worldwide and FAO / - The TPM firm hired for Phase II covers both components (Concern Worldwide and FAO's) and produces joint learning documents bi-annually. / Apart from that, both Concern Worldwide and FAO have been engaging with each other on a regular basis, and successfully delivered joint national and provincial inception workshops for BDRP Phase II.
Refresh political economy analysis: DFID and partners should refresh political economy analysis this year for the programme.	Initially BDRP Phase II was proposed to be a four years phase but later in 2018, it was agreed that programme duration would be reduced by two years i.e. Phase II will now end in Sept 2020[13]. / Considering this reduction in programme duration, this recommendation is now relevant for the new programme. BRAVE will be looking into Political Economy Analysis while designing the programme.
Evidence gathering: Partners need to increase focus on gathering evidence of impact on the drought-affected communities. This should include how to ensure effective mobilization to mitigate drought.	FAO and its partners have undertaken a number of drought specific interventions and supported the Government of Sindh in preparation of their Drought Mitigation Policy and Action Plan. Additionally, substantial efforts have been made in gathering evidence of impact on the drought affected communities in Sindh and Balochistan, including conducting needs assessments for each. WPF assessments were used to inform draft preparedness actions in Ghotki and Kashmore. UNDP is also working on drought risk management strategies to feed into the provincial drought management plan. / Concern Worldwide and consortium members have conducted a detailed drought assessment and baseline studies of new areas for phase II e.g. Tharparkar. Risk and resilience profiles and Union Council Disaster Management plans were also developed.
Coherent project timelines: DFID team need to ensure all timelines are consistent to enable accurate assessment of performance based on the latest data.	This has been addressed in the updated logical framework for Phase II.
[13] See footnote 1; to align the end date with the MYHP programme, BDRP programme duration was reduced by two years. Both MYHP and BDRP programmes now end in September 2020. Team is already working on developing a business case for a new (merged) Humanitarian and Resilience programme ‘BRAVE’ which is likely to start in end 2020/ early 2021 (if approved).

Annex 1: Building Disaster Resilience in Pakistan (BDRP) - Theory of Change (ToC)
£54.5 million for CBDRM: 8,750 villages mobilised to select a Disaster Management Committee; Emergency Response teams in 175 UCs; provisions made for £50,000 resilience fund for each UC.
Village DRM plans designed with support from partner NGO.
Plan will include budget (£5000) for 20% of villages who decide to take up small-scale resilient infrastructure
Each of the 8,750 villages has a DRM plan which has provision for engaging with other villages and UCs.

Small projects financed.

Village-level linkages across UCs strengthened
Inclusive community disaster management committees implement plans; financed projects based on risk assessment

TA for national level risk modelling.
Communities
   Research and evidence
Government institutions
£10 million for institutional strengthening of NDMA, PDMAs and DDMA
This will begin with analysis of roles and mandates in provinces.
Hazard and vulnerability mapping gaps addressed
Research on drivers of disasters

National M&E system for CBDRM and impact developed

£5 million for national and provincial level research and evaluation
Larger scale projects financed.
DDMAs resourced, aware of local needs and engaging with local communities
Early warning systems in place or improved.
Improved climate and related modelling

Government of Pakistan's Disaster Risk Reduction Policy implemented effectively with improved coordination, systems, expertise and capacity at all levels

A comprehensive research programme to pilot and test new innovations and approaches to DRR to inform better future development of national resilience plans and priorities.

Government and communities are better able to reduce the risk from disasters and better equipped to recover from them
Communities have greater ownership over problems which compound disasters, and ways to mitigate such impact. Through planning, they are less vulnerable to different disaster scenarios

Civilian government will be better placed to finance DRR on the basis of need
Responsive to local communities; and lead or assist with recovery and reconstruction

Stronger government ownership of evidence and research on DRM

CBDRM projects are better targeted and more efficient

A reduction in the human and economic costs of disasters in Pakistan
Building capacity of provincial and district officials for planning, financing and disaster response
Accountability
Early warning system capabilities built
Lessons learnt and shared on CBDRM with direct link to Component 1

Links between hazard mapping and investment established at provincial level
UC-level resilience fund (£50,000) will support DRR and environmental projects beyond the scope of one village.

INPUTS / ACTIVITIES	PROCESSES OUTPUTS	OUTCOMES IMPACT