Business Case

Summary Sheet

Title: STRENGTHENING PUBLIC FINANCIAL MANAGEMENT AND ACCOUNTABILITY INSTITUTIONS IN SOUTH SUDAN
Project Purpose: To enhance the capacity and capability of public financial management and accountability institutions and processes in South Sudan.
Programme Value: £15 MILLION		Country/ Region: South Sudan
Project Code: 204745	Start Date: March 2015	End Date: March 2020
Overall programme risk rating:	High
Quest Number: 4706188

Intervention Summary

What support will the UK provide?
The UK will provide approximately £15 million over five years to support public financial management and accountability institutions in South Sudan.

What are the main programme activities?
This support will strengthen four inter-linked areas:
- Public financial management: to build understanding and consensus of senior leadership within the Ministry of Finance for public financial management (PFM) reform along with strengthening budgeting, financial management, control and accounting for enhanced service delivery at the state, county and local level.
- Oversight and anti-corruption institutions: (including parliament and the audit chamber) to carry out their core mandates, including as part of any transitional governance arrangements linked to the Inter-Governmental Authority on Development (IGAD) negotiated peace process.
- Civil society and other demand-side accountability mechanisms: to oversee and analyse the executive and other state institutions, better represent their constituencies and increase accountability relationships between South Sudanese themselves.
- Coherence and coordination of accountability bodies: to increase cohesiveness, effectiveness of the accountability sector, help to build an ‘accountability continuum’ that extends from the local to national levels and links demand and supply side accountability.

Why is UK support required?
South Sudan’s failure to fulfil its core state functions (e.g. to efficiently mobilize, allocate and use public finances) and strengthen accountability arrangements over time, have led to high corruption, weak state legitimacy and persisting high and low level conflict. Misuse of public resources, corruption and limited accountability[1] are highlighted as some of the key drivers of conflict in South Sudan; with the most recent out-break in December 2013. Historically, donor support for institution-building in South Sudan has been skewed towards supply side institutions, along with a technocratic (rather than political) approach to PFM reform which has often not clearly linked national, state and county level spheres.
[1] Drivers of conflict in South Sudan, DFID, 2014

Following the conflict which started in December 2013, donor partners re-configured their portfolios to respond to immediate (and worsening) humanitarian needs. Others (e.g. US, Germany, EU, Canada, and Norway) also scaled down their support to the governance and accountability sector along with re-thinking their approach to PFM reform.[2] However, there is common consensus that strengthening PFM (through a more politically astute lens) will be a critical state-building measure, especially over the transition period post the Addis peace process.[3] But also, that these important PFM improvements (including control of corruption) can only occur if undertaken in tandem with the strengthening of oversight and accountability institutions and supporting citizen voice and empowerment to promote demand-side accountability. There is a window of opportunity for the UK to demonstrate the strength of its leadership on accountability and anti-corruption. Accountability institutions will play an important role (during and post the transition) to deepen the relationship between the state, society and represent the interests of citizens, particularly the poorest, most vulnerable and excluded people. These institutions will facilitate support for the new political settlement during and post the transition period by helping to ensure fairer and wider distribution of public goods and reducing opportunities to accumulate power through corruption.
[2] USAID has commissioned a study to assess critical PFM functions across select institutions, in September 2014.
[3] In fragile countries, public financial management (PFM) serves as a critical confidence-building measure and an important signal of governments’ willingness to re-orient often scarce resources toward fighting poverty, addressing grievances/disparities in service delivery and achieving greater resilience.

This programme will be tailored to be fluid and responsive; to adjust to the ever-changing and fast-paced political environment. A carefully designed inception phase will carve out detailed activities from the following thematic areas for the greatest impact, sustainability and sensitiveness to conflict drivers in South Sudan:
Public Financial Management
- Support senior management within the Ministry of Finance and Economic Development (MoFED) to implement a number of strategic PFM reforms that are politically feasible.
- Ensure that transfers for critical services (e.g. health, education, humanitarian and livelihoods) are efficiently utilized through sound planning, budgeting, financing, management and accounting processes at the local level.
- Strengthening of state and county level institutions in public financial management and accountability.

Institution building
- Support to accountability bodies such as Parliament, the Audit Chamber and other institutions that show potential for tackling corruption and leveraging influence over the executive and other state institutions.
- Strengthen structures and mechanisms (especially at local and community level), that support grievance redress/civic dialogue around core government services (e.g. health and education) and improve accountability.

Civil society/empowerment
- Empower civil society to: engage in transition processes, oversee PFM reforms and support citizens in holding government accountable to delivering on key priorities (e.g. humanitarian assistance, health; education and justice).
- Enhance capacity of public policy institutes/think tanks/academia to provide evidence to civil society, accountability bodies and government on key thematic strands such as PFM and service delivery.

Strengthen the accountability continuum
- Facilitate interface and linkages between accountability institutions and government (Parliament/Audit Chamber/Civil Society organizations/Ministries of Finance and Economic Development, Health and Education).
- Strengthen the Accountability Sector Working Group (ASWG) to pursue cleverer ways of joint working e.g. pooling resources for analysis, programming, policy influencing and advisory inputs.

What are the expected results?
This programme will: strengthen MoFED senior leadership to spear-head PFM reforms; enhance state, county and local level planning, budgeting and financial management for improved service delivery; support the development of key accountability institutions, notably Parliament and the Audit Chamber and strengthen civil society/other accountability mechanisms to be more empowered and increase the demand for accountability.

The impact and outcome for this programme will be:
- Impact: Improved public financial management and accountability institutions that hold the executive to account and represent the interests of citizens, particularly the poorest, most vulnerable and excluded.
- Outcome: A more accountable executive that is responsive and key institutions that represent popular interests.
Results will be based on the following outputs[4]:
[4] Precise results will be defined over the inception period and specific evaluation points of the programme.
1. Government leadership on select PFM reforms including those to improve local service delivery, enhanced.
2. Improved capacity of state and county institutions in budget planning, execution, oversight and reporting.
3. Accountability Institutions strengthened to increase oversight of executive actions, undertake outreach, support dialogue and assist the transition process.
4. Improved capacity of CSOs and demand-side accountability mechanisms to engage effectively on public financial management, human rights, access to justice, anti-corruption, peace building and conflict resolution and media.
5. A cohesive and effective accountability sector.

Strategic fit
This programme is in line with DFID South Sudan’s Operational Plan, (2011-2015) which underscores the importance of sustained international support to help South Sudan establish stronger foundations for peace and progress. It also aligns with the Country Poverty Reduction Diagnostic (CPRD) and Interim Strategy to March 2015; which commit to: a) strengthening supply-side institutions of the state, including on public financial management and b) building demand-side accountability institutions and tackling corruption and c) empowering women and excluded groups. It seeks to address actions agreed in the DFIDSS anti-corruption and counter-fraud strategy as well as the UK’s zero tolerance to corruption. The programme also complies with the International Development Act (Gender Equality) 2014 and responds specifically to DFID’s Strategic Vision for Girls and Women.

What are the key risks to the success of the programme?
Key risks include: a) the deterioration of security and political situation and the uncertainty of the fiscal situation may continue to divert the attention of MoFED senior leadership from focusing on key PFM reforms; b) accountability institutions will continue to be starved of resources and struggle to gain sufficient traction in a system that encourages patronage; c) accountability institutions such as parliament could become increasingly politicised with tribal splits undermining its credibility if there is a perception that these institutions are captured by specific interest groups; d) GRSS will perceive UK efforts to strengthen civil society as interfering with South Sudanese affairs and a threat to its authority e) serious deterioration of the security environment may not be conducive for implementing partners.

There has been careful consideration of DFIDSS scenarios outlined in the Country Poverty Reduction Diagnostics (CPRD) and Interim Strategy.[5] The programme has been designed within the current ‘hoping for the better’ scenario, where PFM and accountability institutions are potential vehicles for conflict resolution and mediation and would also enable us to gauge evolving political realities on the ground. Under a worsening scenario, ‘decline into conflict’, PFM and accountability institutions will continue to be captured by narrow patronage interests, perverse corruption and unable to function. It would be hard to deploy technical assistance support these institutions. DFIDSS would consider the feasibility of rolling out this programme and support. Under a more positive scenario (window of opportunity), deepening PFM and accountability institutions, especially over the transition period, could facilitate sustained support for a new political settlement to emerge out of the Addis peace processes. DFID will also work closely with its implementing partners and other donors to embed political economy analysis in the delivery of the programme and to pro-actively manage risks throughout implementation.
[5] Please refer to Annex 1 which provides a detailed outline of how this programme will be delivered across the various CPRD/Interim Strategy scenarios.

Strategic Case

As a newly independent state; South Sudan is at a very early stage of state-building and nation building. It also has a high propensity to violent conflict, illustrated historically, and by the politically driven ethnic clashes which started in December 2013 which according to UN estimates, has displaced over 10% of the population. There have been widespread reports of human rights abuses and horrendous sexual and gender based violence committed by both sides. In May 2014 reports by Amnesty International and UNMISS Human Rights Division provided evidence of rape, gang-rape, sexual slavery, forced abortion and abduction during the conflict. The country is at risk of famine: an estimated total of 3.7 million people currently face serious food insecurity with approximately 50,000 children at risk of dying of malnutrition.[6] Poverty remains widespread. Just over half (51%) of the estimated 12 million population live below the national consumption poverty line, most (92%) in rural areas. South Sudan has the highest maternal mortality rate in the world with an estimated 2,054 women dying for every 100,000 births. One in ten children die before completing a year of life (Infant Mortality Rate 102/1,000). Net primary attendance is 40% and the overall literacy rate is 27% - South Sudan also ranks worst in the world for gender disparity in school attendance. These poor human development indicators are likely to worsen in the short term due to the conflict. Women, girls and youth suffer disproportionately.
[6] Maintaining Humanitarian Response in South Sudan, DFID Submission, August 2014

South Sudan is performing very poorly across a plethora of global governance parameters, overtaking Somalia as the most fragile state in the world in the Fragile States Index (2014), compiled by the Fund for Peace. Under the World Bank’s World Wide Governance Indicators, the country has shown a steady decline in key dimensions such as voice and accountability, stability and absence of violence and control of corruption.

The IGAD negotiated peace process in Addis between Government and the Opposition offers South Sudan an important opportunity for peace and restoration, but requires strong and sustained commitment from both parties to the conflict. Despite growing frustration amongst regional and international parties with the lack of progress, this peace process continues to be viewed as the most credible means of ending hostilities through the adherence and implementation of the Cessation of Hostilities Agreement (CoH) and agreeing transitional governance and interim arrangements. Although there has been significant diplomatic pressure, including a UNSC visit to Juba in early August, the latest deadline for the establishment of a transitional government by 10 August has been missed. IGAD regional leaders have since set a further deadline of 45 days to resolve the crisis and endorsed a protocol on the formation of a transitional government. Both Government and Opposition Parties assert that they remain committed to ensuring credible outcomes from the peace talks.

Accountability institutions
South Sudan continues to operate within an accountability deficit, largely spurred by the weak resilience of its institutions. There is further political fragmentation (and fluid political alliances) as the leadership within the SPLM remains deeply divided with the SPLM in opposition using this status quo to build a case[7] to take leadership of the country. The political uncertainty, hard-line opposition tactics, general political disaffection among citizens and high tensions are playing into accountability relationships between clans, regions, institutions and the Government; leaving them extremely vulnerable. Deteriorating societal norms are such that corruption is endemic and forms a core part of a complex political patronage system that siphons state resources to buy off influential power brokers, rather than deliver services to the South Sudanese population. South Sudanese led processes and institutions to resolve these fundamental issues are still nascent. Administrative institutions are weak, while traditional dispute resolution mechanisms between clans have broken down due to the massive inflow of arms and the pressure of ever scarcer resources. Women, youth and minority clans within the South Sudanese society are heavily disempowered from participating in mechanisms and processes that would enable them to demand greater accountability from a range of power-holders.
[7] There is evidence that the SPLM/IO is creating parallel delivery structures in its opposition strong-holds.

Austerity measures across the public service since 2012 and the further tightening on spend to support GRSS’ conflict response has meant that Accountability Institutions have struggled to fulfil their mandates. This has included extensive cuts in expenditures on personal remuneration, overtime, incentive payments, workshops, training and conferences. Capital expenses on items such as furniture and general equipment, vehicles and civil works have been prohibited. For the Anti-Corruption Commission the impact has been severe, with staff losses and closure of state level offices.[8] The National Audit Chamber has not produced annual audit reports since 2008 and has been unable to respond to specific requests to conduct both compliance and forensic audits.[9] The National Bureau of Statistics has been hindered in taking forward important exercises like the National Census due since 2012,[10] critical to broader national processes such as voter registration and elections.
[8] Many SSACC professional staff have either resigned or taken unpaid leave, resulting in fewer staff than before austerity period. These staff have not been replaced because recruitment of staff even for purposes of replacement have been prohibited unless a special permission is granted by the Austerity Committee, which has not done so for SSACC. Even if permission to recruit were granted, it is unlikely that the required calibre of professionals would be attracted to join SSACC under the terms of the austerity period.
[9] The National Audit Chamber could not respond to the Governor of Northern Bahr El Ghazar’s request to conduct urgent compliance and forensic audit due to insufficient funds and qualified staff.
[10] The Bureau continues to conduct small scale surveys and South Sudan failed to feature in the 2013 UN Human Development Report due to unavailability of comprehensive census and household survey data.

All accountability institutions spend a large proportion of their time aggressively (and at times, informally) lobbying the Ministry of Finance and Parliament to access budgetary resources to do their job. But this yields very minimal returns and even where resources are approved within the budget, these are insufficient and are not released on time.[11] The Accountability Sector Working Group (ASWG) has helped to strengthen collaboration between Accountability Institutions, both state and non-state. The ASWG re-convened earlier this year (2014) to discuss the impact of the conflict on accountability institutions and resource constraints of these institutions in preparation for an ASWG Heads dialogue, scheduled for the later part of the year.[12] However, stakeholders have also flagged for the need of the ASWG to not be seen as a mere ‘talking shop’ for these institutions.
[11] This practice runs contrary to most countries, where resources for accountability institutions are ring-fenced and in many instances, these institutions directly negotiate with and account to Parliament, on their resources.
[12] The ASWG is a forum that brings together accountability institutions, civil society and development partners to foster a cohesive, effective and efficient accountability sector

Space to promote demand-side accountability is increasingly restricted. The NGO Bill currently before Parliament for its final reading has caused wide concern in view of its intention to criminalize community organizing.  By mandating registration, the NGO Bill[13] prohibits all unregistered groups from carrying out voluntary activity in South Sudan. These restrictions are likely to contravene the constitutional rights of South Sudanese citizens to freedom of assembly and association. Unlike other comparator countries, religious institutions are also seen as highly corrupt. South Sudan ranked 119th out of 180 countries in the 2014 Reporters without Borders press freedom index, and according to the report, the country ‘has already left a trail of media freedom violations despite being the world’s newest country’.[14]
[13] Civil Society have argued that Government has set out to pass a package on inter-related bills such as the National Security Bill, which if taken together, to be used to stifle voice and accountability, especially in the period leading up to the elections and transition processes.
[14] For example, in October 2014, reporters without borders flagged that authorities were expressing increased intolerance by banning community radio stations across the country through the new media law, which took effect on 9th September but the final version is yet to be published.

Established in 2005, the Parliament of South Sudan is made up of two Houses: the National Legislative Assembly and the Council of States. Parliament’s formal powers are consistent with legislatures in other countries, including approval of ministers and the budget. However, parliament’s effectiveness is hampered by the dominance of a strong patronage culture within the institution which also spans other areas of government and life in South Sudan. Corruption and electoral controversies have marred its legitimacy and executive attempts at influence have sown discord. The absence of effective political parties means that power in parliament is diffused, and is typically more about personal, religious or ethnic affiliation than substantive commitment.

Despite some capacity-building efforts of donors,[15] the institutional functioning of parliament remains weak and MP’s lack core skills to analyze or draft legislation or hold the executive to account. The South Sudan Parliament has limited institutional autonomy and it lacks the capacity to bid for and manage its operating budget, partly due to its extremely weak financial management, procurement and audit systems. While there are parliamentary strategic plans in place, these have largely been seen as ‘donor driven’[16] and do not have full buy-in of key stakeholders at both technical and political levels. Furthermore, donor support to Parliament has been uncoordinated and at times, overlapping. Parliament needs to begin to articulate its own priorities as well as align donor support behind its reform agenda.
[15] These include: The Association of European Parliamentarians with Africa (AWEPA) and the National Democratic Institute (NDI).
[16] The Strategic Plans (2011-2016) was developed through AWEPA support.

The needs of the State Assemblies are even more profound. Members of the State Legislative Assemblies do not have sufficient skills to adequately scrutinize the annual budget law, annual financial accounts and external audit reports to ensure a more pro-poor and gender-sensitive resource allocation.[17] Similarly, no oversight mechanisms for fiscal transfers to counties exist at state level.
[17] UNDP Needs Assessment, 2010

Public Financial Management
A DFID South Sudan Fiduciary Risk Assessment conducted in 2011, rated the specific fiduciary risk (exclusive of corruption risk), as high and with a limited positive trajectory of change. The commitment of the Government of the Republic of South Sudan (GRSS) and its plans for reform were judged as not credible.[18] According to the 2012 Public Financial Management Assessment (PEFA), South Sudan’s Public Financial Management (PFM) systems are very weak, especially at the State and county levels.[19] The credibility of annual budgets is low, due mainly to major weaknesses in the budget execution process. Although the PFM law is now in place, its implementation is ad-hoc and patchy, especially in reporting and accounting, particularly at the local/service delivery levels. Internal control systems that govern PFM are not well established and external audit and oversight is extremely weak.[20]
[18] Fiduciary Risk Assessment for South Sudan, DFID South Sudan, 2011
[19] More than 60 % of indicators in the Public Expenditure and Financial Accountability (PEFA) assessments conducted in four states in 2011 performed poorly.
[20] South Sudan Public Finance Management Assessment, May 2012

PFM at the sub-national level, which is critical for service delivery, is the weakest. While the majority of high-yielding revenues – including from oil exports – are collected at the national level, the Constitution, together with the Local Government (LG) Act (2009), devolves primary service delivery responsibilities to states and counties. State Ministries of Finance are vitally important in three respects: First, they have to accurately establish the level of resources required to avoid unfunded mandates. Second, they must serve as an efficient, effective and accountable conduit for funds flowing from the national, to state and county level. Third, they must optimize local revenue collection in order to reduce dependence on national transfers. State institutions have lacked capacity to follow the PFM cycle that mandates the approval of all budgets and exercise their role of oversight through approval and monitoring of budgets.[21] States spent an average of over 30% of resources outside their approved budget lines in 2012/13 due to indiscipline among state government officials and/ or inability to write proper accounts in a timely manner so that actual expenditure and corresponding ceilings in each sector are known throughout the fiscal year.
[21] While all State Ministries of Finance now develop budgets, only four states had approved budgets by the end of December 2012, six months into the 2012/13 Fiscal Year (FY).

Helping to create a ‘coalition’[22] of senior leaders to champion PFM reforms in South Sudan is likely to take some time to come to fruition. The current political space in South Sudan is scarcely conducive to launching wholesale PFM reform initiatives. First, the government’s current overriding priority is to access sufficient funds to maintain military capability and to buy peace. The uncertainty regarding the duration of the current government and its future composition, also lends itself to a situation in which rent-seekers, both from within and outside of government, will try to maximise their returns in as short a period as possible. These factors combined, limit the authority of the MOFED to impose fiscal discipline or promote fiscal sustainability, while also escalating external resistance to reform. However, there is a number of individual reform opportunities that currently exist, which lie within the capacity and authority of MOFED and State institutions to execute; as are elements of senior leadership within the MOFED and State institutions that are capable and dedicated. The latter is in part due to the institution’s ability to attract some of the best staff available and high donor investment in this area, both politically and programmatically.[23] That said, while these institutions have some solid reform champions, they needs to harness the political capital of their leaders to influence the wider cabinet to alter incentives within these institutions (e.g. political pressure to spend, understanding implications of weak expenditure control, lax procedures for allocating and spending money especially at the local level and tackling corruption); so that they can work transparently and in the interests of the people of South Sudan.
[22] BSI’s emerging political economy analysis on PFM reforms argues for the importance of creating coalitions of champions (rather than merely focusing on individuals); for PFM reform.
[23] Donor investments in PFM have included support to revenue management and administration (US, UK and Norway), budget planning, procurement, expenditure and arrears management, debt management, state and county PFM capacity, capital investment management (UK, US, Norway, World Bank).

Corruption
South Sudan’s performance on control of corruption and government effectiveness is extremely weak along with a large and growing gap with its comparators. South Sudan ranks 174 (out of 177) in the Corruption Perceptions Index 2013, making it the third most corrupt country in the world. Corruption continues to pose serious reputational and development risk for South Sudan. In 2013, the Corruption Perception Index for South Sudan was 14. According to this classification, South Sudan is the fifth most corrupt country in the world. The December 2013 conflict highlighted lack of serious political commitment to tackling corruption. Weak institutions also failed to curb abuse of state resources, which were used to advance narrow patronage interests and ethnic alliances whilst further perpetuating the fragility of the state. Endemic corruption and violence had become the system for managing official relationships and this drove a wedge into deeper fissures that existed prior; coupled with ethnic feud, rising urban crime, citizen disenfranchisement and heavy-handed security forces. According to the Global Corruption Barometer 2013, 23% of the interviewed population said that corruption has increased a lot and 15% said that corruption has increased a little, since 2011. In other words, 38% of the respondents considered that for the two years prior to 2013, the level of corruption has increased. Whilst a large proportion of South Sudanese believe that ordinary people can make a difference in fighting corruption, most are not willing to report any incidents due to fear of reprisals. Unlike other comparator countries, religious institutions are seen as highly corrupt.[24]
[24] Global Corruption Barometer, 2013

Lessons learnt
Donor engagement:
International efforts are often: too slow, volatile, narrow and quick to exit. Donors also tend to focus on “post conflict” windows of opportunity and not enough on a longer term vision of institutional strengthening.
Strategic approach[25]:
[25] Alexandre Marc, Chief Specialist , Centre of Conflict, Security and Development, World Bank (February 2014)
- Need to focus on the underlying drivers of violence. The particular manifestations of violence at any one time are less important than the underlying institutional deficits that permit repeated cycles of violence.
- There is no single decisive “make or break” moment. Countries that move away from fragility and conflict often do so through many transition moments. Just a violence repeats, efforts to build confidence and transform institutions typically follow a repeated spiral. It is important for donors to know how to give the right signals to Government on the necessity of an inclusive political settlement, whilst at the same time remaining engaged on long term institutional building.
- Need to increase the coalition of stakeholders being able to influence South Sudan and work with them. Working with Partners such as regional organisations, willing neighbours, civil society and non-traditional partners is central as aid will only be a small part of the incentive.
Programme
DFID has also generated extensive lessons from its substantial experience on strengthening public financial management and working with accountability bodies in South Sudan:
- The most critical accountability and transparency institutions are those that oversee the collection and expenditure of public finances and these include the Ministry of Finance and Audit Chamber. Capacity in these entities is extremely weak.
- Public financial management, especially at the sector level needs to be used as a tool for peace and reconciliation. But this also means that these reforms are heavily political and require the stewardship of senior leadership within the Ministry of Finance and across cabinet.
- Efforts to address the ‘accountability deficit’ in South Sudan need to combine support to PFM reforms at all levels (national, state and county) and efforts to deepen the culture of accountability in the society. The latter also includes working with institutions that represent the views of citizens such as civil society, parliaments and other representative bodies.
- Political engagement must be embedded in these types of interventions, as this underpins the overall success of these interventions. This should be clearly linked with both upstream and downstream elements of support to both PFM and the accountability sector; using a blend of instruments (programming, policy influencing and diplomacy).
- Investments should be made to build the capability, accountability and responsiveness of these accountability bodies and support should be broadened beyond one body into a coherent package of institutions that holistically contribute to deepening accountability. Linkages should be made with sector level work (e.g. in health, education and humanitarian assistance), along with direct support to accountability bodies and working through the Accountability Sector Working Group (ASWG), to foster accountability sector coordination, ownership and sustainability.

Entry-points
There is evidence of nascent developments across society which point to the demand for PFM and accountability reforms.

Media, voice and empowerment: Despite initial official attempts to curb dialogue, South Sudanese have recently engaged in feisty debates around the usefulness of a federal system as a means to tackle corruption. Religious groups and civil society (who have also lobbied to be included in the Addis peace process), have spoken out on corruption/poor governance along with its impact on fragility and the need to broaden the peace talks to include other fundamental reforms necessary for the country.[26] South Sudan media has been highlighted as extremely resilient[27] and remain keen to operate in difficult environment where there are massive power losses, limited internet access, illiteracy and weak purchasing power.[28]
[26] See Catholic News Service ‘Bishops call for an end to corruption, nepotism to help heal South Sudan’ and ‘South Sudan activists call for civil society role in the peace process’, 2014
[27] Nihal Bol founder of South Sudan’s prominent paper the citizen, has been detained 5 times in recent years and remains committed to strengthening the role of the media in South Sudan.
[28] Reporters without Borders, 2014

Anti-corruption: There is increasing consensus among South Sudanese citizens that corruption was one of the key drivers of the December 2013 conflict and some important parts of the current leadership seem to concur. A special committee headed by the Minister of Cabinet Affairs was formally set up in May 2014 to scrutinize the status (and transparency) of non-oil revenues collected from various revenue-collecting agencies.[29] In June 2014, the South Sudanese Vice President revealed that government investigators found wide-spread corruption and irregularities in the collection of taxes and fees in the country. This included mismanagement of at least 6.5 million South Sudanese pounds in civil aviation revenues. The Minister of Finance has also underscored that the state lacks capacity to tackle individuals that siphon public resources for private use because these individuals are more powerful than the state.
[29] Initial findings of this committee were presented to Ministers, under-secretaries, director generals and financial heads of departments.

Accountability institutions: Parliament recently flexed its muscle by refusing to replace key committee chairs with those believed to have been pushed for by the Executive. The National Assembly is also working through a proposed budget bill (to be modelled on the Uganda experience); to make the rules around the budgeting process more transparent and predictable.[30] It is also gearing up to playing a key role in the transition process e.g. in ratifying the agreements. There is a desire within Parliament to embed institutional processes and systems to help mitigate the anticipated turnover of Members of Parliament (MP’s) through work with its Secretariats/administrative units.[31] The National Audit Chamber is keen to ramp up its capacity to scrutinize public finances over the short to medium term. The Auditor General has highlighted the importance of addressing underlying constraints of the institution (i.e. the weak autonomy, inability to prepare convincing resourcing bids and weak systems to manage and account for the use of these resources).[32] In his 2014/15 budget speech, the Minister of Finance pledged that the Government is putting in place measures to ensure that the funds transferred to states and counties are monitored and spent effectively. Budget funds earmarked for the Accountability Sector also include resources to conduct external audits and investigate corruption allegations.[33]
[30] Key areas in this Bill will include: a) setting out clear criteria for determining the budget ceilings and disbursements to spending agencies; b) curtailing ad hoc expenditures by spending agencies and ensuring that they regularly report to Parliament; c) limit the discretionary movement, across expenditure categories.
[31] Conversations with South Sudan Parliament (National Legislative Assembly and Council of States)
[32] Conversation with the Auditor General, Juba, August 2014.
[33] GRSS 2014/15 Budget Speech, June 2014

Public Financial Management Reforms: Significant in-roads have also been made under PFM reform. Key pieces of legislation e.g. the Public Financial Management and Accountability Act, the Petroleum Revenue Management Act (PRMA) and the 2012 Taxation Amendment Act have been enacted. The Public Procurement Bill is currently before the Assembly, and the National Revenue Authority Bill is expected to be submitted to Cabinet shortly. The budget preparation system has been upgraded and the capacity of the budget department strengthened, aspects of the revenue collection system are in the process of being modernised, and some progress has been made in establishing systems and strengthening state and county level fiscal transfers, expenditure management and reporting. The ministry has also demonstrated willingness to be transparent, with budget documents and reports publicly available and some limited engagement with civil society on the budget. The Auditor General has made considerable progress in dealing with the audit backlog from 2006 and audit reports are publicly available. Notable improvements have been made in state level capacities to develop strategic plans, improve quality of their budgets as well as capacities to manage, report and audit financial resources. Other key donors, including the World Bank and UNDP recognize the importance of consolidating these achievements and have set out to develop comprehensive programmes within this sphere.[34]
[34] World Bank is in the process of developing a $40 million institutional development and capacity building programme. UNDP is also designing the next phase of its Rapid Capacity Placement Initiative (RCPI).

Collaboration and coordination: Donors and the Government of South Sudan endorsed the development Donor Principles in July 2014, which reinforce: a) free and effective participation for all South Sudanese in the country’s democratic institutions and processes, including decision-making in relation to sharing resources, delivering services, development, and peace and nation building and b) transparent, accountable and equitable distribution and use of resources and services to serve the needs of all South Sudanese. These principles also provide a platform for engaging with preparations for the transition arrangements post Addis. This is the opportune time to provide continued support to these areas as they will be critical in defining inclusive relationships between the South Sudanese state and its citizens.[35] Accountability institutions are also increasingly seeing the usefulness of participating in the Accountability Sector Working Group (ASWG).[36] There is also keen interest to use the ASWG to pursue cleverer ways of joint working e.g. pooling resources for analysis, programming, policy influencing and advisory inputs. The PFM donor working group, albeit new, has picked up on its key activities which have included shared analytical work to understand critical PFM functions across government and joined up informal dialogue with the Minister of Finance on PFM priorities over the coming period.[37]
[35] Negotiating a peaceful settlement in South Sudan: Peace and Power, A. Hirblinger, 2014
[36] For example, the August 2014 meeting saw the attendance and high level representation from the Ministry of Finance, Anti-Corruption Commission, Parliament, Human Rights Commission, National Election Commission, National Bureau of Statistics and key civil society organizations.
[37] In October 2014, the PFM donor group arranged for the first informal dialogue between the Minister of Finance and all key PFM donors in South Sudan. Prior meetings were also held to carve out key messages/priority areas for conversation.

Why DFID?
DFID is the lead donor on accountability in South Sudan and founder and co-chair of ASWG. DFID also spear-headed the formation of the PFM donor group and led in setting out its initial vision and objectives. Like DFID, most donors in South Sudan are still re-calibrating their support to institutional building (including PFM reforms and strengthening accountability) following the onset of the conflict in December 2013. However, there is a shared understanding that both the implementation of donor principles and gearing up to assist the transitional period will be critical to building a solid foundation for an inclusive political settlement and lasting peace. DFID has a strong understanding of institutional reform in South Sudan through its work with the executive branch and has also amassed substantial experience and established a credible reputation within and outside Government through programmes such as health, education, security, PFM and work with accountability institutions. DFID’s engagement through this programme will therefore help to galvanize other donors support in line with the Donor Principles towards making a long term investment in strengthening accountability in South Sudan as evidence shows that building legitimate institutions takes time. This has been underpinned by robust analytical work[38] and lessons learned from deepening accountability programmes across DFID and elsewhere.
[38] DFID has commissioned two key pieces of analytical work to understand accountability institutions and corruption in South Sudan. These will feed into the carving out of concrete activities during the inception phase of the programme.

Sustained international support to help South Sudan establish stronger foundations for peace and progress features strongly in DFID South Sudan’s Operational Plan, (2011-2015). The Country Poverty Reduction Diagnostic (CPRD) and Interim Strategy to March 2015 commit to: a) strengthening supply-side institutions of the state, including on public financial management and b) building demand-side accountability institutions and tackling corruption. The CPRD also highlights the need to empower women and excluded groups.

This will be DFID’s most comprehensive effort to strengthen accountability in South Sudan and will be supportive of other core interventions including:
- Humanitarian (Emergency Response to South Sudan Crisis) – The multi-year humanitarian programme seeks to strengthen the accountability of the delivery of humanitarian supplies and services through an increase in support for a range of monitoring tools – including local level due diligence assessments, third party monitoring and beneficiary consultations.
- Health (Pool Fund) – This programme supports citizens and services working together for deepened accountability, increased awareness and access to good health at the local level (specifically through village health committees).
- Education (Girls Education in South Sudan) - This programme strengthens citizen participation and social accountability of education service providers to citizens, with a focus on financial accountability, performance accountability (quality performance of service provision), and material accountability (infrastructure, equipment and supplies).
- Access to Justice Programme- This programme will seek to promote dialogue and actions to improve oversight and accountability on human rights. It will also work with targeted communities to manage and mitigate disputes and low level conflicts without violence.
- Gender-this is a cross cutting area which is mainstreamed across all of DFID South Sudan’s interventions. Given its importance, this programme will explicitly prioritize delivery of the DFID South Sudan gender strategy which will include: a) unpacking barriers to and addressing women’s political and social participation especially within and across accountability institutions; b) embedding gender-sensitive budgeting, monitoring and reporting especially at state and local levels; c) engaging with influential male leaders to champion the importance of gender sensitivity in PFM and accountability sector reforms.
- DFID South Sudan Anti-corruption and counter-fraud strategy-this commits us to tackling corruption and fraud at country level through: a) ensuring strategic leadership on anti-corruption issues, b) building strong institutional foundations to tackle corruption and c) build the demand for accountability. Emphasis is also placed on strengthening the scrutiny of financial management and handling of corruption risks across our programmes, active corruption risk mitigation by delivery partners and integrating corruption risk monitoring more actively into our monitoring and evaluation activities.

It is also in DFID’s interest to strengthen domestic accountability institutions so that they can, over time, provide better oversight of the use of UK tax payers’ and other donor’s money invested in key areas such as humanitarian aid, health, education and justice. This has become more pertinent now and increasingly over the transition period, when our ability to monitor UK and other donor investments through our own systems will be reduced due to: the physical remoteness of donors from operating in South Sudan as a result of continuing security concerns; the complexity of understanding South Sudanese culture and norms; the high degree of societal corruption. We will need to complement on-going efforts to strengthen innovative monitoring arrangements[39] with support to domestic accountability bodies. Failure to deliver improved accountability would compromise DFID’s other investments in service delivery (especially health, justice), humanitarian aid and livelihoods and render these resources susceptible to fraud and corruption.
[39] DFIDSS interim strategy commits to fast track efforts to establish innovative monitoring arrangements that will help to deepen our response to corruption and fraud risks, at the programme level, while taking into account staff limitations due to the security situation.

This Programme is compliant with the International Development Act (Gender Equality) 2014. It will respond specifically to DFID’s Strategic Vision for Girls and Women, in line with this Structural Reform Plan (SRP) priority. It will support both a transformation process where women and girls know more about rights and accountability and are empowered, supported and resourced to advocate effectively on these issues. This ambition will be supported by evidence-based conflict and gender sensitive approaches to ensure sustainable impact and results. Specifically, this intervention will support the development of policies and facilitating actions promoting gender equality, by responding to accountability deficits reducing the voice of both men and women, working with state and non-state partners. The programme will seek to address structural aspects of gender imbalances such as broadening focus beyond targeted beneficiaries to seeking to understand barriers that constrain women’s participation within accountability institutions and how to strengthen the capability of these institutions to be responsive to the needs of women, girls and men. Focus will also be placed on understanding gender practices within public financial management and accountability institutions (e.g. recruitment practices, norms, women in leadership positions and their involvement in decision making) with a view to seeking to strengthen these to achieve the snow-ball effect of influencing longer term change across society.[40]
[40] Emerging evidence from West Bengal also shows that increasing political participation of women in formal institutions such as parliament and local accountability institutions may be an effective entry point for addressing broader governance issues relating to patronage networks and corruption.

GRSS currently has a weak and deteriorating commitment to the Partnership Principles. This has informed the decision to work at some distance from government, but supporting some limited opportunities for engagement which are in line with programme objectives to reach poor and vulnerable populations. This will not involve direct funding to government. The Partnership Principles will be used to inform decisions about which specific opportunities to pursue with government, but will not be used to inform the management or monitoring of the programme as a whole.

## Appraisal Case
Summary of description of programme options

Option	Description	Feasibility
“Do Nothing More”	No resources allocated directly.	Not possible to test feasibility if resources are not allocated.
Channel support through existing programmes (within and outside DFID)	Deepen support to public financial management and accountability through existing DFID sector programmes in health, education, livelihoods and humanitarian assistance. / Use other partners e.g. USAID, UNDP, World Bank and African Development Bank.	Somewhat feasible, but only for some elements (e.g. World Bank and UNDP where planned programmes already under design complement rather than duplicate each other along with opportunities of scale) and less so for others (e.g. USAID and AfDB due to limited scope and expertise as well as uncertainty of current and future programming).
Fund a separate umbrella programme	This would be a package with the following elements: / Continued support to PFM strengthening through the Overseas Development Institute Budget Strengthening Initiative (ODI/BSI) programme. / Support to accountability institutions and ensuring coordination and cohesiveness of the sector along with clear synergies with existing DFID sector programmes. / A detailed scoping during an inception phase to further understand ‘what works” in terms of strengthening accountability for both men and women followed by rigorous interventions through both state and non-state institutions, supported by comprehensive monitoring and programme management.	Highly feasible. A package of coherently linked interventions will help to test the anticipated hypotheses whilst also building on lessons learnt from our previous engagement.
Combine Options 2 and 3	Fund an umbrella programme as under Option 3. / Use World Bank and/or UNDP as complementary funding mechanism for PFM and accountability initiatives.	Highly feasible. A package of inter-linked interventions to strengthen accountability institutions at national, state and county along with increased coordination, coherence and ability to build a coalition of like-minded stakeholders who can influence the trajectory of these reforms in South Sudan.

Option 1 – Do Nothing
Public financial management and accountability institutions will continue to function sub-optimally. They will fail to address the needs of ordinary South Sudanese, fight corruption and would also not be part of the transition arrangements/political system that will be needed to sustain any new political settlement and to prevent South Sudan from slipping back into a cycle of war. Failure to do so would also contradict commitments in the UK National Security Council’s Strategy for South Sudan, DFID’s Operational Plan, Interim Strategy, CPRD and the July 2014 donor partnership principles for South Sudan. There is currently a gap in support to public financial management and accountability institutions. A number of key donors have re-configured/suspended their support to the accountability sector since the December 2013 conflict. EU wound down their parliamentary programme and Germany is re-thinking its approach to governance reforms, having re-directed resources to humanitarian aid and livelihoods. Other donors (US, Netherlands, Denmark and Belgium), have continued with some support to civil society. Norway’s support to the Audit Chamber has been temporarily suspended due to travel and security constraints.

Donors also recognize the importance of consolidating fragile gains made in PFM across the national, state and county levels and that failure to do this, will have a direct impact on the government’s ability to deliver services and public investments which will in turn, continue to fuel conflict and ethnic tensions. South Sudan will need external assistance to strengthen its PFM and accountability institutions. Gains consolidated through previous support to the ASWG and the recently convened donor PFM group (which have created an important entry point for HMG’s political engagement with key PFM and accountability stakeholders, minimized duplication, coordinated the PFM, accountability and anti-corruption response and held the potential of leveraging both the supply and demand elements in a coherent and cohesive manner); would be lost if not consolidated.

Option 2 – Channel DFID support through new and existing programmes of other partners
This would entail a combination of the following options: a) deepening focus on accountability and where possible, PFM reform, within existing DFID programmes in health, education, livelihoods and humanitarian assistance; b) channelling resources through on-going programmes (e.g. USAID SUCCESS and CORE II as well as the African Development Bank programme on institutional to Public Finance Management and Aid Coordination programmes-PFAID) and c) support to the World Bank and UNDP programmes currently under design.

Channelling through existing DFID programmes would entail identifying gaps within the current sector efforts to strengthen accountability and provide support to address these. This could also include a limited range of discrete but highly durable stand-alone interventions not directly supported by the existing pillars. However, this goes against the current evidence that single sector interventions can help to transform accountability relationships in a complex environment such as South Sudan if not twinned up by broader ranging support. This is also contrary to the recommendations of the comprehensive November 2013 Annual Review[41] on DFID support to accountability bodies which recommends that DFID should deepen its engagement on accountability both within the sectors and to a coherent package of accountability institutions.
[41] DFID Annual Review Report; Document Ref. 4269561.

The USAID SUCCESS programme was designed to cover support to accountability bodies such as parliament, the constitutional review process and national election commission. However, these components were suspended following the December 2013 conflict; with some limited focus on civic engagement. It is not clear when these areas will be resumed.[42] Under its PFM work through CORE II, which is largely focused on expenditure management, USAID is undertaking a stock-taking exercise to assess the critical functions of the core PFM institutions to inform its decisions of future support and it is uncertain as to when the final outcomes will be adopted into their internal decision making processes.[43] Furthermore, DFID’s current support to PFM through the Overseas Development Institute Budget Strengthening Initiative (ODI/BSI) complements rather than duplicates, the USAID CORE II support. DFID would also find it hard to justify extremely high overhead costs (running at approximately 23-27% for each of the two USAID programme components). DFID would have less control over programming and these programmes would be vulnerable to changes in positions/US financial expenditure decisions. The African Development Bank has only begun to re-establish its presence in South Sudan and continues to have limited capacity within the PFM sphere.
[42] Meeting with USAID Governance Team in Juba, August 2014
[43] DFID South Sudan has extensively engaged with this assessment, through the group on economic governance. Its findings (which will be available during the inception period), will also help to shape DFID’s planned support to PFM reform.

The World Bank is in the process of finalizing its technical assistance loan of $40 million over five years; to provide institutional strengthening support to results-oriented leadership, human resource management and selected aspects of public financial management and accountability in selected central agencies and sector ministries. The programme will comprise of three elements: a) results oriented management and leadership; b) strengthening institutions for human resource management and development and c) strengthening selected aspects of public financial management and accountability in selected central agencies (including select parliamentary committees in public accounts, budget, the National Audit Chamber) and sector ministries. Particular attention has been made to complement existing efforts, in particular those by USAID/CORE II, DFID/BSI and other IDF and SPF grants currently provided by the Bank. DFID has been actively involved in the design of this programme.[44]
[44] DFID has been involved in appraisal mission consultations as well as follow up individual conversations with the Task Team.

UNDP is in the process of designing a follow up successor programme to Rapid Capacity Placement Initiative (RCPI) which will seek to: a) improve the capacities of the state institutions in annual budget planning, execution and reporting; b) enhance capability and oversight of public financial management by state legislative assemblies, county transfer monitoring committees and the public and c) ensure more efficient and effective pro-poor and gender-sensitive multi-year resource allocation by Ministries of Finance in at least seven states in South Sudan. Both the World Bank and DFID recognize the strategic importance of the UNDP programme in filing in the current gap of support to state and county level public financial management and accountability institutions.[45]
[45] Meetings between DFID and the World Bank in October 2014, Juba

Option 3 – Fund an umbrella programme of support to accountability institutions
This option would provide a mix of technical assistance (both long-term embedded and short term), facilitation, training, equipment and limited externally-managed operational funding to improve the implementation of critical functions across the public financial management and accountability chain.

The Public Financial Management strand would be implemented by ODI/BSI. This would mean continuation of support to the ODI/BSI programme, beyond March 2015. This would enable us to deepen our existing knowledge, consolidate excellent relationships within and outside the Ministry of Finance as well as enhance the on-going work to strengthen government-led delivery of local services.[46] Providing additional funding to extend the scope of the existing BSI programme would ensure continuity to reforms that seek to deepen and strengthen political leadership for reform and government’s ability to deliver local services. Key successes under the BSI programme to date have included supporting the Minister of Finance to take a strong lead in budget preparation and coordination of the 2014/15 budget process.[47] The unique positioning of BSI advisers within the Ministry of Finance will support the Minister and his senior team to manage the political aspects of PFM reform and build coalitions within cabinet to implement a number of these core priorities. Key areas identified include: establishment and use of the Arrears Fund and an Emergency Contingency Fund; use of these funds to cater for expenditures which would otherwise undermine the execution of spending agencies’ appropriations and to provide for their allocation in a rules-based manner.[48] Continuity of this support and guaranteed early investment, especially over the transition period, will be critical. The BSI approach is unique. No other implementing partner has thought through a package of assistance of this nature thus far. BSI will continue to place great emphasis on donor coordination, especially with the World Bank, UNDP, AfDB and USAID and other programmes, especially within the donor group on economic governance.[49]
[46] For example, in both Education and Health and through ODI/BSI support, the Government itself has made significant contributions e.g. in increasing both Health Worker salaries and the contribution to the Girls Education programme.
[47] Following the withdrawal of ODI/BSI technical assistance in December 2013, the Budget Department was able to submit a supplementary budget for approval by the National Legislative Assembly without direct support. BSI also helped the Government to restructure and simplify the 2014/15 budget and highlight the need for collective political ownership of the budget.
[48] ODI/BSI: Briefing Note on South Sudan PFM Reforms, 2014.
[49] World Bank (supported by the ODI/BSI team), have prepared a mapping of key donors supporting PFM initiatives. A similar exercise is to be undertaken for the accountability sector.

Support to accountability institutions will be provided through another component and delivered by an implementing partner, who will bring global experience/expertise as well as lessons learnt from similar programmes implemented in the past and elsewhere. Key elements will include support to a ‘package’ of oversight institutions (e.g. parliament and the audit chamber), including on areas where these institutions have been hardest hit by the ongoing austerity measures.[50] While there appears to be many NGOs and groups representing “civil society”, the extent to which they are deemed as legitimate is unclear and they continue to struggle to make a meaningful impact in shaping South Sudanese policy. Furthermore, due to the conflict in South Sudan, there is little evidence of effective past and current accountability processes that can be built on by South Sudanese themselves. The programme will deepen the understanding of accountability relationships in this area through grants to civil society partners and where possible, deployment of high quality technical assistance to these institutions.
[50] The September 2014 PCR on DFID support to accountability bodies underscored the importance of supporting AI’s in areas that they have been most affected by with austerity measures, for example: developing basic policy and operational documents, strategies and manuals, organizational development; provision of basic operational equipment and relevant training.

Coordination across the public financial management and accountability chain: Explicit focus will be made to strengthen the interface and relationships between the government (especially Ministries of Finance, Health and Education), and accountability institutions. Support for joint actions to improve performance at each stage of the accountability chain – standard setting, investigation, answerability and sanction will be pursued.[51] The ASWG and the donor PFM working group will be used as the platform to ensure this coherence and where possible, to develop a pooled funding mechanism which will significantly reduce transaction costs for these institutions and help to align donors behind its priorities, which is an essential part of successful support to accountability bodies, globally.[52] We will use the ASWG and the donor PFM working groups to pursue cleverer ways of joint working e.g. pooling resources for analysis, programming, policy influencing and advisory inputs. This approach will allow us to share the burden of risk with others investing in these complex sectors.
[51] Graham Teskey and Mick Moore: Capability, Accountability and Responsiveness, 2006.
[52] Work in this area is already underway, within the Accountability Sector Working Group (ASWG).

Option 4 – Combine Options 2 and 3
This option would entail the following: a) funding Option 3 and b) support to reputable multi-laterals working on public financial management and accountability such as the World Bank and UNDP. Both institutions score very highly under the DFID Multilateral Aid Review (MAR).[53] This will help to deepen linkages across the various components, increase the scope of potential impact of these interventions while building credible coalitions for reform across national, state and county levels as well as share the burden of risks.
[53] Both UNDP and World Bank score highly under the Multilateral Aid Review (MAR). The World Bank (IDA) was rated as very good value for money for UKAid as it was: a) taking reform seriously; b) reasonable progress made against gender, fragile states and contribution to results reform priorities and c) some progress had been made with respect to partnership behaviour. UNDP was rated as good value for money as it was: a) delivering on MDG’s; b) had strong partnerships and ability to include beneficiary voice and c) committed to IATI along with good member states accountability.

The World Bank support complements the DFID umbrella programme as follows: a) the establishment of a staff training institute for formal training of all GRSS leadership will help to leverage BSI’s on-job mentoring and strategic advice to MOFED senior leadership;[54] b) roll-out and use of the human resource and payroll management will build on BSI’s previous work that set out to develop these critical manuals and systems c) World Bank’s planned support to the audit chamber will focus on ‘front office’ support (e.g. core audits of national, states and counties) while DFID will focus on ‘back-office’ support (e.g. supporting the NAO to drive its own reform agenda, secure a sustainable staffing structure and control its own resources) and d) DFID will undertake institutional strengthening of both the National Legislative Assembly and Council of States, while the World Bank will focus on support to the public accounts and budget committees as well as in setting up a parliamentary budget office. Most of the activities to be supported by the World Bank programme will either be provided through procurement of consultants or training. Through its TA, ODI/BSI will support MoFED to draft relevant ToR, enhance participation in the procurement process and to quality assurance of the consultancy products. This will be a critical approach to helping GRSS gain better returns from loan financing. The World Bank is keen to provide co-finance with other donors on this planned project and has specifically highlighted monitoring and supervision and enhancing coordination as some of the key areas that will face potential financing gaps.[55] Initial discussions with the World Bank have highlighted the following potential areas for collaboration: a) establishment of of a joint PFM coordination/secretariat post that will lead in coordination of all the key donors (especially USAID, WB, AfDB, DFID, EU and UNDP) and to help bring together the different strands of support to PFM strengthening at national/state and county levels. There are also plans to align this post with that of ASWG coordination; b) co-financing M&E and reporting arrangements-including developing a joined up results framework, undertaking joint annual and mid-term reviews and pooling together resources for analytical work.
[54] Evidence shows that a twinned approach to on-job training, mentoring and formal trainings yields the maximum returns to capacity building.
[55] The World Bank also anticipates that GRSS will push for a broader coverage of the programme beyond the targeted institutions on the basis of equity. While this would be feasible, it would imply additional resources.

1. UNDP’s planned support to development planning and public financial management project seeks to plug in the current gaps of PFM strengthening and accountability at state and county levels, which is currently not met by any other donor, including DFID.[56] The project builds on and seeks to consolidate gains from the Rapid Capacity Placement Initiative (RCPI) which was designed based on similar initiatives in post-conflict countries across sub-Saharan African countries where civil servants and United Nations Volunteers (UNVs) provided urgently needed technical assistance (TA).[57] The programme had registered the following successes: a) it improved skills of government officials in PFM, even for those with low education attainment; b) by December 2012, approximately 90% of state strategic plans were produced for the first time and ratified by state assemblies; c) notable improvements in the quality of state budgets, timeliness and completeness of expenditure reports and d) considerable increases in revenue collection and administration (before the centralization of tax administration); e) State Ministries of Finance registered improved budget execution through strengthened implementation of financial management procedures as well as improved application of the Integrated Financial Management Information System (IFMIS). The State Transfers Monitoring Committee (STMC) also reported reduced misuse of funds through enhanced internal controls in the management of public funds in a number of states, namely Lakes, Warrap and Northern Bahr el Ghazal (NBeG).[58]
  [56] RCPI was initially complemented by USAID CORE II but with short term advisory visits to the states. This is now currently under review.
  [57] A UNDP commissioned independent review of the programme in 2012 stated that the initiative was endorsed by GRSS across the board. This was largely due to the capacity building model deployed. RCPI UNVs were deployed as resident TA, located on government premises, subject to the conditions and constraints within which government operates, at hand to address technical problems and emerging policy issues, influencing public sector reform in large and small ways through formalized capacity building and day to day conduct”.
  [58] The percentage of total state expenditure spent according to budget averaged 66% for the three states of Northern Bahr el Ghazal, Warrap and Eastern Equatoria. In addition, the State Transfers Monitoring Committee (STMC) of MoFEP reported that there was more accurate and timely financial reporting within and between government levels. The STMC also reported reduced misuse of funds through enhanced internal controls in the management of public funds in a number of states, namely Lakes, Warrap and NBeG.
2. The UNDP support further complements the planned DFID umbrella programme in that it will provide solid entry points to strengthening informal state/county level accountability institutions which are complex, and enhance our limited understanding on how to support these. This programme also has an explicit component on strengthening gender sensitive budgeting, expenditure, reporting and monitoring within state and county institutions. Evidence from other fragile contexts also shows that strengthening women’s participation within state and county institutions is more feasible and sustainable. Furthermore, these local institutions also form the locus of power for important political elites who will need to acquiesce to a new political settlement, especially over the transition period.[59]
  [59] Evidence from Afghanistan shows that women leaders, in local institutions, when well-equipped with the necessary skills to do their job, can play a more important role than many female MP’s in ensuring that women’s concerns are adequately addressed on the ground’. Another AREU study also showed that women in areas with female representatives felt elections had benefitted their interests as their representatives had successfully secured girls schools for their communities along with better road access.

Combining these two options will maximise the leveraging effect of support to public financial management and accountability institutions. It will ensure that DFID takes full advantage of both scale and impact of interventions in this field whilst also sharing the burden of reputational and delivery risks associated with investing in such a complex area. Furthermore, both programmes also highlight the importance of helping the government to solidify its institutions and expand on the gains against the background of renewed conflict, uncertainty and insecurity which has a knock-on effect on increased pressure on South Sudanese leadership to demonstrate a focus on service delivery whilst on the other hand also creating high pressures to satisfy various particularistic and patronage-based demands.

Strength of the evidence base for each feasible option including delivery routes
In the table below the quality of evidence for each option is rated as either Very Strong, Strong, Medium, Limited (or No Evidence):
Option	Evidence rating
1	Limited: there is no evidence that accountability institutions will be able to weather the transition period and influence more transparent use of revenues, without committing more resources than what is currently the case for governance and accountability in South Sudan.
2	Medium Evidence to support the assertion that channelling of resources through specific programmes currently under design (specifically World Bank and UNDP), would provide complementary technical support to ensure successful delivery of these objectives is strong. However, evidence that sole investments in sector interventions not complemented by upstream and influencing efforts, can influence policy and be replicated at scale and other programmes (e.g. AfDB and USAID) would achieve the stated objectives, is limited.
3	Medium evidence that by providing good quality technical support to key PFM institutions along with strengthening a package of oversight institutions and other key demand-side accountability bodies will help to strengthen public financial management and accountability institutions so that they can hold the executive to account and represent interests of ordinary South Sudanese, including women.
4	Medium evidence base to support the theory of change that by providing a package of support that includes: a) oversight institutions and other key demand-side accountability bodies; b) PFM and c) working through other like-minded partners such as the World Bank and UNDP to support inclusive enough coalitions and efforts that link national, state and county levels will enhance both the impact and scale of efforts as well as to strengthen these institutions in the short, medium and long term. / (See the relevant section below which provides more detailed information about the evidence and assumptions underpinning the Theory of Change.)

Theory of Change for Preferred Option 4
The Theory of Change (ToC), (to be routinely reviewed against DFID South Sudan Scenarios) is explained below.

The Problem:
South Sudan is locked in a cycle of violent conflict due to a combination of internal and external stresses and weak and illegitimate institutions. Legitimate national institutions are the key to reducing and managing the risk of violence, but local (formal and informal/traditional) institutions are often the ones that count most for the majority of citizens. Building the state requires much more than building institutions; it also requires mutual accountability between the state and citizens. One of the key underlying problems is that accountability institutions are unable to function effectively due to weak leadership, operational challenges and constraints. There is also an absence of safe spaces for ordinary people to hold government to account through formal and informal institutions. Without strengthening these institutions (and space for ordinary citizens’ participation), South Sudan will continue to operate with an accountability deficit: executive power will be unchecked; public resources will be siphoned for private use, patronage, personal, ethnic and religious interests will continue to dominate these institutions for narrow factional purposes rather than for national political consolidation and development. It is important to start restoring confidence before embarking on wider institutional transformation. A major challenge for any transitional arrangements will be supporting “inclusive enough coalitions.” At a broad level, this requires building national support for change and bringing in relevant stakeholders and at a local level, by promoting outreach to community leaders to identify priorities and delivery programmes. These may be built around patronage, redistribution to specific groups, but need to generate some sense of fairness among groups. Persuading various groups to work collaboratively requires strong signals of a real break with the past and signs of commitment to govern more equitably.

Inclusive enough coalitions have to be complemented by tangible early results to restore confidence in national institutions. This will require:
- Concrete indicators of government’s good intentions towards citizens, through its response to popular expectation;
- Results that demonstrate the government’s ability to deliver on its promises, which will require setting realistic priorities; drawing on NGO capacity to deliver and communicating results to the population;
- Indication that leaders are able to withstand pressure from their own supporters to play a “winner takes all” game and that they instead provide benefits to all citizens.[60]
  [60] World Development Report 2011: Conflict, Security and Development

Analytical explanation of the Logic Underpinning the ToC:
The Theory of Change argues that by providing:
- Senior leadership within the Ministry of Finance at both national and state levels with the capacity and capability to set out their vision and identify core PFM reform priorities and implement these;
- Capacity building of state and institutions in engendered planning, budgeting, financial management and oversight for local service delivery;
- Technical support to oversight institutions (such as parliament, audit chamber) at national, state and county levels to undertake their core activities;
- Capacity building of civil society and other demand-side accountability mechanisms to oversee and analyse South Sudan administrations, better represent their constituencies (both men and women) and increase accountability relationships between South Sudanese;
- Support to nurture coherence among and between PFM institutions and accountability bodies through the accountability sector working group; strengthening interface between supply and demand side institutions;

This will lead to the following outputs:
- Government leadership on select PFM reforms including those to improve local service delivery, enhanced.
- Capacity of state and county institutions in engendered planning, budgeting, financial management and oversight for local service delivery enhanced;
- Accountability Institutions at national, state and county level strengthened to increase oversight of executive actions, undertake outreach, support dialogue and the transition process.
- Feasible programmes on voice and accountability in South Sudan initiated and rolled out to ensure effective coverage and impact.
- A cohesive, coherent and effective public financial management and accountability sector backed by a coalition of key stakeholders.

Taken together, these outputs will lead to improved public financial management and accountability institutions that hold the executive to account and represent the interests of citizens, particularly the poorest, most vulnerable and excluded. This in turn should contribute to a more accountable executive that is responsive and key institutions that represent.

Assumptions
There are several key assumptions made in this theory of change at different levels:
Activity to Output: Implementing partners are able to recruit and redeploy adequate and high quality staff to implement programme activities in a timely manner.

Output to Outcome: Leadership in Ministries of Finance across national, state and county levels, champions PFM reforms and implements agreed areas of reform. Accountability institutions are accorded the space to pursue required reforms and demonstrate willingness to do so. Government (especially the Executive, at national, state and county levels) is open to demands for accountability.

Outcome to Impact: Formal accountability institutions and processes begin to serve wider South Sudanese interests (and are seen as credible/legitimate) albeit being captured by interest groups. There is also an assumption that the Executive will not subvert efforts to strengthen accountability institutions and women/other marginalized groups will continue to be given opportunities and space within the public/political sphere.

Evidence
Rigorous research and evaluation of accountability programmes generally and those that focus on fragile states specifically, is limited. However, there is an emerging body of evidence in this area, over time, which includes the following:
- DFID’s Building Peaceful States and Societies practice paper says that an effective state is one that also builds accountability- to enable citizens, civil society and the private sector to scrutinize public resources and governments that hold them to account. These institutions are critical to shaping state/society relationships, especially in negotiating how public resources should be allocated and wider voice and representation. Accountability institutions underpin effective states and help to facilitate a platform for a durable and positive peace. These institutions help to generate legitimacy of the state. Weak (accountability) institutions are an underlying cause of fragility in fragile states. They play an extremely critical role during periods of transition (i.e. windows of opportunity); to help in building inclusive political settlements as exclusive ones can trigger conflict. These institutions can also help to tap into informal arrangements that are really at the centre of defining the underlying political settlement/allocation of power that is otherwise resistant to change.[61]
  [61] DFID, Building Peaceful states and societies: Practice Paper, 2011
- PFM, accountability and anti-corruption initiatives in divided societies such as South Sudan are likely to struggle; where formal and impersonal rules have limited strength. Without broader social change, these institutions can be prone to elite capture and contribute to, rather than solve, the accountability deficit problem.[62] Schouten (2011), argues that mobilizing citizens and engaging them in formal accountability mechanisms may be premature if there are high levels of social fragmentation, low levels of trust and weak capacity/legitimacy; as these efforts could be viewed as a challenge to the state. However, there is also evidence that identifying civil society and other accountability institutions that are able to coordinate the demands of the population (especially at the local level), will have a significant effect on improving accountability. But these institutions must be able to endure resistance by elites and withstand attempts to be subverted by narrow interests of the elites themselves.[63] Hence this support must be complemented with efforts to generate an in-depth understanding of citizens’ coping strategies and relationships with the state (McLean-Hilker et al). This will also require a coherent/triangulated approach (von Kaltenborn-Stachau, 2008), where the demand/supply side, national/local elements are strengthened simultaneously (e.g. building voice and also listening capacity within the media, government and civil society). A ‘social contract’ approach – which rather than being confrontational emphasises the role of all parties and their collective responsibility for problem-solving – can be constructive in improving accountability (Fooks, 2013). This approach asserts that working with non-state actors including civil society can be an effective entry point, even in authoritarian settings. Aid agencies should also develop a better understanding of gender inequality as a driver of conflict, and informal power arrangements that support or constrain this change.[64]
  [62] The search for peace: A synthesis report in the peace mapping process, Inter-peace, 2011
  [63] Acemoglu, D and Robinson, J.A, Why Nations Fail; 2012
  [64] DFID, Voice, Empowerment and Accountability Guide, 2014
- Mason 2012 highlights that to meaningfully address corruption issues of both petty and grand corruption must be effectively resolved to reduce corruption. Moreover, given the linkages between petty and grand corruption, it is difficult to expect technical reforms to lead to a reduction in a country’s overall level of corruption where other factors are equally important in driving it (culture, accountability deficit and history for example). (Isaksen, 2005; Kolstad, 2008). Transparency International reports that anti-corruption efforts in post-conflict countries suggest that marked, but modest, progress can be achieved over a decade (Stabalisation Unit, 2012). There is also evidence that combining PFM reforms (which seek to largely address petty corruption) along with other efforts such as strengthening demand side accountability (which have the potential of addressing grand scale corruption), is critical.[65]
  [65] The impact of Public Financial Management Interventions on Corruption, Ben French, 2013
- PFM is inherently a political process which requires political and technocratic leadership as well as domestic demand for reform outside the executive. Successful PFM reforms in fragile states are those that have four elements: a) supply side engagement to drive and prioritize reforms; b) linked between national and local efforts; c) international actors to supply ideas for driving these reforms and d) domestic accountability institutions to demand, facilitate and sustain these reforms.[66]
  [66] World Bank, Challenges of Strengthening PFM reform in Africa, undated
- The task of social service delivery and infrastructure development in South Sudan primarily falls on the sub-national government level, where resources are most limited and public financial management (PFM) capacity is weakest.[67] A recent assessment of local social service systems in South Sudan established a direct link between weak PFM capacity and poor social service delivery; lacking PFM capacity was manifested in weak upward and downward accountability and led to inadequate, unbalanced and unclear modalities for funding decentralised service delivery. In resolving these blockages, State Ministries of Finance have a key role to play. They are the major conduit between national resources and local service delivery, exercise control and oversight over fiscal transfers to the county level, and support county governments in public financial management.[68]
  [67] UNDP design proposal, July 2013
  [68] Service Delivery Frameworks for Health, Water and Education, ODI/MOFEP, 2013
- PFM reforms can contribute to state building but they cannot guarantee progress, especially where strong countervailing factors (such as weak accountability institutions, high levels of corruption) are present. However, this may not be the case in some fragile countries e.g. Afghanistan, where substantial progress on PFM reforms has been made with virtually no progress on government effectiveness or control of corruption on the other hand. The most likely explanation is that countervailing factors—insecurity and a drug-based economy—have been dominant (while PFM reforms and improvements such as being able to pay civil servants and soldiers on time may still have contributed to preventing a slide back into full-fledged conflict).[69]
  [69] World Bank, Public Financial Management in post-conflict countries
- Successful PFM reforms in fragile states were influenced by the ambition of the political leadership to develop the structures and capabilities of a sovereign state and to achieve international recognition. In contexts where political leadership has been less focused on the relationship with the international community, there tends to be more limited reform progress as well as less space for development partners to become involved in PFM reforms.[70]
  [70] ODI, Public financial management reforms in fragile states: the case of Sierra Leone, 2012
- Efforts to improve service delivery and PFM should be joined up better, especially in fragile countries where there is little evidence to support that more PFM reforms have resulted in any greater improvement in service delivery. PFM reforms tend to traditionally target central agencies and functions, while efforts to target improvements throughout the expenditure chain within sectors and across levels of government—which is essential for effective service delivery—are still relatively scarce. Providing vital public services – like health, education, water & sanitation and security and Justice– is likely to enhance state legitimacy, especially in fragile or conflict-affected environments where services are likely to be poor or non-existent. However in practice, there is no straightforward relationship between how well a state performs in delivering services on the one hand, and its degree of legitimacy on the other. A more nuanced and rounded account of the significance of service delivery for state legitimacy; (one that includes the effects of services on citizens' ideas about the state and relations with providers and that engages with the criteria [e.g. of equity] by which citizens judge them) is required.[71]
  [71] Mcloughlin, C. When Does Service Delivery Improve the Legitimacy of a Fragile or Conflict-Affected State? 2014
- Improvements in governance in countries emerging from fragility can take a long time and that the international community must recognize this by tailoring programming to respond to this reality. A survey on field experiments in strengthening institutions in conflict-affected countries highlights the need to adopt a longer term horizon (not less than five years) in investments to reach a level of sustainability of community accountability systems and processes.[72]
  [72] King, E. et al. Fast track institution building in conflict affected countries? Insights from relevant field expectations, 2014

Economic Appraisal
To assess Value for Money (VfM), an analysis of the DFID recommended 3E (economy, efficiency, effectiveness) Rating and Weighting framework has been used. The 3E framework allows for a qualitative judgement of each feasible option of a project against the three VfM criteria. These are:
- Economy, which looks at the quality and cost of project inputs;
- Efficiency, which looks at the productivity of the project; and
- Effectiveness, which looks at how effective each option is at delivering the desired project outcome.

Economy (cost and quality of inputs)
Unit cost of inputs: Options 3 and 4 scored the same and lower than Option 2 (scores of 4 and 4.5 respectively) on the cost of inputs, i.e. it is expected that Option 2 will be more costly.
- The USAID component under Option 2 is expected to carry very high over-head costs (approximately 23-27% for SUCCESS and CORE II respectively).
- Although both UNDP and World Bank will have lower costs (UNDP’s costs are capped at 8% while the World Bank expects to spend approximately 6.9% of its total budget on project management); when added together with USAID’s costs, this brings up the total costs significantly.
- Under Option 3, a competitive procurement process for selecting the implementing agent will ensure that the firm offers reasonable overhead costs with demonstrable value for money and BSI/ODI will continue to charge the same overheads which have been significantly negotiated down under the current programme.
- Although the cumulative total of unit costs for Option 4 will be quite high given the use of multiple partners, this will be significantly off-set by the low over-head costs by ODI/BSI, World Bank and UNDP (at 6.9% and 8% respectively).
Quality of inputs: Option 4 scored the highest on quality of inputs (score of a 5 compared to 4 for Option 3 and 3.5 for Option 2 respectively).
- Under Option 4, DFID will have a significant leverage on the design of all components thus ensuring their quality and all partners (ODI/BSI World Bank, UNDP) have strong credibility in mobilizing and delivering high quality technical assistance along with a track record of a robust understanding the context.
- Under Option 2, the USAID component will need to hire additional staff to deliver on an expanded scope of the CORE II and SUCCESS programmes. There is uncertainty on the potential quality of the additional TA and DFID’s role in influencing USAID’s recruitment decisions.
- UNDP has existing UNV/TA that is of high repute and will be located within government premises as well as subject to similar conditions of their counterparts. World Bank will establish a Project Management Unit (PMU) but it also has a track record of bringing on board credible and high quality staff.
- Under Option 3, DFID will have more leverage in the design of the project components through a carefully designed inception phase.

Efficiency (Productivity)
Productivity: Options 3 and 4 scored the same and higher than Option 2 on productivity (scores of 4 for Options 3 and 4 and 3 for Option 2 respectively).
- Under Option 2, USAID has significantly scaled down its scope and coverage of programmes which has had a knock-on effect on programme deliverables.
- UNDP will deploy a large number of high quality UNVs across all states and within all critical state institutions which also cater for the counties. The World Bank will focus on a targeted number of institutions that are critical to public financial management and accountability.
- Under Option 3, support will be provided to a multiple range and number of PFM and accountability institutions and focus will be on addressing the underlying structural constraints to PFM and accountability.
- Option 4 will include joined-up support to a range of institutions at national, state and county levels. There will also be a careful blend of technical assistance/mentoring, building coalitions, financial support and influencing/dialogue to maximise on results.

Quantity of benefits: Options 3 and 4 scored the same and higher than Option 2 on quantity of benefits (scores of 4 and 3.5 respectively).
- Under Option 2, USAID has deployed limited resources at limited scale and for limited results (i.e. support to budget execution through CORE II and civic education through SUCCESS). Although both elements have the potential to be scaled up, it is uncertain as to when this would happen.
- UNDP support will target all state institutions to improve their capacities for budget planning, execution, reporting, accounting and oversight. World Bank will provide targeted assistance to strengthen national M&E systems, establish a training institution, and improve payroll management and core PFM strengthening.
- Under Option 3, there will be a comprehensive coverage of a ‘package’ of accountability institutions along with support to government leadership on select PFM reforms including those to improve service delivery.
- Under Option 4, the combined approach will seek to pool together multilateral and bilateral support that addresses short, medium and long term needs, whilst building critical domestic and international coalitions for change.

Risk of programme failure: Options 3 and 4 scored the same and higher than Option 2 on productivity (scores of 8 and 7 respectively).
- Under Option 2, the use of contractors under USAID buffers elements of risk but the uncertainty risk of US programming decisions is also significant.
- By operating through GRSS structures, both UNDP and World Bank expose themselves to possible delay and political interference, especially within the short term and over the transition period. In other similar contexts, UNDP has also experienced a very high turn-over of UNV’s.[73] The use of a PMU by the World Bank may also buffer some risks.
  [73] UNDP acknowledge this in their risk matrix for the new programme which also articulates a mitigation strategy to lengthen the duration of the programme to 4-5 years rather than the initial 2 years under the Rapid Capacity Placement Initiative (RCPI). UNV turn-over rates will be closely monitored over the duration of the programme.
- Under Option 3, support will inevitably seek to re-orient the balance of power between the executive and accountability institutions/citizens. Countervailing forces against MOFED leadership may also thwart efforts for reform.
- Under Option 4, Government may view the total package of efforts to strengthen PFM and accountability as seeking to undermine an already fragile status quo. If this programme does not ensue, it is likely that any other donor is unlikely to step in a timely and comprehensive manner. The use of multiple delivery structures (GRSS and parallel mechanisms), allows a degree of spreading and buffering against risks.

Effectiveness
Relevance and Robustness of indicators: All three Options score equally high on their design of indicators (scores of 4).
- USAID, World Bank and UNDP have the capacity to develop SMART indicators. DFID’s previous experience with UNDP, World Bank and ODI/BSI is that all three organizations are keen to develop results frameworks in consultation with partners. However, there is some level of uncertainty on the part of USAID.
- Under Option 3, DFID will also work closely with the implementing agent to influence the design of a credible results framework during the inception period.
- Under Option 4, there will also be opportunities to pool resources for developing joint results frameworks as well as for monitoring and evaluation activities.

Theory of Change: There is limited evidence for Option 2 (specifically on the USAID component) design but with some evidence for the World Bank and UNDP components.
Both Options 3 and 4 score the highest (scores of 4 each). This is because there is medium evidence that by providing a package of support that includes: a) oversight institutions and other key demand-side accountability bodies; b) PFM and c) working through other like-minded partners such as the World Bank and UNDP to support inclusive enough coalitions and efforts that link national, state and county levels will enhance both the impact and scale of efforts as well as to strengthen these institutions in the short, medium and long term.

Leverage, replication and influencing: All three Options scored equally high (scores of 8 respectively), on the basis that: a) all initiatives (including USAID programmes), are focused on niche areas that complement other efforts; b) World Bank and UNDP have specifically expressed a strong appetite to coordinate and share lessons better; c) programmes will deliver support through a range of national structures; c) there is scope for pooling other donors resources into these programmes and d) this programme will feed into the scarce body of evidence on this work in fragile contexts.

Summary of Value for Money Statement
Based on the 3-E Methodology, Option 4 proves to show better value for money. Option 4 scores 41 out of 55. Option 3 scores 37.5 out of 55 and Option 2 scores 36.5 out of 55. A follow up 3E appraisal will be undertaken during the inception stage.
Measures to monitor Value for Money during the intervention
At the annual and project completion reviews the following proposed 3E measures (which will be fine-tuned at the Inception Phase), will be used to monitor Value for Money
Economy measures will include:
- Overhead costs compared to other similar programmes (SUCCESS, CORE II)
- Unit cost of staff employed.
- Unit costs for capacity building materials.
Efficiency measures will be based on the data collected through the internal monitoring functions of the programmes and could include:
- Cost per capita of institutional building programmes for PFM and accountability bodies in similar countries and programmes.
- Unit costs for: strengthening finance, HR and procurement functions of oversight/accountability bodies, Civil Society Organisations (CSOs), etc.
- Cost per CSO grant/ratio of grant spent against administrative/overhead costs
Effectiveness will be measured through impact assessments from an independent evaluation of the programme utilising a third party evaluator. These could include:
- Ratio of increase in AI’s core functional capabilities (e.g. budget and staff positions compared to previous budget and staffing structures);
- Cost per beneficiary (disaggregated by gender, youth, location)
- Cost per policy change (measure will enable us to assess the overall cost-effectiveness of the programme, as we will be able to track the total programme costs against beneficiaries reached, and against the changes in policy resulting from the efforts of key accountability institutions).

Equity will be measured through inclusivity: disaggregation of results by location to include location, ethnicity, age group and gender of beneficiaries.

Commercial Case

Direct procurement through a contracted supplier

The table below sets out the several procurement options that were considered for the preferred option:
Option	Analysis of Applicability for Programme
UN Agencies and other multilaterals	UNODC could be considered for some elements, (UNODC previously managed DFID support to the South Sudan Anti-Corruption Commission-SSACC). However, UNODC is unlikely to fulfil the scope of work required under the preferred option; as it currently has limitations in terms of scope, substance and geography. / UNDP has built a strong reputation in PFM and accountability programmes in South Sudan. Some of its comparative advantages are: (1) capacity development for PFM, human development planning and reporting; (2) its strong legitimacy and credibility with government thus enabling it to support change at highest political levels; (3) its ability to deliver day-to-day support at the sub-national level in a cost-effective manner, where challenging logistics, living and security conditions often limit the ability of other partners to provide permanent assistance; (4) strong frameworks and systems for financial management, procurement and human resources that comply with international standards; as well as (5) its established presence in all State Ministries of Finance; and (6) its ability to draw on wider UN system support. / The World Bank is a global thought leader on PFM and accountability and is aggressively re-establishing its presence in South Sudan while extensively learning lessons from its programming and engagement pre-December 2013. The Team has taken on the active chairing of the PFM donor group and is in the process of developing the South Sudan Institutional and Capacity Building Project. The World Bank’s comparative advantages include: a) strong global and in-country expertise in PFM and accountability; b) strong reputation with key stakeholders across government including key PFM institutions; c) solid networks with civil society organizations and wide stakeholder consultation capabilities; d) robust systems for project management, monitoring and analytical work and e) ability to draw on the wider governance global practice including the Centre on Conflict Security and Development in Nairobi.
Accountable grant with ODI/BSI	ODI/BSI have established a credible track record of technical assistance to the Ministry of Finance. DFID has channelled its support through this programme, which has produced tangible results to date. BSI is keen to extend their programme with DFID support and already have technical presence and capacity to deliver a PFM programme on the ground through their lead advisers, backed by their head-quarters technical and research support teams. However, BSI’s model of TA of deployment will need to be fine-tuned further going forward, given that the advisors presence in-country will be largely determined by the evolving security context.
Supplier Contract	A supplier contract represents an efficient way to bring together the potential partners needed to be able to deliver the programme under the preferred option. This arrangement may also allow for the establishment of partnerships between national and international partners so as to maximise their niche areas and comparative advantage. There has been a significant level of interest in the market already expressed to DFID from a range of suppliers in this area. It is anticipated that the market will respond positively to the programme.
Conclusion	Option 4 would be best delivered through a combination of using multilaterals (UNDP and World Bank), an accountable grant arrangement (ODI/BSI) and a commercially contracted supplier (to be selected through a competitive tendering process).

Direct procurement (Commercial Supplier and ODI/BSI)
Under Option 4, a component of the programme (support to accountability institutions and the ASWG) at inception phase will be delivered by a consortium recruited by competitive tender through the DFID Fragile & Conflict-Affected States (FCAS) framework due to the unique nature of South Sudan and the envisaged scope of work. This would help to widen competition and allow for robust combination of specialist skills for programme delivery. Use of the FCAS framework will be considered for any tenders under the implementation phase, as appropriate.

The team will:
- Set out specific interventions to strengthen accountability in South Sudan and related actions under the inception phase and beyond.
- Produce a detailed, costed proposal for the implementation phase.
- Manage the delivery of the interventions during the implementation phase.

A decision point will be built in following the inception phase to assess quality, efficiency and effectiveness of the proposals. DFID will reserve the right to re-tender the implementation phase if it is not satisfied that the selected consortium can implement the programme or that the budget presented to DFID at the end of the inception phase is significantly in excess of the indicative budget presented in its original proposal.

The PFM component will be delivered through an Accountable Grant to ODI/BSI. BSI is already implementing DFID’s PFM programme and was identified as an implementing partner of choice on the basis of its track record and ability to mobilise quickly. Break points (aligned to the inception phase timelines) will also be factored into the Accountable grant, to allow critical points of assessment/reflection of progress. This would also be in line with BSI’s own internal decision to adopt more realistic time-frames to programming; as annual chunks are too long in such an environment. BSI will develop a detailed stock-take of the successes, achievements and key issues of the programme to date (based on their September 2014 retreat) along with a proposal for the follow up scope of work from March 2015 to March 2020.

Competition and commercial advantage for DFID
DFID will undertake competitive procurement of the inception phase to ensure that the best value for money bid is selected. The Terms of Reference will allow for a single service provider or a consortium to apply in order to attract the full set of competencies needed, which cut across support to oversight institutions, demand side accountability and strengthening of the ASWG. The terms of reference will set out specific outputs and outcomes for the programme interventions, as well as specifying outputs at the end of the inception phase and outputs, outcomes and impact for the implementation phase. DFID’s Procurement and Commercial Department will lead the procurement process.

Market place response
A high level of interest on the tender is envisaged, from reputable international consulting firms, international NGOs already working in this area within South Sudan and other similar contexts. DFID South Sudan has experience working with consortia to date and will seek to build on lessons learnt from previous and existing programmes, whilst also ensuring to monitor these in its monitoring arrangements - especially at the inception phase.

What are the cost elements that affect the overall price?
Some of the key cost drivers are likely to be the technical assistance and security costs. It is likely that interventions related to institution and capacity building will be relatively more expensive. It is thus important to ensure that a reputable organisation that has experience of operating in South Sudan, with the right expertise and knowledge, and can draw from internal methodologies is selected. This will ensure that maximum value is added at a minimum cost. Careful scrutiny and monitoring of key cost drivers will be important; specifically by building on lessons learnt from DFID’s previous support to accountability institutions (e.g. the need to provide sufficient information on comparators and to clearly identify areas of cost savings at the outset).

Procurement process to support contract award
Proposals will be sought from bidders under DFID procurement procedures through use of the existing FCAS Governance, Security and Justice framework agreement (FA), which allows DFID ease of access to a panel of 43 pre-qualified service providers who have already been successful following a restricted OJEU tender process.

The FCAS procurement process is anticipated to begin in December 2014 with an anticipated start date of April/May 2015 for the inception phase. Bids will be assessed by February 2015and will be carried out by an Evaluation Team composed of representatives from DFID South Sudan and Procurement and Commercial Department (PCD). As the contract will be over £1 million, approval to contract is required by the Parliamentary Under-Secretary of State (PUSS) prior to it being issued to the preferred bidder.

ODI/BSI will be tasked to prepare a proposal which will be used as the basis for developing the Accountable Grant agreement. The AG will be signed before March 2015 to allow for a seamless transition of support, along with a follow up inception period.

Management of contract and supplier performance
Contract and supplier performance will be managed throughout the life of the intervention through:
Contract design: based on the Terms of Reference, the contract will specify reporting requirements including the inception phase report, annual work plans, annual and mid-term reviews, project completion report, financial forecasts and bi-annual financial expenditure reports.
Implementation plans: the service provider will be required to develop an implementation plan, agreed with DFID South Sudan, and specifying outputs at regular stages of implementation. Payments will only be made against satisfactory delivery of outputs.
Decision point between inception and implementation phases: During the inception phase, assessment of progress will be made by the Governance and Security Team of DFID South Sudan (management arrangements are discussed in the “Management Case”). At the end of the inception phase, the service provider will provide an Inception report which is expected to include a detailed outline of planned activities for implementation. The Team will then make a recommendation to the Senior Governance Adviser and Head of DFID South Sudan as to whether or not to proceed to the next phase of implementation.
DFID will engage with BSI to monitor spend, results and performance and use our influence to drive improved procurement practices and management. This will be done through partner VFM training sessions, analysis of quarterly reports and our monitoring and evaluation programme. Additionally, we will be able to exert influence over the direction of the programme through BSI’s governance structures. As noted earlier, the inception phase period will be factored into BSI’s Accountable Grant to allow for a stock-take of progress, discussion of findings to emanate from the USAID study on critical PFM functions and decisions to be undertaken over the transition period.

Overall DFID South Sudan will work the Service Providers to:
- Ensure that the service delivered is fit for purpose;
- Ensure that the Service Provider develops a strong approach to developing and understanding the value for money that the programme will deliver;
- Negotiate management charges as part of programme budget negotiations to ensure these charges are set at an appropriate level to deliver programmes in the South Sudan context;
- Agree and monitor a risk strategy, which sets out specific responsibilities of DFID, and any sub-contractors for managing and mitigating risk;
- Ensure that the service provider/the lead firm in the consortium has a corporate social responsibility that reflects international good practice in terms of commitment to diversity, sustainability and anti-corruption

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner?
DFID has opted to use the World Bank and UNDP as implementing partners due to their good track record on delivering similar programmes elsewhere.

The World Bank has vigorously re-established its presence in South Sudan, taken an active role in convening and chairing the PFM donor group and has undertaken a comprehensive consultation process for its planned PFM and accountability programme. We have good experience of working with the World Bank through two critical programmes (support to the high frequency survey/institutional building of the National Bureau of Statistics-HFSS and Building Resilience through Asset Creation and Enhancement-BRACE). DFIDSS and the WB have also stepped up on their wider collaboration by seeking to identify areas of joint working and opportunities to maximize synergies and leverage returns to investments in South Sudan. The World Bank has a team in Juba and is backed by a dedicated team in Nairobi and Washington.

UNDP commissioned an independent review of the Rapid Capacity Placement Initiative (RCPI) programme in June 2012 and has fed the findings and lessons learnt into the design of the new successor programme. There is no comparative alternative partner (with the presence and influence within the state and county institutions) to provide the highly complex support envisaged. DFID has a long-standing working relationship with UNDP on programmes such as Community and Small Arms Control (CSAC) and South Sudan Recovery Fund (SSRF). Wider lessons from these programmes will be embedded in the programme design and these include the need to: a) develop a robust theory of change and results frameworks for the programmes; b) conflict and political economy analysis to underpin future interventions; and c) create strong governance and oversight arrangements of the programmes especially to oversee monitoring and implementation of programmes.[74]
[74] SSRF PCR submission, September 2014 (DFID Document Ref. 4663550); CSAC Annual Review, December 2013 (DFID Document Ref. 4350186).

DFID will undertake Due Diligence Assessments (DDAs) of all programme partners and the findings will be incorporated into routine monitoring arrangements. We will engage with UNDP, the World Bank, the Overseas Development Institute (ODI) and the contracted service provider to monitor spend results and performance and use our influence to drive improved procurement practices and management. Financial procedures for UNDP, World Bank and ODI/BSI will be followed as they have been determined by DFID to be sufficiently robust. This will be done through partner VFM training sessions, analysis of quarterly reports and our monitoring and evaluation programme. Additionally, as the Management Case sets out, we will be able to exert influence over the direction of the programme through the relevant programme oversight structures. DFID agreements with all implementing partners will make reference to these DDAs and the programme management team will continue to measure progress within the respective implementation plans.

The overall effectiveness of the support for UNDP and World Bank (both in terms of realising project goals as well as value for money) will be assessed throughout the inception phase and in close discussion with UNDP and World Bank. At the end of the inception phase, the findings will be discussed with UNDP and the World Bank and a decision taken in close consultation with the relevant South Sudanese stakeholders, about how this programme can best support their needs going forward based on the findings.

B. Value for money through procurement
Utilising UNDP and World Bank in the first year of the programme in this manner (and possibly in outer years depending on the results of the inception phase) presents good value for money since:

- UNDP and World Bank are fully mobilised and operational in South Sudan already which enables a high degree of oversight and contact between UNDP/World Bank staff and the various stakeholders;
- Given the mobilisation costs and security costs associated with private suppliers, UNDP and World Bank management fees of (8% and 6.9% respectively) are not excessive in South Sudan compared to other options. Additionally since both programmes are keen to bring other potential donors on board, such costs will be distributed between a group of donors;
- DFID has worked with UNDP and World Bank on a range of programmes within South Sudan and elsewhere, which has provided the space and opportunity to enhancing their approach and understanding of DFID’s value for money requirements as well as reporting and M&E systems;
- Both UNDP and World Bank score highly under the Multilateral Aid Review (MAR). The World Bank (IDA) was rated as very good value for money for UKAid as it was: a) taking reform seriously; b) reasonable progress made against gender, fragile states and contribution to results reform priorities and c) some progress had been made with respect to partnership behaviour. UNDP was rated as good value for money as it was: a) delivering on MDG’s; b) had strong partnerships and ability to include beneficiary voice and c) committed to IATI along with good member states accountability.
- The Global UN administrative costs for UNDP are negotiated and agreed by DFID centrally. World Bank is extremely stringent on its application of overhead costs where focus is to build government capacity, especially in fragile countries.
- The synergies across all the various components of the programme can also serve to provide a multiplier effect to the wider intervention, thus further increasing the value for money of the programme, if sustained.

## Financial Case

The estimated total cost of the project is £15.00m over five years.
Year	2014/15	2015/16	2016/17	2017/18	2018/19	2019/20	Total
Amount (£)	0.52	3.4	3.33	3.33	3.33	1.09	15.00

Preferred Option Cost Allocations
OPTION 4 (£)	2014/15	2015/16	2016/17	2017/18	2018/19	2019/20	Totals (£)	%
Design	225,000	0	0	0	0	0	225,000.00	1.5
Inception	250,000	800,000	0	0	0	0	1,050,000.00	7
Implementation	0	2,200,000	3,250,000	3,250,000	3,250,000	695,000.00	12,645,000.00	84.3
Due Diligence/ Annual Reviews & Audits	50,000[75]	80,000	80,000	80,000	80,000	80,000.00	450,000.00	3
Independent Evaluations[76]	0	315,000	0	0	0	315,000.00	630,000.00	4.2
Total Costs	525,000	3,395,000	3,330,000	3,330,000	3,330,000	1,090,000.00	15,000,000.00	100
[75] This represents costs for Due Diligence exercises to be carried out on all project partners (UNDP, the World Bank, ODI and the Service Provider to be contracted through a competitive tender)
[76] DFID expects to pool resources with the World Bank to undertake joint Monitoring & Evaluation (M&E) exercises

The costs estimates for Option 4 are indicative and have been done without access to full budget and costings data or consultation with implementation partners. These will be firmed up after the service provider is chosen, ODI/BSI has submitted their financial proposal under the PFM component and agreements are made on total DFID contributions to the UNDP and World Bank programmes. During the inception phase more detailed design work for each intervention will take place that will enable more accurate estimates to be made for the costs of delivering the interventions. The cost estimates assume that equivalent programmes will be provided. Accurate forecasting will be achieved through the planning and reporting required of the service provider. Annual work-plans and financial forecasts will be submitted to DFID South Sudan and will be monitored through quarterly financial and implementation reports which will trigger funding instalments. Forecasts may change around the inception/implementation transition.

Assessment of financial risk and fraud
Fraud and corruption risks: The Accountability Programme will mainly be delivered through service providers/implementing partners with no funds going directly through Government mechanisms in South Sudan. Given that fraud and corruption risk management mechanisms, including beneficiary feedback, will be included in the intervention design and reporting, the risk is still likely to be high. The programme will also be subject to rigorous monitoring requirements as set out in the DFIDSS anti-corruption and counter-fraud strategy which highlights the need to: a) strengthen the scrutiny of financial management and handling of corruption risks across our programmes, b) active corruption risk mitigation by delivery partners and c) integrate corruption risk monitoring more actively into our monitoring and evaluation activities.

Mitigating measures: This programme will be designed in compliance with priorities articulated in the DFID Anti-corruption and counter-fraud strategy and action-plan. Rigorous mechanisms will be implemented: work-planning and financial forecasting, quarterly disbursement, regular reporting which will trigger disbursement, annual review, annual audit, and an assessment of financial management and accounting systems of the service provider. The programme risk matrix will be further developed during the inception phase and will monitored and revised every six months once the project is under implementation and reviewed during annual reviews.

DFID will undertake due diligence of all its implementing partners. Partners will also be expected to undertake fraud and anti-corruption risk assessments with particular attention to any risks around procurement. Ad hoc audits should be carried out by the programme management team.

Monitoring and accounting for expenditure
1. Reporting requirements: the contract for the supplier will specify reporting requirements including financial forecasts and bi-annual financial expenditure reports, audits, annual reviews and a project completion report. The service provider will also have to ensure that beneficiary perceptions (both at the State and non-State levels) inform the design of the programme and are taken into account in the implementation, which will provide additional monitoring of expenditure. Similar provisions will also be made with regards to the Accountable Grant with ODI as well as agreements with UNDP and the World Bank.
2. Audits: Audits will be taken into account for all components. DFIDSS will use the annual published country financial audit statements of the World Bank, UNDP and ODI that they are mandated to share with us. However, annual reviews will also be combined with an audit of the overall programme, to provide an added level of assurance and to fully inform VFM/ and financial management aspects of the programme during implementation.
3. Implementation plans: the service providers/implementing partners will be required to develop implementation plans, agreed with DFID South Sudan, and specifying outputs at regular stages of implementation. The quality, robustness and rigour of the outputs will be reviewed by the DFID South Sudan Programme Team. Implementing partners work and reporting requirements will be managed and overseen through the programme structures to be agreed with all partners.

Management Case
By its very nature, the Accountability Programme will strive to be inclusive in its management approach and will involve a number of partners and structures to provide oversight, co-ordination, quality assurance and peer-review.

Overall programme leadership: The programme will be supervised by the DFIDSS-appointed Senior Responsible Officer (SRO) who will be responsible for its vision, leadership and overall performance and who in turn will be accountable to the Head of Office. Day-to-day oversight will be provided by DFIDSS’s A2 Governance Adviser and Governance and Security Team Programme Manager (B1), Programme Officer (B2) and Programme Assistant (C1). The team will draw in thematic advisers and programme managers, Foreign & Commonwealth Office (FCO) colleagues and other relevant team members as and when required. The team will:
- Be responsible for the development and publication (in partnership with FCPD) of the necessary terms of reference, as well as organising reviews of the proposals. It is estimated the terms of reference will be finalised and published in December 2013, with proposal reviews taking place in March/April 2014;
- Agree the methodology with the service provider for the inception phase as well as being explicit with regards to the success criteria to be reviewed at the end of the inception phase.
- Agree the overall strategy and initial messaging as well as target audience for the programme;
- Provide direct steers to the service provider with regards to key areas to focus on in South Sudan (including geographic areas, programmatic areas and so on). Such decisions will be taken in line with agreed annual work plans and budgets.
- Ensure that all DFID requirements such as reporting and annual reviews are completed on time and to the necessary standards.
- Be responsible for monitoring the delivery of the inception phase commitments set out in this business case. The table below summarises these commitments:

Commitment	Description
Produce Inception Phase Report	Inception Phase Report would consist of detailed scoping including: (i) the existing evidence base, (ii) analysis of past and existing accountability improvement interventions for key “lessons learned”, (iii) engagement of relevant stakeholders including government, Parliament, civil society, clans, research institutions, universities, the international diaspora and implementing agencies (particularly identification of key champions), (iv) delivery and performance of ODI/BSI, World Bank and UNDP components (v) scoping of current data collection and establishing of baselines. It would also include the design of proposed interventions and the preparation of fully costed proposals for the programme interventions.
Communications Plan Developed	Develop a set of criteria as to how to classify and disseminate the information found.
Costs and benefits finalised	Finalise detailed cost breakdown for the programme as well as cost benefit analysis.
Finalise VFM approach	Given the limited evidence and quantification possible at the appraisal stage, the VFM measures to be monitored will be particularly important in order to determine which the cost effective pilots to scale up are. A rigorous approach must be used to ensure a better sense of the value which can be established, ideally at the end of the inception phase, and definitively before a mid-term review. This should cover all aspects of economy, efficiency and effectiveness
Finalise log frame	Draft Log Frame reviewed and populated in close consultation with partners.

ASWG: made up of representatives accountability institutions (including the Ministry of Finance), civil society, donors and leading organisations in South Sudan with an interest in accountability programming and research. This forum will continue to meet quarterly to provide on-going direction to the sector and the programme, agree work-plans and changes and ensure full cooperation, communication and information sharing by all participating institutions and donors. The ASWG might create sub-groups covering the specific results areas/outputs of the overall accountability sector work plans, or other specific functional groups. The contracted service provider will also provide a secretariat function to the ASWG. Additionally, they will perform a support function to all donor support to accountability institutions, helping ensure coordination across the whole chain. In the longer term, other donors could be encouraged to provide funding to be either pooled with DFID or directly to be managed by the service provider, or to delegate cooperation to DFID. DFID would remain the contractor and manager of the service provider.

Donor group on PFM: comprised of all donors engaging on PFM issues and is co-chaired by USAID and the World Bank. This forum is yet to agree on the format and frequency of its meetings but it has thus far been used for strategic discussions on analytical work, consultations on new programming and preparations for strategic dialogue with MOFED leadership. Through the World Bank support, efforts will be made to strengthen the effectiveness of this group through scheduling of regular meetings, identification of agenda items and using these forums to also engage with national stakeholders on PFM issues as well as to enhance linkages with other institutions. UNDP will explore whether this structure is sufficient for the state and county level PFM and accountability work.

ODI/BSI Advisory Board: The BSI programme has an Advisory Board which includes DFID membership from the head-quarter level but this arrangement will need to be reconfigured after central level support winds down. Extensive efforts will also be made to strengthen country level governance arrangements. These will include DFIDSS monthly bilateral meetings with BSI, partnership meetings with the Government and other implementing partners.

Working across HMG: As noted elsewhere, the programme will work across HMG. It will link up, not only with other relevant programmes in the DFID portfolio, but also the political work that the FCO and MOD undertakes to raise the understanding around “accountability” in the broader stabilisation work that is undertaken in South Sudan.

Exit Strategy: The primary exit strategy for the PFM and accountability programme is to have created sufficient capacity over the five years of the project – both through the work the programme itself intends to undertake and other donor programmes it seeks to influence – for public financial management and accountability institutions in South Sudan to have progressed to such a stage that they are able to either (a) raise, allocate and efficiently account for use of public resources; b) draw on resources sustainably from interested supporters within South Sudan and/or (c) be sufficiently developed to engage directly with donors and drive the work started by this project themselves. However, the scale of the challenge itself and evidence from similar programmes elsewhere point to a strong possibility that the programme may need to be extended in both timelines and resources in order to have a sustainable impact.

What are the risks and how will these be managed?
This programme is high risk but with potentially high returns. DFID support will need to be underpinned by a robust risk analysis and mitigation in close alignment with the DFIDSS Scenario Matrix. The risks will be routinely reviewed every 3 to 6 months and more comprehensively at the Annual Review process every year.
Risk	Probability	Impact	Management/Mitigation
Deteriorating political environment (and possible stalemate in Addis) makes it impossible for PFM and accountability institutions to operate.	High	High	Continued support to robust negotiations for the Addis peace process. / Diplomatic engagement and dialogue. / Programme will balance engagement with both political and technical interlocutors.
Security – for security or duty of care reasons, the implementers may be unable to access some parts of South Sudan where we would need them to travel.	Medium	High	Work with the implementers to encourage them to use local partners who are better able to access insecure areas. It is likely that if it is possible for a DFID-funded project to operate, then it will be possible for the implementers to access it.
Government (in particular the executive branch) unwilling to engage with demands for “accountability”	Low	High	Leverage influence through support to supply side interventions including the ODI/BSI PFM component. Additionally, the range of intervention points and the theory of change suggest that an extremely high degree of buy-in by central government at present is not required for the programme to achieve its ends.
UK Government seen to be interfering in South Sudanese affairs.	Low	High	The project will be seeking to tap into inherent South Sudanese demand for increased accountability and both on the “demand” side of civil society but also in the “supply” side of administrations. Success for the project will be in working with both of these areas to increase the responsiveness to accountability issues. Robust political economy analyses (PEA) to identify entry points and critical points of risk.
Fraud – Risk that project funds will be misappropriated or diverted and project beneficiaries will not be reached	Medium	High	Due diligence will be carried out on all implementing partners. Sub-contracting processes will also have to follow rigorous due diligence assessments. Additionally, the project emphasis on accountability and transparency will inculcate a sense of effective reporting of such issues should they happen.
Government able to by-pass “accountability” discussion due to new sources of rent extraction becoming available (natural resources/oil)	Medium	High	Lobbying directly by HMG and political work to promote the benefits of “accountability” to administration officials. Working through civil society and non-governmental organisations will ensure that the debate around this issue remains a key priority within society. Deepen work in extractives sector including PEA.
Theory of change means impact and results are hard to measure within the lifetime of the programme	Medium	Low	The programme is committing a substantial amount for resources to undertake rigorous monitoring and evaluations, which should yield substantial information around results.
Programme ends up too dispersed and therefore fails to have an impact on anything	Low	High	The inception phase, coupled with deepened engagement and strengthening of the ASWG. DFID review ToC on a regular basis and develop a robust log-frame to monitor progress of the programme.

How will progress and results be monitored, measured and evaluated?
Theory of change and log frame: The primary tool for tracking progress is the log frame, guided by the theory of change, which details indicators and milestones at output, outcome and impact levels. The log frame will be fully revised during the inception phase and indicators strengthened and finalised to reflect the actual design.

Monitoring framework: The implementing partners will be required to develop a full monitoring framework and strategy for the Programme Indicators, which will be refined (and possibly amended) during the inception phase to ensure they reflect the analysis, conclusions and optimum design of the programme. Evaluation is addressed within the research design and methodology. The work to be undertaken by BSI will also be monitored through the quarterly reports and Project Board, monthly meetings as well as direct bilateral engagement on key issues.

DFID South Sudan reporting requirements: the implementing partners will be required to provide annual work plans and financial forecasts. They will provide quarterly progress reports which will trigger disbursement. An annual review, following DFID annual review guidelines, will be required and will include analysis relating to VFM as well as progress against the log frame and monitoring strategy.

Evaluations: The break points for the implementing will be informed by the commissioning of an independent evaluation for the programme as a whole. The evaluation will consider inter alia the following questions:
- Is the umbrella approach proving effective in the context of South Sudan?
- Are interventions being rolled out? What are the prospects for their efficiency and effectiveness?
- What is the impact that the programme has had on the overall environment for public financial management and accountability in South Sudan?
- Could the programme be adapted in some manner in order to better achieve its results?
- Is the programme proving to be effective value for money?
- Is the programme still relevant?

In addition to this required evaluation, the programme will be encouraged to determine how to undertake more frequent evaluations of its own interventions to ensure that it continues to be relevant and programming is based on the best available evidence rather than assumptions. DFID will also draw on UNDP, World Bank and BSI’s own research facility which is geared to strengthening the evidence-base for the programme.

Smart Guide
The Business Case

- Sets out the case for a programme, adapted to suit the context
- Explains very clearly what the programme will do within what timeframe and is explicit about the risks and uncertainties and how they will be managed
- Records an understanding for DFID, our partners and intended beneficiaries about what we are planning to do and the results we expect to achieve
- Allows DFID to report to the UK public on what we are doing with taxpayers’ funds

The Business Case is structured around the Treasury 5-case model. Within this broad framework the design should be adapted to suit different contexts and investment types. The content is indicative, not prescriptive and teams are encouraged to use judgement in making a logical argument to make the case in a way that suits the individual investment. There is also a set of questions in the Smart Rules that design teams should consider during the process. This is not a checklist and only the questions relevant to the context should be answered.

Teams should refer to the considerations below as a guide to writing the business case

Intervention Summary (2 Pages)
A succinct and unambiguous description of what the project will do. The summary sets out the problem the programme will address, what it will do and what the money will be spent on. It sets out the expected results in the context of the Operational Plan and DFID’s wider priorities and a summary of risks. The accompanying submission should set out any sensitive information that supports the case (e.g. risk tolerances and escalation measures)
Strategic Case
This section makes the case for DFID intervention by setting out the overarching context and the problem to be addressed. It should be clear what the programme will do and how with evidence. It should link to – but not repeat – the Operational Plan with a clear illustration of how the programme contributes to DFID global and portfolio priorities of poverty reduction.
Appraisal Case
The Appraisal Case explores how we will address the need in the Strategic Case in a way that optimises value for money. It appraises genuinely feasible options for achieving the objectives, including high level commercial choices, with a summary of the quality of evidence. The appraisal considers delivery mechanisms including capability and capacity, costs and benefits, risks and likelihood of success. It concludes with a preferred option.
Commercial Case
This section provides more detail on implementation and how value for money will be achieved. It sets out the procurement approach and requirements, proposed funding instrument and how the choice of instrument will be used to ensure VfM. It considers the market place response to this intervention with an explanation of how supplier performance would be managed. It sets out the procurement policies, capabilities and systems of the third party entity to ensure we get VfM.
Financial Case
This section sets out issues of affordability and the sources of funding. It includes a high level budget which does not impair VfM in procurement exercises for individual contracts. It sets out how funds will be disbursed and how expenditure will be monitored, reported and accounted. It highlights the evidence underpinning a judgement that funds will be used for the intended purposes.
Management Case
This section focuses on governance and management arrangements and the ability to deliver. It sets out the management implications for the business unit/ level of effort with realistic timings for mobilisation and start up. It outlines out the expected roles and responsibilities, including DFID’s own resourcing strategies (SRO, project team etc.). / It sets out how it will respond to changes in context and the key elements of the Delivery Plan, key milestones and decision points where we can course correct. It includes a clear illustration of the risks, tolerances and approach to escalating problems and issues as well as exit and possible closure scenarios.